## Sheet1
4.19.2 | Retaining Wall Concrete | All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam. The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works | PS 18.2.5 PS 18.5.1 | Mix Design | before the commencement of works | HP | ENG | 4.19.2 - Retaining Wall Concrete | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam. The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works | Standard / Specification - PS 18.2.5 PS 18.5.1 | Verifying Document - Mix Design | Frequency - before the commencement of works | Verification Activity: Activity - HP | Verification Activity: By - ENG | 4.19.2 - Retaining Wall Concrete
4.19.3 | Hot-dip Galvanising | Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680. All alterations to fittings shall be hot dip galvanised following fabrication. | PS 18.2.3 PS 18.2.1 PS 18.2.2 | Datasheet | Prior to Works | R | SE | 4.19.3 - Hot-dip Galvanising | Acceptance / Conformance Criteria - Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680. All alterations to fittings shall be hot dip galvanised following fabrication. | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2 | Verifying Document - Datasheet | Frequency - Prior to Works | Verification Activity: Activity - R | Verification Activity: By - SE | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam. The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works
4.19.5 | Welding Procedures | All welds shall be weld category GP in accordance with NZS 3404. All welding procedures shall be in accordance with AS/NZS 1554. The Contractor shall submit full details of the proposed welding procedures and electrodes, with drawings and schedules as required. | PS 18.2.3 PS 18.2.1 PS 18.2.2 | Welding Procedures | Prior to Works | R | SE | 4.19.5 - Welding Procedures | Acceptance / Conformance Criteria - All welds shall be weld category GP in accordance with NZS 3404. All welding procedures shall be in accordance with AS/NZS 1554. The Contractor shall submit full details of the proposed welding procedures and electrodes, with drawings and schedules as required. | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2 | Verifying Document - Welding Procedures | Frequency - Prior to Works | Verification Activity: Activity - R | Verification Activity: By - SE | Standard / Specification - PS 18.2.5 PS 18.5.1
4.19.6 | Welders Qualifications | Only welders qualified to AS/NZS 1554, or equivalent standard shall be employed on the works. Proof of welder’s proficiency and qualification shall be made available to the Engineer on request. | PS 18.2.3 PS 18.2.1 PS 18.2.2 | Qualification | Prior to Works | R | SE | 4.19.6 - Welders Qualifications | Acceptance / Conformance Criteria - Only welders qualified to AS/NZS 1554, or equivalent standard shall be employed on the works. Proof of welder’s proficiency and qualification shall be made available to the Engineer on request. | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2 | Verifying Document - Qualification | Frequency - Prior to Works | Verification Activity: Activity - R | Verification Activity: By - SE | Verifying Document - Mix Design
4.19.7 | Steel Piles | Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680. Only new steel pile section to be used. All piles and production certificates shall be made available for inspection by the Engineer at any time. | PS 18.2.4 PS 18.2.1 PS 18.2.2 | Mill Certs | Prior to Works | R | SE | 4.19.7 - Steel Piles | Acceptance / Conformance Criteria - Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680. Only new steel pile section to be used. All piles and production certificates shall be made available for inspection by the Engineer at any time. | Standard / Specification - PS 18.2.4 PS 18.2.1 PS 18.2.2 | Verifying Document - Mill Certs | Frequency - Prior to Works | Verification Activity: Activity - R | Verification Activity: By - SE | Frequency - before the commencement of works
4.19.8 | Steel Reinforcement Compliance | Conformin Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied. | AS/NZS4671 CHAR(AMP) NZS3109 | Detail Sheets and Mill Certificates | Prior to ordering steel | W | SE | 4.19.8 - Steel Reinforcement Compliance | Acceptance / Conformance Criteria - Conformin Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied. | Standard / Specification - AS/NZS4671 CHAR(AMP) NZS3109 | Verifying Document - Detail Sheets and Mill Certificates | Frequency - Prior to ordering steel | Verification Activity: Activity - W | Verification Activity: By - SE | Verification Activity: Activity - HP
4.19.9 | Reinforcing Welding Qualifications | Welders and Procedures are to be qualified to AS/NZS 1554.3, reviewed by TPI for conformance and submitted to the Engineer for Acceptance. | Drawings | TPI Report | Prior to Welding | HP | ENG | 4.19.9 - Reinforcing Welding Qualifications | Acceptance / Conformance Criteria - Welders and Procedures are to be qualified to AS/NZS 1554.3, reviewed by TPI for conformance and submitted to the Engineer for Acceptance. | Standard / Specification - Drawings | Verifying Document - TPI Report | Frequency - Prior to Welding | Verification Activity: Activity - HP | Verification Activity: By - ENG | Verification Activity: By - ENG
4.19.10 | Reinforcing Welding | All welded reinforcing shall be completed as per AS/NZS 1554.3 and be 100% Visually NDT inspected by an independent and approved Third Party Inspector (TPI). | Drawings | TPI Report | Prior to concrete pour | R | PE | 4.19.10 - Reinforcing Welding | Acceptance / Conformance Criteria - All welded reinforcing shall be completed as per AS/NZS 1554.3 and be 100% Visually NDT inspected by an independent and approved Third Party Inspector (TPI). | Standard / Specification - Drawings | Verifying Document - TPI Report | Frequency - Prior to concrete pour | Verification Activity: Activity - R | Verification Activity: By - PE | 4.19.3 - Hot-dip Galvanising
4.19.11 | Pile Concrete Mix Design / Tremmie Mix Design | Mix design compiling with the requirements of the contract to be approved by the Engineer. | Drawings | Approved Mix Design | Submitted to and approved by the Engineer prior to concreting | HP | ENG | 4.19.11 - Pile Concrete Mix Design / Tremmie Mix Design | Acceptance / Conformance Criteria - Mix design compiling with the requirements of the contract to be approved by the Engineer. | Standard / Specification - Drawings | Verifying Document - Approved Mix Design | Frequency - Submitted to and approved by the Engineer prior to concreting | Verification Activity: Activity - HP | Verification Activity: By - ENG | Acceptance / Conformance Criteria - Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680. All alterations to fittings shall be hot dip galvanised following fabrication.
4.19.12 | Concrete Aggergate | Aggregates for concrete shall be selected from a single source, which shall be used for all concrete that will form part of the permanent works. Nominal maximum coarse aggregate size shall be 15mm. | PS 18.2.5 PS 18.2.1 PS 18.2.2 | Mix Design | Prior to Works | R | SE | 4.19.12 - Concrete Aggergate | Acceptance / Conformance Criteria - Aggregates for concrete shall be selected from a single source, which shall be used for all concrete that will form part of the permanent works. Nominal maximum coarse aggregate size shall be 15mm. | Standard / Specification - PS 18.2.5 PS 18.2.1 PS 18.2.2 | Verifying Document - Mix Design | Frequency - Prior to Works | Verification Activity: Activity - R | Verification Activity: By - SE | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2
4.19.13 | Concrete Capping Concrete | All concrete shall have a minimum 28-day compressive strength of 30 MPa. | PS 18.5.1 | Approved Mix Design | Submitted to and approved by the Engineer prior to concreting | HP | ENG | 4.19.13 - Concrete Capping Concrete | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa. | Standard / Specification - PS 18.5.1 | Verifying Document - Approved Mix Design | Frequency - Submitted to and approved by the Engineer prior to concreting | Verification Activity: Activity - HP | Verification Activity: By - ENG | Verifying Document - Datasheet
4.19.14 | Capping Steelwork | All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process. Quench and tempered is not permitted. | PS 18.5.2 PS 18.1.2 | Detail Sheets and Mill Certificates | Prior to ordering steel | R | SE | 4.19.14 - Capping Steelwork | Acceptance / Conformance Criteria - All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process. Quench and tempered is not permitted. | Standard / Specification - PS 18.5.2 PS 18.1.2 | Verifying Document - Detail Sheets and Mill Certificates | Frequency - Prior to ordering steel | Verification Activity: Activity - R | Verification Activity: By - SE | Frequency - Prior to Works
4.19.15 | PFC CHAR(AMP) UC Steelwork | Sections shall be grade 300 unless noted otherwise. All PFC CHAR(AMP) UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P. All welds to be 6mm minimum continuous fillet welds, unless noted otherwise. | PS 18.5.2 PS 18.1.2 | Detail Sheets and Mill Certificates | Prior to ordering steel | R | SE | 4.19.15 - PFC CHAR(AMP) UC Steelwork | Acceptance / Conformance Criteria - Sections shall be grade 300 unless noted otherwise. All PFC CHAR(AMP) UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P. All welds to be 6mm minimum continuous fillet welds, unless noted otherwise. | Standard / Specification - PS 18.5.2 PS 18.1.2 | Verifying Document - Detail Sheets and Mill Certificates | Frequency - Prior to ordering steel | Verification Activity: Activity - R | Verification Activity: By - SE | Verification Activity: Activity - R
4.19.16 | Precast Mild steel fixings | All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication. | PS 19.15.6 | Datasheet / Mill Certs | Prior to use | R | SE | 4.19.16 - Precast Mild steel fixings | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication. | Standard / Specification - PS 19.15.6 | Verifying Document - Datasheet / Mill Certs | Frequency - Prior to use | Verification Activity: Activity - R | Verification Activity: By - SE | Verification Activity: By - SE
4.19.17 | Precast Stainless steel | Stainless steel shall be type 316 unless otherwise specified. | PS 19.15.7 | Datasheet / Mill Certs | Prior to use | R | SE | 4.19.17 - Precast Stainless steel | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified. | Standard / Specification - PS 19.15.7 | Verifying Document - Datasheet / Mill Certs | Frequency - Prior to use | Verification Activity: Activity - R | Verification Activity: By - SE | 4.19.5 - Welding Procedures
4.19.18 | Reinforcement cover spacer blocks | Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas. | PS 19.7.8 | Datasheets | Prior to use | R | SE | 4.19.18 - Reinforcement cover spacer blocks | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas. | Standard / Specification - PS 19.7.8 | Verifying Document - Datasheets | Frequency - Prior to use | Verification Activity: Activity - R | Verification Activity: By - SE | Acceptance / Conformance Criteria - All welds shall be weld category GP in accordance with NZS 3404. All welding procedures shall be in accordance with AS/NZS 1554. The Contractor shall submit full details of the proposed welding procedures and electrodes, with drawings and schedules as required.
9.01.1 | Contractor’s Methodology for Pile Construction | The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works. | PS 18.3.1 PS 18.1.2 | Approved Methodology | At least two weeks prior to commencement of the works. | HP | ENG | 9.01.1 - Contractor’s Methodology for Pile Construction | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works. | Standard / Specification - PS 18.3.1 PS 18.1.2 | Verifying Document - Approved Methodology | Frequency - At least two weeks prior to commencement of the works. | Verification Activity: Activity - HP | Verification Activity: By - ENG | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2
9.01.3 | Setting Out | The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings. | PS 18.4.2 | Survey Records | Each Pile | S | SE | 9.01.3 - Setting Out | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings. | Standard / Specification - PS 18.4.2 | Verifying Document - Survey Records | Frequency - Each Pile | Verification Activity: Activity - S | Verification Activity: By - SE | Verifying Document - Welding Procedures
9.01.4 | Setout Approval | On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer. | PS 18.4.2 | Engineers Approval | Each Pile beofre excavation | HP | ENG | 9.01.4 - Setout Approval | Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer. | Standard / Specification - PS 18.4.2 | Verifying Document - Engineers Approval | Frequency - Each Pile beofre excavation | Verification Activity: Activity - HP | Verification Activity: By - ENG | Frequency - Prior to Works
9.01.5 | Depth of Foundation | The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals. | PS 18.3.2 | Engineers Approval | Each Pile Before Survey and Concrete | HP | ENG | 9.01.5 - Depth of Foundation | Acceptance / Conformance Criteria - The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals. | Standard / Specification - PS 18.3.2 | Verifying Document - Engineers Approval | Frequency - Each Pile Before Survey and Concrete | Verification Activity: Activity - HP | Verification Activity: By - ENG | Verification Activity: Activity - R
9.01.6 | Pilling Records | The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded. The daily records from the driller shall be submitted no later than noon the following day. | PS 18.3.2 | Pilling Records | Daily | I | SE | 9.01.6 - Pilling Records | Acceptance / Conformance Criteria - The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded. The daily records from the driller shall be submitted no later than noon the following day. | Standard / Specification - PS 18.3.2 | Verifying Document - Pilling Records | Frequency - Daily | Verification Activity: Activity - I | Verification Activity: By - SE | Verification Activity: By - SE
9.01.7 | Pilling Timming | During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time. | PS 18.3.2 | Survey Records | Each Pile | S | SE | 9.01.7 - Pilling Timming | Acceptance / Conformance Criteria - During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time. | Standard / Specification - PS 18.3.2 | Verifying Document - Survey Records | Frequency - Each Pile | Verification Activity: Activity - S | Verification Activity: By - SE | 4.19.6 - Welders Qualifications
9.01.8 | Pile Excavation Survey | On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete.” | PS 18.3.2 | Survey Records | Each Pile before concrete | HP | ENG | 9.01.8 - Pile Excavation Survey | Acceptance / Conformance Criteria - On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete.” | Standard / Specification - PS 18.3.2 | Verifying Document - Survey Records | Frequency - Each Pile before concrete | Verification Activity: Activity - HP | Verification Activity: By - ENG | Acceptance / Conformance Criteria - Only welders qualified to AS/NZS 1554, or equivalent standard shall be employed on the works. Proof of welder’s proficiency and qualification shall be made available to the Engineer on request.
9.01.9 | Construction Tolerances for Piles | The allowable positional tolerances of the concrete piles shall be ± 50 mm. The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical. | PS 18.3.3 | Survey Records | Each Pile | I | SV | 9.01.9 - Construction Tolerances for Piles | Acceptance / Conformance Criteria - The allowable positional tolerances of the concrete piles shall be ± 50 mm. The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical. | Standard / Specification - PS 18.3.3 | Verifying Document - Survey Records | Frequency - Each Pile | Verification Activity: Activity - I | Verification Activity: By - SV | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2
9.01.10 | Remedial Painting | Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110. | PS 18.2.3 PS 18.2.1 PS 18.2.2 | Site Records | Each Occurance | S | SE | 9.01.10 - Remedial Painting | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110. | Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2 | Verifying Document - Site Records | Frequency - Each Occurance | Verification Activity: Activity - S | Verification Activity: By - SE | Verifying Document - Qualification
9.02.1 | Monitoring Surveys / Deformation Surveys | Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures. | PS 18.7.1 | Survey Records | As Required | I | SV | 9.02.1 - Monitoring Surveys / Deformation Surveys | Acceptance / Conformance Criteria - Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures. | Standard / Specification - PS 18.7.1 | Verifying Document - Survey Records | Frequency - As Required | Verification Activity: Activity - I | Verification Activity: By - SV | Frequency - Prior to Works
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.7 - Steel Piles
Acceptance / Conformance Criteria - Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680. Only new steel pile section to be used. All piles and production certificates shall be made available for inspection by the Engineer at any time.
Standard / Specification - PS 18.2.4 PS 18.2.1 PS 18.2.2
Verifying Document - Mill Certs
Frequency - Prior to Works
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.8 - Steel Reinforcement Compliance
Acceptance / Conformance Criteria - Conformin Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied.
Standard / Specification - AS/NZS4671 CHAR(AMP) NZS3109
Verifying Document - Detail Sheets and Mill Certificates
Frequency - Prior to ordering steel
Verification Activity: Activity - W
Verification Activity: By - SE
4.19.9 - Reinforcing Welding Qualifications
Acceptance / Conformance Criteria - Welders and Procedures are to be qualified to AS/NZS 1554.3, reviewed by TPI for conformance and submitted to the Engineer for Acceptance.
Standard / Specification - Drawings
Verifying Document - TPI Report
Frequency - Prior to Welding
Verification Activity: Activity - HP
Verification Activity: By - ENG
4.19.10 - Reinforcing Welding
Acceptance / Conformance Criteria - All welded reinforcing shall be completed as per AS/NZS 1554.3 and be 100% Visually NDT inspected by an independent and approved Third Party Inspector (TPI).
Standard / Specification - Drawings
Verifying Document - TPI Report
Frequency - Prior to concrete pour
Verification Activity: Activity - R
Verification Activity: By - PE
4.19.11 - Pile Concrete Mix Design / Tremmie Mix Design
Acceptance / Conformance Criteria - Mix design compiling with the requirements of the contract to be approved by the Engineer.
Standard / Specification - Drawings
Verifying Document - Approved Mix Design
Frequency - Submitted to and approved by the Engineer prior to concreting
Verification Activity: Activity - HP
Verification Activity: By - ENG
4.19.12 - Concrete Aggergate
Acceptance / Conformance Criteria - Aggregates for concrete shall be selected from a single source, which shall be used for all concrete that will form part of the permanent works. Nominal maximum coarse aggregate size shall be 15mm.
Standard / Specification - PS 18.2.5 PS 18.2.1 PS 18.2.2
Verifying Document - Mix Design
Frequency - Prior to Works
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.13 - Concrete Capping Concrete
Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa.
Standard / Specification - PS 18.5.1
Verifying Document - Approved Mix Design
Frequency - Submitted to and approved by the Engineer prior to concreting
Verification Activity: Activity - HP
Verification Activity: By - ENG
4.19.14 - Capping Steelwork
Acceptance / Conformance Criteria - All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process. Quench and tempered is not permitted.
Standard / Specification - PS 18.5.2 PS 18.1.2
Verifying Document - Detail Sheets and Mill Certificates
Frequency - Prior to ordering steel
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.15 - PFC CHAR(AMP) UC Steelwork
Acceptance / Conformance Criteria - Sections shall be grade 300 unless noted otherwise. All PFC CHAR(AMP) UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P. All welds to be 6mm minimum continuous fillet welds, unless noted otherwise.
Standard / Specification - PS 18.5.2 PS 18.1.2
Verifying Document - Detail Sheets and Mill Certificates
Frequency - Prior to ordering steel
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.16 - Precast Mild steel fixings
Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
Standard / Specification - PS 19.15.6
Verifying Document - Datasheet / Mill Certs
Frequency - Prior to use
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.17 - Precast Stainless steel
Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
Standard / Specification - PS 19.15.7
Verifying Document - Datasheet / Mill Certs
Frequency - Prior to use
Verification Activity: Activity - R
Verification Activity: By - SE
4.19.18 - Reinforcement cover spacer blocks
Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
Standard / Specification - PS 19.7.8
Verifying Document - Datasheets
Frequency - Prior to use
Verification Activity: Activity - R
Verification Activity: By - SE
9.01.1 - Contractor’s Methodology for Pile Construction
Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works.
Standard / Specification - PS 18.3.1 PS 18.1.2
Verifying Document - Approved Methodology
Frequency - At least two weeks prior to commencement of the works.
Verification Activity: Activity - HP
Verification Activity: By - ENG
9.01.3 - Setting Out
Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings.
Standard / Specification - PS 18.4.2
Verifying Document - Survey Records
Frequency - Each Pile
Verification Activity: Activity - S
Verification Activity: By - SE
9.01.4 - Setout Approval
Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer.
Standard / Specification - PS 18.4.2
Verifying Document - Engineers Approval
Frequency - Each Pile beofre excavation
Verification Activity: Activity - HP
Verification Activity: By - ENG
9.01.5 - Depth of Foundation
Acceptance / Conformance Criteria - The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals.
Standard / Specification - PS 18.3.2
Verifying Document - Engineers Approval
Frequency - Each Pile Before Survey and Concrete
Verification Activity: Activity - HP
Verification Activity: By - ENG
9.01.6 - Pilling Records
Acceptance / Conformance Criteria - The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded. The daily records from the driller shall be submitted no later than noon the following day.
Standard / Specification - PS 18.3.2
Verifying Document - Pilling Records
Frequency - Daily
Verification Activity: Activity - I
Verification Activity: By - SE
9.01.7 - Pilling Timming
Acceptance / Conformance Criteria - During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time.
Standard / Specification - PS 18.3.2
Verifying Document - Survey Records
Frequency - Each Pile
Verification Activity: Activity - S
Verification Activity: By - SE
9.01.8 - Pile Excavation Survey
Acceptance / Conformance Criteria - On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete.”
Standard / Specification - PS 18.3.2
Verifying Document - Survey Records
Frequency - Each Pile before concrete
Verification Activity: Activity - HP
Verification Activity: By - ENG
9.01.9 - Construction Tolerances for Piles
Acceptance / Conformance Criteria - The allowable positional tolerances of the concrete piles shall be ± 50 mm. The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical.
Standard / Specification - PS 18.3.3
Verifying Document - Survey Records
Frequency - Each Pile
Verification Activity: Activity - I
Verification Activity: By - SV
9.01.10 - Remedial Painting
Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
Standard / Specification - PS 18.2.3 PS 18.2.1 PS 18.2.2
Verifying Document - Site Records
Frequency - Each Occurance
Verification Activity: Activity - S
Verification Activity: By - SE
9.02.1 - Monitoring Surveys / Deformation Surveys
Acceptance / Conformance Criteria - Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures.
Standard / Specification - PS 18.7.1
Verifying Document - Survey Records
Frequency - As Required
Verification Activity: Activity - I
Verification Activity: By - SV