## Sheet1
1.1 | Set out | Composite Drawings | Is the position of the pipe in accordance with the drawings? IFC and latest available revision used? | ☐ Yes ☐ No ☐ N/A | H | W |  | 1.1 - Set out | Ref docs - Composite Drawings | Acceptance criteria - Is the position of the pipe in accordance with the drawings? IFC and latest available revision used? | Acceptance | Key - H | VIVA - W | Remarks / record (eg. test frequency, reports, certificates, checklist etc) - | 1.1 - Set out
1.2 | IFC Submission & Approval | Composite Drawings | Is IFC Construction Drawing and Most Current Revision Approved by the client? | ☐ Yes ☐ No ☐ N/A | H | H | [8 empty] | Ref docs - Composite Drawings
1.3 | Permits | Symal Safety Procedure | Have the below permits been created. -GPP -Working at Heights -Hot Works -Confined Space | ☐ Yes ☐ No ☐ N/A | H | W | [8 empty] | Acceptance criteria - Is the position of the pipe in accordance with the drawings? IFC and latest available revision used?
1.4 | Determine Lot Size |  | What is the lot size? | ☐ Yes ☐ No ☐ N/A | S | W | [8 empty] | Acceptance
1.5 | Materials |  | Have the provided materials been accepted, and checklist completed? Have the materials and tag numbers/heat numbers been verified? | ☐ Yes ☐ No ☐ N/A | W | W | ☐ Material Inspection Checklist | [7 empty] | Key - H
1.6 | Electrical and Earthing Pre- Qualification | Welder Qualifications and tickets. This ITP | Welding procedures, equipment to be used, welding qualifications and calibration of welding machines to be submitted and approved by the client, has this been completed? | ☐ Yes ☐ No ☐ N/A | H | H | ☐ Calibration Certificates | [7 empty] | VIVA - W
1.7 | Bedding and Backfill Materials Approval |  | Has bedding and backfill materials been approved for use? | ☐ Yes ☐ No ☐ N/A | H | H | ☐ Material Approval | [7 empty] | Remarks / record (eg. test frequency, reports, certificates, checklist etc) -