## Sheet1
1 | Issued For Construction Drawings | IFC Drawings Issued by Client/Engineer | Issued For Construction Drawings Available | Contractor Rep - H | 1 - Issued For Construction Drawings | SPECIFICATION REFERENCE - IFC Drawings Issued by Client/Engineer | ACCEPTANCE CRITERIA - Issued For Construction Drawings Available | DATE/SIGN - Contractor Rep - H | 1 - Issued For Construction Drawings
2 | Survey CHAR(AMP) Setout | IFC Drawings CTS General Civil Construction Spec CTS Excavation Works Spec | Foundations and embedded items shall be setout following the tolerances, heights and positions shown in each foundations respective drawing. | Contractor Rep - P | 2 - Survey CHAR(AMP) Setout | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Spec CTS Excavation Works Spec | ACCEPTANCE CRITERIA - Foundations and embedded items shall be setout following the tolerances, heights and positions shown in each foundations respective drawing. | DATE/SIGN - Contractor Rep - P | SPECIFICATION REFERENCE - IFC Drawings Issued by Client/Engineer
3 | Waste Management CHAR(AMP) Disposal | CTS General Civil Construction Spec CTS Excavation Works Spec CTS Contaminated Environmental Ground Soil Managenet Plan RW-231 | Waste management plan prepared and followed. Supporting documents available on request | Contractor Rep - P CTS Civil Inspector - R | 3 - Waste Management CHAR(AMP) Disposal | SPECIFICATION REFERENCE - CTS General Civil Construction Spec CTS Excavation Works Spec CTS Contaminated Environmental Ground Soil Managenet Plan RW-231 | ACCEPTANCE CRITERIA - Waste management plan prepared and followed. Supporting documents available on request | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R | ACCEPTANCE CRITERIA - Issued For Construction Drawings Available
4 | Trim Subgrade | Underground Services Drawings CTS Excavation Permit CTS Excavation Works Spec CTS General Civil Construction Specification | Subgrade to be trimmed within -250mm of the Finished Site Concrete level and to the levels stated on the drawings | Contractor Rep - P CTS Civil Inspector - H | 4 - Trim Subgrade | SPECIFICATION REFERENCE - Underground Services Drawings CTS Excavation Permit CTS Excavation Works Spec CTS General Civil Construction Specification | ACCEPTANCE CRITERIA - Subgrade to be trimmed within -250mm of the Finished Site Concrete level and to the levels stated on the drawings | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H | DATE/SIGN - Contractor Rep - H
5 | Backfill/Subgrade Compaction | IFC Drawings CTS General Civil Construction Specification Clegg Compaction Inspection Record | Foundation subbase shall consist of 200mm of Gap65 Blue-Brown Rock hardfill material. Subbase compaction shall be tested using a clegg hammer, all readings to exceed a CIV of 24 with 90% of tests to exceed 30. | Contractor Rep - P CTS Civil Inspector - H | 5 - Backfill/Subgrade Compaction | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Clegg Compaction Inspection Record | ACCEPTANCE CRITERIA - Foundation subbase shall consist of 200mm of Gap65 Blue-Brown Rock hardfill material. Subbase compaction shall be tested using a clegg hammer, all readings to exceed a CIV of 24 with 90% of tests to exceed 30. | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H | 2 - Survey CHAR(AMP) Setout
6 | Site Concrete | IFC Drawings CTS General Civil Construction Specification Inspection Records Delivery Dockets | Site concrete to be placed at the thicknesses shown on the drawings and finished to a height of +/- 10mm | Contractor Rep - P CTS Civil Inspector - R | 6 - Site Concrete | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Inspection Records Delivery Dockets | ACCEPTANCE CRITERIA - Site concrete to be placed at the thicknesses shown on the drawings and finished to a height of +/- 10mm | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Spec CTS Excavation Works Spec
7 | Reinforcing | IFC Drawings CTS General Civil Construction Specification NZS3109 Manufacturers Documentation Inspection Records | All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's. All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted. All reinforcing shall be tied and laid out to comply with the IFC drawings | Contractor Rep - P CTS Civil Inspector - H | 7 - Reinforcing | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification NZS3109 Manufacturers Documentation Inspection Records | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's. All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted. All reinforcing shall be tied and laid out to comply with the IFC drawings | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H | ACCEPTANCE CRITERIA - Foundations and embedded items shall be setout following the tolerances, heights and positions shown in each foundations respective drawing.
8 | Cast in Items - Nuts, Bolts and Studs | IFC Drawings CTS General Civil Construction Specification CTS Epoxy Grouting of Anchor Bolts Manufacturers Documentation Inspection Records | Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings Drilled holes for Anchors shall be inspected by Civil Inspector | Contractor Rep - P CTS Civil Inspector - H | 8 - Cast in Items - Nuts, Bolts and Studs | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification CTS Epoxy Grouting of Anchor Bolts Manufacturers Documentation Inspection Records | ACCEPTANCE CRITERIA - Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings Drilled holes for Anchors shall be inspected by Civil Inspector | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H | DATE/SIGN - Contractor Rep - P
9 | Formwork | IFC Drawings CTS General Civil Construction Specification NZS3109 Inspection Records | Fillets to corners above ground as noted on IFC drawings. Tolerances for Insitu formwork shall be +/-20mm dimensionally, and +/-12mm level Minimum cover shall be 50mm unless cast against the ground which shall be 75mm unless noted otherwise. | Contractor Rep - P CTS Civil Inspector - W | 9 - Formwork | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification NZS3109 Inspection Records | ACCEPTANCE CRITERIA - Fillets to corners above ground as noted on IFC drawings. Tolerances for Insitu formwork shall be +/-20mm dimensionally, and +/-12mm level Minimum cover shall be 50mm unless cast against the ground which shall be 75mm unless noted otherwise. | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - W | 3 - Waste Management CHAR(AMP) Disposal
10 | Grouting | IFC Drawings CTS General Civil Construction Specification Manufacturers Specification Inspection Records | Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings | Contractor Rep - P CTS Civil Inspector - W | 10 - Grouting | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Manufacturers Specification Inspection Records | ACCEPTANCE CRITERIA - Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - W | SPECIFICATION REFERENCE - CTS General Civil Construction Spec CTS Excavation Works Spec CTS Contaminated Environmental Ground Soil Managenet Plan RW-231
11 | Concrete | IFC Drawings CTS General Civil Construction Specification NZS3112/NZS3109 Inspection Records Delivery Dockets | Concrete shall be 30MPa 28 day compressive strength Slump Tests - one for every pour Crush Tests taken per pour as per NZS3109 CHAR(AMP) CTS General Civil Specification | Contractor Rep - P CTS Civil Inspector - H | 11 - Concrete | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification NZS3112/NZS3109 Inspection Records Delivery Dockets | ACCEPTANCE CRITERIA - Concrete shall be 30MPa 28 day compressive strength Slump Tests - one for every pour Crush Tests taken per pour as per NZS3109 CHAR(AMP) CTS General Civil Specification | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H | ACCEPTANCE CRITERIA - Waste management plan prepared and followed. Supporting documents available on request
12 | Complete final Civil Inspection and close off ITP | IFC Drawings CTS General Civil Construction Specification Manufacturers Specification | ITP/QC has been completed; all steps CHAR(AMP) hold points signed byrelevant party. All work completed as per work pack, and any field instructions issued during construction compiled | Contractor Rep - P CTS Civil Inspector - R | 12 - Complete final Civil Inspection and close off ITP | SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Manufacturers Specification | ACCEPTANCE CRITERIA - ITP/QC has been completed; all steps CHAR(AMP) hold points signed byrelevant party. All work completed as per work pack, and any field instructions issued during construction compiled | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R
13 | Non-Conformance Reporting | UCC Internal NCR and or Lucidity event NCR QC Requirements for Civil Works | All Non-Conformance reports and Investigations are attached and closed out | Contractor Rep - H | 13 - Non-Conformance Reporting | SPECIFICATION REFERENCE - UCC Internal NCR and or Lucidity event NCR QC Requirements for Civil Works | ACCEPTANCE CRITERIA - All Non-Conformance reports and Investigations are attached and closed out | DATE/SIGN - Contractor Rep - H | 4 - Trim Subgrade
14 | As Built CHAR(AMP) Final Design Documentation |  | Confirmation From Engineer on as built records CHAR(AMP) redline mark ups | Contractor Rep - P | 14 - As Built CHAR(AMP) Final Design Documentation | SPECIFICATION REFERENCE - | ACCEPTANCE CRITERIA - Confirmation From Engineer on as built records CHAR(AMP) redline mark ups | DATE/SIGN - Contractor Rep - P | SPECIFICATION REFERENCE - Underground Services Drawings CTS Excavation Permit CTS Excavation Works Spec CTS General Civil Construction Specification
15 | Reference Info, Specifications |  | Provided a completed construction defect report that that details any remedial measures taken, CHAR(AMP) snag lists closed out |  | 15 - Reference Info, Specifications | SPECIFICATION REFERENCE - | ACCEPTANCE CRITERIA - Provided a completed construction defect report that that details any remedial measures taken, CHAR(AMP) snag lists closed out | DATE/SIGN - | ACCEPTANCE CRITERIA - Subgrade to be trimmed within -250mm of the Finished Site Concrete level and to the levels stated on the drawings
16 | Punch Listing | CTS QC Requirments for Civil Work | All punch list items are closed out in the relevant timeframe to the required standard | Contractor Rep - P CTS Civil Inspector - R | 16 - Punch Listing | SPECIFICATION REFERENCE - CTS QC Requirments for Civil Work | ACCEPTANCE CRITERIA - All punch list items are closed out in the relevant timeframe to the required standard | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R | DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H
17 | Compilation of ITP |  | ITP Completed and Signed off | Contractor Rep - H CTS Civil Inspector - H | 17 - Compilation of ITP | SPECIFICATION REFERENCE - | ACCEPTANCE CRITERIA - ITP Completed and Signed off | DATE/SIGN - Contractor Rep - H CTS Civil Inspector - H | 5 - Backfill/Subgrade Compaction
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Clegg Compaction Inspection Record
ACCEPTANCE CRITERIA - Foundation subbase shall consist of 200mm of Gap65 Blue-Brown Rock hardfill material. Subbase compaction shall be tested using a clegg hammer, all readings to exceed a CIV of 24 with 90% of tests to exceed 30.
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H
6 - Site Concrete
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Inspection Records Delivery Dockets
ACCEPTANCE CRITERIA - Site concrete to be placed at the thicknesses shown on the drawings and finished to a height of +/- 10mm
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R
7 - Reinforcing
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification NZS3109 Manufacturers Documentation Inspection Records
ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's. All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted. All reinforcing shall be tied and laid out to comply with the IFC drawings
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H
8 - Cast in Items - Nuts, Bolts and Studs
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification CTS Epoxy Grouting of Anchor Bolts Manufacturers Documentation Inspection Records
ACCEPTANCE CRITERIA - Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings Drilled holes for Anchors shall be inspected by Civil Inspector
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H
9 - Formwork
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification NZS3109 Inspection Records
ACCEPTANCE CRITERIA - Fillets to corners above ground as noted on IFC drawings. Tolerances for Insitu formwork shall be +/-20mm dimensionally, and +/-12mm level Minimum cover shall be 50mm unless cast against the ground which shall be 75mm unless noted otherwise.
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - W
10 - Grouting
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Manufacturers Specification Inspection Records
ACCEPTANCE CRITERIA - Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - W
11 - Concrete
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification NZS3112/NZS3109 Inspection Records Delivery Dockets
ACCEPTANCE CRITERIA - Concrete shall be 30MPa 28 day compressive strength Slump Tests - one for every pour Crush Tests taken per pour as per NZS3109 CHAR(AMP) CTS General Civil Specification
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - H
12 - Complete final Civil Inspection and close off ITP
SPECIFICATION REFERENCE - IFC Drawings CTS General Civil Construction Specification Manufacturers Specification
ACCEPTANCE CRITERIA - ITP/QC has been completed; all steps CHAR(AMP) hold points signed byrelevant party. All work completed as per work pack, and any field instructions issued during construction compiled
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R
13 - Non-Conformance Reporting
SPECIFICATION REFERENCE - UCC Internal NCR and or Lucidity event NCR QC Requirements for Civil Works
ACCEPTANCE CRITERIA - All Non-Conformance reports and Investigations are attached and closed out
DATE/SIGN - Contractor Rep - H
14 - As Built CHAR(AMP) Final Design Documentation
SPECIFICATION REFERENCE -
ACCEPTANCE CRITERIA - Confirmation From Engineer on as built records CHAR(AMP) redline mark ups
DATE/SIGN - Contractor Rep - P
15 - Reference Info, Specifications
SPECIFICATION REFERENCE -
ACCEPTANCE CRITERIA - Provided a completed construction defect report that that details any remedial measures taken, CHAR(AMP) snag lists closed out
DATE/SIGN -
16 - Punch Listing
SPECIFICATION REFERENCE - CTS QC Requirments for Civil Work
ACCEPTANCE CRITERIA - All punch list items are closed out in the relevant timeframe to the required standard
DATE/SIGN - Contractor Rep - P CTS Civil Inspector - R
17 - Compilation of ITP
SPECIFICATION REFERENCE -
ACCEPTANCE CRITERIA - ITP Completed and Signed off
DATE/SIGN - Contractor Rep - H CTS Civil Inspector - H