## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Fabrication - Structural Glaze Fabrication QA Checklist |  |  |  |  | Yes | Fabrication - Structural Glaze Fabrication QA Checklist | 2d544da2-c504-405d-89fc-5178bac3c212
checkpoint-status |  |  | checkpoint | Cutting
button | 5e95636c-2605-5aac-bed3-acd3e441b54e |  | button | Materials free of damage/distortion | YES, NO, N/A
button | 5763a58c-52a5-52d2-baf1-8b1a19240353 |  | button | Extrusion dimensions correct (+/- 1mm) | YES, NO, N/A
checkpoint-status |  |  | checkpoint | CNC Machining
button | c1819587-335c-5199-8512-0ec90b96b355 |  | button | Materials free of damage/distortion | YES, NO, N/A
button | 27a05b9b-9b1a-56d3-81f1-324e2eb4a36b |  | button | Machine coding correct to assembly sheet | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Assembly
button | 3df4827a-f363-591a-9660-3f42ff4cce78 |  | button | Extrusion correct to assembly sheet | YES, NO, N/A
button | 35dcf051-a968-5442-9a20-4e51a57f2c96 |  | button | Panel configuration correct as per assembly sheets | YES, NO, N/A
button | 64560e8d-00b4-5592-b1c0-37badb1d966c |  | button | Extrusion dimensions correct (+/- 1mm) | YES, NO, N/A
button | 09e4ae65-c7ee-5702-9796-3c539100d450 |  | button | All required additional components Installed and fitted correctly | YES, NO, N/A
button | 8f9f0e47-9b8d-5db6-9d16-6db0aee70573 |  | button | Rubbers continuous and free of damage | YES, NO, N/A
button | 87f9e352-6081-5a74-8429-05d3e8a9caf0 |  | button | All joints are tightly fitted, prepared and sealed | YES, NO, N/A
button | 08d1d9e3-9a76-5d25-bbee-0bed8bd4c9c5 |  | button | Drain holes are as per drawings and free of debris | YES, NO, N/A
button | 56c9af58-a15c-5e50-bf64-4afdb1891edf |  | button | Backpans/louvres are fitted as per detail | YES, NO, N/A
button | 55adaf91-4e30-50c3-88f7-0a88fb921bf5 |  | button | Frame is clearly labelled in accordance with fabrication sheets | YES, NO, N/A
button | d360c5b5-d6f9-5f42-9500-f4b3dbb799d1 |  | button | Overall panel dimensions correct (+/- 15mm up to 3mm overall) | YES, NO, N/A
button | e6418a43-af68-59ad-a6bd-76ee95598d02 |  | button | Frame is clean from marks, scratches and fabrication debris | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Hardware/Doors
button | 08717962-904f-5533-a709-6815006617af |  | button | Door operate smoothly and unobstructed | YES, NO, N/A
button | 42c1df52-b6b1-5ee4-85af-131ed22c4c48 |  | button | Correct hardware is fitted and operates smoothly | YES, NO, N/A
checklist-flat |  |  | checklist | Glazing - Curtain Wall Glazing QA Checklist |  |  |  |  | Yes | Glazing - Curtain Wall Glazing QA Checklist | 75babf71-9210-4cde-acf9-f673a8d86e56
checkpoint-status |  |  | checkpoint | Glass identified as correct type for location as per shop drawings
checkpoint-status |  |  | checkpoint | Backing rubbers continuous, sealed in corners and free of damage
checkpoint-status |  |  | checkpoint | Glazing Blocks set out as per NZS4223.3:2016 and correct type
checkpoint-status |  |  | checkpoint | Glass placed in opening, damage free as per NZS4223.3:2016
checkpoint-status |  |  | checkpoint | Safety stamp visible as per NZS4223.3:2016 (industry standard is bottom right from outside)
checkpoint-status |  |  | checkpoint | Beads securely fitted and damage free as per NZS4223.3:2016
checkpoint-status |  |  | checkpoint | Correct glazing wedge used and rubber of as per NZS4223.3:2016 ensuring there is no gaps and corners are sealed
checkpoint-status |  |  | checkpoint | Glass trade clean, free of defects and protection tape fitted where required
checklist-flat |  |  | checklist | Installation - Flush Glaze & Curtain Wall Installation QA Checklist |  |  |  |  | Yes | Installation - Flush Glaze & Curtain Wall Installation QA Checklist | bbe9a4fd-519a-4fca-86dd-f3d8a45012e4
checkpoint-status |  |  | checkpoint | Documentation Received
button | 4127f1f7-e507-59ee-bcc0-f99238026a33 |  | button | Received QA documents from window manufacturer | YES, NO, N/A
button | 7ce5eef2-5117-5e57-bbbc-481256741d8b |  | button | Received all relevant setout/survey drawings | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Initial Inspection
button | 57984448-dd4b-5b69-bd2e-2ed04f83c85a |  | button | Gridlines and RL's are visible and accessible | YES, NO, N/A
button | 14c5d22b-b821-5252-a2ee-ebc80a87d7ef |  | button | Installation area is free from obstruction and has suitable access | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Seismic sill, Head, Jambs and Brackets
button | 65c7a65b-85af-5b13-9811-dc2e682d0813 |  | button | Opening structure correct at sill head and jambs | YES, NO, N/A
button | a0aab2a7-4d86-53d4-8ee0-37c210b6cc2a |  | button | Waterproofing/wrapping complete around entire opening | YES, NO, N/A
button | 4c69225b-fcb3-53b8-b676-c87a01aeb9d9 |  | button | Sill head, jamb fixings & splice fixings are fitted correctly as per specifications and to correct RL | YES, NO, N/A
button | e5a55955-cf62-51fd-959a-da6652fd8116 |  | button | Seismic frame inspected and defect free | YES, NO, N/A
button | 8ac17d98-ee6b-5201-b4e2-cfb3553baa5c |  | button | Seismic sill, head & jambs levelled to correct height | YES, NO, N/A
button | 389c6b1a-e1e7-5570-8f41-2485c9a2c21b |  | button | All fixings, corner angles and splice plates are sealed and neatly tooled | YES, NO, N/A
button | ad8ca0e4-4ab2-58b1-9615-f7a491c44038 |  | button | Check primary brackets are seated correctly and are in the correct position, and all nuts and washers are correct as per design | YES, NO, N/A
button | 8ed9aa59-2d08-5667-acc9-9d9e3516012c |  | button | Check primary brackets are torqued to correct setting 30Nm | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Pre-Installation
button | 3d17dec3-26f3-5f24-b94a-e09bb5456542 |  | button | Check panel identification with setout plans | YES, NO, N/A
button | 4b5e1456-a183-5ed4-a169-51791af5cca8 |  | button | Verify that the panel to be installed will be in the correct location | YES, NO, N/A
button | cb564af8-c374-535a-ad62-bbbd4265c072 |  | button | Visual inspection for any glass or sealant defects | YES, NO, N/A
button | 8a15719a-fd23-5d50-9108-1d16ea1d4fba |  | button | Inspected for any other damage, eg: dents or scratches | YES, NO, N/A
button | bf688ae9-0748-5bdd-827d-b4894a2ccc44 |  | button | Check that the gaskets are in place without damage or voids and that the gaskets are crimped both ends | YES, NO, N/A
button | 819fd400-ce72-5987-b250-fcc96704be5c |  | button | Check that the sub sills are clean and free from debris | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Installation
button | 3ae015d4-a59f-5170-9ed0-bed26eb6bce5 |  | button | Check each panel is set to the correct height | YES, NO, N/A
button | 29f44595-9da6-50b5-b94d-4b5841252090 |  | button | Check each panel is plumb, leveled and true | YES, NO, N/A
button | 4becc627-a46e-50dd-abd1-bd5ff2c45252 |  | button | Check that the gap between the mullions are as per design (within acceptable tolerance) | YES, NO, N/A
button | 0feda02a-405f-5cad-8a23-9ccc2a072189 |  | button | Check bracket is engaged correctly to the primary bracket | YES, NO, N/A
button | 5f610b00-141b-5c3f-a003-1fc9e9b06a41 |  | button | Check that the lock off angle is fitted correctly | YES, NO, N/A
button | f08ee143-3f8e-570a-91b0-86c4a8e53ee4 |  | button | Verify that the connecting spigot and front soaker are clean, sealed and neatly tooled | YES, NO, N/A
button | 2c98bd72-fc7d-5493-bb77-2807c43efad8 |  | button | Check beads are fitted and are rubbered off | YES, NO, N/A
button | 5596f0d4-03c8-595f-8aa0-69daeafcb259 |  | button | Horizontal and vertical air seals applied and neatly tooled | YES, NO, N/A
button | 43874fda-f2db-56f1-8aa8-e6c53cbc76a2 |  | button | Horizontal and vertical weather seals applied and neatly tooled | YES, NO, N/A
button | fc2f38fd-3d39-51bf-a1d2-a30bec369e0d |  | button | Rain shield flashings are installed correctly | YES, NO, N/A
button | ef083ab5-5863-500b-bc59-93a050f9ad73 |  | button | Head flashing is installed correctly | YES, NO, N/A
button | ac1a7ac7-ad50-556b-abe7-b67ff51bf13f |  | button | Parapet flashings are installed | YES, NO, N/A
checklist-flat |  |  | checklist | Fabrication - Curtain Wall Fabrication QA Checklist |  |  |  |  | Yes | Fabrication - Curtain Wall Fabrication QA Checklist | c4994f1c-d351-4f82-8bfc-5e853ddb8571
checkpoint-status |  |  | checkpoint | Cutting
button | f83d9bff-f3a1-5546-a2ed-cba20bb21b4a |  | button | Materials free of damage/distortion | YES, NO, N/A
button | 9d49a552-6640-5ab6-9a40-d64dc78b9c0e |  | button | Extrusion dimensions correct (+/- 1mm) | YES, NO, N/A
checkpoint-status |  |  | checkpoint | CNC Machining
button | 8853b332-9d02-5b5c-8175-1221fc4907be |  | button | Materials free of damage/distortion | YES, NO, N/A
button | ded25dc4-5990-5ea2-80d7-888121a616b7 |  | button | Machine coding correct to assembly sheet | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Assembly
button | f111767e-634c-534f-8924-528ab1211e9e |  | button | Extrusion correct to assembly sheet | YES, NO, N/A
button | 3b2e7186-76c7-539f-97cb-534055ad67c3 |  | button | Panel configuration correct as per assembly sheets | YES, NO, N/A
button | 340a61fc-d005-555a-b839-5f5a92aa0832 |  | button | Extrusion dimensions correct (+/- 1mm) | YES, NO, N/A
button | a2a5c639-58fb-55d2-9169-afeab08d18fc |  | button | All required additional components Installed and fitted correctly | YES, NO, N/A
button | 3a318b54-9308-548a-8a6a-eab648ce1237 |  | button | Rubbers continuous and free of damage | YES, NO, N/A
button | 041b95ed-6833-5d97-a992-09d8cbf7799e |  | button | All joints are tightly fitted, prepared and sealed | YES, NO, N/A
button | a81589f2-658b-5e91-bb0e-ea3070b94856 |  | button | Drain holes are as per drawings and free of debris | YES, NO, N/A
button | 6be69fff-e000-5bde-9b32-b4a8d1ebab00 |  | button | Backpans/louvres are fitted as per detail | YES, NO, N/A
button | 01b40206-68a6-5bb2-b72f-cb6187762750 |  | button | Frame is clearly labelled in accordance with fabrication sheets | YES, NO, N/A
button | 747298db-0dac-5fe7-a444-6cc836168502 |  | button | Overall panel dimensions correct (+/- 15mm up to 3mm overall) | YES, NO, N/A
button | 63699ae1-a9af-567b-9667-48d9104c3a46 |  | button | Frame is clean from marks, scratches and fabrication debris | YES, NO, N/A
checkpoint-status |  |  | checkpoint | Hardware/Doors
button | cfa9d843-069a-58e9-b6db-eb0364cf4b9a |  | button | Door operate smoothly and unobstructed | YES, NO, N/A
button | 973fa7d4-7505-5450-bc29-d17c883fed0d |  | button | Correct hardware is fitted and operates smoothly | YES, NO, N/A