## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building A & B)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Vacuum area and minor patch as required | Complete,Pass
radio | Apply Intertact Pressure Sensitive adhesive | Complete,Pass
radio | Installation pattern and direction followed | Complete,Pass
radio | Installation complete and rubbish placed in bins provided | Complete,Pass
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Vinyl ITP | [5 empty] | Vinyl ITP (Building C)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Grind, vac and clean | Complete,Pass
radio | Apply moisture barrier as required | Complete,Pass
radio | Prime and self level as quoted (3mm) | Complete,Pass
radio | Set out vinyl to minimise waste and cross joins | Complete,Pass
radio | Apply cove fillet to perimeter as required | Complete,Pass
radio | Install vinyl and cove with recommended adhesive | Complete,Pass
radio | Heavy roll finished floor | Complete,Pass
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building C)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Vacuum area and minor patch as required | Complete,Pass
radio | Apply Intertact Pressure Sensitive adhesive | Complete,Pass
radio | Installation pattern and direction followed | Complete,Pass
radio | Installation complete and rubbish placed in bins provided | Complete,Pass
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building D)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Vacuum area and minor patch as required | Complete,Pass
radio | Apply Intertact Pressure Sensitive adhesive | Complete,Pass
radio | Installation pattern and direction followed | Complete,Pass
radio | Installation complete and rubbish placed in bins provided | Complete,Pass
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Vinyl ITP | [5 empty] | Vinyl ITP (Building D)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Grind, vac and clean | Complete,Pass
radio | Apply moisture barrier as required | Complete,Pass
radio | Prime and self level as quoted (3mm) | Complete,Pass
radio | Set out vinyl to minimise waste and cross joins | Complete,Pass
radio | Apply cove fillet to perimeter as required | Complete,Pass
radio | Install vinyl and cove with recommended adhesive | Complete,Pass
radio | Heavy roll finished floor | Complete,Pass
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Carpet ITP | [5 empty] | Carpet ITP (Building E)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Vacuum area and minor patch as required | Complete,Pass
radio | Apply Intertact Pressure Sensitive adhesive | Complete,Pass
radio | Installation pattern and direction followed | Complete,Pass
radio | Installation complete and rubbish placed in bins provided | Complete,Pass
checkpoint | Install 150mm feather edge skirting
checkpoint | Protection - woven plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Timber ITP | [5 empty] | Timber ITP (Building E)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to be finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Vac and clean area | Complete,Pass
radio | Floor prep (grind, MB, 3mm) as required | Complete,Pass
radio | Ensure joinery kickers, skirting boards etc removed where possible | Complete,Pass
radio | Set out Rezil sleeper system as per manufacturer recommendations | Complete,Pass
radio | Set out solid timber to sleepers | Complete,Pass
radio | Install timber with recommended adhesive and secret nails | Complete,Pass
radio | Allow for expansion gaps at perimeter and to fixtures | Complete,Pass
radio | Sand and seal timber as per manufacturer recommendations | Complete,Pass
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms
checklist | Vinyl ITP | [5 empty] | Vinyl ITP (Building E)
section | Details
checkpoint | Working to latest plan revisions and check latest correspondence
checkpoint | Prior works checks
radio | Area free of building debris and trade tools | Complete,Pass
radio | Walls plastered and first coat of paint | Complete,Pass
radio | All adjacent finishes completed and ready to receive finishes. Area to be flagged if LF cannot finish 100% | Complete,Pass
checkpoint | Specification checks - Correct materials as per finishes schedule and sample approvals
checkpoint | Installation procedure as per manufacturer's recommendations and AUS standards -
radio | Barricaded areas | Complete,Pass
radio | Grind, vac and clean | Complete,Pass
radio | Apply moisture barrier as required | Complete,Pass
radio | Prime and self level as quoted (3mm) | Complete,Pass
radio | Set out vinyl to minimise waste and cross joins | Complete,Pass
radio | Apply cove fillet to perimeter as required | Complete,Pass
radio | Install vinyl and cove with recommended adhesive | Complete,Pass
radio | Heavy roll finished floor | Complete,Pass
checkpoint | Protection - corflute plastic
checkpoint | Confirm material warranty applies
checkpoint | Confirm installation warranty 12 months applies
checkpoint | Care and maintenance as per O&Ms