## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: QA / ITP's
| step |  |  | Tier 2: 01a. Roof - Building A Canopies (G)
Box Gutter Installation Checklist (01a. Roof - Building A Canopies (G)) | checklist |  |  | Tier 3: Insulation
Insulation Checklist (01a. Roof - Building A Canopies (G)) | checklist |  |  | Tier 3: Roof Installation
Roof Installation Checklist (01a. Roof - Building A Canopies (G)) | checklist |  |  | Tier 3: Flashing / Capping Installation
Flashing/Capping Installation Checklist (01a. Roof - Building A Canopies (G)) | checklist |  |  | Tier 3: Roof Penetration
| step |  |  | Tier 2: 01b. Roof - Building B Canopies (G)
Box Gutter Installation Checklist (01b. Roof - Building B Canopies (G)) | checklist |  |  | Tier 3: Insulation
Insulation Checklist (01b. Roof - Building B Canopies (G)) | checklist |  |  | Tier 3: Roof Installation
Roof Installation Checklist (01b. Roof - Building B Canopies (G)) | checklist |  |  | Tier 3: Flashing / Capping Installation
Flashing/Capping Installation Checklist (01b. Roof - Building B Canopies (G)) | checklist |  |  | Tier 3: Roof Penetration
| step |  |  | Tier 2: Building C Canopies (G)
Box Gutter Installation Checklist (Building C Canopies (G)) | checklist |  |  | Tier 3: Insulation
Insulation Checklist (Building C Canopies (G)) | checklist |  |  | Tier 3: Roof Installation
Roof Installation Checklist (Building C Canopies (G)) | checklist |  |  | Tier 3: Flashing / Capping Installation
Flashing/Capping Installation Checklist (Building C Canopies (G)) | checklist |  |  | Tier 3: Roof Penetration
| step |  |  | Tier 2: Roof - Building A Glazed (L1)
Box Gutter Installation Checklist (Roof - Building A Glazed (L1)) | checklist |  |  | Tier 3: Insulation
| step |  |  | Tier 2: 02b. Roof - Building B & C Glazed (MZ)
Box Gutter Installation Checklist (02b. Roof - Building B & C Glazed (MZ)) | checklist |  |  | Tier 3: Insulation
| step |  |  | Tier 2: 03a. Roof - Building A Glazed (R)
Box Gutter Installation Checklist (03a. Roof - Building A Glazed (R)) | checklist |  |  | Tier 3: Insulation
| step |  |  | Tier 2: 03b. Roof - Building C Glazed (R)
Box Gutter Installation Checklist (03b. Roof - Building C Glazed (R)) | checklist |  |  | Tier 3: Insulation
| step |  |  | Tier 1: Variations
| step |  |  | Tier 2: Jan
| step |  |  | Tier 2: Feb
| step |  |  | Tier 2: Mar
| step |  |  | Tier 2: Apr
| step |  |  | Tier 2: May
| step |  |  | Tier 2: Jun
| step |  |  | Tier 2: Jul
| step |  |  | Tier 2: Aug
| step |  |  | Tier 2: Sep
| step |  |  | Tier 2: Oct
| step |  |  | Tier 2: Nov
| step |  |  | Tier 2: Dec
| step |  |  | Tier 1: OH&S
| step |  |  | Tier 2: Daily Prestart Toolbox Forms
| step |  |  | Tier 3: Jan
| step |  |  | Tier 3: Feb
| step |  |  | Tier 3: Mar
| step |  |  | Tier 3: Apr
| step |  |  | Tier 3: May
| step |  |  | Tier 3: Jun
| step |  |  | Tier 3: Jul
| step |  |  | Tier 3: Aug
| step |  |  | Tier 3: Sep
| step |  |  | Tier 3: Oct
| step |  |  | Tier 3: Nov
| step |  |  | Tier 3: Dec
| step |  |  | Tier 2: Weekly Toolbox Forms
| step |  |  | Tier 3: Jan
| step |  |  | Tier 3: Feb
| step |  |  | Tier 3: Mar
| step |  |  | Tier 3: Apr
| step |  |  | Tier 3: May
| step |  |  | Tier 3: Jun
| step |  |  | Tier 3: Jul
| step |  |  | Tier 3: Aug
| step |  |  | Tier 3: Sep
| step |  |  | Tier 3: Oct
| step |  |  | Tier 3: Nov
| step |  |  | Tier 3: Dec
| step |  |  | Tier 2: SWMS
| step |  |  | Tier 2: Onsite Material Install Form1
| step |  |  | Tier 1: Foremans Diary Reports
| step |  |  | Tier 1: COVID Tracking Reports
| step |  |  | Tier 1: Delivery Dockets
| step |  |  | Tier 2: Jan
| step |  |  | Tier 2: Feb
| step |  |  | Tier 2: Mar
| step |  |  | Tier 2: Apr
| step |  |  | Tier 2: May
| step |  |  | Tier 2: Jun
| step |  |  | Tier 2: Jul
| step |  |  | Tier 2: Aug
| step |  |  | Tier 2: Sep
| step |  |  | Tier 2: Oct
| step |  |  | Tier 2: Nov
| step |  |  | Tier 2: Dec