## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Post Tension ITP | [5 empty] | Post Tension ITP
section | Details
checkpoint | 1 - Documentation
label | Timing / Frequency - Prior to start
label | Method - Visual
label | Acceptance Criteria - Ensure current revision of design drawings and specifications
label | ○ Shop drawings approved for construction
button | Accepted | Yes,No
label | Comments / Record Type / Reference - A.S.1310 to A.S.1315, A.S. 3600-2009, A.S 4672.1
textbox | Drawing No:
textbox | Rev No:
checkpoint | 2 - Material Handling
label | Timing / Frequency - Prior to Start
label | Method - Visual
label | Acceptance Criteria - Check Strand, ducting anchors & blocks off the delivery truck.
label | ○ Ensure material are damage or rust free.
button | Accepted | Yes,No
label | Comments / Record Type / Reference - A.S. 3600-2009, A.S 4672.1
checkpoint | 3 - Production & Performance Tests (1)
label | Timing / Frequency - Prior to start
label | Method - Check with office
label | Acceptance Criteria - Ensure client has received and approved control & performance test for Coils.
button | Accepted | Yes,No
checkpoint | 3 - Production & Performance Tests (2)
label | Timing / Frequency - Prior to start
label | Method - Check with office
label | Acceptance Criteria - Ensure client has received and approved control & performance test for Anchors & blocks.
button | Accepted | Yes,No
section | Installation
checkpoint | 4 - Set Out for tendons
label | Timing / Frequency - Progressive
label | Method - Measure
label | Acceptance Criteria - As per current design documents/drawings
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (1)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check for strand type
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (2)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check strand Size
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (3)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check Alignment
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (4)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check depth of recess formers
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (5)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check position within tolerances
label | ○ Tolerances Horizontal +/- 50mm
label | ○ Tolerances Vertical +/- 5mm
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (6)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check secured to prevent movement
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (7)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check number of slab anchorages
button | Accepted | Yes,No
checkpoint | 5 - Pre-pour Check Anchorages (8)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check number of pan anchorages
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (1)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check required number of strands each tendon
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (2)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check position as per layout
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (3)
label | Timing / Frequency - Pre-pour
label | Method - Measure
label | Acceptance Criteria - Check profiled with tolerance
label | ○ High & Low +/=5mm
label | ○ Intermediate +/- 10mm
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (4)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check chairs stapled to soffit (if required by builder)
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (5)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check ducts cross tied to chairs
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (6)
label | Timing / Frequency - Pre-pour
label | Method - Measure
label | Acceptance Criteria - Check sufficient stressing length
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (7)
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check for grout hoses
button | Accepted | Yes,No
checkpoint | 6 - Pre-pour Check Ducting and Strand (8)
label | Timing / Frequency - Pre-pour
label | Method - Measure
label | Acceptance Criteria - Tenders longer than 50m should have an intermediate grouting hose
button | Accepted | Yes,No
checkpoint | 7 - Pre-pour Check Coil Record
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Record coil number in TRD Coil registry.
button | Accepted | Yes,No
checkpoint | 8 - Pre-pour Check Reinforcement positioned
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check anti-burst reinforcement is positioned correctly
button | Accepted | Yes,No
checkpoint | 9 - Pre-pour Check Ducts & Grout tubes sealing
label | Timing / Frequency - Pre-pour
label | Method - Visual
label | Acceptance Criteria - Check Ducts & Grout tubes for sealing at both ends & joints
button | Accepted | Yes,No
checkpoint | 10 - Pre-pour Inspection by Post Tension Engineer (1)
label | Timing / Frequency - Prior to pour
label | Method - Visual
label | Acceptance Criteria - Post Tension inspected and signed off by Structural Engineer
button | Accepted | Yes,No
checkpoint | 10 - Pre-pour Inspection by Post Tension Engineer (2)
label | Timing / Frequency - Prior to pour
label | Method - Visual
label | Acceptance Criteria - Site Foreman to sign off engineer’s report to verify that all work to be rectified was checked for compliance prior to the pour
button | Accepted | Yes,No
checkpoint | 10 - Pre-pour Inspection by Post Tension Engineer (3)
label | Timing / Frequency - Prior to pour
label | Method - Visual
label | Acceptance Criteria - Inspection Certificate provided
button | Accepted | Yes,No
section | CONCRETE POUR CHECKLIST
checkpoint | 11 - Pour Check Components (1)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Is the weather fine?
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (2)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria -
label | Is the weather overcast?
button | Accepted | Yes,No
label | Did it rain during the pour?
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (3)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Monitor during pour Components are not displaced
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (4)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Monitor during pour profile and cover is maintained
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (5)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Are the tendons treated with care and not damaged?
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (6)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Is the concrete being placed properly and well compacted around anchors, dead ends etc.?
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (7)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Are anchors free from concrete?
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (8)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Is any grout hose/tube buried?
button | Accepted | Yes,No
checkpoint | 11 - Pour Check Components (9)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Is any pan buried or filled with concrete?
button | Accepted | Yes,No
checkpoint | 12 - Delays in concrete pour (1)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria -
textbox | Time Stopped:
button | Accepted | Yes,No
checkpoint | 12 - Delays in concrete pour (2)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria -
textbox | Time Resumed:
button | Accepted | Yes,No
checkpoint | 12 - Delays in concrete pour (3)
label | Timing / Frequency - During Pour
label | Method - Visual
label | Acceptance Criteria - Is there any cold joint?
button | Accepted | Yes,No
section | INITIAL STRESS
checkpoint | 13 - Block up (1)
label | Timing / Frequency - Pre-Initial Stress
label | Method - Visual
label | Acceptance Criteria - Is there any crack/or honeycomb around the anchors?
button | Accepted | Yes,No
checkpoint | 13 - Block up (2)
label | Timing / Frequency - Pre-Initial Stress
label | Method - Visual
label | Acceptance Criteria - Are the anchors filled with concrete slurry?
button | Accepted | Yes,No
checkpoint | 14 - Initial Stressing Check Equipment
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - Is jack calibration older than 6 months, if yes stressing may not proceed until updated calibration equipment is available
button | Accepted | Yes,No
checkpoint | 15 - Initial Stressing Check Concrete Required Strength
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - Has the concrete reached the required Strength >= 9 MPA
button | Accepted | Yes,No
checkpoint | 16 - Initial Stressing Check Approval to Stress
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - Approved by Structural Engineer Strength >= 9MPA
button | Accepted | Yes,No
checkpoint | 17 - Initial Stressing Check Initial Stress (1)
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - 100% complete
button | Accepted | Yes,No
checkpoint | 17 - Initial Stressing Check Initial Stress (2)
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - Record sequence and continuity
button | Accepted | Yes,No
checkpoint | 17 - Initial Stressing Check Initial Stress (3)
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria -
textbox | Not Stressed Tendons ID:
button | Accepted | Yes,No
checkpoint | 17 - Initial Stressing Check Initial Stress (4)
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria -
textbox | Broken Strand Tendon ID:
button | Accepted | Yes,No
checkpoint | 17 - Initial Stressing Check Initial Stress (5)
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - Approve stressing records of each stressing operation
button | Accepted | Yes,No
section | FINAL-STRESS
checkpoint | 19 - Final Stressing Check Equipment (1)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - Current Calibration Certificate
textbox | Jack Calibration Date
label | ○ Is jack calibration older than 6 months, if yes stressing may not proceed until updated calibration equipment is available
button | Accepted | Yes,No
checkpoint | 19 - Final Stressing Check Equipment (2)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - Load vs Pressure graph available
button | Accepted | Yes,No
checkpoint | 20 - Final Stressing Check Minimum Concrete Strength Required
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - Has the concrete reached the required Strength >= 22MPA?
button | Accepted | Yes,No
checkpoint | 21 - Final Stressing Check Approval to Stress
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - Approved by Structural Engineer Strength >= 22MPA
button | Accepted | Yes,No
checkpoint | 22 - Final Stressing Check Final Stress (1)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - 100% complete
button | Accepted | Yes,No
checkpoint | 22 - Final Stressing Check Final Stress (2)
label | Timing / Frequency - Initial Stressing
label | Method - Visual
label | Acceptance Criteria - Record sequence and continuity
button | Accepted | Yes,No
checkpoint | 22 - Final Stressing Check Final Stress (3)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria -
textbox | Not Stressed Tendons ID:
button | Accepted | Yes,No
checkpoint | 22 - Final Stressing Check Final Stress (4)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria -
textbox | Broken Strand Tendon ID:
button | Accepted | Yes,No
checkpoint | 22 - Final Stressing Check Final Stress (5)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - Approve stressing records of each stressing operation
button | Accepted | Yes,No
checkpoint | 22 - Final Stressing Check Final Stress (6)
label | Timing / Frequency - Final Stressing
label | Method - Visual
label | Acceptance Criteria - Submit Stressing Records for approval
button | Accepted | Yes,No
section | CUT & SEAL
checkpoint | 23 - Cutting off strands & packing recess (1)
label | Timing / Frequency - After Final Stress
label | Method - Visual
label | Acceptance Criteria - Has the approval to cut strands ben received from the engineer?
button | Accepted | Yes,No
checkpoint | 23 - Cutting off strands & packing recess (2)
label | Timing / Frequency - After Final Stress
label | Method - Visual
label | Acceptance Criteria - Have the strands been cut with adequate cover?
button | Accepted | Yes,No
checkpoint | 23 - Cutting off strands & packing recess (3)
label | Timing / Frequency - After Cutting
label | Method - Visual
label | Acceptance Criteria - Have the recess pockets been painted with epoxy? (where required)
button | Accepted | Yes,No
checkpoint | 23 - Cutting off strands & packing recess (4)
label | Timing / Frequency - After Cutting
label | Method - Visual
label | Acceptance Criteria - Have the pre-grout well mixed as per SDS
button | Accepted | Yes,No
checkpoint | 23 - Cutting off strands & packing recess (5)
label | Timing / Frequency - After Cutting
label | Method - Visual
label | Acceptance Criteria - Have pockets and pans been sealed properly?
button | Accepted | Yes,No
section | GROUTING
checkpoint | 24 - Approval to Grout
label | Timing / Frequency - After Cut & Seal
label | Method - Visual
label | Acceptance Criteria - After final stress and prior to commencing grouting, obtain approval to grout
button | Accepted | Yes,No
checkpoint | 25 - Tests on Grout
label | Timing / Frequency - After Cut & Seal
label | Method - Visual
label | Acceptance Criteria - Test Certification provided for:
label | ○ Minimum compressive strength
label | ○ Shrinkage
label | ○ Bleeding
button | Accepted | Yes,No
label | Comments / Record Type / Reference - A.S. 3600-2009, A.S 4672.1
checkpoint | 26 - Grout Mix
label | Timing / Frequency - After Cut & Seal
label | Method - Visual
label | Acceptance Criteria - Approval for grout mix design
button | Accepted | Yes,No
checkpoint | 27 - Grouting Operations (1)
label | Timing / Frequency - After Cut & Seal
label | Method - Visual
label | Acceptance Criteria - Monitor Grouting operations are:
label | ○ carried out within specified period from approval of stressing records
label | ○ grout screened prior to pumping
label | ○ grout is free from excess water and air bubbles
label | ○ specified grout pressure is obtained
label | ○ ends sealed correctly
button | Accepted | Yes,No
checkpoint | 27 - Grouting Operations (2)
label | Timing / Frequency - After Cut & Seal
label | Method - Visual
label | Acceptance Criteria - Have all tendons been grouted properly?
button | Accepted | Yes,No
checkpoint | 27 - Grouting Operations (3)
label | Timing / Frequency - After Cut & Seal
label | Method - Visual
label | Acceptance Criteria - Have you notified the engineer for any blocked/un-grouted tendons?
button | Accepted | Yes,No
checkpoint | 28 - Final Inspection (1)
label | Timing / Frequency - On completion of works
label | Method - Visual
label | Acceptance Criteria - Area is clean and tidy
button | Accepted | Yes,No
checkpoint | 28 - Final Inspection (2)
label | Timing / Frequency - On completion of works
label | Method - Visual
label | Acceptance Criteria - Certification Provided
button | Accepted | Yes,No
holdpoint | CLIENT / TRD SIGNATURE