## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Shotcrete Walls ITP |  |  |  |  | Yes | Shotcrete Walls ITP | 1723be22-a4a1-48e5-a0a0-b22672eadde4
checkpoint-status |  |  | checkpoint | Concrete mix design confirmed
checkpoint-status |  |  | checkpoint | Soil cleaned off piles and back of the wall
checkpoint-status |  |  | checkpoint | Reinforcement installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Reinforcement drilled and epoxied (correct epoxy being used and embedment)
checkpoint-status |  |  | checkpoint | Cover to reinforcement as per specifications
checkpoint-status |  |  | checkpoint | CHS Confirmed as per drawings
text | 166184ac-4486-53cb-b50b-7e7ec5cb6ce2 |  | textbox | Thickness
text | c142b9ca-3324-5408-b2d4-0971305671e5 |  | textbox | Size Gauge
text | 3f185b23-766f-5579-897e-2e6e4f3093d9 |  | textbox | Length
checkpoint-status |  |  | checkpoint | Water Proofing installed
checkpoint-status |  |  | checkpoint | Engineer inspection completed or photos sent
label | 4528516d-5d7c-5311-8a86-ca468701b829 |  | note | Engineer sign off attached
checkpoint-status |  |  | checkpoint | Concrete mix design checked upon delivery of concrete
label | f3ad1568-dac9-55ee-97f1-0461dd7b5569 |  | note | Delivery docket attached
checkpoint-status |  |  | checkpoint | Wall trowelled, and finish completed as per architectural (or architectural sample)
checkpoint-status |  |  | checkpoint | Slab Starters for B1
checklist-flat |  |  | checklist | Rafts ITP |  |  |  |  | Yes | Rafts ITP | 6c38ff27-290e-40b8-be10-30fca27dd2ec
checkpoint-status |  |  | checkpoint | Drawing & Reference
text | 53eab1fc-bd3b-56df-9131-8017fdc09ab1 |  | textbox | Drawing & Revision Number(s)
text | e660e0ff-c867-500e-9d2a-ae7700037e3c |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
label | eed5c60a-b3c2-5a8e-a13a-a648624db45f |  | note | Surveyor to set out pads and starter positions - Check position
text | 6b323446-1ebf-513c-88ee-1bf31f86116e |  | textbox | Top blinding
text | 8c4156a3-612a-5d0d-97a4-dcd5ec6bb8de |  | textbox | Top of pad
checkpoint-status |  |  | checkpoint | Reo Placement
text | cb4c8c99-bccd-5b91-a18b-b3571a4b4264 |  | textbox | Pile Reo Length
text | f1c33ff5-5157-539f-b8d8-ae71ca15bcb7 |  | textbox | Reo Size/Configuration as per schedule
label | 88770571-9bf8-548c-9882-d17a019194e0 |  | note | Cover: 50mm
label | c509e784-7ebe-564f-83aa-87bd26badfff |  | note | Photos attached
label | 42ad9e33-30ac-5e88-9ade-0809b629d1fe |  | note | Engineers Inspection - sign off + evidence of close out attached
checkpoint-status |  |  | checkpoint | Commencement of pour
checkpoint-status |  |  | checkpoint | Concrete
text | 83beacf3-7478-5395-942e-3b24735ad739 |  | textbox | Concrete Strength
label | eff05ee2-74c3-5fbe-993f-01a467ee4ee8 |  | note | Concrete dockets/test Docket attached
checkpoint-status |  |  | checkpoint | Signed off / Handed Over
checklist-flat |  |  | checklist | Piling Records ITP |  |  |  |  | Yes | Piling Records ITP | 88f00359-caa1-4910-a484-90d5359559c7
checkpoint-status |  |  | checkpoint | Pile Drilling Sequence
text | 7a32e8f5-8a76-5daa-91c5-f9041be17872 |  | textbox | Platform Level (RL m)
text | 89fee861-f28f-5bc3-9679-6035c4be2127 |  | textbox | Diameter (mm)
text | 23f1c5cb-0c4a-5b9d-b4fa-e8001644e775 |  | textbox | Concrete Grade (MPa)
text | e9adeaab-d30a-5a34-af6b-833386efd725 |  | textbox | Drill Depth (m)
text | f8f845fc-d654-5ed8-862d-a9e0acb35ac2 |  | textbox | Socket Length (m)
text | c7ae9b29-0634-5372-b6e7-60e49dba8bec |  | textbox | Top of Concrete (RL m)
text | 37c51b4e-d6b8-5b43-a3b3-4867b1e4d370 |  | textbox | Concrete Volume (m3)
checkpoint-status |  |  | checkpoint | Reinforcement - Cage
text | 16abd667-a47b-55c5-ac8c-92720a69d449 |  | textbox | Top of Cage (RL m)
text | c46adcaa-532e-5aaa-ab6f-2a676ae9ce79 |  | textbox | Bars xNyy
text | 91ef5bb3-eaf0-5673-ab39-8edeaba66efd |  | textbox | Spiral Size (mm)
text | 4ae16294-482d-5732-ae23-93968ceaadc4 |  | textbox | Spiral Pitch (mm)
text | 6d52985e-f974-59e1-94c2-8c43dc662ddb |  | textbox | Length (m)
checkpoint-status |  |  | checkpoint | Reinforcement - Bundled Bars
text | b2de8de1-db8a-51a9-8081-cf1ef81599cd |  | textbox | Bars xNyy
text | 5633cedd-b335-5ee7-9590-e1d456101754 |  | textbox | Length (m)
checkpoint-status |  |  | checkpoint | Final
text | fac0c011-fd01-54cc-8b60-3b17ed7db96a |  | textbox | Verticality (mm / m)
text | 45bea662-a302-501b-9453-dbaa7c633622 |  | textbox | Offsets (mm / direction)
button | e585f838-ca54-59b5-bc71-288818cc0649 |  | button | Concrete Test | Yes,No
text | 970344bf-d434-5b70-b9b5-3bdce7c20c9e |  | textbox | Concrete Test Result
checkpoint-status |  |  | checkpoint | Keller Superviser Sign Off / Handover
checkpoint-status |  |  | checkpoint | Delta Group Sign Off
checklist-flat |  |  | checklist | Pad Footing - Crane Base ITP |  |  |  |  | Yes | Pad Footing - Crane Base ITP | e3640884-0a88-43a2-bf59-e64d706d4246
checkpoint-status |  |  | checkpoint | Drawing & Reference
text | 9dca0572-0906-58da-ab2e-4820e93897e0 |  | textbox | Drawing & Revision Number(s)
text | 97ca111d-2f4a-5a72-92da-797f53d0c17d |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
label | fd9db7b9-db56-5bf3-865f-4646c2ee7310 |  | note | Surveyor to set out pads and starter positions - Check position
text | 239a7781-fc75-58de-bcbe-1d9992a25baf |  | textbox | Top blinding
text | 4761f53f-ee31-5d31-b3a1-637ad4d76d0b |  | textbox | Top of pad
checkpoint-status |  |  | checkpoint | Reo Placement
text | 6125db88-08ef-59c1-829c-d17c149c287d |  | textbox | Pile Reo Length
text | c40c5bcc-d4b3-5339-9154-d681b8b55a9d |  | textbox | Reo Size/Configuration as per schedule
label | 995a93c9-cb9c-53de-b5d2-3b46597a3167 |  | note | Cover: 50mm
label | 4465554e-2cd7-59d2-887b-272763d1c9b8 |  | note | Photos attached
label | f40b12ec-70b0-51ca-b4c8-0ceeb3919f2f |  | note | Engineers Inspection - sign off + evidence of close out attached
checkpoint-status |  |  | checkpoint | Commencement of pour
checkpoint-status |  |  | checkpoint | Concrete
text | bb20ede7-838d-5664-9167-ade74b5245c3 |  | textbox | Concrete Strength
label | 8fd556f4-ace3-5ca4-92d7-795aea747687 |  | note | Concrete dockets/test Docket attached
checkpoint-status |  |  | checkpoint | Signed off / Handed Over
checklist-flat |  |  | checklist | Document / Photo Upload Checklist |  |  |  |  | Yes | Document / Photo Upload Checklist | e714b138-d277-41b3-b29b-a74230a6ec95
checkpoint-status |  |  | checkpoint | Photo / Doc Uploaded below
checklist-flat |  |  | checklist | Capping Beams ITP |  |  |  |  | Yes | Capping Beams ITP | f78a572e-25cb-4b53-b9c8-cc3ed299653f
checkpoint-status |  |  | checkpoint | Drawing & Reference
text | e4607604-ad86-5a2f-b98f-fa6318741a4e |  | textbox | Drawing & Revision Number(s)
text | 1b4c0f37-c3b7-56dd-a35b-1d3f5d330a32 |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
label | 0817ee01-ca34-506f-a3c6-0cbd6de5df78 |  | note | Surveyor to Check Position of Capping beam
text | 3b926fbc-3d1d-51f8-9628-5cc626d4bf2a |  | textbox | Blinding RL
text | 699aacf1-5742-5c7c-a53d-321ffb646d50 |  | textbox | Top of Capping Beam RL
checkpoint-status |  |  | checkpoint | Reo Placement
text | 6871c5c3-5cc1-529e-860a-3d69b6d03c4e |  | textbox | Pile Reo Length
text | e3cf83e8-75d0-531e-8be9-7c0866b48165 |  | textbox | Reo Size/Configuration as per schedule
label | 1caa5cd5-1b5e-57d5-8e9f-2af4173f516f |  | note | Cover: 50mm
label | 4ef4c811-23b4-5b6b-bccf-1dc1429a3944 |  | note | Photos attached
label | 96763aac-b542-5af2-901d-0a4dcf4b7fd7 |  | note | Engineers Inspection - sign off attached
checkpoint-status |  |  | checkpoint | Commencement of pour
label | 2ea8a982-9255-53f9-a798-28bafe445adf |  | note | OK to Pour. Shotcrete methodology attached
checkpoint-status |  |  | checkpoint | Concrete
text | 68e36568-262c-55bd-9e25-54ebd6b56277 |  | textbox | Concrete Strength
label | e0e657ae-bf46-5601-9ce5-5e993355685a |  | note | Concrete dockets/test Docket attached
checkpoint-status |  |  | checkpoint | Signed off / Handed Over