## ITP
|  |  | Inspection and Test Plan - Welding Carbon Reinforcement | [7 empty] | Document # 1145-C200-FUL-QAC-ITP-0086
[11 empty] | Revision : 00 | 2023-02-07
Client: | MRPV |  | Construction Process: | Structural Concrete - Welding |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Craigieburn Road Upgrade |  | Specifications: | VicRoads Specifications Section 204 (Dec 2015), 602 (Oct 2007), 610 (Feb 2020), 611 (Nov 2018), 613 (Jun 2017) & 614 (Jun 2017), AS5100, AS3810, AS1554.3-2014 |  | Name: | Jonathon Rock | Name: | Mustafa Kamel |  | Name: | Babak Rudd
Contract No: | 1145 |  | Structure / Component: |  |  | Position: | Project Engineer | Position: | Project Engineer |  | Position: | Quality Manager
|  |  | Location: |  |  | Date : | 2023-01-25 | Date : | 2023-01-25 |  | Date : | 2023-01-30
Lot No: | ITP-086-AX-LOT-XXX |  | Lot Details: | ITP-086-AX-LOT-XXX - Desc |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminaries - Permits
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the CRG site | PMP Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | Prior to commencing | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Project Specs. Cl.1125.02 Cl.1125.07 Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP* | Site Engineer | N/A |  | N/A
2 | Preliminary Works
2.1 | Welding Procedure Qualification |  | Prior to commencing | Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding procedure has been qualified and reviewed by the Superintendent. Submit the following documents: • Qualified welding procedure • Qualified welders record • Welding supervisor qualifications • Welding Test Plan • Welding test certificates | VicRoads CL611.14 AS1554.3 Section 4 | Document Review | Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
3 | Construction Activities
3.1 | Surface Preparation |  | Prior to Welding | Surfaces to be welded are free of corrosion & paint or any other foreign material that may effect the quality of the weld | AS1554.3 CL5.1 | Onsite Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.2 | Assembly |  | Ongoing | Where reinforcing steel is to be assembled prior to welding, it shall a) Bars are to be in the correct location b) Before welding a butt splice, bars shall be not out of alignment by more than 0.1 times the diameter up to a max misalignment of 3mm c) Parts to be spliced shall be into as close a contact as practical but not more than 0.25 times the diameter of the smaller bar but not more than 3mm d) Tack weld, shall be subject to the same initial treatment (preheating). Tack weld that will be consumed in the final weld shall be cleaned. Defective tac weld shall be removed before final weld | AS1554.3 CL5.2 | Onsite Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.3 | Preheating |  | Ongoing | Please refer to table 5.3 to determine if preheating is required Grade 500N, bar size less than 40mm pre heating is NOT required | AS1554.3 CL5.3 Table 5.3 | Onsite Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.4 | Weather Conditions |  | Ongoing | Welds shall not happen when: a) Temperature of the metal is colder than 0 degrees b) Surfaces are wet. If surface can be dried pre heating is required to 20 degrees c) During periods of high winds | AS1554.3 CL5.5 | Onsite Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
4 | Testing
4.1 | Inspection and Quality of Welds |  | As per table 611.141 | Testing shall not be less than what is shown in Table 611.141 | VicRoads 611.14 AS1554.3 | Test Reports | Signed ITP Test Reports | IP | Site Engineer | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On: (free text field)
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent