## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Louvres Installation |  |  |  |  | Yes | FC - R - Louvres Installation | 05c3f63f-c460-4f4e-b7be-597bc3d0cf80
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Louvres installation completed and acceptable
checklist-flat |  |  | checklist | Detailed Excavation |  |  |  |  | Yes | C - S - Detailed Excavation | 061041e7-d075-49a0-bc47-2ae8625b6e73
checkpoint-status |  |  | checkpoint | Grids/profiles/set out completed, clearly marked and accurate
checkpoint-status |  |  | checkpoint | Excavation depths and locations confirmed prior to detailed excavation commencing
checkpoint-status |  |  | checkpoint | Services (overhead / below ground) considered and isolated where required before excavation commences
checkpoint-status |  |  | checkpoint | Approval given to commence detailed excavation
checkpoint-status |  |  | checkpoint | Excavation checked, correct and approved
boolean | d882e39b-b5f1-5ad6-aff1-3acc8c04f71d |  | tickbox | Location accurate
boolean | 95dff6db-be15-541f-aca6-b4a7cc6db92a |  | tickbox | Depth correct (allow for site concrete if required)
boolean | d7b78cd8-6219-5dcf-b65d-cc587871622d |  | tickbox | Width correct (allow for boxing if required)
checkpoint-status |  |  | checkpoint | Placement of Geotextile (2 photos required)
checkpoint-status |  |  | checkpoint | Placement of hardfill
checkpoint-status |  |  | checkpoint | Placement of Geogrid (2 photos)
checkpoint-status |  |  | checkpoint | NDM test and report (supporting documents incl. photos)
checkpoint-status |  |  | checkpoint | Completed level of hardfill (completion NDM test with report and supporting documents (incl. photos) and uploaded into QA system)
checkpoint-status |  |  | checkpoint | Any additional layer of hardfill (300mm) requires an NDM test (report and supporting documents (incl. photos) sent uploaded into QA system
holdpoint |  |  | signoff | Sand blinding and check final RL. (completion required to handover to the next stage-townhouses only)
checkpoint-status |  |  | checkpoint | Excavation for services is completed and accurate
checkpoint-status |  |  | checkpoint | Excess material cleaned up and removed as required
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Detailed Excavation |  |  |  |  | Yes | C - R - Detailed Excavation | 0625c869-cdab-4c5f-b197-0d8507d7859b
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Detailed excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | Waterproofing |  |  |  |  | Yes | F - R - Waterproofing | 08dc60c5-6a39-4b5b-b39f-80ba78733262
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All waterproofing works completed as per the specifications
checklist-flat |  |  | checklist | Connection to public systems |  |  |  |  | Yes | C - R - Connection to public systems | 0b538e9b-e241-4e79-9515-2d5a43a1f32e
checkpoint-status |  |  | checkpoint | Approval to connect given by relevant Authority (AC, Watercare, Vector, etc)
checkpoint-status |  |  | checkpoint | Area signed off by engineer
checkpoint-status |  |  | checkpoint | Pipe line connected in accordance with requirements, checked and accurate
checklist-flat |  |  | checklist | Roof structure - Timber Trusses |  |  |  |  | Yes | ST - R - Roof structure - Timber Trusses | 0cbcd340-92c2-4296-a9a7-d96227b6d861
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All timber trusses correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | Fitout |  |  |  |  | Yes | ITP - R - Fitout (per townhouse unit) | 0dba0630-92af-4d45-8567-a0821ea07951
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Finishing completed, meets benchmark standard. Refer separate checklist. Full response to the items below needed.
button | 7ec6fe0e-9c2e-5dbb-aab9-1419364a0ba3 |  | button | Hardware/Fittings | Yes, Reworked, N/A
button | 89981d82-009b-5acc-a8c2-9382cc4e95ba |  | button | Plumbing completed and acceptable | Yes, Reworked, N/A
button | 24f0a58a-bec1-5ab4-af28-185dcfdb0b5a |  | button | Electrical completed and acceptable | Yes, Reworked, N/A
button | 4b6f6b4c-84ec-5757-b550-ea0e88971c95 |  | button | Joinery/Doors completed and acceptable | Yes, Reworked, N/A
button | 3131ac14-8cf5-5747-8756-80fc323484a8 |  | button | Decorating completed and acceptable | Yes, Reworked, N/A
button | fe9ebfaf-ae50-52c0-a13b-97d9b10cdf3f |  | button | Flooring completed and acceptable | Yes, Reworked, N/A
button | f2443d5b-d155-5f3b-aae4-266d0290156c |  | button | Other works completed (inc. client extras) and acceptable, state below. | Yes, Reworked, N/A
text | 086745be-8ee9-5594-bc6c-18eaa650b7d8 |  | textbox | Details:
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
holdpoint |  |  | signoff | Raise remedial as required.
checklist-flat |  |  | checklist | Punch Windows Frames (unglazed) |  |  |  |  | Yes | FC - R - Punch Windows Frames (unglazed) | 10d09cda-acf3-481b-9c0d-c87575b323ea
checkpoint-no-status |  |  | checkpoint | Window # / Elevation / Level
text | 11d7d579-5e62-5e76-a2ba-8a91e9b8b85b |  | textbox | Window # / Elevation / Level
checkpoint-status |  |  | checkpoint | Installation (By others) completed as per detail Y/N
checkpoint-status |  |  | checkpoint | Check the joinery is free from damage
checkpoint-status |  |  | checkpoint | All glazing beads attached to Frame PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Check Frame number PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Inspection of Backing rubber - no damage and continuous around perimeter
checkpoint-status |  |  | checkpoint | Glazing Blocks inserted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Glass units installed (Glass sticker) PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing Beads fitted correctly PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Correct Wedge Rubber installed and rubbered off as per WGANZ guidelines
checkpoint-status |  |  | checkpoint | Glass Stickers removed
checkpoint-status |  |  | checkpoint | Trade Clean
checkpoint-status |  |  | checkpoint | Final Inspection PHOTO REQUIRED
checkpoint-status |  |  | checkpoint | Glazing complete for handover to Ryman Healthcare
holdpoint |  |  | signoff | Raise Remedial
checklist-flat |  |  | checklist | Roof structure - Steel |  |  |  |  | Yes | ST - R - Roof structure - Steel | 15cd17be-a71b-4def-9fec-90d7be0a40c5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | Passive fire |  |  |  |  | Yes | FC - R - Passive fire | 15d99ec9-cb63-4506-bfa0-499be8994911
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Passive Fire works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Concrete Pour |  |  |  |  | Yes | ST - R - Concrete Pour | 18dcf1f2-56cd-4077-a15c-81942a482c45
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
checkpoint-status |  |  | checkpoint | Concrete strength test reports attached and required concrete strength achieved
checkpoint-status |  |  | checkpoint | Mill certificate reviewed, attached and approved
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete pour completed and acceptable
checklist-flat |  |  | checklist | Observation/Remedial: |  |  |  |  | Yes | Add Observation / Remedial | 2098a773-c2ed-4449-8527-11903a5db44a
checkpoint-status |  |  | checkpoint | Observation/Remedial Status
text | 4095cc9e-08a9-5a52-a71d-b20e000941e5 |  | textbox | Location of Remedial
text | 6cf9e181-7d13-52af-bb3a-7e18eb62b79c |  | textbox | Observation/Remedial Description
text | b57e1ea4-e54b-5e0a-9b38-16928aacef1b |  | textbox | Action Required
holdpoint |  |  | signoff | Request Signoff on Remedial
checklist-flat |  |  | checklist | Air conditioning |  |  |  |  | Yes | FC - R - Air conditioning | 23b9db20-a6da-4234-b563-9b12e09a36f6
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Air conditioning works completed and acceptable
checklist-flat |  |  | checklist | ST - R - Precast beam installation |  |  |  |  | Yes | ST - R - Precast beam installation | 256fb1df-d16b-440b-8797-5899953701a7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | Structural Consent |  |  |  |  | Yes | CST - R - Structural Consent | 26b653e2-70e8-46a6-a28d-933a86ca97e2
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | 76a8bc02-e00a-5276-ab8f-aa9886127280 |  | tickbox | Producer Statement Design(PS1): Prestressed beams, walls, stairs, columns and floor units
boolean | 15015c3a-c45a-5533-a98a-bf67f217c3cf |  | tickbox | Producer Statement Construction(PS3): Prestressed beams, walls, stairs, columns and floor units
boolean | 7230e69c-3cca-5de9-84ed-11e091f31d3c |  | tickbox | Producer Statement Review(PS4): Prestressed beams, walls, stairs, columns and floor units
checkpoint-status |  |  | checkpoint | Structural Steel
boolean | 7cf9a693-ca9f-5541-b30a-c93902b4498c |  | tickbox | Producer Statement Construction(PS3): Corrosion Protection
boolean | 446ae770-426a-539c-a95f-ec0f74fc7379 |  | tickbox | ITPs approved by structural engineer
boolean | 122bde50-2470-595a-b07a-822cd0b44b02 |  | tickbox | weld inspection and test records
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | ed6cfe58-3808-57ce-893a-57692a6c4fbc |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | 9b55a37a-082f-5ce8-abea-015360f6f838 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | 40dd28eb-4734-564f-bbd1-4dd3f190a5f7 |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Trusses
boolean | ba021b97-c987-531c-b69e-242d329762e0 |  | tickbox | Producer Statement Design(PS1): Layout Plan for timber roof trusses
boolean | 23942125-99be-507c-8ecd-0b851d78114c |  | tickbox | Producer Statement Construction(PS3): for timber roof trusses
checkpoint-status |  |  | checkpoint | Construction Review (Structural)
boolean | 710e8a8d-8891-5bf2-9ca8-ab86bce6a8c5 |  | tickbox | Producer Statement Construction Review(PS4): Certification of work in accordance with design, drawings, specifications and material codes
boolean | 7887a019-7a1e-5c39-8472-a8751e7de23c |  | tickbox | Producer Statement Construction Review(PS4): excavation near boundary and site observation notes
boolean | 30af5094-ea2c-5220-a8f2-061900112602 |  | tickbox | Producer Statement Construction Review(PS4): Raft slab and site observation notes
boolean | 01fe5f9f-51b0-5c49-b224-642c7887257c |  | tickbox | Producer Statement Construction Review(PS4): Swimming pool and site observation notes
boolean | d780ae4f-8daa-57eb-820b-c7f1b5d95b39 |  | tickbox | Producer Statement Construction Review(PS4): Type A or B masonry and site observation notes
boolean | 79bff89d-a5d3-5aeb-8c42-703fdafd648a |  | tickbox | Producer Statement Construction Review(PS4): Underpinning and site observation notes
boolean | c4b400eb-58cd-5c6e-9da2-69f4bcceb034 |  | tickbox | Producer Statement Construction Review(PS4): Structural steel including connections and site observation notes
boolean | 7359e789-af83-5a94-b7b4-062f6405f974 |  | tickbox | Producer Statement Construction Review(PS4): Timber pole retaining wall and site observation notes
boolean | 1c9e0e59-e35a-50a3-b506-bb2564c6e2b4 |  | tickbox | Producer Statement Construction Review(PS4): reinforced concrete foundations and site observation notes
boolean | 35d2cc22-3f53-5522-a70c-c6d79f36955d |  | tickbox | Producer Statement Construction Review(PS4): Suspended concrete slab and site observation notes
boolean | 45de41a7-502f-53ef-829e-3f9837dbfdcb |  | tickbox | Producer Statement Construction Review(PS4): Precast elements and site observation notes
boolean | 7575fd8c-1af1-53a2-abcd-ae13bcc7ad4d |  | tickbox | Structural engineer's variations and contractor advice notes
checkpoint-status |  |  | checkpoint | Surveyor certificate for finished floor levels
checklist-flat |  |  | checklist | Water Test |  |  |  |  | Yes | FC - R - Water Test | 281b4881-8228-4087-a0ed-11d28b071751
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Water Test completed and acceptable
checklist-flat |  |  | checklist | External Plaster - Nibs & Beams |  |  |  |  | Yes | FC - R - External Plaster - Nibs & Beams | 29753e92-48c9-47ce-9bfa-59b0f9f49e5c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | External Plaster works for Nibs & Beams completed and acceptable
checklist-flat |  |  | checklist | Handover |  |  |  |  | Yes | H - R - Handover | 2afc7abc-b021-482c-9046-f0d765854a1b
checkpoint-status |  |  | checkpoint | Hardware/Fittings
checkpoint-status |  |  | checkpoint | Plumbing
checkpoint-status |  |  | checkpoint | Electrical
checkpoint-status |  |  | checkpoint | Joinery/Doors
checkpoint-status |  |  | checkpoint | Decorating
checkpoint-status |  |  | checkpoint | Flooring
checkpoint-status |  |  | checkpoint | Other
checkpoint-status |  |  | checkpoint | Upload Related Ryman Fitout quality inspection record (QT-012)
checklist-flat |  |  | checklist | Project Manager Handover to Operations |  |  |  |  | Yes | ITP - R - Project Manager Handover to Operations (per townhouse unit) | 2bdc96b4-876a-42b3-a008-212f2afc9d7c
checkpoint-status |  |  | checkpoint | No outstanding defects/snag list items
holdpoint |  |  | signoff | Raise remedial as required.
checkpoint-status |  |  | checkpoint | Chattels confirmed as operational
checkpoint-status |  |  | checkpoint | Chattel manuals provided.
checkpoint-status |  |  | checkpoint | Unit meets benchmark standards and expectations
checkpoint-status |  |  | checkpoint | Resident "Welcome Letter" completed by PM and left in property.
checkpoint-status |  |  | checkpoint | Formal handover to Sales/Operations conducted by PM.
checklist-sectioned |  |  | checklist | SVR # / Date: |  |  |  |  | Yes | Add Consultant Site Visit Report | 2fead0ea-ac38-4c08-96aa-2cd6cf905296
checkpoint-group |  |  | section | Site Visit Details
checkpoint-no-status |  |  | checkpoint | Site Details
text | 9ff3bded-74c6-4232-b35b-2d75fb97f396 |  | textbox | Area of site visited:
text | 918b5269-465a-4c8e-868d-623bda2919ab |  | textbox | Work element monitored / purpose of visit:
text | 0100c314-6ea6-4022-9fc7-e89d7fbf9603 |  | textbox | Date of site visit:
text | eefff17c-65a9-4c08-bc71-2463e071ec06 |  | textbox | Time on site (include start and end times):
text | aa5dbfb2-391c-4b01-8f4d-3b7115fbfdef |  | textbox | Weather conditions:
text | 299ebcf9-b4a0-4cde-8543-93464580b42b |  | textbox | Report prepared by:
text | a10ff5b4-7560-437a-944e-486c179be710 |  | textbox | All personnel present during inspection:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | eb38cf50-ef40-4ddc-8024-f2840f5cd941 |  | textbox | Building Consent Number:
text | 74e9724e-9c3b-4116-82c1-ad3d71297d01 |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
folder-normal |  | Not allowed as a child of checklist-sectioned. | folder-normal | Observations / Remedials
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | 4296f55a-75cd-456a-a2be-1f143551249c |  | note | Select Pass if works accepted or Fail if further information required and/or reinspection required to defective elements
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Symonite Alucobond Cladding System |  |  |  |  | Yes | FC - R - Symonite Alucobond Cladding System | 36dd8162-e0a1-4768-afa6-13beafb731dc
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Symonite Alucobond Cladding works completed and acceptable
checklist-flat |  |  | checklist | Electrical - Distribution Boards |  |  |  |  | Yes | S - R - Electrical - Distribution Boards | 3786b1b5-a5bf-4a65-acd9-a72c697a78a7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | Envelope Penetrations |  |  |  |  | Yes | FC - R - Envelope Penetrations | 42b45877-1541-42e7-8985-8dc2f53d318a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Envelope Penetrations completed and acceptable
checklist-flat |  |  | checklist | Structural Steel Installation |  |  |  |  | Yes | ST - R - Structural Steel Installation | 4322e70c-23e5-40e3-9223-50a1f99850f9
checkpoint-status |  |  | checkpoint | Chemical anchor proof tests conducted on the sample selected by the MV Engineer
boolean | e5fc64ea-d330-5276-b418-6de6e8d9cccb |  | tickbox | Chemical anchors are tested to 0.7xdesign load
boolean | d32b9f42-f64a-5ccf-b898-ddac8baef3b9 |  | tickbox | The test load of the bar is provided by the MV Engineer
boolean | f025587a-d3c1-594f-bd4e-a129be4e58a3 |  | tickbox | Proof load tests maintained for a minimum of 30 seconds
boolean | 77600ae0-454f-5869-bf6d-e3d66a634041 |  | tickbox | The load did not drop more than 10% during the testing
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Mechanical anchor testing conducted on the sample selected by the MV Engineer and witnessed by the MV Engineer
boolean | 563461a2-61c4-5d2b-8d9c-2169837e0d72 |  | tickbox | For trubolt or similar anchors the maximum tightening torque is reviewed
checkpoint-status |  |  | checkpoint | If the proof of tests show failure of the anchors, installation of anchors should stop, cause of failure investigated and installation methodology should be reviewed. If failure is recorded, the minimum test sample shall be increased to 6 specimens or 5% of the total relevant anchor population, whichever is greater.
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All structural steel correctly installed in respective area and acceptable
checklist-flat |  |  | checklist | Service Trenches - Common Service Trenches |  |  |  |  | Yes | C - R - Service Trenches - Common Service Trenches | 43c97c74-69cf-44d3-b4c8-510729dfe3cd
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Common service trench works completed as per the specifications
checklist-flat |  |  | checklist | Windows and Sliders |  |  |  |  | Yes | FC - R - Windows and Sliders | 4415cf7b-fb2e-4c95-a455-315f54297894
checkpoint-status |  |  | checkpoint | Check clearance around opening min 6mm/ max 18mm
checkpoint-status |  |  | checkpoint | Packers to be correctly used and set back to allow continuous air seal
checkpoint-status |  |  | checkpoint | Check air seal is provided at the rear of the window reveal
holdpoint |  |  | signoff | Raise remedial/ request signoff
checkpoint-status |  |  | checkpoint | Window and slider installation completed and acceptable
checklist-flat |  |  | checklist | Crane Piling |  |  |  |  | Yes | F - R - Crane Piling | 45151990-74e2-4c8a-9b9b-8a783ea60531
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Crane Piling completed and acceptable
checklist-flat |  |  | checklist | Precast Wall Bracket Installation |  |  |  |  | Yes | ST - R - Precast Wall Bracket Installation | 45d85181-15d5-419e-9e8b-3a34dd825ad9
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Bracket Installation completed and acceptable
checklist-flat |  |  | checklist | Piling |  |  |  |  | Yes | F - R - Piling | 4695cc66-9cc9-4853-ab9d-249ce1b0e67c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Piling completed as per the specifications
checklist-flat |  |  | checklist | Stair Installation |  |  |  |  | Yes | ST - R - Stair Installation | 47a4cea2-b1e4-4386-9a42-26eca303844c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stair Installation completed and acceptable
checklist-flat |  |  | checklist | Manhole Installation |  |  |  |  | Yes | C - R - Manhole Installation | 47bd601e-cce3-4eb5-8f6d-80d88585eef2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Manhole Installation completed as per the specifications
checklist-flat |  |  | checklist | Precast Shell Beam Lintel Installation |  |  |  |  | Yes | ST - R - Precast Shell Beam Lintel Installation | 49274801-a227-4055-8ad9-5176578a65aa
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Shell Beam Lintel Installation completed and acceptable
checklist-flat |  |  | checklist | Precast Spandrel Panel Installation |  |  |  |  | Yes | ST - R - Precast Spandrel Panel Installation | 4aab362b-b70b-4300-bbc5-03e8d44aed7d
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Spandrel Panel Installation completed and acceptable
checklist-sectioned |  |  | checklist | ST - R - Concrete Pour Planning |  |  |  |  | Yes | ST - R - Concrete Pour Planning | 4b38bb0a-00ea-4698-b820-7019660961a1
checkpoint-group |  |  | section | POUR DETAILS
checkpoint-no-status |  |  | checkpoint | POUR DETAILS
text | af6ec2ba-bf97-57d9-9ddc-dd42616aae1a |  | textbox | Area to be poured:
text | aa1ebefd-b82b-56a1-9955-4d2358b18bbc |  | textbox | Date of pour:
button | c2683a5a-865a-550a-96f6-caf58576420e |  | button | Type of pour: | Rib Raft, Reinforced
checkpoint-group |  |  | section | CONCRETE SUPPLIER SPECIFICS
checkpoint-no-status |  |  | checkpoint | CONCRETE SUPPLIER SPECIFICS
text | e7fbfb5d-5bf9-543d-b8aa-3acaafb0bf37 |  | textbox | Specified concrete strength:
text | 6727d7ea-ed25-5e40-9a45-ef654c11d464 |  | textbox | Concrete strength ordered:
text | 4a8d9271-f128-55f8-b77e-f20513cedae6 |  | textbox | Concrete quantity ordered:
checkpoint-status |  |  | checkpoint | Test blocks booked
checkpoint-group |  |  | section | METHODOLOGY AGREEMENT
checkpoint-status |  |  | checkpoint | Sequence
checkpoint-status |  |  | checkpoint | Placement
checkpoint-status |  |  | checkpoint | Erection
checkpoint-status |  |  | checkpoint | Assembly
checkpoint-status |  |  | checkpoint | Temporary works
checkpoint-status |  |  | checkpoint | PM Sign off to receive inspection results - concrete pour planning inspections completed by Foreman. Pass this checkpoint once signed.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO PROJECT MANAGER TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Townhouse Block Build |  |  |  |  | Yes | ITP - R - Townhouse Block Build (per townhouse block) | 4beffe8d-e92d-4939-a28e-8fa8db8ba847
checkpoint-group |  |  | section | Structure/Framing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Timber Framing installed
checkpoint-status |  |  | checkpoint | Council pre-clad inspection completed and approved. Note date of inspection in comments
button | 778450e8-dce4-5160-9304-4b246a6c4da3 |  | button | Note remedial work needed | None, Minor, Major
text | 9948fe6a-cd59-5a69-b0e7-eaeeaca376f7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Roofing
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Verify materials supplied to site (material and fixings) are as specified or approved samples
checkpoint-status |  |  | checkpoint | Construction complies with specifications
checkpoint-status |  |  | checkpoint | Obtain and upload all performance and authority certificates as required by specification or statutory regulations.
checkpoint-status |  |  | checkpoint | Council Pre-Roof Inspection completed and passed
button | a26af162-40cf-5c56-a6bc-59dfa23fc2a8 |  | button | Note remedial work needed | None, Minor, Major
text | 91114399-025d-5956-b1d0-2bc4e67b5d0f |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Façade
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Envelope/Watertightness Completed (requirements below)
button | b5a10b94-50cb-5969-b2f7-8d3667a662e2 |  | button | Ecoply Board installed | Yes, Reworked, N/A
button | f7d00e46-713b-5c9b-8030-2c764bb4e693 |  | button | Lintels installed | Yes, Reworked, N/A
button | c026c06e-0397-544a-9773-93f632ede435 |  | button | Tapes and VaproShield installed. | Yes, Reworked, N/A
button | 3da4a7f8-37c1-58ad-8b88-a5d8a1dcc09f |  | button | Windows and Sliders installed | Yes, Reworked, N/A
button | 0ee80d1b-8c1e-503a-ade3-0965e27d5214 |  | button | Flashing installed | Yes, Reworked, N/A
button | 8abc1da4-c89d-5956-835b-04d0bc94cad2 |  | button | Envelope Penetrations completed | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Council pre-wrap inspection completed and passed
button | 4f29ff0a-4d0a-55e4-8f9d-aca0b401272d |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council brickwork 'half-high' inspection completed and acceptable
button | 0670cfc6-0fe8-5aef-ba8a-7806016c5515 |  | button | Note remedial work needed | None, Minor, Major
text | d10ecf7a-e750-5236-8a37-c381f3c6fb0f |  | textbox | Describe cladding type:
button | ac752167-ab84-5ae2-855d-bea409c97808 |  | button | Brick Works completed | Yes, Reworked, N/A
button | f21f07d3-ba25-52f7-b587-26b4d39dc9a1 |  | button | STO Poly Plaster completed | Yes, Reworked, N/A
text | e9a0a440-c827-58ca-ae47-5993cd514f40 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pre-Line
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Pre-line completed
button | d98d0f32-783f-5c3c-9739-6db4e866aeac |  | button | Timber frame installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Nogs Installed as below and comply
button | 83fcca6e-1cf5-5434-8329-848cc6868ffd |  | button | Steel Stud frame installation completed and acceptable | Yes, Reworked, N/A
button | 68d6ea6a-ecee-51a2-8878-a87e67864ff0 |  | button | Electrical First Fix completed and acceptable | Yes, Reworked, N/A
button | 22b81049-60eb-5085-a500-297cc817cc0a |  | button | Plumbing First Fix completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Insulation installation completed and acceptable
checkpoint-status |  |  | checkpoint | Security, Comms and Data First Fix completed and acceptable
button | 00da87a7-4529-55a5-8b60-e1b25f8421ae |  | button | HVAC First Fix completed and acceptable | Yes, Reworked, N/A
button | eff83f07-bc54-5c55-9aa9-c84104581c7c |  | button | Fire Security First Fix completed and acceptable | Yes, Reworked, N/A
button | 7eaf7d98-2552-50ec-9f5a-bf3e204ded88 |  | button | Underfloor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, Reworked, N/A
button | a215fd3e-b0ed-56fa-a4e5-8ff42a29e615 |  | button | Kitchen extract First Fix completed and acceptable | Yes, Reworked, N/A
button | ecb2ead4-f601-5b2d-b9de-7f4bc16c42cf |  | button | Passive fire installation completed and acceptable | Yes, Reworked, N/A
button | b58351c5-850e-51fb-bfba-11cff1470721 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Pre-line plumbing external inspections completed and uploaded. Any remedial work signed off.
button | 2758dd95-11ec-5ede-b9d2-430f42f80f5e |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Pre-line building external inspections completed and uploaded. Any remedial work signed off.
button | a3ad6da4-8b5b-5cca-b051-c44bb4c2af78 |  | button | Note remedial work needed | None, Minor, Major
text | 5c3b8ed4-afdc-530b-bdbb-32b199e63eee |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 60033d76-cbc4-5d41-b811-da11bcd0c3d8 |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | Pipe Laying - Water |  |  |  |  | Yes | C - S - Pipe Laying - Water | 4c669197-7e52-412a-a128-b49bb1089d24
checkpoint-status |  |  | checkpoint | Set-out completed, checked and accurate
checkpoint-status |  |  | checkpoint | Excavation location and depth accurate
checkpoint-status |  |  | checkpoint | Ground conditions checked and acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct
checkpoint-status |  |  | checkpoint | Correct pipe (size, material & class) laid to specified level, grade and jointed as specified
checkpoint-status |  |  | checkpoint | Pipe laying completed as per the specifications
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-sectioned |  |  | checklist | Site Visit Report: |  |  |  |  | Yes | I - C - Site Visit Report | 5198f4dd-46b1-47a2-a0a7-1d39275a664c
checkpoint-group |  |  | section | Site Visit Details
checkpoint-no-status |  |  | checkpoint | Site Details
text | 506694dc-7d26-582f-8c8b-443ab7465b99 |  | textbox | Area of site visited:
text | ae5a27c3-c6aa-5a37-8261-f9744cb57713 |  | textbox | Work element monitored / purpose of visit:
text | c3e18f4f-7dfb-58c9-8c9d-7476d610b959 |  | textbox | Date of site visit:
text | 97934ec8-4896-5467-a8c0-3d4008b139b0 |  | textbox | Time on site (include start and end times):
text | 383327cf-ec8c-5f2e-9055-2fb798ae83de |  | textbox | Weather conditions:
text | 521ffd86-f63f-5781-8ca1-17fbcb771907 |  | textbox | Report prepared by:
text | 02482c33-9e25-5e82-acd7-f4c7ef397019 |  | textbox | Additional personnel accompanying:
checkpoint-status |  |  | checkpoint | Consented drawings have been followed
text | 9175b57c-d29d-550d-b8e8-75c9deffb26e |  | textbox | Building Consent Number:
text | a64da548-9cfe-5114-8ed1-30ff39c1d50a |  | textbox | Drawing & Revision Number(s):
checkpoint-status |  |  | checkpoint | Health and Safety acceptable
checkpoint-group |  |  | section | Site Report Summary/Closeout
checkpoint-status |  |  | checkpoint | Works accepted and may proceed
label | 1de6dba1-a846-5608-ad17-1d0622aa0911 |  | note | Select Pass if works accepted or Fail if reinspection required to defective elements
boolean | f390e71d-ed58-5a83-a242-6709c361eb0a |  | tickbox | Report attached or remedials summarised below
text | 74ed08e2-bd4a-5c53-9cd2-579f0135e4de |  | textbox | Remedial(s)
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Pipe Laying - Wastewater |  |  |  |  | Yes | C - R - Pipe Laying - Wastewater | 5a4f11df-b2d5-4e44-887a-96ae9e112032
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Wastewater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | Exterior Tiling |  |  |  |  | Yes | FC - R - Exterior Tiling | 5d2acf4f-1c03-4665-919c-176d81b092db
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Exterior Tiling works completed and acceptable
checklist-flat |  |  | checklist | Underground services |  |  |  |  | Yes | F - R - Underground services | 60c67764-7819-4b19-8e62-3ff2d3829665
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underground services installation completed as per the specifications
checklist-flat |  |  | checklist | Precast Edge Beams Installation |  |  |  |  | Yes | ST - R - Precast Edge Beams Installation | 62c6cda4-c0e4-49c5-ba01-d40b095026dc
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | Fire door installation |  |  |  |  | Yes | POST - R - Fire door installation | 632210f2-de6e-44c2-98b1-fda3c53f141a
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | PRE - R - Fire Penetration |  |  |  |  | Yes | PRE - R - Fire Penetration | 65bee8bc-4cce-4d37-86b3-885a00d3634f
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | Fire Consent |  |  |  |  | Yes | CST - R - Fire Consent | 65ce718c-7c54-48fc-949e-524675a2b012
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 68570193-5281-5fd1-a5a1-4e8992e81278 |  | tickbox | Electrical compliance and safety certificate
boolean | 0f4043b7-24fb-546f-9ac9-33b69d81b5de |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Fire rated (Intumescent) Coatings to Structural Steel
boolean | 97910a6a-e896-55b7-be62-a752624c5d07 |  | tickbox | Producer Statement Construction(PS3 - AC2334): Intumescent coatings to structural steel from approved applicator
boolean | fdfa1db4-9118-5a45-80b4-c2d460b118a9 |  | tickbox | Suppliers material schedule - products used and thicknesses applied
boolean | e3468e16-0c68-58e6-81af-c6e5eeef4e7a |  | tickbox | Floor plan of intumescent coating locations
checkpoint-status |  |  | checkpoint | Fire Rated and Stopping Systems
boolean | aef7b5fa-affe-5d4d-bbd6-54523713d06a |  | tickbox | Producer Statement Construction(PS3): Fire stopping of penetrations(collars, wraps, sealants) for Plumbing, Mechanical, Ventilation and Communication services
boolean | 1477d6f5-8a3f-5e2f-9d8c-5e323d338451 |  | tickbox | Fire rated penetration Schedule: Plumbing, Mechanical, Ventilation and Communication Services
boolean | f7fbd412-1b6d-594c-86bc-2abe6bf54697 |  | tickbox | As built plans: penetrations
boolean | f0ed6e98-20a9-5c0e-a0c1-53cd6083a8b4 |  | tickbox | Producer Statement Construction(PS3): Installed fire rated constructions; fire rated walls, partitions, floors and ceilings to show fire rating
boolean | fc114e6e-2819-5ba5-9d9d-cf9e4f4c2080 |  | tickbox | Fire door declaration documentation and register of door sets by the manufacturer (refer NZS4520: 2010 clause 6.4.3
checkpoint-status |  |  | checkpoint | Sprinkler systems
boolean | 8dff0d44-f8b3-5f1c-8ad6-0100e88dcd70 |  | tickbox | Producer Statement Construction(PS3): Automatic sprinkler system (in compliance with NZS4514:2013)
boolean | 3d2bafb2-e41d-5dba-b45e-288489246361 |  | tickbox | Accredited inspection company's automatic sprinkler system certification confirming compliance with NZS4514:2013
boolean | e5b8381f-67c5-5385-82bf-fcf29b420511 |  | tickbox | As built documentation; sprinkler block plan, equipment manufacture register
checkpoint-status |  |  | checkpoint | Manual and Automatic fire alarms
boolean | 42886e59-eee3-56cc-b8d3-e1262025376f |  | tickbox | Producer Statement construction(PS3): Manual/automatic fire alarm in compliance with NZS4512:2010
boolean | fd98ffd1-7611-5f52-b187-11eecc199cb9 |  | tickbox | Accredited inspection company's fire alarm certification confirming compliance with NZS4512:2010 (new system)
boolean | a076a0c7-cbb1-5b7a-a151-09d275068d7c |  | tickbox | As built documentation; zone index plan, operation manual and maintenance manual
checkpoint-status |  |  | checkpoint | Riser Mains for use by fire services
boolean | 67f32333-6ca4-5cf5-944c-978b5be8d1fe |  | tickbox | Producer Statement Construction(PS3): fire hydrant riser confirming compliance with NZS4510:2008
boolean | c22e1232-8383-501b-bd7a-c5d77b6a31c3 |  | tickbox | Certificate of Compliance or Verification Report for fire hydrant riser confirming compliance with NZS4510:2008
boolean | 4ceffbd2-d1fd-578b-87f3-9b723d1630fb |  | tickbox | As built documentation; fire hydrant schematic as built
checkpoint-status |  |  | checkpoint | Emergency Lighting systems
boolean | 83bee471-8546-50be-97aa-9a7577e79317 |  | tickbox | Producer Statement Construction(PS3): Emergency lighting from electrical contractor confirming compliance with NZBC F6
boolean | b9623740-0ddd-57fd-985c-652b7b168a4e |  | tickbox | Producer Statement Review(PS4): Emergency Lighting from council approved electrical engineer confirming compliance with NZBC F6
boolean | 590e70e0-f4de-5eda-9e03-5f4e394741d1 |  | tickbox | Duration test results for emergency light fitting from electrical contractor or IQP
boolean | dbe696db-4930-5865-81ea-6ba5ef0a0625 |  | tickbox | Lux test results for the emergency lighting system
boolean | 86f7926d-4d27-5cde-9ae9-875defcf1752 |  | tickbox | As built plan with model of systems installed
boolean | af08c8da-1ddd-5b18-889a-785ba98fbd3a |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Fire separation that forms part of the means of escape from fire
boolean | 039f8056-9572-55eb-b058-dc2dad3b5db5 |  | tickbox | As built plans confirming final location of Fire separation that forms part of the means of escape from fire
checkpoint-status |  |  | checkpoint | Smoke separation that forms part of the means of escape from fire
boolean | 6d4881ac-df70-5c0f-bdc3-67bbb49dd91b |  | tickbox | As built plans confirming final location of walls forming a protected path in a building, smoke resistant lift lobby, smoke stop door, smoke cell
checkpoint-status |  |  | checkpoint | interfaced fire or smoke doors on windows
boolean | 8452aabf-eb74-5ccb-92f4-f626f0dcf066 |  | tickbox | Producer Statement Construction(PS3): installation of magnetic door holders
boolean | a8cc3068-a275-5f28-b04b-46d22c1e409e |  | tickbox | As built documentation; location of systems, the make of the systems, operation manuals and maintenance manuals
checkpoint-status |  |  | checkpoint | final exits
boolean | 21bbdf25-1422-5c1f-90fc-6e7b56be8ff4 |  | tickbox | as built plans confirming location of final exit (include info on if any doors are automatic or access controlled)
checkpoint-status |  |  | checkpoint | Signs for all systems
boolean | e9aa213e-5175-5efc-96a3-1b258c7dfdbd |  | tickbox | SS 1/1: Sign showing maximum storage heights
boolean | 35e2dec4-29be-506c-95dd-d5fa48ae7185 |  | tickbox | SS 2/1: Sign showing how to operate a fire alarm call point
boolean | 908b5c10-2d6a-53e9-adbb-b698c089de2a |  | tickbox | SS 3/1: Sign showing location of accessible automatic
boolean | 645218ec-6b89-5557-9843-09e91b81895f |  | tickbox | SS 3/2: Sign showing and automatic closing fire or smoke door
boolean | ef6b6b81-0495-51f7-98a6-3768a2b0e7c8 |  | tickbox | SS 3/2: Sign showing location of an emergency door release on access control doors
boolean | 59022784-d234-5b22-ad7c-52547037fbb0 |  | tickbox | SS 8/1: Sign showing location of accessible lift
boolean | def1904e-d40c-58d0-9dfe-0e1bc63f8f7a |  | tickbox | Sign showing not to use the lift in event of fire
boolean | 1eb68642-2046-535e-b839-cdab9674fe34 |  | tickbox | Sign showing lift load ratings
boolean | d64c0f27-7d6b-5cd5-91c1-6544579b00c3 |  | tickbox | SS 8/3: Sign showing hazards to escalators and moving walks
checkpoint-status |  |  | checkpoint | Fire safety construction review
boolean | 21b259d4-5c5f-5fc1-aa8e-228c16170dd8 |  | tickbox | Producer Statement Review(PS4): council approved fire engineer to confirm systems conform with the relevant NZBC clauses and fire reports
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | Anchor Points - Anchor Point Installation |  |  |  |  | Yes | FC - R - Anchor Points - Anchor Point Installation | 68b2092b-83fb-4b0d-9113-f17503839384
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Anchor point installation completed and acceptable
checklist-flat |  |  | checklist | Piling Consent |  |  |  |  | Yes | CST - R - Piling Consent | 6cb5273f-ed52-48ba-a35b-1b1a0193a0a3
checkpoint-status |  |  | checkpoint | Record of Title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Construction Review
boolean | 1a69ee3d-59c8-53f3-acec-27c3baf7f5ca |  | tickbox | Producer Statement Review(PS4): Geotechnical
boolean | e92b3363-c177-5ea7-867d-2ff365967ce5 |  | tickbox | Producer Statement Review(PS4): Compaction of hardfill
boolean | bc175a44-8977-5724-a16d-e4d051b42f7a |  | tickbox | Producer Statement Review(PS4): Drain Bridging
boolean | 9766aa0a-c85a-5d1a-8dd0-f8ebce314c0c |  | tickbox | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): Piling
checkpoint-status |  |  | checkpoint | Pile records and cards
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checklist-flat |  |  | checklist | Eyebrow - Canopy |  |  |  |  | Yes | FC - R - Eyebrow - Canopy | 6fefcc7c-ef9e-4182-b2a4-006b0b9a1338
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Eyebrow - Canopy works completed and acceptable
checklist-flat |  |  | checklist | Anchor Points - Intermediate, Corner and End Plate Installation |  |  |  |  | Yes | FC - R - Anchor Points - Intermediate, Corner and End Plate Installation | 72471575-90c8-4e45-b231-697944834224
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Intermediate, Corner and End Plate installation completed and acceptable
checklist-flat |  |  | checklist | Ecoply Board |  |  |  |  | Yes | FC - R - Ecoply Board | 78bf2896-aa52-4d32-8326-f9a226e88c66
checkpoint-status |  |  | checkpoint | Fixing and spacings checked in accordance with manufacturers specs.
checkpoint-status |  |  | checkpoint | Bracing checked and accurate
checkpoint-status |  |  | checkpoint | Penetrations and punctures sealed with flashing tape
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Ecoply board installation completed and acceptable
checklist-sectioned |  |  | checklist | Contractor Allocation |  |  |  |  | Yes | ITP - R - Contractor Allocation (Use at stage level for each subcontractor on the stage) | 791af72a-90b3-4174-afca-b31ffb8acb16
checkpoint-group |  |  | section | Contractor Allocation
checkpoint-no-status |  |  | checkpoint | Contractor Allocation
text | 6c670185-c818-52b5-8bd6-fb44310d37c3 |  | textbox | Record Subcontractor Company Name
text | 8a77d268-43a2-5155-bb75-b1c135389c7c |  | textbox | Record scope of works
checkpoint-status |  |  | checkpoint | Specifications confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | Programme milestones confirmed with subcontractor management
checkpoint-status |  |  | checkpoint | All subcontractor ITPs (inspection test plans) attached and agreed.
checkpoint-status |  |  | checkpoint | Quality expectations and requirements discussed and confirmed as understood.
text | ae9c61fe-e20c-598a-8977-5c90c42646d7 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
holdpoint |  |  | signoff | Escalate concerns to QA Advisor
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Post-Line GIB
checkpoint-status |  |  | checkpoint | GIB installation correct, screw types, pattern, etc..
checkpoint-status |  |  | checkpoint | Fire rated GIB installed to adjoining unit walls & garage, correct thickness.
checkpoint-status |  |  | checkpoint | Post Line Council Inspection completed and acceptable. GIB stopping to proceed
button | 560a3fd3-4cd9-52be-81a0-e17778847407 |  | button | Note remedial work needed | None, Minor, Major
checklist-flat |  |  | checklist | Soffits |  |  |  |  | Yes | FC - R - Soffits | 7baa4456-8f24-4dfb-91cb-33d291a91728
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Soffit works completed and acceptable
checklist-flat |  |  | checklist | Anchor Points - Static line installation |  |  |  |  | Yes | FC - R - Anchor Points - Static line installation | 84e4b76d-b28d-4768-a1c5-197ab5987ec5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Static line installation completed and acceptable
checklist-flat |  |  | checklist | Service Trenches - Common Service Trenches |  |  |  |  | Yes | C - S - Service Trenches - Common Service Trenches | 8c0cb010-c9dd-4691-93b6-1f45df28cd39
checkpoint-status |  |  | checkpoint | Excavation location and depth accurate
checkpoint-status |  |  | checkpoint | Bedding for Trench completed and acceptable
checkpoint-status |  |  | checkpoint | Installed correct number of Power Ducts and Comms Ducts as per cross section drawings
checkpoint-status |  |  | checkpoint | Covering ducts installed with fines at correct depth and confirmed
checkpoint-status |  |  | checkpoint | Mag slab laid on top of ducts
checkpoint-status |  |  | checkpoint | Trench work completed and acceptable
checkpoint-status |  |  | checkpoint | Backfill completed & compacted as per the specifications
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Mechanical Consent |  |  |  |  | Yes | CST - R - Mechanical Consent | 8ceb2f48-0611-4285-8f8f-1aac04d74158
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Electrical
boolean | 08a2617f-1084-5739-9acc-7d147ca3f826 |  | tickbox | Electrical compliance and safety certificate
boolean | 89d87743-3453-527e-8a52-675c6ddb345e |  | tickbox | record of inspections for high risk works
checkpoint-status |  |  | checkpoint | Automatic doors
boolean | 47bfa648-f624-5066-bdb7-9402e83d653e |  | tickbox | Producer Statement Construction(PS3): automatic door installation and failsafe override
boolean | 07740bd5-01e6-5917-a541-7e8258e0bb6d |  | tickbox | As built documentation; plans, operation and maintenance manual
checkpoint-status |  |  | checkpoint | Access controlled doors
boolean | 0cccda62-96ed-5be8-b9ab-49d40b200c08 |  | tickbox | Producer Statement Construction(PS3): installation of access control to doors and failsafe override
boolean | 92884a13-5a5e-57c0-b56c-d14e9d5b0fb9 |  | tickbox | As built documentation; location of systems, the make of the systems and operation manuals
checkpoint-status |  |  | checkpoint | Escape route pressurization systems
boolean | 002f90d4-17b2-5ce6-859d-e05cc6475a60 |  | tickbox | Producer Statement Construction(PS3): Installation of escape route pressurization systems from approved mechanical contractor
boolean | e46ee303-3fc1-5074-aaf1-dec2d9bf321f |  | tickbox | Producer Statement Review(PS4): Installation of escape route pressurization systems from approved mechanical contractor
boolean | d423ce40-ece3-573f-97c4-48e8c62c45e4 |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 6e3c8f94-f2ea-5eb1-afeb-ed8f97331c0f |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
boolean | f3362c1d-ab4e-5959-8032-4d27a0627c05 |  | tickbox | Electrical work certificate
checkpoint-status |  |  | checkpoint | Passenger Carrying Lifts
boolean | 9e072109-55c2-5572-b455-69e9ef637ad0 |  | tickbox | Codemark construction certification and inspection/maintenance sheets
checkpoint-status |  |  | checkpoint | Mechanical ventilation or air conditioning system
boolean | ddbbd814-c346-5956-9ca5-79a2065a6f38 |  | tickbox | Producer Statement Construction(PS3): Kitchen extract system (compliance with NZBC G4)
boolean | 1af29161-b995-5ca7-926e-d0f3194daf20 |  | tickbox | Producer Statement Construction(PS3): Confirmation from mechanical contractor the systems comply with NZBC G4
boolean | 76354ace-24d0-599c-b23e-34b917876e91 |  | tickbox | Producer Statement Review(PS4): Confirmation from council approved mechanical engineer that the systems comply with NZBC G4
boolean | 4594eb4a-e450-586b-be8f-408e7d3d90dd |  | tickbox | Producer Statement Review(PS4): Installation of seismic restraints in accordance with NZS 4219:2009:"Seismic Performance of Engineering Systems in Buildings"
boolean | e731a4a8-0389-5c25-bcbc-48eb672c3b96 |  | tickbox | test/commissioning results verifying measured airflow rates meet design and interface with alarm system
boolean | 7ef057b3-52d8-54ea-9729-32cfc99ba43c |  | tickbox | As built documentation; equipment schedules and make of systems, operation and maintenance manuals
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | Flashing installation |  |  |  |  | Yes | FC - R - Flashing installation | 8df4180e-607b-4dbd-8e4e-b75fff81ebd4
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Flashing installation completed and acceptable
checklist-flat |  |  | checklist | Precast Wall Panel Installation |  |  |  |  | Yes | ST - R - Precast Wall Panel Installation | 916e89fa-8f5f-4db4-9995-91d0118d7b72
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Wall Panel Installation completed and acceptable
checklist-flat |  |  | checklist | Completion Documents |  |  |  |  | Yes | CST - S - Completion Documents | 9501a565-ff79-47cb-b0df-71df504091c3
checkpoint-status |  |  | checkpoint | All relevant Compliance Documentation completed and attached above
boolean | ecf6bb7d-1a3f-53d9-a436-3fc73953385e |  | tickbox | Any Additional Compliance Documentation (Required under Section C and by Consultants) - Completed and Attached
label | 203fff04-0246-5b76-aaa4-5eb395e82753 |  | note | Do not select "Pass" HERE until all requirements have been marked as "Yes" & attached or you have selected "N/A"
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | Inspections completed and issued to Foreman
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Brick Works |  |  |  |  | Yes | FC - R - Brick Works | 95209210-f02b-4320-9452-94cbba5eb706
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Brick works completed and acceptable
checklist-flat |  |  | checklist | Site Inspection Details |  |  |  |  | Yes | CST - R - Site Inspection Details | 98231761-c836-4553-9468-20add41bd237
checkpoint-status |  |  | checkpoint | Specific site works location
checkpoint-status |  |  | checkpoint | Contractor QA reviewed and approved
checkpoint-status |  |  | checkpoint | Have the consented drawings been followed?
checkpoint-status |  |  | checkpoint | General comments, photos, and observations during inspection
checkpoint-status |  |  | checkpoint | Works completed to required specifications - Engineer signoff
checklist-flat |  |  | checklist | Intumescent Painting |  |  |  |  | Yes | ST - R - Intumescent Painting | 99ff00a6-8aa6-4d34-a698-b50b894c5683
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Intumescent Painting completed and acceptable
checklist-flat |  |  | checklist | Underslab plumbing |  |  |  |  | Yes | F - R - Underslab plumbing | 9a02b241-f1cf-4c73-a07e-ab9934931f19
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All underslab plumbing installation completed as per the specifications
checklist-flat |  |  | checklist | Foundation Consent |  |  |  |  | Yes | CST - R - Foundation Consent | 9dadcba8-98f7-4923-865e-c21c9aa01969
checkpoint-status |  |  | checkpoint | Record of title
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Pre-cast concrete
boolean | c99523e6-5856-50db-8c3d-393baaaa75ee |  | tickbox | Producer Statement Design(PS1): Prestressed concrete beams and floor units
boolean | 57ec697c-7c76-52cf-84ef-da0ccc774714 |  | tickbox | Producer Statement Construction(PS3): Prestressed concrete beams and floor units
boolean | eece0c6c-bffe-55d6-8d68-9661ec25f5d2 |  | tickbox | Producer Statement Review(PS4): Prestressed concrete beams and floor units
boolean | 49fd7e0b-ec5d-5806-a440-18b645a132ab |  | tickbox | Shop drawings for concrete beams and floor units
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3): sub-soil drainage
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 8f6d1802-e3e7-55e8-aa10-babee6e01795 |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | f0aab6d5-34b0-57eb-9a92-7f02e3bdb03e |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Mill certificates
checkpoint-status |  |  | checkpoint | Concrete dockets
checkpoint-status |  |  | checkpoint | Producer Statement Review(PS4): Engineer's observation
checkpoint-status |  |  | checkpoint | Surveyor certificate for siting
checklist-flat |  |  | checklist | Fitout Consent |  |  |  |  | Yes | CST - R - Fitout Consent | a1ce4c82-b6c9-4c70-be56-e72ed4d4e0a7
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP records
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 044b4876-b373-557a-b2b3-a220740d697d |  | tickbox | Producer Statement Construction(PS3): Waterproofing Membrane
boolean | 5ea6a226-b3c5-52e6-8e78-4e1e9f0cb5a1 |  | tickbox | Manufacturer's warranty for waterproofing membrane
checkpoint-status |  |  | checkpoint | Surface Coatings
boolean | 3a277ac2-5a27-5707-ad0d-860f0b9fd59e |  | tickbox | Producer Statement Construction(PS3): surface finishes complying with (material categories 1-3 NZBC clause C3.4(a)
boolean | 7854afaa-c9b6-52ac-91e6-5f7768a37c59 |  | tickbox | Producer Statement Construction(PS3): floor surface materials complying with (NZBC clause C3.4(b))
checkpoint-status |  |  | checkpoint | Acoustic testing
boolean | 8f765bf9-4ebe-5fbd-8fb5-b8cc8aecb4bf |  | tickbox | Report/Test certificates from council approved acoustic engineer confirming compliance with NZBC G6
checkpoint-status |  |  | checkpoint | Balustrades
boolean | e6abd268-9a7e-54a0-9007-12c4c9ea20c5 |  | tickbox | Producer Statement Construction(PS3) for balustrade installation
checkpoint-status |  |  | checkpoint | Producer Statement Construction(PS3) for proprietary products
checklist-flat |  |  | checklist | Precast Flat Slab Installation |  |  |  |  | Yes | ST - R - Precast Flat Slab Installation | a4ad83b3-dcfe-4c25-8894-228f3e7d0d44
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Flat Slab Installation completed and acceptable
checklist-flat |  |  | checklist | Timber Framing |  |  |  |  | Yes | ST - R - Timber Framing | a72a009b-d841-40a4-8009-ca9ee959d9c2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Timber frame installation completed and acceptable
checklist-flat |  |  | checklist | Hydraulic Consent |  |  |  |  | Yes | CST - R - Hydraulic Consent | aad1634a-f292-4539-a1eb-2a27fd0c23a3
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Plumbing
boolean | b43f0808-8623-5c38-872e-298ba6cf3f8b |  | tickbox | Producer Statement Construction (PS3): Plumbing
boolean | 1db64d09-1581-57c7-a2f3-cd01ef8cfff1 |  | tickbox | Confirmation of water saving devices
boolean | 9c741f0e-486f-5aff-9342-b6dc36484b64 |  | tickbox | Plumbing under slab as built plan
boolean | 07a22cc9-374a-5f4d-847a-249d2b19d00e |  | tickbox | Producer Statement Review(PS4): hydraulic systems of the building from a council approved engineer
checkpoint-status |  |  | checkpoint | Gas-fitting Work Certificate
checkpoint-status |  |  | checkpoint | Automatic Backflow Preventers Connected to Potable Water supply
boolean | 1874615f-d89e-517e-8edc-5b7107fe6f65 |  | tickbox | Backflow prevention - PS3 and test certificates showing location and type of devices
checkpoint-status |  |  | checkpoint | Application for compliance schedule (AC2102)
checkpoint-status |  |  | checkpoint | Confirmation of performance standards for specified systems (AC2150)
checklist-flat |  |  | checklist | Down Pipes |  |  |  |  | Yes | FC - R - Down Pipes | ad4ddcda-9054-43ea-8946-2c880e257912
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Downpipe installation completed and acceptable
checklist-flat |  |  | checklist | Lintels |  |  |  |  | Yes | FC - R - Lintels | af83695e-2c0f-4d77-b4d1-47944ab4364c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Lintels completed and acceptable
checklist-flat |  |  | checklist | Asbestos Removal |  |  |  |  | Yes | C - R - Asbestos Removal | af97dac8-779f-44ac-a9c0-0169bdefc360
checkpoint-status |  |  | checkpoint | Demolition Survey reviewed and attached
checkpoint-status |  |  | checkpoint | Asbestos Removal Control Plan (ARCP) reviewed and attached
checkpoint-status |  |  | checkpoint | Background Air Monitoring Results (BGAM) reviewed and attached
checkpoint-status |  |  | checkpoint | Clearance Certificates reviewed and attached
checkpoint-status |  |  | checkpoint | All asbestos removed and approval given to progress with work
checklist-flat |  |  | checklist | Hatches |  |  |  |  | Yes | FC - R - Hatches | b04f4b1e-072b-4310-b8d2-674163c6deda
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Edge Beams Installation completed and acceptable
checklist-flat |  |  | checklist | PRE-line |  |  |  |  | Yes | PRE - R - PRE-line | b643a8a9-074b-4a2e-82fd-1cf2c74d83bc
checkpoint-status |  |  | checkpoint | PRE-line works completed and acceptable. Trades QA received, reviewed, attached and approved for all pre-line trades. Approved to line the area.
button | bc89e3dd-3306-535a-948a-698ebd23db0c |  | button | Timber frame installation completed and acceptable | Yes, N/A
button | fa2caac9-e176-5efb-8c6a-2a4a57a6e660 |  | button | Steel Stud frame installation completed and acceptable | Yes, N/A
button | 2a936e87-d0cc-5c03-bce1-684b44caac75 |  | button | Electrical First Fix completed and acceptable | Yes, N/A
button | 760015cc-00d5-56d7-80d0-7f4bf106edd1 |  | button | Plumbing First Fix completed and acceptable | Yes, N/A
button | 897c9695-5b19-55f5-aa02-84b4b5f2a9c2 |  | button | Security, Comms and Data First Fix completed and acceptable | Yes, N/A
button | 34752827-8aa8-5521-b19c-149c9a5963a0 |  | button | HVAC First Fix completed and acceptable | Yes, N/A
button | 2f8c9b16-034a-563f-84a0-0a307dfd6655 |  | button | Fire Security First Fix completed and acceptable | Yes, N/A
button | f86fd790-8074-5596-aa0f-784040cf8695 |  | button | Under floor heating First Fix (including screeding and soundproofing of the bathrooms/ wc) completed and acceptable | Yes, N/A
button | 299ce7b7-4bc2-5076-919c-4971728817f0 |  | button | Kitchen extract First Fix completed and acceptable | Yes, N/A
button | 39e8ae3d-829e-5a18-9a7a-e7d9d759d4cd |  | button | Insulation installation completed and acceptable | Yes, N/A
button | 4e2aaee4-3a56-5e7e-a239-50688a0326c2 |  | button | Passive fire installation completed and acceptable | Yes, N/A
button | b3354301-d350-5c6d-b43c-b56a15868d69 |  | button | Suspended ceiling grids installation completed and acceptable | Yes, N/A
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-flat |  |  | checklist | Pipe Laying - Stormwater |  |  |  |  | Yes | C - R - Pipe Laying - Stormwater | b6fd2f5d-816d-4277-b7b1-5dc6181399d2
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Stormwater pipe laying completed as per the specifications
checklist-flat |  |  | checklist | Unit Benchmarking |  |  |  |  | Yes | ITP - R - Unit Benchmarking (Use at stage level) | b8182158-a57d-49e1-8171-313f92c1c177
checkpoint-status |  |  | checkpoint | Benchmark standard agreed as per Quality Management Plan
button | 1488fc59-d3ea-57e5-a98d-ad89059d9fb0 |  | button | Project Manager or delegate present | Yes, No, N/A
button | 015652a6-7ed5-5999-aa13-ac51ddd6daf6 |  | button | Sales representative or delegate present | Yes, No, N/A
button | ea43b0a6-e130-55f9-805a-785fa426866d |  | button | QA Advisor or delegate present | Yes, No, N/A
button | 7696f428-ba8a-5bf8-ac37-5c221b3bfae5 |  | button | Design representative or delegate present | Yes, No, N/A
text | c27324c1-d7c8-5dc3-a53c-2e451994e8f3 |  | textbox | Benchmark details (e.g. apartment number or explanation)
text | 63047fe4-188e-5296-84de-2224b5436f89 |  | textbox | Record benchmark date
checklist-flat |  |  | checklist | Civil Consent |  |  |  |  | Yes | CST - R - Civil Consent | ba0c717a-c40e-4776-8dac-a62d171f20c4
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Drainage
boolean | 247808aa-e33b-5273-a03b-8f8a66d2bf2e |  | tickbox | Producer Statement Construction(PS3): sub-soil drains
boolean | eeafe7dc-585e-5f59-a75e-0658d7ce48d9 |  | tickbox | Producer Statement Construction(PS3): drainage
boolean | bf423192-c601-59f4-9b37-7801a6de3e58 |  | tickbox | Drainage as built plan
boolean | 14384879-cfa4-52c2-a420-4ac1fe556613 |  | tickbox | Producer Statement Construction(PS3): Stormwater Management
boolean | a5270e95-3f62-5218-b02e-214acf4e60ea |  | tickbox | Producer Statement Review(PS4): Stormwater management approved by council Engineer
boolean | c7e85089-e03d-5404-91bb-89e025950809 |  | tickbox | Operations and Maintenance manual for stormwater management systems
boolean | a91e6f88-8403-536f-9ee4-b2da5022729f |  | tickbox | Backflow test Certificate | Yes,No,N/A
checkpoint-status |  |  | checkpoint | Drainage Pump Systems
boolean | 7901451c-e329-5f37-afbc-83c78df05e90 |  | tickbox | Producer Statement Construction(PS3): installation of drainage pump system
boolean | c2401d25-a3c0-548a-92ff-a9054833503b |  | tickbox | Manufacturer's warranty for pump system
boolean | b3996033-4e50-556b-95d4-daf6a7bac9ec |  | tickbox | Maintenance agreement for pump system
checkpoint-status |  |  | checkpoint | On-Site wastewater Systems
boolean | 5506aa38-5f5c-5d75-99c5-da068c890668 |  | tickbox | Producer Statement Construction(PS3): wastewater treatment and disposal system
boolean | d04fed30-c00a-5cc9-83f8-3270bfe52507 |  | tickbox | Plan showing location of treatment and disposal of systems
boolean | 9be5a18a-48ef-5d03-882e-a6a0f3e71135 |  | tickbox | Producer Statement Review(PS4): System of onsite treatment and disposal of wastewater
boolean | d9d595d7-ac8a-58a7-b475-c55f6936407b |  | tickbox | Maintenance agreement for on-site wastewater treatment and disposal system
checkpoint-status |  |  | checkpoint | Development Engineering
boolean | a2f69bf1-408e-5e5e-8486-bb3df55d26fb |  | tickbox | Written approval of works completed within 2m of public waste water drainage
boolean | 6f0fa42b-a37f-567c-a44e-33aad562d8ae |  | tickbox | Engineering Approval Completion Certificate for ENG
checkpoint-status |  |  | checkpoint | Watercare Services/Viola Approval
boolean | fb847d75-95be-5fdb-9b58-e2c0d67b2fb5 |  | tickbox | Certificate of connection for both incoming and outgoing water to the public system
boolean | e11d3c1a-4894-55e5-bb70-2a2726f220d4 |  | tickbox | Written approval of completed works
checklist-flat |  |  | checklist | Shell Beam Installation |  |  |  |  | Yes | F - R - Shell Beam Installation | bbe75cd4-79e0-4437-825b-e0d6d2e079d7
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Shell Beam installation completed as per the specifications
checklist-flat |  |  | checklist | Demolition |  |  |  |  | Yes | C - R - Demolition | bc187dc5-1ce4-4288-a5fa-b7f7501d6562
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Demolition completed and acceptable
checklist-flat |  |  | checklist | Roofing |  |  |  |  | Yes | FC - R - Roofing | bcf89317-99c7-4185-84df-f1f6f1fc3aa5
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Roofing installation completed and acceptable
checklist-flat |  |  | checklist | C - R - Lift Pit Installation |  |  |  |  | Yes | C - R - Lift Pit Installation | bf2c3b9a-4b5b-4c9e-ab2f-1b32c8f6c162
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Lift Pit installation completed and acceptable
checklist-flat |  |  | checklist | Cladding Sealant |  |  |  |  | Yes | FC - R - Cladding Sealant | c04f46da-10fc-4781-bd0c-24b9041d78cb
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Cladding sealant completed and acceptable
checklist-flat |  |  | checklist | Demolition Consent |  |  |  |  | Yes | CST - R - Demolition Consent | c2017a55-6070-4ba7-bc98-644153321e57
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection passed
checkpoint-status |  |  | checkpoint | Summary Sheet - Site inspection records
checkpoint-status |  |  | checkpoint | Summary Sheet - LBP Records
checkpoint-status |  |  | checkpoint | Asbestos - Asbestos Clearance Certificates & PS3
checkpoint-status |  |  | checkpoint | Demolition - PS3
checklist-sectioned |  |  | checklist | Rib & Infill Installation |  |  |  |  | Yes | ST - R - Rib & Infill Installation | c3474408-cf84-4b92-a919-80a7cdb2a7b4
checkpoint-group |  |  | section | Pre-commencement
checkpoint-status |  |  | checkpoint | Rib lifting plan confirmed, correct chains and hooks verified.
checkpoint-status |  |  | checkpoint | Propping layout confirmed as "issued for construction" with contractor and attached.
checkpoint-status |  |  | checkpoint | Floor area cleared for propping to be erected.
checkpoint-status |  |  | checkpoint | Rib grid layout confirmed with contractor and drawing attached.
checkpoint-group |  |  | section | Rib Installation
checkpoint-status |  |  | checkpoint | Rib inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Ribs placed as per layout.
checkpoint-status |  |  | checkpoint | All ribs visually supported as per plan, no visual damage. Ready for infill panels.
checkpoint-group |  |  | section | Infill Panel Installation
checkpoint-status |  |  | checkpoint | Infill panel inspection results received from the contractor
checkpoint-status |  |  | checkpoint | Infill boards constructed as panels, including 'backbone', 6 to 10 boards in length and fitted tightly between the ribs
checkpoint-status |  |  | checkpoint | Infill panel adjacent ends are joined, locked with timber blocks to prevent lateral movement, and secured to wall supports
checkpoint-status |  |  | checkpoint | No obvious visual defects on infill boards, no knots, no cracks or other weakness across 25% of the width.
checkpoint-group |  |  | section | Completion
checkpoint-status |  |  | checkpoint | All propping below timber infill complete
checkpoint-status |  |  | checkpoint | Handrails installed on all edges (top of slab)
checkpoint-status |  |  | checkpoint | All penetrations closed or exclusions in place
checkpoint-status |  |  | checkpoint | Pass to indicate agreement to proceed to lay reinforcing.
holdpoint |  |  | signoff | Raise Remedial if failed
checklist-flat |  |  | checklist | Backfilling |  |  |  |  | Yes | F - R - Backfilling | c4b768f0-f4f3-4f45-8119-a3ed407f6839
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Backfilling completed as per the specifications
checklist-flat |  |  | checklist | Balconies |  |  |  |  | Yes | FC - R - Balconies | c60da965-4169-40ae-bcc5-46c6fc92f403
checkpoint-status |  |  | checkpoint | Waterproofing and flashing checked and acceptable
checkpoint-status |  |  | checkpoint | All screed to nib and deck falls checked and accurate
checkpoint-status |  |  | checkpoint | Soffit Checked and accurate
checkpoint-status |  |  | checkpoint | Flood test completed and acceptable
checkpoint-status |  |  | checkpoint | Installation of deck tiles completed and acceptable
checkpoint-status |  |  | checkpoint | All works on balcony are completed to required specification.
checklist-flat |  |  | checklist | Restricted Building Works Consent |  |  |  |  | Yes | CST - R - Restricted Building Works Consent | cb3f86b7-c1bc-42a7-b5f6-a9692586a67d
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Record of works
boolean | b11fe41b-e253-5cce-9ddd-7f7b95d18994 |  | tickbox | Foundations
boolean | 1c1d8066-2dc8-51b5-80d0-653ccd25aee5 |  | tickbox | Slab or subfloor framing
boolean | de2d046d-8402-58e0-83ac-4bc5878be2c8 |  | tickbox | Blockwork
boolean | 5d22784c-fae7-5e37-9c81-ab9dca13bdc1 |  | tickbox | Walls
boolean | 49e6004b-9768-52e7-bdff-fe5ca693d45d |  | tickbox | Roof
boolean | 3b4602d9-999b-5fe0-90fe-a34748f62d46 |  | tickbox | Columns and Beams
boolean | 2f13658d-4721-5a3d-b988-4298b9fa6541 |  | tickbox | Bracing
boolean | 6b23be81-8cb7-5c33-af6e-58dba9f77062 |  | tickbox | Damp proofing
boolean | 2ca31b9b-ec90-54f7-8495-dd87fa97b328 |  | tickbox | Roof cladding or roof cladding system
boolean | 5b6968e0-0a58-5e4e-a3b1-52af4cd2af51 |  | tickbox | Ventilation system
boolean | 4044ea53-6473-556a-be4c-34b3f3b2bac9 |  | tickbox | Wall cladding or wall cladding system
boolean | 0f2295ab-c640-5081-a8c0-ea9952bafc34 |  | tickbox | Waterproofing
checkpoint-status |  |  | checkpoint | Record of warranties
checklist-sectioned |  |  | checklist | Concrete Planning and Pour |  |  |  |  | Yes | ITP - R - Concrete - Planning and Pour (per townhouse block) | d118ce29-c294-4794-8512-32264beba255
checkpoint-group |  |  | section | Pre Pour Planning
checkpoint-status |  |  | checkpoint | Concrete pour planning completed with subcontractor
text | 3340c025-f69a-584b-8b1d-1b53122123cc |  | textbox | Date of pour
text | 986301ec-dd9e-5710-8600-6c361fdbac48 |  | textbox | Specified concrete strength:
text | cd61dc64-4ebc-59d6-80e7-279014af1dea |  | textbox | Concrete strength ordered:
text | 1832f9ae-d6a6-57d4-a6e5-9ffb9a307e54 |  | textbox | Concrete quantity ordered:
text | 032f44f3-f481-576e-a229-7a79c2ec9725 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checkpoint-group |  |  | section | Pour
checkpoint-status |  |  | checkpoint | Request to pour received and approved
button | 0bf9b1b1-9235-563c-9fc5-c83a3d75b2b4 |  | button | Reinforcing meets specification | Yes, Reworked, N/A
button | 14e8e4c8-8f26-5a47-947e-3f5476fe03d7 |  | button | Service penetrations present and correct | Yes, Reworked, N/A
button | 1d80cd9c-a7c3-5694-88c5-53bb6b428e30 |  | button | Waterproofing elements present and correct | Yes, Reworked, N/A
button | 04521062-7ee6-55ec-9bc2-dd542753bc2b |  | button | Couples present and correct | Yes, Reworked, N/A
button | 5fc28eef-340e-51c0-b5c0-42fa87cb8cb7 |  | button | Control joints/ stop ends installed accurately and correctly braced | Yes, Reworked, N/A
checkpoint-status |  |  | checkpoint | Engineer Inspection conducted and passed
button | 40ba8d87-c9e9-5e6b-9e9c-0309ea7cdcbf |  | button | Note remedial work needed | None, Minor, Major
text | 4e17959c-26a6-5651-bfd4-0bda24555550 |  | textbox | Inspected by and date:
checklist-sectioned |  |  | checklist | ITP Concrete Pour |  |  |  |  | Yes | ST - I - ITP Concrete Pour | d30e16e0-f367-4015-a270-b53d5b27f99c
checkpoint-group |  |  | section | DESIGN
checkpoint-status |  |  | checkpoint | Attach relevant design documents as references
checkpoint-status |  |  | checkpoint | Confirm Mpa/Slump/Aggregate size - attach mix design
checkpoint-status |  |  | checkpoint | Reinforcing design, attach approved engineering design
checkpoint-group |  |  | section | PRELIMINARIES AND PLANNING
checkpoint-no-status |  |  | checkpoint | PRELIMINARIES AND PLANNING
holdpoint |  |  | signoff | Local authority compliance, council inspection completed, confirm compliance with consent conditions
checkpoint-status |  |  | checkpoint | Project Quality High Risk Activity, risk assessment completed, attach copy
checkpoint-status |  |  | checkpoint | All equipment calibrated and operating within tolerances. Attach calibration ceritificate for relevant equipment.
checkpoint-status |  |  | checkpoint | Subcontractor QA Completed in CONQA (ST - S - Concrete Pour) with no issues.
checkpoint-status |  |  | checkpoint | Ryman 046 ST - R - Concrete Pour Planning checklist completed and SIGN OFF request issued and completed
checkpoint-status |  |  | checkpoint | PM Sign off request - all preliminaries and planning section requirements are met. Pass this checkpoint once signed.
holdpoint |  |  | signoff | Add signature as per checkpoint above
checkpoint-group |  |  | section | SET OUT
checkpoint-status |  |  | checkpoint | 3rd Party Sign off: Set out of concrete elements, Grids and RLs clearly marked for reference - Check setout in accordance with Architectural and Structural Drawings
checkpoint-status |  |  | checkpoint | Set out of concrete elements, Grids and RLs clearly marked for reference - Check setout in accordance with Architectural and Structural Drawings
checkpoint-group |  |  | section | GROUND PREPARATION
checkpoint-status |  |  | checkpoint | All underslab services installed, inspected, backfilled and compacted - Services Trades ITP's signed off to relevant points. Services Trades to sign as confirmation of all underslab works complete. Attach Photos of signed trade ITPs
checkpoint-status |  |  | checkpoint | Subcontractor sign off required. Ground preparation confirmed by subcontractor. Pass this checkpoint once signed.
holdpoint |  |  | signoff | SUBCONTRACTOR CONFIRMATION, CLICK TO EMAIL SIGN OFF REQUEST
checkpoint-status |  |  | checkpoint | PM Signature required. Ground preparation confirmed by subcontractor. Pass this checkpoint once signed.
holdpoint |  |  | signoff | ADD SIGNATURE - PM SIGN OFF TO PROCEED
checkpoint-status |  |  | checkpoint | Thickenings / footings / pads correct - location/ depth / width - Attach Photos
checkpoint-status |  |  | checkpoint | Subgrade prepared, compacted and finished to correct RL's - Confirm levels
checkpoint-status |  |  | checkpoint | Vapour barrier installed under internal slabs on ground including integral ground beams. Joints lapped and facing away from concrete pour. Seal laps & penetrations with water adhesive tape. Patch or seal punctures. Plastic is taped around pipes and other slab penetrations. Any holes or tears have been repaired or taped - Attach photos
checkpoint-status |  |  | checkpoint | Waterproofing membrane installed and correct - Attach photos
checkpoint-status |  |  | checkpoint | Installation of edge forms, rebates, setdowns, penetrations etc. checked - Formwork has been placed and securely fixed plumb and level to prevent displacement during pour. Slab RL's checked in accordance with the approved plans. Dimensions have been checked against plans. All set downs are in the correct place and are the correct depth. Slab is square.
checkpoint-group |  |  | section | SLAB PREPARATION
checkpoint-status |  |  | checkpoint | Formwork. Checklist 046 F - S - Formwork Inspection completed by subcontractor
holdpoint |  |  | signoff | PM SIGN OFF TO PROCEED
checkpoint-status |  |  | checkpoint | Services trades to confirm all embedded items are installed, tested and checked as required. Underslab drain penetration positions have been checked in accordance with the approved plans - Electrician, Plumber, Mechanical to sign off
checkpoint-status |  |  | checkpoint | Reinforcement installed as per structural design. Checklist 046 ST - S - IMBMS Couplers Tests Checklist completed.
checkpoint-status |  |  | checkpoint | Engineer inspection and approval to pour - Attach certificate / report and photos of slab prior to pouring
checkpoint-status |  |  | checkpoint | Confirmation that all work to be rectified from Engineer Inspections has been completed checked for compliance. Project Manager's review of all required check points and approval to proceed with Concrete Pour.
checkpoint-group |  |  | section | CONCRETE POUR
checkpoint-status |  |  | checkpoint | Review and confirm: - Pour sequence (attach pour plan), Concrete truck discharge point, supply rate and turn around time, Pump type, setup location and timing, Placement equipment (chutes, barrow runs, ramps etc.), Construction joint forms and inserts, Finishing equipment, Curing method, Weather forecast check. Confirm all planning is in place and pour is approved to proceed.
holdpoint |  |  | signoff | PM SIGN OFF TO PROCEED
checkpoint-status |  |  | checkpoint | Concrete Slump Test Report. Attach Slump test report.
checkpoint-status |  |  | checkpoint | Tolerances. Delivery dockets checked for MPA, slump tolerance, maximum elapsed time from batch plant to discharge. Check tolerances as laid from straight edge, Visual inspection Ponding of water after rain
checkpoint-group |  |  | section | POST POUR
checkpoint-status |  |  | checkpoint | Concrete Cylinder Test Results. Attach Test Results (7, 14, 28, 56 days) - Confirm all concrete installed reached nominal strengths
checklist-flat |  |  | checklist | RAB Board |  |  |  |  | Yes | FC - R - RAB Board | d66d4a5f-1605-4241-9c64-b0b6fc9a91e4
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | RAB Board works completed and acceptable
checklist-flat |  |  | checklist | Façade Consent |  |  |  |  | Yes | CST - R - Façade Consent | dc47cd92-0d99-471e-9563-7731235f2874
checkpoint-status |  |  | checkpoint | Title Recorded
checkpoint-status |  |  | checkpoint | Final Inspection Passed
checkpoint-status |  |  | checkpoint | Summary sheet - site inspection records
checkpoint-status |  |  | checkpoint | Summary sheet - LBP Records
checkpoint-status |  |  | checkpoint | Exterior
boolean | af5b4d72-771f-55f5-b9bf-d3cf7473ab1f |  | tickbox | Producer Statement Construction(PS3): Plaster system and manufacturer's product warranty
boolean | d8296d8f-3610-565f-8b76-d122308bd2c2 |  | tickbox | Producer Statement Construction(PS3): Brick work and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Glazing and external joinery
boolean | d80bcfc0-eedc-57a1-bf78-e1aadaf7748c |  | tickbox | Producer statement for aluminium joinery complying with NZS4211:2008
boolean | 59fa7d30-b987-524f-ab76-359b2b0aaafb |  | tickbox | Producer Statement Construction(PS3): safety glazing in compliance with NZS4211:2008
boolean | 0c3af0ef-f767-5817-a9a8-1dfc64764dc3 |  | tickbox | Producer Statement Design(PS1) from joinery manufacturer
boolean | 2e96a0c1-0f45-5e95-a9cf-05477897cf2d |  | tickbox | Producer statement for fire rated windows confirming compliance with NZS4232
checkpoint-status |  |  | checkpoint | Waterproofing
boolean | 9f37522c-5d52-5927-8b62-292c9a558b9d |  | tickbox | Producer Statement Construction(PS3): Roof membrane and Manufacturer's product warranty
boolean | 9514cd34-c62d-5659-a49f-2a558ca35386 |  | tickbox | Producer Statement Construction(PS3): Deck Membrane and manufacturer's product warranty
boolean | c990c875-5b77-5ab8-92aa-1f85b0e38041 |  | tickbox | Producer Statement Construction(PS3): Tanking membrane and manufacturer's product warranty
checkpoint-status |  |  | checkpoint | Roof abseil and fall arrest system
boolean | a28a60f9-47c4-54ef-b8aa-bbff221f3b9c |  | tickbox | Producer Statement Design(PS1): installation of roof abseil and/or fall arrest system
boolean | 234d59bf-85ff-59c1-a0c6-ad388e08143a |  | tickbox | Producer Statement Construction(PS3): installation of roof abseil and/or fall arrest system
boolean | a13a6321-1f15-5fe1-9c75-449d6893262d |  | tickbox | Producer Statement Review(PS4): installation of roof abseil and/or fall arrest system
checkpoint-status |  |  | checkpoint | Balustrades
boolean | 31d253d3-d8aa-5c8d-9bef-c51e46fe39ae |  | tickbox | Producer Statement Construction (PS3) for the balustrade installation
checkpoint-status |  |  | checkpoint | Façade systems
boolean | 5aa07554-8851-5a9a-a891-d2e26c081820 |  | tickbox | Producer Statement Review(PS4): from council approved façade engineer for façade system
boolean | 401774d3-9ac5-560f-a254-0579298a3652 |  | tickbox | Written report from council approved façade engineer for façade system (supporting the PS4)
boolean | e6e9575f-d454-5545-964a-9c2cc8b2c301 |  | tickbox | Producer Statement Construction(PS3): installation of the façade system
boolean | b69f8d5a-a155-55c9-85fa-dfdc3dea56e8 |  | tickbox | Façade System Maintenance Manual
boolean | b0163c22-c95f-589e-8692-e0612feac030 |  | tickbox | Warranties/Guarantees from main and sub-contractors
checklist-flat |  |  | checklist | Blockwork |  |  |  |  | Yes | ST - R - Blockwork | e0bf5475-eaf0-4e9e-9e5a-e9a34eb29e2c
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Blockwork walls completed and acceptable
checklist-flat |  |  | checklist | Tapes and VaproShield |  |  |  |  | Yes | FC - R - Tapes and VaproShield | e41f5b72-91f2-421e-beef-52c68a69d4a3
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Tapes/VaproShield works completed and acceptable
checklist-flat |  |  | checklist | On Grade Slab Pre-Pour |  |  |  |  | Yes | ITP - R - On Grade Slab Pre-Pour (per townhouse block) | e7ed8807-9b57-4989-88a7-bda562dc1767
checkpoint-status |  |  | checkpoint | All subcontractor QA uploaded, attached, and meets ITP requirements.
checkpoint-status |  |  | checkpoint | Survey set out (height, location, setout) - confirmation attached.
checkpoint-status |  |  | checkpoint | Underground services installation completed
checkpoint-status |  |  | checkpoint | Backfilling completed
checkpoint-status |  |  | checkpoint | Waterproofing completed
checkpoint-status |  |  | checkpoint | DPM overlapping/taping with no tears or perforations. Council requirement
checkpoint-status |  |  | checkpoint | Reinforcing completed
checkpoint-status |  |  | checkpoint | Engineer sign off completed and approved for pour
button | 9d98a256-270e-5f05-8b58-3eae45a398b7 |  | button | Note remedial work needed | None, Minor, Major
checkpoint-status |  |  | checkpoint | Council inspection completed and approved for pour
button | 9464620e-aa9b-5165-9399-bccddf8196bc |  | button | Note remedial work needed | None, Minor, Major
text | f54286af-2b1f-5b9f-aa20-756d30efeb91 |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Precast Balcony Installation |  |  |  |  | Yes | ST - R - Precast Balcony Installation | e82d3755-f05a-4abb-8c99-5c3affc4bced
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
checkpoint-status |  |  | checkpoint | Joints grouted with Sika 212 and PEF rod.
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Precast Balcony Installation completed and acceptable
checklist-flat |  |  | checklist | Fascia/Gutter |  |  |  |  | Yes | FC - R - Fascia/Gutter | e85cf016-24bd-4e16-9d54-7053cce78965
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Fascia/Gutter installation completed and acceptable
checklist-flat |  |  | checklist | Exterior Timber Framing |  |  |  |  | Yes | FC - R - Exterior Timber Framing | ea4dfe34-2cc8-4be1-b71f-6baef6b875dd
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Exterior Timber Framing works completed and acceptable
checklist-sectioned |  |  | checklist | ST - R - Concrete Pour Inspection |  |  |  |  | Yes | ST - R - Concrete Pour Inspection | eb0addfa-efe3-4e00-8f64-37148bba46de
checkpoint-group |  |  | section | IMMEDIATELY PRIOR TO POUR
checkpoint-no-status |  |  | checkpoint | IMMEDIATELY PRIOR TO POUR
text | 1284f4f9-10b3-5a46-b725-d5ca0324eb7e |  | textbox | Confirm temperature on site is within allowable range to pour (Deg C)
boolean | b42eea20-8537-584b-bcc8-d8a85878caf2 |  | tickbox | If air temp > 32°C then confirm aliphatic alcohol to be applied.
boolean | 53e6de86-0ff8-5aef-8914-f996e6ee311c |  | tickbox | Rain forecast?
checkpoint-status |  |  | checkpoint | Confirm concrete tester is onsite to take samples (slump & cylinder) as per approved testing rate
checkpoint-status |  |  | checkpoint | Confirm agreed concrete truck turn around times and supply rate with supplier
checkpoint-status |  |  | checkpoint | Confirm maximum waiting time with concrete supplier
checkpoint-status |  |  | checkpoint | Confirm positioning of pump is adequate to place concrete in a safe and timely manner
checkpoint-status |  |  | checkpoint | Confirm all required access permits, traffic control and the like are in place for movements of concrete trucks and pumps
checkpoint-status |  |  | checkpoint | Reinforcement installed as per structural design
checkpoint-group |  |  | section | DURING CONCRETE POUR
checkpoint-status |  |  | checkpoint | Concrete dockets - attach photo of each docket to this item
checkpoint-status |  |  | checkpoint | Confirm delivery docket complies with mix design prior to dispatching concrete, check for MPA, slump tolerance, max. time from plant to discharge.
checkpoint-status |  |  | checkpoint | Location of each batch of concrete marked up on pour plan
checkpoint-status |  |  | checkpoint | Ensure no water is added to the concrete mix (whether pump or truck).
checkpoint-status |  |  | checkpoint | Confirm vibrator use, rubber tipped vibrator used at regular intervals and penetrate vertically approx. 50mm into previous layer.
checkpoint-status |  |  | checkpoint | Confirm levels, as per drawings, confirm correct cover, falls and flatness tolerances achieved.
checkpoint-status |  |  | checkpoint | Confirm jointing as per drawings, do not relocate, eliminate or make other construction joints.
checkpoint-status |  |  | checkpoint | Confirm Finishing - As per drawings, confirm finish requirements achieved (sufficient to receive nominated floor coverings) - Steel trowel finish to carpet & vinyl areas, wood
checkpoint-group |  |  | section | IMMEDIATELY AFTER POUR
checkpoint-no-status |  |  | checkpoint | IMMEDIATELY AFTER POUR
text | 637fcd24-02f8-5ce2-b76f-ce005aa616d1 |  | textbox | Approved Curing Method (nominate)
checkpoint-status |  |  | checkpoint | Check cured when bleed water stops and able to access slab without marking and also amount used complies
checkpoint-status |  |  | checkpoint | Curing commenced and will continue from completion of finish - Fully enclosed internal surfaces/Early age concrete: 3 days - Other concrete surfaces: 7 days. Prevent rapid drying out at the end of the curing period.
checkpoint-status |  |  | checkpoint | Foreman Sign off to receive inspection results - concrete pour inspections completed by subcontractor. Pass this checkpoint once signed.
holdpoint |  |  | signoff | CLICK AND SEND EMAIL TO PROJECT MANAGER TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
checklist-flat |  |  | checklist | Bulk Excavation |  |  |  |  | Yes | C - R - Bulk Excavation | ecff9512-b5f5-4fe2-829e-52f187aef094
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
checklist-flat |  |  | checklist | Survey Certificates |  |  |  |  | Yes | F - R - Survey Certificates | ef3983ae-c62c-422d-8527-856862ad583f
checkpoint-status |  |  | checkpoint | survey certificates for correct building height/location/setout attached
checklist-flat |  |  | checklist | Balustrades Installation |  |  |  |  | Yes | FC - R - Balustrades | f1a44181-b47c-4c98-b30f-ed744b8d57bd
checkpoint-status |  |  | checkpoint | Chemset bolt pull testings completed and passed. Test results received and confirmed.
label | 0c8116b1-d780-55f9-88fb-c731645f748e |  | note | Record sample size (%)
checkpoint-status |  |  | checkpoint | Lateral load pull testings completed and passed. Test results received and confirmed.
label | a8a2758e-9d8e-5c18-824e-ac5897cd1249 |  | note | Record sample size (%)
text | ff57b221-a6b6-5f7c-b4c5-346e4a276fac |  | textbox | Record details of Consultant Advice Notices issued relating to this work (CAN Ref numbers and Consultant)
checkpoint-status |  |  | checkpoint | Confirm CANs implemented as directed, including external sign off as required. (n/a response if blank above)
checklist-flat |  |  | checklist | Council Inspection |  |  |  |  | Yes | CST - R - Council Inspection | f6fdb2da-4004-4a54-9839-9ad472cde0cf
checkpoint-status |  |  | checkpoint | Inspection details complete
text | 2f4ae729-42ce-5b97-baba-2eea43743648 |  | textbox | Date of Inspection
text | daa7501b-b0dc-5310-a431-7f8f2ee1ddd0 |  | textbox | Type of Inspection
text | aa1b8d75-cb40-5bf1-96bf-1908af7e393f |  | textbox | Area Inspection relates to
select | f0bd5b86-10e4-5749-b480-8dd3ce774959 |  | dropdown | Inspection outcome | Pass, Partial Pass, Fail
boolean | dc6e987c-879c-532c-84ce-a2fde40fa189 |  | tickbox | Council inspection attached
checkpoint-status |  |  | checkpoint | Relevant Observation Closeout evidence attached below if applicable (pass once completed)
text | ac637893-86a6-586c-afc3-af36dd32bcfc |  | textbox | Failed comments and Required Action
checklist-flat |  |  | checklist | Service Trenches - Pulling Pits |  |  |  |  | Yes | C - R - Service Trenches - Pulling Pits | f8ed29a2-e2fb-42d4-9316-22a4615d6e02
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Pulling Pits trench works completed as per the specifications
checklist-flat |  |  | checklist | Sheet Piling |  |  |  |  | Yes | F - R - Sheet Piling | fbfaef87-9a7d-49aa-af01-672e3938e497
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Sheet pile installation completed and acceptable
checklist-flat |  |  | checklist | STO Poly Plaster |  |  |  |  | Yes | FC - R - STO Poly Plaster | fdbdaf31-586c-46b9-834f-4bbf2ade5aa3
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | STO Poly Plaster works completed and acceptable