## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: eGSE DBs
| step |  |  | Tier 2: EL-eGSE-02-19
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-eGSE-02-20
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-eGSE-02-21
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-eGSE-02-22
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-eGSE-02-23
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-eGSE-02-24
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-eGSE-02-25
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 1: GPU DBs
| step |  |  | Tier 2: EL-GPUDB-02-19
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-GPUDB-02-20
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-GPUDB-02-21
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-GPUDB-02-22
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-GPUDB-02-23
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-GPUDB-02-24
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-GPUDB-02-25
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 1: PCA DBs
| step |  |  | Tier 2: EL-PCADB-02-19
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-PCADB-02-20
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-PCADB-02-21
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-PCADB-02-22
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-PCADB-02-23
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-PCADB-02-24
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-PCADB-02-25
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)