## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: HOUSE DB - E
| step |  |  | Tier 2: EL-HDBE-01-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-01-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-01-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-01-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-01-701
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-101
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-102
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-103
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-104
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-201
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-202
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-203
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-204
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-02-703
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-101
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-102
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-103
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-104
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-201
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-202
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-203
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-204
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-05-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-101
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-102
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-103
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-104
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBE-06-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 1: HOUSE DB - N
| step |  |  | Tier 2: EL-HDBN-01-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-01-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-01-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-01-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-01-701
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-101
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-102
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-103
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-104
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-201
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-202
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-203
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-204
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-02-703
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-101
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-102
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-103
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-104
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-201
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-202
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-203
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-204
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-05-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-101
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-102
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-103
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-104
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-301
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-401
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-501
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HDBN-06-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 1: HYD DBs
| step |  |  | Tier 2: EL-HYDDB-01-601
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-HYDDB-01-702
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 1: Apron DBs
| step |  |  | Tier 2: EL-APRONDB-02-19
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-APRONDB-02-20
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-APRONDB-02-21
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-APRONDB-02-22
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-APRONDB-02-23
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-APRONDB-02-24
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 2: EL-APRONDB-02-25
| step |  |  | Tier 3: Distribution Boards
Testing & Commissioning - Distribution Boards (Pre-Energisation) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31042000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Distribution Boards (Energised) | checklist |  |  | Tier 4: WSA20-MPX-04000-EL-ITC-31043000 - Component (Energised)
| step |  |  | Tier 3: Subcircuits
| step |  |  | Tier 4: Lighting
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)
| step |  |  | Tier 4: Power
Testing & Commissioning - Subcircuits (Pre-Energisation) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31072000 - Construction Tests (Pre-energisation)
Testing & Commissioning - Subcircuits (Energised) | checklist |  |  | Tier 5: WSA20-MPX-04000-EL-ITC-31073000 - Component (Energised)