## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
b2f4da22-a585-47e7-a65b-5fec25def3dc | checklist | CHK-009-CIV-FRMS-RSS Walls-Fill Placement Rev 0 |  | CHK-009-CIV-FRMS-RSS Walls-Fill Placement | ffe7b419-4243-4447-86b7-9d093767d774
ceb3c2b4-669a-4aaa-8c26-7c1ae4715c5f | section | Details
d36d87c5-8bdc-42e0-99df-7eb8cf478035 | checkpoint-no-value | Referenced Documentation
8dc1a090-cc79-50b1-b9be-a1e55864f44d | note | Document Title: CHK-009-CIV-FRMS-RSS Walls-Fill Placement
7263b61f-c120-514d-a066-398b6bcdb5a6 | note | Checklist Description: RSS Walls-Fill Placement
7ad1b907-2cfd-5d6a-9382-e916b3d51ad4 | note | Discipline (e.g. CIV/STR/RAIL): CIV
faa4153c-e22c-531a-86a7-330300b487b6 | note | Revision Number: 0
ca074711-8317-56a4-9d1a-48f68aff7d19 | note | Revision Date: 03/06/2024
e41d1b6a-1d7b-52d3-b8cb-3d0e5e85e166 | note | ITP created by: Kamel ALHOBAKI
19a7bea9-0b2d-5615-a8a9-357ac0e26eb8 | note | ITP approved for use by: Pradeep Talasila
f2a950a1-79ee-4716-916d-dcf7d9b5f67a | checkpoint | 1 - Soil reinforcement-Straps
7dab120a-29e3-535b-b19c-aa9f85c30d72 | note | Reference - VR682.08, VR682.17 IFC Drawings
2deb419e-9960-5c8f-a5fa-19ad8209f56e | note | Acceptance Criteria - Reinforcing elements shall be placed on top of the compacted fill material and connected to the wall panels.
a879369b-18fa-5f97-b9ea-c9bcc77d7819 | note | ○ Any twists, kinks, sags or deviations in the reinforcing elements shall be removed prior to the placement of fill material on the reinforcing.
f7585231-9b9c-5f2d-870d-178e276d2932 | note | Method - Visual
82239437-73fa-5963-b188-2d98c853f903 | note | Frequency - Each strap
084cffb3-f8c2-5139-87e1-acd2aaa55c6d | note | Category - IP
81db5f19-c829-50ad-bcdf-8878cc3cc3f3 | note | Responsibility - SE/PE
2f9c3f66-ac88-5dd7-8ae6-cb2c554bb88a | note | Verifying Documents - This Checklist
30d0cff2-4b5f-529a-a3d1-5ed474448179 | date | Date Completed:
6b2ba26f-8ef0-4e12-b051-b4b7762b7ae7 | checkpoint | 2 - Soil reinforcement-Straps
54ed340a-f3fc-5950-be2b-0638f49b4279 | note | Reference - Installation manual
ea708e40-1dd0-5cd2-b005-758530ffdd7b | note | Acceptance Criteria - Correct number of reinforcing element shall be attached to each panel/wire facing units
2928424e-ef70-52f8-8e52-e18900ea2562 | note | Method - Visual
399525d6-a31a-55ba-b7fa-6e51a6a8a0aa | note | Frequency - Each panel/wire facing unit
fc0357ba-00c3-56fa-9c76-1e27418bc7a0 | note | Category - IP
61da524b-be31-54b1-afc8-3867ceedee44 | note | Responsibility - SE/PE
0e6c78ee-5391-5605-92eb-e612a1957788 | note | Verifying Documents - This Checklist
60a4a3df-5eff-56e5-9638-aac55cf4a625 | date | Date Completed:
8d8e340f-fb16-4002-80a9-cfaf79697f34 | checkpoint | 3 - Pre-cast Panel Soil reinforcements-Bolts Connections
a5d6728f-54c0-5b88-9cf5-5481efc8614a | note | Reference - IFC Drawings
de2b7e83-c224-5fc4-aa8d-3542365e6dea | note | ○ Schedule of lengths:
2b14b24f-450c-5e7e-8f80-abaac954ece4 | note | — MRP-103-C-RFL-DRG-35-RBK-CSW-1303 to 1604
b0bfd8df-b182-5175-9141-b51382f0b5e6 | note | ○ Connections arrangement:
6564422f-13d6-5de6-a3b7-8605bfa4893d | note | — MRP-103-C-RFL-DRG-35-RBK-CSW-2002 to 2003
0e586088-6599-5192-afd2-320679563dc2 | note | Acceptance Criteria - Grid Strips are to be installed at the back of each panel in correct length and to the correct anchors at the back of each panel
e907e7ff-ed5a-588f-9a72-9d27b8d4f58f | note | ○ Finger tight nut or use a wrench so thread emerges from top of nut
6feb32a9-8a5a-5c0d-8cd0-76994e79d827 | note | Method - Visual
ae8b39b0-0b0d-530b-bbe9-7d47f00fdb53 | note | Frequency - Each Fill Layer
0848c1bf-718e-50ca-bf10-19b7ae01b8dd | note | Category - IP
5ce5d4b5-1650-50ad-b7ac-e7018eed5dc4 | note | Responsibility - SE/PE
85f5510d-9e4b-51d5-95f1-bdbad255aed2 | note | Verifying Documents - This Checklist
502d9781-34f5-5936-a265-39ed067a5dfc | date | Date Completed:
c0b0b0bc-1f4a-4688-802f-5f455ae1d268 | checkpoint | 4 - Wire Wall Soil reinforcements-Connections
36fe0555-b4c6-511f-9631-8c89e10aa8d1 | note | Reference - IFC Drawings
170d7908-0054-5315-8387-b4f3c22214b8 | note | ○ Schedule of lengths & Connections arrangement:
684201c5-0acb-51a1-9e3a-04c59fdc5552 | note | — MRP-103-C-RFL-DRG-35-RBK-CSW-1901 to 1903
77d6d55a-f0ef-503f-b6d0-03ea36f6d94b | note | Acceptance Criteria - Grid Strips are to be installed to the wire facing units in correct length and to the correct locations based on the number of grid-strips.
1964c1dc-43c0-5af5-a8c0-e1bfe744b096 | note | ○ The first layer of grid-strips are to be ziptied or connected via hog rings to the facing units.
80f51798-676b-56c1-89e5-4e19f0d5de59 | note | Method - Visual
120f6039-e306-5dd5-b284-fe36c0b45ad0 | note | Frequency - Each Fill Layer
fb07ff77-93d4-5cf1-b9e3-780128e6a670 | note | Category - IP
1eaf0048-bb67-5b0e-8148-5c68c655ee7d | note | Responsibility - SE/PE
fece0679-21a1-5075-bddb-351562debe19 | note | Verifying Documents - This Checklist
6e4db642-d65f-501d-be31-e85831855c7e | date | Date Completed:
d1653744-e319-45d2-9224-7a7ae142c77f | checkpoint | 5 - Soil reinforcements-Plan arrangement
3edcfa25-3339-5cec-8d95-7b5206971745 | note | Reference - IFC Drawings
f558fb60-4bba-51d9-b0a2-5ad21a0862f7 | note | ○ Arrangements:
5114da55-15aa-588a-91ab-4c002522085b | note | — MRP-103-C-RFL-DRG-35-RBK-CSW-1101 to 1105
1ec55e28-9cee-57dd-b46b-3ba051077701 | note | Acceptance Criteria - Plan positions of Grid Strips are to be as IFC Drawings.
6917b2f1-f7ee-5a14-856e-cded87c14fe2 | note | ○ Grid Strips to be placed perpendicular to back of panel where possible.
1bfd7017-3d40-5ff2-8ef3-5d08d56be29f | note | ○ Grid strips shall not overlap
e3d39968-dbbe-553d-ac1e-6f569e27f887 | note | Method - Visual
69788654-cebd-57a0-9c82-6d906f7c9d4f | note | Frequency - Where applicable
378ad2cd-33f2-5559-b351-006b68fce136 | note | Category - IP
f0744f2c-1c10-50b7-b34b-677ca4e22cf3 | note | Responsibility - SE/PE
514fee43-a9a6-51f9-8a34-d1064e318a21 | note | Verifying Documents - This Checklist
9dc47a78-90a3-5919-addb-aa4915fcf19b | date | Date Completed:
e95cf704-ea7e-4e8a-a8e9-44f472ef6179 | checkpoint | 6 - Soil reinforcements-vertical/horizontal deviation
54a59b35-df11-5527-a736-7a2605d37ebc | note | Reference - IFC Drawings
6249c6e6-4596-5c75-af4e-88cf00927841 | note | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1002
9499d05f-2ccf-5432-8938-623fc47cd4eb | note | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1102 - 1103
edf6d47e-13ea-5e39-942a-72d996c0b44b | note | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1701
569955b3-4b00-5cbc-aa45-1b812ac9473b | note | Acceptance Criteria - Where grid strips are in the same horizontal plane, ensure 75mm Min horizontal clearance between grid strips
a40d4201-ee31-517b-88ae-6d73b387f14b | note | Method - Measure, Survey
6584f475-2e15-5eed-842b-aac8c46814ae | note | Frequency - Each fill Layer
cabb36bc-ff61-5c7d-83c9-a9a4c6994a65 | note | Category - IP
115d7cde-a23c-577d-a87c-7b0a91e8f10f | note | Responsibility - Surveyoe/SE
cb8c5668-9b9f-5fca-b295-e7f4669a2366 | note | Verifying Documents - This Checklist
ef541ac9-32b9-50f8-b05e-3f90b40c0579 | date | Date Completed:
7d4efc32-1dd3-4f34-a031-c6a4d846f033 | checkpoint | 7 - Soil reinforcements-clash with drainage
071589d9-5665-57a7-9a5c-fd2c544166ed | note | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1101 - 1105.
3b38e037-b96a-57ca-a48d-ba3fa212a9e1 | note | Acceptance Criteria - Avoid clash with stormawater pipe as per IFC drawings
14c92d28-11a7-52d6-9d03-a73f1e3517bf | note | ○ SKEW TOP LAYER OF GRID-STRIPS HORIZONTALLY TO AVOID CLASH WITH DRAINAGE PIT TYP. MAX ALLOWANCE SKEW ANGLE =20 DEG.
cf601044-16f8-578e-a8e2-a95f619880a3 | note | Method - Visual
d5c3949d-af77-54a5-9686-f500dc574ab9 | note | Frequency - RW02 and RW03 stormwater and grid-strip interface
fd5f97b1-b716-5caa-9a6a-8026e04abe63 | note | Category - IP
502a597b-6d00-5983-95a5-bcbc58537537 | note | Responsibility - SE/PE
3935cf9c-3bdf-574e-baa0-5fe619ae6c31 | note | Verifying Documents - This Checklist
5177a997-4cf1-5c9b-9043-0703ea1b586c | date | Date Completed:
392bda33-d4fd-4390-9ef5-f583fb10c1df | checkpoint | 8 - Fill-Placement
64a9e96e-1ad9-57a2-9a78-a22e1e471ea4 | note | Reference - VR204.10
b69c3b92-65c4-5110-a0fe-da0bad8a41e1 | note | Acceptance Criteria - Select backfill shall be placed in accordance with Vicroads section 204.
e00e220b-1b21-5d4a-9fad-8a4606b3a27c | note | ○ Fill layers to be spread and compacted in layers not exceeding a compacted thickness of 200mm.
a16f9b16-84a2-57c3-9a0b-29791699fe94 | note | ○ Fill dispensation to be granted by superintendent to increase thickness layers.
e25a6bf3-a2e1-538c-8efe-352364f4cef0 | note | ○ All RSS fill layers to be spread from face of panel to tail of soil reinforcing straps.
5154c9d5-f7d9-5410-ad6e-b3a923e14661 | note | Method - Measure, Visual
2c3c774f-71e9-5826-88c0-6f0edf7e8100 | note | Frequency - Each fill layer
f49938c1-cc7c-5c4f-8ec8-30bae3541615 | note | Category - IP
953a0d1e-89f6-5473-87a3-0fe568f4616b | note | Responsibility - SE/PE
7a971d51-edec-53e9-8b6b-b07200292977 | note | Verifying Documents - This Checklist
9052178f-d56a-5f32-ba2d-4a603bd07cf4 | date | Date Completed:
bb0a62d3-abe5-4460-a106-69e99dba9d0f | checkpoint | 9 - Fill-Placement compaction
6f1112d0-807c-5cfa-a762-11f69c4cadf3 | note | Reference - 204.111
1db14881-4055-5fc9-bec4-cad0853c4c49 | note | Acceptance Criteria - 0 - 0.15 m Light weight hand operated DPU
3dceee31-e28a-55da-a2a2-8374fd8ff076 | note | ○ 0.15 - 0.30 m Less than 5T Roller
31b8dbe4-6bf4-5bcb-a25e-b095bfef1478 | note | ○ 0.3 - 1.2 m Less than 10T Roller
38f86263-aa9c-5dba-a278-9b3ad62262a7 | note | ○ 1.2 - 2.4 m Less than 20T Roller
8b589c92-f962-51f3-89ea-7b7c2bd9fb18 | note | ○ >2.4 m Less than 35T Roller
6ddd70aa-2016-541f-a488-25a8e71d62a7 | note | Method - Visual
c886e4ac-a6af-54be-9512-3a7ebd4a1f18 | note | Frequency - Each fill layer
2b12aba1-01fd-56d6-abb6-3d7b0397e9f7 | note | Category - IP
a8cb3781-4801-56c8-a10b-56f18d4c561f | note | Responsibility - SE/PE
623f7913-ffe1-54ab-8b82-5fa8255eab52 | note | Verifying Documents - This Checklist
f6ccbb0a-df9b-57f8-b23b-eae871777ca7 | date | Date Completed:
a9ee7274-f918-4eb6-a7bc-ad57a98893c6 | checkpoint | 10 - Fill Test roll
bb962126-c903-5faf-80b8-9644f87ad58d | note | Reference - VR 204.12
54c36f5a-cdf6-5a7b-b0cb-97c4eb5cb635 | note | Acceptance Criteria - All layers of fill shall be test rolled in accordance with VR 173. The contractor Shall provide for the superintendent to be present during all test rolling
89dd0154-2cd0-5a1c-ab23-7a1c9a991626 | note | ○ Static Smooth drum roller with a mass >12T; or
2a4d561a-b088-59df-81ba-c5befd506975 | note | ○ Tandem truck or water cart with a mass >20T.
915321c4-8be2-5b10-bc64-59f580ba62dc | note | ○ No visible deformation or springing during test roll.
e5a540c8-91bd-533f-a6d8-6594251370b7 | note | ○ Unstable areas rectified as per agreed method.
fe458020-386c-55b2-a6e9-e95e9340afa8 | note | Method - Visual
a9d7d1d3-5e51-5311-855b-1fe70f6e0069 | note | Frequency - Every Fill Layer
a18684af-cda2-5b93-bd3f-f7f9450556c2 | note | Category - HP
5d0992cf-3dd8-56a7-b2fa-e0ff53865491 | note | Responsibility - Nominated Authority
34502a09-7649-5c01-962f-3b2d04a9b741 | note | Verifying Documents - This Checklist
924f744d-e244-5d05-a061-c32f3dc2d700 | date | Date Completed:
baa090e4-a55f-4770-8cd3-6d6b42716d9c | signoff | AUTHORITY HOLDPOINT
fc7396c4-4ac3-4671-a7d9-62c8cc02068c | checkpoint | 11 - Select back fill-Compaction Testing
a34b09fe-844d-5698-a2bb-517ab678b585 | note | Reference - IFC Drawings VR 204.14, VR 682.16
6115cfe2-4302-5163-b212-a17f175b6dc1 | note | Acceptance Criteria - Testing frequency shall be in accordance with Vicroad Specification section 204.14
10a1b9ec-a987-5023-9a99-0e96665f0c44 | note | ○ Moisture content shall achieve minimum characteristic value of density ratio: 98%
d7342f3c-e20f-5308-97f0-784b18b00f2c | note | ○ Moisture content of backfill shall be maintained evenly at all times. Moisture content shall be +0%/-2% of the optimum moisture content. Any backfill material exceeding the optimum moisture content must be allowed to dry.
04092a5a-d59b-5006-82bf-6520adce5802 | note | ○ Attach: Compaction test results
fff44d36-10a1-5178-a63e-d47accaa76bd | note | Method - Document review
d327b70c-330d-5618-9648-ff8eb399f0b9 | note | Frequency - Each Fill Layer or every second layer as agreed
888b4811-e19d-521d-8029-140c26073820 | note | Category - IP
de3c29e1-4d8d-5481-97aa-8d98b38ef38b | note | Responsibility - Nominated Authority/PE
bbd89d2e-e7ea-57fa-a640-a28ee780477c | note | Verifying Documents - Attached Test Results
afa61479-2241-5241-aee6-94347f4165ec | date | Date Completed:
44911999-52a0-406b-8a63-d3ad20933415 | checkpoint | 12 - Select back fill-Test frequency
38157e05-c6b3-5a54-bffc-3431db92fe3a | note | Reference - IFC Drawings VR 204.14, VR 682.16
16d55bcc-0d3a-56df-be08-362689118151 | note | Acceptance Criteria - After three consecutive lots of like material have achieved the specified requirement, reduce frequency of testing of subsequent lots to the minimum requirement specified in table 204.142:
4b59600a-ef41-5fc6-90e6-ced718c3c9fd | note | Method - Document review
5fad916d-b8e3-5a15-abad-5c5cfcac78fb | note | Frequency - Each Fill Layer or every second layer as agreed
31de1d54-9cf6-56c0-b590-bebbba3951be | note | Category - IP
c5888cae-8b35-5b98-8e99-afb79fbf2ec1 | note | Responsibility - Nominated Authority/PE
f7bb9517-31eb-5583-a9f6-a8556a00e419 | note | Verifying Documents - Referenced Lots in This Checklist
49aa5ba1-a718-59ec-8de7-6abf96c76bea | date | Date Completed:
35db4cb2-6a96-47fb-94b0-5e08e2701a48 | checkpoint | 13 - Survey Conformance Asbuilt
66200a78-daed-5188-ac0e-9b2012cce56e | note | Reference - MRPA Quality Management Plan
51e84a2c-6d86-502b-afdb-a5e71d58ad9e | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances
92def6da-65a7-5ba3-bcad-4e42940832bc | note | Method - Document review
217cbd2d-2a2e-5d8f-9434-3808a69ca792 | note | Frequency - Each Fill Layer
fb992212-df27-5180-8d9f-a89c296442ef | note | Category - IP
aed0588a-934b-5aad-b90f-21974ba13934 | note | Responsibility - SE/PE
672edf1c-88ea-56e1-b04b-500cd092c5ab | note | Verifying Documents - Attach: Survey Conformance As Built
7a2cb792-3d21-5c1c-bed9-748226cbf6b9 | date | Date Completed:
61513cea-aafd-4173-bf88-7a938724fe60 | checkpoint | Final Inspection
83c3899a-cfa3-5e94-9fe4-757b0a46bfef | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9debb93b-2402-5b84-b8e1-aa38655a9b57 | textbox | Name:
9bd73327-a7b0-5f40-852a-749a77dd77ca | textbox | Position:
f5c7ad29-103a-570a-bc06-f2db7144f4fc | date | Date Completed:
0fb701c6-fbda-40a9-8074-9563482397dc | signoff | Sign ITP
51fd4c16-e878-4445-a9e4-d9762bde98cc | checklist | CHK-010-CIV-FRMS-RSS Walls-Pre-cast Panel Installation Rev 0 |  | CHK-010-CIV-FRMS-RSS Walls-Pre-cast Panel Installation | 56b48625-080b-4af9-bb4c-3c16beddaf02
815cd6f9-eb75-443d-9d39-c44e4f82a158 | section | Details
9068ff41-7ea4-4f77-a205-c974f09955c0 | checkpoint-no-value | Referenced Documentation
42d3f000-b2b7-5627-a1dc-31aaae9553be | note | Document Title: CHK-010-CIV-FRMS-RSS Walls-Pre-cast Panel Installation
76da9a40-f005-5461-a0e6-7b085e877593 | note | Checklist Description: RSS Walls - Panel Installation
7d25de3c-b077-51e9-8446-0819d4c13c50 | note | Discipline (e.g. CIV/STR/RAIL): CIV
52c7f690-e229-54ee-8a7c-5e6ce8caa73e | note | Revision Number: 0
4574008a-cf63-5be4-8894-3002d9d7908c | note | Revision Date: 03/06/2024
07e6e93a-f054-5fac-ad2f-8d27a6116620 | note | ITP created by: Kamel Alshobaki
dfaf884b-6bab-51d9-95be-6709308099ef | note | ITP approved for use by: Pradeep Talasila
b8507329-9a64-4cca-bbb7-f695b485359a | checkpoint | 1 - Panels-survey set out-Tolerance
7ce4365a-115b-51be-b0a7-d2086585b8bf | note | Reference - VR 682.20 IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1001
d8792189-4247-5c0a-8181-28361d5d241b | note | Acceptance Criteria - Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
a1a44cde-9594-50fc-894b-2ea9baa4d124 | note | Method - Measure
135994e7-a466-5fc6-bf3d-90c6187d4a91 | note | Frequency - Base course panels
1bb7f4f9-835b-52dc-8e12-176e84e6fe89 | note | Category - IP
be16add6-7114-542c-b8dd-d66c9c459558 | note | Responsibility - Surveyor/PE
26f49fc4-377b-58bc-bdd0-a737af155aea | note | Verifying Documents - This Checklist Signed-off
4f3bac2a-9d96-5372-a583-f9b47d1db0da | date | Date Completed:
3466215c-7ffd-4973-baa6-f892a696f42b | checkpoint | 2 - Mark-up panel for construction team
e103b92c-f1aa-5435-b297-534875e7f24f | note | Reference - IFC Drawing:
aae23bef-4572-5ba2-9551-744e85eb48c2 | note | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1101 to 1105
d9fb62a6-10e0-50c4-86b6-7fabce0a4b5d | note | ○ MRP-103-C-RFL-DRG-35-RBK-CSW-1108 to 1404
bdba0e0c-d1c9-5278-a434-6e6c37415c4e | note | Acceptance Criteria - Mark number of strips per row on the back of each panel.
fada1840-e6c8-53d1-9c82-2bc440c0df04 | note | ○ Mark design location (Wall number, row and column) as per elevation drawings on the back of each panel
ec13d689-9a21-501d-9067-43c305e08027 | note | Method - Visual
ae920f32-0c9c-5e79-87cf-e139715fa080 | note | Frequency - Each panel
a18a8dbc-9858-596f-8e71-c323434bfcca | note | Category - IP
f750bf34-e3c0-595a-8037-a43a7c7d90f8 | note | Responsibility - SE
4a5cd85a-231c-5ea4-9b5f-ad75c4d6dcde | note | Verifying Documents - This Checklist Signed-off
60777bad-5409-59c5-acef-238e98f2e3d2 | date | Date Completed:
711119e8-3432-46ce-b07a-911f6e0b3503 | checkpoint | 3 - Panel installation
16819d5b-d582-5d34-8dff-3ade07a69a72 | note | Reference - IFC Drawing:
d879ee47-2783-55c6-88b8-ec3e9a02f658 | note | ○ Instructions: MRP-103-C-RFL-DRG-35-RBK-CSW-2001
6eb36539-4989-5346-84dc-dc92167f0420 | note | ○ Weephole Locations: MRP-103-C-RFL-DRG-35-RBK-CSW-1108 to 1404
b286d7c0-bc66-5c43-b2f8-9011a4ee6918 | note | ○ Archtectural pattern drawings: MRP-103-C-RFL-DRG-35-RBK-CSW-1104 to 1604
498d37d3-f4c7-586c-8ea4-80fdbc23591b | note | Acceptance Criteria - RSS Panels are to be installed as per IFC Drawings and specified schedule.
6f92f8f7-ad75-58b1-a669-3cf41116b6a9 | note | ○ Check for correct architectural pattern
4e950a0e-6b9f-5494-8b92-d199b041ef8c | note | ○ Check for Weephole Locations
fbd9f423-ddff-5a1d-90e7-7156e25b8b4b | note | ○ Check the 1 in 40 slope is to be maintained
e1a52e4d-6f0c-5b8e-b4d7-85858c399dc2 | note | Method - Visual, Measure
fe091361-06b9-5bd0-8e1b-7c7dbe544fbe | note | Frequency - Each panel
a8f9c232-f8a4-5bcc-8886-2304265000df | note | Category - WP
2d0b9fd9-3954-5e3b-b54a-5c008dd7e223 | note | Responsibility - SE
28ae80b3-3fc2-5890-a67a-2c624ffd60ce | note | Verifying Documents - This Checklist Signed-off
acb86cef-2fcf-5cb5-81f8-176e8ffe694a | date | Date Completed:
1792d6a7-59f7-4068-89f8-0dc1fb39efb4 | checkpoint | 4 - Bearing Pad Installation
d20c8144-4db2-52df-9180-feec40b93a86 | note | Reference - IFC Drawing:
3bb05c7f-c1c2-5b47-acb5-ff17430b1c7a | note | ○ Instructions:
95761944-fab2-59df-9255-27687af3aeab | note | — MRP-103-C-RFL-DRG-35-RBK-CSW-2003
90ae4931-b2f2-5b46-afc6-23e94e5669b9 | note | Acceptance Criteria - 3 x bearing pads must be installed per panel - Centre of the outer bearing pads must be 200mm+/-10mm from the edge of the panel
903e5185-7556-5c18-b82c-5d9ec58bcf1b | note | ○ Check the 19mm nominal gap to be maintained
e68aa250-be26-5365-a8de-c95e4673b166 | note | ○ Install 3 Bearing Pads at rear on top of panels
d080dec1-d118-58ad-a7a0-d6feef8a92e8 | note | ○ Above must be checked with Surveyor prior to backfill
96bd4411-b998-53c1-aa40-d92add4853a3 | note | ○ Note bearing pads shall not be installed under base row panels
f85c07b8-43de-5e59-bea5-233f33709d69 | note | Method - Visual
619e90e3-deda-5f67-bb24-92f68b6e3f5a | note | Frequency - Each panel
4c7dc567-47e7-52d5-a3ed-29c89d41ae28 | note | Category - WP
85300c54-cd59-5a18-a036-ac5d3ddbaea0 | note | Responsibility - SE
2396145a-a8a2-5e53-9dd1-44de887fb23d | note | Verifying Documents - This Checklist Signed-off
2167ed57-4d76-54bb-abaa-0e0b7a1c3b95 | date | Date Completed:
df3308d9-73b1-4aba-8b33-eedf04d69475 | checkpoint | 5 - Panel installation-Abutment interfaces
c2b3a185-38a0-5ece-9097-33e946bb75e7 | note | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1106
83b6a72c-d5b7-5a1f-b4e6-2d1fef6b27f1 | note | Acceptance Criteria - Panel installation and abutment interfaces
689e4266-b599-5b0c-9d4b-6124e8d87322 | note | ○ 30mm nominal gap between panels and Abutment wall is to be mainatined
97fadabe-51a1-5576-bdb0-e9beb8df8e32 | note | ○ 150mm wide x 14mm Folded Galvanized plates (Grade 250) drill and fix to as per IFC drawings with Galvanized M12x75 Long Excalibur screwbolts at 500 CTRS Typical each wall.
eeed23ef-dfdb-59d5-b07b-3eaee5f1d080 | note | ○ 600mm wide BITAC tape installed
a38d534b-fd05-5fe2-a802-b9ecb6391291 | note | Method - Measure
0e9eb185-69ad-5cdb-a0d2-13ecf7afc041 | note | Frequency - Where applicable
4fe36d0f-5e09-5e78-a647-768dff0c7b67 | note | Category - IP
169be49c-d5ac-5b91-bba1-a168fdb00221 | note | Responsibility - SE/PE
0e8ec213-33fc-537c-96ee-860b39ccd551 | note | Verifying Documents - This Checklist Signed-off
b3888153-35fa-5d02-96d3-c5cb0b735e30 | date | Date Completed:
678b095c-b80c-4868-84d0-a8f672cc083e | checkpoint | 6 - Filter fabric -Installation
ccb134a0-46b4-59d8-a454-1b96579df67d | note | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-2003, VR682.11
b29a7abb-bd76-516a-8d66-d68fa41c4c7b | note | Acceptance Criteria - Install Filter Fabric against all vertical and horizontal joints
142372a5-6721-5d63-b8ee-8b20562b8d87 | note | Method - Visual
4c62b0fb-faf4-5dfe-b5e7-f3a89fe80115 | note | Frequency - Each course of panel installation
b5919fbc-9ee1-5524-a16a-008f093f6df7 | note | Category - IP
70f45823-0c89-5cce-bb23-efd31893051a | note | Responsibility - SE
cc5d7c90-036b-5e5a-b2f3-13de126c6a73 | note | Verifying Documents - This Checklist Signed-off
47d690b6-0118-5e2b-9e32-13cdca7f17c2 | date | Date Completed:
9aed6fa3-1ae1-4bc4-a2c2-d5ae600e5a85 | checkpoint | 7 - Drainage-Strip Drain
a97be389-ef9b-593d-95b8-d75af1c7a21b | note | Reference - VR682.11
e3194a80-8e52-5f1f-8f66-2a1c814b0745 | note | Acceptance Criteria - Install 300mm wide strip drain between precast wall panel vertical joints.
b16b821e-4179-50ad-b57d-e31566e95a7b | note | ○ Strip drain to be encapsulated by nonwoven geotextile in accordance with section 682.11
9bd546b5-de8b-59bc-b668-c5c09850df2a | note | ○ At every vertival joint between panels in RSS wall, ensure no gap is formed bewteen strip drian and RSS panels
d82ca3dd-4db3-5faa-bccf-147fbaf1e365 | note | Method - Visual
5cda2971-7d9e-5c78-acfc-ca8dd822f5a6 | note | Frequency - Each course of panel installation
656a0acb-8fc7-511d-b28b-b047e22cba55 | note | Category - IP
beb521c4-8f21-5c6e-80b4-29d7d261326e | note | Responsibility - SE
45dec738-bf11-5d16-bc82-a5f9530d71f7 | note | Verifying Documents - This Checklist Signed-off
c70833d7-f8c5-5e9e-befc-459f46b2d3d5 | date | Date Completed:
68429216-57e2-49ee-916d-3baf02038273 | checkpoint | 8 - Panel installation-Survey reference points
742945c4-f9b5-5181-89ad-76dad7718341 | note | Reference - VR 682.20
39b6ef58-7165-5acc-a389-017ab606ae30 | note | Acceptance Criteria - To ensure compliance with the tolerances specified in clause 682.20, the Contractor shall install stable and permanent survey reference points on a not more than 5 m (horizontal) by 2 m (vertical) grid covering the whole face of the RSS
a861b62c-488a-5333-a6d6-0fcabb761734 | note | Method - Visual
2e0ae265-fa02-5487-9476-394cbbc33de8 | note | Frequency - Each course of panel installation
140ec9f6-6e3c-57ed-a4e6-287c33caa5bd | note | Category - IP
0907231c-0767-562a-a751-b780efb9f445 | note | Responsibility - Surveyor/SE
390c7957-0250-5d3b-ac7b-909244b9cd29 | note | Verifying Documents - This Checklist Signed-off
58702469-9f16-5806-9e54-3c2d222cc0a9 | date | Date Completed:
9901d0f7-58e8-4903-ac14-6794324b9be5 | checkpoint | 9 - Traceability of precast units and records
c67d78c5-4e0c-59e7-a5a1-3cb523c3307a | note | Reference - VR 620.09
9de2a642-a173-55cc-b037-a09351a0f65a | note | Acceptance Criteria - Unique ID of precast panel is recorded.
82beaafb-b468-50ee-90b6-855b2b1916e2 | note | ○ ATTACH: marked-up elevation drawings or installation record with reference to panel ID
e5db0343-83c9-5dd1-9d29-0bb032628637 | note | Method - Visual
e8976025-ca9f-56a2-95dc-f2f8eed1d040 | note | Frequency - Each panel
2d6d6f37-572c-5d6e-ab14-b3ce3997e4d3 | note | Category - IP
d6065bbe-aa85-5b0e-92e1-0c19dbf9f53f | note | Responsibility - SE/PE
eab0e32e-6a8b-5ce7-a0d5-312992fa6f0a | note | Verifying Documents - This Checklist Signed-off
1c5d3b87-def5-5c34-b783-457a2b01d803 | date | Date Completed:
805b09d6-961e-42e3-a125-f2bd4157a164 | checkpoint | 10 - Panels installation-Conformance Survey
8de90046-f608-50f9-ad2c-ff6b62e3bd71 | note | Reference - IFC Drawings
430a3b99-70c5-5c6b-9b37-2955bcebee7f | note | ○ VR 682.06
1213fbf8-a62f-5e53-8b33-c9e4eddf95a6 | note | ○ VR 682.17
e71555b7-1cc2-57f9-a84f-8feb229b4d50 | note | ○ VR 682.20
74a0e06f-7682-514c-bcad-2a733f1f8f1c | note | Acceptance Criteria - The level and alignment of each course of facing panels shall be checked progressively after placement of each course and prior to placement of the next course to ensure compliance with the dimensional and positional tolerances stated in the design. The Contractor shall record the results of this checking together with details of any non-conformances and the associated corrective actions
cc1661dc-8461-59ee-ba41-eb1c59849f6a | note | ○ Relative displacement of adjoining smooth panel faces shall not exceed ±15mm measured normal to face of the wall
229fb4f5-a0b8-550f-a6a2-f7fdabf2ab1a | note | ○ Local deviation of the wall face at any location with a 3m straight edge, shall not exceed 15mm
a961fcee-aa93-59d6-b44e-464610bd5026 | note | ○ Variation in gap width between facing panels shall not exceed 5mm per meter length and 10mm over the full length of the gap
cc63cdce-e888-5ec5-8611-048349725b3e | note | ○ The wall level shall not deviate from the specified level by more than ±20mm
77926d08-2487-5163-8511-640c48b841e3 | note | ○ The tolerance of position measured at the top of the wall face shall not excedd 5mm per 1m of wall height
85aed232-b026-5a45-8eb5-7e7021ffae96 | note | ○ The verticality of the RSS wall facing shall lean backward at a minimum slope of 1(H) in 40 (V)
6a4b6995-eb7b-5f59-a0f1-31bfff43b367 | note | ○ Attach: Survey Report
809bb6ca-7843-59c8-a4d6-879f17aa3479 | note | Method - Survey, Measure
3346d514-2669-5272-97f3-9700b987c99f | note | Frequency - Each course of panel installation
85ca7e50-46e4-5ff6-be5c-f176eaec86ac | note | Category - HP*
29eda537-4a6f-5384-ac88-afbe54e6cc4a | note | Responsibility - Surveyor/PE
dda1b6f0-5c75-576f-8b12-7e9b4fd38242 | note | Verifying Documents - This Checklist Signed-off
0cc17f5e-75ec-5385-85a1-58992977ff33 | date | Date Completed:
28f52914-3f4e-4b3e-9ae8-f757b8d10630 | checkpoint | Final Inspection
4c81a5fc-5d66-5d38-b7b9-aa3e66a96f0b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
50e09fb5-a527-589d-9628-6a6193c66448 | textbox | Name:
c313acd9-8af7-5335-b029-bf9d4dd75add | textbox | Position:
e2be75a6-fab7-5dfa-824f-4809ee232aef | date | Date Completed:
e2e88f01-f973-4e30-a02d-cf948e41c04c | signoff | Sign ITP
1ae05afe-6bc9-430a-beec-a823e41257af | checklist | CHK-011-CIV-FRMS-Precast Material Inspection Rev 0 |  | CHK-011-CIV-FRMS-Precast Material Inspection | ba5f3798-4553-439d-b799-743c1c7d5682
b89f12d6-0143-4e54-a91d-b0d99389eae7 | section | Details
a300a725-627e-4da0-81a1-78e5b0f4094e | checkpoint-no-value | Referenced Documentation
f2a8c443-e310-5c2e-8767-5a6e89a9ef8c | note | Document Title: CHK-11-STR-FRMS-Precast Material Inspection
77d1397e-4490-5be7-aa12-ade40641e705 | note | ITP Description: FRMS-Precast Material Inspection
82c5ee01-5283-5b60-bbb6-29fdc973504c | note | Discipline (e.g. CIV/STR/RAIL): 11-STR
9caefb27-5770-545f-ab0a-c671703b13cc | note | Revision Number: 0
82d40619-bc5a-5301-9cb7-8f2f5e5c27e2 | note | Revision Date: 5/08/2025
7f718417-b891-5103-b89e-a0a21390f03f | note | ITP created by: Jaidyn Kempster/Jonathan Kogan
968885cb-6012-5d59-b1c6-ee9ac2c69c55 | note | ITP approved for use by: Pradeep Talasila
b446b682-45b2-464e-927e-ee03bde21eb7 | checkpoint | 1 - Delivery Details
fefdc8d7-79af-578e-9e74-7885fc77dbf3 | note | Acceptance Criteria -
5c1b7e63-87b5-5fd7-a835-a3b21303c004 | textbox | Enter: Delivery Docket Number:
96a072dd-9118-52fa-9b9e-be3c7ce55ec3 | textbox | Enter: Delivery Date:
91564242-0576-59d1-85a3-e03bed6e76a2 | textbox | Enter: Element ID (s):
866cff5b-762f-57ee-8f15-6bc5e2d9e14b | note | ○ Attach: Delivery Docket and packaging Slip
33958c16-5654-564b-80d1-88882e834589 | note | Method - Document Review, Visual
464cf35a-b86e-5fb4-8243-80b0ad975de5 | note | Frequency - Each Delivery
68745ebf-fbc4-560c-a55f-9203afff74db | note | Category - IP
9bf8e342-bd89-56a9-b06b-4a4a62e352df | note | Responsibility - PE/SE
13d00d3f-2d5e-506b-aa9b-396e33cf1f9f | note | Verifying Documents - This Checklist
8b6cd1f8-288d-5439-9398-cc9880bba560 | date | Date Completed:
bbd3e832-526e-42d8-93b6-e950b1a13089 | checkpoint | 2 - Packaging Inspection-Quantity
d131b94c-f531-5f1d-82c8-d5cf742b32bb | note | Acceptance Criteria - Does the number of packages/items in the delivery match that listed on the freight list and/or docket?
6e12c458-f80f-5c2d-80b6-efcdec25acd1 | note | Method - Visual
8beb0c3c-958f-5f2a-a9c1-710cdb165434 | note | Frequency - Each Delivery
75e0bffd-c123-59d7-9f20-70e2a648f3be | note | Category - IP
16142a92-6391-5ccb-925d-f47c92a53fae | note | Responsibility - PE/SE
5d3c76db-abc3-5f7f-bf50-d18b52a3a0b9 | note | Verifying Documents - This Checklist
f21cb78a-c5b6-5569-b6b1-975c6d156396 | date | Date Completed:
32ce5fe9-92de-419b-85fb-87d8a8965f5a | checkpoint | 3 - Packaging Inspection-Delivery Contents
712d2a4a-fea8-53c6-b2c8-b9f511e9388d | note | Acceptance Criteria - Have the correct precast elements been delivered? Check labels/markings, birth certificates and check actual dimensions against dwgs to make sure. Check that elements have the correct number of lifting points and hold-down brackets.
e68df20c-c0c3-5762-833c-fe48a95a0df7 | note | Method - Document Review, Visual
161a9898-fcc6-5f49-abce-c49a74be820d | note | Frequency - Each Delivery
7436cf76-3a13-5c4e-993a-b1f3347f7815 | note | Category - IP
5bd08920-d9d9-54ac-995a-d5c0f67fe7d1 | note | Responsibility - PE/SE
5d690919-fdd3-541b-95f2-75b97c01c730 | note | Verifying Documents - This Checklist
a375277a-f5d7-57a8-9228-ac1943373417 | date | Date Completed:
680e2b37-9030-4700-be1c-54835982e25d | checkpoint | 4 - Packaging Inspection-Birth Certificate
4bc39f44-ffdd-5c53-b5ac-25cad44f3975 | note | Acceptance Criteria - Is the delivery accompanied by Precast items Birth Certificates?
653db5be-240b-55bd-af19-708fd5e9cd96 | note | ○ Precast components are to be marked on the birth certificate.
30492be9-ef2e-5b62-bc46-4bb46913d098 | note | ○ Cast date and lot are to be marked on the birth certificate.
332ce011-d996-53e5-b5f1-f69625dc852e | note | ○ ATTACH: BIRTH CERTIFICATES
9e3a70cd-3f8a-556b-a2d0-b5f24f3c0991 | note | Method - Document Review
8f06f3a5-949b-59e6-8a64-6e0bd7b7b166 | note | Frequency - Each Precast item
b7d10fd2-dcc3-50dd-8b35-4437774d1a81 | note | Category - IP
f21ac370-ee36-5014-ac71-e7cfa936ce5b | note | Responsibility - PE/SE
00732bad-3fff-559c-b8fc-85204740d7ad | note | Verifying Documents - Birth Certificate
ec119b2f-0fcf-52a4-9493-4a31eb5355ec | date | Date Completed:
fc15280d-9bce-4cf1-ae74-c8558d2d6728 | checkpoint | 5 - Product Verification prior to delivery
13ce4cac-3048-507e-b268-14d305cd66fa | note | Reference - VR620.08
81c64dc4-65fd-5615-b7ee-f60f8cdf889d | note | Acceptance Criteria - Prior to delivery have the following evidence been provided:
93eca109-48e8-5d64-ae3c-556028bd2198 | note | 1 - Validation that the concrete strength is as per the 28-day strength in IFC (40MPa or 50MPa)
70445f58-3409-5f42-bbbf-de129c0a4c00 | note | 2 - Validation that the precast elements are least 7 days (168 hours) old?
ff9e2111-f5b2-5ff1-a627-746576b9f336 | note | Method - Document Review
b8a9b019-def7-509b-b496-fd2f3b0cd494 | note | Frequency - Each Precast Item
bc15c986-ce2b-50b9-9f18-2ac5d0256819 | note | Category - IP
b8c172c6-c2ae-5a10-ad46-1882d2b29857 | note | Responsibility - PE/SE
d692f2c8-2a11-5550-8332-0d9a6fc08ef9 | note | Verifying Documents - Concrete Test Reports, Birth Certificate
6c31dd9c-a0cf-51fa-8150-f18b768f7a7f | date | Date Completed:
96710db1-47a8-43cc-ac09-af5431f09d21 | checkpoint | 6 - Packaging Inspection-Transport
d7b9a61d-fb18-5a6f-9fed-635e41c65356 | note | Reference - MRP-103-C-AUR-DRG-30-RBK-CBR-0095
b41481b4-9c57-52d2-938b-9dc2033dba78 | note | Acceptance Criteria - Is the condition of packaging acceptable.
33e359d0-6561-573c-91d9-ba3e3109893e | note | ○ Precast items are protected from damage during the transport. Check for cracking or damage around dunnage locations.
eff59ad6-b627-5fb5-b283-65c2271522d3 | note | ○ Are the Ferrules capped with a protective cap
3f5aa960-d335-5b81-aa1f-b41e0beaeca3 | note | Method - Visual
ff9e06bf-d8af-5dce-9f03-612140d7b9f9 | note | Frequency - Each Precast item
a29c9fe8-58e8-501a-85d3-48a86785759f | note | Category - IP
0ac2925b-4b34-5381-a0e4-8460ba188fac | note | Responsibility - PE/SE
3e7ce03b-507a-5245-bb3a-9bceb2d083d3 | note | Verifying Documents - This Checklist
37254375-fe5a-5097-a49d-8d8c787fc76f | date | Date Completed:
04864c40-b726-49b8-917d-91bd250465e9 | checkpoint | 7 - Product Inspection - Markings
997cdec7-1ea6-5d2f-87a4-9bdc393ddbc0 | note | Reference - VR620.06
228e9152-079f-5c12-a9af-2f5871a9d740 | note | Acceptance Criteria - Are markings of the element on each element and approximately 40mm high?
63e2ea0a-8cd5-5bae-8175-54fb02ba1ba8 | note | Method - Visual
8af580f9-40fc-5be4-bd52-71e4a73fc67b | note | Frequency - Each Precast item
4658399d-4ae9-5377-b8b0-4b25496d8739 | note | Category - IP
ac1ae97a-2d85-50b6-b17e-d345a7403621 | note | Responsibility - PE/SE
78838f5d-ec5b-51c5-b6cc-34d652c7183f | note | Verifying Documents - This Checklist
b57d8fe1-823b-514e-bcb8-e93c22c042a2 | date | Date Completed:
157cf83c-82b7-4044-b9b2-cf87f24fc682 | checkpoint | 8 - Product Inspection - Reinforcement & Cast-in items
f64a71c5-1336-57be-ba70-72712e79cda7 | note | Reference - VR620.04
edf9d656-59ea-5915-aab2-4e4f73092f76 | note | Acceptance Criteria - 1 - Has any of the projecting reinforcement been damaged?
1260e4a5-728a-5122-9c39-202df8dff094 | note | 2 - Are bars as per shop drawings and within tolerance (±3 mm)?
513b5d34-4b28-5069-9844-e2971ca89e87 | note | Method - Visual, Measure
e977daf1-c795-5e92-949f-084995c1fe91 | note | Frequency - Each Precast item
b3ee7fe6-cd7d-5a2c-9341-419a645a6ac6 | note | Category - IP
5ce5a747-f9cd-5185-ae39-f71893721391 | note | Responsibility - PE/SE
3f1fceab-a831-59ec-87c0-eb2e7b13a87c | note | Verifying Documents - This Checklist
7fd124d9-55fe-5683-9727-d902cbde3e01 | date | Date Completed:
6ef3a413-db3d-498a-8370-d9fba500a177 | checkpoint | 9 - Product Inspection - Dimensional Tolerances
b06bc62f-a061-5c31-91e7-fb4016a91711 | note | Reference - MRP-103-C-AUR-DRG-30-RBK-CBR-0105
8b0ae4cf-5902-56ee-b3d2-3fe4b402b177 | note | Acceptance Criteria - Have the dimensions of the item been verified?
5f94d191-7a41-5207-8c3d-45f1ee2007d8 | note | 1 - Validation of dimensions
3c2eafb5-ec04-565d-ba0d-57b16b43569b | note | 2 - Validation of cast-in locatios
e441a63f-759f-57c8-95ad-f80585b09416 | note | 3 - Validation of Hog (if referring to beams)
93c7fa3d-a2a8-5b62-9822-06d8682479a4 | note | Method - Visual, Measure
e95ea0b1-9707-575b-b041-2ed8370ca8c8 | note | Frequency - Each Precast item
ad70575d-6e25-53a3-bb2d-ba36dd692f2c | note | Category - IP
909666bf-c3fa-57b4-a4e2-2d8877995a8f | note | Responsibility - PE/SE
94d51bc7-18f0-55f6-911c-f75217c13de7 | note | Verifying Documents - This Checklist
d273a80d-3f56-5656-8d6a-3a30a60c0f10 | date | Date Completed:
418adb97-2116-4617-b706-f1f93c4369b1 | checkpoint | 10 - Pre-Lift Inspection-Transport
89d2a99d-5ceb-5c90-b0b1-3cad47ed9e72 | note | Acceptance Criteria - Are the elements stacked in the correct way to allow for lifting per the approved lift plan? Check lifting points for damage to concrete or lifters. Is there safe access to lifting points and elements can be lifted without damaging the element.
8637aea8-9b81-5db4-a3f0-a83fc61593a0 | note | Method - Visual
6886a28d-7297-5c66-88a6-ce5e61d344ae | note | Frequency - Each Precast item
8372ea0a-3e8d-5d52-a02e-50f6d6e07735 | note | Category - IP
935e2a72-4185-5cbe-a8e0-bc711d7c16bc | note | Responsibility - PE/SE
cb40dc51-3057-5d54-9ab6-31a6b17a9b8c | note | Verifying Documents - This Checklist
b4af0133-71c6-5ebb-9d11-fde6a6259aec | date | Date Completed:
70350a46-1358-4d52-8efe-992c12d559e3 | checkpoint | 11 - Fault IDs:
890d4e91-49e2-56f2-bdcc-86310def9d95 | note | Acceptance Criteria - For each precast type delivered, check for the following:
7e174091-4525-5b87-9ae0-79bfc6a53b66 | note | 1 - Identification markings match the panel type
12756ca3-155b-5ef1-8053-e872b3cdae9c | note | 2 - Element fabricated as per drawings
cbb478f4-97e2-535a-bf60-1895dd950e71 | note | 3 - Cracks
06ba13d5-a858-5e4e-adb1-d3dddae2a9d2 | note | 4 - Spalling/Damage to concrete surface
20f5c31e-1324-5cac-9733-51590451429f | note | 5 - Exposed Reinforcement
521f9040-ff6b-523c-bd4c-ae13a19e0da5 | note | 7 - Incorrect Lifting mechanism size/Orientation/Quantity as per lifting design
293543ab-8246-5b95-bc90-b8db3f404923 | note | 8 - Cast-in items incorrect or damaged inc bolts, hold-down brackets, conduits etc.
9ebc6760-9d0f-5e9f-951c-7a027ce7da23 | note | Method - Visual
580471d3-2cc7-5ad2-b886-8ad35a96ef93 | note | Frequency - Each Precast item
c769ce7c-06fb-579c-898a-1003c6fc9747 | note | Category - IP
273ab867-d457-5f3f-bc33-8d05eaad848c | note | Responsibility - PE/SE
66707f1d-b84a-5828-80bc-d0fd9c72418f | note | Verifying Documents - This Checklist
3ac77d2b-8df9-5d8a-8852-8cd7d1a8a88c | date | Date Completed:
c21385e8-6e0b-408f-8b56-6d3600be52a8 | checkpoint | 12.1 - Check for Faults - 1
d947a05d-00af-53e5-9d51-6f0d0b1fd032 | note | Reference - Item 7 on this Checklist
00256565-71d9-5820-a609-a9fb70d1b242 | note | Acceptance Criteria - For Each Precast type delivered:
ba84f5e9-e522-55d8-b90d-b8e0cf76c817 | textbox | Enter: Panel Identification:
b64a19bc-60c5-5440-b838-0db82fe855da | textbox | Enter: Quantity:
9fcde057-80e4-5b64-abbc-689b2a13e40a | textbox | Enter: Fault ID if any:
008d1d08-5cdd-5e36-8283-251eed335e32 | note | Method - Visual, Measure
b17e16fa-09af-5ffb-8738-fde987a50b1e | note | Frequency - Each precast type delivered
f35d601d-7f33-5e52-a0bd-dc576a849240 | note | Category - IP
692a66b8-a9c7-53a5-a6e2-818a5487eeb5 | note | Responsibility - PE/SE
e993d105-bf5d-5890-a3bd-b277b7335c6a | note | Verifying Documents - This Checklist
649b8d69-7bda-50e2-95bf-b65bf155010e | date | Date Completed:
3626e204-82f5-4efe-bb93-79b0f10e29e1 | checkpoint | 12.2 - Check for Faults - 2
797dd441-eb08-591b-a866-b013a713e21e | note | Reference - Item 7 on this Checklist
73815205-4943-584f-bab9-8150c646a58a | note | Acceptance Criteria - For Each Precast type delivered:
9c04a66e-2937-5a0a-a9cb-88f475858e82 | textbox | Enter: Identification:
b055019d-f76c-5c45-ba22-ce02e80cf788 | textbox | Enter: Quantity:
fa88d490-ddbe-5be2-ad9e-c2aaa528cdb3 | textbox | Enter: Fault ID if any:
efeb35e4-4369-514e-8c03-5bf1981559ba | note | Method - Visual, Measure
ca9e12e3-0fd3-58be-b744-9930e8b9226f | note | Frequency - Each precast type delivered
cb92d287-cbf1-51f0-87ec-ba2e754368b0 | note | Category - IP
125799f1-c10e-5ee7-98bb-be621ff56e2a | note | Responsibility - PE/SE
7f88b290-94a9-5d33-aaed-3e9dd2c1a1b6 | note | Verifying Documents - This Checklist
46231fdd-ceef-5ec5-8d6c-8ddac66bb9b2 | date | Date Completed:
6b7dbad8-494c-4c6d-8d67-8cda7a165ef3 | checkpoint | 12.3 - Check for Faults - 3
03591f8b-a868-5bb6-bacc-fe01ca39a61c | note | Reference - Item 7 on this Checklist
f59368b8-463f-52bf-9fbe-5b07c80617f0 | note | Acceptance Criteria - For Each Precast type delivered:
874255cf-cf7e-5ab8-99d9-140e555c4de0 | textbox | Enter: Identification:
d131332e-28db-503e-b289-aec6da71df79 | textbox | Enter: Quantity:
6ce46d16-d34c-5059-922b-e6886acf1403 | textbox | Enter: Fault ID if any:
88f4d6c2-6684-579d-800c-facd7458ba49 | note | Method - Visual, Measure
236ba76b-fee6-5543-9340-e786c887c822 | note | Frequency - Each precast type delivered
6f8418aa-4e3a-5c2b-a864-f6420dbd8979 | note | Category - IP
e3a6d7f2-f068-5557-a53e-7c736a831a09 | note | Responsibility - PE/SE
af627281-e07d-5d10-99e8-2942ea0bac82 | note | Verifying Documents - This Checklist
6ee33d22-1dc4-5286-b3b2-2f62d803f902 | date | Date Completed:
16e4b4f2-d458-44f6-b0a1-b407b4b107b0 | checkpoint | 12.4 - Check for Faults - 4
01b0a46e-85c1-5e87-b457-287c9d248912 | note | Reference - Item 7 on this Checklist
ac35197c-f799-53e8-abfc-c67af635188d | note | Acceptance Criteria - For Each Precast type delivered:
766b80af-eb20-5262-a8d5-89793a51e079 | textbox | Enter: Identification:
116953b8-4c63-52f5-9663-c2c3ff2e9404 | textbox | Enter: Quantity:
9ea03206-7dff-5901-a43c-1233f1fdac46 | textbox | Enter: Fault ID if any:
8da2a847-315f-5b29-abf3-263871e5b477 | note | Method - Visual, Measure
a627574e-ce8b-5de7-88c6-d3499479c05c | note | Frequency - Each precast type delivered
e0c3ca8b-996d-5419-9645-a4e86b00b7e2 | note | Category - IP
38f0644c-4461-554d-897f-de7de8252ae5 | note | Responsibility - PE/SE
daba7fd3-4816-5c97-98bc-ff779907d4df | note | Verifying Documents - This Checklist
2229a7ca-b6c7-548d-b5f8-9b3b3b4a6faf | date | Date Completed:
42c9f2dc-e1e7-49c0-8012-995c98fbaee9 | checkpoint | 12.5 - Check for Faults - 5
4de36b29-606d-513c-963b-54bd67e017c7 | note | Reference - Item 7 on this Checklist
4c6f7112-3c5a-5a22-827f-fd32d628a177 | note | Acceptance Criteria - For Each Precast type delivered:
8da15c6e-ff6e-54fc-a523-6a861a296f86 | textbox | Enter: Identification:
1fd2f23a-1990-501e-b8aa-ac88f106b62e | textbox | Enter: Quantity:
2820f473-0a81-5d61-bf07-dddc760a534b | textbox | Enter: Fault ID if any:
08e3cb55-169c-5923-ad4a-35e0a984089a | note | Method - Visual, Measure
553b4f2f-7e45-5214-9c8d-408c56805729 | note | Frequency - Each precast type delivered
afd68329-aadd-5a09-8f80-4d6ff96ad2a9 | note | Category - IP
73a80858-1963-5f55-b297-4a11fcf62a27 | note | Responsibility - PE/SE
aa740cb7-5e4e-53d9-9634-d53bb6b95a62 | note | Verifying Documents - This Checklist
b5a9391b-5869-598d-a773-48cc3b95b94a | date | Date Completed:
e04838a6-12c5-4865-b53d-5c57fa543c45 | checkpoint | Final Inspection
382eef27-c856-502e-9ca1-01e28779874d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d3a5c3e9-ddb3-5aef-9a6c-f2b55e753761 | textbox | Name:
8ecb44af-0952-598c-81a6-972dfc0d7f95 | textbox | Position:
230276bb-14f1-568f-add3-3571480d212b | textbox | Date Completed:
bcfe8dda-8e63-4d4c-bdd7-f7586043dd44 | signoff | Sign ITP
ff6e00b1-fa75-46d1-8134-21f99024d96d | checklist | ITP-225-CIV-Ferris-Subgrade Preparation - Road Rev 0 | itp | ITP-225-CIV-Ferris-Subgrade Preparation - Road | e2f40730-87d1-420c-acfe-2863dacbdf28
7b52391b-ac4c-46eb-aa97-c87e43a5693c | section | 1. Referenced Documentation
91c7839a-a511-4b35-b05b-2542bbd97dbf | checkpoint-no-value | Referenced Documentation
bf33e101-ad81-5f2e-9964-02e0e1b3d770 | note | Document Title: ITP-225-CIV-Ferris-Subgrade Preparation - Road
c5dd3542-f14d-52db-8ecb-f037b967331c | note | ITP Description: Ferris-Subgrade Preparation - Road
9daedb8e-ee59-56fa-8559-fe277f14a176 | note | Discipline (e.g. CIV/STR/RAIL): 225-CIV
e60f056c-9e3b-5d66-aa18-8c112dbe0929 | note | Revision Number: 0
3ae169bf-8e9d-50f2-9534-36550dc8f3b3 | note | Revision Date: 29/01/2025
c433abcf-e7e8-53e2-9dde-694500980ffb | note | ITP created by: Kamel ALSHOBAKI
1926a7c0-4f7c-516d-a20a-2ed04920f8f1 | note | ITP approved for use by: Pradeep Talasila
677013aa-75a6-5e61-9713-1fec4345eca4 | note | 1.1 - Non Dependent
0c2f88b5-cf09-52ae-bc2f-0a3d570f2f4b | note | Reference - VicRoads Section 204
a55d49e8-0822-59d1-a3b1-aabea34c42a9 | note | 1.2 - Non Dependent
61296dc7-5a89-54fe-9c8e-d7e62c0d18bd | note | Reference - VicRoads Section 173
053c52e9-6bdf-4482-9e14-d898b6777902 | section | 2. Preliminaries-Materials
7458ce6c-0294-4a73-8e44-3fb50eb7603b | checkpoint | 2.1 - Material Approval
3ffb6e92-bb18-5f32-99d9-e5fb5fd5a575 | note | Reference - VR 204.4 ©
f5081114-e64d-5155-9d8d-cb8b2db514d2 | note | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
cd53a4b2-148e-54e9-bea1-f19eef2c2d3e | note | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
e80a7def-2c51-56e7-ae52-18171bdf4de1 | textbox | Enter: Teambinder Material Approval number
61b8257e-0828-587c-b7fe-197e95432d19 | note | Method - Document Review
caa6cc22-b394-5d60-92de-40bc49992345 | note | Frequency - Once, for each mix material
7e6ac380-ef2e-50cc-8569-356d2b936fc9 | note | Category - HP
57a64b11-3cbf-52f7-a011-44f2334c415c | note | Responsibility - Nominated Authority
cefeabd9-d4f5-587c-a511-2a74756600de | note | Verifying Documents - ConQA Hold Point Release
9a2d04e9-9b33-5b83-b108-42414b054ad3 | date | Date Completed:
4c55ead9-6dd1-47a7-8688-8ab84c22bbbc | signoff | AUTHORITY HOLDPOINT
c66d8a3e-4830-450e-ad87-a946b2930e54 | section | 3. Preliminaries-Documentations
a566f287-4302-4c28-b7b3-c1ba252bb057 | checkpoint-no-value | 3.1 - Non Dependent
bacf7db2-9c70-4551-b70e-7b7d05b6ef46 | section | 4. Pre-construction / Pre-installation Activities
fd261655-c7ef-4635-a0d0-7fdb7db4707e | checkpoint | 4.1 - Survey Set-Out
7e012c5f-4ecc-5bae-9245-09d3842bb4a9 | note | Reference - IFC Drawings
a7a10d69-b7ee-5d55-98e1-45ec12f5cbf5 | note | Acceptance Criteria - Area has been set out in accordance with the drawings
0f85ce9b-1043-5d83-a8fb-6aeccea9e2c7 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
18c2de51-fd6d-5f8d-bbe4-e7d53f1544d4 | note | Method - Verify
a780c087-756f-5950-9a7b-ba30bbecbc54 | note | Frequency - Prior to commencement of excavation
20957b8e-4635-5187-a7f8-586ccf020357 | note | Category - IP
24ad4ea5-5c91-5ad5-8714-77605761072e | note | Responsibility - SE/Surveyor
1003e945-1259-57e0-bd1d-d3da6d0eae2d | note | Verifying Documents - This ITP
5ec7d648-dff8-5425-815c-a2bd9587bd63 | date | Date Completed:
df582e2e-c453-4418-9d78-0885bded7aa9 | section | 5. Construction / Installation Activities
a88e2d55-5ce9-45a5-8a4d-87aeacc1b5dd | checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
8ee9c714-7e25-5363-8a31-66484e8f06ee | note | Reference - Section 204.06 (c), Section 204.06 (e) IFC Drawings
903517f0-d367-5fe3-ab79-5892848dd2d0 | note | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
f41c3d5b-36d3-5a53-a49d-5b0ee0a9a4f7 | note | ○ Assigned CBR ≥ 2.0%
21741f37-206a-5d83-8515-61c2be6bdf2d | note | ○ Assigned Swell less than 2.5%
084294ce-7fab-509f-bb1e-a4c03bff4c87 | note | ○ If parameters are met, rip and re compact to a depth of 150mm.
ff581b6e-96d1-5a22-8ce5-d85650d2d892 | note | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type B fill.
a79bd214-81e8-59ba-bccc-06c0a0e4b9ac | note | ○ If existing material needs to be removed and replaced with Type B Fill, ITP-CIV Type A/B Fill - Road is to be utilised.
ba1fa54e-c6ce-5671-a6ac-33bf39e192f9 | note | ○ Attach: Laboratory testing Verification:
fe74a465-4b0e-5988-a1ba-a45fec50724d | textbox | Enter: Type A/B fill Lot Number:
c69618f3-9645-58d8-ba72-8c08a24647ae | note | Method - Verify-Document Review
222c9a6b-6ed1-5191-b386-69c81ec067be | note | Frequency - Each lot
7f5c4927-dcd5-5772-a6c0-a2fcd4c7ebab | note | Category - HP
a87c3dac-e016-589c-8b96-4d626d1ddcc3 | note | Responsibility - PE/Nominated Authority
2e5e3a2b-ea20-5402-a08a-cf330180551d | note | Verifying Documents - This ITP/Test Report/Referenced Lot number
6a580748-91db-5929-8591-133f9a5660b7 | date | Date Completed:
c58e3e26-5258-419f-9885-5f2fdff63b13 | signoff | AUTHORITY HOLDPOINT
d974f8b1-b714-4500-9d2d-8de6adabcf0e | checkpoint | 5.2 - Material classified as silt
5561dc3a-c3d3-59f2-894e-bb80206f0871 | note | Reference - Section 204.04 b)
daf19a94-3a08-57e9-9d30-2f63d69f3c4e | note | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
5e3cb6b1-db8a-5e2d-8793-876637a59d0c | note | Method - Document Review
3fe9fb78-933b-55a0-b274-1e6ae5427a53 | note | Frequency - Prior to commencing
8f94f79f-6eff-541a-afe8-250ad9e86d09 | note | Category - HP
9b7d74c9-3151-5fd0-b4e4-18955a2e8e81 | note | Responsibility - SE/Nominated Authority
85432a43-c4f4-5345-a59d-3e79dda65f20 | note | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
63f4f722-e839-50c1-99f1-cadd85cb7b7a | date | Date Completed:
5b058efa-e993-4f0c-87b1-0378f77f67f6 | signoff | AUTHORITY HOLDPOINT
2863433e-ebf1-400d-8866-e250248cab22 | checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
0884a149-fe73-5b9e-912d-69b8c901e283 | note | Reference - Section 204.06 f)
677600ff-5e3f-571a-9363-3cd8552088ad | note | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
279f658f-8860-5fbf-a69e-4efbf95a29ca | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
8ab98008-ab9a-5ef5-a33d-fbd670c91881 | note | Method - Site Inspection/ Document Review
a2614f61-b412-5023-b453-ae9711ba55c9 | note | Frequency - Prior construction of the regulating layer
14290d39-3072-548c-ab8b-172ae5b6245b | note | Category - HP
84f9e883-8a61-594b-9926-a3e13a5fb2bc | note | Responsibility - SE/Nominated Authority
427fdc69-1e92-5770-8722-aac602b8c3d3 | note | Verifying Documents - This ITP
281425a1-5f40-5000-bff5-c31a986f3252 | date | Date Completed:
5222c264-cefb-4ab8-aefb-206ec37a054d | signoff | AUTHORITY HOLDPOINT
b45fc5c7-7156-4408-9fa2-a09a9cdf69ae | checkpoint | 5.4 - Unsuitable Material
920e1a88-63a7-5235-9601-d7e053eb9488 | note | Reference - Section 204.07 d)
3323b40d-63f5-5b2f-8395-040eda67fc53 | note | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
d808f85e-adce-566e-b7d9-304ace381dd3 | note | Method - Visual inspection
1e80a9bf-268e-5338-9a92-afaf6a3af930 | note | Frequency - Each lot
3266c92a-401a-51ce-80c5-2ae08c867079 | note | Category - HP
27a25fbe-df7a-592d-8767-6344630ed9ff | note | Responsibility - SE/Nominated Authority
2f337b49-7182-5911-997d-fe9638ac0e8c | note | Verifying Documents - This ITP
33a7e6a9-6d23-5f3e-9e89-b1e56ae8d5aa | date | Date Completed:
555b6d41-b254-4f1a-91de-d107134f8da1 | signoff | AUTHORITY HOLDPOINT
35d28ce1-e9ca-4056-a45e-f4d3951ec9d6 | checkpoint | 5.5 - Groundwater
c9de7442-2a04-5660-b334-2424f80efb7d | note | Reference - Section 204.06 h)
4302d040-b0fb-5711-b92c-500f3c10e87f | note | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
fc865157-fb31-580f-90d5-ec0d2ebc2a96 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
af5108ca-9a9e-5400-9da4-e5d91eafad3c | note | Method - Visual inspection
7b42affd-1cc2-5e9a-b690-f5607f7777c4 | note | Frequency - Each lot
d2db9434-da08-5fcd-8ff3-f4c5bbb8f82c | note | Category - HP
8ef2db1c-9a3e-546d-b033-db37086f4ffb | note | Responsibility - SE/Nominated Authority
6f24e728-a028-5ffb-bb06-21c1dd8a9fb2 | note | Verifying Documents - This ITP
edd2e88a-82fa-5484-973e-9a4a0cd31c67 | date | Date Completed:
66d85a0c-7c16-4f1c-9316-19d6048ca0ec | signoff | AUTHORITY HOLDPOINT
d4fc7723-7150-48f3-b0b5-55c3f718cf7d | checkpoint | 5.6 - Cut to Fill Zones
9569e63f-28e1-5489-b73e-5f5c4e645bf1 | note | Reference - Section 204.06 g)
1b921c92-29ea-5e2f-93ca-40032d6630ef | note | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A/B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A/B material.
00d88832-413a-56b1-8b52-ed17c471c374 | note | Method - Site Inspection
b47118e3-e7ae-57cb-aba1-0b64bc2a04af | note | Frequency - Each lot
92139080-67f0-5504-8763-3947b6105cb0 | note | Category - IP
3720c37f-ad89-5641-a5a8-22bdd2e9348f | note | Responsibility - SE/Site Supervisor
6eecb523-d677-5eb3-a333-f63ef44d2642 | note | Verifying Documents - Sign ITP
e858e123-63db-53f1-9f3e-2d63ac942501 | date | Date Completed:
08397a0f-5971-4477-b193-bd0a652c8c4a | checkpoint | 5.7 - Proof Roll
80b8fd6e-60da-511f-a93a-5ae95bea3f82 | note | Reference - Section 173
4e74c48c-d2f9-5ffb-9b5f-1741517465fd | note | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
2c3f852f-2796-5f4d-9792-5057cd792a4e | note | Method - Visual inspection
5604c166-1012-5541-b521-cf13ec37711d | note | Frequency - Each lot
9199ba2f-59ae-5308-ac98-5181208ad6fd | note | Category - HP
45a56bbf-5264-5ae8-a266-3bc496cfcc2c | note | Responsibility - Site Engineer/Superintendent
29e0ff93-4ca2-52b4-8ee2-4bb84cd6a3a2 | note | Verifying Documents - This ITP
a0a0f91f-1f97-5c84-a688-e22cc4df3978 | date | Date Completed:
d618f530-8ca4-477d-8cc3-b150c0b61ba0 | signoff | AUTHORITY HOLDPOINT
dedb3cac-a58f-482f-87c2-4d4daeabb176 | checkpoint | 5.8 - Compaction Testing
1bf7c7b1-adaa-5c29-81fa-cc2ab459005b | note | Reference - Table 204.131
3dbf4ce0-93eb-5436-8ec1-403e64cf0ad9 | note | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level
e162db90-ad48-5849-a86a-4c3b7ffb0bd4 | note | ○ Scale B: Characteristic Density Ratio 98%.
1b946f3e-486e-5c64-a3b5-226d6013376d | note | ○ Attach: Compaction Test Result:
2d75fd2a-d190-548b-b728-cdb177d746d3 | note | Method - Document Review
e626005d-3486-5c51-8411-122743d8647d | note | Frequency - Each lot
bdb1d54c-1647-5430-9c88-91840c1f47c7 | note | Category - IP
5e7df62e-9efa-5a89-a36c-1797f8be4cf1 | note | Responsibility - PE/SE
326e0513-2ff5-5c9a-b9e9-9a1cda4d0046 | note | Verifying Documents - Test Records, Lot Register
5737c462-377e-5d00-83dc-ff2e69a6e97c | date | Date Completed:
f58d806c-8bde-4afd-8b1e-1e76fe3833cd | section | 6. Post Construction Activities
ab99ecd0-5d53-4762-8cd9-bd3f3334a891 | checkpoint | 6.1 - Post Compaction Material Property Testing
a49cb4d4-69bd-5149-9e36-9e71326d8671 | note | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
4534444f-2aee-56db-9a51-c5aa811e56f6 | note | Acceptance Criteria - Material Properties:
ad2121cd-03be-5841-accf-cf01640d7b54 | note | — CBR ≥ 2% and Swell ≤ 1.5%
54c5e00d-4360-5381-b193-01ee98d0d42d | note | — Max Permeability = 5X10-9 m/s
cca5c107-76f8-56c5-9e1b-9a2387342a70 | note | ○ Grading:
5f1c65a6-9d57-5223-a4f2-dc6c220ba600 | note | — 75.0mm 100%
767c7ed0-0f23-558d-a6e1-cb6dfa9f7d47 | note | — 4.75mm 40-80%
b9a408e5-5627-50c3-95c8-ad2ebae63975 | note | — 0.075mm 10-40%
a7611230-78b9-5466-83a7-1b12c0522164 | note | — Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
66ca715a-646a-5f68-9db2-381e956bad3a | note | ○ Scale B:
e26cd8ff-2941-5fc4-97f7-9f2ffad8510c | note | — 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
c6fddaa7-8684-5b4f-8102-9d4ce217dc82 | note | — Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
bc01d941-4079-5068-a9a4-ed3c3b4bcd5b | note | ○ Attach: Post compaction test results:
6960e8d4-2662-5c9a-b6f8-71cfc87ea05d | note | Method - Review Document
3fe130f2-f10c-527a-b839-7e56b0394a15 | note | Frequency - Refer to Section 204
6350efcb-8cf8-5525-ba41-e9cc1f11474b | note | Category - IP
ed5277d0-1f52-541e-b4ff-0a32f90c02df | note | Responsibility - PE/SE
bad861d0-5a58-534a-a247-b4b2be9c74e2 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
411931ac-b3fe-53e8-87d8-fc1ac05d0c1e | date | Date Completed:
48c908a8-7f0d-483b-b8d8-c06b85fbbc71 | checkpoint | 6.2 - Survey Conformance
6528bc45-6b10-5109-a88e-914f8af3d0d0 | note | Reference - VicRoads 204.03f,g and h
3fa0afc6-8d64-5788-b4cb-7fe6c5eb1aaa | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
df839e69-cdd1-53c9-81cd-aea5d3d5c8ec | note | ○ Level tolerances (Scale B):
d4d2917d-d745-5fad-b5b5-dd917ea344b8 | note | — Range x = +5, -25mm
834ecddd-7c72-5a65-a1bf-4b11cd5c1584 | note | — Max S = 15 mm
05101f7a-7f8f-509d-8a92-784e587905c2 | note | — 40 measurements per lot
45dbc9d9-8a0b-52c6-80a2-ac9a28b1c1af | note | Method - Review Document
43e5fe43-6b5a-5f11-b5a3-cc933cc0f26c | note | Frequency - Each lot
52cced5a-ed75-528f-be07-c9c49c5aa762 | note | Category - SCP
86a9bd21-7c1e-50bd-80d1-f7ea0c6afbc5 | note | Responsibility - SE/Surveyor
f72d79e1-64f0-5768-82ff-edea2fc810ca | note | Verifying Documents - Sign ITP, Attach Survey Report
3b83e103-f17a-510e-971c-f68078898021 | date | Date Completed:
eb6b4722-f431-4e1a-8203-609d79ee74eb | checkpoint | Final Inspection
a09e3277-61ba-5686-a69a-ba0800160f83 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
aa4ef702-2b3b-5298-8059-750634d81433 | textbox | Name:
535afe58-6077-5d01-988d-f16c6714a6c5 | textbox | Position:
b45c7731-7fac-50de-af79-ee6bc4986f69 | textbox | Date Completed:
cf4ef08e-5e2b-47a6-87c6-7481c11859c1 | signoff | Sign ITP
9b5d3812-7d1a-4e07-b48a-aaa24516f45a | checklist | ITP-227-CIV-Ferris-Kerb & Channel (Supply and Install) Rev 0 | itp | ITP-227-CIV-Ferris-Kerb & Channel (Supply and Install) | 5052ff9d-b20e-4ba5-a18a-8b7c93b259d1
19e270c0-cb94-4d45-af36-24b1e35e55c9 | section | 1. Referenced Documentation
e6b350e5-1d1a-4478-9c33-c34d8b147c54 | checkpoint-no-value | Referenced Documentation
3e0a5031-b434-549e-97c0-be0ea6b0cf66 | note | Document Title: ITP-227-CIV-Ferris-Kerb and Channel (Supply and Install)
327ef5ff-0262-5de5-a8c7-0b4b8661b5b5 | note | ITP Description: Ferris-Kerb and Channel (Supply and Install)
d7beba6e-1da1-5709-8fe6-1e24dcbb1cc3 | note | Discipline (e.g. CIV/STR/RAIL): 227-CIV
06eb4c1f-98e3-5d1a-bb34-39a27dd4d7cd | note | Revision Number: 0
07da6883-42f0-55dc-80aa-ba2a08a87d6c | note | Revision Date: 23/01/2025
e63a8b4d-7a15-56be-84b6-2070d676832f | note | ITP created by: Kamel ALSHOBAKI
4f4dfb8a-3f28-5f19-904a-e48207fede32 | note | ITP approved for use by: Pradeep Talasila
d75cd20e-1a11-5ac7-9d30-6079162e1d8a | note | 1.1 - Non Dependent
4330bd7f-4b1f-5288-8879-1cd1e2fea379 | note | Reference - VicRoads Section
3f2609ab-1380-5f62-b26d-e7a2c0c7606d | note | ○ 703 (August 2021)
50654fc4-6be7-5f11-b9e1-f276a9a0b16b | note | ○ VR SD2001
3590b75f-2ef3-586a-b309-2aa4159d9a87 | note | ○ VR SD2102
58909279-021e-5f77-8f76-e05df29a13ff | note | ○ AS 2876
92324ace-2a16-5eef-8b84-fafea3d59164 | note | ○ AS1379
f573439b-e7c1-4596-8452-1d1e1da2c8e6 | section | 2. Preliminary - Materials
c8f7eb0b-ca62-42c5-9d38-2bccdb34a405 | checkpoint | 2.2 - Mix design
784e39bf-e240-533f-a99f-5ab87536a221 | note | Reference - Section 703.05, 703.06, 703.07
23c8f380-3c5e-57af-be4a-a301f6ff1fd4 | note | Acceptance Criteria - Approved VR mix design to be used.
b7754d05-38ce-5976-964b-8f10789fdc57 | note | ○ Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3
17988ed7-9c6d-5614-aa82-bfe4b77363f8 | note | ○ Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete
dbb2a1a2-1a9d-5cb7-ab27-f5addcccf942 | note | ○ Attach: TeamBinder Material Approval Ref No.
6d0de6b5-899c-538d-afb7-a7f1fe7b9165 | note | Method - Verify, Document Review
c08efdd9-f913-5f26-bfdd-c3929d075d27 | note | Frequency - Prior to commencing any activity
d9578739-6741-545a-ad52-b6f6c003dc25 | note | Category - HP
ad31b2d3-8350-5f77-a8b3-3d9e4b992171 | note | Responsibility - Nominated Authority
29fd1b38-95d9-561c-b2ec-a345decdb0b3 | note | Verifying Documents - Conqa HP Release
67096bd3-8b38-550b-ae41-d902288a208a | date | Date Completed:
a0ae1357-c75c-4aa6-9ade-158a041f68c7 | signoff | AUTHORITY HOLDPOINT
2719a63e-b1bf-493c-97d5-c50a3e20831f | checkpoint | 2.3 - Bedding Material
06c4f750-6f51-574e-ba0f-d5e82a4e5b68 | note | Reference - Section 703.21 IFC Drawings
175050d5-d5b0-5e39-9693-c71170d77565 | note | Acceptance Criteria - Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively.
4d8ac858-5ce6-55c9-bd60-fa6030528ae1 | note | ○ Attach: TeamBinder Material Approval Ref No.
cd722431-4b36-51cc-812a-9d446bbcf7ca | note | Method - Verify, Document Review
6bbe06b4-b827-5ada-bc79-bb136d573a9f | note | Frequency - Prior to commencing any activity
2d445620-9823-5917-b53a-f0eee4cbf4c8 | note | Category - HP
c772bec1-f22d-5030-8818-ea2c235a1e0c | note | Responsibility - Nominated Authority
8edd0d70-75b6-59c0-9787-7f5ec340e4f1 | note | Verifying Documents - Conqa HP Release
b0bbb60c-4f7d-55c6-82f3-2750677b697e | date | Date Completed:
ad63c6dc-e5ad-4066-b174-a7e592972875 | signoff | AUTHORITY HOLDPOINT
b35d972f-5b41-4571-b6a8-12a0bef510c9 | checkpoint | 2.4 - Curing Compound
e7361666-beb4-5b96-bc6c-84536f597e9b | note | Reference - Section 703.10
a7011487-ba99-5de5-b961-9c30810ef558 | note | Acceptance Criteria - Curing compound shall comply with AS3799
1b6e4595-1717-50f8-af58-cfe58d3b36a1 | note | ○ Attach: TeamBinder Material Approval Ref No.
311f016b-12fa-58cc-9c19-c33f280e406f | note | Method - Verify
f540f97f-3c25-5511-ae4d-1653861d6dd9 | note | Frequency - Prior to commencing any activity
7e0bb16c-493c-5209-b80e-51955cf28153 | note | Category - HP
3266aa9f-c1e8-5f8c-893c-c78e34d58389 | note | Responsibility - Nominated Authority
8540f64d-45ed-5145-8986-794cb7c5d33f | note | Verifying Documents - Conqa HP Release
d199de46-8441-59dc-8729-4bcaa45e42ee | date | Date Completed:
7aa1cc23-47de-43a3-b706-2c2493cc30ba | signoff | AUTHORITY HOLDPOINT
ffcb1083-3855-4115-be26-633787e8520b | section | 3. Preliminary - Documentation
18c6772c-bef5-493d-8e15-cbc20ce6f2b7 | checkpoint | 3.1 - Check for correct documentation
f08898c7-2e50-5cd9-8475-34679e0facb2 | note | Reference - IFC Drawings
e32d0661-e846-59b6-824b-b857c7e909f8 | note | Acceptance Criteria - Ensure that all employee and sub contractors are:
aa13a859-17a3-563f-8408-521f1c9ec25e | note | – Using the correct and complete set of drawings
4ee8bb63-ae8b-5e20-a44d-b5e8229a4adb | note | – All drawings are the latest version
18a7c5d1-96a5-5479-82e9-796f7fd5bd77 | note | Method - Visual inspection
cc5b9d72-8e94-516b-8134-a706d0b14f96 | note | Frequency - Prior to commencing any activity
f499426e-45f3-5154-9ec9-99d79a3bf28a | note | Category - HP*
f8b58858-559a-5bf9-a239-72f4892718db | note | Responsibility - SE/Site Supervisor
5b90a2b6-4217-5bf0-8ac9-84e15cd09f58 | note | Verifying Documents - ITP Signed
3ae87ecc-19e4-56e1-be67-06ba63e73c38 | date | Date Completed:
f081c9bd-0287-423e-ad47-a3b94b04148e | checkpoint | Lot Map
d7180ef9-57fc-5f27-998d-843f4f85f3cc | note | Reference - MRPA Lot Management Procedure
579ecd8e-93c6-54f1-b500-e25264a67c1a | note | Acceptance Criteria - Upload a Marked up drawing which indicates the Location of this Lot:
a25a0060-c5b4-55a6-88c0-23ecc1a7c368 | note | ○ Attach: Lot Map
9ea50cc3-d045-58f0-870d-f479e73d3c9c | note | Method - Document Review
f44ff8e7-8645-5427-bb8b-d5e94f467fda | note | Frequency - For Each Lot
6581afe4-fe30-5893-ba38-e98d32f2e4f7 | note | Category - HP*
e33a7fee-37e7-55f5-b92b-26bee38237f8 | note | Responsibility - SE/PE
201e7019-0abb-5d7d-afba-bef675a31f42 | note | Verifying Documents - Lot Map
ccbc401f-77d1-583f-9b8f-f2fa6475247a | date | Date Completed:
82095e27-1dd1-41dd-98b2-9b3645a14ad4 | section | 4. Pre-construction / Pre-installation Activities
0ae3c881-b1b3-4d02-ad26-71159512dfd9 | checkpoint | 4.1 - Setting out
dd320e6e-f891-5e93-b5f1-cffa6292880c | note | Reference - Section 703.17 IFC Drawings
c53018e4-544a-55de-91d6-61994634d43e | note | Acceptance Criteria - Set out work in accordance with IFC Drawings.
789b46d6-4563-5b3e-a689-7cdf13c50367 | note | ○ The superintendent will review and confirm set out.
cedf7da2-54d6-597d-9ce2-74ab291e2622 | note | ○ The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings.
3a70d09a-c806-5fe9-a480-5a673ea4fe3e | note | ○ Attach: Lot Map-Marked up drawing to indicate the location of the Lot
3833e348-13cb-5190-9087-7e742824e1b4 | note | Method - Verify
9dc4d596-776d-558b-93d2-03251092db91 | note | Frequency - Prior to start
174388e7-5a35-53fb-b53f-f696910f99bd | note | Category - HP
5e173dc4-1307-587c-9158-a44cc6f2997b | note | Responsibility - Surveyor/Nominated Authority
6ac7209b-984b-530e-bc12-66dd7f4de6e1 | note | Verifying Documents - Conqa HP Release
25d21716-1a66-58b9-9102-705688c6cd64 | date | Date Completed:
1b987d97-6243-4575-b7bb-d41cccda42fb | signoff | AUTHORITY HOLDPOINT
1d9b4b4a-a81b-4149-b282-111112d3aa5c | checkpoint | 4.2 - Temporary drainage provisions
49ddb9ab-02cc-50eb-8468-953250cfe873 | note | Reference - Section 703.18, CEMP
4e401666-a0c9-5f1e-86ef-39fe142e1834 | note | Acceptance Criteria - If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place.
6325c5ad-c747-5a36-b1f5-ce1eab7d50a8 | note | ○ Need to obtain prior written approval from the relevant waterway authority prior to diversion.
c9cc9217-6da2-5bcf-88ff-11d8b4bca56a | note | ○ Attach: relevant written approval from relevant stakeholder.
7074c32c-a148-5cca-beb1-858247d8ff65 | note | Method - Visual inspection, Document Review
2b85b532-b8f8-518d-967d-c2a639e31c33 | note | Frequency - Prior to start (where required)
17a363a6-160f-51fd-83f0-a47d3828959a | note | Category - HP*
08a828cd-a79a-55d8-8a51-50858dd4ac35 | note | Responsibility - SE/PE/Site Supervisor
6fa9e615-d6be-5bfa-8997-2ccff6400aa3 | note | Verifying Documents - ITP Signed
fea07976-f50c-5f51-8a96-5dbc9e839450 | date | Date Completed:
c6115ca8-d8d3-40d2-9b06-722cec1185bb | section | 5. Construction / Installation Activities
e60e79f5-4807-40d1-be44-fec5f583e90a | checkpoint | 5.1 - Bedding
916e3333-11d4-5136-9e13-39d113c6a5b8 | note | Reference - Section 703.21
1ad617bd-1257-5da1-ba65-721d04835fc6 | note | Acceptance Criteria - Bedding to be compacted to a thickness of not less than 100mm.
3a52da18-7e2d-5916-bb1d-15dbc6f61d5b | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
bfd9f2ba-9228-5283-9f7f-5652b1a800fc | note | Method - Visual inspection
656abf73-6f85-53d0-8871-ea172d4cecb1 | note | Frequency - Each lot
b0ed6d64-c649-5260-b2fd-0a2b78f9f37e | note | Category - WP
94a3fe97-ce99-564a-a575-afee01a87fb8 | note | Responsibility - SE/Site Supervisor
0fd5ba5f-8801-5252-a873-950f394dd44c | note | Verifying Documents - ITP Signed
65643170-d39d-53b7-a7e5-656febfe466a | date | Date Completed:
04a1963b-0f24-496e-9371-dec1a264a003 | checkpoint | 5.2 - Formwork
9ead5182-6779-5b8d-8a44-d2e7bfc751d4 | note | Reference - Section 703.12 AS3610
aa378169-c8b0-5fd2-99ae-eecb5eb153dd | note | Acceptance Criteria - Joints in formwork shall be constructed such that loss of mortar is prevented.
42628e13-3aae-5e1d-acae-9203d049c1fb | note | ○ Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
3c7b4a5a-421d-527e-8222-8bef8927d7dc | note | Method - Visual inspection
111fc329-a132-52b2-a1b2-7b5eb20ba02e | note | Frequency - Each lot
0df1ac8e-3cba-5a94-9b56-0a6038e23e77 | note | Category - WP
b112c5c6-56a1-5fa3-83cf-e5650a1a4803 | note | Responsibility - SE/Site Supervisor
c385edb5-3230-5e92-9e24-07e59c2d734e | note | Verifying Documents - ITP Signed
9ab1ab81-47a0-5930-94c2-e468b1416792 | date | Date Completed:
dde12457-a9da-4be1-8862-7e97778e8388 | checkpoint | 5.3 - Pre Pour Check
591304c8-e9e5-5fd8-a6b3-aa81d6bd4b5a | note | Reference - Section 703.09, Section 703.2, Section 610.17 (a,b,c)
d1b86e3f-5531-5186-bef7-4d70e7adee9a | note | Acceptance Criteria - Bedding shall be moist but shall have no free water on the surface .
e3949edc-1554-5aad-80e4-35d1357b3c79 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C
a19033c1-eaf6-536e-908c-0972b444c79b | note | ○ Attach: Pre-pour Inspection Record
7e3fdab3-1bed-567f-afef-ad23f99855ac | note | Method - Verify
c5670c76-8a7f-565a-a82c-2f8371696146 | note | Frequency - Each lot
bf78fa0f-1794-562e-9501-eef1c0e13c38 | note | Category - HP*
245fc535-0821-518a-bcfe-94baaa96c4fd | note | Responsibility - SE/Nominated Authority
c175876b-51f3-5c04-a9cd-5468d7a4cd3f | note | Verifying Documents - ITP Signed
82034ab9-59d8-5077-8a29-c194ac08c2dc | date | Date Completed:
5272244d-35eb-4687-bbdc-71b57fc3b505 | checkpoint | 5.4 - Concrete placement
f0096218-7e09-554d-86ca-926acabc540d | note | Reference - Section 703.08, Section 703.23
804cb44e-6411-5fec-a5eb-f4ecac533e9e | note | Acceptance Criteria - Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C.
37f77f80-9b22-5080-beaa-cd105607fbc9 | note | ○ Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches.
d98e834a-5141-5ab9-bc15-613b2e7a9d79 | note | ○ Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints.
c426a58d-ef5b-56bf-8bc6-bff1ca42ee24 | note | ○ Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate.
59a669ba-ac58-5dcb-9cc1-4fa44837a49f | note | ○ Attach: Concrete Pour Records
a76b5734-2651-5344-b8ea-efe97653c2a6 | note | Method - Site inspection
39b16373-30bd-51f8-9daf-d1e20525eba8 | note | Frequency - Each lot
73b2a6b1-4757-54bb-9398-68571cbb5bbc | note | Category - IP
37815f49-eed3-5c3d-9316-60b8117528bc | note | Responsibility - SE
78b56617-c8d9-532c-a965-6663d8fad512 | note | Verifying Documents - ITP Signed
df758e99-08d6-5a06-9f0e-730744336714 | date | Date Completed:
d70fdae4-ed0d-4863-aaed-b18ece782a05 | checkpoint | 5.5 - Transitions
5d203917-5b1b-509b-87a1-a0b53f48511d | note | Reference - Section 703.24
6f3100ee-719c-5665-b26f-ed1371a437a9 | note | Acceptance Criteria - Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre.
de121c23-bafd-5a16-9f20-2d3a9ea60de4 | note | Method - Site inspection
b87d1cff-046e-5dac-b0b1-3a2b62f99077 | note | Frequency - Each lot
a6a4f804-4ff2-55bc-a51f-aa9739fdb963 | note | Category - IP
35a6018c-df4f-5cfe-9fa0-334d4ef03b09 | note | Responsibility - SE
14baa172-790c-5aac-8dad-38ef6bdbbbff | note | Verifying Documents - ITP Signed
31384909-edd1-57a3-b2a5-424eb54351d8 | date | Date Completed:
3b3b2a3c-2ce7-42b2-b446-d1bf550ba83a | checkpoint | 5.6 - Surface Finish
8b575630-3826-5270-bfe3-113a9f631ac2 | note | Reference - Section 703.25
5bef37ca-5b52-5879-a67e-b4e16684d0db | note | Acceptance Criteria - All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished.
1ea4e7c4-43b6-5e98-8fd7-037632ebf525 | note | ○ Renderings shall be applied within 30 minutes of extrusion.
6892d8e3-3a59-58af-8d64-be96953733d5 | note | ○ Concrete to have a neat appearance and uniform colour.
e5dc4765-18af-54aa-ac49-50507a76b5c6 | note | ○ Class 3 finish required for external surfaces.
5fa980b2-0691-59c2-a6f4-d92f78c04ba4 | note | ○ Class 4 finish required for permanently hidden surfaces.
612b13d2-9294-5326-8021-b942aa27cd48 | note | Method - Visual inspection
f77951d0-555e-54a2-aa45-40eb21c2014f | note | Frequency - Each lot
4fa57ebc-72c3-522b-adf3-48ab40140094 | note | Category - IP
73fa738f-7d8e-5df4-b853-59225f4951c3 | note | Responsibility - SE/ Site Supervisor
c9d145f8-ad68-578b-afb7-821b63a8b6ad | note | Verifying Documents - ITP Signed
ab776645-4c3b-5c02-956a-0d775ae836d3 | date | Date Completed:
d33d66ce-da50-4a97-a6e3-7406173a0517 | checkpoint | 5.7 - Formwork Stripping
e22203b2-40a8-5b48-9f63-a61824234032 | note | Reference - Section 703.12 AS3610
24a04ad8-a6d8-5ded-9712-1aa7da02a908 | note | Acceptance Criteria - Formwork shall not be stripped before the minimum time of:
a3868117-5cd5-5767-9968-5cbe97fbb022 | note | – External faces 2 days
099e1aea-e3b3-5eb3-8b9f-33ed8ade1c08 | note | – Permanently hidden faces 1 day
3dc70f20-df4d-59a3-ac27-e7aa34f9351b | note | Method - Visual inspection
2acfa548-6185-5037-bba0-8eb6c7e3534e | note | Frequency - Each lot
8af2c1db-02f9-5371-a0a5-f0904c0581c9 | note | Category - HP*
65183fad-923f-579a-8ea2-a5a89c27ee7e | note | Responsibility - SE/ Site Supervisor
9d9d8e47-3f7d-5fc3-843f-38c416747f15 | note | Verifying Documents - ITP Signed
d3c8cad0-3591-5645-a601-06773d46d82c | date | Date Completed:
ca7ecfca-e7b1-4951-a3de-e824d57b0de8 | checkpoint | 5.8 - Tolerance
2dc7447f-8af8-5539-9623-4bc453d837b1 | note | Reference - Section 703.15
e44d528b-f19c-5af3-986c-6f4a4309a2bd | note | Acceptance Criteria - Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm.
93c60677-8255-5280-a39e-b442d2305c0a | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm.
1ccb7f9b-b28d-5d0a-b4ef-e13990a6463c | note | ○ Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point.
54517dfa-0f37-5717-8e93-bc9800a4e9bc | note | ○ Attach: Post-pour Inspection Records
44ffa194-a9fb-5b2d-87d9-4dab0ba663a7 | note | Method - Verify
22022d47-8896-583c-8fe4-ebb78bbf52dd | note | Frequency - Each lot
99d344b0-aae9-593d-ae58-429f2d4c5f93 | note | Category - IP
dc2e7d56-2e6b-5758-a996-1b87e2415cec | note | Responsibility - SE/Surveyor
65750a08-2335-5c82-bb72-b03275aeb597 | note | Verifying Documents - ITP Signed
abf3878e-e0d4-5bd0-b718-39423e3b49b6 | date | Date Completed:
754e5927-70d7-4089-a224-11324bda8eec | checkpoint | 5.9 - Curing
c04087f1-38a5-5a82-ab65-f3db1ea96ecd | note | Reference - Section 703.10
02edc628-14f0-5ecf-aec3-37d531316ee8 | note | Acceptance Criteria - The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed.
6c408969-eba3-5ffc-ab1d-1873a2f6e706 | note | ○ Concrete edgings shall be cured for a period of not less than three days after placing the concrete
f4ec1203-dbc9-58b2-b9be-f12915bf5ebf | note | Method - Visual inspection
47c37aa3-8737-50ef-8477-2e931ab212b3 | note | Frequency - Each lot
e622fae7-40e3-5204-bfeb-430f69ab9c29 | note | Category - IP
726bcf67-2165-5190-a8b7-7581174840f5 | note | Responsibility - SE/Site Supervisor
21221f08-e167-56a5-93c4-4558b789e2e6 | note | Verifying Documents - ITP Signed
8e65b11d-69e3-51a8-9150-6b41833bae05 | date | Date Completed:
da8eb5d8-eca1-47b9-83fb-fc6c40e0b04f | checkpoint | 5.10 - Joints
b70ede06-9a5f-5c5e-b3de-ea37a61c4722 | note | Reference - Section 703.26
b4759870-25f6-5f82-b96a-b40d7c87ca08 | note | Acceptance Criteria - Transverse joints constructed at intervals not exceeding 2.5m.
83d316e7-441b-560c-9c47-71c51ed2c38c | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section).
cc085fed-604e-5260-b40d-b7c202779b20 | note | ○ Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path.
11cd0c5c-6de4-5974-a4da-710ea852d6ce | note | Method - Verify
87550dea-5c55-5048-8990-927e56d10a91 | note | Frequency - Each joint
e91f6ba4-1a2b-5883-870a-35def2984ff0 | note | Category - IP
4757126c-f81d-541c-b1d8-e4781f2e6981 | note | Responsibility - SE / Site Supervisor
c4ab6843-b903-510d-90bb-a1b2f08d89be | note | Verifying Documents - ITP Signed
daf163fb-85ca-5894-9d03-6425c39e454e | date | Date Completed:
d5a0000a-e41d-4e65-bdb7-062cf0fdc39d | checkpoint | 5.11 - Protection of Concrete
b9518ef2-2e46-5a0c-a919-e9e26cba4a63 | note | Reference - Section 703.27
14ca9abe-bf85-5e64-ac3f-8ad0499bf62a | note | Acceptance Criteria - All concrete shall be protected from damage from early loading.
05d72d52-417b-5847-abbf-3b1f2309f3fd | note | Method - Visual inspection
3cde988f-319f-5636-9929-72da1cc478d8 | note | Frequency - Each lot
b9095944-88d3-594a-b3df-ca3e5c5f92ad | note | Category - IP
f0138bdf-3380-54f6-93a7-e2d05b08e172 | note | Responsibility - SE
05407808-6ff0-5549-8dc8-010089055680 | note | Verifying Documents - ITP Signed
b122ab9d-da22-5aa4-9c4a-4d48ba1d1cab | date | Date Completed:
ea724ab9-2827-4b3b-a522-e7b3970fd3d4 | section | 6. Post-construction / Post-installation Activities
901030bd-3652-48cd-9d61-9a41e8269b22 | checkpoint | 6.1 - Backfilling
277bff85-dac2-5f09-a590-5aa761afe6bd | note | Reference - Section 703.29
7737bd76-56cd-5978-8613-a87b8b0bbc7d | note | Acceptance Criteria - No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging.
0ca5c0f2-56a4-5403-b64c-b42cfc365af0 | note | Method - Verify
4fa8ceae-2d5d-503b-8943-750fbd21d5ba | note | Frequency - Each lot
edb48d33-b7b6-530e-a975-9670239ca21b | note | Category - IP
9942ed56-a9d3-5d72-9575-e3fc54d2f2a8 | note | Responsibility - SE
7ad02e27-a514-5672-8009-c1efd1525972 | note | Verifying Documents - ITP Signed
dc08d476-50b8-543e-b787-c7e4d1c9e177 | date | Date Completed:
444251a0-7945-49fe-8b01-210e4afb356a | checkpoint | 6.2 - Cracking of Concrete
189ee0ec-6643-563b-acdd-0a65b5a0bbe8 | note | Reference - Section 703.30
de7d85ee-a761-50db-936d-b4d99886acf3 | note | Acceptance Criteria - The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm.
c735c3de-34e8-5d87-97da-0060fae15d00 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687
e78b09fa-f0bd-5f7b-9720-bda364634268 | note | ○ Attach: Pot-pour Inspection Record
e2b44217-5231-5979-a92b-47e5989a539a | note | Method - Visual inspection
2aca5f50-6442-5f2b-8a53-4967e660422f | note | Frequency - Each lot
b8512be9-2e21-5021-9fbb-2ad565d8e6e7 | note | Category - IP
b456a435-7c18-55e2-a21f-f82543009ecc | note | Responsibility - SE
ee947d2a-9622-5691-ac33-d07ec3157c8f | note | Verifying Documents - ITP Signed
2d7206a0-56db-56c0-8a9c-a1750702a73b | date | Date Completed:
086adf4b-0ee1-4ae0-bad7-1057bff4a1bb | checkpoint | 6.3 - Survey Conformance
c6fed5f9-729e-57c0-b538-95986117d982 | note | Reference - Section 703.15
e2e5c2d6-a5c6-5d7d-b612-8f8da9c728e2 | note | Acceptance Criteria - Survey to as built the works and to confirm the works are within the specified tolerances.
ee27751d-34b8-5af2-8219-8ecd724f0a19 | note | ○ The departure of the finished work from line or level shall not exceed 10 mm at any point, and the rate of change of deviation from line or level shall not exceed 10 mm in 10 m.
3824af15-a1c0-528b-b180-9d0e166f76b5 | note | Method - Document Review
7dda6c02-61d4-569c-982a-25adc81c3e04 | note | Frequency - Completion of each lot
2a03005f-4764-5e70-9450-d2fe32f056c2 | note | Category - WP
48ae3f62-df56-5d93-856b-4a5d3c8405db | note | Responsibility - Project Engineer/ Surveyor
cde7314c-c402-507f-8dd0-e6215fab6372 | note | Verifying Documents - As-built survey records
f6f1cdde-adf6-52e9-b8a6-c36046f14c37 | date | Date Completed:
3d085f28-c444-43a8-bad7-4e8d826f5a5d | checkpoint | 6.4 - Non-conSupervisorce Report (NCR) Closure
8dc6f711-ff8d-5ec2-84e0-b384dd57c08f | note | Reference - MRPA Quality Management Plan
14539acd-9f64-5519-9d47-af4487623582 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
5e82713b-9ef4-545d-803e-d8cb14339844 | note | Method - Document Review
0297573f-bc43-5278-82b5-6eb413e3c3a6 | note | Frequency - Once, prior to closure of this lot / element / Work area
102aca85-7e01-527e-ab55-9ccb09fd4610 | note | Category - HP*
c3ca593b-2c4c-58b4-9038-8d1397ea3fd5 | note | Responsibility - SE/PE/SPE
2ad364a3-4932-5ad0-b5dc-9a6735e3bf8c | note | Verifying Documents - This ITP
ea3e6017-0ac9-57d3-b345-6aaacad02e6c | date | Date Completed:
b3df7fad-c03a-45fb-a0d0-3e1fafdfba13 | checkpoint | Final Inspection
8382baaa-cbc3-5b56-baf4-b12072407fa2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
91a8fe3b-62c0-5591-8b58-811bfd9e570f | textbox | Name:
3d24ed5a-2803-54c5-8757-9a1d29052e65 | textbox | Position:
6280f2c2-34e8-59bb-bbec-d17bd6039cf5 | textbox | Date Completed:
a7b5231e-cfd0-4a6c-9794-eb945526008b | signoff | Sign ITP
d7c626e3-6615-457b-8b55-94808ed0dca9 | checklist | ITP-228-CIV-Ferris-Unbound Flexible Pavement Construction Rev 0 | itp | ITP-228-CIV-Ferris-Unbound Flexible Pavement Construction | 2cd2a132-f641-4356-9e85-070b4efac011
5bfd761d-e679-48fc-a563-a56b4271472d | section | 1. Referenced Documentation
1b0d2d3a-33dc-423e-812b-f8fe9e8dd8d7 | checkpoint-no-value | Referenced Documentation
94bc5b0d-42d0-5f59-881f-f79ad938fef9 | note | Document Title: ITP-228-CIV-Ferris-Unbound Flexible Pavement
689dcba7-ad7a-5f9d-aa57-55db24a0f8a4 | note | ITP Description: Ferris-Unbound Flexible Pavement
1bb5ac89-cebd-5738-b83f-63bd647d58da | note | Discipline (e.g. CIV/STR/RAIL): 228-CIV
97911c5a-9746-5000-9f3f-02b229f5ee73 | note | Revision Number: 0
cba6deca-4a07-5044-b180-40f44c94b923 | note | Revision Date: 23/01/2025
5ee7d73b-cb62-5418-a8d7-533a1d057766 | note | ITP created by: Kamel ALSHOBAKI
edebbe4c-c307-534a-b063-24b39f688943 | note | ITP approved for use by: Pradeep Talasila
f3affd18-d32c-5133-a9b2-17be7726fbba | note | 1.1 - Non Dependent
bba5105a-a9c7-586a-af33-93495dfaabc9 | note | Reference - Reference Documents: IFC Drawings
8115ad43-4315-57a5-9d75-c68e07e7f49a | note | 1.2 - Non Dependent
b1094e60-a078-5dd5-98b4-b8ffafbf3ac3 | note | Reference - VicRoads Section 173 (10/9/2008)
4c953396-56b4-5bba-b80d-c0f431852e62 | note | ○ VicRoads Section 304 (13/8/13)
87cf478b-4c6e-5bf9-b543-82bc3d5e0816 | note | ○ VicRoads Section 801 (19/07/18)
128ea6db-3c0c-5d71-a63d-a0c7331bfa16 | note | ○ VicRoads Section 812 (13/07/16)
91c0c057-0f57-470a-ad96-4fc293eb91c1 | section | 2. Preliminaries-Materials
f77fd82d-431b-44c5-8ac1-1f9eaf200c70 | checkpoint | 2.1 - Crushed Rock Mix Design
75213f5f-8a79-5c9b-83d6-03008c8e9945 | note | Reference - Section 304.03, Section 304.05, Section 812.04 Table 812.121 IFC Drawings
b17b8e85-dbfd-51fb-af6d-679b7281f7f7 | note | Acceptance Criteria - All crushed rock proposed for use shall be current registered mixes in accordance with VicRoads Code of Practice RC500.02 and conform to specified requirements applicable to that class of product.
c1612dbc-4734-561a-8ba8-659c749a0576 | textbox | Enter: Teambinder Material Approval number
e423bf8b-2597-51be-bb19-04f12aad0a1c | note | Method - Document Review
c64c129f-0ab3-50f6-baa3-ff051b39f791 | note | Frequency - Material conformance as per Table 812.121
cc4b160d-a38f-516b-8237-27794d33f81c | note | Category - HP
508ec507-0b19-5347-bd8b-10b79ec43f07 | note | Responsibility - NA
046aa2bf-95e0-5305-9e13-26082b183db8 | note | Verifying Documents - TeamBinder Material Approval Number
dc733069-5629-5467-8b68-b894613ab847 | date | Date Completed:
c12e70e9-3ce1-4778-b836-76777082a4b6 | signoff | AUTHORITY HOLDPOINT
d660c1fb-14d9-4084-ad99-5defac412f7f | section | 3. Preliminaries-Documentation
7768206d-5a59-4834-a3c1-e4c4135192c5 | checkpoint | 3.1 - Subgrade Preparation
315d8dbe-5b32-5ffd-9858-d606fb435da5 | note | Reference - 304.04
d9b8ec59-f654-56d4-bf45-15c4c14cd598 | note | Acceptance Criteria - Prior to placing subbase material, the subgrade shall meet the requirements of Section 204.
c3646f6c-eff2-5153-9b1c-d74fcd662599 | textbox | Reference: Subgrade Preparation/Type fill Lot Number:
f3f8978f-24c0-58b6-835a-c8aed8d67e48 | note | Method - Document Review
bc0a11aa-00b7-596d-bcca-dea54e8ea566 | note | Frequency - Each Lot
a1f36ebf-3ac6-509a-b693-96722ccbc9b6 | note | Category - HP*
e0365043-5c90-5bd8-b6e9-987ed454cab2 | note | Responsibility - PE
49dac1f3-dba4-5d4c-8d95-2190cadf8dd3 | note | Verifying Documents - Underlying layer Lot number
e898e6d8-356c-5714-b597-81859caf0933 | date | Date Completed:
1e559946-16bc-4159-a6e7-7ccedee10bd5 | checkpoint | 3.2 - Select Scale
b1899fc2-f31b-5f66-bc99-3e475d4f624b | note | Reference - Project Requirement Specifications, IFC Drawings
2deed4fb-8f89-5b6a-a3f6-592345896c76 | note | Acceptance Criteria - Specify site specific scale:
ae1c44dc-6ea4-55e4-818d-ac79f96be917 | textbox | Enter: Site Specific Scale (A, B or C)
15cd363d-8a4e-59f3-a2ad-ecd9a78fd6da | note | Method - Document Review
d48ba17f-ead6-59f3-92d3-08b656c9c3a2 | note | Frequency - Prior to Commencement, Each lot
267925c1-b1f4-57e3-afe9-4b06a00006b9 | note | Category - HP*
89f64940-6a4e-59f6-8f0a-4b65fc532147 | note | Responsibility - PE
c5ee92c3-1e5b-5469-a846-5553281404a1 | note | Verifying Documents - Sign ITP
f15df170-fb48-5cf2-95fa-81156398ab75 | date | Date Completed:
2a9dcc84-97c8-4744-8349-9e71633f33d5 | section | 4. Pre-construction / Pre-installation Activities
b26b6169-6e48-46c2-8d70-0b469c93d54d | checkpoint | 4.1 - Survey Set-out and Lot size
f69e5a7b-3479-56c1-93d5-7be934bdf1be | note | Reference - IFC Drawings Section 304.06
dc2f7b3a-9232-5af7-b49d-f6f182ec28ef | note | Acceptance Criteria - Lot size shall be the lesser of 4000sqm or a days production.
8a22c8ce-192b-513f-ad81-a1fc79478b24 | note | ○ Set out pegs are in place and clearly mark out limits of works as per IFC Drawings and VR 304.06.
adc6005e-8ae4-5fae-af26-f5f6fe53ce84 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
18be6c55-f04d-558a-a62a-634454343fc9 | note | Method - Survey, Document Review, Measure
74f6944b-84f0-5eec-ac66-6ead7cddf29a | note | Frequency - Each lot
b1f8b17b-5ca9-5abf-ba70-eded40550905 | note | Category - IP
7e0f2076-bfb4-51a1-ba6b-c467ae559d2d | note | Responsibility - Surveyor, SE
4783aa25-595d-54c8-b97a-6f0f6cf3c1ac | note | Verifying Documents - Sign ITP
8e9adb31-906e-51ae-abb7-9669220741d9 | date | Date Completed:
feabd607-1b8c-491b-882f-77373c67cf06 | section | 5. Construction / Installation Activities
e08fec53-bf58-4294-a6c8-252571bc00f0 | checkpoint | 5.1 - Crushed Rock Delivery Dockets
5a292608-e4ef-5ef8-80d2-dd61516cda68 | note | Reference - 304.04
35ed3350-2585-5dc6-a4d4-dada3811ad12 | note | Acceptance Criteria - A delivery docket for each load shall be issued to the Superintendent at the point of delivery. Check Delivery docket for compliance to the referenced Material Approval (Line Item 2.1)
949b941d-39bf-5ba3-ba25-cf6d5a0d3fde | note | ○ ATTACH: Delivery Docket(s)
ead006bb-441e-5e7d-becb-e1d6334ca157 | note | Method - Document Review
be575e29-c880-591f-a655-374215c4dc52 | note | Frequency - Each Lot
bc5432e8-be12-5c96-98aa-bf68b4de48aa | note | Category - IP
fa1695b2-7bb6-5773-a512-27585f300e2c | note | Responsibility - SE
56fc4da8-85b3-55b9-a548-fb8fce4e55d6 | note | Verifying Documents - Attached Docket, Sign ITP
8fe49fd3-ef9e-5324-9366-75077c202222 | date | Date Completed:
eabb05ab-eba6-4307-9ba6-158c60e1b6d1 | checkpoint | 5.2 - Placement of Material
04873d40-9622-5ce8-a477-010dc17698ae | note | Reference - Section 304.03, Section 304.06, Section 304.08
e6a97fb3-52da-5784-9c75-0c6567d3542e | note | Acceptance Criteria - Place and compact layer. Surface finish is smooth and uniform. Free from segregated areas.
fe96639c-cf27-5071-995f-a4157213e7ce | note | ○ Base layer shall not exceed 150mm. Subbase layer shall not exceed 200mm. Minimum layer thickness shall be 4 times the nominal size of the material.
a106ca00-f511-57fd-91a9-c4c7d0b2edf7 | note | ○ Water added to the pavement material shall be clean and substantially free from detrimental impurities such as oils, salts, acids, alkalis and vegetable substances.
d27b71d5-8abb-5c94-a7c1-5fa6477a0275 | note | ○ At no location shall water pond on the surface of any pavement layer.
dd038a50-968f-586d-9d1b-208678a06323 | note | Method - Visual and Measure
7e8e6d75-8d9e-5bbd-8b64-72949c72ff83 | note | Frequency - Each lot
eda66243-9228-5160-874d-61dbaf752f35 | note | Category - IP
36795587-a8c8-568a-94f3-4b4fa9d0382e | note | Responsibility - SE/Site Supervisor
e377123c-6942-5878-823f-85bd7d6e852f | note | Verifying Documents - Sign ITP
94e02bca-19b5-57fd-8cef-91f2c1afcf93 | date | Date Completed:
343c6401-bdb7-4414-8dd1-507f210b8d99 | checkpoint | 5.3 - Construction - Jointing
40e62f26-733d-5500-810c-bdd3d3c37fc1 | note | Reference - Section 304.07
8c1e437e-6175-5cfb-916c-9f4b0d579209 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
0ca3865f-241d-5430-bb7f-223399602d83 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
c364d6e4-70d2-533a-84bd-ed13f23db362 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
749eaa10-c029-52df-ae60-9ed931c2ca8d | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
9140aee5-ffa3-537a-8259-3552bc99a397 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
80138c86-4a6a-5ad4-8fe4-e97f50a8332a | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
acbc2888-1780-577b-93ea-88b931f1c533 | note | Method - Visual and Measure
2ff587ad-af2a-524b-b2cf-12354dbe73fb | note | Frequency - Each lot
2153ca57-f620-5bc5-bd22-b0915cf6e05b | note | Category - IP
f96a4b9a-fbe6-53cc-8a0e-02fe11f73749 | note | Responsibility - SE/Site Supervisor
e58e85d5-a093-5c94-92ca-2f68ccefaf81 | note | Verifying Documents - Sign ITP
e902f320-c2f1-5e63-b280-c00a41f96109 | date | Date Completed:
a76dff69-ca1e-481e-8d32-b37c77ae462e | checkpoint | 5.4 - Compaction test (Frequency)
c0e2f461-8af4-5044-aeae-4c944058c170 | note | Reference - 304 .11 (b)
e5790790-a9cb-5ce5-a2c5-cb073cfcbbd7 | note | Acceptance Criteria - The Contractor shall initially test every lot for acceptance of compaction in accordance with the requirements of the Specification.
a445a973-eafb-5e1f-b5b6-fcb268c023e5 | note | ○ The Contractor may reduce the frequency of compaction testing to the minimum test frequency (One per 2 Lots).
1b214994-16cb-5d17-b860-f15c489c8bf6 | note | ○ Scales A and B: 6 samples
cb3546f3-75f4-50d3-94c1-09691dd65c03 | note | ○ Scale C: 3 Samples
39ccae25-41ed-5746-8292-b70a1e37fdc5 | note | ○ Pass: Tested
9e9758e4-b7cd-5f9b-b3bb-2bb39d88bd6d | note | ○ NA: Not Tested
4e5fc303-534a-5819-bd6e-67d77bdd72cc | note | Method - Visual
6c931f38-db18-5f2b-bd0f-4e02dd8a953c | note | Frequency - Each Lot Where applicxable
f8e7fbae-3d19-5dfd-80fb-bc9a65ae3942 | note | Category - IP
e1183df7-6510-5e4d-aefc-8d01f1cfc575 | note | Responsibility - SE
7c5377c7-ed12-5e1f-a948-3d17f0e2a1bd | note | Verifying Documents - Sign ITP
89fd469f-6ea1-5c22-810a-62b4ed36a085 | date | Date Completed:
147226a5-0ce6-4375-b863-b1fe147330d4 | checkpoint | 5.5 - Post Compaction Materials Testing (Frequency)
d24384ea-1e3a-503e-b9f8-6e0be93e6fc2 | note | Reference - 304.11 (c)
68c51254-2d05-5dfa-979f-f09f20e30ff4 | note | Acceptance Criteria - SCALE A:
d096f024-7788-509d-97b9-b109eb3448bc | note | — The first lot of each pavement layer shall be tested for post-compaction grading and PI. If the lot satisfies the requirements specified in 6.1 as applicable, the Contractor may test at the minimum frequency:
4c156ccf-1038-514d-ade3-583cba9a18ad | note | ○ Compaction:
6b3733b4-73a2-523f-af36-f6fc0f9ee25a | note | — Lower Subbase: none
66e02c6b-3499-5861-86ed-884a0de24bde | note | — Upper Subbase: 1 in 4
50288837-eadb-5241-a8a2-606656278b37 | note | — Base: 1 in 2
0a102269-9705-5733-a431-3a34fbfb0da8 | note | ○ PI:
c8d02f49-12c9-5ec2-ac4e-39048ae5b595 | note | — Upper Subbase and Lower Base: 1 (two samples) in 8
b4c569bb-0d5b-5163-a0be-a2c07ee88613 | note | — Upper Base: 1 (two samples) in 4
f837d325-ecc6-57fa-b152-c71ee8d65799 | note | ○ SCALE B:
df1bd44c-8272-5275-9824-6908f97b6838 | note | — the first lot of each pavement course shall be tested for post-compaction grading and PI.
e18a7d10-e24b-56ac-8548-123ddcb38426 | note | ○ SCALE C:
ea3dacde-ce23-5b8b-b497-aee2083b27d4 | note | — Post compaction grading and PI testing is not required (CHOOSE NA)
7961f5fd-ed6d-5676-822b-da7f8e63ed93 | note | Method - Visual
60da7249-6c45-513f-8bb7-15ce6de8e76d | note | Frequency - Each Lot Where applicxable
38e50a92-dab8-5ee9-9faa-f0fbb9217ce4 | note | Category - IP
e4efcf57-fa85-5f34-9465-70731dbcb83e | note | Responsibility - SE
76257f2b-a1b6-577e-9a87-2bc7ca9bf38e | note | Verifying Documents - Sign ITP
3a429e8b-21a4-55bb-a3e5-07194d45d688 | date | Date Completed:
c8b18319-1879-4b35-b27a-54fb9c5854c5 | checkpoint | 5.6 - Proof Roll
62e93ccd-b9f8-5ab4-acf7-2bcb9c596d17 | note | Reference - Section 304.08
cb004e86-b271-5f48-a901-bbfba3fa5100 | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173 prior to acceptance of the layer.
408fe42b-14fb-57ca-bb0a-e9095a675782 | note | Method - Visual
03fae410-03d8-580e-8af5-d41382682cbc | note | Frequency - Each lot
53b04dce-fa1d-598e-982e-a44d990892d7 | note | Category - HP
4c974696-fa2b-5078-8146-86ff10fe7fd6 | note | Responsibility - Nominated Authority
af8d7e9f-6dac-5866-bbc5-cddb39008e07 | note | Verifying Documents - Sign ITP
76a2fa3b-dc3f-577b-846e-707834a044ed | date | Date Completed:
097a83ed-e89f-4eb3-884f-3d71671710c9 | signoff | AUTHORITY HOLDPOINT
bbb27a1d-f482-4e95-abd7-1f9830e89f43 | checkpoint | 5.7 - Protection of compacted layer
d45281fd-7a89-594b-be22-e84a34551114 | note | Reference - Section 304.09
a224a19d-2c29-5cf9-b302-a9edbda99d7d | note | Acceptance Criteria - The surface of each compacted layer shall be kept moist, in good condition and free from contamination until the subsequence pavement work is to commence.
4125456f-1896-50f6-bcf7-bd08b67b62d0 | note | Method - Visual
9e788ebe-a320-523c-9cdf-753421ba5ade | note | Frequency - Each lot
c95f4bca-f2d8-5ea3-8ca5-d2811302213f | note | Category - IP
3ded5804-a6b9-5dc8-b191-c909f17625fe | note | Responsibility - SE/Site Supervisor
4c2c1ab3-785a-5b96-b740-84ebe23c91f9 | note | Verifying Documents - Sign ITP
c816bdf0-17ce-5955-95b6-2648f215b41b | date | Date Completed:
13687ab9-63bc-4304-a9d5-2bc395cfda5e | section | 6. Post-construction / Post-installation Activities
06041a83-3cb9-4d24-a4ac-bcd94a70549b | checkpoint | 6.1 - Compaction Testing (results)
00c21baa-88a2-512a-83ed-ba3d2ddeef2e | note | Reference - Section 173, Section 304.08 Table 304.081
c4276ebe-98b5-5753-b1d1-38481e957c79 | note | Acceptance Criteria - During compaction, material Moisture Content ≥ 85% of OMC and maintained until test rolling has been completed.
7ef32f03-8de6-5051-a9b7-690e17c2751c | note | ○ Density Ratio to be based on tests performed with Modified Comp active Effort.
457cda31-a8aa-538b-ad2b-c1d46d970126 | note | ○ Scale B:
131d2e52-64ab-525b-9747-c3f5714c68b2 | note | — Subbase Layer CDR ≥ 97%
2160d0b0-7924-53f8-830b-39a225f3a487 | note | — Base Layer CDR ≥ 98%
5a346e27-101c-5a9b-800d-aa36676c080b | note | ○ 6 tests per lot for lots >500sqm. If the lot is < 500sqm, then 3 tests per lot.
de173051-7d83-57c5-9ea3-568dc4060ffe | note | ○ Scale C:
da337d53-5056-59bc-a8d8-3a9159b45656 | note | — Mean Value of Density Ratio (3 tests):
8789b060-e518-52eb-9edd-ee179b7ad640 | note | — Subbase Layers >98%
c23d88a0-1d7f-517e-b989-852ec9ea3e74 | note | — Base Layers >100%
4fb94da8-46fc-5f34-b8f0-1b66ac0935c0 | note | ○ ATTACH: Compaction Test Results
38d6a0ec-61b9-5618-b413-9365350ec004 | note | Method - Document Review
9e39ceae-fd15-5ff4-b57e-adc70d16581d | note | Frequency - Each Lot Where applicxable
584e3ef9-5bc4-5d2e-92ab-eb77044cf4b3 | note | Category - IP
e38bcd4d-19f0-5b31-ab67-e6e540b123bf | note | Responsibility - PE
3167d71a-950a-5a37-9eb8-5a8d4ed10f15 | note | Verifying Documents - Compaction Test Rersults
ff5d816e-f074-52e9-91a5-c86a291229a9 | date | Date Completed:
3839de14-bc2f-4007-88eb-4ccb9b571bcb | checkpoint | 6.2 - Post Compaction Materials Testing (Results)
d9e06317-a020-5cf3-ab80-f849e7d83ae9 | note | Reference - Section 304.10, Section 304.11, RC 500.02
c1649cc3-dd86-5ee0-a78d-168c21ebc394 | note | Acceptance Criteria - Note: Refer to IFC drawings to confirm material required. Material property requirements will vary depending on material type.
f96af24a-f5fc-5751-aa91-4c00adf7d3f7 | note | ○ 20mm Class 3:
f944c00e-07fe-5f5e-9a80-44c8138b1ae2 | note | Grading
d8c616ee-60bd-5c0c-9462-9523af2796a4 | note | — 26.5mm 100%
b194d89c-56ab-5560-b190-42348e0891cd | note | — 19.0mm 95-100%
f908994e-bd3f-5c1d-8c9b-0f2d14c5d0ba | note | — 13.2mm 75-95%
f6f2cfe0-75fc-576f-9831-7ab453959ba8 | note | — 9.5mm 60-90%
6a576cf2-3194-5778-b933-6206729a5dc9 | note | — 4.75mm 42-76%
6623f1cd-b187-5185-ba67-cb417a62abf8 | note | — 2.36mm 28-61%
8d83c353-6e4c-527d-9ee5-3fc1705ace13 | note | — 0.425mm 14-29%
757cec31-04ee-534e-9ccf-9e52a5fe2437 | note | — 0.075mm 6-14%
619e900d-6979-560e-82d8-54581ee42854 | note | — PI between 0 to 10
cc9e2b25-abb0-5dea-999d-e4abedbb20cd | note | ○ 20mm Class 4:
b59a0edb-0d60-5bf7-a74b-e3eb8bc22718 | note | Grading
bd1ba9c7-51fc-5cc2-9edb-0f84a91da6ec | note | — 26.5mm 100%
b27288ef-b095-525d-b8b3-fe439d45f930 | note | — 4.75mm 42-76%
0161b132-c906-58c3-b73d-7e8156e98669 | note | — 0.425mm 10-28%
a70167f9-e77f-596d-a3ff-a47581376c01 | note | — 0.075mm 2-14%
bfd7686f-46be-5ea4-945f-1a886ddea741 | note | — PI between 0 to 20
156e8da2-b9a0-5651-a48b-1e9324892d37 | note | — PI x % passing 0.425 mm sieve (max) 450
37bc043d-ab5f-5860-837f-5e9d79a2058f | note | ○ Scale C: Post compaction material testing is not required (Choose NA)
b537814f-86d9-5f47-843c-57609bdfd2c1 | note | Method - Document Review
314aaf67-f477-5cd3-98b1-8b7ba41ea3d7 | note | Frequency - Each Lot Where applicable
8e9bd916-9ac4-535c-8e62-89cfe1a3c86d | note | Category - IP
bc4b6629-16ab-56a8-9562-25cc70669e5a | note | Responsibility - PE
2f4277d9-0772-544f-a5f6-1c83adf86849 | note | Verifying Documents - Compaction Test Rersults
4383289f-c446-510e-9d5a-f7e4b244e9e9 | date | Date Completed:
4da4ba49-828d-4024-8c31-f7a7dacc9d98 | checkpoint | 6.3 - Survey As-Built - Surface Level
7c525a37-b52e-5b4e-ba85-f0f4456b4e12 | note | Reference - IFC Drawings Section 304.06 Table 304.061, Table 304.062
b1577c2d-b9bb-504d-b439-0f08680f3cdd | note | Acceptance Criteria - No point on the surface of any pavement layer shall vary by more than 8 mm from a 3 m straight edge placed in any direction.
5bdf6947-3aee-5a01-9972-e9de23030e26 | note | ○ Subbase course shall be not < the specified thickness by more than 15 mm.
f6825c7f-e220-5213-b97c-fdb067547bf9 | note | ○ Base Course shall be not < the specified thickness by more than 10 mm. The avg. thickness over every 100m shall not be < specified thickness.
05e26699-997e-5b6c-8d9d-7416d5fe01ce | note | ○ The combined thickness of subbase and base courses shall be not < the specified thickness by more than 15 mm.
5268abd3-07cc-54c8-ba82-52069ceb612d | note | ○ Scale B: A minimum of 40 measurements per lot
2be1e9b4-af26-5969-9a0a-60f5f062e9ea | note | ○ Subbase: mean range +6mm to -12mm, maximum Standard Deviation of 13mm
d96a2b91-8711-519e-acee-8d6aa6b54d1b | note | ○ Base: mean range ±8mm, maximum Standard Deviation of 10mm
089aa683-6bf6-5356-86a3-adec535e91d1 | note | ○ Scale C:
c1854501-16bc-5049-a89b-100dad0271d0 | note | — Lower Subbase (mm) +15/ -25
3a8e5630-2d41-5fec-9be7-9ccebd10fdb2 | note | — Upper Subbase (mm) +10/ -25
0eb68a02-39f3-58a3-9214-614f76249551 | note | — Base (mm) +/-15
1c078be5-fe14-554e-bfbd-1521d8ec091c | note | Method - Document Review
4cc1f079-298f-58e4-bd57-853d20a4a8e1 | note | Frequency - Each lot
98856719-1917-5c75-b42d-98d210651731 | note | Category - IP
cf644941-db80-5138-82b5-523766a3aee1 | note | Responsibility - PE/Surveyor
6161b39b-692d-5a8f-9f33-5bd4161bdd9d | note | Verifying Documents - Survey Conformance Report
c3bb2fee-d6d8-5c62-a64a-ff23d0a03c56 | date | Date Completed:
c41f856c-c653-4393-8d02-546e3e2ec1fd | checkpoint | Final Inspection
3579465c-829d-592b-92ed-4db38d71b497 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
bc914a30-1db0-5d7c-81cd-b1ee3ca35cf6 | textbox | Name:
0306f38f-4489-5220-8117-0752b5c535db | textbox | Position:
1b4a7755-377d-572a-ba4d-47f935f73336 | textbox | Date Completed:
507a9363-4a43-48b5-8046-429d8d47f5d8 | signoff | Sign ITP
af89f4c3-3bf5-42db-88cd-c88434827b51 | checklist | ITP-229-CIV-Ferris-Subsoil Drainage Rev 0 | itp | ITP-229-CIV-Ferris-Subsoil Drainage | ff3eb146-057d-4906-9fdc-155ca2f326a1
d62bbbb8-0fa3-450c-841e-267f69a5bedd | section | 1. Referenced Documentation
ffee9dcd-f8c5-4a82-b527-220749c871ce | checkpoint-no-value | Referenced Documentation
3bbe4216-5463-5721-b0bc-b06ce0d4ee54 | note | Document Title: ITP-229-CIV-Ferris-Subsoil Drainage
71303997-0df8-5e80-b15f-61da4472281b | note | ITP Description: Ferris-Subsoil Drainage
71101d52-4ded-5a05-ac26-cc35b2482bf7 | note | Discipline (e.g. CIV/STR/RAIL): 229-CIV
e4fb8a42-dc84-5b28-a913-6aa11a4c08f9 | note | Revision Number: 0
fac9a7bc-cf02-5e4f-8df3-5f9778f76f5c | note | Revision Date: 23/01/2025
1d011472-b0d9-5c62-b232-c00475db276f | note | ITP created by: Kamel ALSHOBAKI
8e47b507-416b-522e-a1aa-e3e847e35b39 | note | ITP approved for use by: Pradeep Talasila
abdbf87d-7384-57bd-a427-9029feca5c14 | note | 1.1 - Non Dependent
91ed0788-23f1-5429-8918-dd8aa270ca30 | note | Reference - VicRoads Section 702 (May '19)
599f5658-109b-4d29-959f-6697cfe29ec2 | section | 2. Preliminaries-Material
fe1b822b-e36c-4ba1-bdad-bb40daeb81db | checkpoint | 2.1 - Pipes
d8706b1d-d4bc-511d-ac7c-e93b0cb7655f | note | Reference - IFC Drawings VR 702.04
288e93cd-7961-5946-8ee3-12618a12677d | note | Acceptance Criteria - All subsurface drainage shall be Category 1, 100mm DIA Class 1000 Perforated Plastic Pipe. Perforations shall be max 1.5mm and minimum length of 150mm per sqm
4f52d0d2-b1b4-5dd7-bb04-3c8e93800e08 | textbox | Reference: Material approval in Teambinder:
5ea63642-2a0a-5b8e-a00e-79d10b13661a | note | Method - Verify, Document Review
64d0b35f-69cd-567e-9397-29b6f3362549 | note | Frequency - When applicable
b8347c6f-cdfd-5982-ac3a-6c0e50859dc2 | note | Category - HP
4f533b7c-d0ad-5235-8fe2-a81c390cad57 | note | Responsibility - PE/Nominated Authority
50ab5b33-8571-5498-8397-078d44501b83 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
4344fe12-c972-565d-908c-aa011e81ee70 | date | Date Completed:
fe5ba36c-de34-4a55-b332-01fced39d4b8 | signoff | AUTHORITY HOLDPOINT
6f11c502-202a-4762-81c6-a4754f6d71c0 | checkpoint | 2.2 - Granular material: Filter Sand
a46c4578-e51c-5627-9e18-0dfb86a862fb | note | Reference - IFC Drawings VR 702.05
c8b0f087-8ffe-5bbd-98ab-9cc87f3a2386 | note | Acceptance Criteria - Filter sand to be Grade A4 and comply with Table 702.051 and Section 801. Supplier to be accretied with Vic Roads.
055d5b10-2b76-588b-9686-73eaa2aaebf3 | textbox | Reference: Material approval in Teambinder:
15df3fad-4915-5ec0-ae53-cfc20b1830b2 | note | Method - Verify, Document Review
384b61f1-9475-5540-a366-8e8070c52979 | note | Frequency - When applicable
4cad7a40-08bd-559a-a100-b6de0893c00f | note | Category - HP
fc1e99d0-3d01-5e80-8206-00c48cf6d4fc | note | Responsibility - PE/Nominated Authority
43f3e6fe-be8d-573b-a170-6b3787a98d81 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
82cefd1b-46c3-5135-9c5e-2a5e114bb0e3 | date | Date Completed:
cae44efa-e431-4a16-b069-5677fd7c0465 | signoff | AUTHORITY HOLDPOINT
33a86448-0680-4e32-bd1f-5b8c17e73c60 | checkpoint | 2.3 - Granular Material: No Fines Concrete
61ef3d9b-c6df-5c16-bc36-6e82ef260be3 | note | Reference - IFC Drawings VR 702.05 (e)
7eb5154f-7955-57b8-ac13-ca73a0e69d58 | note | Acceptance Criteria - No Fines Concrete: Shall comply with 702.05 e)
cd3c24da-f8e2-5612-a8f6-ca3116a3d56d | textbox | Reference: Material approval in Teambinder:
dcc48873-48a5-5268-8462-944b937db48e | note | Method - Verify, Document Review
048b7121-a2ae-5699-abb0-1d8234c034c9 | note | Frequency - When applicable
1d4d724d-3cfa-5693-a31e-4afbcf939b42 | note | Category - HP
d79f3ad8-3378-5b40-af6f-92e615d43916 | note | Responsibility - PE/Nominated Authority
baf40432-92f0-5f2a-a626-02b712bfe68d | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
68badb88-1801-58e7-a6c9-bf8b5231fa92 | date | Date Completed:
3472d57d-1fa9-4275-bcae-608c6002ea64 | signoff | AUTHORITY HOLDPOINT
6845b6a2-41e3-4fb4-85a8-05527e41700d | checkpoint | 2.4 - Geo textile
319dc623-aef7-53de-a2d4-01eaec7ffc5f | note | Reference - IFC Drawings VR 702.06
6a2e6e57-35fb-59a6-be8c-75c2c4726690 | note | Acceptance Criteria - Geotextiles: Shall comply with table 702.061
12ae6353-46e9-537f-9b77-5e71c9766afd | textbox | Reference: Material approval in Teambinder:
4e2bc262-857a-508c-885a-070435a559fc | note | Method - Verify, Document Review
1234df39-4f7b-5fa4-a2c6-186d4de6bfd9 | note | Frequency - When applicable
d1981d18-dd88-5c02-b10e-63fe7f714754 | note | Category - HP
c1c303ac-58a2-568b-8ead-134af52e2278 | note | Responsibility - PE/Nominated Authority
2522cf04-c3f8-59cd-91ff-5243fd6a9d19 | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
091b32e6-a4e1-5e38-b76c-6d05f818c32b | date | Date Completed:
3e9bd49b-0517-4605-abc2-9d85388892db | signoff | AUTHORITY HOLDPOINT
24d4d759-4975-46f3-9153-5384174238ba | checkpoint | 2.5 - SSD Pits, Pit Lids, Flushout Risers
4ba65a36-4a8a-5bdf-a591-3c98aa413a70 | note | Reference - IFC Drawings Section 702.04, 702.05 & 702.06
fdf6640d-1ff8-57ac-a566-0fb7426eacf4 | note | Acceptance Criteria - Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
46d32aee-720e-5460-80a3-64bfd467f29c | note | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
fb6fba39-7042-52e7-85d9-1ce284d8acba | note | ○ Flushout risers: As per SD 1631
b58260eb-32cc-5562-9e43-565001906452 | textbox | Reference: Material approval in Teambinder:
db5e882e-9e00-52a9-99b4-1f489ab96ad1 | note | Method - Verify, Document Review
274d7399-cd2a-5158-9a72-9936940d94e9 | note | Frequency - When applicable
fc2b453d-24d1-5286-a3ce-54c85057bd2f | note | Category - HP
058c39c1-59b7-5996-a0ef-6f9a27b36d67 | note | Responsibility - PE/Nominated Authority
e1aba871-b6bf-515c-ad06-c5b61c9dd1cf | note | Verifying Documents - Material approval in TeamBinder, This ITP signed off by Nominated Authority
03a092ad-16cb-5215-b027-41e760d80c24 | date | Date Completed:
92a49235-efed-427c-8ff2-d91cf533e1a3 | signoff | AUTHORITY HOLDPOINT
ba0b9345-6242-424d-80ed-ba129d3d5931 | section | 3. Pre-construction / Pre-installation Activities
ecb00963-b2eb-4a74-8ce9-0a4827773a22 | checkpoint | 3.1 - Survey Set Out
b2390052-16cd-5c6e-9fe0-cefdb526438f | note | Reference - Section 702.03
3e3d51ee-22fe-5412-88a9-7a3292ec2224 | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
e5368ada-0ae7-5429-aebd-b149671804dd | note | Method - Visual inspection
953b14e2-4ed0-5d60-96f8-371e5a6c7d15 | note | Frequency - Each Lot
a7d8ac66-2551-5914-85bb-d8f6c0268bab | note | Category - HP*
e48bad0f-f63d-5780-b525-869eb7db266f | note | Responsibility - SE/Site Supervisor
3153698e-5a8f-5515-bf59-33be680c33de | note | Verifying Documents - This ITP
c4a63891-3ebc-571a-92af-7dc7d96c21bb | date | Date Completed:
ddfbf719-3f07-4b93-a44b-d48955aaaae3 | section | 4. Pre-construction / Pre-installation Activities
b9bfa2a8-9d4a-4f11-b669-d7b9f0d49e47 | checkpoint | 4.1 - Survey Set Out
78bfeab6-5fc8-5330-8409-973050325981 | note | Reference - IFC Drawings Section 702.03
45a51bb4-e8e9-559b-8128-859bc0a8a9f1 | note | Acceptance Criteria - Survey to set out Subsurface Drainage line.
2092e0a3-eb68-53cc-80fa-0ce3bf335ce2 | note | Method - Visual inspection
d2fda7a1-4cae-527a-b8c4-d9ff0d292313 | note | Frequency - Each Lot
a91d9049-7509-55dc-aa7c-fe3451c0bb8f | note | Category - IP
f5b21723-92b7-5b5a-9176-521012954d01 | note | Responsibility - SE/Site Supervisor, Surveyor
e372fe10-6ec2-52d3-a207-2ad07f9c65a6 | note | Verifying Documents - This ITP Signed-off
b7f07661-9a1f-5ef6-b924-1284c88e5494 | date | Date Completed:
a8be2d9c-f314-4c6b-ae76-bb2fb7718700 | section | 5. Construction / Installation Activities
746f604a-d848-431f-ba9b-4a2806719f4d | checkpoint | 5.1 - Trench Excavation
fd3a5db9-82c1-54d1-ad5b-ee33bdae8e16 | note | Reference - IFC Drawings Section 702.08
56ce388c-dbe4-5b1f-8f66-987651104ac0 | note | Acceptance Criteria - The bottom of the trench shall be compacted and shall be not more than 50 mm below the specified level of the invert of the pipe.
de3fa237-5303-52c9-84e4-514c809bafbd | note | ○ There shall be no departures from the grade of the base of the trench that would allow ponding of water.
d8830f83-e293-5893-b943-11aa9dde88c1 | note | ○ Excess trench excavation shall be made good by filling back to grade with compacted material of permeability similar to that of the surrounding material and any loose material shall be removed.
0c37b651-1db9-54e2-8eb0-2174ad30f84e | note | ○ Where a geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when the granular filter material is placed against the geotextile.
6146ab02-2737-5325-b086-5e544f130249 | note | Method - Visual Inspection
85bbe902-56dc-5d6a-acda-2ca54b9ec5cf | note | Frequency - Each lot
609b6851-78db-5eaf-af55-e0927fc5f513 | note | Category - IP
0bbeb2ef-dc06-520a-8f83-ae9814367bff | note | Responsibility - SE
95242939-e61f-50c0-9c8d-9c8ced24efcc | note | Verifying Documents - This ITP
48342e2c-82d5-563e-8335-947c9237d2ef | date | Date Completed:
9f02f0dd-6402-4176-b732-976ad7a2287d | checkpoint | 5.2 - Trench Excavation
112c459b-9bdb-5916-bff3-b20b3318c57b | note | Reference - Section 702.08
aa0d68ce-74aa-58e6-be76-9b969286f640 | note | Acceptance Criteria - The base of the trench shall be inspected to verify compliance with the requirements in VR 702.08 prior to placing bedding in completed excavations. The Superintendent shall be notified at least 24 hours prior to the inspection.
bdee55c4-67a4-51f7-b861-aa697abef6bd | note | Method - Visual Inspection
af445870-acaf-5a1e-abf0-d36fae05ab2e | note | Frequency - Each lot
863f7bf9-c8c8-5658-aba3-27f452a2e3e6 | note | Category - HP
50911c64-6a7d-566e-8b34-94b4479b8d98 | note | Responsibility - SE/Nominated Authority
5debe6f7-50c3-5fc4-a835-2ce626a75cbb | note | Verifying Documents - Nominated Authorith sign off ThisLine
2aae0828-14c0-5d05-a510-8007325c3b08 | date | Date Completed:
683261b2-7888-4db3-b8ac-ebfceb5c967a | signoff | AUTHORITY HOLDPOINT
4c4787d2-de5a-4a90-bd8c-7468a6a77e36 | checkpoint | 5.3 - Placement of bedding
7a51099c-a100-5224-adc7-93742a7c43ca | note | Reference - Section 702.09 c)
9c8180e6-b493-5764-af33-3bd4e813dd3b | note | Acceptance Criteria - Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
af230465-5f3f-5f70-b287-f357e6bb0c25 | note | Method - Visual inspection
cfca8217-9785-57bb-9ec6-c9e367d6b3cd | note | Frequency - Each lot
2b0500aa-54cc-54a6-b828-b54620f66422 | note | Category - IP
3a5df60b-c092-52ec-9a06-969fdf6b4899 | note | Responsibility - SE/Site Supervisor
3583b800-0e2a-5324-952a-0625feda00ee | note | Verifying Documents - This ITP
f33a91dd-0301-54e4-a583-e29471c9739f | date | Date Completed:
09f1b20b-8683-4a75-8852-0bd9b820de62 | checkpoint | 5.4 - Traficable Pavements
b5803197-6eac-508d-b379-93ef2badb52a | note | Reference - IFC Drawings SD 1601, EDCM 201
b08785c5-f6af-5f93-a10e-d48df9283d5d | note | Acceptance Criteria - Choose pass when applicable
ebbb273e-b8e0-56ee-87f6-045c509a5b12 | note | ○ All Subsurface drains located within trafficed pavement shall be Type 2 with no fines concrete filter with filter fabric wrapped around the trench in accordance with SD 1601 and MCC202B
dd4f01bf-a249-58c6-a2b8-e0970a216c6d | note | Method - Visual inspection
bc262f01-e064-5999-80bb-5ea3e2f4f229 | note | Frequency - Each lot
9e16bba4-2ee1-5fdf-a090-ffa99d693667 | note | Category - IP
51f011c7-0166-5332-bd1e-5e2f46c3eda8 | note | Responsibility - SE/Site Supervisor
9f91aab1-c1d2-563c-8173-815e7910f85f | note | Verifying Documents - This ITP
69062753-d197-5125-b793-89bea2abfeef | date | Date Completed:
fb42edb4-3ed1-4ece-acfb-c8d97138a13d | checkpoint | 5.5 - Outside trafficable pavement
1528eee9-23e1-5060-a8dc-3ae2410c36ad | note | Reference - IFC Drawings SD 1601, EDCM 201
12910347-2999-5b07-98c8-34e613dcf090 | note | Acceptance Criteria - Choose pass when applicable pavement drains outside trafficable pavement shall be type 3 with grade A4 Sandfilter and Geotextile wrapped around the pipe with minimum 150mm lapping length
5405a44a-2cc8-5190-9e33-b0bc5f5317e7 | note | Method - Visual inspection
75c617dd-0d4f-56b4-b4ef-79d994453ab2 | note | Frequency - Each lot
1032269d-6213-590c-a380-fdc07c481d3c | note | Category - IP
2c2ca5fb-148d-5515-ae21-7370e470c8b2 | note | Responsibility - SE/Site Supervisor
7f055432-9a03-5f4f-82d0-56898d0a89d2 | note | Verifying Documents - This ITP
2177e799-7e79-556a-ba18-26ce00281c05 | date | Date Completed:
b0420eb4-c2f6-4220-9f08-5ad9373e1036 | checkpoint | 5.6 - Pipe and Geotextile Installation (if required)
6e08f3e7-d660-5826-b2f3-d70144fe1e58 | note | Reference - Section 702.03, 702.09
a648f164-e991-501e-89df-8069fb1ee27c | note | Acceptance Criteria - Pipe shall be placed centrally in the trench on the prepared bedding.
8cfde8ce-8b7c-5965-888a-672f8ece598e | note | ○ Slotted pipes shall be laid with the opening in the lower half of the pipe. Pipes, geocompotises and geotextiles placed, joined and lapped (Mininmum 150mm lap)
6cbcf3df-284d-5462-a0a3-b05404078aee | note | Method - Visual inspection
b487c0cd-adad-5d11-b477-7e9871cacd0e | note | Frequency - Each lot
9e4f9302-37f4-5b29-ba7e-b87acbb240dd | note | Category - IP
bc0c5a95-61cf-50cb-b0f1-08b85c1927d3 | note | Responsibility - SE/Site Supervisor
eb7225f6-3654-54a8-8706-284857d78e9b | note | Verifying Documents - This ITP
265f287e-dec5-5f84-8bad-d0611103805b | date | Date Completed:
3848e9ab-134b-4b40-804f-63c3eae82c68 | checkpoint | 5.7 - Backfill Installation (Granular Filter Material)
86703a2a-af67-5f6b-91bd-de6021981985 | note | Reference - Section 702.09 (g)
cad385a3-e367-58be-860e-2d31d33f28a8 | note | Acceptance Criteria - Material shall be placed moist and compacted in layers not exceeding 300mm.
0cb8187c-50b8-5fc1-a77e-980543422781 | note | ○ The method of compaction shall be in accordance with the procedures and reviewed by the NA.
23fe0fb8-9ddf-5c05-a7fe-ab20ddfb5c38 | note | Method - Visual, Doc. Review
f282fda3-c506-5796-b9c5-7ac455d4222d | note | Frequency - Each lot
9d6a0ad9-e423-5a45-9a07-4b7962e31605 | note | Category - HP
67b7bf7a-100f-55e0-9d10-31b69bedf819 | note | Responsibility - SE, Nominated Authority
3cfdc29c-905f-559a-92e6-9165f0f8f4b3 | note | Verifying Documents - Nominated Authorith sign off This Line
84263c3c-af66-56c0-b2eb-56fbb5b00ebd | date | Date Completed:
abf33565-390c-4ab0-a3da-b0cd05823f02 | signoff | AUTHORITY HOLDPOINT
9001b2ab-281d-4286-a9de-267724aed994 | checkpoint | 5.8 - Backfill Installation (No Fines)
1fdbd77e-f3ab-514c-ad0b-4666fef5a408 | note | Reference - Section 702.09 (g)
dd6ce415-f4fb-5ebe-a1dc-6e08ade74c8a | note | Acceptance Criteria - All subsurface drainage beneath trafficable areas shall have no fines concrete filter medium. No-fines concrete placed and compacted within 1 hour of mixing
3ac9aa6b-9a50-5169-aa98-58a28c7c56e0 | note | ○ ATTACH: No Fines Delivery Dockets
e8a8aec8-0fe6-5611-8df3-8d7b0b89f90b | note | Method - Visual
9d1429ee-3551-5844-9f19-a7679c4d76d5 | note | Frequency - Each lot
da34b816-4f6c-545b-9e2c-a7691c722e46 | note | Category - HP
4fef4466-e183-599e-bed7-27b68a4f65b9 | note | Responsibility - SE, Nominated Authority
eafb1d34-9bf5-59f2-b9e2-3ebab356f29c | note | Verifying Documents - Nominated Authorith sign off This Line
decf15ca-3c85-5a81-b116-15cb9af515b8 | date | Date Completed:
9a06f139-3b63-4b13-b036-4d4764fc34e1 | signoff | AUTHORITY HOLDPOINT
514da10e-d659-4d09-971d-d5ec154dd406 | checkpoint | 5.9 - Install Pits and Flushouts
4278d120-2dc1-5659-8f88-ffd9d01d4928 | note | Reference - Section 702.10
71889f63-7bab-5f31-bdaa-ba9aad16d435 | note | Acceptance Criteria - Subsurface drains shall have access points at the start and finish of each run. Subsurface drain end shall be located min. 100mm above the invert of the stormwater drainage pit outlet unless noted otherwise on drawings. Inspection openings shall be provided between 100m and 150m intervals unless noted otherwise on drawings.
541bf296-b7e6-52f6-9a16-37d00b6298b3 | note | Method - Visual
783cb14b-df25-577c-ad27-e3a5484ec89d | note | Frequency - Each lot
ab4b0393-7eed-572f-9f6c-1fd27669cdad | note | Category - WP
ecea2807-6765-527b-8d72-766329efd72c | note | Responsibility - SE/Site Supervisor
6123e466-1405-534a-911d-cbcfb176a88a | note | Verifying Documents - This ITP
a555d096-254a-5103-b894-f08cd067c2c4 | date | Date Completed:
1ad69f89-a809-42d9-b65b-f6dfef13e726 | checkpoint | 5.10 - Marker Points
ead987df-bd25-5d0e-8e9b-06bac0f17d4e | note | Reference - Section 702.11
75383053-be38-569c-82b0-4a2264cad07a | note | Acceptance Criteria - At all fill batter and drain outlets, supply and erect marker posts as shown on drawings
2c48ef5b-faee-57a6-98f2-de2f1f5f3ede | note | Method - Visual
a77c60d9-d268-531f-ac70-0aeeee2ff719 | note | Frequency - Each outlet
494c31ed-0c1f-559c-aa25-fb3be53a36b7 | note | Category - IP
ce769859-b2bc-5b94-bcb6-f6b45a9539f3 | note | Responsibility - SE/Site Supervisor
1181eb14-20f1-571e-80f4-77f9636f9026 | note | Verifying Documents - This ITP
7daa2cc1-2683-5e1b-99b7-e78140042597 | date | Date Completed:
3dc0f925-d75b-475f-9a59-48fa37c4f615 | section | 6. Post-construction / Post-installation Activities
71000a1f-fc00-453e-a026-1516be621030 | checkpoint | 6.1 - As Built Information
9a173a9f-a6a0-516b-9624-99747bcaa8dd | note | Reference - Section 702.03
125a381f-0429-5b2f-af1d-4e483bd916d7 | note | Acceptance Criteria - The invert of the sursurface drainage pipe or the geocomposite drain shall not be more than 25mm from the specified level and not more than 50mm from the specified line
d73b0c26-33f0-5dc3-9635-bf43e6e52dc1 | note | ○ Changes of grade shall not be abrupt, or occur at a rate exceeding 10mm in any 3m length
dd6ab7a1-bb5e-5c6e-9f74-c659555ab6f8 | note | Method - Document Review
65a20cb5-e7f8-527d-94dc-a18744d7c013 | note | Frequency - Each lot
4aff6612-6b70-58f6-a31e-69e3f307dda7 | note | Category - IP
506e3f48-15de-5dde-b6b1-2c04b442a644 | note | Responsibility - Surveyor, SE/PE/SPE
bbb0504d-33a0-58d6-9f6d-f7b6ab575dbc | note | Verifying Documents - Attach Survey Conformance Report
eb63ecb9-764e-5ee8-8f0a-f552945f917e | date | Date Completed:
3269e488-5822-4a6c-8781-a8fc3540b2a7 | checkpoint | 6.2 - Flushing
72c86832-e86b-5cef-8b03-2e3d0e6c1c4c | note | Reference - Section 702.09 (h)
24fcde0a-2da9-5299-8254-39829482c1f2 | note | Acceptance Criteria - Flushing test shall be witnessed the NA and shall confirm that the drainage line is free of obstruction. To be completed after installation of kerb and channel, barriers and road furniture.
811824f2-bb4b-5e64-9eef-1e47d7dc4ef5 | note | Method - Record Review
555c254a-39d8-507f-bf25-fb93b7cd8526 | note | Frequency - Each lot
106e9ae2-0479-52c4-b724-b2b2d662d10d | note | Category - HP
55f4bac4-5368-51cf-a46b-aae5b12af122 | note | Responsibility - SE, Nominated Authority
ad47b3b2-c5d9-5a91-bc6c-e714791ae0c8 | note | Verifying Documents - Nominated Authorith sign off This Line
afb5ac1c-4a9a-5077-a780-33faf07071b4 | date | Date Completed:
78ea2f38-1e8c-4dab-a6be-8e93878c472f | signoff | AUTHORITY HOLDPOINT
d4146fdd-2703-4882-a1e5-4e709b8873ee | checkpoint | 6.3 - CCTV
95babddb-9e74-537d-9c5a-902129c61335 | note | Reference - Section 702.09 (g)
b45b80e2-dafa-54b7-b487-d4a656c10dd0 | note | Acceptance Criteria - Placement of asphalt shall not proceed until the CCTV inspection has been completed, damaged or deformed subsurface drainage pipe has been removed and replaced and the waste and defects free condition of subsurface drainage lines has been verified by the NA.
e3e74e10-4db6-597a-ad62-00595458c639 | note | Method - Record Review
e4cf91f5-4a41-5d04-9219-10e798b8ae03 | note | Frequency - Each lot
9aeba76f-c0ad-5e18-9975-1ea41c827962 | note | Category - HP
ca84987f-37dd-52dc-98dd-8ce24e886aaa | note | Responsibility - SE, Nominated Authority
f681eaea-45bb-56cc-93fe-b36fcae23acf | note | Verifying Documents - Nominated Authorith sign off This Line
73aaf7e8-51f1-5f97-8e69-db338d5c3a63 | date | Date Completed:
5944eea1-d76b-4568-aedb-b8a45d480d02 | signoff | AUTHORITY HOLDPOINT
2788e9d3-b9f6-48d5-956d-36b71070ec9c | checkpoint | Final Inspection
78a917ea-f522-57a9-a927-95f38f4b597b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9da750df-0e95-5578-9015-78279ca25d3e | textbox | Name:
e02ad69f-db30-5e4b-b603-3802f7d1add9 | textbox | Position:
777765ee-aeb6-5a0d-97cd-480ef9782b62 | textbox | Date Completed:
8fb4c302-fe53-47c0-a063-76cda9ea9f19 | signoff | Sign ITP
a4ffc4e2-d159-40f8-9776-82f47c0686cc | checklist | ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation Rev 0 | itp | ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation | 551122e4-70a4-4bf6-bc79-3e66e5d7a20c
c1458f5d-8f08-420a-9285-1f6ba4423c73 | section | 1. Referenced Documentation
220090b8-116c-42cf-ad50-e57e76245948 | checkpoint-no-value | Referenced Documentation
ccfce74e-f68f-5676-8b4c-40613f22bbea | note | Document Title: ITP-230-CIV-Ferris-Stormwater Drainage Supply & Installation
c8444932-17b6-5939-8c7a-95234c88043e | note | ITP Description: Stormwater Drainage Supply & Installation
a0427d61-2f46-5164-8802-5422a1d4f05e | note | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
fa74261b-d028-52b0-ba86-a608fa3ddabd | note | Revision Number: 0
05405eea-c70b-5cf3-9067-655fe6a8f0e4 | note | Revision Date: 23/01/2025
344887af-c9f7-5c2a-839e-45042c4d933a | note | ITP created by: Kamel ALSHOBAKI
947903f2-7dcc-5ca5-8d5d-7560d3905131 | note | ITP approved for use by: Pradeep Talasila
1d3f91fb-3e67-541c-82f9-d5ffd116fdf1 | note | 1.1 - Non Dependent
82529233-1540-5060-a6db-dd8b5516a4b2 | note | Reference - VicRoads Section 701 (May 2020)
e48d3d4e-37c2-52e4-a3a9-04ef4070b609 | note | 1.2 - Non Dependent
0821ea2b-9705-5346-bc76-9d1fb654054b | note | Reference - VicRoads Section 705 (June 2021)
f6c82e23-67f5-561c-ba2d-4476b2b413ba | note | 1.3 - Non Dependent
71d6970a-b27d-51fe-a5c0-268da18e3a83 | note | Reference - IFC Drawings
e3dce7d9-6668-5f18-b190-b1c39d60e4ce | note | 1.4 - Non Dependent
0febfdc2-14b4-5802-864a-565736279823 | note | Reference - CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
48c506a0-4fc6-4d3e-973e-fc1b93b49038 | section | 2. Preliminaries-Materials
cce3a0e7-0856-4e58-8528-46e735456ea9 | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
470e0936-56e1-5175-9da4-cef6c756f18c | note | Reference - VR Section 701.04, VR Section 701.05, VR Section 701.09
ba91699d-38af-526a-838e-078853ab75d5 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
9af38dd8-484b-5730-a7af-8257a09d4405 | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
8ebee7f7-4bbc-5e81-9fed-0d9d2006d85b | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
8679f7ed-5e02-505b-8554-68c093755d2f | textbox | Enter: Teambinder Material Approval number
bd40449e-b6e7-5198-a83c-c3d06eefca13 | note | Method - Document Review
ef26ff40-d94f-5ab6-8df1-6a98a2cc0e13 | note | Frequency - Each lot
b3355a87-679c-5645-a4b9-6b03b0ea98ee | note | Category - HP
759a1f18-1ac1-5106-aee7-8b409365a6e4 | note | Responsibility - Nominated Authority
a27e808f-8c8c-57d2-bfb9-a59578b679e3 | note | Verifying Documents - ConQa HP Release
b9801965-0716-56a4-a113-e902c98d848e | date | Date Completed:
102835fd-4a5b-4247-8dce-ff511a6a976f | signoff | AUTHORITY HOLDPOINT
62933d01-6665-4355-87f1-e4115e7ec986 | checkpoint | 2.2 - Drainage Flexible Pipes
43d2098d-f47d-5887-9c5d-4a2a7e70697f | note | Reference - Section 701.08
d5ff89f8-4494-5342-a4d4-f9a71fa9b9bd | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
de30c4fa-a9a4-598d-94ec-bac7f6596c2d | textbox | Enter: Teambinder Material Approval number
c2cb2fd9-82e2-5bdb-bf72-e36bf65b3a20 | note | Method - Document Review
0434435e-812a-57c9-9083-fa31a46427b9 | note | Frequency - Each lot
08be0792-5c00-53ba-922f-e63d5d3a1756 | note | Category - HP
6fdfac13-14ad-5fe4-9dda-98d858aa2c11 | note | Responsibility - Nominated Authority
8e4cca4d-da05-5564-a158-b18952dab20a | note | Verifying Documents - Teambinder Material Approval
189260a9-2a0e-57f2-9769-3d5359d71a5b | date | Date Completed:
20b7c56c-6325-4531-8ce7-47014d3e0c27 | signoff | AUTHORITY HOLDPOINT
50575fda-09ef-462e-adc4-9e2f2faab41d | checkpoint | 2.2 - Precast Drainage Pit
198128c6-7062-57e5-8f80-37ef128047f8 | note | Reference - VR Section 705.07, VR Section 705.04, VR Section 705.09
651a7a5a-86e8-5aa6-86ad-411106da4d79 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705.07 & 705.09
0b773400-b93f-5610-bf32-ba33c2896cbc | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04. Concrete grades shall comply with Table 705.041
10bc1542-0e8e-5393-87cb-b3da77700288 | textbox | Enter: Teambinder Material Approval number
b94b60b5-aa9e-556b-a04b-4d46c9d29942 | note | Method - Document Review
bf3cfed3-7a5e-59b8-a8d9-ac063f7ab3f7 | note | Frequency - Each lot
dfe86fc9-7f3c-5c6d-bdd6-43d3942f3f6f | note | Category - HP
cf97c5ed-3a79-57dc-9e41-bba3e9d2ac54 | note | Responsibility - Nominated Authority
f24f0835-5b3c-5413-a192-863ba7bda9e9 | note | Verifying Documents - ConQa HP Release
0d6fc806-36e3-5e95-bbbe-989c9c521098 | date | Date Completed:
4a944266-5af0-43b5-93c2-60d46519ea87 | signoff | AUTHORITY HOLDPOINT
7fa2fa6e-7f28-4189-a3fb-f4066bb0fea9 | checkpoint | 2.3 - Cast in Place Drainage Pit
39c22bdb-b157-5b22-8a17-bd362aec8746 | note | Reference - VR Section 705.06 IFC Drawings
9a891a7d-2b99-5239-b159-6cf10e941eb6 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed in accordance with the requirements of VR Section 705.06 and at the locations and to the dimensions shown on the drawings.
9b4383af-af2d-5d30-8eef-19c6ca3efef2 | note | Method - Document Review
e240781b-5531-5da4-9230-bc57774595fc | note | Frequency - Each lot
7722055b-ab8d-5cce-9a91-8b72c8835e35 | note | Category - HP
3671213e-cea5-5a47-a28a-528e04362a08 | note | Responsibility - Nominated Authority
47bef8c9-73d1-5543-9401-d4c71feaa63e | note | Verifying Documents - ConQa HP Release
6d53071f-adc4-591e-a4a6-a09e7993ac6d | date | Date Completed:
84fbd892-9039-42de-809a-fae173b6ae41 | signoff | AUTHORITY HOLDPOINT
4e3c9b3e-fabb-4b34-87c3-ed30e47b6d81 | checkpoint | 2.4 - Drainage Pit - Step Irons
f5db679e-e602-5e4f-ab29-216f40ff6335 | note | Reference - VR Section 705.04, VR Section 705.12
dae4db1e-1655-5f09-a3ff-40ee396b77e5 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
4bc60850-8f40-53c9-83d8-90071e055035 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705.12
2ad73898-bb84-5630-979d-1afb0bffa2c6 | textbox | Enter: Teambinder Material Approval number
992ab594-3129-53d2-9265-dce93b10171c | note | Method - Document Review
fa447817-78f0-51ce-b88c-ba2aeb876614 | note | Frequency - Each lot
502c8fbb-919c-50f5-a3bf-fc47a92272e6 | note | Category - HP
17ffca41-a4fa-5ba3-91f1-83fc001e5c22 | note | Responsibility - Nominated Authority
335b257a-4b80-55b1-a421-f1cb2dca27b9 | note | Verifying Documents - ConQa HP Release
1536e889-ed6f-5ddd-8447-aba87c8766e6 | date | Date Completed:
e3b15165-5247-4e5a-9c92-0899af7ee35d | signoff | AUTHORITY HOLDPOINT
cf680f23-93d3-4520-bc69-5945c1fbf0f8 | checkpoint | 2.5 - Drainage Bedding Material
27c848c0-4e9d-586a-a23e-4c9be1a7de44 | note | Reference - VR Section 701.09
64d539fb-3aa5-50a4-9673-83157d9f1b71 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
9d253069-e17e-5c9b-a308-7c941e3df9e7 | textbox | Enter: Teambinder Material Approval number
7fd1cd6f-fe05-5af1-b011-0f236bee7db9 | note | Method - Document Review
a9c16fd7-75e4-5a04-9271-3579f6278632 | note | Frequency - Each lot
826cf96b-20b8-5044-9abd-f1fd17b44dc2 | note | Category - HP
05a76894-1ff7-5ec5-bcc6-418ff29d2458 | note | Responsibility - Nominated Authority
969afbcf-46c3-5c27-a36a-267d58d18604 | note | Verifying Documents - ConQa HP Release
93626551-690b-5239-8b9f-de5bb0301f70 | date | Date Completed:
b36f8881-cbcb-4819-bb7b-895b94e5a1d0 | signoff | AUTHORITY HOLDPOINT
190fe515-9daa-4bca-a7bb-dd002e49f33c | checkpoint | 2.6 - Drainage Backfill Material
7295a1de-ba9e-5142-acdb-dee674aff65d | note | Reference - VR Section 701.09, VR Section 701.19
27073973-59bd-535b-b155-91ec7ef320d8 | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
1d343d55-64c8-5890-b802-7d72f102da4f | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
5e1ea76f-c5e7-5629-9045-cf78c7f36bb2 | textbox | Enter: Teambinder Material Approval number
e8b54f35-d1cf-5068-a58d-b2d7ac3180dc | note | Method - Document Review
daa30693-9119-5bdc-9ba7-fa3e6dd2a5cf | note | Frequency - Each lot
f7194fb1-4511-53dc-8324-56bec54ca8d1 | note | Category - HP
d5744249-d17b-527b-a624-c6dadda7ef78 | note | Responsibility - Nominated Authority
5a8ea354-9b1c-55da-aabb-b69544404b1f | note | Verifying Documents - ConQa HP Release
26800e36-485f-5ff5-9e6b-719378d5a431 | date | Date Completed:
adfbaf56-f0b5-4096-bc66-4820ce40add4 | signoff | AUTHORITY HOLDPOINT
758f5daa-195d-49dd-8bf3-738640947661 | section | 3. Preliminaries-Documents
6c0b045d-a762-4b58-918f-06014187c44b | checkpoint | 3.1 - Subcontractor ITP (where required)
68419f85-a30b-5a0f-848d-b2ebfbb8c572 | note | Reference - Subcontractor ITP
20595ae8-a911-56ea-8ef6-a19ea7ae573c | note | Acceptance Criteria - Subcontractor ITP shall conform with the IFC Drawings & Relevant Standards & Specifications.
02db9a94-09e1-5197-b88c-c9cc05b19668 | note | ○ Attach: Approved Subcontractor ITP
0320e519-06cf-5e6d-b461-13b4bbb18baf | note | Method - Document Review
2af16b77-a7f1-5253-a5a0-ef7ea29d175e | note | Frequency - Each Lot
abb56578-f483-53f3-bd83-b473bcdfa23a | note | Category - HP
1c48dc3d-983a-56e4-9bcd-b8155c92e1d5 | note | Responsibility - Nominated Authority
8ae0667e-feca-503c-aff5-694f451936d6 | note | Verifying Documents - ConQa HP Release
94c7aa07-89fd-566c-b6f6-ed07ddf8ef4e | date | Date Completed:
1ca5fe47-d888-4ca2-8d55-6ea3e08c8cfe | signoff | AUTHORITY HOLDPOINT
cc5f3e68-74c7-4f27-b0eb-3aa36bf9e06d | section | 4. Pre-Construction Activities
54fb33f4-b3e0-437f-8ed4-1d489df74be1 | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
57a9932f-9866-55c0-a74d-e669e25643a8 | note | Reference - IFC Drawings VR Section 701.10
0d9558eb-0213-569b-949e-9d122e45ce9f | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
ea4ca6e3-f528-5862-850a-7b11dad93985 | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
056c3a7c-ad6e-5686-aef8-3086f8b742eb | note | Method - Survey
55d9c549-fd09-538a-b793-720ae4f425f3 | note | Frequency - Each Lot
9e7df4df-32d9-574d-a63d-cc4e5d18e76d | note | Category - HP*
42b42011-811a-5efd-b922-a5a2c77e24dd | note | Responsibility - PE
4b440c77-4d96-5b6e-8a83-1faa5e8dc5b9 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
234e80a1-36fb-5547-b761-5b5d60a0cc37 | date | Date Completed:
02c93c40-0f0c-4d67-8f5e-af4add9967b1 | section | 5. Construction / Installation Activities
48a6c48b-4293-42de-8104-eb460747f76e | checkpoint | 5.1 - Pits - Excavation
5e90185c-f791-5c5d-a308-b284e01edeeb | note | Reference - IFC Drawings VR Section 705.05
749671b8-d2c2-5608-97f8-eb5544a4ceb8 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
c0c37d1e-08a8-5537-a029-5a06af918330 | note | Method - Visual inspection, Measure
8b9eb036-f9c7-5016-b9c3-ee89983a0ef9 | note | Frequency - Each Lot
9f8ad79e-4d87-524f-82e7-60cec2041001 | note | Category - IP
28bde88f-ac73-51e4-80c0-d447878bfd53 | note | Responsibility - SE
25bdf1e5-fcf9-5829-b0b1-7ab285c381f3 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
9c036b9b-55cd-5eec-98ef-648a170d4580 | date | Date Completed:
28edc8f2-58fd-4799-934c-152e1be3cd27 | checkpoint | 5.2 - Pits - Placement of Bedding Material
d25fa03f-2c19-5ea6-b490-944ed93079e3 | note | Reference - IFC Drawings VR Section 705.05
d905836b-66bd-5701-ab0f-77c8f3decf9a | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
6f2c1337-d2b9-5e09-9781-927c293e4a11 | note | ○ > 80mm for clay foundations
61d60df6-4b06-5a41-b2c3-310ea5fc0d1e | note | ○ > 150mm for rock foundations
8e8a66a3-9d7e-5c08-93ee-1dfbe7f6fd7d | note | Method - Visual inspection, Measure
dc3124df-7802-570b-8657-80647192b037 | note | Frequency - Each Lot
7f719ab6-19d9-5d63-a589-e6ac2a90947f | note | Category - IP
5405809a-1642-5693-b625-22c0be3ead66 | note | Responsibility - SE
f59cdc52-3a0f-57e1-b179-dc2a42e5a4b5 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
dd035bed-2a83-5ba2-9c57-514f9d7f4307 | date | Date Completed:
527d338f-fb04-413b-9d0d-d263ebfceb89 | checkpoint | 5.3 - Pits - Bedding Testing
19a11e68-33cb-5a96-b1f0-b65995e89fb7 | note | Reference - IFC Drawings VR Section 701.20
10353034-158d-5f82-bf3e-533fa7c509ce | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
3eb60bd2-2116-55d6-b944-caf4e0ba03fe | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
900ce843-ff50-51b5-8f5d-b1ac923e7c55 | note | Method - Compaction Test
407650d4-dc79-5997-ad41-43e7bb7759ca | note | Frequency - Each Lot
fd586cb3-6a66-5c6b-954d-02992696405d | note | Category - IP
c7433226-5737-5064-abd7-e7294adc0753 | note | Responsibility - SE
7d4b1f1b-4e25-5ced-b8bf-cd5c828efff2 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
1e0e6727-447b-5aaf-adea-56f537e9207f | date | Date Completed:
626b9bb4-60fb-4375-84c2-558fa376362e | checkpoint | 5.4 - Pits - Placement of Precast Drainage Pit
18b80367-4064-5b92-bf16-32809f044074 | note | Reference - IFC Drawings VR Section 701.10
64162453-df07-5ae4-a3dd-76666c9834f8 | note | Acceptance Criteria - Survey pick-up to verify:
f7161d18-2f90-5308-a4b6-19ed6bf8ba47 | note | – Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
244268c7-09aa-52de-ab17-f169da2b4ca8 | note | – Offset of entry pits required to match lines of kerbs or barriers ±20 mm
cbb26e14-b435-54ea-9bf5-24aa0e2e51a8 | note | Method - Visual inspection, Measure
13757fa2-4718-5d5f-b27e-ed7430c86b03 | note | Frequency - Each Lot
2599bdab-97c6-5696-a008-ff971efe9115 | note | Category - IP
c9a63140-37e7-5a9c-8900-c6e6635a7612 | note | Responsibility - SE
6cf9e8ba-a9e4-5f47-8d55-f223c2b7b240 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
f1b14f80-6cae-5b47-91d5-7580ad4572f5 | date | Date Completed:
24d9945a-7a7a-412f-a1b8-2a79c1ae1956 | checkpoint | 5.5 - Pits - Cast in Place Drainage Pit
10af61bf-0496-5efe-9f75-54271204d530 | note | Reference - IFC Drawings VR Section 705.06, VR Section 610, VR Section 611
af8bad3b-eb87-50e1-91dc-6fe9bc75e693 | note | Acceptance Criteria - Cast in place drainage pits shall be constructed at the locations and to the dimensions shown on the drawings and in accordance with the requirements of VR Section 610 and 611.
726a8757-ae7d-5e2a-9fbf-b6ef046f0353 | note | ○ Cast in place drainage pits shall not be constructed with fibre reinforced concrete (FRC).
98b43e85-620e-5824-86ea-1f1d903c3b1e | note | Method - Survey, Measure
8e4e36e8-18e2-5b5e-ae23-885de2c579f6 | note | Frequency - Each Lot
4c87b2e7-fcbd-5b5f-b8da-7f14b04f4203 | note | Category - IP
090efc70-9b7f-5dbc-9ec5-71cb04aaff39 | note | Responsibility - SE
18ec0563-5187-54d7-b895-2f8092d584ab | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
45e7eb85-fe84-50cb-820e-0d9d0dd5f391 | date | Date Completed:
6130c857-e771-4907-8b49-0aa4a97bb973 | checkpoint | 5.6 - Pits - Jointing & Drainage Connections
a0963b5c-f0b0-5d5a-a41e-ce69b9ae467d | note | Reference - VR Section 705.11
81c63451-e478-589a-be60-017f6f64919b | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
50b75ee4-a25e-5381-8474-18dacfa1c036 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
942acbaf-a738-52a3-aa8d-6839f6f55642 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
24b48428-d970-5791-94a1-1a0edd0ff8cc | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
69c4c994-7966-5c03-bb97-512b4f179721 | note | Method - Visual inspection, Measure
c9bac6ed-8744-5b02-9da7-3e89357836b7 | note | Frequency - Each Lot
92c900c4-ad03-5c9e-aa3b-47ce24a8c6b5 | note | Category - IP
10efc7e5-a0d6-514d-936e-c58ffc0c2ef1 | note | Responsibility - SE
8bde8bc6-9330-57fd-8306-bd8b065f6171 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
9cf92292-0b90-52a6-a9ee-c7f13ce5ffe6 | date | Date Completed:
dab69464-66f7-4920-affc-80de87af300e | checkpoint | 5.7 - Pits - Shaping of Floor
09d27d42-ebd0-541e-91f3-0ecae227302b | note | Reference - VR Section 705.13
40dc880e-53b4-5631-8c9c-8794a1e05598 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Section 705.13.
02fdba74-d99b-523a-a78a-aed07a0441fb | note | Method - Visual inspection, Measure
1c7f1902-e821-5653-83c2-25674dbf10af | note | Frequency - Each Lot
f5084a58-4d35-5a13-b986-dafef672646e | note | Category - IP
1b96ecc1-8043-5726-81c3-dbd6ee2e06e1 | note | Responsibility - SE
bcc9992d-92d2-51ed-91c1-55d3c8509624 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
e191083c-7a6e-59c8-9697-999747918bbc | date | Date Completed:
baa851a2-5a69-40ee-ab98-d70ac409b99c | checkpoint | 5.8 - Pits - Step Irons
3eacaf58-b0f6-5247-b89e-a4e4b57c39ca | note | Reference - IFC Drawings VR Section 705.12
ea65d037-0eb5-588c-85b5-ba2040abcb8c | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with 705.12. Ladder rungs shall not opbstruct openings and that water does not discharge on them. Step rungs do not come within 50mm of the top of the riser.
a65269b2-6486-54ab-9e88-8075475159e1 | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
e952a302-0b0e-5f3d-8cac-5724fe815c71 | note | Method - Visual inspection, Measure
f4014870-4a26-5958-a8c3-3141ccaa207f | note | Frequency - Each Lot
c49ec835-0e5f-573a-8912-5eead91273de | note | Category - IP
5b94c668-57c0-56b0-95c3-916d6d2a7b42 | note | Responsibility - SE
d07061de-b43b-5a3f-8a19-8715435dd053 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
cb4d53f9-4926-5259-a637-fc085991073c | date | Date Completed:
a7c324a4-7c69-4926-a5bc-e35530d07388 | checkpoint | 5.9 - Pits - Fitting of Covers
ba9750f3-34bd-5f30-88f6-67108824ef97 | note | Reference - IFC Drawings VR Section 705.17
d74af244-c310-546b-8b78-cc221883cd62 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
47f6e3db-916a-532a-96dc-90602a6f3c0f | note | ○ Height shall be within 10mm of the design level.
c62bd232-8dbf-546e-ba56-ff2dad11797d | note | Method - Visual inspection, Measure
4914efa6-7149-571d-a8a2-8326662546ff | note | Frequency - Each Lot
de59d8af-5afa-5de6-9b9e-15cb8fc32045 | note | Category - IP
81434496-7ed4-5894-b285-5cb2b5e8a730 | note | Responsibility - SE
2218561e-50fd-5934-8918-b3b60f92a44b | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
cdb56f2b-087f-56b3-9378-19d5e33a7f83 | date | Date Completed:
675130e3-7072-42c7-9dcf-1e3a0dd51a37 | checkpoint | 5.10 - Pits - Pit Lids
d486f89c-6dfd-5110-800d-b362f9088ea3 | note | Reference - IFC Drawings
bc59230c-516c-589d-b64f-b949b49ff70a | note | Acceptance Criteria - All stormwater pits shall be provided with a locakable pit lid minimum Class D with in-fill material or fibre glass Terra Firm Enduro or similar.
2e6ca747-c502-52f2-8031-fa7c739b7d2a | note | Method - Visual inspection
3b5dd9c6-a4dd-5caa-8b17-c2764c695f25 | note | Frequency - Each Lot
b814bf99-0a95-562f-9a67-9e173a023fcc | note | Category - IP
56ede307-82af-5e51-8cfa-b5f9f71e9515 | note | Responsibility - SE
ce0ae12c-3a0e-569c-ac8f-a6cfed8d088f | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
a2d12075-21ac-5f4c-9f65-428fc1eb7cb3 | date | Date Completed:
eaeecdf5-f1b3-497c-b38e-8a8d8b8c6429 | checkpoint | 5.11 - Pits - Backfilling Around Drainage Pits
af5d29c0-ff8b-57c6-ab4e-1089ce76591e | note | Reference - VR Section 705.18
b195c757-5cac-5c9a-a399-2f21c1dd1d3b | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
18eb44b7-3e98-55af-ad8c-08dfdcac12d4 | note | Method - Visual inspection, Measure
67925a1f-c2dd-57de-8c77-98df32211af0 | note | Frequency - Each Lot
cbc8753a-6391-5805-b024-aefe22940728 | note | Category - IP
60268fb8-6df1-5558-a8fd-22d744b6af89 | note | Responsibility - SE
f01be20d-728a-5814-b6bd-8919c57e0ff8 | note | Verifying Documents - CHK-002-CIV-Stormwater Drainage Pit Installation
95ad74b0-fc36-50cf-9b66-8452e1b8b032 | date | Date Completed:
bd8ff0d2-5f1f-44e2-be3d-c18829da14f0 | checkpoint | 5.12 - Pipes - Trench Excavation
0e5a6652-5f20-5c52-9bc2-24cfb4ad84ad | note | Reference - IFC Drawings VR Section 701.15
3b641820-fccf-5446-bffb-3f6cd24be7b0 | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
27a45233-81f4-58e0-805d-d2fb2bc81322 | note | ○ > 300mm, < 600mm for RCP
2e620c6b-7dbb-5c2c-95f4-739c082a5908 | note | ○ > 150mm for Flexible Pipe
b8a3bdfc-dcc0-5337-b74f-c3cf01d60a64 | note | — The base of the trench shall be compacted to refusal using mechanical plant.
cbacb612-298e-52ac-a354-2c950f4cc9fe | note | Method - Visual inspection, Measure
8951f87e-36f5-5029-a795-7dd3371a59d7 | note | Frequency - Each Lot
90525523-5dbb-52ed-b610-aaffa1bf3e33 | note | Category - IP
dd6c3d67-db2c-5649-b9a3-be3242e6c931 | note | Responsibility - SE
ae2b04a4-71e1-5cb9-b7f3-d57e9ffea835 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
ec797a46-8a96-5d9a-a6b8-382821b3d2d8 | date | Date Completed:
4b034458-e38c-4425-b003-5ea7a4938ff9 | checkpoint | 5.13 - Pipes - Bedding Placement
64b62072-ec3a-55cb-a223-399b61757316 | note | Reference - IFC Drawings VR Section 701.16
7a3225a8-445d-5e34-8f48-9dd0e292f507 | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
de60335c-3bce-5328-81d8-850403ed54b8 | note | ○ > 100mm where D<1500mm
f56c14ee-7246-584a-9d70-95d29b77e785 | note | ○ > 200mmwhwere D≥1500mm
2907b09b-9388-5f1f-97bd-424b98ceb4ca | note | — Bedding material shall be placed and compacted in layers <150mm loose thickness
016d7f2f-c8d4-55d1-9ef4-82e1c2bcabae | note | Method - Visual inspection, Measure
5ba12217-b93c-5dbf-88dd-bac3e6facca5 | note | Frequency - Each Lot
ba72b709-d4eb-58d9-bba8-6f54956346a7 | note | Category - IP
9fc6646d-6ac6-537e-85ca-1c10fbd0de1a | note | Responsibility - SE
a74f94d9-8544-5629-ae7e-e9b7b255292e | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
b3db2330-cbdf-5157-9cba-b1f8406c3486 | date | Date Completed:
982735d0-0df8-4537-82e6-9dfd1324f459 | checkpoint | 5.14 - Pipes - Bedding Testting
06e9d871-1211-58e6-a8e1-63a33553d9c1 | note | Reference - IFC Drawings VR Section 701.20
312d113f-f7f6-5068-a87c-acbc71b6af3c | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three
d0fe262c-ab2d-59b1-94b9-a08deebad505 | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
ae15d648-f572-5f2b-a22f-36e1d4bb16cb | note | Method - Compaction Test
ce338965-18d8-5418-81f6-606512d62497 | note | Frequency - Each Lot
730c7399-5866-566b-8542-3feac1078cc9 | note | Category - IP
725cbac5-6011-5959-95a4-4c8b1678d5b2 | note | Responsibility - SE
2308354d-0d96-5d91-abf9-d0267dbd12d3 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
2153d31d-625a-5b9b-af47-fa12b404076f | date | Date Completed:
07eab39e-55d4-4c2e-ac45-baa4175e4cbe | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
9f99b6a2-829b-5819-9480-f5ff7c79f808 | note | Reference - IFC Drawings VR Section 701.17, VR Section 701.20
0b759aaf-74ce-5d7f-842d-122b21d71c84 | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
f5c5c6af-de65-5285-9398-f952da893981 | note | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
2404d5b7-9fea-5219-b6dd-fdcbaafb92df | note | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
67811088-f98e-54c4-ae3b-2bf3fbee22c0 | note | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
5d806d36-ff45-5efd-8e5f-820c5cbb502d | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
2f2920db-f0d7-53b2-913f-173cf4c25167 | note | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
4251f9e4-a3ac-5d2d-92d0-44b9ac263946 | note | Method - Visual inspection, Measure
85b25263-0f23-56e3-bac1-e6b546773b71 | note | Frequency - Each Lot
b9e32d5b-55f6-5970-b9cc-827fc276088c | note | Category - IP
544cae08-6fe5-5dee-8882-6264a164cac9 | note | Responsibility - SE
362c72e8-8e45-5c87-9316-5fc3fd424b1a | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
4f720238-419a-5811-8056-17da86416e18 | date | Date Completed:
e4fdd2ab-fc98-4a57-b35d-c4d4cf618694 | checkpoint | 5.16 - Pipes - Lifting Holes
2146302a-067c-5fdc-8760-36385eaf2ba8 | note | Reference - VR Section 701.18
8c9fdfab-717b-59ac-960a-5ea048c54a8c | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
d314049b-fec4-5cd7-b412-c1ec4278a5a5 | note | Method - Visual inspection
2a601e40-61ea-56cb-93a0-399fb93227fe | note | Frequency - Each Lot
9e35cc51-18c2-59c4-8730-4e726e876e61 | note | Category - IP
e853f010-2735-5500-bf73-dd2079b367a2 | note | Responsibility - SE
d3a7585a-9534-5904-abd5-9d8f44f0d30d | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
8f291058-9e2d-5440-8094-777448324f15 | date | Date Completed:
172f98be-1b9d-4b82-b443-8e081fda0055 | checkpoint | 5.17 - Pipes - As-built survey pick-up
c13372ad-fb37-5a19-8d46-25ba5f90952b | note | Reference - IFC Drawings VR Section 710.10
3aef12f6-ca9a-5e5d-a742-c75fb3f2ee02 | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
a5802c09-dec2-5a91-99f7-34f3244a31ab | note | – Offset pits to kerb +/- 20mm
29dc9106-68a2-5fea-9ffd-b0d9fc418690 | note | – Plan location pits not adjacent to kerb +/- 100mm
8d4ce209-7830-56c5-8fef-d0a4dd76d7ad | note | – Invert level of pipes at pits +/- 50mm
d56c57b1-908d-50f2-9ee1-40e0c13e3eae | note | – departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
5ac11493-8edd-59c7-859a-dc150dc9c1b1 | note | Method - Survey
c50c0fa8-3ccd-51b2-9507-0460e3ff7afc | note | Frequency - Each Lot
c36d2801-927a-5f55-b750-a91a3a6caf77 | note | Category - IP
5d87dbc1-71cc-5cb1-b63c-97ce8ff5152c | note | Responsibility - SE
a50f35d2-bf06-50e2-8805-77a8edbc792a | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
7072f28a-30e8-5dcc-9cbb-f4ab85548a2c | date | Date Completed:
1bfc055f-8ce1-4a0a-8c83-b9e455187bb0 | checkpoint | 5.18 - Pipes - Backfill Placement
cdbf58a3-2f81-5a2e-bc6f-ec8a7d47ba72 | note | Reference - IFC Drawings VR Section 701.16
16631132-ae01-5645-a403-f22ff4699aa1 | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
958109ff-9b96-54aa-8ff4-7bdda2e42324 | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
daf99899-4183-58c0-8bb3-5746025a8d92 | note | Method - Visual inspection, Measure
e2966eb0-7e43-53b0-9963-94a345b9eafd | note | Frequency - Each Lot
c528dd5e-4ca3-500e-a0e7-5673c017ae47 | note | Category - IP
3f345548-70fd-5230-a772-4a559dea009b | note | Responsibility - SE
f1b8b7be-0bc7-57a1-afc2-35883cd2b57e | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
7a16d966-68ba-5b02-a06c-da830f597673 | date | Date Completed:
1dba4fc6-11ea-4550-b456-12dace036dad | checkpoint | 5.19 - Pipes - Backfill Testing
ad031c38-6a70-5752-951c-62104381be3f | note | Reference - IFC Drawings VR Section 701.20, VR Section 701.29
a9e659d8-872c-506c-8f50-342d297b9047 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
39390773-95b4-511c-a6cc-864aecc69df3 | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
ee4668a6-8641-53db-9ff8-9781287d82b0 | note | Method - Visual inspection
35ffc3ad-0320-5f94-ac85-6b50fb104773 | note | Frequency - Each Lot
63aab8d6-7590-50a5-9ee3-dd940b0f6629 | note | Category - HP*
29880db9-dff1-5a34-aa7e-16b17853e08d | note | Responsibility - PE
6309a45e-7828-530f-8c50-653ed5edc331 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation
04ac9d4a-46ad-51b2-a35c-61c493d03b2d | date | Date Completed:
9cc87885-713a-4118-938b-646daed89143 | section | 6. Post-construction / Post-installation Activities
f9a41ac0-8d6b-4c4a-baa7-c29399992acc | checkpoint | 6.1 - Flushing & CCTV
3c4da116-c8d3-5891-b7fd-ab267b06c5e2 | note | Reference - VR Section 701.28, VR Section 701.30
5ea28935-7fae-5197-a86e-f93158864d66 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
6dcbf382-43c9-520b-952e-896ff45f8868 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
0adb5997-ebb8-5349-91c1-78aeb95c907f | note | ○ Attach: Flushing Record, CCTV Reports
e128e27e-dd57-59d4-9ab0-99b2f93bd270 | note | Method - Record Review
81fc2ef8-b455-5a25-a310-f46c08a37f34 | note | Frequency - Each lot
e79418b2-3585-5e6f-9839-a5a5593eb210 | note | Category - HP
c588bc0d-da30-5d42-a392-d877cd964bc8 | note | Responsibility - Nominated Authority
5cf70f4b-f059-54f6-97eb-193320fee8da | note | Verifying Documents - ConQA HP Release, Flushing Record, CCTV Reports
d10c7084-911f-5b64-96a6-618a83356adb | date | Date Completed:
e5ed1d81-7fbf-4f91-9477-baf2cb43a1b1 | signoff | AUTHORITY HOLDPOINT
8751d992-b4ef-439f-97c4-21113c325338 | checkpoint | 6.2 - As Built Survey
c5de9a05-7d9a-5a0a-be4a-fa265ea09d1d | note | Reference - VR Section 701.10
270e778c-a5bc-5ea3-b595-ce457783f4e4 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
3665d1d0-22dd-5e98-a585-6d78db2d5872 | note | ○ Attach: As-Built Survey Conformance
4f5261e2-0f1d-5c1b-b854-622bebfc9f9a | note | Method - Document Review
fd27154d-1cfe-585a-9dce-6c5ff6ea293d | note | Frequency - Each lot
2a6da622-ec42-5a8f-aedf-37d20072f4f4 | note | Category - IP
26fe221d-e4fb-5b6c-9804-88450fed179f | note | Responsibility - SE
6eb1da31-3447-57ef-8829-643a0bd4e98f | note | Verifying Documents - ConQA HP Release, As Built Survey Report
5f695a52-2d2b-580d-b758-880566298bf5 | date | Date Completed:
ede930f7-7235-479c-b2d2-440557540de5 | checkpoint | 6.3 - Repairs to Damaged Pipes
e6c08bcb-6f34-5e01-9967-24a576039b5b | note | Reference - VR Section 701.31
134de21a-dcf0-52a3-b3e4-b0dbe0b20cf4 | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
8983f845-d611-51c8-913d-87329370bda5 | note | — cracks wider than 0.5 mm
f7d88140-2755-53a9-aa2a-08298fd7cac6 | note | — spalling of concrete
04cb9f23-b71d-51c6-ae10-cdaab543df1b | note | — exposed reinforcement
b7990621-2cf1-542a-a9aa-979b5394df64 | note | — joints that are not fully engaged.
9e9c1ce5-ab67-5757-a660-7550ce6307c2 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
071d5ae7-56fc-5910-aead-084dbed5f284 | note | — longitudinal cracks greater than 2 mm
bca0d54c-51c2-5fae-9a65-d4b99c32ce3f | note | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
2aee65da-910e-5af1-a532-e335913e4943 | note | — circumferential cracks around part of the circumference with width greater than 4 mm
e9608df1-cdbf-500f-83b2-501c00479521 | note | — penetrations with area greater than 400 mm2
12339def-49d0-598d-8022-e65ca61d1ea3 | note | — pipe joints that are separated.
45cadd91-1ef1-580a-89a6-f0ecb98c404a | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
7cb7338a-4275-576e-86d9-93aa695d191d | note | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
a64ea455-387a-5f06-8299-923a63f72166 | note | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
bbf2a39c-7e81-52db-88b1-3240a8d9d32d | note | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
3a96e46b-e346-59fc-9674-2dc300490cf2 | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
f6e65d57-8e4a-57c6-86f6-ab5dd30824e8 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
b436a538-3cb5-531e-92c2-9b08a22931ec | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
c17719d4-fd84-5eb2-88d4-5359db326d13 | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
c248198e-0953-5965-bae4-41ab4af49ebf | note | Frequency - Each lot
93295d0d-9665-5e54-a243-7892c2ea6147 | note | Category - HP
58c27da4-6646-55a0-8552-cdbf972118dc | note | Responsibility - Nominated Authority
f0d11e9e-a11c-51c6-b765-3243257a5534 | note | Verifying Documents - ConQA HP Release, Approved Repair Procedure, Post Repair CCTV Report
9eade41e-475c-53a9-b896-132113b0e51e | date | Date Completed:
6ee0f28b-f311-4db0-9c85-938fd3418aea | signoff | AUTHORITY HOLDPOINT
7f0787b1-a044-41b0-84e9-f6b954caca8e | checkpoint | 6.4 - Non-conformance Report (NCR) Closure
f9b044c7-6b74-5e9c-b2a7-1e4899313ce7 | note | Reference - MRPA Quality Management Plan
b111e9da-6e57-5d40-ab31-162ff0f3c517 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
e412e432-ce53-55e7-85a3-8d19013a6a61 | note | Method - Document Review
7e347ea8-ae7d-5eb5-84fa-912512e490f4 | note | Frequency - Once, prior to closure of this lot / element / Work area
15c7e608-fbf3-59af-8749-fb429be08716 | note | Category - HP*
106a79b3-296a-5fbd-a3b3-6408f366f468 | note | Responsibility - PE
73ddb569-94c3-5dec-adcc-fa701ab0f511 | note | Verifying Documents - CHK-001-CIV-Stormwater Drainage Pipes Installation, CHK-002-CIV-Stormwater Drainage Pits Installation
ceaf3904-485a-5441-85b0-d7eea7a4721c | date | Date Completed:
df1945a3-519b-4c39-b79e-4002cb32c4b8 | checkpoint | Final Inspection
612d7a1d-bc26-5320-bffb-c7dfe2fb72d0 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
1dc4e762-7bd0-5a63-86e1-f5db305feb51 | textbox | Name:
896e1b4f-8c17-5237-b3c4-c98465efc585 | textbox | Position:
35b679e8-cead-562d-b744-e4c0e65f592f | textbox | Date Completed:
e9338047-24cb-466a-b3d2-4c220042645c | signoff | Sign ITP
| checklist | ITP-231-CIV-FRMS-Type A Fill - Road Rev 0 | itp | ITP-231-CIV-FRMS-Type A Fill - Road | 36d68765-6c1b-49e6-9d9f-ba1899663467
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
b4cf90d3-4ef4-5500-8308-ba8a6088b631 | note | Document Title: ITP-231-CIV-FRMS- Type A Fill - Road (Supply and Install)
c02769f1-0de3-5186-8660-a492346b8cef | note | ITP Description: Type A Fill - Road (Supply and Install)
41e82946-a9fd-53c6-9465-1ac69a648bec | note | Discipline (e.g. CIV/STR/RAIL): 231-CIV-FRMS-
9eaa99cc-b1b6-525b-829a-8e863fc28c39 | note | Revision Number: 0
69bb6bb8-ba74-54a7-8ba0-e234cdb3385a | note | Revision Date: 28/10/2024
aeee9bc6-1d47-586f-867b-f9029e36568e | note | ITP created by: Cedric Guico
1d2cb22d-cfeb-53a5-9b3d-e3db0a5435ce | note | ITP approved for use by: Pradeep Tisala
2bdd7751-7a85-5970-9799-d81ea84f8afe | note | 1.01 - Non Dependent
20cdafa7-ab70-5679-9de3-217b925bf637 | note | Reference - IFC Drawings
a2ef19fc-60a2-5160-8d81-12d5fea2b9ed | note | ○ VicRoads Standard Section 176 (Sept 2008)
ec2118d3-d4df-5d9e-8b35-ce621dbc6ef1 | note | ○ VicRoads Section
9177e861-ee6b-5030-9e72-2485a8fa54af | note | ○ 204 (Dec 2015)
8b7e21f7-b531-5cf6-8bcf-85205f551f3c | note | ○ Code of Practice RC500.20
c358de88-2b5a-5da9-8b7c-ac4ca4a50005 | note | ○ Code of Practice RC500.5
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
97d33fde-be6a-5ddb-a787-9d68a1eb3387 | note | Reference - Section 204.04 b) Table 204.041 IFC Drawings
47aa3f38-4adf-59d3-ac78-5e03bdc3fc19 | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
b8bd69c4-761d-5032-b18b-cf7abd33e80a | note | ○ Assigned CBR≥8%
ddd12352-171e-541c-a101-4c8151cbb95c | note | ○ Swell ≤ 1.5%
c0bfaadb-5f86-5406-ba1b-e596dab99c2b | note | ○ Permeability ≤ 5X10-9 m/s
cbff4a32-d49c-51c1-986b-eaa45966754e | note | ○ Grading:
64e3d265-a9ff-5223-b49d-60f3254d65a1 | note | — 75.0mm 100%
67fbed68-6e1c-5dc2-a06f-cc59a72b380a | note | — 4.75mm 40-80%
632bb070-36d9-5cb1-a949-a0b624c14fa2 | note | — 0.075mm 10-40%
09f793e1-4cdf-5f4f-abc2-ebb22254cbd0 | textbox | Reference: Material approval in Teambinder:
0e4d8d0e-e6a3-558b-9121-c6ca1e3e4293 | note | Method - Document Review
ef7d2fb0-a49e-5d35-bc3c-b91d21dfe747 | note | Frequency - Once, for each material type
022b49bf-8132-571b-b7d1-43c238b154d4 | note | Category - HP
cdea62a1-0f45-5576-a2dc-0ccc7c616114 | note | Responsibility - SE/Nominated Authority
f73b8e7a-dc9d-5f7f-bbb5-f9b68bb1cb7d | note | Verifying Documents - Supplier Material Conformance Certificate
ffcf06e4-247f-5c7b-973c-8026fb54010d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
d0052291-b446-5bd7-b53f-1ed86933aadc | note | Reference - Section 204.10 (b)
4dc4d39f-c8e7-5fe5-a423-c8247846e84e | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
284b7b9a-b8a9-576d-94d0-39388cd71a27 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
2254a28c-48a3-5c3d-be20-e9586a9f9c7c | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
88696e81-2283-570a-bc1f-c89e0071566f | textbox | Reference: Subgrade Preparation Lot Number:
71e86f21-53bf-5470-8ec6-355f228f1ad9 | note | Method - Visual Inspection
0dccba75-84a5-5d82-aa2c-feed1fb223ca | note | Frequency - Prior to commencement of fill works
460b6207-eb75-59d5-b5c8-74bbe4ee49c5 | note | Category - HP
d7fa1318-2d93-52f9-9f24-d656edb65150 | note | Responsibility -
0c5a3ea5-6d51-5e9c-a2a4-915b69890451 | note | Verifying Documents -
6e3ca31d-a125-5b33-bec7-7bfb30467009 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
2111c622-165a-5208-a69a-6744fd60c784 | note | Reference - Design Drawings
11fa4729-5026-5a75-9fba-ca2b025f50c8 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
eb39f693-477e-59ec-978c-e95ede250ec8 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
a8834ac8-9d67-54a2-a765-fc34ee132b0c | note | Method - Visual Inspection
e3c1bfcf-0a01-5ff5-be9e-0e1f9186a1f6 | note | Frequency - Each lot prior to commencement
184eb843-d49f-51ec-9b3e-23d3a2f9298e | note | Category - HP*
3a967ead-72e6-5faa-a8e1-4832d809417c | note | Responsibility - PE
890f0ad3-935d-5716-82cc-d9433bdfafbe | note | Verifying Documents - Signed ITP, Lot Map
e274067d-9cc0-521a-96be-9763637ea8e5 | date | Date Completed:
| section | 5. Type A Fill/Verge Activities
| checkpoint | 5.1 - Placing of Fill
dd07bbcb-3197-5f7d-9044-7717b8440bf8 | note | Reference - Section 204.10
63bcb50a-2124-5687-b757-08e87f62fbac | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
0ac8a7dd-f30e-569f-9617-4e43f2137394 | note | Method - Visual
e7e64a82-5166-5869-b09a-ef677262e73b | note | Frequency - Each Lot
0de16e73-6364-5aef-b16a-388b167787b3 | note | Category - WP
bd7891a5-f5c6-515a-a81d-eef3602c0fab | note | Responsibility - SE/Site Supervisor
ca25b959-7750-5807-b3f4-85828d897801 | note | Verifying Documents - Sign ITP
2ffad2fa-ac47-503e-9e4f-d56415cdf259 | date | Date Completed:
| checkpoint | 5.2 - Test Roll
0f8c6213-c8f7-5f50-acdb-fe7c27f3bd21 | note | Reference - Section 173.03, Section 204.12
2b6688be-6cb4-5fa6-911e-afcba2c2c0e9 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
669fde16-2f8c-50a7-a558-b5f677839ca0 | note | Method - Test Roll as per 173.03
d167c7fe-d8d3-5635-9619-b84bdc8e92f8 | note | Frequency - Each Lot/Layer
b155294c-1c66-5222-8fe9-dabb3fed60f4 | note | Category - HP
69030d80-ee3d-5662-bd39-8f219c3b18a8 | note | Responsibility - SE/Nominated Authority
170d8260-a7bf-55dd-9633-f143832d7428 | note | Verifying Documents - Sign ITP
da6ab2f6-b80a-5ea8-bc34-7a5fcc591cc7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Compaction Testing
58c9e270-b024-52ea-ad81-aa975c73f79d | note | Reference - Table 204.131, Section 204.14 c) Table 204.142
4f72f2aa-f52b-5a11-bc0b-b8986b398dbd | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
c985de56-e650-548a-b40e-b41c09129a8f | note | ○ Standard Compactive Effort
51529567-5c28-5008-a16e-b7c79305dae0 | note | — For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
7131e2bd-1c58-5329-b3a5-b46bfd9baeb2 | note | — For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
b4857039-e420-5d6a-a269-18b23fdc8f44 | note | ○ Compaction and Moisture content
26e62e44-2e05-5aaf-aaf3-bdfa51fc45eb | note | — Scale B: Standard Compaction 98%.
e3052ed7-2b19-5520-a00d-10ea6a78b9b5 | note | ○ Lot size - the leser of one day's production or 5,000sqm
ba52c1b0-ed1b-50b3-9744-18e510adb373 | note | ○ ATTACH: COMPACTION TEST RESULTS
23b9c822-7a01-5413-9dd2-8c5abee72d4a | note | Method - Review Document
3f0838ba-3d5d-523d-ae40-b0bcec5f7d71 | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
1c435dfc-0250-5690-9a8c-61a810da0f34 | note | Category - IP
e4eeb7e5-1cc8-50be-a642-865199d3967d | note | Responsibility - SE/Site Supervisor
17defbaf-8347-5529-a3b0-4a84d5552ae3 | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
7d87af61-6c4e-5018-8743-498981a239da | date | Date Completed:
| checkpoint | 5.4 - Preparation of final surface
e6697215-be1d-5dbb-9a4c-b2c905e492a3 | note | Reference - Section 204.15, 204.03 (g)
3ddf9f31-734e-5366-b15d-fd915c00e843 | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
ea17f7b8-4b18-5b33-9d2c-3d273ac5e732 | note | Method - Measure
c1b88c6a-1eda-5164-8073-35905e798c9a | note | Frequency - Top layer
2991a479-a11e-5342-9756-ec5b1b823e70 | note | Category - IP
d1f0ea0c-7f89-529d-96de-bdab73f811b4 | note | Responsibility -
5ff934b6-b2a6-5d4f-a2aa-6e352d8a634a | note | Verifying Documents - Signed ITP
bdddab9b-e9f5-5c3e-a9a4-be24b17d4082 | date | Date Completed:
| section | 6. Post-construction Activities
| checkpoint | 6.1 - Post Compaction Material Property Testing
ce54d093-b5f5-545f-89c7-af0443e64544 | note | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
eb568dea-68b2-5f63-875f-16384c70e53c | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
5fdddfcb-79ef-550d-9572-a8c005497460 | note | — CBR ≥ 3% and Swell ≤ 1.5%
5c17f14e-2ca7-5ab3-af90-c0b5a80dd94b | note | — Max Permeability = 5X10-9 m/s
d0afa4ee-b89a-5fbf-b8ca-ae4f907638ab | note | ○ Grading:
59464fac-9794-5968-9dde-03e8cb3cf2ad | note | — 75.0mm 100%
06a8d303-3a9c-5fed-84e8-5a6f5515b9f0 | note | — 4.75mm 40-80%
047fc7b6-2c9c-5825-a84a-8f9c348ef5c3 | note | — 0.075mm 10-40%
1a36ef48-ebd7-530d-8beb-60e2d0a3f170 | note | — Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
0ce9f84d-f276-5bc5-bc08-6ae2878b85cc | note | ○ Scale B:
4ea0bfe1-c8a7-5ba6-905a-ccf85d4e9f22 | note | — 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
1872e97c-121b-55a5-ae7a-c59a433684c8 | note | — Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
b6aae5de-b429-5a34-8d13-af3ba70d3dd4 | note | ○ Attach: Post compaction test results:
c6faaa0d-9ce8-5e49-98ec-9a6e52292281 | note | Method - Review Document
c294274f-ac8b-552b-85a7-ddf1a12be31f | note | Frequency - Refer to Section 204
e72aa4d9-386e-5da3-989f-d469ee4744d1 | note | Category - IP
32569d7a-75fc-5d11-8275-dfa0448f6a53 | note | Responsibility - SE/Site Supervisor
638b194e-6318-5a20-99c5-e8b8de269e00 | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
4c922ded-3324-5d57-9d9f-8ea2e686c36a | date | Date Completed:
| checkpoint | 6.2 - Survey Conformance
3ec4b5c0-2e0d-5b7c-9b78-30521ae2f361 | note | Reference - VicRoads 204.03f,g and h
e549d43c-283a-5fe3-8ff1-bb092a41e985 | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
36ff8bdd-e881-528b-bdf6-0b0b87fe22c1 | note | ○ Level tolerances Scale A:
9d2196b8-e898-5b74-9aa9-387fae4a9ef8 | note | — Range x = +5, -15mm
0ce8c6b9-e97f-57df-9d3c-a60b44700e87 | note | — Max S = 12 mm
28d5d968-9d42-5fce-9133-b5ca4c0454cb | note | — 80 measurements per lot
b7457a65-cff1-59ff-8f06-b8f0ad75eb50 | note | ○ Level tolerances Scale B:
329877c5-b45f-53cf-a0a9-7de5f3486436 | note | — Range x = +5, -25mm
0fabef7e-4e6e-5292-992c-756158d516f0 | note | — Max S = 15 mm
45eea8ef-e32d-597e-97c5-0fc67869b15c | note | — 40 measurements per lot
c34da6a8-510d-5d51-8e62-c0804af20c9a | note | ○ Level tolerances Scale C:
f8d1440d-7aea-5c9d-bcf0-c68806ecbb07 | note | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
db6b78fe-d4e7-5fdf-978f-6cc9dd45b78d | note | Method - Document Review
f4e84c94-43f0-5a4c-8d84-cbb06261038c | note | Frequency - Top of Type A/Verge
c4e7206e-0819-5fae-8fb3-10937e2893ea | note | Category - IP
5e438e75-5414-5f91-a040-6a3020ca87a2 | note | Responsibility - Surveyor, SE/PE/SPE
ece6792e-e242-553e-8e48-eea4dbb0fc75 | note | Verifying Documents - This ITP, Survey Conformance Report
fa14a14e-35af-5ca4-8e8e-cef09eeddbd2 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
c981c651-47fd-5432-97a4-7e95144bea6d | note | Reference - MRPA Quality Management Plan
7f98cade-1af9-5a95-8117-ad12ad71c210 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
66319302-c261-5065-9d46-79a91cc4625b | note | Method - Document Review
a0b0337b-3dc6-5e72-9043-b0c89720e483 | note | Frequency - Once, prior to closure of this lot / element / Work area
8d9f9571-6160-5314-879b-188c408561be | note | Category - HP*
325d98a1-0135-5735-8757-e344a52dc22d | note | Responsibility - SE/PE/SPE
ee7e4011-2e77-5a6f-9151-9765ebf044c1 | note | Verifying Documents - This ITP
4ae921f7-8512-5276-9143-c8bee6a35ea6 | date | Date Completed:
| checkpoint | Final Inspection
fa4aa1e9-fca3-51d8-96e8-f1e0389a3e29 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2c56bb32-5256-582b-ad88-7191ad89b9bc | textbox | Name:
85f8c840-b769-5243-9e6b-fab02b680723 | textbox | Position:
7292dc9e-1c14-5c5d-ba80-16a4f5ec2c9a | textbox | Date Completed:
| signoff | Sign ITP
3f043095-2677-4535-a3b1-a1d502f4fccd | checklist | ITP-234-RAIL-Ferris-ITP Track Removal & Construction Rev 1 | itp | ITP-234-RAIL-Ferris-ITP Track Removal & Construction | c35dff7a-70b1-4eb0-a5d6-8286a8c6a7d6
7b17ff0c-fcbe-4487-8d16-065cb8ff53a1 | section | 1. Referenced Documentation
6fcd8fd2-a9bd-40b2-8a56-799325d64041 | checkpoint-no-value | Referenced Documentation
17a5f63a-0d59-5804-aa09-53ba6f561fd8 | note | Document Title: ITP-234-Rail-Track Removal & Construction
a7fdfb62-26af-5e39-84a6-cbcaea9a8d1b | note | ITP Description: Track Removal & Construction
ca18d297-d4e6-5510-9247-cc6a70bc0891 | note | Discipline (e.g. CIV/STR/RAIL): 234-Rail
3a1ea297-2cae-5ee4-aaa8-01f3024f17c5 | note | Revision Number: 1
375cdc3e-4ba1-53f5-8f6e-1b4f08da2f76 | note | Revision Date: 22/10/2024
c644fe27-af92-5007-8946-991651747482 | note | ITP created by: Jake Argentaro
a53f5cb9-3c06-5b42-8769-245d5a0eec78 | note | 1.01 - Non Dependent
6fea73b4-c1f3-5f55-9cf9-f3075c150fe8 | note | Reference - Ferris Road Track & Civil IFC Drawing Set MRP-DPK-103-00-CPW-0060, MRP-DPK-103-00-CPW-0063
9f3355d3-8447-5ae6-9a7d-b8145a8249ff | note | 1.02 - Non Dependent
b7c3366c-eeb3-5f12-86bc-d6c0fc84f1c8 | note | Reference - NIST-2654 Ballast
a3d68af5-16b8-5b95-95a5-a989f4ee2d50 | note | 1.03 - Non Dependent
2445e212-a9a3-57da-852b-54543550d884 | note | Reference - NIST-2651 Sleepers and Fastenings
427169e7-c1e4-539e-8182-ef29dc179e9e | note | 1.04 - Non Dependent
69610329-fa2f-5c41-a562-ac12d53be84f | note | Reference - NIST-2650 Rail Use Laying and Adjustment
e8d8d3e7-5fb5-52c6-a9fb-c323ae4d8f15 | note | 1.05 - Non Dependent
6aa0944c-c036-5e7b-b938-c536ef541fb9 | note | Reference - NIST-2630 Track Construction
ad348c0d-4c7a-52a2-81bb-13e01803fc48 | note | 1.06 - Non Dependent
4e055cbf-ecd8-5a66-bd0a-be3fef68cd62 | note | Reference - NIST-2706 Track Geometry
8c0aa477-041b-5a39-9a21-fdb8d7526e15 | note | 1.07 - Non Dependent
2ee2fc13-c46e-5a44-8c81-3513fd02b577 | note | Reference - NIST-2659 Earthworks and Drainage
b525ffb4-8ae5-5f8f-b633-e5774d3361e2 | note | 1.08 - Non Dependent
03104d11-c390-5cc2-877c-ac1720e7e547 | note | Reference - NIST-2618 Track Design
65b46f22-eb32-5bd2-88ff-13d2551465bb | note | 1.09 - Non Dependent
52fcba43-da58-543c-9d82-4c7d9ac3c7f3 | note | Reference - NIFO-2650.5 Aluminothermic Weld Record
066fbf2b-e495-5270-86f1-dcd558935db3 | note | 1.10 - Non Dependent
661006d2-f9f9-55c9-b557-1b08dfa441ce | note | Reference - NIFO-2690.3 Certificate of Track for Operation
22e39aec-6444-4f27-a0c8-fbdd5aa5f78e | section | 2. Preliminaries
b20f0266-1318-4007-b3d9-dccdd3cae199 | checkpoint | 2.01 - Obtain and submit Material Certificate of Compliance for Track Materials;
f76fd7c2-70a2-5a6c-9d9d-c6131c704879 | note | – Track Rail
bb70ade2-52e9-5933-bc29-40a0b826717e | note | – Track Sleepers
b8b0564d-f6e6-5bf7-a810-af17333bf335 | note | – Track Jewellery
6de01d94-c631-5759-bb57-67802255d8bb | note | – Geofabric
79a5dace-635f-5f2d-ae56-4a0dcba6c380 | note | – Ballast Matting
c95215e9-778a-551e-b928-619cd043f7a8 | note | – Ballast 60mm Aggregate
aeb0e23b-7f07-5953-898b-d27be0bab7a1 | note | – Welding Kits
691d216f-142a-5194-a799-55dea45901af | note | – Welding Crucibles
e203f048-70db-5a7d-99b9-25f530c73191 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap, Bill of Materials
fe6c4161-6809-5e20-b74f-6267c0007aa8 | note | Acceptance Criteria - Units to be free from damage, total and types of units for full set validated No signs of discoloration
138e14a4-f97e-56c6-8c6d-a0e65647aa22 | note | ○ Attach: Manufactuer Cetificates of Compliance
5d24978a-f88b-51f6-a3cd-d8731ea046cb | note | Method - Review Document
0b151a46-5d48-5440-9ba6-470ce500de53 | note | Frequency - Once
f5a081ec-b7fc-51b7-a518-02f9b0c2e38b | note | Category - HP
f0b81ecf-414e-551f-97fd-275e1fcca7bb | note | Responsibility - Site/Project Engineer
ba02584d-b86d-5f1c-8c40-dde77e8376f8 | note | Verifying Documents - ConQA Hold Point Release
6fc908e1-f10c-5781-8026-dd7c26640451 | date | Date Completed:
28ec26de-3bee-4081-be12-1cabcf167ee2 | signoff | AUTHORITY HOLDPOINT
c5e61da2-de40-4f8f-82ed-4fce2eca6b40 | checkpoint | 2.02 - Submit Welding Procedure/welding qualification welders Record
fc76bf5a-9eda-58bb-8635-037337f30daa | note | Reference - NIST-2650 Rail, AS 1085.20 Welding Rail Steels
c15457c6-934c-58da-8407-bd59c71a7c14 | note | Acceptance Criteria - Qualified personnel & welding accordance with manufacturers specs.
c1dd9cbc-3b3b-5e41-b8f7-d9facdb6b47f | note | Method - Review Document
416502d8-c821-5225-ac5f-de7e53964658 | note | Frequency - Once
39700b9d-3fc0-58b4-9a60-224476399c92 | note | Category - HP
67dc9916-84b9-505c-8df8-ee30f23ba919 | note | Responsibility - Site/Project Engineer
ffc62353-1009-52e9-a58b-af23460dd0fc | note | Verifying Documents - ConQA Hold Point Release
481a98b4-55cb-5840-a879-8e674d9aff15 | date | Date Completed:
a897e3d4-2c21-490b-9c4e-e7a3db125c2e | signoff | AUTHORITY HOLDPOINT
cf6573c8-aee3-4105-9f0b-5020c119bb66 | checkpoint | 2.03 - Inspect supplied items upon delivery
438df81f-3489-5270-9777-01050c1d6f7f | note | Reference - Bill of Materials
0d44f53d-e079-5976-80ab-8c2693effbc4 | note | Acceptance Criteria - No damage or debris on components
2f9dd9bf-162d-5d33-862d-d91d484ec98e | note | ○ Validate total number and type of components matches drawing
f9eaa26e-af71-59b5-a6df-9e7408ef9835 | note | ○ Attach: Photos on site;
05f2af86-c359-576c-a621-6c8247307eec | note | – Track Rail
ba40a1aa-0d67-5e35-9652-fc27f8749d4e | note | – Track Sleepers
a3322dc7-517c-59c2-a922-2ec63bf8c31e | note | – Track Jewellery
fa070f24-d849-59a0-86f0-dfa56ddc928d | note | – Geofabric
a17225ff-9058-56f0-a7cd-0925d99d2de4 | note | – Ballast 53mm Aggregate
326aa831-cdf4-57a9-946a-11283b73a2a1 | note | – Welding Kits
48b089b6-a1c7-5d1e-83c9-3048cde4ae0e | note | – Welding Crucibles
513446d4-7c4e-5f13-a8b2-fedb923500c7 | note | Method - Visual, Measure
5253ea5f-79d0-52ac-b05d-a9ea3d69a350 | note | Frequency - Per delivery
55c1c16c-8c6a-5185-837e-822e052d2d0a | note | Category - IP
30a4624a-970b-5707-85f5-c3362f3360ee | note | Responsibility - Site/Project Engineer
a2b43818-c730-52ff-8fb0-df8767335b44 | note | Verifying Documents - Material Inspection Report
dc2ef0f0-dfd1-5f1e-8bac-7f453b2ef811 | date | Date Completed:
341356f3-cfb1-4fe6-af52-79a10929b104 | checkpoint | 2.04 - Confirm extent of track removal required for civil works
5a136d20-32c4-501e-ac22-2fc0d341be56 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap
862ee407-c35a-5b74-b2ec-62f0fd5852e9 | note | Acceptance Criteria - Extent of civil works and subsequent track removal to be confirmed in conjunction with MRPA civil team, limits of removal to be marked up on site
321ecc5b-dcbe-580d-8974-d69bff4de800 | note | ○ Pre-removal survey of existing track alignment
c9c0ca51-312a-5da4-a776-0e9d45ef765a | note | Method - Visual, Measure
d06c9cdd-52a7-58ab-8153-8a1a7b228b03 | note | Frequency - Once
c70a2767-1899-5d31-aa65-511a3b88ee25 | note | Category - IP
27b6157d-01dd-5696-b6e6-ab9f3590c9d9 | note | Responsibility - Site/Project Engineer
6ff46dcd-a013-58a3-bc77-efd27f14e09a | note | Verifying Documents - This ITP
1734c7d4-1049-5021-983c-eabf1015ae27 | date | Date Completed:
bc8c39cb-1511-447e-9b6c-cce5018a90d3 | section | 3. Construction / Installation Activities
a1dc810b-25a2-4e65-a724-936e80ea985f | checkpoint | 3.01 - Deconstruct and remove track componends, including rail, sleepers, jewellery & ballast. Stockpile materials as required for reuse during construction
aa1e7394-95f4-5028-a57a-fa469ab2ff30 | note | Reference - IFC Drawing(s), Track Constrction Site Mudmap
af0a2d64-7498-5170-9609-ebe57ff9e97c | note | Acceptance Criteria - Track structure to be removed to the designated limits as identified.
ee1df8c5-56ca-501a-9c4a-1593c071475e | note | ○ Visual confirmation of removal on site
0c3cbe89-a3f0-544c-92de-854b8ea5968d | note | Method - Visual, Measure
056e4c0c-ccc5-5d92-9866-e4de71e512fc | note | Frequency - Once
272a9fb6-b482-575d-992c-b3e39b57b8e3 | note | Category - IP
c1b0f700-a4c9-543f-98ac-3a5e43edda1a | note | Responsibility - Track Supervisor, Site/Project Engineer
e225b1de-d734-5553-821c-aece59bcada6 | note | Verifying Documents - This ITP
b9715218-9ef3-5a72-af2c-e587288c88f3 | date | Date Completed:
8b0a8711-a27c-46b4-95c2-e1094a72a4d3 | checkpoint | 3.02 - Earthworks completed and site handed over from Civil Contractor
1e505d9b-c954-5cba-916d-41e94068d6dc | note | Reference - NIST-2659 Earthworks and Drainage
fdf0ca0a-9f03-5279-aea7-b7fb63d804e6 | note | Acceptance Criteria - Confirmation of completion of underlying ITP(s)
f18db6f7-dffa-58c6-b966-6181967d7ae8 | textbox | Underlying ITP reference:
49e4b70b-232f-5df6-ac22-b0d64acaabd4 | note | ○ Applicable: Stage 2 - Track Construction
4aad1c13-f140-5cc1-a3dc-da6f66cde184 | note | Method - Visual, Measure
0381f801-11cb-56f9-8f0f-ec526f3afce4 | note | Frequency - Once
a024b44d-05da-55a4-9980-eaa4e11ece96 | note | Category - IP
4280d3c3-b68a-5c21-9357-d5c6c056e00d | note | Responsibility - Track Supervisor, Site/Project Engineer
c90d871e-b7d8-5cf7-acba-f27e13eda503 | note | Verifying Documents - This ITP
e984618d-c786-58bb-87b9-3bce4e67a318 | date | Date Completed:
a97743a3-49e1-40c2-aae8-dbe384b4abb4 | checkpoint | 3.03 - Installlation of Bottom Ballast
88064ab7-1384-5187-8c5d-c0d1b5dcafd7 | note | Reference - NIST-2654 Ballast
71eb6e5e-a5e6-5372-a4ca-56e9f68d2ba1 | note | Acceptance Criteria - Overal Minimum 300mm bottom ballast depth
9ae863c9-2a53-5e36-899a-7ae8c26a8af0 | note | ○ Ballast to be placed in 150mm max layers. Layers to be compacted with 10 tonne smooth drum vibrating roller with minimum 3 passes, in areas where wheeled roller cannot access, ballast to be compated using a vibratory compaction plate
3d361beb-a91f-5bd4-8c7c-5f9c46bff007 | note | ○ Bottom Ballast to be left 20mm below final design level
62c08b44-0be6-5683-9233-14de0571ac63 | note | ○ Tolerance: Under sleeper -0mm/+25mm.
bcb1a0b7-8ed0-5d4b-86dc-fe125e453d75 | note | ○ Attach Site Photo: Installed Bottom Ballast Layer
d6dabb63-69eb-57d4-a291-6c0cdfbf108e | note | ○ Applicable: Stage 2 - Track Construction
20d132c0-1316-590c-af8b-551b2ed2175d | note | Method - Visual, Measure
a7629fd9-7566-524b-82c5-bdf5f15d55e1 | note | Frequency - Once
48c94753-0bdb-5bd6-abbc-ef374de50f2d | note | Category - IP
79294b72-0e8d-5132-8d91-31d64bf161e8 | note | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
435a436b-4f05-5eb6-a274-fe3c8ba4e23a | note | Verifying Documents - This ITP
28320485-ecfe-58e4-b12f-cca6c449b02f | date | Date Completed:
df51f0d2-7a64-4dba-9feb-1090bf7d5660 | checkpoint | 3.04 - Laying of Sleepers
d70cc812-c6d2-5536-ab61-28df6788c1a9 | note | Reference - NIST-2651 Sleepers and Fastenings
7a2ffc5a-93f8-537a-a6ff-2a15b3d188af | note | Acceptance Criteria - Sleepers square at nominal 685mm +/-25mm for open track
51266f40-07d8-57e1-9023-dc2d06ae5aa0 | note | ○ Attach Site Photo:
820b37c2-c438-5691-b9f3-9b05cf0eca35 | note | – Laid Sleepers
0142b1b8-bc95-5173-9e25-633ce1011921 | note | – Sleeper Spacing Measurement
467e075d-8482-5853-8a1a-4422a41b8664 | note | Method - Visual, Measure
7b278671-9630-5730-a934-a4f0283d747e | note | Frequency - Once
33d4cc4f-044c-508d-8e3b-6482ddb6f29b | note | Category - IP
61fd7add-4418-5da2-b42f-d80dc10c9225 | note | Responsibility - Track Supervisor, Site/Project Engineer
7faaf70c-d80a-5183-af00-7dda1e0bb183 | note | Verifying Documents - This ITP
5a728278-59f1-593a-bbef-c8bfa203d944 | date | Date Completed:
82336199-11a6-4dd8-afee-0d902a796ebb | checkpoint | 3.05 - Rail & Fastening Installation
9b5806cf-1471-5b80-b134-a990c5607ade | note | Reference - NIST-2650 Rail, NIST-2651 Sleepers and Fastenings
dacb3d6b-d6bd-5b44-bc18-669239ca9a2b | note | Acceptance Criteria - All rail sitting within Sleeper footing with correct sleeper insulators, rail ends positioned the midpoint of sleeper bays +/-50mm, no rail ends to be located within 3m of existing track welds, rail fastenings installed
4a67dcd9-f69d-5336-bee1-dcd7ff2eae09 | note | ○ New Rail lengths installed to be as per approved Ferris Road Rail Weld Plan
ccdd4781-d069-5482-9a80-d898b5b95ef4 | note | ○ Gauge of track to be checked upon installation of fastenings
cdec2ec1-ffc2-5cc8-bfe7-112a3f2d80f8 | note | ○ Gauge +4mm/-3mm
52d5cbdf-d03a-58be-8d8f-a8ce3388c83e | note | ○ Gauge Variation over 2m 4mm
006dce59-f2c8-5e3e-91b9-c189eee52e9b | note | ○ Attach Site Photo:
a7bbebb1-048e-54df-820c-4beaa7a26a3c | note | – Laid rail
b3a1f40f-8f1e-54d1-ac62-16a4c4adcc06 | note | – Rail joint to exisiting weld measurement
7a7e4ad7-3ce7-5609-bd42-f68f7b0e3738 | note | – Rail joint between sleeper bay measurements
df3822ce-cd6d-50ef-b424-19419662efb1 | note | Method - Visual, Measure
a804c1f2-2242-5c84-a527-34168d1e8701 | note | Frequency - Once
71f02aa5-0996-5d40-bbe9-c0a373a02072 | note | Category - IP
f57ca4c9-1bbc-55af-8eaa-8f5704aa4b4e | note | Responsibility - Track Supervisor, Site/Project Engineer
85e81fb9-5fd6-591a-83af-59ea882f6c6f | note | Verifying Documents - This ITP
afa60355-74e1-562b-b94c-2a23f91f9db5 | date | Date Completed:
960c6b39-324b-4a0f-ad91-7e5f35dc9ea9 | checkpoint | 3.06 - Track Tamping
d5f51db8-5722-5d74-af6c-217aec9c6b0e | note | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
1080e4e0-21e7-550a-bf2e-f68671ee4cf3 | note | Acceptance Criteria - Tamping Ensures Track Geometry Tolerances are not breached (dimentions are in mm);
90aef726-fe61-55ec-a8ca-e2b71ef3f0c7 | note | ○ Line (10m Chord) +/-5mm
954b0eb1-3b51-5dcb-9827-bf755ffc6a7d | note | ○ Twist (3.5m Chord) +/-5mm
983348e2-94ed-591f-a9d2-489afbc4dfbe | note | ○ Twist 10m (Chord) +/-10mm
f86d39c3-fbad-56c9-ba02-2f5da0bb0099 | note | ○ Cant +/-5mm
9ab33c75-1be7-5843-9af0-9e6df6a7b6b8 | note | ○ Top (10m Chord) +/-5mm
daa9d0b3-dbb1-55e3-b4f5-bc2e0131301c | note | ○ Alignment +/-20mm
a59f432d-b32a-50da-b276-8ad1271e3ed3 | note | ○ Survey measurment of RL of top of rail head
4628cfac-afc2-5bd1-b71b-1db06b2a6a4b | note | ○ A minimum horizontal clearance of 3.0m from track centreline to structure.
e32d3d18-1a22-5ded-80ce-448d000c578e | note | ○ Attach;
fc92d169-1b66-5c3e-b23f-76bb72866757 | note | – Tamping Geometry Recording
44de8d2b-a593-5818-9918-02551e790d1b | note | – Survey RL measuring sheet
0e8191de-ece5-5b5f-8bc7-537edd581b4b | note | ○ Attach Site Photos:
e50e98a8-dfe7-5fce-8830-fbe6a8aa62e4 | note | – Tamping Activity
5bd58f70-e0b9-5244-8a78-c2c355a53723 | note | – Structual Offset Measurement
26020b3b-a123-5799-ab44-a30c54cb0c7d | note | Method - Visual, Measure
f6a9788f-85ff-52d0-8efa-8aa7ca2bea70 | note | Frequency - Once
1f67de70-2a5f-523c-8b9e-53f3b24121a4 | note | Category - HP
c0a3fe6f-8592-5b3a-b64a-8855c7c59b03 | note | Responsibility - Track Surveyor, Track Supervisor, Site/Project Engineer
6786ca34-56e1-56e7-b20c-0ff897952eb6 | note | Verifying Documents - This ITP
575b3ac9-e95d-57aa-91d1-f723860ff495 | date | Date Completed:
9fd3c966-a475-4e72-a836-4bfc6923878e | signoff | AUTHORITY HOLDPOINT
054f0540-52d7-4566-bd87-7f1e7aef687a | checkpoint | 3.07 - Regualting and Ballast Profile
1e638d54-4158-5991-b07b-6f4be2a95c04 | note | Reference - NIST-2630 Track Construction, NIST-2706 Track Geometry
1e441607-88a4-5ce3-8fb5-3b9b46c3a011 | note | Acceptance Criteria - Ballast shoulder of 400mm width from outer edge of sleeper and with 1:1.5 angle of repose thereafter
ca578f6f-f3d6-559d-b7ad-bc77638aa708 | note | ○ No Ballast to be on top surface of sleepers or aorund rail Fastenings
f8b31e69-5cac-578e-b520-e96f1a02c06d | note | ○ Attach Site Photos:
d5d9b1dd-2006-50a0-a516-bd4176a95f4a | note | – Ballast Shoulder Measurement
6a18e226-e581-58ae-a091-8c268235b5f9 | note | – Rubber Panels free of ballast materials
2e1a2b9a-19f6-5864-9944-465fbabcba0b | note | Method - Visual, Measure
ffd0b14f-3caa-5d27-b5c4-efd290b0e2ed | note | Frequency - Once
08d801ab-9d23-5138-aa5e-48ead472bcd9 | note | Category - IP
1be67c62-c38e-565e-b413-52900874c58f | note | Responsibility - Track Supervisor, Site/Project Engineer
f62e5888-2381-5c4c-a161-135d4166a90a | note | Verifying Documents - This ITP
2a7f9b0a-7c61-55cd-8d17-d154f959b389 | date | Date Completed:
2c047fd0-e5fd-47e6-b931-9877c9c151d7 | checkpoint | 3.08 - Aluminothermic Welding
12a37549-94f8-5312-8458-6704cfbf99a2 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
f10d65d9-5f9d-5887-a1bf-b8065cccf5b7 | note | Acceptance Criteria - Welds to be lined and finished to alignment standard
4f80ece0-cf3c-586c-900c-4bb2f1c66515 | note | ○ Tolerance:
24d8af1a-12fb-573a-8d1c-9d203ce844f3 | note | – Gauge Face +1.0/-0.5mm
203961a1-675c-5adc-9a36-cb522cdc3bbd | note | – Running Face +0.6/-0.0mm
d988704c-f798-5cb9-9b6e-578bbd466966 | note | ○ Verify Aluminothermic welding carried out in accordance with AS1085.20
9a5b61ac-703b-537b-9429-05cd3a1ea043 | note | ○ Aluminothermic Weld Return Form to be completed
8d0e6513-76ce-5550-b1ec-45bc20179b3e | note | ○ Attach
88d26dac-7ef6-593f-b198-80372a313dc3 | note | – Aluminothermic Weld Return Form
76446464-f5c4-5725-9cdb-51e00f29397c | note | ○ Attach Site Photos:
0ebee534-75de-5588-a32b-41f8033389f9 | note | – Welding Aligning
90722b74-d814-5881-b213-d54724c441e9 | note | – Welding Process
7622586d-f94c-5d02-90d7-8b06ff01f038 | note | Method - Visual, Measure
a3872ece-23d6-5b3e-adf8-d5eed017523d | note | Frequency - Each Weld
7d45389f-e008-59c7-b494-f80c577d3086 | note | Category - IP
d3f3363f-7f85-5ab7-9e80-1509b10d8ded | note | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
eb8d35df-e477-5b4b-b0f9-54b52fc6491b | note | Verifying Documents - This ITP
a24dac46-6b5d-5c2c-97be-008a0d108196 | date | Date Completed:
a3c7f8df-0c73-4375-a746-ee0cce736663 | checkpoint | 3.09 - Track Stressing
85414535-3ae6-504a-acaa-6f6a6b0c2fa9 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
de687921-2a59-587d-a738-714672592d66 | note | Acceptance Criteria - Stressing Rail in line with V/Line Rail Welding Process
5014354b-56a1-577c-abad-e2f6eed68d5b | note | ○ Ensure Stressing only performed between rail temperatures; >10 and <38 degrees
c0b7ea59-d457-5c82-87b9-dc979b9e76cb | note | ○ Complete track stressing in 330m module or otherwise as noted on approved track stressing plan
c877c5cd-8f21-5942-b651-d6a17a6fc463 | note | ○ Reference Marks recorded pre and post tensing of rail
16b5b68f-6a7a-5431-a19e-f83509c211dd | note | ○ Aluminothermic Weld Return Form to be completed
47229535-9d0c-5a1d-957b-10d23f661ef4 | note | ○ Attach
d2ad4983-5d92-5538-9f2d-bbba3cf205ac | note | – Aluminothermic Weld Return Form
acaee5ae-dcfe-5ff9-9ef2-804946994999 | note | ○ Attach Site Photos:
6e4869aa-5b32-5cd4-99b5-d34d27ac4fd1 | note | – Stressing Activity
e8dfeebf-80ff-5662-9f7d-216a6b5aee57 | note | – Under Rail Roller Spacing
acf4ec52-cd96-5d7b-9c70-46b1c37ae2fc | note | – Before/After Reference Mark Measurments
b171b0b4-3a7f-509d-929b-0d19568621c8 | note | Method - Visual, Measure
4da3012c-17b8-58ea-a006-761f0f4c8f33 | note | Frequency - Each Restress module
b1292ba7-a74b-5802-9552-49768e1c9fa3 | note | Category - IP
476caa99-e907-5f30-9e56-6a671ba998db | note | Responsibility - Track Welder, Track Supervisor, Site/Project Engineer
4c081846-2177-5e08-9ee1-cf12cb5d33bd | note | Verifying Documents - This ITP
9e4dd50f-4f7a-5035-9313-843ba3536e16 | date | Date Completed:
e51008e8-0058-4035-a9a0-47f7463cbeae | checkpoint | 3.10 - Weld Ultrasonic Testing
1b5f7b64-e514-5f19-90e4-726b706bc5a7 | note | Reference - NIST-2650 Rail, NIFO-2650.5 Aluminothermic Weld Record
218b2bbb-411e-5cd1-987e-e80447c97f0e | note | Acceptance Criteria - Ultrasonic testing to be carried out in accordance with NIST-2650 Rail
83d3ed2b-94e9-5370-8942-d369e2749508 | note | ○ The cross section of the area of the head and web shall be completely scanned;
99d7a55d-f7cb-5571-befc-22e31d27b750 | note | – The foot area shall be scanned in accordance with AS 1085.11 Permanent Way Material – Head-hardened Rail, Figure C2.
81622894-1e55-577a-82f3-3f740f2898d4 | note | – Welds shall be scanned to both directions.
71168a01-044a-5473-9a4c-09ff4a314e8a | note | ○ No classified internal defects found
e8c85939-c7ba-59f4-96f3-43687342f061 | note | ○ Final weld geometry to be assessed
117214ea-a800-5847-8808-eedb4c3bff00 | note | ○ Tolerance:
9d9db7e6-cb74-5874-b586-62e033a20134 | note | – Gauge Face +1.0/-0.5mm
bee5cb72-0672-5c74-a9c3-e3b12fca1214 | note | – Running Face +0.6/-0.0mm
82bd6481-d019-5550-8cab-168d4ca445fc | note | ○ Aluminothermic Weld Return Form to be completed
9882acba-329a-5a4e-86ff-e9c192b553f6 | note | ○ Attach
9357bd68-6832-5724-ac21-0045b43ad7c2 | note | – Aluminothermic Weld Return Form
5d4b2484-bb1c-574c-975d-55cb3398548f | note | – Aluminothermic Weld Test Report
58ac1b7f-a27e-51cc-b16b-f620c5bbf7f6 | note | ○ Attach Site Photos:
b0db5d53-0dcb-5887-aa26-5c135439d975 | note | – Welding Aligning
f0d1ebf5-92d5-557c-bb01-6a919da288a2 | note | – Welding Process
33a6a8a7-a6b3-5908-a618-1130a0be61cc | note | Method - Visual, Measure, Test
96a6eb38-560c-5266-ae19-e5080bc5fe6c | note | Frequency - Each Weld
8d3a7535-57a5-5536-97f7-82e616ced6d2 | note | Category - HP
7dfaa03b-f6ac-572f-a3e3-61a7964a5e62 | note | Responsibility - Weld Tester, Track Supervisor, Site/Project Engineer
909ece79-3692-5299-b1e4-0eabb706aa1a | note | Verifying Documents - This ITP
841b6029-df42-5afd-a6d3-f64babc7bab5 | date | Date Completed:
7086fc54-8854-4629-a580-9cf37a11fb2f | signoff | AUTHORITY HOLDPOINT
c86eb3f8-b191-495d-aecb-de726df3a5f2 | checkpoint | 3.11 - Installation of Guard Rail & Guard Rail Nose
94377d48-4385-522a-ac18-580ebf20064c | note | Reference - IFC Drawing(s), NIST-2650 Rail
ec88853a-0e06-550a-a804-b3a199929fef | note | Acceptance Criteria - Install guard rail and guard rail nose as per IFC design
9f5f091b-ab7b-5c9f-8371-1ecce92aeaba | note | ○ Guardrail to be installed with alternating fastening pattern
41871324-d1e6-52db-aee1-9bdf179b53ee | note | ○ Guardrail to be isntalled at lengths of either 13.7m, 19.9m or 27.5m, joints to be gap adjusted and plate & bolted upon completion
054bff4f-df9d-5df9-939b-3c7280e8f70a | note | ○ Attach Site Photo:
30a92980-53d6-5ab9-8a0e-4359d0942915 | note | – Guard rail installed
e1acf82d-e4dc-54a5-b9a2-b6cf373af3cf | note | – Guard rail nose installed
1b0ae0a1-e5fe-5bc1-aa7d-fa5fc17dd6cf | note | Method - Visual, Measure, Test
98ddc68e-9338-5f08-9495-c2aeab0efe85 | note | Frequency - Once
7f28c8a2-feea-555b-8980-57abf869906f | note | Category - HP
2438dded-965f-5405-81c6-526e8ae8a4ce | note | Responsibility - Track Supervisor, Site/Project Engineer
26517010-1563-522b-a047-2e5c08677b07 | note | Verifying Documents - This ITP
22b5e759-5ef2-54f4-af5b-3b6c990ba7ca | date | Date Completed:
19a4b9d1-af89-459f-8cfe-cf37a2bf2401 | signoff | AUTHORITY HOLDPOINT
e91a6a53-011c-4dc9-b4ef-f1a2156c3284 | section | 4. Post-construction / Post-installation Activities
408266eb-6d4b-4338-b850-161b4dc44c57 | checkpoint | 4.01 - As-built Survey
0607e5f9-5439-5bdf-8c32-5a615e599ba6 | note | Reference - IFC Drawing(s)
e5b6a061-707d-59aa-a075-fd0ba88d728e | note | Acceptance Criteria - Survey activities undertaken to validate correct construction
d122f316-0c04-5779-a314-c735c4b9bc16 | note | ○ Attach:
866df5a5-678a-5d74-bf06-911c263d0e65 | note | – Survey Report
65f09069-409c-5923-9e37-c5b5ec8620c7 | note | – Engineering Asset From
f7ad8339-3044-5f4b-b308-d6062f7e0645 | note | Method - Survey, Document Review
ef84ed39-2559-5cfe-91a5-36db8f502196 | note | Frequency - Once
62e10818-0082-5e18-948f-3f7fd8db10ff | note | Category - IP
aaaebeca-eaee-52d6-be13-a56ed7369fa4 | note | Responsibility - Track Surveyor, Site/Project Engineer
32b4e050-12cc-5b5d-b34d-2ed2a564708b | note | Verifying Documents - This ITP
d0968761-b563-5aed-8229-4f78632efd06 | date | Date Completed:
db89547f-d88e-416a-8036-2845832b4891 | checkpoint | 4.02 - Track Certification
88970b56-d626-5700-aee2-176aeae6dc73 | note | Reference - NIFO-2690.3 Certificate of Track for Operation
bad01eeb-e301-582f-a539-7e52b1e5c39c | note | Acceptance Criteria - Attach:
de4f61f3-a362-52f7-9c2f-1cd3fc140f60 | note | – Track Geometry Conformance Certificate
6d336b26-40cd-56ad-a3ad-299450be7e15 | note | – Track System and Component
2089ac30-b456-5047-893d-d30e230830d5 | note | ○ Attach Site Photos:
25443785-fef4-5470-afe3-8c445fcc98b0 | note | – Before/After Photo of worksite
925de8ed-2383-5f2d-87bb-4da09e89da71 | note | Method - Visual, Measure, Doument Reivew
c13ab590-7040-5fdd-8f12-8dd9a9b76225 | note | Frequency - Once when all occupation works complete
00b721eb-8151-51ed-880d-8a32545f483e | note | Category - HP
37547553-0e11-584b-95d5-2de19d863278 | note | Responsibility - Track Certifier, Site/Project Engineer
2f69da8b-bd0a-57c3-8cfe-2aa50c38485a | note | Verifying Documents - ConQA Hold Point Release
ec0be400-622b-5969-88a6-d6b008c3af54 | date | Date Completed:
2991c8be-cc1c-4ef3-b210-cbf6cc48698a | signoff | AUTHORITY HOLDPOINT
5bf28eaa-f677-4d6c-baeb-071bf1bc3fae | checkpoint | Final Inspection
fd7a6cce-89b4-5f6f-abea-5a8c85485674 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
41327a68-4683-56b6-af54-f33e1e85c39a | textbox | Name:
29706c66-5254-593e-99a3-8129a0b47f53 | textbox | Position:
97eb8f9b-6bb8-550b-800c-b02f33e2b735 | textbox | Date Completed:
aa2985ce-8f4f-432c-a4fe-dc592f1e4065 | signoff | Sign ITP
0c40e999-067b-459a-840c-186dfe916e7a | checklist | ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra Rev 0 | itp | ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra | ec7d87cf-fc6a-4d2c-8171-3a4d1c40ddae
9ec67a72-98bb-479a-b7db-1d189552be46 | section | 1. Referenced Documentation
685216f6-8935-470f-af55-763cb210804e | checkpoint-no-value | Referenced Documentation
7090e209-2d6a-5d97-a4bb-a4948e584f21 | note | Document Title: ITP-240-CIV-Ferris-Under track crossing - Ausnet Gas and Telstra
abd81861-4567-51f2-938a-27c21c7822e0 | note | ITP Description: Under track crossing - Ausnet Gas and Telstra
cce5b5fb-2e76-5bd5-aac2-994ca30f8046 | note | Discipline (e.g. CIV/STR/RAIL): 240-CIV
0b82eaa2-e8f2-5a2d-a505-cd776dff16df | note | Revision Number: 0
5f663a16-4504-51fd-bc7f-c32f927bcd19 | note | Revision Date: 4/02/2025
ebc0a0c0-d55a-57ea-91f8-ad9d921d54ae | note | ITP created by: Joanthan Kogan
f5ef5671-5ecb-5d45-84c0-e63eac8f147e | note | ITP approved for use by: Pradeep Talasila
72842eb8-8113-5b4d-b106-156228f23ca8 | note | 1.01 - Non Dependent
5fafe724-a9da-5df1-af64-5720b87ba110 | note | Reference - AS 4799-2000 Installation of underground utility services ad pipelines within railway boundaries
ae454a50-fcc1-545f-adc8-a0a2a0ba0f19 | note | 1.02 - Non Dependent
2f6357e5-cd6a-516b-ac73-101fa59a6026 | note | Reference - D/17/62901 Design Requirements & Guidelines - Civil Works on, under or over VicTrack Land
7491bd6a-9a7b-5889-8c74-f25b2787df1f | note | 1.03 - Non Dependent
33ec1f6e-f06d-52ec-9eb8-5f8b2072bc5f | note | Reference - NIST 012.2 - Specification for Signalling Supply, Construction and Installation (V/Line)
e1663b8a-a383-5a00-8d4f-cbfbc56bb1ef | note | 1.04 - Non Dependent
38bbad47-69bc-5d7e-ad48-c53dcfe6a8df | note | Reference - AS 4142 Fibre Ropes, installed and anchored in the pit
ff4a6867-42ae-5482-9d60-25a60ca0c768 | note | 1.05 - Non Dependent
ff92ea96-36c4-5b23-8bc2-9716bb38d6fa | note | Reference - NIST 012.2.1 - Standard for Construction of Cable Route and Signalling Civil Works (V/Line)
c0dc24a9-63a2-520b-8823-6e7c38ce259a | note | 1.06 - Non Dependent
5f4e6aea-57e1-515d-b6f3-22790bd8c437 | note | Reference - NIST-2706 - Inspection and Assessment Track Geometry (V/Line)
71bdc860-d7b1-596c-9bab-c75f5f150303 | note | 1.07 - Non Dependent
3b635cf1-de13-5a92-acd2-0e49cb70d46d | note | Reference - VRIOGS 012.2.1. Settlement Monitoring during construction
bde3595a-326d-509c-9d16-66ec48ea80f3 | note | 1.08 - Non Dependent
17698a44-9b0d-5083-a0d9-c2903a00cd4c | note | Reference - VICTRACK STANDARD TS-SP-013 installation of the encasing pipe
1603f5f1-79e9-4c4b-955b-afcfe2db19e9 | section | 2. Preliminaries
3bc0d022-0ecf-42df-8722-36ddc52a32b3 | checkpoint | 2.01 - Materials - Gas Jacking Pipe
c48e205c-414f-50fc-a0b9-44a2cc95f231 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
ed4db007-7afd-5fa4-a0cd-6b18a95f4401 | note | Acceptance Criteria - Confirm that the GRP pipes delivered to site meet the Pipe Specifications:
71621b9d-9a2a-5f18-867a-8a0f44262a23 | note | — Internal Dia: 389mm
bdacd56d-c71c-58ea-bf63-70ceff297510 | note | — Outside Dia: 427mm
5f3d9e76-d6f0-51e7-aa7a-f61f07c2bab3 | note | — Material: GRP Pipe
64e83414-9ecb-52c3-8d06-0ef5611da798 | note | ○ Specification & Grade: DM427 SN100,000 N/m²­­
243726c7-c58d-54e7-ba0e-083d97ce0e3e | note | — Wall Thickness: 19mm
74657397-3e36-5186-b949-544ee925caf1 | note | — Maximum Working Pressure: N/A
c6ff4191-265b-53b1-af61-48ab28cd9529 | note | — Joint Type: Stainless Steel Collar with EPDM Seal
58cd5a5a-7130-5443-a310-2e2c8d08b36f | note | — Pipe Coating: N/A
7489028b-ecd9-5f1b-8d89-139988b85671 | note | — Cathodic Protection: N/A
bb40fb62-eae8-5b45-9cde-06dc282c3333 | note | Method - Document Review
6aa24a0d-ed69-563a-8c9b-fd00496783b4 | note | Frequency - Prior to Commencement
f11aee15-97c9-5e9d-8c74-d55b863e2278 | note | Category - HP
43c07f18-ec9d-5b29-b106-f8c71324cec3 | note | Responsibility - SE
d9392d8d-9544-5256-94b4-9413e367cf6d | note | Verifying Documents - Material Compliance Certificate
f6d6890a-288f-58bd-bf80-b90ef9db25ad | date | Date Completed:
115574fc-0bd5-4185-a2c2-74b5eef1ed5b | signoff | AUTHORITY HOLDPOINT
5f1d9fcc-c3e3-47eb-bf69-161f1277f2dc | checkpoint | 2.02 - Materials - Comms Jacking Pipe
879db6e7-ee18-5acb-a4e1-df8407d6c7bb | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203
1e6e565e-6e1f-514c-bd52-30f56245d37f | note | Acceptance Criteria - Confirm that the GRP pipes delivered to site meet the Pipe Specifications:
593dfa77-d57b-561e-a3a9-82889d4e6d06 | note | — Internal Dia: 389mm
cf173a30-6525-53f9-acce-b57ddab270e1 | note | — Outside Dia: 427mm
63b23ff1-d8d4-5e1b-870d-9b9518d46e45 | note | — Material: GRP Pipe
e0dd0388-02c9-517c-9c4e-c90fb7a2473e | note | ○ Specification & Grade: DM427 SN100,000 N/m²­­
493544c2-6b0f-53a9-96db-435a542a1948 | note | — Wall Thickness: 19mm
da194ff4-ccf7-508d-849a-a076795a549f | note | — Joint Type: Stainless Steel Collar with EPDM Seal
cd61a245-6a7b-5e2a-9135-ef176fafadb7 | note | — Pipe Coating: No Coating
928790e7-ede1-5427-abc1-f05c4f2a2ae4 | note | — Electrically Continuous: N/A
165b4810-1640-56f2-8cec-8630ee7944c6 | note | — Cathodic Protection: N/A
0f3384eb-bc69-5453-926c-580df71f7ed5 | note | Method - Document Review
65b66ffa-ab10-569e-a5c7-38004baaed0b | note | Frequency - Prior to Commencement
2423e292-722e-5835-8e07-f83b024582cf | note | Category - HP
b98e91de-67e7-5b0f-8b56-e39838434b09 | note | Responsibility - SE
b5dd03d6-88c1-5402-8187-c7af9e816fbb | note | Verifying Documents - Material Compliance Certificate
b8779216-5920-5910-8afa-0326d2cc19b4 | date | Date Completed:
cd606d18-9226-4066-971a-55bd7a146c8e | signoff | AUTHORITY HOLDPOINT
ae4e9094-ce5f-4aed-b1ae-d9cdde4c568d | checkpoint | 2.03 - Materials - Draw ropes
f51af56c-f063-559c-bb51-e779d7da5c11 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
ab64f1a7-3010-5ef6-8f64-b87955ff1e48 | note | Acceptance Criteria - All conduits must have minimum of one 6mm polypropylene draw rope to AS4142.
8947bef6-777c-5366-a67b-4fb33e4cecd6 | note | Method - Document review/ Visual
73877361-e0b8-50f3-97ab-b98c6f1b8d7a | note | Frequency - Prior to commencement
5e6b2f81-ee29-5839-a78a-0e56aed20d8e | note | Category - HP
c37fdf6a-3473-5c64-83ce-b2c255a06766 | note | Responsibility - PE/SE
8b8f549b-647a-5415-a59d-47abb77b0821 | note | Verifying Documents - Material compliance certificate
21ac63a3-8b9b-5728-a8e2-3762ccefa825 | date | Date Completed:
b4b8b140-60da-4a9a-bf27-266229b096e4 | signoff | AUTHORITY HOLDPOINT
1e76014d-1afa-4f9f-b1d9-86670413e345 | checkpoint | 2.04 - Materials - Comms Carrier conduits
a8376a12-aed6-58ad-b692-faca127bc1d1 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203
76bda481-d50d-5a62-af94-634474ba384e | note | Acceptance Criteria - Conduit fittings shall be the same type and material as the conduit.
8706a9fe-d28e-5e11-9715-a6dc308718e8 | note | ○ Comms conduits to be:
4f398130-f734-5c8c-b75b-31d4114502f9 | note | — Internal Dia: 93.3mm
7f97b882-065d-5698-b699-bac67ca6a327 | note | — Outside Dia: 110.5mm
83240bad-07e5-590d-a53c-2e40fc69b43d | note | — Material: White PE100 Branded "TELSTRA"
d6ef63fe-fa3a-5d04-8c04-82552a50e8a3 | note | ○ Specification & Grade: OD110 PE100 SDR13
af248380-2d09-5b70-956a-25a05d68957c | note | — Wall Thickness: 8.6mm
3e31fffd-c6fa-548e-8013-2e9f88a6c09d | note | — Joint Type: Butt weld
b7cde180-e700-5dc4-a172-0c49a628a9e8 | note | — Pipe Coating: N/A
4f11fe49-e3cf-501d-9be6-0704a7310193 | note | — Cathodic Protection: N/A
11d0d19a-3cee-5d97-be03-12d7fa31c0ae | note | Method - Document review/ Visual
a2afca55-18fb-5fa9-b6c5-9b74eb2f9692 | note | Frequency - Prior to commencement
3f757bb1-a5f8-51cf-b443-90fce23ebe71 | note | Category - HP
5e98ccc6-42dc-510e-b344-5e6b2f7c0f5b | note | Responsibility - SE/PE/SPE
5da83596-7b7d-5be0-bbf8-cc969a5907db | note | Verifying Documents - This ITP/ Material compliance certificate.
39942658-c891-5510-8cd6-494cbb7ea17a | date | Date Completed:
231bb9c6-b418-4b9d-90a9-50641071901a | signoff | AUTHORITY HOLDPOINT
6cbd055d-0e47-4a06-9141-72a02af53b24 | checkpoint | 2.05 - Materials - Gas Encasing pipe
bfe13b5a-df11-5c81-9d19-59884503dfe2 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
72110ce2-ebe4-5a0b-8022-89b227d958af | note | Acceptance Criteria - Confirm that the Gas Encasing pipes delivered to site meet the Pipe Specifications:
e8d3a333-193b-5e7c-8318-d74d0e86921a | note | — Internal Dia: 256mm
536f4c86-08a3-539e-a085-8815f083f12e | note | — Outside Dia: 315mm
2a251416-a305-5087-a7a3-0ff111594982 | note | — Material: Polyethylene
0248926a-b343-52c9-a747-562be8eceb23 | note | ○ Specification & Grade: DN315 PE100 SDR11
85e9ca81-9ced-585b-85e8-4330b8977695 | note | — Wall Thickness: 28.6mm
41d4edd1-097b-5321-b130-38cf2c00ac4a | note | — Maximum Working Pressure: 700kPa
5d933db5-29df-5856-a507-d06124d6362a | note | — Joint Type: Burtt Weld
c3825c83-a70e-5a8f-a7f1-8f653145c30b | note | — Pipe Coating: No Coating
b3eb19c3-6d04-5687-8cfd-61bb9cc19a97 | note | — Electrically Continuous: N/A
c31c6384-d963-5821-94a1-7285344028a6 | note | — Cathodic Protection: N/A
944db182-964d-567d-ade4-99e2ab66c6d5 | note | Method - Document review/ Visual
6673a5fe-711c-51bf-afa1-ceb569e831c4 | note | Frequency - Prior to commencement
d20406dc-cc82-5c19-a861-65c89080d0b5 | note | Category - HP
8c5b18d7-9f84-5f4a-a321-9f10c308d3a7 | note | Responsibility - SE/PE/SPE
1a0e06a5-f1b9-5a28-a11e-893d5c0c7386 | note | Verifying Documents - This ITP/ Material compliance certificate.
4a19f27e-e57c-51cb-8e0a-0cf53a66e983 | date | Date Completed:
8026ecd0-efe6-4a6b-9526-d7a160a92eb3 | signoff | AUTHORITY HOLDPOINT
34eea79b-7027-416e-a933-508b820b3578 | checkpoint | 2.06 - Materials - Gas Carrying pipe
efc78249-be2b-588a-8a95-03a26a5f25bf | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
008f2ec7-6475-51fd-bca6-358aacf6aab5 | note | Acceptance Criteria - Confirm that the Gas Carrier pipes delivered to site meet the Pipe Specifications:
1ebadd9c-ef2e-568b-b42a-bf0b5324f508 | note | — Internal Dia: 145mm
3f2820be-c9ab-5ba6-8e87-40031cafe56b | note | — Outside Dia: 180mm
6b99801f-d517-5145-84f5-d6fda8faf054 | note | — Material: Polyethyene
35613f24-f3a8-5826-962b-0e2b50165729 | note | ○ Specification & Grade: DN180 PE100 SDR11
92a6204a-b639-5d4e-9734-0faac897fae1 | note | — Wall Thickness: 16.4mm
293980ff-7981-540c-9540-9fd7c69846af | note | — Maximimum Working Pressure: 700kPa
68b542c4-c857-523b-991e-909b089f9b97 | note | ○ Joint Type: Burtt Weld
7cb34291-59e5-588e-933e-50ffcf14f749 | note | — Pipe Coating: No Coating
3494c557-794a-5e89-ae76-415eeb534266 | note | — Electrically Condinuous: N/A
28a36b80-a5f8-59ff-aa2a-a182efb82fce | note | — Cathodic Protection: N/A
01bc89c7-c237-5f80-ba72-a8a49398f997 | note | Method - Document review/ Visual
f2af3a07-6e69-564d-9600-2b066757bdf4 | note | Frequency - Prior to commencement
131ae206-3ad1-525b-b33b-cc65a6951fc6 | note | Category - HP
cf75a342-c0a7-55ad-9e22-5ab331a87a5c | note | Responsibility - SE/PE/SPE
4e42d6aa-ff74-5d8f-8a3c-421a1d7bd9d4 | note | Verifying Documents - This ITP/ Material compliance certificate.
66386190-7321-5a50-a4ee-c44d2fb60b33 | date | Date Completed:
99554717-8b51-49da-aaac-17541622f8ac | signoff | AUTHORITY HOLDPOINT
69b87636-ad9a-4bfd-b45c-81c2025b3f85 | checkpoint | 2.07 - Materials - Grout
d8d6c465-8b84-5ac1-ab5b-956fc8a1b0ff | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
ae59eefd-782e-56a1-808a-38ec259cb9ff | note | Acceptance Criteria - Diameter of bored hole to jacking pipe shall not exceed diameter of encasing by more than 50mm. annulus to be grouted with an approve controlled low strength material (CLSM) of minimum 2MPa strength material
f6875379-1cca-50c4-9786-6d79f3f6de02 | note | Method - Document Review
66b33d0f-aeac-5a25-9f39-3f4ee9043a2d | note | Frequency - Prior to Commencement
f76ed94b-4b2a-5b1c-924a-9f35e601203a | note | Category - HP*
f4c1e92a-97ca-547f-b2f5-2bc90759f64c | note | Responsibility - SE
35356bb6-cda8-51c6-b2de-d1b6ea77bb24 | note | Verifying Documents - Material Compliance Certificate and TDS
1feceb36-3d31-5d9f-ab20-04c1013ecfff | date | Date Completed:
f32be13d-83cb-47a3-b353-7c6b9fbb6fbf | checkpoint | 2.08 - Marker Post and Marker Plate
f67973a3-0162-519b-b9dc-8fc459acd506 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203, AS4799-2000 cl 3.10
5629a3df-b085-5970-b9e5-1f88be9caf35 | note | Acceptance Criteria - Be of non-combustible material for the marker plates and of at least fire-resistant material for the pole.
9287c8ca-7f9d-56ae-96b8-f0dc36ed391c | note | Method - Document Review
a39be917-115e-5058-9ec1-02ae07339e19 | note | Frequency - Prior to Commencement
4021e267-f544-5bef-bb0c-ea5adda4aa1c | note | Category - WP
ecaa248a-ab4e-5a49-8abc-f4cbf56fe0ab | note | Responsibility - SE
0a1b3b72-21c1-54a1-8924-73bf41794ab7 | note | Verifying Documents - Material Compliance Certificate
7273c7c3-eb2f-525e-b673-ffa6de03a1e0 | date | Date Completed:
5fcea3bc-11a1-4e4a-b61e-34e4ff3c1b7d | checkpoint | 2.09 - Poly Welding Qualification (if applicable)
1c230bf0-7cb2-5cad-adcd-dbdb8c5ac93e | note | Reference - IFC Drawings
a4cf8899-debc-5b47-ad1f-39f5ad2c975c | note | Acceptance Criteria - HDPE welder qualifications to be supplied
0cc79b0b-e74a-5491-8f6e-350556bc40cf | note | Method - Document Review
fd478ef5-fb9d-5116-9db7-9b584dbf6785 | note | Frequency - Prior to Commencement
74a46efb-e3ef-596e-bf7a-d02f85add3aa | note | Category - WP
2f1aa2f4-0ef5-5e13-ba58-108643841aa2 | note | Responsibility - SE
2211ca68-b924-5a3c-a9e8-230a2fd700aa | note | Verifying Documents - Welding Certificate
f2cf57a4-81d0-5c16-bfd0-7047406f72e9 | date | Date Completed:
fa290789-e346-4c40-9b4e-4402fad6f400 | section | 3. Pre-construction Activities
c19fba44-a079-435e-b912-920f86a287ed | checkpoint | 3.01 - Survey Set-out
2e42ac70-37d7-54c6-944c-e47bc9021ce1 | note | Reference - IFC Drawings: MRP-DPK-103-00-CUT-0065, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
86ff6123-62b2-5619-9ba9-b09b428007ce | note | Acceptance Criteria - Set out line and level of drilling works.
f9f195b5-e5a4-5bda-8c04-d96e3fc77129 | note | ○ Survey to mark out existing services.
588a3535-231a-5bf6-869f-8457767cb9ac | note | ○ Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
a986526a-f680-59ae-baa9-dd260fde5ad6 | note | ○ GFRP must achieve a min. 1200mm vertical clearance to tracks and minimum 800mm to surface level. Check FSL of track and ground.
0ae6ebe1-7988-52c2-9261-eef224737946 | note | Method - Measure, Visual
61d70257-9183-5ae4-8819-adb38f067d3d | note | Frequency - Each element
55b15e64-0399-55b0-9f85-f3dada773ade | note | Category - IP
981474e3-91be-5727-abd9-4eee87fd5523 | note | Responsibility - Surveyor, SE/PE/SPE
e4e6c590-b77d-5d09-ae89-7c9baeb91323 | note | Verifying Documents - This ITP
57444901-fe6b-5eef-bd09-52b9bdb0a032 | date | Date Completed:
0c7977be-1473-45c0-978d-e6a4c2b0e190 | section | 4. Construction Activities
b98ebc44-1cde-4d0d-864a-54657f7a88fd | checkpoint | 4.01 - Drill rig set out
0235e862-dd8a-5868-87f4-a5db40e3c82f | note | Reference - NA
40aa23cd-76d7-58c8-9f0f-6dbf6bdc410d | note | Acceptance Criteria - Location as per current Drill shot plans
7965147c-7be5-5ed8-82fa-136c47af4c1a | note | Method - Visual
d5700400-9782-5e68-be21-2c7dd1bad3e3 | note | Frequency - Prior to commencement
3a6ed27c-335b-5040-a59d-ae4bb9b5c856 | note | Category - VP
5b599b34-99e6-5758-9a4e-59bac00af387 | note | Responsibility - SE
a3245dbf-696b-5121-86a3-7cfc4912b398 | note | Verifying Documents - This ITP
789beff2-e72b-5f48-be01-65feab1535a3 | date | Date Completed:
d62a319e-cf94-40c9-b589-cb491a5d8391 | checkpoint | 4.02 - Ground Conditions
e81c42ce-4159-53eb-a4a2-d497fb3bd8af | note | Reference - IFC Design Report
bb9510f5-7ce5-5f73-820b-dda7f2bc9e98 | note | Acceptance Criteria - Assumed ground conditions are as per site geotechnical report.
d0b8c99c-ea11-594d-8246-c2fb63be7e01 | note | ○ Geotech Engineer to be immediately notified if the excavations encounter different materials than expected
18f93609-0ff8-577b-826a-be182acc872f | note | Method - Visual
46d7bd1f-d002-503a-82a1-b071a37c180d | note | Frequency - Each lot
c3440667-3ae1-55aa-953c-c9c5268c822b | note | Category - IP
3cfd42fd-55eb-528c-9f80-e6dd22f28b5b | note | Responsibility - SE/Site Supervisor
5e9e4d59-4505-5786-ae03-f70c97042e6c | note | Verifying Documents - Photos, Sign ITP
8e2e269e-afba-5739-8305-7ca8d87e4b4e | date | Date Completed:
871f486b-a262-4bbb-82df-2a7a8a84bced | checkpoint | 4.03 - Pilot Hole Drilling
ef7d51bc-188c-5eae-88a2-64502b1fa268 | note | Reference - IFC Drawings & SAP
a53a64ee-f6f4-5555-820d-bc092d0c2e60 | note | Acceptance Criteria - Pilot hole to be drilled and fully supported at all times.
891183a0-eb77-58e2-8668-e11a75ca13b5 | note | Method - Visual
02551687-f3b8-5ebd-b4ee-205546f685e5 | note | Frequency - Each lot
4c2c529f-ca00-5416-a609-d920209169ad | note | Category - IP
214137dd-6e5a-5995-afea-7e12573cc621 | note | Responsibility - SE/Site Supervisor
75259b71-d860-5fba-8748-b7587b80d700 | note | Verifying Documents - Sign ITP
e4e893ff-a2ec-5884-a6db-b35bb8bf24f1 | date | Date Completed:
ac7d6171-a4b1-42d0-a77c-2fbd42125e2f | checkpoint | 4.04 - Pipe Jacking Monitoring
b847fef1-ff6f-5fdf-afe2-c88536dca334 | note | Reference - IFC Drawings & SAP
61ac1638-4613-54ca-83db-e8acf0b84d7b | note | Acceptance Criteria - Inclination and path to be monitored as per design alignment.
c3ce40e8-d485-5a72-9af9-f061a7ede038 | note | ○ Ensure bore hole blockage and fluid losses are detected and addressed by:
6587b960-cbf3-5981-aba9-03d98bd64ac7 | note | ○ Monitoring drilling fluid volumes, monitoring annular pressureand monitoring cutting returns.
e1cc81f9-2b31-5af5-b302-a9e40add1d98 | note | Method - Measure
c4c93bac-cb10-58fd-9e99-e2d14a21479e | note | Frequency - Continuously through installation
0cb7c8b5-c42f-57c3-9d60-aa6633be422b | note | Category - WP
fc3151a6-04ed-5a68-b5c0-61e41dcefc29 | note | Responsibility - SE/Site Supervisor
f7f17a99-e971-516d-9e0a-a72989ceb297 | note | Verifying Documents - Sign ITP
0ea38cdd-df53-5a70-a640-28859b2ac3fa | date | Date Completed:
55f81a22-f4fd-4cc3-b9c9-a05ef597000b | checkpoint | 4.05 - Jacking Pipe installation
662b743f-80fc-5239-bdb7-74784e1ec5bb | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203, D/17/62901
b4ae9e82-0872-552a-9b43-11532c757def | note | Acceptance Criteria - DN427 GRP Jacking Pipe to be reamed, then immediately followed by pipe being pulled through. Bore should remain supported at all times.
3336d1ef-5bce-5095-8ae2-9451be82d5f4 | note | ○ Diameter of bore is not to exceed diameter of pipe by more than 50mm.
e7171fe3-e008-5988-a004-10b8b8de3b7a | note | ○ Pipes to be installed in straight sections with no excessive bending in the pipes
fde98351-660c-599e-be8b-818c03cf2547 | note | Method - Visual and Measure
982824c8-94e1-5e1e-b9b8-d605af7a0daf | note | Frequency - Each lot
e12ff3da-a5f1-5c05-b8fb-c72a84e50833 | note | Category - IP
d340c156-bafe-50d4-aedf-1df6bc530da7 | note | Responsibility - SE/Site Supervisor
9f4f0ae4-eca3-56a8-b096-c553c4908583 | note | Verifying Documents - Sign ITP
33ecb7fe-8ba2-50a4-8a0c-967a90009e2d | date | Date Completed:
f992adbe-8cb1-45af-8080-71da5b22f6d1 | checkpoint | 4.06 - ULX1 - Gas Encasing Pipe Installation
c1513785-a0a9-5e72-9d90-ba6deb0b38e1 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
392c7245-0dbb-5ba0-9e03-e2a3d9f6604e | note | Acceptance Criteria - Install thininsulators @ 1000mm centres between Encasing pipe and Jacking pipe to ensure centralisation
4020fd39-86f8-5e5d-91c6-31f324b9f97c | note | Method - Visual
f8629e6f-1bbd-5c30-aa1d-cbc9c2f3f04f | note | Frequency - All Pipe
b4d1e5b1-2231-5969-9799-9251315a298c | note | Category - VP
d26c87e7-18eb-54e3-8cdc-fe12dc7798ca | note | Responsibility - SE
9d60e9a7-6ea0-5282-9552-e47791b47356 | note | Verifying Documents - Sign ITP.
20c0719b-9278-52ba-86b9-d966addacabc | date | Date Completed:
4112a6e1-c54d-4d43-83d6-7cea8561067b | checkpoint | 4.07 - ULX1 - Gas Carrier Pipe Installation
a430972b-2863-5196-871a-4096694e6083 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
32514224-c80a-5b94-8bfe-62778fddaffb | note | Acceptance Criteria - Min depth as per IFC drawings.
71b0614e-ca25-51cf-b01e-945d79c6ae99 | note | ○ Install thininsulators @ 1000mm centres between Encasing pipe and carrier pipe to ensure centralisation
2294a341-77e9-5709-83d4-49a37bba5933 | note | Method - Visual
43882b98-1c42-5e62-817a-392bdeb47057 | note | Frequency - All Pipe
206a1ac3-3f89-5b4f-9f05-a91fdeb301ce | note | Category - VP
3b58d40a-e900-57a6-b8d8-7c598cc3ed45 | note | Responsibility - SE
4baf258c-311f-5b9e-94a7-392da859a632 | note | Verifying Documents - Sign ITP.
429d998c-1413-5500-a500-a6c5521e2191 | date | Date Completed:
8a957817-6846-46e5-8d73-5bb62256e057 | checkpoint | 4.08 - ULX2 - Conduit Installation and Trace Wire
c313c9a1-faa6-5e47-b6da-ef1d70de4a1c | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0203
9d27ffaf-d872-5a29-adda-8922e1d4203e | note | Acceptance Criteria - Min depth as per IFC drawings.
653cdc60-83b9-59e1-894b-33e764ace988 | note | ○ All bored communications conduits shall include the installation of stainless steel 3mm trace wire.
62bca84d-8a56-58d6-a6d3-2b98b5b97cbd | note | Method - Visual
beec80bc-2666-535c-b8fe-d8c7910a1195 | note | Frequency - All Pipe
50f8f6ae-8d31-5bfd-9c14-ba0c0440c4a5 | note | Category - VP
17cdd888-02c6-5867-b458-59b7ef8d72ef | note | Responsibility - SE
74346641-bb94-5a2e-babc-ec6a3fa3be01 | note | Verifying Documents - Sign ITP.
5ca04c27-7cdb-564f-b62e-398663007d95 | date | Date Completed:
a436be1d-f08f-48c2-9dfc-fd22746e19eb | checkpoint | 4.09 - Track Monitoring and Ground Settlement
7ce4a1dc-ddda-5d9d-a173-99fce92c05ff | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
67430561-d138-5a0a-94ff-2d71fb3b6919 | note | ○ NIST-2706
8add79e6-955c-50a9-a8e9-5217f0dd5896 | note | ○ MRP-000-MRPA-PLN-XPM-0055
42f87696-db25-5c47-a51c-a9c485b88f42 | note | Acceptance Criteria - Both tracks are to be monitored at 2m intervals either side of the centreline of the under bore for 10m either side of the bore centreline, with additional tilt sensors at 5m intervals up to 20m either side of the bore centreline.
b488806f-4873-5b71-be15-4ba42f94bac7 | note | ○ Settlement to be monitored with the escalation matrix on the monitoring plan to be followed. <5mm = no action. 5 to 9mm = notify v/line for inspection. 10 to 14mm = stop works and rectify. >14mm = halt train operations.
db4aa07a-9342-51cb-a430-0cdf4a15d66c | note | Method - Measure and Visual
3da51a22-9f24-5928-87f6-d10e4a0f2639 | note | Frequency - Continuously through installation
ea354ba9-75e2-5593-bca8-e9d1550d3c35 | note | Category - IP
94709ab3-79fd-5fe9-bedb-85075ac40db1 | note | Responsibility - SE/Site Supervisor/Survey
a95dc8aa-473b-52db-9a59-84df5bd3a752 | note | Verifying Documents - Sign ITP
d2d4edfa-7031-580d-9cf4-b069819980a5 | date | Date Completed:
fed36038-a28d-444c-866c-d8037671fc90 | checkpoint | 4.10 - Conduit Welding
8fb6be23-fa66-5b4d-b51f-372a4e4699af | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
84a30b49-5dc7-542f-86b0-5a6e65df3978 | note | Acceptance Criteria - Joints are to be butt welded.
ea963599-f7ba-5a7a-811f-f546f4941d11 | note | ○ Weld map to be supplied and identify unique joint numbers.
627bf2ab-6ea7-5afa-a668-a58e02ac10da | note | ○ Butt Welding records to be supplied.
d536d142-b859-5db5-b05d-0937f5d90989 | note | Method - Record and Review
945e782a-64a5-5532-a6af-9eb383c4baa2 | note | Frequency - All Joints
718cbf5e-402d-588d-9753-f1ed6d023978 | note | Category - IP
5beb1304-91f4-57de-915d-1f598a1a5e82 | note | Responsibility - SE/Site Supervisor/Survey
f7795835-5549-59e5-b8ca-120a5228c8f3 | note | Verifying Documents - Sign ITP, Butt Welding Records
06d8b5d2-33cc-5162-94b1-a59cfbff083c | date | Date Completed:
4515b6be-d1d3-4e7a-8f92-2f5f2e602a95 | checkpoint | 4.11 - Vent Pipe Installation for ULX1 Gas
3c95d7c5-8916-5e67-a4b1-fe352f8d7093 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202
a2908692-02f6-524c-b595-d3c8b3da6631 | note | Acceptance Criteria - DN50 PE Gas Ven to be installed by Asset owner (Downer) a minimum of 3m away from rail assets
0742f1dd-57e7-5ce4-8800-7bcb0dba7d13 | note | Method - Record and Review
5a6bd358-f9db-5162-94ab-3bafed674f2c | note | Frequency - All Pipe
7c0f8122-6dcb-5caa-97ff-d6eabf353d80 | note | Category - HP*
6d6ea4af-de17-5b1b-87ce-bcf23eacfb85 | note | Responsibility - SE/SPE
63cef8f1-3981-5077-b357-871e7af8f5e2 | note | Verifying Documents - Sign ITP
18adce3f-ff2a-5372-b3db-5072000f763f | date | Date Completed:
fa772c06-d9cc-4355-9d5f-bbd3d37aa7fe | checkpoint | 4.12 - Grouting
13f37c6b-e569-5346-95df-a3cd10d92f22 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
24c52f1b-fc7b-5e88-a7c3-e90c0d070de9 | note | Acceptance Criteria - Diameter of bored hole to jacking pipe shall not exceed diameter of encasing by more than 50mm. annulus to be grouted with an approve controlled low strength material (CLSM) of minimum 2MPa strength material
2e14f2fd-c29d-5f97-955a-9f59ab9de214 | note | Method - Review
aba393a7-bb02-56bd-9dda-c13afb96abed | note | Frequency - Each lot
c25fb45d-ea0a-56e7-b222-f96de80b7398 | note | Category - IP
c7c0a3e3-a9c2-570d-8a69-05a5148cb3dd | note | Responsibility - SE/Site Supervisor
6df48572-fb14-55d3-92d3-4d505ccc94ec | note | Verifying Documents - Sign ITP
1536e8df-e053-593a-8080-bfafe46af089 | date | Date Completed:
4c3e8215-ff43-4f21-ba2f-6575d3ffad0d | checkpoint | 4.13 - Draw rope
0ee4ccc3-99a5-5dcb-9f12-1d0c9eef10d5 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
91b26510-df2f-50b7-9390-2beffa19fb8b | note | Acceptance Criteria - The draw rope shall be continuous for the complete length of the conduit run.
c28afdeb-230e-5611-8bce-f7938f19a096 | note | ○ All draw ropes must be continuous between pits and have 2m slack in the pit.
1e43b804-86fd-53cc-b2a2-bd0014fb7c24 | note | ○ Draw ropes to be restrained in each pit to prevent them from being inadvertently pulled into the conduits
2e1d0d3e-6514-59ee-b201-e89b43e254fa | note | Method - Visual
015559e1-d64b-58d2-9223-458fbbb8323d | note | Frequency - All Pipe
4cf0c673-a510-5bc9-9794-3102505215b3 | note | Category - VP
6a5b8a00-f35a-5bab-a3d0-90acca53b9ac | note | Responsibility - SE
bb6ae419-5209-562a-bc8a-51765a6f233e | note | Verifying Documents - Sign ITP.
9b6a3108-4da8-5585-88fc-c1bad9d385e3 | date | Date Completed:
ca960845-40d9-4082-9f0a-e1b5cb25b2c0 | checkpoint | 4.14 - Mandrelling
fecaaab6-4459-5587-812c-605bd3872b49 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
31aee3bf-6724-5973-be49-8a9fa84060cf | note | Acceptance Criteria - Plug with 90% of the pipe diameter to be pulled through each conduit to ensure the conduit hasn't been compressed.
bfd7589a-4a0c-5cd2-ade9-fc506d72bed4 | note | Method - Record and Review
5d776272-73a3-5760-b648-643c51fcabce | note | Frequency - All Pipe
d1e9ff85-9f5f-5614-aef0-53156bbff7a3 | note | Category - HP*
e1fa9c66-57be-5b50-8124-939c509e2585 | note | Responsibility - SE/SPE
b8e6a24b-7fe9-5455-81c1-75c30371642a | note | Verifying Documents - Sign ITP
63784f15-71b6-5088-ad05-04ecc2e03c5c | date | Date Completed:
06f8e0df-b695-4490-adb6-9e74302a990d | checkpoint | 4.15 - Tracer Wire
a5aa2666-1fcd-5a46-a1d2-7cd83048fc48 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002
23eccefe-2b26-5a2d-bee9-2c75f1b6b410 | note | Acceptance Criteria - All bored communication conduits shall include the installation of a stainless steel trace wire of 3mm diameter.
7ef3f9da-9dac-5e1c-9d69-2e53ed1d8a05 | note | Method - Record and Review
eeae155d-6cdb-53a8-9784-db67769f22f7 | note | Frequency - All Pipe
497b6842-65f1-590f-ac8b-b900d550fb97 | note | Category - HP*
85995889-8436-5aa1-b7c2-e02601fd834c | note | Responsibility - SE/SPE
c43ec950-a854-5637-9bb1-be3f4884eea0 | note | Verifying Documents - Sign ITP
e032e011-20f2-5759-b566-915523ed341b | date | Date Completed:
7fc90178-31ab-464c-9b6c-19d6b289db4e | checkpoint | 4.16 - Pipe Completion
5f6b2bfc-245e-5de4-baae-3e94eb17df90 | note | Reference - IFC Drawings
9ba26092-564d-5dcd-bd04-cb3155e20a20 | note | Acceptance Criteria - End of encasing pipe to be sealed at each end as per IFC drawings
02b3f7c9-ceed-5d58-8c5e-20cb6b7eaf77 | note | Method - Review
96e98c64-75db-5c70-a041-8f8fa066c33f | note | Frequency - Each end of pipe
8dffb93e-a27a-5bf6-8cd8-e0b2469345f2 | note | Category - IP
e531150a-ec31-5847-aa38-fdb3009962f2 | note | Responsibility - SE/Site Supervisor
d6bbaddb-84e1-5765-95af-5ef7001cefb6 | note | Verifying Documents - Delivery dockets, Sign ITP
130f1cf9-a9c1-5a58-8e39-d67036b7d7f5 | date | Date Completed:
c7405d59-1c30-46f4-8313-33076f3ff1ba | checkpoint | 4.17 - Reinstatement
5b611a52-9a93-569c-8b1d-1bad575d7e19 | note | Reference - IFC Drawings
f49f7aba-2f8d-5e1f-8d30-0b413da6b6ba | note | Acceptance Criteria - Entry pits, exit pits and trenches to be backfilled using approved fine crushed rock material. Backfill material shall be compacted to the same density as adjacent material or as specified.
b0667202-ed3f-5738-b298-40736e59d3c3 | note | Method - Review
7520baf4-9c97-514d-b23d-f56b507aefd9 | note | Frequency - Each lot
a8159e17-adcb-5b80-a690-f77171984a4e | note | Category - IP
e0d93d47-04ef-52c1-856c-21627d3c5ded | note | Responsibility - SE/Site Supervisor, VicTrack
d5576fb2-3a50-5a30-8294-12db6e5b9561 | note | Verifying Documents - Sign ITP
1ee9b078-1545-5db3-8135-d845ca2604a2 | date | Date Completed:
e8c6989e-4235-4287-9827-bd35b100b9e2 | checkpoint | 4.18 - Marker Post Installation
7ac31c1c-e065-56af-9514-daaea8dd5280 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203, AS4799-2000
d0a8c54d-41a3-502e-8584-2df23b83acd9 | note | Acceptance Criteria - Marker posts to be installed at every 200m intervals, any change in direction and at the entry and exit points of VicTrack property.
abb19644-835e-54a2-8438-6b63c81a1eec | note | ○ Marker Posts to be placed facing the rail tracks within VicTrack property
28983b33-a5b5-528a-b10b-69ef172f0874 | note | ○ 50mm x 8mm Galvanised Steel Plate Welded to 50mm Ø Galvanised Post with as Capped top protruding to the air and flatted end in concrete
c2696a3c-8fc7-5087-8bcb-d612e8236dd5 | note | ○ Marker plate riveted to post with 8mm insulated aluminium rivets.
157c90b2-694c-556c-a111-56aff3d78c1f | note | ○ Post to be extend 500mm in ground and be concreted in a 300mm Ø footing, concrete to extend out of ground
0cae94d8-638b-5303-a4aa-57b56f510722 | note | Method - Review
79e89079-6d6d-5ad0-ad1b-4bab38ea1b73 | note | Frequency - Entry and Exit Points
38c5fdd8-c0d5-5949-bd6e-e5dad829a933 | note | Category - IP
b04a8aca-6466-5a03-8cc9-aa225135e6e1 | note | Responsibility - SE/Site Supervisor
02316bc8-8182-5994-b2d6-b213c39bd3fb | note | Verifying Documents - Sign ITP, Delivery Dockets
455aa703-2cf9-5c2d-879b-73080cce041c | date | Date Completed:
09be45db-2a9f-471c-aaba-af3718aa5e6b | section | 5. Post-construction Activities
d54c6d4d-b299-420e-9c32-f00553d0a18f | checkpoint | 5.01 - As-built Survey
91c4d1c4-6ea0-5076-ae6c-401c14815df8 | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
ec4f2448-4171-569e-b1e3-55f3a001a447 | note | Acceptance Criteria - Survey as built report to be compiled.
4a937e28-015f-56f9-8199-72973b4096a9 | note | ○ Must maintain a min. of 600mm clearance to any existing service and a min. 3m clearance to any Railway Structure UON.
fc68d918-f5a5-5186-952a-fb42d3dba1c1 | note | ○ Sleeve must achieve a min. 2000mm vertical clearance to tracks.
daf8a076-ef86-5dad-bd1b-082e5149bb96 | note | Method - Document Review
ba6b4dc6-b8b7-5c93-a5d6-8d7ac8fa578f | note | Frequency - Each element
a445d29a-28aa-5222-848e-e24e2146b83e | note | Category - IP
62aafee4-6942-5a95-bba2-972a65a614a8 | note | Responsibility - Surveyor, SE/PE/SPE
5862d78e-094f-53cf-b622-251af329d452 | note | Verifying Documents - Survey As Report
b62c76ff-259c-58da-8ae9-f262b0e54ab2 | date | Date Completed:
fbb2247a-1684-4952-a17d-1d5d4b6d441e | checkpoint | 5.02 - Track Inspection and Maintenance
362f28ad-9ea0-5f6e-aa12-72521d8beb6b | note | Reference - IFC Drawings: MRP-103-C-AUR-DRG-65-RBK-CUT-0002, MRP-103-C-AUR-DRG-65-RBK-CUT-0202 & MRP-103-C-AUR-DRG-65-RBK-CUT-0203
c56b4072-dddd-596b-ac81-d1b628415540 | note | ○ NIST-2706
ce3572a2-7091-5378-bc06-da6368035acb | note | ○ MRP-000-MRPA-PLN-XPM-0055
0a1da398-ba6b-5432-925a-70ff16e3e586 | note | Acceptance Criteria - Once works are completed, survey to confirm settlement of the track and ground are within the predicted design settlement values.
898effa2-4b87-51c0-9dbf-7d1c9c9249ff | note | ○ Not > 15mm
d02a616d-f672-5b10-bc63-264c5af5e075 | note | ○ To be provided to V/Line prior track hand back.
b629abcb-8d92-59b2-9327-0c93204ccd2a | note | ○ Where track has been disturbed beyond the tolerances, realignment and/or maintenance is required by a qualified sub-contractor.
422a062c-55d2-5cc5-941e-cb1fb6360486 | note | ○ Attach: Track Inspection & Maintenance plan
194b4774-be6f-594b-ad06-3f477e8b3bb2 | note | ○ Attach: Track Measuring Sheet
348e9581-74dc-51b9-8ad8-d8d64223fb3e | note | Method - Document Review
591f8269-8d07-527c-aad0-d682ce98ba31 | note | Frequency - Each element, Where applicable,
2f469c64-c94c-525c-ae10-dd3ee34a3c5e | note | Category - IP
9c088c4b-5f4e-5c10-919c-3a0a6123a79c | note | Responsibility - Surveyor, SE/PE/SPE
42a0ec5b-bea5-5bcf-ba7c-0254687ed951 | note | Verifying Documents - Survey As Built Report
f3adba56-86e5-5ad4-bdf2-a0ea4c1ba28e | date | Date Completed:
17a887d4-aae1-4414-b432-e5507f5cfb9f | checkpoint | 5.03 - Red-line / As-constructed IFC Drawings
7dac1486-465d-539e-89ba-fa0649977b91 | note | Reference - MRPA Quality Management Plan
88e58a79-77d3-5df8-9992-83c0ccfd6f2c | note | Acceptance Criteria - All RFIs, NCRs and changes to the IFC drawings are captured on a controlled drawing set marked "Red-line", "As-built" or similar.
40a4a7e7-4e34-5c7e-8647-45412ffb2672 | note | Method - Document Review
2d0a4c9b-b16d-5cb6-a3ae-32dce1832a08 | note | Frequency - Once, after construction of the design package
db45fe64-42fe-5c0f-a2f4-835fc9da35f9 | note | Category - WP
37f4bdc7-7667-53a4-94dd-857a7c66175f | note | Responsibility - SE/PE/SPE
e03cdc51-e5a2-5492-912f-4378c0190159 | note | Verifying Documents - Red Line Drawing Pack
8d3fdabd-a515-5a2d-bddd-86bffd39ea63 | date | Date Completed:
de2b1fa7-5372-47d4-8278-af1dd35eb86e | checkpoint | Final Inspection
ac4c7329-6028-591d-a25d-39038c16e6ec | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
662989da-65f3-5ae5-b7e6-e8b9d6c596c8 | textbox | Name:
863595d3-c687-5a88-bc52-b6f82ae18111 | textbox | Position:
0ca63c3b-eaeb-5126-90e9-f44f278458af | textbox | Date Completed:
35417162-075e-4b87-91c3-67622999185f | signoff | Sign ITP
43092937-2b7a-404d-a998-2f3127e6ff3e | checklist | ITP-242-CIV-FRMS-Stormwater Drainage-Pipes Supply & Installation (CCTV) Rev 0 | itp | ITP-242-CIV-FRMS-Stormwater Drainage-Pipes Supply & Installation (CCTV) | cf608dc6-ead3-4a49-a530-48e9f94d3256
7581c8ec-02da-4910-94b9-a553e772a8af | section | 1. Referenced Documentation
97a79493-94fd-4b3e-bc5b-04583e15caec | checkpoint-no-value | Referenced Documentation
b2bad124-0d86-570a-8bc4-589dcfd401d2 | note | Document Title: ITP-242-CIV-FRMS-Stormwater Drainage-Pipe Supply & Installation (CCTV)
9e1661c3-d5c7-52a9-b51d-5a48081722df | note | ITP Description: Stormwater Drainage - Pipe Supply & Installation (CCTV)
0306865b-cf06-56ef-aa88-50775d92ece3 | note | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
a922d9d9-43cd-591d-bf60-e060fdeedc81 | note | Revision Number: 0
9aca6c59-b0d2-5d1e-932a-670a10ab462c | note | Revision Date: 27/02/2025
87ebbdb3-82c4-585a-8567-53c7515870e5 | note | ITP created by: Kamel Alshobaki
a693ae13-7179-57c3-aa12-13030c2f093b | note | ITP approved for use by: Sandy Escalona
bd304a99-53ce-5118-a29f-fd6fa96c1a9b | note | 1.1 - Non Dependent
09813e2a-daff-5238-b8c7-4503a13aef70 | note | Reference - VicRoads Section 701 (May 2020), VicRoads Section 705 (June 2023), IFC Drawings
73dc2fd4-9c0d-477e-a595-403e3efd157c | section | 2. Preliminaries-Materials
9527f8df-4f6c-441b-926c-ba1ae96fa646 | checkpoint | 2.1 - Drainage Reinforced Concrete Pipes (RCP)
1c94413a-cd63-507e-8779-d067bc11672f | note | Reference - VR Cl 701.04, VR Cl 701.05, VR Cl 701.09
ebeba305-f032-5a3e-90e3-158447c0f2f7 | note | Acceptance Criteria - Precast reinforced concrete pipes shall be manufactured, supplied and installed in accordance with AS/NZS 4058 and VR Sections 701.05 & 701.09
41244360-dd74-5f47-8c43-330cf5d54ec7 | note | ○ Precast reinforced concrete box culverts shall comply with the requirements of VR Section 701.04
97ee68cb-105c-5461-bb18-0db820e4243a | note | ○ Rubber ring joints shall comply with the requirements of AS 1646
5a540e41-2807-58cb-b801-905be764e268 | textbox | Enter: Teambinder Material Approval number
ea4fc245-8e92-552f-b640-8fc2b75aeb96 | note | ○ Attach: pipes delivery docket
18860954-c813-52ba-a7ef-da29736333bf | note | Method - Document Review
6803c54f-63b9-5423-a540-1d5effb255c0 | note | Frequency - Prior to Commencement
e72914b0-d53c-51ba-866c-96f85b405d6c | note | Category - HP*
9057c4a4-2428-5407-9672-86c8500ac8f3 | note | Responsibility - PE/SE
3b5b2111-5ab5-5d57-b41a-ac9aef2ee1d6 | note | Verifying Documents - Teambinder Material Approval Number, Pipes Delivery Dockets
59f18f23-aab6-5c21-bfb1-a33368dceafc | date | Date Completed:
07186493-8508-4ef2-89b8-1dacd105c0c3 | checkpoint | 2.2 - Drainage Flexible Pipes
f93d1feb-65a1-5eee-8039-1f8afdbc7cf1 | note | Reference - Section Cl 701.08
a4d8e23e-3e74-57e5-98e5-c9ae90fc4b3f | note | Acceptance Criteria - Flexible pipes shall be supplied in accordance with 701.08
57011122-8797-5e90-9f62-deedd06866bf | textbox | Enter: Teambinder Material Approval number
fff923d5-7483-58a6-9416-8e0c75235a7d | note | ○ Attach: pipes delivery docket
214735aa-7b7d-573c-9228-7e08b8136b9a | note | Method - Document Review
f3944dd0-4387-5be0-b28b-f53a7d6caf73 | note | Frequency - Prior to Commencement
8bd92ca3-9cd3-5eb3-9210-147e7f37f7d9 | note | Category - HP*
ab29dfa0-9bc7-5b4b-88ee-555e7f2d483c | note | Responsibility - PE/SE
5332ce71-6412-55f6-8950-a357322b4d3b | note | Verifying Documents - Teambinder Material Approval Number, Pipes Delivery Dockets
dc7035e7-06e7-5bbd-84b2-bdf299d34754 | date | Date Completed:
150385db-519b-443e-a897-cb7ae1daa0be | checkpoint | 2.5 - Drainage Bedding Material
7e89b9a1-9590-55ae-b6bc-1fae74e6c142 | note | Reference - VR Cl 701.09
b8cd7032-eaf2-54fd-bb8b-abab0907d622 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
978316ff-2c9f-5423-85ee-bbab860b6372 | textbox | Enter: Teambinder Material Approval number
ca9329aa-b060-5174-acc1-543bcacda99b | note | ○ Attach: bedding material delivery docket
4c06f92b-0ffb-5451-ae94-2b285556e118 | note | Method - Document Review
80c7cf66-bad1-55f0-a51d-bcdca82137b6 | note | Frequency - Prior to Commencement
35676737-3223-5a6c-b585-c6af7aa7aecb | note | Category - HP*
afc6c7db-248d-589d-be17-a9d17be9481c | note | Responsibility - PE/SE
96ba572e-5f24-5a00-9b1b-06e783b1d088 | note | Verifying Documents - Teambinder Material Approval Number, Material Delivery Dockets
f936247c-12e6-5720-b618-22ccd5500b9d | date | Date Completed:
0609428e-c520-4a98-b9a6-22e059ddc33b | checkpoint | 2.6 - Drainage Backfill Material
2964d1ea-e862-58c1-b4b2-f593e0392fdc | note | Reference - VR Cl 701.09, VR Cl 701.19
6d73e428-2b79-5411-b335-675541d1a5ae | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
010d4201-85ee-54b8-b2f6-3752a99ff145 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
639798f1-b5ec-5fd9-9f5d-6d89bae718c1 | textbox | Enter: Teambinder Material Approval number
ac40d008-61ce-54e9-8c3f-0a8bf8433bf4 | note | ○ Attach: backfill material delivery docket
a8d0e51b-1efb-57d6-a3fa-b9c24b50be88 | note | Method - Document Review
9d35195b-59a3-5221-98b2-ff19bfe78e66 | note | Frequency - Prior to Commencement
22713e65-8245-5489-a8a5-3604b67af18d | note | Category - HP*
c8ffdfbe-fa30-5e4f-912e-8a018650e020 | note | Responsibility - PE/SE
e9e95e62-9433-5ed1-a4c8-e42083b78ee5 | note | Verifying Documents - Teambinder Material Approval Number, Material Delivery Dockets
2fd872e7-e725-5c43-be24-ba22ce623552 | date | Date Completed:
bbc07197-cc1e-49b0-8ca6-fec5e8fa59b7 | section | 4. Pre-Construction Activities
91a6e63d-7d69-4161-beff-3b913fac99a0 | checkpoint | 4.1 - Survey Set Out - Pits & Pipes
55c8a636-b339-527c-8a29-ffef592020a0 | note | Reference - IFC Drawings VR Section 701.10
0ded5e2c-e9c5-5490-9f07-1e207551bf07 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
38dd4ce3-9303-5d25-896c-52ede033537d | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
e14d783a-98c6-5d77-9edd-e2625d529ee0 | note | Method - Survey
6512259e-73fa-51b0-8ce8-9bc04ab0190b | note | Frequency - Each Lot
fbd24d2b-5547-5393-bb07-6cad7eae5946 | note | Category - HP*
0bdb636e-7e0b-5f4f-a5b5-f820f59d0a61 | note | Responsibility - SE/PE
a49f745b-3f61-58f7-ae75-0def793a9f3a | note | Verifying Documents - This ITP
c48bfce9-f0c9-57d3-b5c6-81baf72f6c6f | date | Date Completed:
57f4a3fa-8c5b-44c9-88d9-599bd99acbff | section | 5. Construction / Installation Activities
aab0be52-aed6-4a6a-9c39-e9cc42a17bed | checkpoint | 5.12 - Pipes - Trench Excavation
b458a6ea-ecfb-5c0c-a3c4-e2ccc8019255 | note | Reference - IFC Drawings VR Section 701.15
419cd0e5-be87-5222-8504-51df10bd59b3 | note | Acceptance Criteria - Excavation for pipe shall have a horizontal clearance between the pipe and the excavation wall of:
6ccae899-0032-55eb-a708-a8af7831189e | note | ○ > 300mm, < 600mm for RCP
aa938209-d050-5249-898e-e0df5490df89 | note | ○ > 150mm for Flexible Pipe
ed6ef863-fb66-52b3-a640-ffc25a586ea4 | note | — The base of the trench shall be compacted to refusal using mechanical plant.
85622e76-1f74-505b-9ee4-a08ea04c3ce5 | note | Method - Visual inspection, Measure
6b46fde5-b095-509d-a59a-c3dd09bb8346 | note | Frequency - Each Lot
71f3a393-62f9-51ea-bad7-e0d794be8dd5 | note | Category - IP
2d0dd505-3df9-5288-9acd-01b8694a688f | note | Responsibility - SE
cda62f91-3051-547b-b4f3-1ee560c29530 | note | Verifying Documents - This ITP
d96ea54d-46b3-51d6-9789-4fc8d9ad94b4 | date | Date Completed:
71f47218-b879-43d6-b67e-469047642202 | checkpoint | 5.13 - Pipes - Bedding Placement and compaction
0132c4e3-6bd4-5ac4-9af3-0c4799f406d6 | note | Reference - IFC Drawings VR Cl 701.16, VR Cl 701.20(a)
6bc108a5-2c7a-5458-ae24-8987fe059a54 | note | Acceptance Criteria - Bedding material shall be provided and placed in the full width of the trench to the below minimum:
41300f2b-0f19-5693-b8b3-705a31e6af11 | note | ○ > 100mm where D<1500mm
897e0c0b-aef1-5d9e-a472-6b2caa40f92e | note | ○ > 200mmwhwere D≥1500mm
a4b575bd-7837-5f83-994e-8cf2e233ff21 | note | — Bedding material shall be placed and compacted in layers <150mm loose thickness
d48a05cb-70cd-59fa-8e12-0c0d62c40bfd | note | — Bedding shall be compacted to refusal using hand held mechanical equipment and material (Swell ≥ 2.5%) and mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
bb6ea1ae-7d27-51cc-8c7c-498d0035355a | note | Method - Visual inspection, Measure
69a99ecc-8ffa-5092-9836-16b7df67abf6 | note | Frequency - Each Lot
1e41f3de-0704-5162-9e8c-d4f03c021eb1 | note | Category - IP
1997e3e9-63dc-5a7d-8911-fdbf54ecd08a | note | Responsibility - SE
2358f385-1979-5bf7-a633-6031527a5e7d | note | Verifying Documents - This ITP
f77b2739-e561-575d-af49-f3c0eeab940a | date | Date Completed:
b5eac23d-36a7-4a71-b3ad-55b63e03f9af | checkpoint | 5.15 - Pipes - Placement of Pipe - RCP
3e2a1adc-c2fc-545c-b090-e52c4c8b82c9 | note | Reference - IFC Drawings VR Cl 701.17, VR Cl 701.20
0e413cae-ec99-5188-9397-b695854ca885 | note | Acceptance Criteria - Laying of pipes shall not commence until the Contractor has verified that culvert bedding complies with the specified lines and levels and compaction requirements, and pipes are not damaged. Laying of pipes or box culverts shall commence from the downstream end.
767c9dc1-0f09-5786-8810-784171430017 | note | ○ Rebate and socket ends of pipe segments shall be placed facing upstream and be fully entered.
dd70ecd7-e955-5ef2-afde-b3b16bb453eb | note | ○ Gaps between spigot and socket are in accordance with the manufacturers specifications
96875811-f10e-5ea3-b907-a800d413fd0e | note | ○ The lower portion of the pipe shall be in contact with the bedding layer and shaped to accomodate the joint collar along its full length
c60148ee-6b76-54a0-af9b-a9bed0c26ed7 | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position of the rubber ring on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
9084bb26-2a57-51f5-81c6-bef01a60aee6 | note | ○ The spacing for multiple row culverts shall be as shown in Table 701.171
4b526094-79b8-5251-9f60-087fdbb61e08 | note | Method - Visual inspection, Measure
c5721109-1b1f-548d-90bf-72babe079d54 | note | Frequency - Each Lot
8d9b64e9-8fce-5587-83e3-7a23c67d2a7c | note | Category - IP
af1a3b1c-b01b-5f52-a7cc-33d73e8b988a | note | Responsibility - SE
e84eb0c0-b8a9-5699-95a3-8cd576ddd2d6 | note | Verifying Documents - Ferris Rd - IFC Drawings
da4e531e-20e5-555b-80a9-16a44bd2502a | date | Date Completed:
37e93e4e-f329-4d6a-ba37-e7580dc41972 | checkpoint | 5.16 - Pipes - Placement of Pipe - Flexible Pipe
a0ab7fbe-e3bb-5b97-80a1-ce8bf1aa00fc | note | Reference - IFC Drawings VR Cl 701.22
f8195e1f-2cb4-5fc7-9a4b-37f16cd391d3 | note | Acceptance Criteria - All buried flexible pipe sections supplied shall be assembled in accordance with the manufacturers specifications.
6c192a77-69f1-5a3f-a0d5-9afbe9a67e00 | note | ○ Before proceeding to install the next length of pipe, the conformity of the assembled joint shall be verified by checking that the position on the spigot, and the clearance and overlap between the spigot and socket, are within the values specified by the manufacturer.
f824685b-367c-5c8b-bb17-be782a3b008b | note | Method - Visual inspection
07bf551e-0465-55a3-92d3-37ce8480ff22 | note | Frequency - Each Lot
11ea270b-0f98-5b4a-8aab-cfb664daf92f | note | Category - IP
53b4ac58-be06-531e-b4d8-985a7e776fbb | note | Responsibility - SE
5622aa9d-5b5a-559f-a1ae-e1c1ccee665e | note | Verifying Documents - This ITP
428defe2-e32a-585c-89f9-db75489593f4 | date | Date Completed:
cdbe5c2f-6a73-48c8-9a00-fc4bdefab76c | checkpoint | 5.17 - Pipes - Lifting Holes
733ebc34-7324-542e-98cb-5ffc6b87e086 | note | Reference - VR Cl 701.18
56477181-5de6-50fb-8e59-e8ae33e06d8e | note | Acceptance Criteria - Lifting holes shall be plugged off in accordance with the manufacturers specifications after the pipe is installed.
c03e8c69-cf4b-528c-b87e-2cc78c3b5699 | note | Method - Visual inspection
ad3a24cc-2e09-5ffa-bb28-2bd9611cd28b | note | Frequency - Each Lot
6305a7d5-df9d-5c4c-8538-550ab20d45b7 | note | Category - IP
62582de4-b3e1-5679-bfe7-6784db8293f8 | note | Responsibility - SE
0be33e67-e4ab-52a3-80af-8d05f5477088 | note | Verifying Documents - This ITP
1fed0fc5-ae8a-58dd-97ef-26703b4d6938 | date | Date Completed:
482b2fe6-4cfb-4c4c-9e95-4a74d3064202 | checkpoint | 5.18 - Pipes - As-built survey pick-up
fc12bd94-08c3-52a5-b98e-dd00caf51b7c | note | Reference - IFC Drawings VR Cl 710.10
0ae8aa1b-1b89-5667-b840-41c440427af0 | note | Acceptance Criteria - Each run of underground drainage shall be Survey verified prior to backfilling.
761544a6-8e93-5fa4-bebe-6553565bf27f | note | ○ Offset pits to kerb +/- 20mm
7a759f37-3d43-56fb-828a-8ab68093debc | note | ○ Plan location pits not adjacent to kerb +/- 100mm
ebeda83d-d388-5bf2-a63c-176cac7fad3c | note | ○ Invert level of pipes at pits +/- 50mm
561e22ef-b37d-5734-ae68-ec6a72fc0f2f | note | ○ departure from design grade +/- 10mm in 10m, provided minimum grade is not less than 1:250
d8bba40b-1a18-57e8-9fb2-08d5b33b554f | note | Method - Survey
a1f199ce-dd50-5210-82cf-d0ea00940801 | note | Frequency - Each Lot
ae16dee8-e499-5b8e-ad0b-727bf276800e | note | Category - IP
b997f77c-248d-5aec-8308-1eca3e3cc75d | note | Responsibility - SE
ef02e42c-3417-587b-90b9-abf1e3db23b2 | note | Verifying Documents - This ITP
714b896a-0de0-5949-bde0-3b5a02609e23 | date | Date Completed:
65058507-0d68-4afa-a4f9-eaa57b3d6626 | checkpoint | 5.19 - Pipes - Backfill Placement
37628c45-a934-5475-9203-3d2b95777f14 | note | Reference - IFC Drawings VR Cl 701.16
352c0c17-336a-51b2-9dc7-7b2a919fc97a | note | Acceptance Criteria - Backfill material shall be placed the full width of the bedding material and compacted in layers <150mm loose thickness.
85364b9b-48ff-5b61-9c73-e873e7f17deb | note | ○ Filling shall not be placed within 2.0m of the open end of the pipe where a further section is to be placed.
7c177bb6-6bff-53eb-8716-f091c9f0afa0 | note | Method - Visual inspection, Measure
0232a9fd-887c-55a7-b16c-cb2c677e520b | note | Frequency - Each Lot
adc62d62-7a5f-5740-bf43-903f361301d6 | note | Category - IP
4b19fd1b-1775-560b-94bb-8fed5fd4de80 | note | Responsibility - SE
f246dd7a-33fd-5e18-afac-560dbf725955 | note | Verifying Documents - This ITP
5ae87172-0281-5dc4-ad71-1cfd84974244 | date | Date Completed:
20f6ad5d-9061-4df5-8009-459d0f17b47d | checkpoint | 5.2 - Pipes - Backfill Testing
965fa55b-29bd-5df6-b444-248a4396213d | note | Reference - IFC Drawings VR Cl 701.20, VR Cl 701.29
3baf9053-5641-5ed9-bae3-014c327287d5 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding or backfill)
f0de95f7-6964-5739-9915-e795b0331803 | note | ○ Backfill material shall be compacted to a density ratio > 97%. Material which has a swell equal or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
a452b51a-d423-51ef-88cd-38625bf9287b | note | Method - Visual inspection
97917e51-75ae-5722-9795-d9574086d1a6 | note | Frequency - Each Lot
ef70d902-013c-5ee5-857d-e2348d3c959e | note | Category - HP*
3a965b14-556b-5d3b-886b-a6c520e81ebb | note | Responsibility - PE
42ab1f1b-07fc-5d68-b779-1ba168ce8ed8 | note | Verifying Documents - This ITP
75fa0e6f-3287-54ce-b19a-21156fd0b587 | date | Date Completed:
dfa134e0-5162-4e37-ab5e-dedbc7c377f8 | section | 6. Post-construction / Post-installation Activities
49a2e6a4-d47e-4b45-ab2e-1a1dd6ebf540 | checkpoint | 6.1 - Flushing & CCTV
89766feb-8aad-5015-b873-9bbb5f851928 | note | Reference - VR Cl 701.28, VR Cl 701.30
c7935fef-a41c-55cb-991a-8c2b654a3fb9 | note | Acceptance Criteria - All culverts shall be flushed clean from end to end on completion and maintained in proper working order.
ec35586a-4195-5adf-81f5-8bfbe05bb881 | note | ○ All drainage lines constructed shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed and to check for visible signs of defects.
c0cd57c5-d015-59be-9164-1b2955f353e2 | note | ○ Attach: Flushing Record, CCTV Reports
51683d5b-9243-5467-969d-0993c4474599 | note | Method - Record Review
eb3544fb-dc69-5b54-b7bc-e1ec787c9ad3 | note | Frequency - Each lot
17f475f0-fc0c-5378-b749-ed0e885ce2ee | note | Category - HP
c305a9ca-5f6a-50ee-9cfa-2cb27bc44780 | note | Responsibility - SE/PE
db0a568b-71e1-5062-a7d2-00bef4f1dbe0 | note | Verifying Documents - ConQA HP Release, Flushing Record, CCTV Reports
ad87bc85-8b3e-54a5-94b1-1ea1ab9a82c6 | date | Date Completed:
caa40d04-0fd7-4424-b2c7-35da0f03f578 | signoff | AUTHORITY HOLDPOINT
a67a9313-40e6-4ea7-8adf-3f14e4497284 | checkpoint | 6.2 - Compaction and Moisture content tests
c5113816-d3c9-5c15-94de-5e8d0211be72 | note | Reference - VicRoads, Cl 701.20
220e2305-0bf0-599a-8872-ba629d9b6935 | note | Acceptance Criteria - Bedding and backfill shall be assessed for compaction and or moisture in lots. The number of tests per lot shall be three. A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
ef36cd92-018c-5ae1-918d-590a01e0a2ab | note | ○ ATTACH: Compaction and Moisture content test results
be75e38e-c626-5c17-996f-2b82bee3a5e3 | note | Method - Document Review
74d6a308-6382-512c-b851-5f1b707aabb2 | note | Frequency - Each Lot
8e34c836-bb7f-573b-b44a-0d278e3f4ee6 | note | Category - IP
5a0a18c3-77a4-5ae9-b0d4-2c6ed23d9b7e | note | Responsibility - SE/PE
1f3e3044-83ed-51c2-af1e-0a76e2cc6dd3 | note | Verifying Documents - Test Results
a23e8029-d814-5b88-a4a7-ebd9e07bff15 | date | Date Completed:
57cd4151-3ef5-4a0d-b022-f717f2165049 | checkpoint | 6.3 - As Built Survey
ea0e4cdc-7b79-5f77-b021-f31b3d587092 | note | Reference - VR Cl 701.10
c8c9804d-925f-5cd7-814f-50aa54676ed7 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
b396ba54-fffc-57c3-9cef-f22a64ffb054 | note | ○ Attach: As-Built Survey Conformance
e0f9289d-ae70-5bda-bf2c-8f39d9836a12 | note | Method - Document Review
4328013e-8867-5b5d-ae33-86a139249cd6 | note | Frequency - Each lot
e293b548-f5e9-5d56-b1ea-94618410e43c | note | Category - IP
ec694551-ddfa-569a-a6de-f56dd26819d9 | note | Responsibility - SE
f0b4f71b-610f-5a63-bb06-21f00b4d35b5 | note | Verifying Documents - ConQA HP Release, As Built Survey Report
526b1104-5688-508e-8099-5f70f86942dd | date | Date Completed:
4f13b4d2-3847-45d8-b569-50fb22892c58 | checkpoint | 6.4 - Repairs to Damaged Pipes
37e5af02-b19d-5830-8d18-cb38b0ee3d13 | note | Reference - VR Cl 701.31
8dae66f4-8595-554e-84ab-193a1b24c0c0 | note | Acceptance Criteria - Where inspections after backfilling identify any of the following defects they shall be notified as a non-conformance:
5d280daf-2910-54d8-bda6-ec53d1880de9 | note | — cracks wider than 0.5 mm
5dcd806c-8979-589e-aec9-39a908b44f42 | note | — spalling of concrete
cfcd0bf0-32b2-5e15-b872-d98995e675e6 | note | — exposed reinforcement
9f53a995-337b-50ec-bf5a-a59247c14741 | note | — joints that are not fully engaged.
4bc17e69-ee36-5b4c-a53e-2e39305cd135 | note | ○ Any pipes with defects greater than the following limits shall be removed and replaced:
fc05f128-bc3e-5bd2-9f32-cb91b0c9c884 | note | — longitudinal cracks greater than 2 mm
fd36c274-bd63-543e-8f42-332805c68799 | note | — circumferential cracks around the full circumference with width greater than 3 mm or with lateral displacement of the cracked VR Sections exceeding 3 mm
5d7decc5-e39b-5d92-bfc7-490d2333910b | note | — circumferential cracks around part of the circumference with width greater than 4 mm
dbb8ac30-beed-596a-aba1-7daf1cb35de2 | note | — penetrations with area greater than 400 mm2
6b720546-786a-5049-8b53-9462eb668cd5 | note | — pipe joints that are separated.
13a2bac8-12ab-5b3a-bc60-73e56b3c9782 | note | ○ The Superintendent may agree to accept pipes with defects as noted above subject to demonstration that repairs will ensure that pipes will operate effectively for their design life. Consideration will only be given to products and procedures with proven performance and to the following types of treatments:
1a794105-b4a6-5f86-ac1d-f7a5a7958bdb | note | — hot sprayed epoxy coatings for cracks not wider than 4 mm with no lateral displacement
4e3bddd3-7509-5e7d-922a-e99319fb83fe | note | — fibre glass reinforced epoxy sleeving for cracks not wider than 4 mm with lateral displacements up to 3 mm
8d223ec0-10af-5ec3-8a53-933379bc90f2 | note | — spalled concrete, exposed steel reinforcement and penetrations shall be treated as patch repairs and repaired with polymer modified cementitious repair materials in accordance with the requirements of VR Section 689.
586d9578-cac1-529d-9513-3b18067bf5f6 | note | ○ The Contractor shall submit details of proposed rectification treatments including manufacturer’s product specifications and warranties, the area and thickness of repair treatment, detailed repair procedures, and inspection and test plans.
26022542-85dc-5e78-8f83-01d444e7fe52 | note | ○ No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
68d962ce-7f35-5d7f-9fc9-3c2a15dc77dd | note | ○ All repairs shall be inspected using CCTV to verify compliance with the repair specifications.
7f978741-bbdd-53f2-bdb4-350c2881d60c | note | Method - Document Review for Repair Procedure, CCTV Report Review, Visual Inspection
a093ecb4-4437-53f9-a74b-5f8964150adb | note | Frequency - Each lot
04841da3-4e3f-5543-bb2b-26ba654e27b6 | note | Category - HP
80f7f653-2811-5405-b09f-29323f987a5c | note | Responsibility - Nominated Authority
2fbbbf92-e9e3-5289-9347-038d894cdc9c | note | Verifying Documents - ConQA HP Release, Approved Repair Procedure, Post Repair CCTV Report
4479a175-d47d-5da8-8717-1d89f03f1bca | date | Date Completed:
6c3c65db-9bf5-49f0-945d-0d2244922c9e | signoff | AUTHORITY HOLDPOINT
07e7e3f7-98ff-4e0d-8b40-15483e6f81d5 | checkpoint | 6.5 - Non-conformance Report (NCR) Closure
8b0a81e4-f7ce-59d3-8e23-da46cd492e32 | note | Reference - MRPA Quality Management Plan
12d7f5a6-f1a7-50c6-8f0a-dd5f36f4b4f1 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
5390ddd9-7344-54a9-9d59-c5801ffa9e5a | textbox | Enter: TeamBinder NCR number (if applicable)
89f42375-dcfe-5888-a1fc-f054b93409c3 | note | Method - Document Review
53e927d6-693c-5790-bb73-48b5a32f5571 | note | Frequency - Once, prior to closure of this lot / element / Work area
fde9c862-1d59-5311-a043-381bf2b3037b | note | Category - HP*
e2da1fec-44aa-5ee4-a9f4-57613e88b45b | note | Responsibility - PE
82b33e0a-5cce-54d7-ab28-28f983157a65 | note | Verifying Documents - This ITP
bff9ce9c-ce1e-563e-9308-5845f9ef3347 | date | Date Completed:
2215297e-1d3b-4571-9c2c-1bbb412705eb | checkpoint | Final Inspection
89c65d47-d5d0-5660-870a-ebef1183e3a4 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
2ef27598-6cd0-5750-97ce-9519ac5ec416 | textbox | Name:
1ee387a3-9523-5b0d-897f-72d11e241e76 | textbox | Position:
2fa526b5-a95e-5386-9722-2e6ffc2518b5 | textbox | Date Completed:
170b44d8-6010-4340-8641-b2c76c1fe9eb | signoff | Sign ITP
8520561a-555c-4792-94c1-e6d844c5d68b | checklist | ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation Rev 0 | itp | ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation | 2ddad472-4dcd-4618-a552-88fa6fbaa488
ede3fb35-6966-4f90-b3da-7d1fae4615d6 | section | 1. Referenced Documentation
9a0c52ce-d533-4a0b-9287-987a0f67bb5d | checkpoint-no-value | Referenced Documentation
74b31601-d7a0-5132-b047-82cce977a2b4 | note | Document Title: ITP-243-CIV-FRMS-Stormwater Drainage-Pit & Covers Supply & Installation
135f494c-8825-5bd8-b541-a9cb0753bc02 | note | ITP Description: Stormwater Drainage Pit & Cover Installation
5c026432-12f3-5da1-b580-100949bb7c1b | note | Discipline (e.g. CIV/STR/RAIL): Ferris-CIV
748e5ca7-f0ca-5f43-adb2-ecb2d188a2ad | note | Revision Number: 0
90461164-c6b7-5583-acb5-c1c23d016b08 | note | Revision Date: 27/02/2025
21ccb917-084e-5b0e-b886-e827996fe3ac | note | ITP created by: Kamel ALSHOBAKI
1f9fd696-d136-5a9c-89f9-26f2650236a3 | note | ITP approved for use by: Sandy Escalona
a5b2a9e4-9381-55ad-9fe1-f8fea13c0a76 | note | 1.1 - Non Dependent
655d1876-4853-56dc-a81a-feb990c846d2 | note | Reference - VicRoads Section 701 (May 2020)
94d8f7f5-cea8-5511-8764-ca63f13aa263 | note | ○ VicRoads Section 705 (June 2023)
b6324b4d-90ec-57a3-af1a-4226b55c8842 | note | ○ IFC Drawings
4f0a6fba-9b90-5da3-a593-4d64dfa4d791 | note | ○ CHK-001-CIV-Stormwater Drainage Pipes Installation Rev 0
140e2e48-3138-4d09-a6c8-9d4befa4b6cd | section | 2. Preliminaries-Materials
212191b6-0e58-4c59-ac32-1cdd79a37fa4 | checkpoint | 2.2 - Precast Drainage Pit
17887801-f373-5d62-9d4f-4cdf54e901fb | note | Reference - VR Cl 705.04, VR Cl 705.07, VR Cl 705.09
891dc4ca-6f24-5a7a-84e1-d7f1e593f5f2 | note | Acceptance Criteria - Precast steel reinforced concrete drainage pits shall be manufactured, supplied and installed in accordance with VR Section 705, BTN 033, Section 610 and 611.
0e14b709-7c6c-592d-8fe0-8547c6541243 | note | ○ All concrete shall be manufactured to the concrete mix design registered by VicRoads and comply with the requirements of VR Section 705.04 610. Concrete grades shall comply with Table 705.041
c5bed86c-111c-57a4-a01f-0fa1fda02a08 | textbox | Enter: Teambinder Material Approval number
c242d807-f714-52b8-b061-cdee949c5de4 | note | ○ Attach: precast drainage pit delivery docket
3e4f50ba-d4d0-5ff1-8f2f-611557e5f84a | note | Method - Document Review
9e57a769-515c-5c58-be03-115a422037e8 | note | Frequency - Prior to Commencement
a1a3cc82-2335-538c-9526-b8b2e35fe6c6 | note | Category - HP*
80f5dc07-7fde-5bda-b0ea-ecf243941682 | note | Responsibility - PE/SE
b41fe640-3f42-5db4-9eb3-e7f30598d2a8 | note | Verifying Documents - Teambinder Material Approval, Precast drainage pit delivery docket
86259c62-9214-5e91-b943-98d4db742b29 | date | Date Completed:
d74d051f-63f3-42c4-8e0d-ce8a24910289 | checkpoint | 2.5 - Drainage Pit - Step Irons
b8011209-6de6-5c72-8d19-c05108fa488e | note | Reference - VR Cl 705.04, VR Cl 705.12
aa40543e-0b25-56bd-b487-fc1dbd11e3a1 | note | Acceptance Criteria - Step irons shall be manufactured by 13mm steel bar covered with polypropylene plastic in accordance with 705.04
2bea4459-eb58-5d1a-8904-d32207e65c60 | note | ○ Drainage pits greater than 1.0 m deep shall be fitted with step irons in accordance with VR Section 705 and AS 1657.
41320fd7-eda9-5766-846c-e95948f448f2 | textbox | Enter: Teambinder Material Approval number
713beb71-5288-5e68-90c0-c0d9af3bf655 | note | ○ Attach: step irons delivery docket
9bd33fbd-cf26-59b8-b86c-dba91fd5ffac | note | Method - Document Review
10950149-45ce-52bd-9689-86b535386a5c | note | Frequency - Prior to Commencement
9df71360-151c-5bfe-af8a-3743b7b05ec9 | note | Category - HP*
8216d1b6-9ef8-5275-b1d8-3d9d0c17046a | note | Responsibility - PE/SE
298eebb1-3fa0-59df-b849-44198af29147 | note | Verifying Documents - Teambinder Material Approval Number, Step irons delivery docket
58eac3d3-fdb1-5533-8724-2f3af7069fcb | date | Date Completed:
2c954ca5-85c9-4dcf-9c7a-e57cc27872d1 | checkpoint | 2.6 - Drainage Bedding Material
90f99e58-b147-5802-906d-2ef0dbdd5c95 | note | Reference - VR Cl 701.09
1f08aa0c-9a77-55b1-b1f1-9260f0ef4b46 | note | Acceptance Criteria - Bedding Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
4e266e6d-cbbc-5080-b875-5dc6f39372e5 | textbox | Enter: Teambinder Material Approval number
c22f6b5a-8cd9-51c2-b143-e4431038897f | note | ○ Attach: bedding material delivery docket
f91f215a-7c9e-566b-bf56-1493ae43a981 | note | Method - Document Review
d91ded18-b079-552e-952d-15f42c8e6ba9 | note | Frequency - Prior to Commencement
32e2d1f3-5bee-5cd3-a79d-71c87d1abcd0 | note | Category - HP*
1e6e5b97-cd28-5b9a-a88d-98b072bb4300 | note | Responsibility - PE/SE
963fef66-a7cc-534f-98a2-5e3d173b46ea | note | Verifying Documents - Teambinder Material Approval, Bedding Material delivery docket
918f10c5-a9dc-5c86-ba82-cd686e96a9ea | date | Date Completed:
8c611c6a-8415-477e-8205-afeda4da96fd | checkpoint | 2.7 - Drainage Backfill Material
a466865c-f0f4-5f86-a611-852796fbfa6e | note | Reference - VR Cl 701.09, VR Cl 701.19
b764a71e-8083-56b3-b46b-58b00b9ccc2b | note | Acceptance Criteria - Ordinary and Selected Backfill Material shall be free from perishable matter, lumps and conform with the requirements of Table 701.091 and Table 701.092.
dad74492-e9de-50cc-8a1a-566b2beec7d1 | note | ○ Where approved by the Superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised sand in accordance with VR Section 701.19
5ac74f2f-7d70-5060-acdf-ac6614ee6e47 | textbox | Enter: Teambinder Material Approval number
c0c6859a-44d7-5529-b13b-7c4db9b8a7b5 | note | ○ Attach: backfill material delivery docket
223d5caa-f03f-5c3f-94d8-66cebf975747 | note | Method - Document Review
c566dee3-2c5a-59d2-a8d4-5f98f426546f | note | Frequency - Prior to Commencement
2f584b9e-774f-5e43-a451-39135c8b4e12 | note | Category - HP*
fedd831c-0963-56db-ab48-f9866188b9da | note | Responsibility - PE/SE
5a8668d8-ab2f-5fc9-b18d-b59934162641 | note | Verifying Documents - Teambinder Material Approval, Backfill Material delivery docket
a2a8d0ef-b611-5066-a03c-979634d0edd2 | date | Date Completed:
c637385c-7d8c-495d-a44b-621460548ca3 | section | 3. Pre-Construction Activities
be6f0d8e-b7cb-42c1-b0d0-1ef6659a1c43 | checkpoint | 3.1 - Survey Set Out - Pits
8207d7fb-9aec-5970-acd8-a5f39b32e7da | note | Reference - IFC Drawings VR Cl 701.10
8cf8b9b4-b660-52e3-ac74-2df7f5c1e453 | note | Acceptance Criteria - Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
4134f0f1-2214-548f-bb5f-6569e19d7bff | note | ○ Survey activities undertaken to ensure and validate the plan location, height and line of pits and location, invert level, plan of pipes in accordance with design documentation and 701.10
98187bf3-6cd1-5800-88af-609866046098 | note | Method - Survey
141d4cf0-455a-5cb4-b6f8-3dbb1a27521b | note | Frequency - Each Lot
03b064e5-48fb-5457-8719-d8cd77798f6c | note | Category - IP
77343bd2-86a4-596c-b1f2-0120b0995c62 | note | Responsibility - PE
cf56e4af-3da0-5901-9c5f-4a62a7962d74 | note | Verifying Documents - This ITP
8ea2cfcd-76f1-53b8-b5b0-75041d2c80d2 | date | Date Completed:
6d9408fa-8e20-4587-8b90-7bbe226e09a9 | section | 4. Construction / Installation Activities
a7c6e7b0-9644-48d9-8926-3d85d31c404e | checkpoint | 4.1 - Pits - Excavation
dae92a84-594a-5abd-94f2-2d5566821821 | note | Reference - IFC Drawings VR Cl 705.05
5e82061b-61ba-5ccf-b45a-5e4cdf086bb0 | note | Acceptance Criteria - Excavation shall be to the depth indicated on the IFC drawings or as necessary to secure a satisfactory foundation. Precast pits shall have min of 400mm clearance from all external faces of the pit to each face of the excavation.
2bf694d2-2adc-5a77-b87d-e16600c64f97 | note | Method - Visual inspection, Measure
fb60f38c-bfe7-516d-8e07-274f4ce88a61 | note | Frequency - Each Lot
993f80c4-9624-5806-975f-5cb1831f7cc6 | note | Category - IP
901c9057-5e53-5806-8fdc-cf06a0a9a0d0 | note | Responsibility - SE
0c93428e-8fdb-5828-bf6f-a4c8b934d057 | note | Verifying Documents - This ITP
1fff109f-8d94-5cee-9b1a-e4f60eb76764 | date | Date Completed:
4c3ac13d-39e8-42e3-98f0-9a04a26f0c81 | checkpoint | 4.2 - Pits - Placement of Bedding Material
bef1e165-f5bb-5331-8fb2-0c18b0e6135b | note | Reference - IFC Drawings VR Cl 705.05
a6ec6523-7c3f-539d-81e3-75a98f9180b1 | note | Acceptance Criteria - Bedding conforming to to 701.09 shall be supplied, placed and compacted to a thickness:
d618680f-b2b8-570a-b75f-bb53eee87412 | note | ○ > 80mm for clay foundations
410607c2-98e6-50a5-bf3e-f260a5510746 | note | ○ > 150mm for rock foundations
4f364fb4-0f7f-530a-a06f-b1021cc96d4f | note | Method - Visual inspection, Measure
8aa104e7-914a-569e-b0c3-a3cf079771ef | note | Frequency - Each Lot
2f6ad88d-bf93-5150-b301-afb3b288ce92 | note | Category - IP
5c3bfd4d-c51a-5105-92b2-83a243e657d0 | note | Responsibility - SE
fa9beff7-257a-593b-8f6c-b5d5fbb0a874 | note | Verifying Documents - This ITP
37f6c8ad-722e-5e18-a7cb-d95a58eb216d | date | Date Completed:
dc94c6b7-104d-40bb-93e8-656c2e7f2fe3 | checkpoint | 4.3 - Pits - Bedding Testing
07986812-3a92-5546-b93f-db8d5766473f | note | Reference - IFC Drawings VR Cl 701.20
77655029-b5a3-5481-907a-6f2634c7fa11 | note | Acceptance Criteria - Test a minimum of 20% of all lots for each culvert. (Lot = 1 layer of bedding). The number of tests per lot shall be three.
f7475491-92ad-516b-b579-1704d5d1c491 | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material (Swell ≥ 2.5%) shall be mantained at a mean moisture ratio of 92% between the completion of rolling and the placement of overlaying layer
12a52ee4-0693-5354-98d2-a8bcb7c76138 | note | Method - Compaction Test
556d8c39-5ab4-50f4-abd3-f747c128f407 | note | Frequency - Each Lot
00efbf78-abf6-5878-85b3-0882a97196f8 | note | Category - IP
4b54d070-199f-5d18-8278-530c01720356 | note | Responsibility - SE
6ff5553f-b001-5ed8-ad8e-632018bc8426 | note | Verifying Documents - This ITP
92719d20-3e6c-53ee-a6af-e71ed6262f15 | date | Date Completed:
afb5d259-f903-48dd-80e7-e28af1f78ed9 | checkpoint | 4.4 - Pits - Placement of Precast Drainage Pit
71d9784a-5394-565f-a4cf-0ec354b466a5 | note | Reference - IFC Drawings VR Cl 701.10
a7babfa8-a0c8-5bfe-9b6f-811a1a13a4c4 | note | Acceptance Criteria - Survey pick-up to verify:
7dadc736-56f6-5959-abf2-bceacbba658f | note | ○ Plan location of pits, other than offsets to kerb line or barriers, to be +/- 100mm
2269fbf9-487f-5b3b-bf43-11bea17a0c70 | note | ○ Offset of entry pits required to match lines of kerbs or barriers ±20 mm
5db161ca-0822-5dba-ae21-1aca2b8c5014 | note | Method - Visual inspection, Measure
5f153a82-bddb-5dfe-8e28-2d5c05746b9f | note | Frequency - Each Lot
071c6275-b411-516c-90fa-71836e1777a0 | note | Category - IP
2019dcf1-8532-5f5a-802b-6ca06d66f229 | note | Responsibility - SE
7ea03568-9e66-5b92-a766-af31da8ffec8 | note | Verifying Documents - This ITP
062860db-ddde-5d91-a387-7e6e02eb45ae | date | Date Completed:
c6a69718-716f-4c8b-99b6-0f840f7cdaa7 | checkpoint | 4.5 - Pits - Jointing & Drainage Connections
0e78588b-2407-5ba4-86f8-3749c03c2740 | note | Reference - VR Cl 705.11, VR Cl 705.15
7b425cac-0bae-5904-b2b4-a638770c12d1 | note | Acceptance Criteria - All connections to drainage pits shall be neatly made in accordance with VR Section 705.11.
b5e661b7-5621-5dfd-a33f-e8520ad103f2 | note | ○ Openings into drainage pit walls to facilitate drainage connections shall be neatly saw cut to the required size not more than 50mm greater than pipe diameter. Breaking out of holes is not permitted.
983ce284-a4df-559b-bc1d-af07973cd4c9 | note | ○ Drainage pits shall be replaced if circumferential or longitudinal cracking occurs as a result of installing holes or if the hole exceeds the pipe diameter by more than 50 mm.
de96d864-3f2d-59d4-8599-8ecacc7d7e26 | note | ○ Exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion prior to rendering around the pipes.
dfee28ea-02c3-52b9-9f3a-9985b3f592b0 | note | Method - Visual inspection, Measure
ab0d86df-ff14-568a-863a-9a8d1d73509f | note | Frequency - Each Lot
fe4dddd8-b502-5d36-88ce-76f87c5a61c0 | note | Category - IP
7a83c008-17b9-5b48-bead-eeb222d867e2 | note | Responsibility - SE
c297678a-f4cb-579e-809a-0befabfedbe9 | note | Verifying Documents - This ITP
17936af8-e044-568d-861a-88fde773a7a7 | date | Date Completed:
c240e44b-7009-4ba5-afc5-52e8ccb21317 | checkpoint | 4.6 - Pits - Shaping of Floor
f19317dc-51ff-50f5-9a25-ad2c35a3527a | note | Reference - VR Cl 705.13
7be55e3b-017c-5775-b888-b442f5d779c7 | note | Acceptance Criteria - Drainage pit floors shall be smoothly shaped from the inlets to the outlet for a height of one‑third of the diameter of the outlet pipe with cementitious mortar in accordance with VR Clause 610.33
fdbef760-5fc2-59ac-a643-64683a312efc | note | Method - Visual inspection, Measure
c57af704-4584-55e3-b348-43b6665b8000 | note | Frequency - Each Lot
1f3fa2aa-a1e6-5fc5-879d-237209d168fc | note | Category - IP
b611eb48-ba51-5045-81d6-124036aea4fc | note | Responsibility - SE
f00622be-9a18-5efd-b8dd-7c00d807728d | note | Verifying Documents - This ITP
c99ce628-c162-5db9-866c-e95f47ab57ab | date | Date Completed:
7b19ab5c-c384-4408-aafd-4596ca230665 | checkpoint | 4.7 - Pits - Step Irons
fed47166-88d3-57dd-99a4-6b474a12890c | note | Reference - IFC Drawings VR Cl 705.12
e6e8f6c6-a734-5754-b5ab-e6d41bc1d631 | note | Acceptance Criteria - Drainage pits greater than 1.0m deep shall be fitted with step irons in accordance with VR Section 705 and AS 1657. Ladder rungs shall be located directly below the opening in the cover and set into a wall which has no openings, or beside an opening, or accross a corner of a pit. Step rungs do not come within 50mm of the top of the riser. Ladder rungs shall have circular or rounded edges.
e890b294-0c20-5aaa-ac19-ccfe35211dea | note | ○ Step irons of an approved proprietary type shall be installed in accordance with the manufacturer's instructions.
484a1026-ec2f-5204-aa96-ed53ff0ec066 | note | Method - Visual inspection, Measure
82b8c64a-fd23-5c47-9162-2782364ea99a | note | Frequency - Each Lot
873f79e4-8f1c-5558-b3c0-839be7e9141e | note | Category - IP
c35f8bdd-280d-56a7-93e7-cce1374a0f14 | note | Responsibility - SE
2371e924-2373-5504-9b80-7cb92ed7c950 | note | Verifying Documents - This ITP
989bfb68-b1e7-5b24-87b0-46c5255407ba | date | Date Completed:
276ea893-2378-4c2d-8de9-d1c0cb63eacb | checkpoint | 4.8 - Pits - Fitting of Covers
4b35181c-3c59-5115-aee1-832ade01c06e | note | Reference - IFC Drawings VR Cl 705.17
0b163fce-a863-5f59-b7e8-d2cb0ad1a6b6 | note | Acceptance Criteria - Frames for drainage pit covers shall be cast into the top of the drainage pit or bedded on fresh mortar, 5 mm thick, consisting of two parts of sand, one part of cement and sufficient water to produce a mix of suitable consistency.
b54183bd-85cf-551a-a89e-1706c017e103 | note | ○ Height shall be within 10mm of the design level and the line of the cover shall be within 10mm of the design kerb line.
f74e7001-1299-5d37-a7b3-b272ef8b3128 | note | Method - Visual inspection, Measure
395478da-7846-5916-97e8-23282178fbc0 | note | Frequency - Each Lot
5311ce6a-b01e-50a7-bf20-b69f51d1aae7 | note | Category - IP
8f35a0fd-b934-5a4c-84c2-58255b5c121d | note | Responsibility - SE
ce7a0dfa-c38e-5590-b158-c73d678ac92e | note | Verifying Documents - This ITP
abcbd535-24ee-53b3-82c2-dfeaaa0deb1c | date | Date Completed:
4502eb9c-1a63-494f-a0c2-476c101f2209 | checkpoint | 4.9 - Pits - Backfilling Around Drainage Pits
9bc28ce5-9ddd-5efc-a54f-c136c8a0b6b9 | note | Reference - VR Cl 705.18
8005de66-d09c-54f7-8219-9db0206eb1bb | note | Acceptance Criteria - Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
7000e190-db33-5c90-b353-5b0fa9a9cd80 | note | Method - Visual inspection, Measure
87187dbb-4b2f-537d-9003-78a1de10b304 | note | Frequency - Each Lot
e540d030-4d4e-5f5f-a04b-6bb560efab2d | note | Category - IP
ca0db318-47ee-5ce3-b9a3-02b4aa4abdd6 | note | Responsibility - SE
91a8a1b0-b573-5146-8f50-3dcbf8880fc9 | note | Verifying Documents - This ITP
2b68e953-381d-5f61-a4b5-b8374bc93dcd | date | Date Completed:
60652fb5-868f-4f57-b274-cb26e6055eae | section | 5. Post-construction / Post-installation Activities
de2bf341-7ede-4692-ba3a-fe4f9f596672 | checkpoint | 5.1 - As Built Survey
5f4caf1a-5de9-58ca-a400-52405477bbb8 | note | Reference - VR Section 701.10
e72e3330-b6c2-5923-8e65-88695dfa57bd | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate the drainage lines are installed within the tolerances specified in VR Section 701.10
0b0824e0-cc5f-5994-96ac-f63f431b19a1 | note | ○ Attach: As-Built Survey Conformance
88c65183-e5f6-5af4-8d64-d8447c4ed30a | note | Method - Document Review
977b7b2b-5384-562b-b566-7859832a6705 | note | Frequency - Each lot
e7e6f2fd-c6d5-56e6-bc61-c9de75863015 | note | Category - IP
2708d654-2893-5e82-b72c-e77f49c3e2be | note | Responsibility - SE
cddbd329-2481-5a92-bef8-151f5d1069e8 | note | Verifying Documents - As-Built Survey Report
c2b29596-9a63-5b99-b777-9816752e74a9 | date | Date Completed:
3e411f5d-8842-4251-bf5d-b51da4ee82bc | checkpoint | 5.2 - Compaction and Moisture content tests
a6ca3161-a157-5d1f-a4ec-7d4396e8e932 | note | Reference - VR Cl 701.20
ce5aada7-e5d6-5fbd-a58f-3978d25ea559 | note | Acceptance Criteria - Bedding and backfill shall be placed and compacted in layers not exceeding 150mm loose thickness. Bedding and backfill shall be assessed for compaction and or moisture in lots (3 tests per lot). A lot shall consist of one layer of bedding or backfill for a culvert length between adjacent pits or endwalls. Notwithstanding the provisions of Section 173, a minimum of 20% of all lots for each culvert shall be tested.
e2b44f91-0101-5081-9989-2fee71fc0096 | note | ○ ATTACH: Compaction and Moisture content test results:
58e2b2ce-ea92-5972-834a-57a7b780a61f | note | Method - Document Review
7394dc1d-569a-5bc8-bc01-9b9f7a11baa2 | note | Frequency - Each Lot
54a35276-bb73-5a53-9798-c6057a7ff008 | note | Category - IP
7643ecd3-ad09-5e0f-ba80-8907819b4a98 | note | Responsibility - SE/PE
5a0cb60b-b91e-5b95-983b-51a22b5a432e | note | Verifying Documents - Test Results
88e6bbe3-4e73-5bad-ba17-4704090676fd | date | Date Completed:
cf77e68e-b70e-43f8-8dc8-adaf160e9135 | checkpoint | 5.3 - Repairs to Damaged pits
82b217d4-930a-50c7-96df-e535438b3394 | note | Reference - VR Section 705.16
a8bc4b3a-6ff4-5e41-abfc-2dee26c4580c | note | Acceptance Criteria - The method of repair of minor surface imperfections including porous spots, shallow honeycombing, rough areas and blow holes not conforming to the class of surface finish as specified in clause 705.14.
744d6d50-e480-5d43-b60a-4c5897c8f6d4 | note | ○ The cementitious patch repair of other concrete defects shall be in accordance with Section 689.
14ce5f16-f45c-5f51-981a-c1293b5fda13 | note | ○ Epoxy materials shall not be used for the patch repair of concrete.
25888de6-e2f6-5de1-bbdf-74ca91ee7de0 | note | ○ The exposed surface of the repaired area shall be similar in texture and colour to the surrounding concrete.
61d83d7f-0a94-5431-9373-f49bddfb3f33 | note | Method - Document Review for Repair Procedure, Visual Inspection
88bc1cb4-1380-5602-a001-a51868e96691 | note | Frequency - Each lot
77ccf374-b08e-54ca-b01f-f62777d871ff | note | Category - HP*
cd19ac73-e6f7-56a5-a3fe-75cdcb14a041 | note | Responsibility - SE/PE
2ad04291-62c1-527e-82d6-b27cabc8c825 | note | Verifying Documents - ConQA HP Release, Approved Repair Procedure
9e2abce3-78ed-5f4e-b90b-0c82e5699254 | date | Date Completed:
a438eb99-fc49-4c6b-a7c3-9222adabf1b0 | checkpoint | 5.4 - Non-conformance Report (NCR) Closure
718d1d40-b67a-56b1-b9ea-cd743dd4490c | note | Reference - MRPA Quality Management Plan
1b586730-620a-5212-a11f-7d8a6793a5e1 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in Teambinder.
69e86029-a6cf-5c9d-990d-a439c9a9fc8f | textbox | Enter: TeamBinder NCR number (if applicable)
69bd00b9-9c17-5030-963c-318d769ac3f0 | note | Method - Document Review
8f84b2e1-0124-5fe8-9147-61ef6e423655 | note | Frequency - Once, prior to closure of this lot / element / Work area
56688b0c-03cb-51e6-bd58-5f6750ea4475 | note | Category - HP*
b3c4e05b-5687-5b76-ae06-73c35674b184 | note | Responsibility - PE
2a9cd7cc-9200-5f59-881a-18d6c7561065 | note | Verifying Documents - This ITP
7f30fd34-54b2-526d-9422-0323c7d53beb | date | Date Completed:
8b71f96e-a2f3-4479-8b11-cc773e787308 | checkpoint | Final Inspection
124809f1-43b0-5647-a5e3-f99fddd0a0cf | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
01c28a24-8cf1-5217-a79e-6e557e259be3 | textbox | Name:
de23e9ab-f2d3-55b3-b272-dd4d4a7baa7b | textbox | Position:
a19a5347-d708-5a5b-b7f4-a932ed443d01 | textbox | Date Completed:
26dc68f8-d1f2-4268-b490-a7cf98dfbbd7 | signoff | Sign ITP
c92e5470-33e8-4947-8002-c279a3cecbb5 | checklist | ITP-246-CIV-FRMS-Supply & Installaton of Street Lighting (Vic Road) Rev 0 | itp | ITP-246-CIV-FRMS-Supply & Installaton of Street Lighting (Vic Road) | 7a150e2a-5bb4-40ef-a2fd-f00202af8da0
18c49056-bf87-44f6-a47e-d4f102f5136d | section | 1. Referenced Documentation
63d2bc5d-ed9a-4971-b6a7-55944c2b8285 | checkpoint-no-value | Referenced Documentation
ba1621e6-16a5-5d9f-82c6-08aa386cd8f7 | note | Document Title: ITP-246-CIV-Supply & Installaton of Street Lighting(Vic Road)
d889a601-febd-5098-bdd3-83fc56af572a | note | ITP Description: Supply & Installaton of Street Lighting(Vic Road)
32a50669-0d1b-5a3b-88a5-1fa176b1d335 | note | Discipline (e.g. CIV/STR/RAIL): 246-CIV
19fa8879-d01f-56ee-9de3-fb67634317d0 | note | Revision Number: 0
b9aeae28-c180-5037-9ab0-51ac68dd6a22 | note | Revision Date: 25/03/2025
967ed0ba-4a2b-5433-bf50-745c7ea57cf4 | note | ITP created by: Kamel Alshobaki
f5592489-7d21-55bc-b8f4-99d9b8348d84 | note | ITP approved for use by: Pradeep Talasila
ea3bd6a9-6ad9-5056-9051-ceb623a456c2 | note | 1.1 - Non Dependent
8f416353-576b-5c0a-9eba-30294e4182f7 | note | Reference - VicRoads Section 731 June 2017
2e624a00-ad7e-535b-9aec-00a37a914612 | note | 1.2 - Non Dependent
259f797b-3d17-541b-b2f5-8519f3234c90 | note | Reference - VicRoads Section 733 April 2019
eb127ece-bf30-42d8-aa9e-acd0e02f4f80 | section | 2. Preliminaries
30214adb-c432-4755-ae68-1b6938a86b1e | checkpoint | 2.1 - Obtain and review manufacturer documentations for the supply of materials
e53759e8-ea0f-56dd-9dcc-52f1a5fe5861 | note | Reference - Vic road 733.02 AS/NZS 2053, AS/NZS 1345
8eb7c312-6d82-5715-bece-3052d5cb06ea | note | ○ Vic road 731.02 AS/NZS 3000
422229fd-e943-52f3-a956-94950eca00d7 | note | ○ Vic road 630.07 AS 1627.1, AS 1627.4, AS/NZS 1554.1, AS 1214
b1bbe64e-927f-53f5-8540-a3c9ea04eab3 | note | Acceptance Criteria - Materials comply with Vicroad Section 733.02,731.11, 630.07 and relevant specifications.
18fe11fb-465b-52c6-9589-6f8b717f00d0 | note | ○ All materials shall comply with the standards and specifications shown on the drawings. All structural steel, associated components and welding consumables shall be manufactured by companies that hold quality systems certification to AS/NZS ISO 9001.
74c9fc5f-1a4d-5113-9385-087a2118849e | textbox | Enter: Teambinder Material Approval number
92226b43-23e8-5340-b982-8bbe3682b601 | note | Method - Document Review
370f9ca4-c772-5efd-977f-e353a1e5490b | note | Frequency - Per Source
e5b6a0c4-01ca-54b4-b83e-745c9c5a6636 | note | Category - HP*
fa580efb-8373-5274-8831-884e06fd8d49 | note | Responsibility - Nominated Authority
c1b2f6b1-a7e9-5864-ac41-bfc86c855e94 | note | Verifying Documents - ConQA Hold Point Release
2003650d-40e1-5aa7-9cb3-fc26c64a00d4 | date | Date Completed:
7fc6499c-ffec-4967-b755-2d22e3d64248 | checkpoint | 2.2 - Inspect supplied items upon delivery
e9c14218-07f4-5610-9d82-9136ebbf40b1 | note | Reference - QMP
9877c23b-a7f5-567b-9594-91df56ce09b3 | note | Acceptance Criteria - Supplied items are to correct spec, class, size and undamaged
a3a12657-00f9-5511-8810-de04a8ad456f | note | Method - Visual /Site Inspection & Document Review
9fd9f673-f11e-5642-8d59-7836095fe491 | note | Frequency - Per Delivery
9ea6dc24-a149-52dd-9a2f-2990a4163fe7 | note | Category - IP
bc6fdcff-40f6-5b9c-a3c6-7e86eb5eb060 | note | Responsibility - SE/PE/SPE
35aa084f-640d-5ce8-9232-5a00b462457f | note | Verifying Documents - Material Inspection Report
7cb34ba5-e4db-591c-8d68-305c6f58d768 | date | Date Completed:
8ff2f2e2-68a6-4fe2-b07f-0a07c9105ccb | section | 3. Conduit Pit Installation
df8fdcf6-90dc-43f3-b823-c9b1b4d5dd18 | checkpoint | 3.1 - Conduit & pit installation
ce67b44b-2e4b-5ad9-bbaf-24c1b8cd567b | note | Reference - Vic road section 733 April 2019
a9efabcf-78da-583e-982d-a16b53b383b6 | note | Acceptance Criteria - This Item will be completed under the checklist conduit & pit Installation (Road)
ff925896-73ba-539c-8547-fed1b3d6cb18 | note | Method - Document Review
aacbdddf-e46b-5d37-928e-2d92299a4531 | note | Frequency - Per Lot
b8f5c5d6-e016-521c-b124-4557120d51bb | note | Category - IP
2be7a104-299e-5f8f-9a03-d6be5871d533 | note | Responsibility - SE/PE/SPE
d43ae9ef-c1a6-5cf9-a6be-76017570d3cc | note | Verifying Documents - This ITP
43dbb760-86f8-533a-807b-c9fa45b48fed | date | Date Completed:
3cdfbcf5-7c20-4ef3-aab1-72117dc0a7eb | section | 4. Foundation
b2faf3ad-9ff0-4c26-88e8-babe0130a607 | checkpoint | 4.1 - Prepare the plinth foundation(Excavation & levels)
29d7c39a-debb-546e-975e-2bcecf39a9a9 | note | Reference - VicRoads Standard Drawings IFC
43c86328-7078-5626-8fcf-35a06e78c3e4 | note | Acceptance Criteria - Check levels conform to relevant drawing depending on type of pole to be installed.
7b3fdbc8-0a0f-58b2-a965-d2c543242b0d | note | Method - Visual, Survey
b1bedb9c-d48e-55e9-af5f-e84fc83c6599 | note | Frequency - Per Lot
dba537d9-bc29-5461-91bb-623af8ece939 | note | Category - IP
6012b4b6-6da7-5daa-bf0d-32054a94cf2e | note | Responsibility - SE/PE/SPE
adaf8fd5-f1ed-5972-be8e-0ce15b503458 | note | Verifying Documents - This ITP
a7576002-06d5-5949-b505-457c810db92c | date | Date Completed:
76c2ffd6-ce9d-427c-979f-2b2bfc79ac4d | checkpoint | 4.2 - Installation Street lighting pole bases
675c4b3f-be14-529a-bf73-b0b51c6c363c | note | Reference - VicRoads Standard Cl731.11
65636672-29eb-5362-aa3a-8b9ca420c268 | note | ○ VicRoads Standard Cl731.6
fe5c694e-9d84-507c-bbfd-807b43ca5908 | note | ○ VicRoads Spec Cl733.6
ade0a2e4-ff17-57aa-affc-7cc51328f15f | note | Acceptance Criteria - Pits located 1 metre in advance of, and 1 metre off the line of the pole and in accordance to TC-1210,TC 1220 & TC-1230. A two(2)meter of spare length of each cable shall be left coiled in each pit.
9023411a-ab49-5487-bfc1-7b919a1111e1 | note | ○ The slip plane of a slip base pole is to be located 75mm ± 25mm above the surrounding finished surface level
8ee06280-c568-5b15-9e57-1a3d41008dec | note | ○ All poles/luminaries to be individually earthed to the earth cable in the pit
95765835-c377-59fd-aeb3-a43afe3655ed | note | Method - Visual /Site Inspection & Document Review
9909ef4a-a8b4-5981-81c7-73cda09bcb6d | note | Frequency - Per Lot
b59dccbf-04ad-57a9-8c76-0f2e6910a1b6 | note | Category - IP
76fb0056-44d3-5d6b-8a7f-b01ec42cbb3b | note | Responsibility - SE/PE/SPE
070ac958-831a-5323-91a5-0f6d57497aba | note | Verifying Documents - This ITP
b4ce112e-6e80-50f2-ba92-dd34770f7fe0 | date | Date Completed:
66e2aff1-6848-45b4-84f1-696a1606050a | checkpoint | 4.3 - Installation of frangible poles (Slip base and Impact Absorbing)
4c9935f1-0620-5631-ad9d-714dc3b16f8a | note | Reference - VicRoads Specs. Cl 731.06b
f064030a-6f15-567d-a3ff-5e5a1334d253 | note | ○ Requirements
69138f05-2dcc-52b4-91ea-73ac94bd1274 | note | — TC-1065
f1014ae3-ca32-5c8b-a8cc-408e00b8c6fa | note | — TC-1066
d48cf5f1-d56a-5b2b-8aaa-feeecfda6eee | note | — TC-1072
f2f32db1-177f-5df3-b843-7b7cf7f4f2ae | note | — TC-1071
235ee4c1-ec97-581c-8c07-8d89c56ddab5 | note | ○ TCS014 Supply of Frangible street lighting poles
88407556-eadb-565c-bdf0-18d0e889e7cd | note | Acceptance Criteria - The slip plane of a slip base pole is to be located 75mm ± 25mm above the surrounding finished surface level as per VicRoads Standard Drawing TC-1072
a19030b5-f361-5a67-b29b-67ffd7204961 | note | ○ The holding down bolts and nuts on the flange are to be slackened of one at a time and re-tightened using a torque wrench to 40Mn for Main nut (Half Nut) and 90Nm for Lock nut (Full Nut)
80be1ad7-8418-5093-a4f4-b67efab2739a | note | ○ Record torque of each Slip Base pole in report
a7c99da3-be5c-5130-bf91-1e5ca69523d9 | note | ○ Locking nuts to be installed on all hold down bolts
554390c9-758f-5343-9406-2250353b7e9e | note | ○ Lock nuts to be installed on Slip base as per VicRoads Drawing TC-1065: Slip base pole assembly, Ground set mounted and VicRoads Drawing TC-1064a: Impact Absorbing
ff804a2f-e52b-5582-a647-00d18c5c163b | note | Method - Visual /Site Inspection & Document Review
a7b246ac-a124-5724-b56d-6e51c131daff | note | Frequency - Per Lot
f70d7961-aa7b-576a-838c-930f4098f668 | note | Category - IP
a635015c-3e43-5bed-b9cf-e07ba1a06ca3 | note | Responsibility - SE/PE/SPE
7f725fbe-e368-5fec-a18e-f99e595c9147 | note | Verifying Documents - This ITP
c2389e06-73de-54f2-a02e-b37daf961862 | date | Date Completed:
65453db2-eaad-4bfb-8c31-d825ab7bc2b1 | checkpoint | 4.4 - Erection of Street lighting columns
9ddd445e-c24e-50d1-9c10-1ed5686013b7 | note | Reference - VicRoads Standard Drawing TC-1068
bb7f3160-44ba-599c-95d6-7397361859a8 | note | Acceptance Criteria - Installed on rigid columns as per VicRoads Standard Drawing TC-1068: Rigid Street Lighting Pole
b2b1d978-786c-5aa4-ac06-992272cf0bcd | note | Method - Visual /Site Inspection & Document Review
90fcf4b0-c5c3-5bc8-a3af-27d3fc6b6ac2 | note | Frequency - Per Lot
89b00c72-12c0-56be-86ec-e45adf36d539 | note | Category - IP
1d798826-10f6-5aa8-a00a-ca0c1a7ef9ab | note | Responsibility - SE/PE/SPE
ca643f98-aa60-5930-8614-731b0d1e0619 | note | Verifying Documents - This ITP
c72c55a0-8d8d-5338-a6a5-03d2cdb9f2a4 | date | Date Completed:
5537245c-c359-4d9e-a843-25c448dd5951 | checkpoint | 4.5 - Assembly of outreaches and luminaires
2aa0ea2d-3d37-5199-b992-24aa5925412c | note | Reference - VicRoads Specs. Table 731.061
3c77bbbb-cfd3-505f-9920-56a69cd1dad4 | note | ○ Requirements TCS065
0bb28449-5c91-525b-bb59-280cb4e90b5d | note | Acceptance Criteria - Outreach bracket to be installed to the pole spigot using the clamping bolt assemble
a6d99e7e-4cd2-5035-bf79-929773af2a53 | note | ○ Bracket and luminaire to align at right angles to vehicle path on road
5c12050d-42fa-51c0-8f0a-36c1576b2d51 | note | ○ Luminaire orientation to comply with Table 731.061 from VicRoads Standard, Section 731 - Road Lighting Installation
7d06b1f6-b4b1-5011-a312-c4b7bad38605 | note | ○ Luminaires to conform to TCS 065 - Supply of LED Road Lighting Luminaires
e81976a6-eb74-5bb9-98f1-3b3d244f2f67 | note | ○ Luminaires shall be supplied with the PE cell bypassed or deactivated
88e812e4-c34f-52ce-a8c1-d6d247814001 | note | Method -
bb984953-7449-536d-ac65-123144d675d0 | note | Frequency - Per Lot
58e0ee38-9486-5b7d-a66a-8b49629cdd90 | note | Category - IP
1209ffa3-9449-5666-a100-b9ed82c16f0c | note | Responsibility - SE/PE/SPE
4bf7894c-2f22-5bd6-ba6f-fa4f005f4aba | note | Verifying Documents - This ITP
b37e9081-c32a-5b07-85bf-441857ca8362 | date | Date Completed:
06891a58-72eb-4f71-a42f-1076ad5d9bb5 | checkpoint | 4.6 - Installation of lighting distribution cabinet
273063cd-f34a-5851-b09b-c6a1cf165fdc | note | Reference - VicRoads Specs Cl.731.11 IFC Drawing
71574f5a-ee01-5ec3-a73a-cbfe9a565220 | note | Acceptance Criteria - The lighting distribution cabinets shall be supplied and installed in accordance with VicRoads Specification TCS 043 - Specification for Distribution Box for Road Lighting Power Supply.
d4e7a523-62a9-5857-a11c-e7153a76a4ba | note | ○ The foundation of the distribution cabinet shall be installed as specified in VicRoads Standard Drawing TC-1062.
c780b607-c4da-57b1-b60e-dd18f901816e | note | ○ Distribution cabinets shall be located not less than 5 metres from any carriageway and where possible beyond the clear zone for the particular road. For any distribution cabinet within the clear zone, the Contractor shall provide traffic barriers to protect the distribution
cf04ec0b-47b0-5f0f-b499-c75b47750ec8 | note | Method - Visual
41a2a25d-f107-50a9-b323-88cec923d0b8 | note | Frequency - Per lot
96eb1405-8502-5ce9-94b3-eac5e874a5d2 | note | Category - IP
e9f12887-5d56-50a9-b3f7-8b51736a098b | note | Responsibility - SE/PE/SPE
ed5431b2-2105-5a77-9882-0ca130667347 | note | Verifying Documents - This ITP
9e72b142-8971-56ce-ae53-60070409bddb | date | Date Completed:
941797e5-7488-4194-8d50-5c1a42b41f21 | checkpoint | 4.7 - Installation of cabling
c43cb06d-ea32-5333-a276-1056407eaabd | note | Reference - VicRoads Specs. Cl.731.11
538fae7a-2cb3-5931-abd2-66a8547bd0bf | note | Acceptance Criteria - All electrical cabling to be in accordance with the requirements of AS/NZS 3000: (Australian/New Zealand Wiring Rules)
5e35ca9b-27ff-56b6-89e4-0e4738b82038 | note | ○ Each pole to be cables from the pole circuit breaker
6760a72d-a8df-5e5f-ba30-205e804c5f77 | note | ○ All electrical cable joints to be water proof
f6e1930f-ab7d-551c-9188-e34fcf8b8324 | note | ○ JUP, JUMA or slip base pole: Cable to be supported by nylon cord or steel catenary. Cable to be attached the support wire with cable ties, no less then intervals of 4m
e5536c01-2d42-58a4-968d-a8ff54c67829 | note | ○ IA pole: Cable to be supplied through flexible conduit fitted inside the pole from cable termination access door to pole spigot.
5438e479-af9c-50e3-ab44-416e2a295aa5 | note | ○ Cable for trunk electricity supply from “point of supply” to distribution box to be not less than 16mm square 4 core, three phase copper XPLE cable
600fe2bf-dae9-55f6-8f30-467205943ea3 | note | Method - Visual & Document Review
71183de5-bd1a-5161-8281-a957df08015c | note | Frequency - Per Lot
4406e474-3999-51c7-b430-91b9afba5c84 | note | Category - IP
29072762-657d-5a21-8adf-1a135e874b37 | note | Responsibility - SE/PE/SPE
553c51a0-21d1-5d5e-9dc5-3f956541217f | note | Verifying Documents - Test Certificate, This ITP
63c66762-a423-572d-9c30-952000646a0a | date | Date Completed:
5d4671de-330b-4ced-b287-fe04a915a424 | checkpoint | 4.8 - Labelling of Assets
c1541079-70b5-509e-82fb-b0517e84f2aa | note | Reference - VicRoads Specs. Cl.731.12
07710747-9500-5a47-943b-14fcde8dc2e0 | note | Acceptance Criteria - Labels fixed to poles as per VicRoads Section 731.12
d1243843-6e8a-56be-a1cc-f56ede3678ea | note | Method - Visual /Site Inspection & Document Review
66a2b7aa-54db-592b-810b-251cdc24400c | note | Frequency - Per Lot
cedef795-c3f2-5840-9c23-7678d2f351a8 | note | Category - IP
b80ed199-034f-521a-ac52-da647af0d1d1 | note | Responsibility - SE/PE/SPE
d2bd28ca-3cfd-5cee-b6bf-f5236c94fba0 | note | Verifying Documents - This ITP
bee94a0f-c1c5-544f-8dfa-c1e3132090a9 | date | Date Completed:
5ae1ac78-8821-42cb-a8b4-245c3bf4b2b8 | section | 5. Completion
60582385-5640-4113-865e-d108c4c30a41 | checkpoint | 5.1 - Commissioning & testing(if Applicable)
ca60e5bd-777c-56c8-881d-511363ed0ab2 | note | Reference - VicRoads Specs. Cl.731.16a & c
5b18cce5-4eba-57c5-b577-520e32f3215e | note | Acceptance Criteria - Upon final acceptance, the Contractor shall switch on the lighting installation at the distribution cabinet in automatic mode, and record the time, date and meter reading for contractual, warranty and power supply purposes and supply this record to the Superintendent within 48 hours
fec76ee7-a506-5ab4-98e3-656957ed610b | note | Method - Commissioning & testing
43892e17-4ed0-5a0a-a43c-51ef596e3ec4 | note | Frequency - Upon completion of each section
c68b5215-5a27-5d6b-8524-572716b7c58d | note | Category - HP*
930d4f86-9289-55a2-b2cb-9be54306e30f | note | Responsibility - SE/PE/SPE, Services Engineer
78a68b0f-ba4d-5ce0-9fa5-e88a8c4561ce | note | Verifying Documents - ConQA Hold Point Release
2d1fb885-585e-5b3d-913e-bbe8048431a6 | date | Date Completed:
04271ed9-4f9b-46b5-9fc3-ab110c9d0fb2 | checkpoint | 5.2 - As-Constructed Plans
14eeea4a-3600-5b57-b62b-1c64211782c4 | note | Reference - VicRoads Specs. Cl.731.16d
2bf85186-0489-51ee-847d-b72494018fbe | note | Acceptance Criteria - The Contractor shall supply to the Superintendent two copies of ‘As-Constructed’ plans along with a USB drive or other approved storage medium containing the CADD drawing files, and the same shall be supplied by the Contractor to the local distribution company if appropriate.
7b28ffb7-07a1-58d5-9666-0edf5bf9b40b | note | Method - Document Review
8d7d48ba-2b56-5db9-8b56-4c4a3ec22d6b | note | Frequency - Upon completion/ Work area
a3b43d45-91a7-597c-8130-9ca70ed5fb22 | note | Category - AP
fe292ffa-195c-554f-8fef-3fad8e2b5c46 | note | Responsibility - SE/PE/SPE
edb85f40-abb9-5821-b6bc-bf0408ca3475 | note | Verifying Documents - ConQA Hold Point Release
ed6e3361-a8b9-5e67-8606-979cbd5b67ab | date | Date Completed:
1c6049d8-5d90-46b3-86e1-ccd7bd1914de | checkpoint | 5.3 - Non-conformance Report (NCR) Closure
ea37ca8a-4a37-55e2-b84b-c063da2454c5 | note | Reference - MRPA Quality Management Plan
95c2774d-4de1-5f3b-9864-0eaa60783e7e | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
54597edd-665e-5d96-aef9-9a87ff5545d9 | note | Method - Document Review
29580f64-8ec6-5200-a515-a59a0674c431 | note | Frequency - Once, prior to closure of this lot / element / Work area
2cf51c38-a522-5adf-9164-de0ecf58f8b8 | note | Category - HP*
f8cd1078-5078-505c-97a8-84ca689175f2 | note | Responsibility - SE/PE/SPE
f50b2a9b-f2eb-5908-89e2-ceadd2a3e473 | note | Verifying Documents - This ITP
364023d3-44c2-53f5-a3a5-c4bf8bcfb903 | date | Date Completed:
e3197bdf-ede4-4a81-9385-51f46af97d72 | checkpoint | Final Inspection
ef000ccf-24d9-583b-87e9-28a63f11e84d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5e7f6b8a-0848-525f-8e3e-b391e619c23e | textbox | Name:
ecd06840-c0de-5fe5-aa12-412c6b42d12a | textbox | Position:
9f1b62a2-fdd3-5beb-b6ee-a03049617c54 | textbox | Date Completed:
72f10bfe-566d-446a-9a6d-8a307d4deb1e | signoff | Sign ITP
dd5fb8ef-5729-439e-bf5d-330373c591ed | checklist | ITP-247-CIV-FRMS-Traffic Signals - Commission (Supply and Install) Rev 0 | itp | ITP-247-CIV-FRMS-Traffic Signals - Commission (Supply and Install) | f967406d-0dc9-45ed-a10e-bd3c7762b7e7
7786d2cd-dc93-4024-a9f9-597738cb17f4 | section | 1. Referenced Documentation
f3074cad-ac51-4714-9e21-8ed4c99ca9bd | checkpoint-no-value | Referenced Documentation
476b5fb9-2ca9-5312-b9b2-11aceb3bd4d7 | note | Document Title: ITP-247-CIV Traffic Signals - Commission (Supply and Install)
02f86e4b-99d9-5529-b609-607295d31f75 | note | ITP Description: Traffic Signals - Commission (Supply and Install)
b9a37b9a-8b2a-5c1b-9b3c-e432c745a07f | note | Discipline (e.g. CIV/STR/RAIL): 247-CIV
0f859ebc-a5b5-5328-95dd-2eb0a4a2d4b0 | note | Revision Number: 0
b3da4f85-e358-575b-9982-ee7817299606 | note | Revision Date: 28/03/2025
035b338e-aede-597e-83f1-b2a2e9addeb5 | note | ITP created by: Kamel Alshobaki
1d018c11-20fa-5a9c-b90f-f77ecf91c6f9 | note | ITP approved for use by: Pradeep Talasila
496a0435-3125-58bc-a21d-e8afac903a05 | note | 1.1 - Non Dependent
8f0833a5-1638-58e7-b128-c0fa808c121e | note | Reference - VicRoads Section 730 October 2013
8af7041c-ef7c-5e6d-a5c7-8e072e35c3ef | note | 1.2 - Non Dependent
f42f8e03-a22e-5ad4-8d35-7204142c5540 | note | Reference - AS3000
401a52ea-074c-4c37-96db-229e648eb5b8 | section | 2. Signalling Electrical System
d3c8a3bb-0a5b-4d0b-af94-f088f6f87b7b | checkpoint | 2.1 - Point of Supply
716f6a7b-d56d-5c38-a1eb-8943d2e4b8d5 | note | Reference - Section 730.14 (a), SD TC-1207
087347d6-a62b-59e2-b870-e8807a2630ad | note | Acceptance Criteria - The Contractor shall arrange for the installation of the point of supply with the local power distribution company, at the location approved at the pre-installation meeting
6be3a0db-b0dd-54e9-8646-303838112b9e | note | ○ The point of supply shall be installed in accordance with SD TC-1206 and arranged with the local power distribution company to meet the specific requirements.
724f4386-35fd-57d7-917c-4a0f2d9825d1 | note | Method - Review
03faf906-aeab-5c20-be12-142521e8ba06 | note | Frequency - Per item
d836f641-4853-5059-86cb-75c6b27f29da | note | Category - IP
f53758c5-b8c8-5c40-8cf2-094b1cc2ebf2 | note | Responsibility - SE/Supervisor
14c4c971-a57e-5a56-8ea0-9a39e657a303 | note | Verifying Documents - This ITP
ac3a37fe-f4b5-58ba-b66e-60e911e92995 | date | Date Completed:
92cba62f-03da-4708-af01-218644453cea | checkpoint | 2.2 - Communications Line
d32f9986-bad9-51f3-b358-7cc98ab26e4f | note | Reference - Section 730.14 (b), SD TC-1207
e8089913-fcfb-50fb-9cca-6c76b9065c33 | note | Acceptance Criteria - A communications conduit along with a two pair telecommunications cable is to be installed from the signal controller to the nearest sutable communication supplier's pit as per SD TC-1207
c6dc0d43-311a-5e03-900e-c57737a33579 | note | Method - Visual
ea24952b-8ca5-51d9-a104-872b8bf84cd5 | note | Frequency - Per item
d368c42e-0141-578a-bfa9-13970d9e6b3f | note | Category - IP
9845d2b9-e95b-5db2-a66c-ab37335cc998 | note | Responsibility - SE/Supervisor
ba72c349-37bd-5e5d-a03f-e2d2f66e445f | note | Verifying Documents - This ITP
6af8c951-0dac-589d-a22c-149f3314654b | date | Date Completed:
a31ef9a6-87f6-4bf5-9534-72db0cbd9736 | checkpoint | 2.3 - Cable Installation
8c39dc6a-e751-5f76-8cfb-e4bfeb403e93 | note | Reference - Section 730.14 (c)
822eee70-9137-56ad-9f0c-3aa81b9f6993 | note | Acceptance Criteria - Site cabling is to be completed in accordance with Section 730.14 (c), ensuring all cables are installed with no damage to sheathing and insulation, restrained at the point of termination (top of pedestal and MA/JUP access points) to ensure minimal stress on terminations, as well as sufficient cable provided to reach 1.5m above the signal controller base
33768cd0-4b91-51f8-ab10-73dad59b8f79 | note | Method - Visual
26e067d2-5517-535a-829b-be720a9d6363 | note | Frequency - Per cable
06ef4cf4-04f2-582d-b31a-b1ebf52e95fb | note | Category - IP
6fdda770-f48f-5957-9c46-8031c8a2a674 | note | Responsibility - SE/Supervisor
260f284e-2be8-5492-a62d-7bea34694df5 | note | Verifying Documents - This ITP
600e55c4-1e76-5922-a309-ca30cb84c009 | date | Date Completed:
9505429e-48c3-408a-8b2b-c0d41ccf80b8 | checkpoint | 2.4 - Cable Sizes and Wiring
a1d3749a-04f9-5568-ad54-d442124bcd71 | note | Reference - Section 730.14 (d)
b934af9b-75c0-5473-904d-7c5357449a44 | note | Acceptance Criteria - 51 core cable is to be used at intersection traffic signals and its sequencial assemblies. 29 (dual carriageway) or 19 (single carriageway) core cable is to be used at pedestrian operated signals and its sequencial assemblies
5c4f0ea6-b75f-511f-bad9-4a777d11f856 | note | Method - Visual
94c64aa8-a12f-5aac-ad90-2a93d195106e | note | Frequency - Per cable
2c8cccbd-885a-5a64-8563-a21bfcde58e3 | note | Category - IP
dee1552f-a866-52c7-a66e-c780163d6cea | note | Responsibility - SE/Supervisor
f5385b93-e4ed-5085-aa77-cfed000ec6ab | note | Verifying Documents - This ITP
b2f18709-4fba-51e3-b114-ef0ee6f07bb6 | date | Date Completed:
c0540bd1-87c4-4875-9c50-b2798734819e | checkpoint | 2.5 - Pedestrian push button terminations
81724f62-f303-50de-a3aa-e53c8ff3fa8c | note | Reference - Section 730.14 (e) Table 730.141
0ad78798-0f99-5841-906e-8afda9de5964 | note | Acceptance Criteria - Pedestrian push button detectors are to be connected by 5 core cable and terminated at the required locations.
45549edc-7390-50a2-b826-7c18f8b8177a | note | Method - Visual
cfefdeca-49dd-5f09-920c-ec4ba78f0718 | note | Frequency - Per cable
4e8f4cad-e69b-502d-bc0d-954390f1b14e | note | Category - IP
04d4522f-0976-521d-aba4-c1e7eb27bd31 | note | Responsibility - SE/Supervisor
c9c46c4e-39a3-52bf-b19e-e6d1bb4527f8 | note | Verifying Documents - This ITP
94a91393-e01d-5db0-858f-38e0e57e05fa | date | Date Completed:
9e0132eb-8907-4aee-97da-4931745f7924 | checkpoint | 2.6 - Connecting of traffic signal controller
878335a3-1a7a-555b-8878-5864ad06c45a | note | Reference - Section 730.14 (f)
fd01f5db-bf30-518c-93a2-96a30382a8a3 | note | Acceptance Criteria - Contractor shall install a 3 core supply cable in a 50mm conduit between the supply point and signal controller base. 1.5m of supply cable shall be coiled in the pit closest to the controller base.
0e296785-c0ac-57ee-97a1-13827f27b6a6 | note | Method - Visual
29d5647c-228e-5147-a153-879b01f4f1fd | note | Frequency - Per cable
4faafb8e-3cf1-53c2-a79a-ceadd57971f5 | note | Category - IP
2514999e-09f6-5f4c-af93-7c9c718ba982 | note | Responsibility - SE/Supervisor
fe095af5-3c03-58a8-ab13-217986933fb8 | note | Verifying Documents - This ITP
f7567897-061b-5eec-8739-e83c32d995f3 | date | Date Completed:
5b8bb768-11c6-4ecb-b445-c4a39c186070 | checkpoint | 2.7 - Testing of Electrical Works
74c3253a-c0a2-529f-ba1b-29b07426a61c | note | Reference - Section 730.14 (l), AS3000 Cl 8.3.3
33aeaa61-db48-5434-9a1a-f842b648ba16 | note | Acceptance Criteria - The following tests are to be carried out prior to the installation of lanterns and hardware:
6c060ffd-d7c5-5b41-b2b7-1a4c699ae776 | note | — continuity of all active, neutral and ELV conductors as well as earthing system.
31bcd23d-3e69-526b-989b-52d5d6a9b232 | note | ○ Attach: Electrical Test Report
ff9ce397-9520-5e70-8f7d-e184b12fe84c | note | ○ Following the installation of all lanterns and hardware, the Contractor shall carry out a flash test.
5bed596b-3759-5e4a-ae9b-0d8ee1bb0233 | note | Method - Records
5db33fb2-1b80-56dc-a8de-6e97eabe52c7 | note | Frequency - Per installation
5c9e14f5-9634-5554-a2f2-6161787a7372 | note | Category - HP*
e18c6ec6-9dd6-5551-8ece-7dbaa7386046 | note | Responsibility - SE/Supervisor
8c027bbb-f772-5703-ae39-28a9d4803561 | note | Verifying Documents - Electrical Test Report
245cdb9b-7691-5b87-9c91-45cce5e7121c | date | Date Completed:
60815520-91e6-4de6-8588-1a292df6f43d | section | 3. Detector Loop Installation
459197ab-fc0e-47fa-9ed7-5ac0f3610330 | checkpoint | 3.1 - Cutting of detector loops
4c778cf9-5c0d-52c6-99aa-c123e3dedded | note | Reference - Section 730.14 (j), VicRoads TCS 054
e386bb04-0947-58a5-9272-0c237717ec8d | note | Acceptance Criteria - Detector loops are to be cut as per the locations shown on the design drawings to the TCS 054 specification.
eb38dfae-a472-5ba7-bc5e-9cf6f5f7e6fc | note | Method - Visual
d14ac714-d4fa-533f-982a-689979619dcf | note | Frequency - Per loop
4431a35a-ba1c-54c8-aed6-aa2da22a1c53 | note | Category - IP
4346d10f-0db6-5243-9a6a-d9af8a881f2e | note | Responsibility - SE/Supervisor
8915a25e-3011-5296-ba22-1ebfa40e0f00 | note | Verifying Documents - This ITP
dc639f4b-6fee-50d4-ad81-9ac3f699eea1 | date | Date Completed:
ac5f5787-289b-4cc6-9e86-8fd4e5caa9cd | checkpoint | 3.2 - Installation of detector feeder cables
d2b3e08e-9793-513e-a865-21ca0c30a051 | note | Reference - Section 730.14 (g), SD TC-1300
84be0c18-80d7-50e8-9ec3-240240aa8f22 | note | Acceptance Criteria - Detector feeder cables are to be installed to connect detector loops to the traffic signal controller. Installation is as follows:
8228e338-4c86-54ff-aa25-d814c4cd0451 | note | ○ Install 1 cable per loop and each cable pair shall be clearly and durably marked at both ends to enable positive identification
4ed2d0e3-8048-51ab-a1a0-1329a9f4fafd | note | ○ Connection of the detector loop cables to the detector feeder cables by soldering
8e14be44-4739-5922-b388-db3bc98a73a8 | note | ○ 4 wires for each loop (as per SD TC-1300) shall be tied together in a knot close to the conduit end
3fdfd2bd-0897-5817-a0da-8d2ebfebafec | note | ○ Terminations (joined or unjoined) shall be seperately insulated and sealed against the ingress of moisture with heat shrink
56436780-2eff-562b-bbba-a0861ac93541 | note | ○ Detector cables to have sufficient length to allow 1.5m to be coiled in the pit and 1.5m to reach the top of the controller base
0a519929-f696-57dc-aa85-771ea250251a | note | ○ Cable diagram shall be provided once complete and visible to the controller installation contractor detailing the loop cable/feeder cable connections.
643971c3-e8e4-5c8f-88e8-7e404a108f9f | note | Method - Visual
68690748-fbf9-599f-87d6-fb797339b020 | note | Frequency - Per loop
db383d7c-223f-5576-ae7a-8303eaa1294c | note | Category - IP
38699ee4-66b5-5d12-91ef-f918eeebf8c8 | note | Responsibility - SE/Supervisor
d3f79c17-0ff3-5304-b803-20c870daeed2 | note | Verifying Documents - Sign ITP
ea210598-974e-5581-8730-62ccb2ab0555 | date | Date Completed:
c09e41b3-5b3b-444e-83a5-d9f89d1b5d70 | checkpoint | 3.3 - Cabling of Large Sites
538d50e3-d708-5cb7-844c-e61d6b3a17c0 | note | Reference - Section 730.14 (i)
5dd96c3d-e278-5a92-864b-3e67b3f7b010 | note | Acceptance Criteria - For large signal installations where the standard allocation of cores as specified in SD TC-1204 cannot readily be adopted, MRPA shall draw up a proposed cabling scheme for approval.
484ba14f-eacd-58de-9a07-d158fec3abdf | note | ○ Attach: Proposed Cabling Scheme Checklst
af3efd8a-c92b-59a0-abb8-25244e02c6d4 | note | Method - Records
810e272b-e69c-5719-b9b4-f4a43e13807c | note | Frequency - Per installation
4dff0e9d-e1a8-551d-a8d5-c60b422bf492 | note | Category - HP*
897b12e8-7818-5502-8c60-14fb1784c746 | note | Responsibility - SE/PE, NA
40054e5c-dd87-5e8c-9ae2-d4aef46a7d63 | note | Verifying Documents - Attach Proposed Cabling Scheme Checklist
3eae386a-c122-5bcd-be57-ee2a80875e24 | date | Date Completed:
401d6de7-b324-4f07-b62c-f4e3d71b3648 | section | 4. Pre-Commissioning
e236e3c8-80cc-4230-9478-1f99138b232d | checkpoint | 4.1 - Pre-Commisioning Site Inspection
e63f2059-2722-5b70-8ee8-68235fe2ac78 | note | Reference - Section 730.16 (a)
2a570319-a56e-5a31-a564-45e3acc9dfb3 | note | Acceptance Criteria - Inspection to be carried out between the relevant parties upon completion of the installation works.
1d3526d8-e92b-52dd-a914-7af762201d22 | note | ○ The Contractor is to notify NA and VR of the inspection.
d69dd369-2aec-5f16-aa38-d204975ed63c | note | Method - Records
514cd1a1-b60f-5aa5-b7fe-6869b0d86307 | note | Frequency - Per installation
37464533-8c3b-58fa-ba81-11670d2919d2 | note | Category - IP
09ce5914-7d40-500c-8b1f-780557a53da7 | note | Responsibility - P/E, NA, Supervisor, VR
c6b49c42-7fe4-51cd-80a0-93d328936079 | note | Verifying Documents - Attach Pre-Commissioning Installation Report
8fbd8561-cfb5-51f4-ba1e-63c1155841be | date | Date Completed:
4c85ed22-8a75-45b6-89fc-1b3d92df3cae | checkpoint | 4.2 - Provision of power
4344c56b-1e8d-5200-8d69-e22944625be9 | note | Reference - Section 730.16 (b)
47c4038e-e66d-55c0-b0fc-671c57624489 | note | Acceptance Criteria - Obtain connection of mains supply by submitting all necessary paperwork and payment of fees.
38cc1cf1-0857-5d88-920e-d8edaedfac06 | note | Method - Records
f551c1b8-4d90-5e6c-9ce6-8a5be72d47de | note | Frequency - Per installation
8411573a-8e7c-5688-be01-7f10fd2032db | note | Category - IP
3014c7e6-edb9-5a4b-a7b4-5c16557486a4 | note | Responsibility - PE, Supervisor
acad5d97-e5aa-55d1-a227-f50f69343f00 | note | Verifying Documents - Sign ITP
9adf46c1-7e32-5040-aed5-f8d159985b46 | date | Date Completed:
fd2f2317-13cc-48ec-8462-0255825951bb | checkpoint | 4.3 - Traffic Controller Installation
dfda7abf-589d-5554-9ddc-a9a22029c65b | note | Reference - Section 730.16 (c)
d493dac5-5693-5191-bbb1-1811598e2d95 | note | Acceptance Criteria - Contractor to notify VR when the site is completed, tested and ready for the traffic signal controller to be installed.
9414cb91-5328-5970-b2e5-4688ea72d42c | note | ○ Traffic signal controller to be installed by controller supplier or authorised representative.
5e9d57ca-4d19-5ac6-9977-b9de79a1990e | note | ○ Contractor shall arrange issuing the Certificate of Electrical Safety and the necessary paperwork to obtain connection.
6aa2d9e7-d84d-5f48-b027-ec0495ee4202 | note | Method - Records
09f5d4f4-cd9d-5496-9e71-1bbdaa62211c | note | Frequency - Per installation
6eb0444a-747a-570a-9b5a-2da2c25a34bb | note | Category - IP
72227423-6642-5871-953b-f723c2b49df6 | note | Responsibility - PE, Supervisor
37ab27af-8ed6-5c04-a4e9-0c290bdb4a58 | note | Verifying Documents - Attached Certificate of Electrical Safety
a16f543d-9e95-5369-aec8-51e028bc9b44 | date | Date Completed:
033ae11a-0190-4533-beee-13cd03cf140d | section | 5. Completion of Site Works and Commissioning
7faa8f7a-c8d5-4f1e-9196-d0c63fe008c3 | checkpoint | 5.1 - Switch-On
2854dc18-af95-5a55-b0d0-9c148f53a0d4 | note | Reference - Section 730.17 (a)
a4f8a570-9187-56ea-9894-7b5ed97ee4fe | note | Acceptance Criteria - Prior to switching the signals on, a 'flash test' of the installation shall be carried out to ensure that each lantern is connected to the correct cable core. The flash test shall be witnessed by the Nominated Authority and VR and confirmed as acceptable.
9ff99456-4f4a-5345-a985-2fa1c0c8a985 | note | ○ The controller supplier is to record the relevant details required for the Electrical Test Report.
6e428a3a-eefd-576e-bd42-6645e2d765dd | note | Method - Review
a2a310eb-01a0-5723-9493-b0668417b87b | note | Frequency - Per lantern
1b3dc3d0-a641-5137-bcb9-8a066ce90953 | note | Category - HP*
922df3e6-22a6-56e3-8596-4143e1c4250d | note | Responsibility - PE, NA, VR, Supervisor
f4cb7a22-9976-5fb2-b99c-7714373f47b3 | note | Verifying Documents - Attach Electrical Test Report
406e4a3c-3d12-5e40-ad20-13d244108baa | date | Date Completed:
5918d9e5-948a-4916-9d2b-3a5968e195f4 | checkpoint | 5.2 - Removal of redundant hardware
88bb95db-6b03-5652-a6bb-43b43b72cdbf | note | Reference - Section 730.17 (b)
e234f90f-a5ff-5dd4-96b1-b955e3a5a3d4 | note | Acceptance Criteria - All redundant components of hardware and equipment shall be removed unless specified on the design drawings.
026d581b-2ce8-5273-b931-77a29dc32ecd | note | Method - Visual
267450ae-0c5f-5bc1-be56-273c15533a4e | note | Frequency - Per installation
8158bad8-45a5-5ec5-b0a9-d724e026dfc8 | note | Category - IP
4675b959-4cb3-5849-a247-8fc51044de93 | note | Responsibility - SE/Supervisor
1148307e-1971-506e-a14f-579eb5d627c1 | note | Verifying Documents -
4825450b-b3eb-51a0-8494-61b65a571d42 | date | Date Completed:
ec19d033-dfaf-48e1-9e21-515702689236 | section | 6. Post-construction / Post-installation Activities
f5d6cede-a830-4131-b035-67be8ebdcbe0 | checkpoint | 6.1 - Survey as-built
0deec2fe-7a0d-5a8b-b900-b809e0f28ac3 | note | Reference - IFC Drawings
96b17a8a-5e33-5b2a-90bd-75d10bb2a2ca | note | Acceptance Criteria - Survey to As Built Traffic Signalling works.
355c5bcb-ee6e-50c3-9b68-3ad5fa995dda | note | ○ As Constructed Traffic Signal plan to be submitted to Vic Roads.
b51230d1-1fc6-51cb-bd7c-3a49296cd6fe | note | Method - Document Review
4869c9d2-584e-545a-bea3-0a72c83e1ed0 | note | Frequency - Each element
7a0f7651-c7f9-55c2-9264-c2a16a751b43 | note | Category - IP
829d4ed1-2d85-53ba-a9cb-dfd3b7f75668 | note | Responsibility - SE/Surveyor
70bcaeb9-bdb8-5151-969a-ea3f7f908e63 | note | Verifying Documents - Attach As Constructed Traffic Signal plan
e9a8edd0-9b4d-58b0-a749-c4eb795f2243 | date | Date Completed:
f904ab53-fb74-4138-8bf4-0438e786a3b8 | checkpoint | Final Inspection
963f0b49-37e6-5f2b-8276-7f216f1b4f81 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
d9303bda-4ebf-57f9-90c1-20a705dc9d03 | textbox | Name:
8d19e3aa-4fa9-513d-a218-42be7fc4697a | textbox | Position:
eae8e37d-8673-5fd4-96c2-0600d486172c | textbox | Date Completed:
579e75c3-0d5a-444e-bd0f-d9c71cf7803f | signoff | Sign ITP
8bbe460f-b454-47cf-805d-bf0ad2c3505f | checklist | ITP-250-CIV-FRMS-Hot Mix Asphalt Rev 0 | itp | ITP-250-CIV-FRMS-Hot Mix Asphalt | f7591952-bfa0-4a41-b1a3-6e77913e03aa
febb69dc-33bb-4e75-b228-5f25c8060dff | section | 1. Referenced Documentation
d57581e7-cda5-430f-9cd0-2062832a0d23 | checkpoint-no-value | Referenced Documentation
ff48e7f0-ff37-5fc3-8192-ae59264f70c3 | note | Document Title: ITP-224-CIV-FRMS- Hot Mix Asphalt
0645a962-f035-5cf5-a218-21c32c83795d | note | ITP Description: FRMS- Hot Mix Asphalt
c8b8328c-3d89-5665-a5ee-7fdc7f2f4110 | note | Discipline (e.g. CIV/STR/RAIL): 224-CIV
f04f3e8c-1d5e-58fa-8bbc-b6efd8506d30 | note | Revision Number: 0
82ae9827-6519-5cba-ba49-9bbe5c666786 | note | Revision Date: 11/04/2025
88db5a5f-b0e7-5884-ab78-efd7e9753592 | note | ITP created by: Kamel ALSHOBAKI
7dd641a4-e2c2-5ce5-be22-5fbd86e7224f | note | ITP approved for use by: Pradeep Talasila
19fd40dd-0ec0-5362-87e7-db67fef98902 | note | 1.1 - Non Dependent
ae803dd8-ea09-5517-a5bc-714f7ba8b6eb | note | Reference - VR 407 - July 2022
60732bea-5397-5238-99dd-0da3843a4017 | note | 1.2 - Non Dependent
95a841ba-893f-5f6d-af83-ac7372cfa5b7 | note | Reference - VR 173 - Oct 2008
b9cacb13-e73c-4dcc-b416-8e51f5cdd2f1 | section | 2. Preliminaries - Materials
6063dbb6-9bc0-4b53-8e72-a978d6153cab | checkpoint | 2.1 - Mix Design
cb8aec79-4a47-58fe-acbd-52486fcd4112 | note | Reference - VR 407.09
eae416c0-172f-558c-9963-94c79421b0b4 | note | Acceptance Criteria - All asphalt mixes proposed for use in the works shall have a mix design registered by Department of Transport as ‘General’, unless otherwise approved by the Department of Transport. The registration for all mixes incorporated into the works shall be current at the time of their use.
9319d9eb-5fde-5941-a936-e90f77f6ab84 | textbox | Enter: Teambinder Approval number
e1dcdef2-c31b-5a0e-9a26-0149f5470e2a | note | Method - Document Review
c401e21d-d5cd-5bba-bce9-0e18d0521721 | note | Frequency - Each Mix
b43c4150-76e6-5997-8386-06a17e296761 | note | Category - HP
5a5a6274-7ca2-51e5-a3e4-b64de81f2a25 | note | Responsibility - PE/Nominated authority
64425c9c-49cc-5754-8a22-bc0dcb4d794c | note | Verifying Documents - This ITP, TeamBinder Approval
991815f0-52ec-5f38-8a6c-39758cd9b74d | date | Date Completed:
c3aed1f6-d364-49ad-bc95-4eeeafb53bc0 | signoff | AUTHORITY HOLDPOINT
1e79ef58-bfc3-4a61-9714-be534aaa4a74 | checkpoint | 2.2 - Bituminous Materials-Tack Coat
6325a34a-0502-58ac-8741-396fa1bd7a0a | note | Reference - VR 407.08 (d)
fad39ac0-b115-567f-b673-b379e0d51e15 | note | Acceptance Criteria - Tack coat shall consist of a bituminous based binder.
c28c652e-9873-5246-9b10-aa6b2c7eed53 | note | ○ Only trackless tack coat or a tack coat application system that prevents pickup of the tack coat must be used.
b478a4e4-0459-5a31-bd0d-342446b6e83f | note | ○ The Contractor shall submit the details of the trackless tack coat proposed to be used in the works.
516064fb-0f49-52fb-b0f5-df4090e831ad | textbox | Enter: Teambinder Approval number
a2b4fda0-54d1-577b-870c-9a19c060764c | note | Method - Document Review
9ba38b94-aa98-58d8-b22d-52902a4b5950 | note | Frequency - Each Material
a8fe2b91-b5f7-5643-a025-809826bc2280 | note | Category - HP
80e3944e-54a6-5914-8b06-83f5925d8814 | note | Responsibility - PE/Nominated authority
6c91475d-ff56-5f66-ac60-fa5e37734b9f | note | Verifying Documents - This ITP, TeamBinder Approval
cd019ac8-f696-5eff-b93c-677b500e1be3 | date | Date Completed:
8605373f-b315-4443-8509-a7c4037277d1 | signoff | AUTHORITY HOLDPOINT
32544382-1513-4d82-82dd-67a7182e5520 | section | 3. Preliminaries - Procedures & Documentation
d93447a4-f1d4-48aa-b94e-937761736545 | checkpoint | 3.1 - Asphalt Quality Plan
00e8fca9-6579-5a35-8edd-bbfbc845376f | note | Reference - VR 407.04, VR 407.11
43a04d5b-f682-5d16-a071-56cd11c15542 | note | Acceptance Criteria - the Contractor shall provide an asphalt quality plan that addresses the following requirements:
057c6420-9208-50d9-97e1-239831697009 | note | ○ RAP Management plan (Approved by DTP)
b0644248-2048-5d66-ac5d-98afab99e2a6 | note | ○ asphalt loading and transportation to minimise segregation and achieve adequate mix temperature on delivery to site
ab8c6680-e153-57dd-bbf0-65835f901015 | note | ○ measuring and recording of pavement temperature, wind speed and weather conditions
0e899797-98e4-5f82-ba48-799e064d10a6 | note | ○ achieving a uniform application of tack coat
d2b276ae-8e0b-56c2-a410-3b369c01cfe1 | note | ○ achieving uniform asphalt placement including determination of paving speed and paving plans
6db70821-f509-536f-b8f3-c8dc576e7254 | note | ○ determination of appropriate compaction equipment, number of rollers and rolling patterns required to achieve density
6912727d-1296-5ba7-9469-b45f6a985fb8 | note | ○ procedures to maximise density at joints.
2ed8482d-fcd2-5d7d-9ac5-126c84be0fc8 | note | ○ Production, storage, discharge and compaction temperature ranges for warm mix asphalt shall be included in the Contractor’s asphalt quality plan.
4f8000cf-47f3-5d65-8b18-f79af90117b0 | textbox | Enter: Teambinder Approval number
4409b68e-6e72-54f3-a6a8-48aa1a2c049b | note | Method - Document Review
0ef20f86-be29-5278-bbb1-93ce3ca7d32d | note | Frequency - Each Lot
cf03eba4-ed44-5036-af46-4145ad6c1bed | note | Category - HP
6d0e5520-c7b2-5093-bd30-7c77a2a674ac | note | Responsibility - PE/Nominated authority
8984a1de-3c32-5e8e-a70e-7fb6fb4bf312 | note | Verifying Documents - This ITP, TeamBinder Approval
60c13900-4d25-5720-8e10-ad8f225250f6 | date | Date Completed:
848ed15c-c0fb-450b-83fb-840b92bbf318 | signoff | AUTHORITY HOLDPOINT
daf1b5fc-84a5-41aa-95d5-0dc4622573d0 | checkpoint | 3.2 - RAP Management Plan
c37cb438-4772-5a70-b2bf-3bcf9c4f1926 | note | Reference - VR 407.13 (f)
dcfd1620-604d-5693-ab55-0afcef78822a | note | Acceptance Criteria - No asphalt containing RAP shall be supplied until the Department of Transport approved RAP Management Plan has been submitted at least 14 days prior to the asphalt works commencing and approval to proceed is given by the Superintendent.
e75fd435-f1e8-53a9-8dfe-0afa6d6ab307 | textbox | Enter: Teambinder Approval number
f21d1c90-d90e-5a5a-b8ac-a270a56a408c | note | Method - Document Review
7bb1a127-4f64-57e4-a7cd-cca952cf0fa4 | note | Frequency - Each Lot
167176f6-92df-5cb2-9b8d-6978217c00e0 | note | Category - HP
c8057f00-170f-5c38-ad2d-3190751e7152 | note | Responsibility - PE/Nominated authority
f5aba753-7c1e-51f8-98d9-ac553e196cb7 | note | Verifying Documents - This ITP, TeamBinder Approval
a5e767dc-bbea-54f1-8053-642eeaf89d56 | date | Date Completed:
fbd0fd2a-71b0-430e-be14-2d9f5636967a | signoff | AUTHORITY HOLDPOINT
6093d2cc-9336-4797-96a5-2ee5813d3715 | checkpoint | 3.3 - Cold weather placement
912ad9eb-8f94-5b64-88dc-b43f878d6666 | note | Reference - VR 407.17 (b)
c2989047-4076-5864-acf4-f1761645faee | note | Acceptance Criteria - Where approved by the Superintendent placement of dense graded asphalt in layers 35 mm or greater may take place at pavement temperatures up to 5ºC below the minimum temperatures specified in Table 407.171.
35f07a18-bc2e-5652-bf2d-77d5c357dbc8 | note | Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review.
e0aeea46-6ef4-5070-92c4-3a6c93692f1a | textbox | Enter: Teambinder Approval number
46130b67-d94d-58b3-9fce-7f5cb60e941a | note | Method - Document Review
dc12adda-58f4-5341-a3ea-d1d6e396a68a | note | Frequency - Each Lot
d654d0d2-0679-5391-8ff6-8ea883592191 | note | Category - HP
df22007c-92c2-56ad-9f63-01ce664ac812 | note | Responsibility - PE/Nominated authority
5286d9b9-1c46-5de1-bc5f-efde687726fe | note | Verifying Documents - This ITP, TeamBinder Approval
b6474f67-ba08-5652-836e-0b8d1cd25cf6 | date | Date Completed:
00e422f2-0a58-467c-abcf-817ffa50f838 | signoff | AUTHORITY HOLDPOINT
67ce7f42-70bb-4963-a883-c3154954c732 | section | 4. Pre-construction Activities
890cacc9-cd4b-4f80-ab1e-2f3c779fcfb4 | checkpoint | 4.1 - IFC Drawings
5c35d6e8-c35d-559c-b69d-714e2e7e1725 | note | Reference - MRPA Quality Management Plan
e301cd2e-e1b1-5301-a4af-77a316eeace9 | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
804e51ee-4260-5d03-b341-ad13daf30699 | note | Method - Document Review
7a463aa7-6aac-5cb1-a425-db6b72254fd8 | note | Frequency - Prior to starting Works and at regular intervals
412445ea-d41a-5af0-85e6-cde424f85961 | note | Category - HP*
fdd024a0-8d8d-5130-8029-fa42b4e5bc6e | note | Responsibility - PE/SE
277a861a-19d7-5f93-a422-6146f710490a | note | Verifying Documents - This ITP
c0347561-c601-5fcc-83de-61ce7c33c3a7 | date | Date Completed:
83d4f449-f5f2-456f-9726-b7cb50d76bcc | checkpoint | 4.2 - Lot Map-and Lot size
bb870cb1-0998-5de6-b5fb-e0f4412870c6 | note | Reference - VR 407.21 (a), VR 407.27 (b) (i)
dc6de8bb-6ec9-5bc1-a336-cc17c385e991 | note | Acceptance Criteria - A lot presented for testing shall consist of an asphalt layer which is placed in one shift under uniform conditions and is essentially homogeneous in respect to placement methods, materials and appearance.
0fb39eab-789b-534c-8b79-f85b553a7359 | note | ○ The location of all joints shall be planned prior commencement to achieve the specified offsets between layers and the position of joints in the wearing course.
2344b886-89d9-553c-9a0b-080229986632 | note | ○ ATTACH: Lot Map with planned location of Joints
b5f5b43d-f303-58a0-be87-d2d59f722e1f | note | Method - Document review
56850dbd-32f9-5043-a79e-1d8c4b0c5115 | note | Frequency - Each Lot
9b56578f-a889-581c-9ad5-27186ea89e99 | note | Category - HP*
18349ca4-5f89-5c2f-a58e-8f08133fbad7 | note | Responsibility - PE/SE
4d41d1ef-f596-5bcc-9ae0-367835046b1c | note | Verifying Documents - attached Lot Map
4897b046-e7fd-5dfc-b80a-79153291ba0b | date | Date Completed:
e3bf96f7-1df3-4154-aa84-0bd3cc9b419f | section | 5. Construction Activities
676c82d2-406d-4752-81a6-662815d0cf34 | checkpoint | 5.1 - Ambient Conditions-Surface conditions
2e52b440-9c82-5c77-803d-2350342fbae1 | note | Reference - VR 407.17 (a), VR 407.18
ff01eac5-32f2-5772-927e-e362e469bed3 | note | Acceptance Criteria - The surface on which asphalt is to be placed shall be essentially dry and free from surface water. Asphalt shall not be placed when the pavement surface is wet, or rain is imminent.
d8d4e7d8-454c-5da6-ad64-dc76ad67b2f4 | note | ○ The Contractor shall remove all loose and deleterious material and sweep clean the area upon which asphalt is to be placed.
df60a5c6-bbb5-5d29-a0f1-45829150d7f7 | note | Method - Visual
9902d825-5471-502c-846c-3cf706f2a2b5 | note | Frequency - Each Lot
a904dbdf-ae90-509e-9c24-bb382ca4c781 | note | Category - IP
0cc87426-9ca3-523a-9552-e43a13ff5c36 | note | Responsibility - PE/SE
91010f3e-a38d-5fdf-b033-80d6c98174af | note | Verifying Documents - This ITP
4fe68aba-26fa-5ca4-b859-70a8a6e81cba | date | Date Completed:
7a9132df-2027-47e3-8f6e-324a0683c2d2 | checkpoint | 5.2 - Ambient Conditions-Surface Temperature
c48d50fb-1ad3-5b6f-97a3-045b7ee1f98b | note | Reference - VR 407.17 (a)
8504a9f3-7b39-58e8-b275-28fd881c7295 | note | Acceptance Criteria - Asphalt shall not be placed when the majority of the area to be paved has a surface temperature less than that detailed in Table 407.171 and as below:
276196fe-5d49-52e0-bef7-2c0b1bda7942 | note | — Specified binder class of C170 or C320:
b1c07bd7-5567-5fc8-8464-d3dd1f93858a | note | ○ Wearing course: 10°C
b0dff899-287b-5a73-97c2-9d1791ea9c3d | note | ○ Other courses: 5°C
b887e961-bddb-5fc5-b175-717509ab0078 | note | — Specified binder class of C600 or containing a PMB:
c2e6a85d-280d-5aa8-a7c4-225c5e498928 | note | ○ Wearing Course 15°C
214140b6-c8ff-55d8-a21b-ad6a4be03a80 | note | ○ Other courses 10°C
df151612-ba17-58d7-b614-538a2df8606e | note | Method - Measure
67d5ef06-c90f-5390-90d6-1d0e99bc4825 | note | Frequency - Each Lot
89279bf2-b1ae-5188-ab19-6c962fd13f94 | note | Category - IP
a6244aa7-0c74-5cc7-aacb-c9308928313b | note | Responsibility - PE/SE
36f0459f-9093-50f3-ad71-63e4d74beb5a | note | Verifying Documents - This ITP
237b0335-d00d-5bc7-9068-03ca3f9962df | date | Date Completed:
b4df508e-8970-4899-8c26-6c630295b4d5 | checkpoint | 5.3 - Joints and Junctions-Layer by Layer-Transverse Joints
41742fee-278f-536d-8293-7798b70d316b | note | Reference - VR 407.21 (b)
ae3499ff-6602-518e-bffa-c8a75259cbfe | note | Acceptance Criteria - Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
32f234e3-2274-5117-8f51-76e416560655 | note | — All transverse joints shall be offset from layer to layer by not less than 2 m.
56bc9eff-9774-5429-b89f-b7f991e5d74c | note | Method - Visual, Measure
25312155-c76b-5d11-bc52-d2454249f2e1 | note | Frequency - Each Lot
2dda1398-01d3-573e-a3d3-5cf53eb28324 | note | Category - IP
aee1993a-c962-5d7d-8486-cc5fd06d7327 | note | Responsibility - PE/SE
fb336077-b349-5d86-b915-0d17ffb31022 | note | Verifying Documents - This ITP
bfe89e86-70b9-549b-ba91-1fc4fad6602f | date | Date Completed:
bcec4892-7ea8-478f-aa09-14ced6612b35 | checkpoint | 5.4 - Joints and Junctions-Layer by Layer-Longitudinal Joints
0a0c722d-7652-58f5-bad4-0a4e542cc68d | note | Reference - VR 407.21 (c)
f51808f2-b897-5aa5-8fa0-1ec7f52202ef | note | Acceptance Criteria - Runs to be marked to achieve the specified offsets between layers and the final position of joints in the wearing course.
6c4929c0-c309-5f3a-a505-8eac42290c85 | note | — Longitudinal joints in the wearing course shall coincide with the location of intended traffic lane lines.
497e16c0-9b87-5686-933b-12e868e854c8 | note | — Longitudinal joints shall be parallel to the traffic lanes.
1c53aca9-c1dc-5684-8c70-e3c4901f86e4 | note | — Longitudinal joints in intermediate and base courses shall be offset from layer to layer by not less than 150 mm and shall be within 300 mm of the traffic lane line or the centre of traffic lane.
d93c2c9b-873c-5242-beed-20dae2463f74 | note | Method - Visual, Measure
c03a4799-394e-5b0a-bd4d-76a2d9a54f7b | note | Frequency - Each Lot
4b1139e0-473a-5283-916f-44ccf7286e0a | note | Category - IP
1da75e35-9b91-537d-a051-337ffa342a3e | note | Responsibility - PE/SE
e08fb94f-b56a-503d-8bf5-243b900a8325 | note | Verifying Documents - This ITP
b6f0f025-f2e2-5ce3-84e0-d7e3720bd8ad | date | Date Completed:
ad085ae4-d471-4371-a9df-902c19806d88 | checkpoint | 5.5 - Joints and Junctions-Abutting existing pavement
7bb59926-7c4d-5109-b0d9-f09381131a72 | note | Reference - VR 407.21 (c)
28ba3f63-e354-56ee-900e-d85620ac91a4 | note | Acceptance Criteria - Where new pavement abuts an existing full depth asphalt pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150 mm.
e2b91ec9-8d7f-5da8-a61b-32c0e9a75630 | note | ○ At the wearing surface where the new and existing pavement join, a hot applied bituminous crack sealant shall be applied.
ec12ffbf-a64e-5946-ba33-c992d1da5f77 | note | Method - Visual, Measure
a889d20f-9ddc-5bd7-843d-f1ac2d088b85 | note | Frequency - Where applicable
7c7d3a89-ebec-5b64-bb65-f3583ba00f4e | note | Category - IP
3172c369-1d72-5406-ab94-aa3e90a7fcde | note | Responsibility - PE/SE
7c3e2941-494d-51fb-b567-6247d021f9b0 | note | Verifying Documents - This ITP
33a6ab87-e445-55cf-8bfd-5aaec0b81cd3 | date | Date Completed:
26939b2b-4060-4122-ab34-26aee635d18d | checkpoint | 5.6 - Joints and Junctions-Junctions at limits of works
813ac4c6-45fc-52fe-bf72-ff4920294799 | note | Reference - VR 407.21 (d), VR 402
381d3623-d309-5605-9e61-f23c70422c3e | note | Acceptance Criteria - At junctions where the new asphalt mat is required to match the level of existing pavement surface at the limits of work, chases shall be cut into the existing pavement by cold planing as specified in Section 402.
df7ca5f0-2002-5cd9-9133-3ed31b765d7f | note | ○ The chase shall be cut by removal of a wedge of asphalt tapering from zero to a depth of 2.5 times the nominal size of the asphalt from the existing pavement to the minimum length as follows:
1dd9524c-f0b3-5c50-8566-172af6c6f48e | note | (i) at side streets and median openings – 600 mm
4c61d68f-ffde-5926-82d5-4eb6047b1ded | note | (ii) on through carriageways with a speed limit of 80 km/h or less – 3 m
d8df00fe-2fd4-5dd9-bc99-edab16c480f6 | note | (iii) on through carriageways with a speed limit of more than 80 km/h – 6 m.
e7feead5-96ab-54a7-95bb-92aad1a1f205 | note | Method - Visual, Measure
664b0001-d19c-52cf-92d8-4c29d69ba88c | note | Frequency - Where applicable
aca1154a-7a88-5f83-9a49-823892958fb6 | note | Category - IP
8fdd94a1-c39f-567c-8c1f-dc619ed85e56 | note | Responsibility - PE/SE
4e4cc369-f1e5-5d8d-ab1d-029875eb25e5 | note | Verifying Documents - This ITP
93c99a18-b242-57ec-95ed-695a057f7af7 | date | Date Completed:
1c37a21f-f7e8-414b-a535-0340f27995a1 | checkpoint | 5.7 - Application of Tack Coat
c9b79d41-a149-58fa-bcd4-2c03b4330d90 | note | Reference - VR 407.19
4c23abc8-887e-5baf-91d0-7f1e63aecaa1 | note | Acceptance Criteria - A tack coat shall be applied to all asphalt, concrete or sprayed seals on which asphalt is to be placed.
ca1d6cd7-9a05-56a9-993b-68d45d9224bb | note | ○ The application rate for the tack coat shall be 0.15 to 0.30 L/m2 of residual bitumen
da152860-dba2-5044-b005-06718c18d186 | note | ○ For joints and chases rates shall be doubled.
998eb26d-2e8c-5f74-9eb3-8d346193b962 | note | ○ The Contractor may omit the tack coat where asphalt is to be spread over
caa81095-bd95-54da-96f5-8f94e925ce0e | note | — A clean, un-trafficked, freshly laid asphalt, or
ca70d94c-e579-5a8c-ae51-1f2a21a09d6e | note | — A clean primed surface, or
6cff4ebf-c3fa-5485-bc02-3bdd5cc2b7f9 | note | — Granular material where the overall asphalt depth is 150mm or greater.
d09550cb-7523-5428-87e4-6e3081b06205 | note | ○ PHOTOGRAPHIC EVIDENCE shall be supplied to show that tack has been applied.
dff9d44d-44f0-529b-8d44-cf3ebe93da45 | note | ○ ATTACH: Photographic Evidence
f2fe4dae-2798-541e-adc7-cd744ad5d7f5 | note | Method - Visual
4bc5fd97-72e9-5cd6-966c-cb64f4b5f4c3 | note | Frequency - Where applicable
0d6dee58-ddb7-5c0b-ac9e-118607b9e08d | note | Category - SP
f2188ef1-5a12-5171-86d0-f5e05a145b86 | note | Responsibility - PE/SE
98d42d41-51b6-5349-acec-aeb0fbd2646a | note | Verifying Documents - This ITP
3bffde81-81a1-5b81-8964-74816d3cfb63 | date | Date Completed:
b48e0e61-ad1d-4736-85d6-83187de36d40 | checkpoint | 5.8 - Joints and Junctions
89cba2b2-650d-5fe9-9d9e-648faafa46a0 | note | Reference - VR 407.21 (a)
01ff97fb-74a8-53c7-90b9-c0ed159118ac | note | Acceptance Criteria - All joints shall be well bonded and sealed
436272ba-5766-5d33-b4b6-2be892edb50a | note | ○ All cold joints and abutting concrete edges shall be tack coated
a35db581-c085-542c-ba41-a40f59fe2b24 | note | Method - Visual
bc6b9cba-8959-5d7d-9daf-71c036fbd0d7 | note | Frequency - Where applicable
1653fa0d-a6ab-540e-af0b-34b2154c2dad | note | Category - SP
727a7221-85a4-5552-ac8b-446488e4f3d1 | note | Responsibility - PE/SE
0cdbcc11-449e-5de8-ad07-046dee38fe01 | note | Verifying Documents - This ITP
9121f5cc-ee42-5000-8081-695ab9e3056b | date | Date Completed:
4417d30e-4382-412d-be55-09812db5d685 | checkpoint | 5.9 - Delivery Dockets
10be5c6a-4d41-5de5-a5f0-31145a1fc2e2 | note | Reference - VR 407.20
7f280b28-653e-509a-b1aa-c40b16c8c5a5 | note | Acceptance Criteria - Asphalt delivered to the site, which is segregated, has been overheated, is too cold, contains separated binder, uncoated particles or which does not comply with the Specification shall be removed from the site.
e3fbd79c-05de-5077-ab31-fb86c36d1fce | note | ○ Maximum Asphalt temperature at discharge from the plant is 175°C
b82c6169-ac8a-570a-b6e0-1d1a034f5e45 | note | ○ ATTACH: Mix Delivery Docket
cef648cf-06bd-5234-8f79-f100fb12d7e7 | note | Method - Document review
8131764e-e6c0-5a8a-9ffa-b4d844543b91 | note | Frequency - Each Lot
8e54f461-304b-57e9-9b3b-baa7888d21a2 | note | Category - IP
302c9f13-eb51-5277-b1c8-413bf04520a8 | note | Responsibility - PE/SE
987e2b03-3ef4-56a4-8985-e3940da5fd3a | note | Verifying Documents - This ITP
1e5ea356-2ea6-5c79-833c-607db1ea1a85 | date | Date Completed:
82912f5f-9801-4ef3-8ab0-bd71e35a0c2b | checkpoint | 5.10 - Commencement of Placement
b0c6a939-1dc6-536a-9832-e7030b6fd792 | note | Reference - VR 407.23
141d0f9d-a4a5-5fb5-898f-0f0dc415b7bf | note | Acceptance Criteria - The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until approval to proceed is obtained from the Superintendent.
720ae370-098b-5ab8-9b32-ba47d9cdfc87 | note | Method - Visual
6733de71-fbe5-5b30-a11e-5fd3c31e4bfa | note | Frequency - Each Lot
c73ebc35-4ebf-58d1-b491-4c70c25c927d | note | Category - HP
5914a413-1de5-52ff-a129-a508b80d0356 | note | Responsibility - SE/Nominated authority
ee30f95d-c8f6-5ba7-b192-109854c80474 | note | Verifying Documents - This ITP
993da53e-d75b-5beb-b14e-44a84ce5c0cd | date | Date Completed:
ab3e2271-1645-411d-991e-95f9a6c6f2f6 | signoff | AUTHORITY HOLDPOINT
e35664e0-15aa-4fc6-9f83-f5b7e7354e0c | checkpoint | 5.11 - Paving of Asphalt
1c350ef8-d327-53e0-9df7-165eab05ad83 | note | Reference - VR 407.25
e4ed7f60-3452-515d-97c8-e3192eecffea | note | Acceptance Criteria - Asphalt shall be spread in layers at the compacted thicknesses shown on the drawings.
a3f1872d-fecc-5407-9faa-9205ee71ec8c | note | ○ All asphalt shall be spread with paving machine (or by hand if not accessible by Paver) to form a smooth asphalt mat without segregation, tearing or gouging.
c7bcdb83-f247-5b9f-b5f6-af30d91b8a28 | note | Method - Visual
67193881-28f2-507b-8c94-7b9c497da04d | note | Frequency - Each Lot
e250465b-ce2b-55ea-915b-39629152ecf0 | note | Category - SP
0ee2c704-b4b7-5a63-9b30-2ee8f0369a3c | note | Responsibility - SE/PE
3e52d9d6-13bd-5b70-abf9-fa2a918397c3 | note | Verifying Documents - This ITP
460676d4-e53f-5169-816c-4d8c8e4a5678 | date | Date Completed:
a058ecd5-1e86-4cbb-a2d8-7d9f41143674 | checkpoint | 5.12 - Paving of Asphalt
441223f2-393c-5483-8e4d-08df27371cec | note | Reference - VR 407.25
9974375f-93af-5390-95b8-b4e8172e5a75 | note | Acceptance Criteria - If the paver is required to stop and asphalt in front of the screed cools to below 120°C, a transverse joint shall be constructed.
4df0cb9f-0640-596e-a113-93b833b559b5 | note | Method - Measure
392976a5-a98a-5270-ba61-670fc03dbc1f | note | Frequency - Where applicable
91890440-bb7e-56a5-a975-7e321e397cfd | note | Category - IP
76a79cc0-6632-598a-ac9d-46ad01defc0e | note | Responsibility - SE
b82cbc97-bb71-57bb-8f51-c78ee8917819 | note | Verifying Documents - This ITP
151f1feb-59f6-5aba-85bb-dd98d5f66bee | date | Date Completed:
8232c416-1fc5-4deb-9a1c-cc84d430a088 | checkpoint | 5.13 - Compaction
b0493a97-dfa4-5f89-be62-331909993ba3 | note | Reference - VR 407.26
8ffa5ba1-13e1-5fda-b5b6-4d0bc1b3ae85 | note | Acceptance Criteria - Asphalt shall be uniformly . Compaction shall not commence until the asphalt has cooled sufficiently to support the rollers without undue displacement.
379d4ab8-8e9f-5d91-9f37-2326781d4c70 | note | ○ Vibratory rolling shall not be used to compact asphalt on bridge decks.
3dea43c5-4201-5e05-86b1-6206726f4a9c | note | Method - Visual
ee9bdc0b-ec48-5190-8d38-eb4070497fd3 | note | Frequency - Each Lot
c376235e-e330-57f5-a356-1886cea04ef3 | note | Category - SP
b69818f1-85b8-59e8-8726-12e0555a196b | note | Responsibility - SE
3a9cbb76-389e-5383-a03f-b8d9a0cf364a | note | Verifying Documents - This ITP
35625da3-eb92-558f-921b-1e8c010e7bb6 | date | Date Completed:
338f728f-c8a1-4d81-b9ae-887dfe499db7 | section | 6. Post-construction Activities
d75ee0eb-223a-42b0-acc5-4868ccf0558d | checkpoint | 6.1 - Compaction test-Lots larger than 500 sqm
af7bd21d-afec-5a71-b630-97b909265e17 | note | Reference - VR 407.27 (b) (i)
1173aed5-5ab5-5a26-bf7d-ab449a2b42b7 | note | Acceptance Criteria - The work (excluding longitudinal edge strips) represented by a lot of six tests shall be assessed as shown in Table 407.271.
6123174b-e66b-5dde-b1f9-5124cc6f6e6c | note | ○ For lots exceeding 500 m2 density testing of the longitudinal edge strips (200 mm from the longitudinal joint) for the wearing course shall be undertaken and results reported as a separate lot.
cee75a36-466c-50de-b37f-06fc7115c20b | note | ○ The Characteristic Value of the Density Ratio determined for the longitudinal edge strips within the lot shall be submitted for report only
8063767f-ddb4-5537-a71b-61cf46bd6330 | note | ○ ATTACH: Compaction test report
95a1cbfe-bf8f-58b9-bc11-f171a525a3c3 | note | ○ ATTACH: Wearing course joint strip compaction test results
84d0a16b-4fa0-5701-97d5-ee8117d43357 | note | Method - Document Review
d5ded6c4-8ec5-50fd-9a5f-91b3fee9ac2c | note | Frequency - Each Lot Where Applicable
410ab1ad-fb23-5400-b563-6d62e2caf5d5 | note | Category - HP
5e751763-dbec-5397-a42b-f0f5cc03af7b | note | Responsibility - Nominated authority
af804af3-7917-5a8d-8b20-f4c75f76593f | note | Verifying Documents - This ITP
5490f05c-7d18-50da-8464-d0dee95bdc40 | date | Date Completed:
47128e9e-3ca9-4940-a002-ba79104c1d67 | signoff | AUTHORITY HOLDPOINT
210861ce-bab0-4893-9124-a450e0defed8 | checkpoint | 6.2 - Compaction test frequency-Lots smaller than 500 sqm
9aa6a971-5854-5244-8ca9-f0bd7e4f7b77 | note | Reference - VR 407.27 (b) (ii), VR 173.04 (d)
15659553-5d10-57c5-be50-f8a1f9cd13da | note | Acceptance Criteria - acceptance of the lot shall be based on the mean values of 3 individual tests. The lot will be accepted if the mean value of the individual tests exceeds by 2.0% or more the appropriate compaction scale requirement for the characteristic value of density ratio for a lot of six tests.
00df1d58-6030-5313-9e3a-579f6fb63d57 | note | ○ ATTACH: Compaction test results
1fd45626-c495-575f-9b56-95386746e6f5 | note | Method - Document Review
1f66c9d6-165b-579c-a01f-cec331a8f8d9 | note | Frequency - Each Lot Where Applicable
1e4a7037-805e-55bf-81ec-5c43de2d05bd | note | Category - HP
6191bc2f-9590-5526-80e0-09028ae00d7a | note | Responsibility - Nominated authority
c29ae6fa-bcb2-51f7-a139-836775b75b3c | note | Verifying Documents - This ITP
d30d0c8a-0305-5ab0-8c31-3eadb7455852 | date | Date Completed:
4ee4c4c5-58ac-43e7-b821-d65b5c1f675d | signoff | AUTHORITY HOLDPOINT
04d83cbe-cb8a-4bf3-b7a2-0c2bba21b1a8 | checkpoint | 6.3 - Surface finish and conformity with drawings-Surface Finish and shape
9bb6ab5e-ad5d-5b80-9ba3-11ab95779144 | note | Reference - VR 407.29 (a) (i), VR 407.29 (a) (ii), VR 407.29 (a) (iii)
44a99c68-2c8e-576c-b738-dd2d0c3f0d8b | note | Acceptance Criteria - The finished surface of any asphalt course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks.
c65db3f5-7ca6-5331-b843-80168c20a6c5 | note | ○ No point on the finished surface of the wearing course: shall lie more than 4 mm below a 3 m straight edge
2be1399f-0971-5d90-99b7-55b0e40e4af9 | note | ○ For intermediate and base course layers: the distance below the straight edge shall not exceed 6 mm and 10 mm respectively.
111f14ca-589f-55e3-a471-15216e990e0c | note | ○ Where asphalt is placed against kerb and channel the surface at the edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel
d5a4dee2-ed4c-5b75-8318-f0bdfde06405 | note | Method - Measure
470ec0d0-8729-574d-a034-f0c9bb2a6e34 | note | Frequency - Each Lot Where Applicable
8ccba87f-6a89-538b-a6b4-0d8641f71160 | note | Category - IP
49f096d5-d9b0-5e6e-b9bc-2f7eac88d937 | note | Responsibility - SE/PE
2feb9b71-381b-5f63-a648-4c1875d73d70 | note | Verifying Documents - This ITP
b6f368a6-4538-580b-8a2e-5bd6d89e8048 | date | Date Completed:
59b19b62-ad49-4ac6-accb-037dbc5bf983 | checkpoint | 6.4 - Surface finish and conformity with drawings-Alignment and width
974827d4-0f9e-59e4-8b23-8a85aba6a8ae | note | Reference - VR 407.29 (a) (iv), VR 407.29 (a) (v)
26da54e9-0832-5f32-96af-838d44e23cd9 | note | Acceptance Criteria - Where asphalt pavement is not placed against a concrete edging:
13b4e0f3-8b4e-584b-b291-e526d099e0b6 | note | ○ The edge of asphalt layers shall not be more than 50 mm inside nor more than 100 mm outside,from design line. Within these tolerances, the rate of change of offset of the edge of layer shall not be greater than 25 mm in 10 m.
b5b7c391-092a-5034-9377-6252b2aa54e0 | note | ○ The width of asphalt layers shall not be less than the design more than 50 mm or greater than the design by more than 100 mm. The average width over any 300 m shall not be less than the design.
0dba4985-57d3-574f-9aff-a98a155ef5ac | note | Method - Measure
f1db828b-6e73-5487-8eb2-b2b171910763 | note | Frequency - Each Lot Where Applicable
9a102183-6a27-5e96-bfef-41f3184b2f02 | note | Category - IP
cfb5696d-7e46-5429-9eef-a160e2d38219 | note | Responsibility - Surveyor/SE/PE
81231da5-8c12-5750-87ee-a59a27160545 | note | Verifying Documents - This ITP
2f340337-f108-5fe3-b6f6-2d193cec388f | date | Date Completed:
cac4f41b-a40e-44b6-8442-b17fbddfe4fc | checkpoint | 6.5 - Conformity with drawings-Scale A and Scale B
3100e8e5-56a8-5169-8d6f-0442718dc06c | note | Reference - VR 407.29 (b) (i), VR 407.292, VR 407.293, VR 173.05
975b17df-0277-5b55-b52b-de0124efcf77 | note | Acceptance Criteria - the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.05
74cce9f7-135f-5366-b741-31bfd6152df6 | note | ○ Number of measurements and acceptable tolerances are to be as per tables VR 407.292 and VR 407.293
857ae4b4-211e-5c2d-b47f-4cba283a165f | note | Method - Measure
fab206a4-512b-5d0a-a16c-01c638fc6cc4 | note | Frequency - Each Lot Where Applicable
1313ad7f-169d-5101-9e2a-f1927656d65b | note | Category - IP
f7ed8b26-705f-5d0e-95e0-d1330d486c1b | note | Responsibility - Surveyor/SE/PE
e8fb1ef6-10a1-54a4-8ffb-0579e571e29d | note | Verifying Documents - This ITP
421394af-78da-535b-be3e-70003db6ec68 | date | Date Completed:
752be8ff-e19d-44ab-8617-90be48bad992 | checkpoint | 6.6 - Conformity with drawings-Scale C
d25a093e-7342-5422-97c5-cfc1b62b116c | note | Reference - VR 407.29 (b) (ii), VR 173.06 (c), VR 173.06 (d)
97580121-4409-5314-83c5-550cf8de8749 | note | Acceptance Criteria - the surface level of each asphalt course shall be measured in accordance with the requirements of Section 173.06
439abef1-6f49-504d-8f29-1d5ba4b7f03f | note | ○ The level of the top of each asphalt course shall not differ from the specified level by more than 15 mm for intermediate and base courses and 10 mm for wearing course.
2fe89e51-96e2-5dfc-a5f7-09f128ba3b89 | note | ○ For the purpose of this clause, the maximum lot size shall not be more than 4,000 m2 of pavement area.
e50051d5-507f-5d64-a367-2aee86dd0858 | note | Method - Measure
24e801f0-974f-501d-9490-5d459967156d | note | Frequency - Each Lot Where Applicable
9c4d01bc-c79d-5689-b0da-afdf4e29bb08 | note | Category - IP
7a28176b-9baa-5e6f-97ce-fbdbcdb4defc | note | Responsibility - Surveyor/SE/PE
3e79bedc-5268-50bf-882c-82edc3fda62c | note | Verifying Documents - This ITP
06d9ddf7-ad1b-57c8-987c-eb0c50facd15 | date | Date Completed:
ecbdd5b7-8c33-4f6e-b620-90ec9389d45d | checkpoint | Final Inspection
f758fb94-ed27-5f47-8324-4afd44d5df12 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
25c90d05-4b9a-5c63-be56-fff52fca82c7 | textbox | Name:
d2b0d931-8467-5557-b8b0-090441159e9f | textbox | Position:
41bb53cc-867b-54f8-8fd3-0bc803bea8ce | textbox | Date Completed:
7b9b1d57-4762-445a-8de2-e3b6a0cfb831 | signoff | Sign ITP
5d42458d-c2a4-4f7b-83fa-887f5cf7d0ba | checklist | ITP-251-CIV-FRMS-RSS Wall Main Rev 0 | itp | ITP-251-CIV-FRMS-RSS Wall Main | d5083063-d4d9-4a87-847c-b77767cee9ec
bfb53b61-8e4e-437c-8973-2596e67db59a | section | 1. Referenced Documentation
f77718b1-ae86-429a-b2f9-6244a8543523 | checkpoint-no-value | Referenced Documentation
768b26b3-3a05-5619-8982-24d6cbab4033 | note | Document Title: ITP-251-CIV-FRMS-RSS Wall Main
d6def38e-73d6-59af-bfe5-a9f45f53065c | note | ITP Description: FRMS-RSS Wall Main
f8ac19f1-afbb-517f-8ab5-4d6c295bcb84 | note | Discipline (e.g. CIV/STR/RAIL): 251-CIV
6c921026-d8ed-5949-8c98-95651e72a7ad | note | Revision Number: 0
4fd2b211-f91c-5d49-af18-4cba2b77da68 | note | Revision Date: 03/06/25
2e8cc543-92a9-5046-9f79-7697d5266179 | note | ITP created by: Kamel Alshobaki
c1f6e36e-8826-5209-806e-5b47f7144962 | note | ITP approved for use by: Pradeep Talasila
87a1d50f-6896-53c0-898b-9da414a4929b | note | 1.1 - Non Dependent
11bcc5ed-4f09-5df7-9b5b-2dd05caf804e | note | Reference - VicRoads Section 682 November 2018
c4d399e0-e0c7-5809-8ea8-539f8273c1a1 | note | 1.2 - Non Dependent
7fe75387-dfb9-5e9b-841d-61f0be16144f | note | Reference - VicRoads Section 204 December 2015
09b04fb6-5053-5155-b07a-cdf0010c39fc | note | 1.3 - Non Dependent
e796c519-6e8c-506d-915d-521b913694dd | note | Reference - IFC drawings
22eae5de-27bd-4468-8ce4-ece7dccb9099 | section | 2. Preliminaries-Materials
0bf2f68b-9fd0-4d19-9e45-ed5a0b1c9fd0 | checkpoint | 2.1 - Concrete-Leveling Pad
010f8b9f-3858-5756-af20-3506b0feb8ac | note | Reference - IFC drawings
9a847abc-6cd1-5430-8ce8-57491e8a2de9 | note | Acceptance Criteria - Concrete compressive strength grade must not be less than N25 for levelling course and backing blocks;
0eddb121-ec95-5b52-99f2-5023f5b00677 | textbox | Reference: Teambinder MA number:
e235f6e3-12f0-58e0-93b0-06b903c18a78 | note | Method - Document Review
aa54badd-5837-541c-a8b7-f0ee04decd5d | note | Frequency - Each element
1321b32f-76e8-54e6-a861-5f2456fe5708 | note | Category - HP*
03fe7de6-3696-5be2-9047-18ca157be729 | note | Responsibility - PE/Nominated Authority
b20433b8-5c7b-583a-b856-654bad10e87e | note | Verifying Documents - Material approval
a3491a63-ab04-5d93-b316-62cd25ee511f | date | Date Completed:
6441917b-13cc-4e32-a728-e2664d605760 | checkpoint | 2.2 - Select fill
9b7d065b-0dc5-51f7-a185-5b90652fb3ad | note | Reference - IFC Drawings VR 682
94925d53-0104-5197-b4bd-ce7f7b9ac7f1 | note | Acceptance Criteria - Select fill shall comply with the requirements of the RSS designer:
538b5ea5-d7ff-5006-a295-c666800351fc | note | — UNIT WEIGHT (Max): = 17 kN/m³
3e73274d-a53f-53dd-a4d7-1029641d080d | note | — COHESION (Min): ≥ 0 kPa
958c56cd-465b-5cfe-84f4-66d4c252a618 | note | — INTERNAL FRICTION ANGLE (Min): = 36°
033559e6-be47-5906-9a45-bbb16fb50064 | note | ○ Gradation:
812a27cd-2af2-5330-87c9-8bcedbe76a23 | note | — 150mm : 100% PASSING
c87fbdcc-35a0-5802-8100-7eed3dadb8ab | note | — 37.5mm : 60 TO 100% PASSING
197f84b7-2047-5ac4-9d0e-e1a257a429e1 | note | — 9.5mm : 25 TO 100% PASSING
dde97151-a173-5807-a6bb-1b61ea70e646 | note | — 2.36mm : 15 TO 100% PASSING
7ee72462-a011-567b-b6f0-b3e68ebde968 | note | — 0.6mm : 10 TO 100% PASSING
e9819466-c1af-5427-bcac-72fdc05a536e | note | — 0.075mm : 0 TO 15% PASSING
de7a1ca2-c810-5e5f-a789-0dea20f87dad | note | ○ Electrochemical Properties:
a24c4683-7b93-525f-a5c0-5e9d862bf3e3 | note | — pH: 5 - 10
c2befb6e-2b3e-5788-9da8-fd169ddfbcdc | note | — RESISTIVITY >1000 Ω-cm
f971ccd0-c8e8-5c09-9463-cf4b9c6c2fb1 | note | — CHLORIDES <200 mg/kg
191eb1d7-0280-51b7-92c1-9278e93ab362 | note | — SULPHATES <200 mg/kg
ddd97b14-d267-5847-bfe1-c031b8bb6fe0 | note | — ORGANIC CONTENT 0%
3d7c8993-2d6f-5ac9-a729-4e4b37e01467 | note | ○ Structural Properties:
23195a09-9eb1-5ca9-8e15-638e59ed02bb | note | — COEFFICIENT OF UNIFORMITY ≥ 5
177aecf9-a717-5544-a8b1-c72e50212ff0 | note | — LIQUID LIMIT ≤ 30%
95650dbb-a21b-53d4-8263-50113b5eda1d | note | — PLASTICITY INDEX ≤ 12
2b0eb6b5-459b-57b6-b156-de07b4a86a84 | note | ○ The select backfill must meet the minimum requirements of Vicroads Type A filling
f2dfeebd-3a46-570b-8307-1d24f8bf86e4 | textbox | Reference: Material approval in Teambinder
614fe574-d5e3-5724-94b8-2e5e9780d824 | note | Method - Document Review
9abac64f-bc96-5f67-861c-c2adfd5758ac | note | Frequency - Each material specification
1fb10cbc-06a0-5622-82c1-14a7e6e7dbe7 | note | Category - HP
6b8eb301-91e5-5a1d-9578-bf3ebbea6401 | note | Responsibility - Nominated Authority
9542fea5-209c-509c-8bca-e7c654ee5152 | note | Verifying Documents - Material approval
b92fe6f7-d4ee-5248-9c2e-cbba5ee9fc53 | date | Date Completed:
7be3d093-7354-4f50-8e71-0166a45e9ede | signoff | AUTHORITY HOLDPOINT
868acf63-aae3-454e-a00e-4ec6f6076e8b | checkpoint | 2.3 - General fill
b8e055b2-9e59-5cec-a8a2-6d0e96a0ccf5 | note | Reference - IFC Drawings VR 204
2b44aad6-f0a1-5420-924b-5bb71039c796 | note | Acceptance Criteria - Backfill behind the reinforced block shall be Vicroads Type A or better in accordance with Vicroads standard specification 204:
5abed7c2-e3c6-52df-b203-9886d6e083fa | note | Select General fill shall comply with the requirements of the RSS designer (RW01-RW04):
10488d4b-af6f-5a47-ba2c-b244144ed45c | note | ○ UNIT WEIGHT: = 17 kN/m³
8d99f777-d545-5d4f-b657-ec6bbe92c629 | note | ○ COHESION (MIN): = 0 kPa
808c10d3-34b3-50d2-ac59-74b2907c2ccc | note | ○ INTERNAL FRICTION ANGLE (Min): = 30°
f4ab25c9-601e-53ee-a560-7598cf9550b4 | textbox | Reference: Material approval in Teambinder
b0c3e063-64d2-519e-9ba5-b6ab899a254c | note | Method - Document Review
277994f4-e63c-5b7b-8388-b5e897684bf0 | note | Frequency - Each material specification
adfdb5fb-9a5a-51b9-b8bc-b4594f533081 | note | Category - HP
48de654f-171d-5d05-92b2-61e0cacbdcf3 | note | Responsibility - Nominated Authority
8ce55a78-bae5-5466-a35f-fb1442311e8b | note | Verifying Documents - Material approval
7d12de1a-0b66-57e3-bba9-e750f599dd34 | date | Date Completed:
0b3e1d9f-df99-4112-9b95-cc00bdf5ffc8 | signoff | AUTHORITY HOLDPOINT
cddcab03-a449-42bc-b476-5ea5d13d7e1e | checkpoint | 2.4 - Subsurface Pipe
dbe4b0fb-abf9-57a4-a4f4-aa76c7388ec8 | note | Reference - IFC Drawings MRP-103-C-AUR-DRG-35-RBK-CSW-0101
79968529-fe61-5a88-b615-de4c8c64380f | note | Acceptance Criteria - 100mm SUBSURFACE PIPE WRAPPED IN GEOTEXTILE ENCASED IN FREE DRAINAGE GRANULAR FILL
4360d142-5b1a-5bfc-9f2d-0173855d2750 | textbox | Reference: Teambinder MA number:
9065c9e4-54fb-511b-8a6e-649a6daf1a27 | note | Method - Document review, Measure
51d2aef4-41f5-5017-bfb4-e64848c411f3 | note | Frequency - Each wall
7016535b-926b-5b71-88fb-f8bcd90fea8e | note | Category - HP
5bda9716-7def-56e8-8a2c-128f32f77641 | note | Responsibility - Nominated Authority
0c629e0a-4133-5313-aeb8-d0626b66907d | note | Verifying Documents - Material approval
030038ef-3c6e-5a18-8e0f-a897348b65e9 | date | Date Completed:
19baf5e2-eeb4-4e59-ba31-87faed4f500c | signoff | AUTHORITY HOLDPOINT
21bd8922-610b-4a7c-94f3-b48dd9f24f93 | section | 3. Preliminaries-Documents
02a4edfe-0f20-44bc-b030-130a58471b17 | checkpoint | 3.1 - RSS Panels
44062a30-fc8f-5d33-ad9c-7e52a246b221 | note | Reference - IFC drawings
a6871d80-8a56-5042-ae60-0335e3d0e310 | note | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
22bd7213-1b57-5ca5-8260-93475cbfee90 | note | i. Certificate of Compliance / Birth Certificate
a99a4ba5-9d18-53d7-8362-b3cd2a8b8c72 | note | — 1. Concrete strength;
d0dd3c4e-0e29-557d-82b8-8a3044fe53d6 | note | — 2.Date of manufacture;
b9566928-8bb9-5d35-a680-b75f06dec567 | note | — 3.Unique Identification number;
c49c9a3c-d689-521f-956e-4a416f85eeca | note | — 4.Mass;
03c1e860-1ed1-5e1d-8ee8-a564c1056f00 | note | — 5.Confirmation of number, type and capacity of lifting inserts;
2baaff72-bc78-567f-9f06-f4a59a2db768 | note | — 6.Quality assurance sign-off.
56ebfc57-5fa2-555a-adb5-c8f6ddcf4af0 | note | ii. Compressive strength test results
1d35afac-9003-54f9-b4bf-02b8b6160369 | note | iii. Precast Lifting Design
9a941d4a-daef-57ca-9598-63a8f5a57014 | note | iv. Pre-pour check sheet / ITP
dd4b8269-4ffc-541a-97d5-7f191af87e92 | note | v. Post-pour check sheet / ITP
0f3f7b12-4998-5e2b-b7ea-d442ec606fc1 | note | vi. Covermeter check record
5c46ea9a-731e-5d47-98d0-f34a6c0d619f | note | vii. Record of dimensional measurements
1ffdf218-771a-5738-bb6a-d64cfa6cf98d | note | Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder pre-cast supply Lot (don't attach it here)
4b42f4b8-f062-5fba-9b90-8f8d9e8c5de2 | textbox | Reference: Precast panels MDR Lot in TeamBinder:
7271fcb7-b201-50fc-9e22-52db733266d3 | note | Method - Document Review
ebffd4c1-f32b-53e2-871f-3dc88e3236da | note | Frequency - Once for each type of panels
1a32601c-5e59-5dff-8e60-96958b63ae84 | note | Category - HP
561f5583-f9f0-542e-ab03-41bc56201466 | note | Responsibility - PE
98acbfa6-24ef-54d1-96da-fd06f8490ba8 | note | Verifying Documents - Precast panels Birth certificates and MDR Lot
ab83bc17-bbba-5e29-88b4-36fafd3726ef | date | Date Completed:
e4fb0933-d93b-4b13-b3c2-0d4601346504 | signoff | AUTHORITY HOLDPOINT
2558bee5-7539-406d-abe6-b66cddce584c | section | 4. Pre-Construction Activities
3b0a1462-f5c8-4b5d-9774-e3c6820e1edc | checkpoint | 4.1 - Foundation
6024c385-166f-5b0f-9291-d291d8ca327e | note | Reference - IFC Drawings MRP-103-C-AUR-DRG-35-RBK-CSW-0101
900e870c-8829-5162-bc53-866b03e4fbc5 | note | Acceptance Criteria - Foundation material under RSS wakk (RT01 to RT04) shall adhere with minimum design bearing capacity.
9efc3c50-278f-5ba7-8a1a-1af9673c72fb | note | Max Wall Height
07ade354-c877-58cc-b9b2-867c1552a31d | note | ○ <2.5m - 75/150kPa
ae8063ea-57c3-501f-9121-8b96858e63fe | note | ○ 2.5 - 4.5m - 90/180kPa
3c1f65b6-4e4f-5284-b407-638d9410c68d | note | ○ 4.5 - 5.5m - 100/200kPa
365d8c61-dfb6-5697-96e3-c2398a358d3d | note | ○ 5.5 - 6.5m - 110/220kPa
5832a495-7e39-52eb-aaef-cda53eedc786 | note | ○ 6.5 - 7.5m - 115/230kPa
699d301b-32f2-5847-a31d-0f2ba6aa0de4 | note | ○ 7.5-8.5m - 125/250kPa
733656d0-5f8a-5e1b-82bc-0436af34471d | note | Method - Test, Document Review, Visual
9c254173-ba43-5ff8-bda2-a3e937151186 | note | Frequency - Each retaining Wall
77f4ce98-2425-58bd-bac0-89db60efb03a | note | Category - HP*
86edba38-7038-5f76-8e35-9d84fa274217 | note | Responsibility - PE/Geotechnical Engineer, Foundation geotechnical assessment
1f47fcc5-c495-58cb-b62c-e73edd90578a | note | Verifying Documents - This ITP Signed off, Test results
d4da63b3-491e-5bec-80ac-c4598ad57f3a | date | Date Completed:
7579fc5e-114c-4731-a76f-c24adfa95f92 | checkpoint | 4.2 - Foundation
00d1cc14-68b9-59a1-955a-fd73ef0c0024 | note | Reference - VR 204.12, VR 204.11
de5b2b35-ef83-5b60-ba90-6104aa14f862 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be test rolled in accordance with VR 173
693e8740-dc8f-5d1e-8558-d478ce7310b2 | note | ○ No Fill shall be placed against or within 3 meters of a structure until the foundation for the fill has been reviewed by the superintendant
0590648a-715b-5dc9-a972-6513d678492b | note | Method - Visual
32f0a76a-0c15-52af-9b8e-3cd10fe15f41 | note | Frequency - Each retaining Wall
2161ece5-91b7-5c17-a94e-8af623c47d0a | note | Category - HP
5c818817-a571-5a77-957a-dc4a29542bbe | note | Responsibility - PE/Niminated Authority
24d1835a-ea03-526d-a32d-33a552fb2297 | note | Verifying Documents - This ITP Signed off
8fac91ee-000e-5e8c-956a-e08549c481b6 | date | Date Completed:
39619aa4-c676-4815-8831-3871a4a71acc | signoff | AUTHORITY HOLDPOINT
7358236e-9623-4d04-8e74-7a08677a3667 | checkpoint | 4.3 - Levelling Pad-Survey Set out
c7312e96-a83e-5090-955c-e5507f99a445 | note | Reference - IFC Drawings VR 682.20, MRP-103-C-FRL-DRG-35-RBK-CSW-1001
11b88f8c-4343-5a74-b965-f0a7bfb4c696 | note | Acceptance Criteria - Survey to set up and validate all works meets levels and locations with the right tolerances as per IFC Drawings and Vicroads Specification.
e8b7e0e8-7762-524d-bcdd-6dacd010d2a4 | note | ○ Levelling course level shall not deviate from the specified level by more than +/- 3mm
2e6fa791-2aaa-546f-a2ff-88f51ed552d0 | note | Method - Measure, Visual
cd421dd3-ca4a-523a-a0e2-f3c91ed5bf38 | note | Frequency - Each retaining Wall
28eb772b-c70e-536b-bce5-87583cf045bf | note | Category - IP
c6d4436b-e687-5dbc-b405-5800fed58f5f | note | Responsibility - Surveyor, SE/PE
4ce84e56-3429-5a27-93d4-749cf2dbd731 | note | Verifying Documents - This ITP Signed off
a8418784-aa9a-5b44-be71-bf428a3057d4 | date | Date Completed:
caae5f87-6042-4d4e-bf75-d8bfbed6fb0f | section | 5. Construction / Installation Activities
270e82ea-4b51-4e70-bae9-3f2a4933c789 | checkpoint | 5.1 - Form Levelling pad
fa31f3fa-b9af-5497-b531-a4d129d1553b | note | Reference - IFC Drawings MRP-103-C-RFL-DRG-35-RBK-CSW-1201
dd58e550-ac01-5580-a94e-991d37a1675c | note | Acceptance Criteria - Form timber shutters or Earth form to edge of levelling pad
fd854d72-053f-5a52-b40b-9fcbccad5d95 | note | ○ Levelling pad is a 500mm wide by 150mm thick unreinforced concrete footing
aa093be1-0e77-51ad-a11b-d07f6daad508 | note | Method - Measure, Visual
e298c70b-77f0-539c-8c50-ebbe86a1a303 | note | Frequency - Each Lot
86cca67a-4860-59eb-82b1-1b746e50af22 | note | Category - IP
4ae961fe-80ba-5790-a4a3-c6efad07aeb9 | note | Responsibility - SE/Site Supervisor
771aeee8-d66c-5d4b-8809-fac42d9f1efb | note | Verifying Documents - This ITP Signed off
9557422d-57af-5244-8bc8-caed3b970ae3 | date | Date Completed:
f3bd6ed5-3376-4cf5-9a59-e30817b174d4 | checkpoint | 5.2 - Leveling Pad Concrete Pour
581f2ed4-1186-546a-9194-b7dda583ef3e | note | Reference - IFC Drawings VR610
bb030922-72e6-5e06-b2a1-33039241e6ce | note | Acceptance Criteria - Concrete to be placed in accordance with VR610.
b0e204cc-6e39-50b4-a5c3-5285c7369601 | note | ○ Attach: Concrete Delivery Docket
5633084c-adc7-54bd-8636-c7c84efcd0f0 | note | Method - Visual
86fc58c1-9900-52a0-b153-00f0a67f9e56 | note | Frequency - Each Lot
fd01efe0-d258-5f9a-bcae-34803ed4e9e3 | note | Category - IP
f9d43044-fa33-5b97-af27-6149ad0bef72 | note | Responsibility - SE/Site Supervisor
6f29d2f5-28ba-514f-a1c6-29088833a5c9 | note | Verifying Documents - Concrete Pour record, Concrete Delivery Docket
91d3d430-b48d-5215-9e34-4cbde8d06ec9 | date | Date Completed:
aed329f5-c158-418f-a144-ab960e826192 | checkpoint | 5.3 - Leveling Pad Concrete Testing
ce150998-75f8-5e97-8d6b-43bb4fe00aab | note | Reference - IFC Drawings VR Section 610.16 (b) & (d)
a632eaa2-927e-5c6a-809b-f9a9b2e329a2 | note | Acceptance Criteria - Concrete testing for compressive strength shall be undertaken at the testing frequency specified in VicRoads Section 610.16 (b)
35ce4e59-f08a-5b20-bf52-78d833ef06a4 | note | ○ Concrete strength (Min): N25 MPa
7521777b-bbbf-5196-81c5-19d051911687 | note | ○ Attach: Concrete test report
03aaa5fe-e6ec-5e6b-8627-c1b804c46b04 | note | Method - Document Review
c94152df-c726-5e8a-a142-06b1dcec0ba6 | note | Frequency - Each Lot
3b02673e-dcc3-5d13-a7e8-b0fae1136d46 | note | Category - IP
2cba8f8e-41c1-51c8-aedc-dd4733fefa58 | note | Responsibility - PE
7c3d539b-7e15-5e24-b090-c936d5564cb4 | note | Verifying Documents - Attach Concrete Test Report
bc1e9e77-6f80-5b06-9349-3fe19d1fe170 | date | Date Completed:
c73b41a4-5672-4b17-ace7-4b58db2a0e86 | checkpoint | 5.4 - Levelling Pad-Post Pour Survey-Levelling Course
bcb10036-e143-5711-80f2-ecf0ca9ffa49 | note | Reference - IFC Drawings MRP-103-C-FRL-DRG-35-RBK-CSW-1001
3f7e7985-c7fa-56fd-a3c6-27f582514224 | note | Acceptance Criteria - Levelling course level shall not deviate from the specified level by more than ±3mm
8e730579-7017-5a91-ac49-e32350a5cff6 | note | ○ 20mm Nominal gap between levelling pad and adjacent ground beam is to be maintained
238a2fe5-09fb-59de-85f0-01de6551ceda | note | ○ Plan position shown on the drawings at the base of the wall shall not exceed ±15mm (refer to drawings for WP locations)
ad538a54-a0ea-530d-8c82-3e71b8f71d9b | note | Method - Measure, Visual
75f0f7e8-0081-5a61-b308-efe2fa469b50 | note | Frequency - Each retaining Wall
5b28aa36-3d02-52c9-9f7d-0278c9044faf | note | Category - IP
6c4d7f7b-fc7e-5832-8aae-eda363f0976e | note | Responsibility - PE/Surveyor
498e7fd7-a9ef-59c4-aab7-44d134d228f9 | note | Verifying Documents - Attach Survey Report
a041ade0-ab97-50c0-a907-d6169ba2263d | date | Date Completed:
adec8ccc-e67a-4cac-a813-d09b8fff6562 | checkpoint | 5.5 - Drainage-base of the Wall
69b04623-c504-568b-9558-f405ad6b8dd8 | note | Reference - IFC Drawings MRP-103-C-FRL-DRG-35-RBK-CSW-0151
acb1bdb4-5c5b-564f-9fea-5f015c74c166 | note | Acceptance Criteria - to install 300mmx300mmGranular backfill in Geotextile BIDIM A24 around 100mm Dia. Perforted plastic pipewith 0.5% min fall to weepholes in RSS panels.
2110ace8-bb84-5ea1-b381-a81ca6360775 | note | ○ Geotextile BIDIM A24
48eefef4-56be-5682-b274-ecd397ce6b11 | note | ○ 300mmx300mm Granular backfill
857b218d-6a20-5fc3-8938-d144bc4fa926 | note | ○ 100mm Dia. Perforted plastic pipe
762f9dd3-1e2e-5085-bd3b-4501f199e748 | note | ○ Perforated pipe to have 0.5% minimum fall
7bd95b10-78ac-50e2-8a58-c0d32e05ddd7 | note | Method - Visual
ca706140-8da9-5414-8d3a-969c56b2d201 | note | Frequency - Each wall
c38ce437-f465-5947-88d6-189e0b65b7a9 | note | Category - IP
85171ac6-8864-5d9d-a5c7-a563db251e22 | note | Responsibility - SE/PE
ba133a03-2b29-5822-ba89-6b6fb160f304 | note | Verifying Documents - This ITP Signed off
a04714fb-c749-55c7-b345-debdfc258704 | date | Date Completed:
0a4550a6-5d27-4756-9e93-c73f18f68b1a | checkpoint | 5.6 - Settlement Monitoring horizontal inclinometer
342851b6-4421-5eb5-91e2-00d5222e212d | note | Reference - IFC drawings MRP-103-C-FRL-DRG-35-RBK-CSW-0021, VR 682.15
d099e21e-bdf5-5ba2-a71b-6055a58c00e1 | note | Acceptance Criteria - Survey Pin and Inclinometer survey procedure us as follows:
b0dd945d-b7fa-53ec-a2d3-37cc14de8503 | note | ○ Inclinometers shall be installed prior ro placement of any fill
9f490f71-2f91-5c23-89bc-eda92fe5d2e8 | note | ○ RSS Wall and abutment wall survey pins shall be installed immediately following construction of the first level of RSS wall/Abutment wall and prior to any fill placement
d4db7db1-81d0-5cdf-af2b-e106a7ca259e | note | ○ Traffic barrier survey pins shall be installed following construction of pavement and barriers
769e50cc-b012-5393-9d29-cc577199d663 | note | ○ All survey pins shall have appopriate stick-up from finished surface level for continous settlement throughout construction/post construction
0cb7dc53-3431-5e04-aa0d-47969f99ff71 | note | ○ Pavement construction shall not commence until monitoring from inclinometers and RSS wall/abutment wall survey pins indicate ground movements have reached at least 90% of construction settlements and confirmed by the geoechnical engineer
43de983a-6e33-50d0-bebd-e3050112b089 | note | ○ Settlment Monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) unitl settlement stablisers or advised by the geotechnical engineer
83c9979e-cc0c-5806-af81-d13317c5a5b4 | note | ○ If at any stage prior ro the to the completion of the RSS placement, the total settlement exceeds 100mm, fill placement must be suspendedm and direction sought from the design engineer.
01f3e946-32d5-5377-ae3b-87d7234728b0 | note | ○ Survey pins and horizontal inclinometer shall be installed to monitor ground movement throughout and after the RSS wall construction.
c07663e1-376c-5096-b00e-545519a17064 | note | ○ Only hand operated equipment shall be used within 1m distance from inclinometers
a276a56a-bdcf-5795-8480-0b8e22463e18 | note | ○ Geotechnical instruments shall be preserved and protected for monitoring until the conclusion of post construction. Damaged or malfuctioning inclinometers shall be reported and replaced where possible.
9e957875-b67a-5f44-8018-7768c4efb267 | note | Method - Document Review
5cc38401-f82e-5514-bccc-8f563eabc595 | note | Frequency - Each Inclinometer
2a2cdf68-1b53-543b-ba32-42d25e81a96d | note | Category - HP
5e67ceed-ef6b-509f-a7cf-c448f2258ace | note | Responsibility - SE/PE
18149d38-4e25-5063-a7dd-76ca22025ec6 | note | Verifying Documents - Teambinder approval
57be061b-cc02-5d2d-a811-8aa1d5be3d72 | date | Date Completed:
cf143978-e622-4fbb-9e8b-747b2b9726de | signoff | AUTHORITY HOLDPOINT
03252fa7-76ea-4f50-8962-55e574b09020 | section | 6. Post-construction / Post-installation Activities
f202445d-4b19-4a08-a7c3-b26cb1040f52 | checkpoint | 6.1 - Wall Post construction monitoring
063a99da-ee6c-5f38-88d8-2595d8f077b0 | note | Reference - IFC Drawings VR 682.20, VR 682.151
f43f22de-dd24-59a5-bccd-6bde9cecd388 | note | Acceptance Criteria - The Contractor shall take measurements of the position of the RSS at the points defined in clause 682.20(a) to (f) at intervals not exceeding one month for the first six months immediately following completion of the RSS and at intervals not exceeding six months thereafter until the end of the Defects Liability Period.
29815f02-b48a-59b1-bb6f-0d52120993dd | note | Method - Measure, Survey
fdc8321a-7270-5bf2-ae0a-365fa726b24a | note | Frequency - Each wall
1afa2351-7b63-579a-a64d-709915fbcbec | note | Category - IP
0aa9cbc1-1bc0-5a36-896e-bf6653765aac | note | Responsibility - Surveyor, SE/PE/SPE
17ceb750-52d9-5e9d-9a57-caa4f9623bdf | note | Verifying Documents - Survey Report
8eefb972-beeb-592b-939a-4f55e131e17e | date | Date Completed:
1b1dfe35-0b03-4fb3-a8e2-38a756e42e7e | checkpoint | 6.2 - Settlement Monitoring
039eacb4-74ba-593f-85d9-57b0df1885cc | note | Reference - IFC Drawings VR 682.15, VR 682.20
0bda8a04-2fe8-5adb-b372-d82ea7d405c6 | note | Acceptance Criteria - RSS wall base level:
85c5fc6a-13cc-5588-997b-0b88dd7ff498 | note | — Start of wall construction to completion of wall construction (before pavement placement) Approx vertical settlement < 20mm
5822ba85-c0c6-5141-af4a-b19518f24682 | note | — Completion of pavement construction to end of defects liability period (2 years after practical completion) Approx vertical settlement < 15mm
79ff2e22-2d86-58f2-b1bc-ef2e9d80f37c | note | ○ Pavement level (Top of RSS wall):
695d90dd-30cd-5b7d-a0c7-cc75f706a251 | note | — Start of Pavement construction to completion of pavement construction Approx vertical settlement < 20mm
0e86f3c0-3920-5440-ad30-ec025be746ed | note | — 10 years following practical completion of payment < 50mm
64e96176-aa52-5293-9cc0-a28fb75d8a5b | note | ○ Settlement monitoring readings shall be taken at maximum one week intervals or for every one metre of fill placement (whichever is more frequent) until settlement stabilised or advised by the geotechnical engineer
d25a742c-6660-5c68-8ea5-66bdaed9de3e | note | ○ If RSS fill placement total settlement >50mm, fill placement must be suspended, and the mitigation method reviewed by the superintendent and DTP before recommencing fill placement.
2c3be325-d81e-598a-998c-0ae72f647800 | note | Method - Measure, Survey, Document Review
f1b5a4ea-15a6-50b0-b2f8-e5532aa48572 | note | Frequency - 1m of fill
da7b6700-a655-54b9-bfee-751ace9513b6 | note | Category - HP
0e680f51-a24f-59e0-ae09-2d0d1981fe94 | note | Responsibility - Surveyor, SE/PE/SPE
65e747fc-029c-5df8-be5d-1046f051649f | note | Verifying Documents - Settlement monitoring results
8321ef5c-0283-5e0c-8757-476ccf398047 | date | Date Completed:
02e7b318-1c05-4dc1-91a0-2116ac7b1e34 | signoff | AUTHORITY HOLDPOINT
9080f6b0-94d5-4a32-bd2d-16fbc9bf6adf | checkpoint | 6.3 - Non-conformance Report (NCR) Closure
f015586b-39a6-5052-a451-064ae99a8e86 | note | Reference - MRPA Quality Management Plan
a955e39e-bb9f-593f-a4cf-45e0a1f62f4a | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
dcfb73a2-925a-5029-a247-d8bf0fce6b01 | note | Method - Document Review
42c88dbb-9f78-5a07-be7c-e2c66c2d0cd3 | note | Frequency - Once, prior to closure of this lot / element / Work area
13a0b51a-abb3-5e7e-9180-ce3b80a0b0af | note | Category - HP*
a209ca82-98b5-5094-a20c-d847fe08b4dd | note | Responsibility - SE/PE/SPE
a46e636d-82fb-5bea-8ecb-2fbfe5a5daf3 | note | Verifying Documents - This ITP Signed off
0421c697-e85a-522f-90eb-8ccf465dd655 | date | Date Completed:
14afb3f2-18f1-418a-9dfe-dccc592e5dfc | checkpoint | Final Inspection
ad78f4e1-b925-5f25-9b38-ace8f7b6644d | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
43abd703-8350-5d62-8383-e5eb74af28c7 | textbox | Name:
652a1680-1a68-5ff6-b25c-8de56fea1be9 | textbox | Position:
dd277f47-26c4-5231-b3a3-3ee5d096fc4f | textbox | Date Completed:
e73edde8-b2e5-47ec-a3d3-292db03aa9a3 | signoff | Sign ITP
7aeeadec-6dec-4c81-8f42-b5d027ed360b | checklist | ITP-259-CIV-FRMS-Westkon Permanent chain mesh Fencing Rev 0 | itp | ITP-259-CIV-FRMS-Westkon Permanent chain mesh Fencing | be16f2da-dde0-469e-b7eb-c8f8976ec67b
35d433ef-dc29-4b2f-a46d-0af961cff134 | section | 1. Referenced Documentation
c63d9e56-4f87-4722-9656-e8e664060eb8 | checkpoint-no-value | Referenced Documentation
e2ea3148-992a-5c3e-af90-b06291dfceb5 | note | Document Title: ITP-259-CIV-Westkon Permanent chain mesh Fencing
2d8e8fe0-a355-5514-bc39-ac4a9441bc62 | note | ITP Description: Westkon Permanent chain mesh Fencing
2ce9705a-d1ba-531a-91b3-8da2ea28830e | note | Discipline (e.g. CIV/STR/RAIL): 259-CIV
de94faaa-0157-5a67-8549-eaf1c6d0929e | note | Revision Number: 0
e7f6227f-f03a-54bd-adaf-7ebebb5d9389 | note | Revision Date: 29/04/2025
fd68b357-ba43-5c61-81b8-f9d5b2493abe | note | ITP created by: Kamel Alshobaki
2412b8fb-e5af-511f-b8e8-d0347c5b9f5c | note | ITP approved for use by: Pradeep Talasila
845a9455-c988-5f0c-95cc-7b351edb1eec | note | 1.1 - Non Dependent
8df90ae6-f6b3-539c-8d01-3c2eb16f6b9f | note | Reference - IFC Drawings AS1725.5 Vic Roads SD 3131
fd200dee-c212-4e95-be20-96ccfe6bae91 | section | 2. Materials
355658f7-3ac9-4af3-b925-0a65ad7ca6df | checkpoint | 2.1 - Concrete
b775c379-1dcc-5f60-a808-24b58b1c0263 | note | Reference - IFC Drawings
c39cdfb9-af13-5f31-8129-ff3d70808502 | note | Acceptance Criteria - Min 20 MPa concrete to be used as per IFC drawings & Vicroads SD3131.
a34a3ea8-add1-5275-9a76-aa795c283143 | note | Method - Document Review
d13785d4-df0b-582c-b574-e37f8725b77e | note | Frequency - Each Mix
ada2b87f-2cb0-567d-b5b9-3fa9114ad4aa | note | Category - HP
ee9d8a8b-35a1-5a48-b369-f654bc7a9a8f | note | Responsibility - SE/Site Supervisor
54d79438-ce38-5418-bdda-43977ebee48d | date | Date Completed:
d569fe9e-8ea8-4418-a6a5-6ed90792dd19 | signoff | AUTHORITY HOLDPOINT
67d5e1ae-86ae-4f53-8d5e-bacb32e50cc4 | checkpoint | 2.2 - Steel components including posts, mesh and fittings
2f25dcee-062a-55a7-862d-7a687584374a | note | Reference - IFC Drawings AS1725.5
c5d13509-cc38-53ba-acd5-7ff67bb58df0 | note | Acceptance Criteria - All Steel must comply with Australian Standards.
ae12f13c-c155-5570-9cd5-07f681510b08 | note | ○ Steel section sizes must be checked on site.
8cdcd11b-3b61-5481-b536-ba60976dfce1 | note | ○ Steel posts to be CHS with a medium grade.
f5da8845-88eb-5016-9749-593189a5dc4b | note | Method - Document review, Visual and Measure
c97a7db2-dcbc-534c-b663-909a8bd70da0 | note | Frequency - All elements
066fe7d5-26bf-55aa-9334-cc4a3ed346e7 | note | Category - IP
55911851-ec39-5515-8f2b-c466acd5723f | note | Responsibility - SE/Site Supervisor
fe1c6e4e-ba6f-529c-bf36-e8e2582d6089 | note | Verifying Documents - Supplier Certificate of Compliance
e10dbea5-58c8-5312-973e-1ae8ab02dd19 | date | Date Completed:
e85a3358-a6a5-404d-b9c5-3304f43f70aa | section | 3. Pre-construction / Pre-installation Activities
e07a0071-949e-4deb-a5da-ef3e1ab65755 | checkpoint | 3.1 - Survey Set-out
f95f464e-7ce6-51f1-89fa-ab76c64fec4d | note | Reference - IFC Drawings
64dcff53-293d-5515-8b30-157b44306f72 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, and fence start and end points.
097424ff-30ed-58d0-a3db-f0038f7cb354 | note | ○ Offset checked against the running edge prior to installation of posts.
655612ed-06f1-51d0-a5a6-e34268e341d5 | note | Method - Visual and Measure
46820871-d2fb-55bd-bebe-4a7eed659b92 | note | Frequency - Each element
082607af-024d-50f2-8ac8-de5653d2d17c | note | Category - IP
5db88a2b-a98c-5bdd-a4b6-f4e88b8dc836 | note | Responsibility - Surveyor, SE/PE
587fef88-c677-5b90-ae48-657504e2768c | note | Verifying Documents - This ITP
c93592fc-68c3-5104-8215-49636fae721e | date | Date Completed:
35526f2c-539b-4fd4-8bf2-91d2257970bc | section | 4. Construction / Installation Activities
8d9d5939-fab9-4850-8c01-175eedf30c1b | checkpoint | 4.1 - Excavation works
2bd848c4-99e0-5afd-8da2-ee8291c5b898 | note | Reference - IFC Drawings
c1635c05-d8e7-512c-8df8-0f8875cbda08 | note | Acceptance Criteria - Excavation completed by auger outside of service working limits.
0d5b5b58-525d-51c9-8585-d8fd60802e7e | note | ○ Follow asset owners guidelines for work around their service.
1db83281-e609-5b9f-9550-530b315c5284 | note | Method - Visual
e3c437b8-5bc1-5df8-a2d2-d822bac656d5 | note | Frequency - Each fence footing
43b4e19a-6bc4-5f7c-839d-86247e9e6a50 | note | Category - IP
a4fc9018-1e4d-5f0c-9ac6-7eaf0ef53c74 | note | Responsibility - SE/Site Supervisor
360ac406-2b4d-5284-99b5-98f232e46b85 | note | Verifying Documents - This ITP
56b1b274-e12b-5f28-ae67-b8f65d66e784 | date | Date Completed:
f7630d32-8b5b-49e5-9731-8532fa1ec04d | checkpoint | 4.2 - Ground Conditions
a68b518f-7ba0-5c71-b213-0b4d1f5917b2 | note | Reference - IFC Drawings
b2a3a70f-8b29-518a-ad64-37abb9171952 | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
af2b9a6c-993e-5038-9ae7-77900b06a781 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
ed358127-1579-51d0-a680-7a8690b1e1a8 | note | Method - Visual
241a42e2-82b6-5a54-8d16-9fe1ca0e3a34 | note | Frequency - Each post
465ca531-9726-5557-88e5-b122fe48a2d2 | note | Category - IP
1a4829ba-4179-5464-b70d-d85fe21ef9f1 | note | Responsibility - SE/Site Supervisor
183132c8-c516-5169-983a-bb71158ae5d1 | note | Verifying Documents - This ITP
eaef66fc-c0f3-5985-8449-444434b00592 | date | Date Completed:
d6b4fc24-80b7-4316-8ac1-57ef373dc97e | checkpoint | 4.3 - Fence Footing
d4b0d29a-97b4-594f-9878-8e5856883a08 | note | Reference - IFC Drawings
440223c3-e8fc-51ae-b691-ed1b33f3d49d | note | Acceptance Criteria - Footing dimensions for intermediate post is 600mm deep x 250mm diameter and for Intermediate Strainer post is 750mm deep x 250mm diameter. Corner and Ebd post is 900mm deep x 300mm diameter. Gate post with 1.0m - 1.2m Leaf size is 900mm deep x 300mm, Gate post with 1.3m - 3.6m Leaf size is 1000mm deep x 300mm diameter and Gate post with 3.7m - 4.8m leaf size is 1100mm deep x 400mm diameter.
1b60a411-c3c6-50c4-8912-f84a96f766c2 | note | ○ 25 MPa concrete with min. 80mm cover when cast against ground. Concrete sampled as per VicRoads Table 610.161 (1 sample taken for 0-10m3). Slump test to be performed for each sample, and three cylinders for testing of compressive strength taken for each sample.
a84041a2-c3ca-5d58-bdef-bcb30f851cb7 | note | Method - Measure
33bf67e9-48a8-5f73-9db4-a7b97dee9536 | note | Frequency - Each footing
f4a1eb57-c80e-5d4a-b088-0b18bffe87b8 | note | Category - IP
63d01211-da42-51f5-8f65-93b1b26c1b61 | note | Responsibility - SE/Site Supervisor
87db65ed-b6bc-5818-8b9c-ed30fa8b50f5 | note | Verifying Documents - This ITP, Concrete Dockets
35cb350c-3344-531a-a4b4-2318ba87ffba | date | Date Completed:
06553501-c0a9-45ba-a181-fd1ed4f48bdd | checkpoint | 4.4 - Fence Post Installation - Non-sleeved
08b1136d-ee08-515b-bfa2-b0dbaf0dfa6f | note | Reference - IFC Drawings
76b82c31-c99c-5ad0-8022-4d512f762ba1 | note | Acceptance Criteria - DN80 MS Pipe (88.9 X 4CHS) to be installed with min. 80mm cover.
6ad9358c-2637-5f2e-a6bc-b548d31d8a74 | note | Method - Measure
4c835690-c316-57a4-aaa0-5725c9871719 | note | Frequency - Each post
e2e5559c-c68a-508c-9491-9e32caf4e997 | note | Category - IP
b5856788-503c-59e6-8184-d6f8a703e911 | note | Responsibility - SE/Site Supervisor
9e84eaeb-4b62-5389-9ce2-88be079d1e04 | note | Verifying Documents - This ITP
91489c6c-2a0b-5570-a3b6-7d712db20a48 | date | Date Completed:
4d86f4da-d91b-4217-bccb-a1b8599f44ab | checkpoint | 4.5 - Chain Wire Mesh Installation
86144c9a-c0dd-5118-acd0-0af5f3f8985d | note | Reference - IFC Drawings
279eec4d-212f-5f28-b1b9-3cace7b209f2 | note | Acceptance Criteria - Chain-wire mesh 1800x50x3.15 to be fixed to fence post with cable ties in accordance with manufacturers specifications.
3d9e8f6d-a864-5d6a-8380-f7aaf5e83348 | note | ○ Chain shall be tightened and securely fastened to posts at max. 400 crs and tension wires at max. 500 intervals with 2.5 dia. galv. tire wire or clips.
350ef106-054b-57c0-ba70-09a560baac5c | note | Method - Visual
3916983a-dd6d-56bd-8b53-dbe9fd78ad40 | note | Frequency - Each element
0a420875-a3d6-518a-a520-9ac200deaea8 | note | Category - IP
17475b4b-a7b5-5a58-ae91-48ed3106055c | note | Responsibility - SE/Site Supervisor
f77726fb-e769-5017-9715-055aefbc9ac9 | note | Verifying Documents - This ITP
e86327c0-c78f-5b66-866c-5842a467acfc | date | Date Completed:
8e88d419-ea6d-43e8-bfad-ecd8fd9cb5db | section | 5. Post-construction / Post-installation Activities
e37fd45f-7ad7-4b63-a790-38a0a6495f0a | checkpoint | 5.1 - As-Built Survey
c176bc78-a5cb-5dc0-9e52-4767ed9f9681 | note | Reference - IFC Drawings
58e5b97a-38d7-5ca2-94df-6ae63164d136 | note | Acceptance Criteria - Posts are to be checked for verticality and ensure spacings do not exceed standards.
2e1bcd7d-ade1-5f95-856c-c70151ff8fab | note | Method - Measure
5dde242d-b9a5-57c1-be76-217dc37aea5d | note | Frequency - Each lot
b4e7aed1-15a5-5396-a178-59842d443a56 | note | Category - IP
a4718bd9-1ca1-552e-8ae8-35e10fc47029 | note | Responsibility - SE/Site Supervisor
9c631d7c-72be-57ee-9fa2-15030d9384f9 | note | Verifying Documents - This ITP
d1e9c172-5e64-5333-a0ec-3bc4b265f468 | date | Date Completed:
065161ea-bca5-4380-8c36-2dfcd855bdf3 | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
99c0ea9f-b42f-5a3e-8981-77cc6230d6ac | note | Reference - MRPA Quality Management Plan
c7fdc869-cebf-5167-91c7-e6b28c281fc2 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
d7978a2c-400f-52d8-8867-96bcbe69810a | note | Method - Document Review
d1d9d7bb-dfbd-580e-9a8c-86080cc1c35f | note | Frequency - Once, prior to closure of this lot / element / Work area
b58a18e8-2fa9-5299-987b-d1d1ece8642e | note | Category - HP*
dab82023-86dd-5121-8406-692bd8d6930d | note | Responsibility - SE/PE/SPE
264bb28f-9ea7-5847-9f89-90c0dad4c981 | note | Verifying Documents - This ITP
a0debc3c-2645-5dd7-90a0-4ad3220377cc | date | Date Completed:
47e473e9-e444-4fd3-9fcf-b3547c1ff5f0 | checkpoint | Final Inspection
cc100898-57d5-5c19-a920-246a6e9e0028 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
9fe5f587-fa62-5847-a2ce-8cfb67cf553e | textbox | Name:
945c430e-7ddf-5d39-a21f-96be1744fced | textbox | Position:
c8442893-e229-5704-a392-943bf9b272c4 | textbox | Date Completed:
30e57ace-0368-4bb2-91d4-2fd0cadee5ca | signoff | Sign ITP
d2d097ea-f3fb-4813-abec-ad99d7a95663 | checklist | ITP-260-CIV-FER-Piling Pad (Supply and Install) Rev 0 | itp | ITP-260-CIV-FER-Piling Pad (Supply and Install) | 6e916821-94ef-47fb-b528-da1511b87446
48054fb0-5ed0-4720-acef-4998df211ae6 | section | 1. Referenced Documentation
49d149a0-29db-459a-8a9f-dca947786bc5 | checkpoint-no-value | Referenced Documentation
cd410094-f700-539c-bd49-bb75482edc5c | note | Document Title: ITP-260-CIV-FER-Piling Pad (Supply and Install)
fb0444cc-fcb4-5a3d-af82-35acc064122e | note | ITP Description: Piling Pad (Supply and Install)
7c75e423-6469-5f3c-8366-dcdd74d20c7c | note | Discipline (e.g. CIV/STR/RAIL): 260-CIV-FER
dd9c4078-5f50-5405-8aa1-d61aa0389c49 | note | Revision Number: 0
c0a8211d-0f83-54e0-8e70-745f7433a370 | note | Revision Date: 7/05/2025
ea13ef90-5e75-5598-9e8c-1a4badeb496e | note | ITP created by: Josiah Butter
7071cd6d-8744-574e-8a1d-8daee4a4cf51 | note | ITP approved for use by: Pradeep Talasila
243c2f35-7b49-5a68-9665-0a0a6fe6a8cf | note | 1.1 - Non Dependent
3df79db7-5454-52ea-90ae-97082b6e0ade | note | Reference - VicRoads Standard Section 204 (Dec 2015)
5ab1a0bc-51fb-52ee-b844-49318afad4d2 | note | 1.2 - Non Dependent
c97c2fbb-692b-592d-90e3-0d37ff3db174 | note | Reference - VicRoads Standard Section 173 (Oct 2008)
dbbfde68-80fa-591d-9c95-c47e00116d2c | note | 1.3 - Non Dependent
8679c8ee-0989-55ba-9260-388562490bc9 | note | Reference - Temporary Works Design - Crane Piling Pad Design
9290ed85-b3d7-5cb1-aa8d-b6af3f0b96c8 | note | 1.4 - Non Dependent
68a7de5a-904c-5504-b3ce-13ecd925e3bb | note | Reference - IFC Drawings
786075cd-a8e6-41fd-8d93-3a8d9ee7cf95 | section | 2. Preliminaries - Materials
d5ef13a0-d789-4413-81a5-2760ea50a7d6 | checkpoint | 2.1 - Class 3 Crushed Rock
59f020be-a24f-5064-a092-a56a0be1bf54 | note | Reference - IFC Drawings
8bdf3e82-f9d9-549e-a157-174add5638ee | note | ○ VicRoads: Section 204, Section 173
63a6e780-889c-5c8b-ac13-4109d4539454 | note | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
4e473b27-08bd-5337-9a33-1cf9889dfd7a | textbox | Enter: TeamBinder Material approval No.
b73176ad-94af-5f1d-98db-83587e009053 | note | Method - Document Review
4a4161d6-9909-5268-a678-ccf13c095005 | note | Frequency - Each Lot
8b236288-e67a-5e59-b1ef-7b09bc0fad62 | note | Category - HP
94254f34-f9a3-5837-bc7b-7ff18c33d676 | note | Responsibility - SE/Site Supervisor
21db8d73-c352-5fa8-9be2-544f3ce12de0 | note | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC, This ITP
2e366dec-294d-5afe-bfd9-8fb015bf0296 | date | Date Completed:
25868029-1f20-4779-a6a6-d96c1f74a20e | signoff | AUTHORITY HOLDPOINT
ed17e4ff-0d79-4c02-9b63-6e9ff258a53c | checkpoint | 2.2 - CTCR
f7980c18-5785-5890-9e57-59e8a62dcd63 | note | Reference - IFC Drawings
3901c050-a3cc-5658-8460-fc82e550ab36 | note | ○ VicRoads: Section 204, Section 173
2f1c5e0e-a6ef-5bfd-ba89-a21638365748 | note | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
798423e3-c3e6-5bfa-8487-490d93e6eb71 | textbox | Enter: TeamBinder Material approval No.
ae58334f-9430-5bbe-8d1b-97a8ffc084c9 | note | Method - Document Review
f12d7b3d-cff5-5dbe-883e-dcafcf5e2b51 | note | Frequency - Each Lot
2f40f276-bfd0-590b-90c4-048ca65f28ce | note | Category - HP
85784386-f0c6-5396-9aab-1d325d4aca5c | note | Responsibility - SE/Site Supervisor
3add9e64-e57e-5b38-a5ff-04b41ecd42be | note | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC, This ITP
8aa42cee-0790-587a-b16e-0b6752a94504 | date | Date Completed:
b42f3c41-050d-482d-b943-b81710dd6de9 | signoff | AUTHORITY HOLDPOINT
73c82ee0-7625-4bf5-a6f2-f6fdc472ab77 | checkpoint | 2.3 - Recycled Concrete
e38280fa-b4c1-59e9-90dc-7ede4d31eec2 | note | Reference - IFC Drawings
cec35891-136d-5637-bf3b-db15db23b494 | note | ○ VicRoads: Section 204, Section 173
222592f9-3e42-57a0-9b32-a2c892c044e2 | note | Acceptance Criteria - Material shall meet the requirements as per Temporary work design requirements
2e4fab38-fba7-5e9e-8b3b-1610090e322e | textbox | Enter: TeamBinder Material approval No.
45af9396-2c53-57cf-8389-a1e30e3731b4 | note | Method - Document Review
4396862b-83c8-5889-8d3b-7ca09534833d | note | Frequency - Each Lot
8dba9b6e-39cc-5b6b-9f7e-0aefe2f3d105 | note | Category - HP
f47f7044-a9f5-5e84-9b66-c295426dedad | note | Responsibility - SE/Site Supervisor
c052af4f-d5bf-53dd-9b0e-20f121175d06 | note | Verifying Documents - NATA Test –Material Test Report PSD,LL,PI,PL,MMD & OMC, This ITP
1f836916-1d8d-51cc-8a88-0fef2d8a033a | date | Date Completed:
a9be2a79-e4dc-4fab-a861-3d74c5649824 | signoff | AUTHORITY HOLDPOINT
1968172a-d06d-4b07-b529-71edb12b2968 | section | 3. Pre-construction / Pre-installation Activities
ecb9d8d5-b6ef-4463-866c-9357d3e84bdf | checkpoint | 3.1 - Survey Set-out
3484bb0b-7aef-559f-a8ab-e4cba4383e0a | note | Reference - Temporary Works Design Drawings
889766be-2e33-5487-91ca-3003776c2153 | note | ○ VicRoads: Section 204, Section 173
74039100-7821-5009-a96c-c16b6b995bdf | note | Acceptance Criteria - Survey to set out extent of piling pad requirements.
cf9cffe5-93b5-579d-bc0b-bbfd70b5e7a3 | note | ○ Survey pegs in place and clearly marks out the limits of works.
0938e8fc-7e4b-545e-959e-95442059a956 | note | Method - Visual and Measure
f1a5d21a-028f-5154-9710-c0af8f5a5d9b | note | Frequency - Each element
0aa6d87f-33be-590d-90d0-4e3d4017b7bd | note | Category - IP
1dc5140b-6305-504b-9b78-7c4db87a6275 | note | Responsibility - Surveyor, SE/PE
8c9b2fbc-c87a-5f84-aca9-921f21ccdc98 | note | Verifying Documents - This ITP
1317f4c1-3044-51ed-b459-d5cd8330f364 | date | Date Completed:
8bf3ee9f-d486-4336-9916-2299d2c17f89 | checkpoint | 3.2 - Check location of underground and above ground utilities
1d5b78c3-883b-5d03-8039-75d80dcb9473 | note | Reference - DBYD Combined Services Plan
8fed2d3f-3123-5e4b-8027-69081e89c4ef | note | Acceptance Criteria - Ensure that:
778f9ce7-c62d-51e1-b385-a3fa29831c80 | note | — Dial Before You Dig
5b766f97-7771-5232-90de-14128bee1d21 | note | — Services isolated
890fb521-5111-53d5-b8e8-252329a46ca0 | note | — Permits obtained from internal and external authorities
d71ae568-788b-5b3c-aa00-0bd0ab3ee612 | note | Method - Visual and Measure
809f0385-7e28-5ed6-82a3-5067f28f1906 | note | Frequency - Each Lot
c0c21d8d-a2d6-5fb2-bfdc-251d7173032b | note | Category - IP
97469a7e-c781-5f65-a90d-30aee219658f | note | Responsibility - SE/PE
54d4e213-c78a-5c7a-88aa-bfeb1bfd3fb5 | note | Verifying Documents - This ITP
92941d95-c18e-5621-8806-2cb6bc6119db | date | Date Completed:
64eb36bd-ac1c-41dc-9c5e-2a30517dfeff | section | 4. Construction / Installation Activities
d705f9ba-18fd-46ff-8a35-1c9886d3b0a6 | checkpoint | 4.1 - Ground Conditions
062377ae-3010-5379-8ad2-8717bd68c9f0 | note | Reference - IFC Drawings
1f289c03-2a76-519c-8a0e-4cff028aaf32 | note | Acceptance Criteria - All foundations are to be free of water and loose material.
e7e5e473-9417-56d2-8b8a-c7c356d3ab83 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
ab264d92-d91e-5d65-998b-222bd1b2f35d | note | Method - Visual
323caf0f-5337-55a5-a8dc-e93a75e87fec | note | Frequency - Each Pad
4f4e2238-f081-5c01-bbec-670ea03e9340 | note | Category - IP
d6a55a24-fcd9-504d-a72e-5a77ddcd4063 | note | Responsibility - SE/Site Supervisor
3c5563bc-4a8b-58c0-98af-e1889e9fbdef | note | Verifying Documents - This ITP
3f541ea1-3ce3-5755-a7d8-f0917efafd1b | date | Date Completed:
bdf40ab1-910c-4868-8b97-0b42935e1bfc | checkpoint | 4.2 - Preparation of piling platform foundation (proof Roll)
e8c87bde-1b52-5b9e-a6e3-c22caa307b7a | note | Reference - Temporary Works Design Drawings
e50a66c4-8659-54cc-ae2b-6cd0fe7ea3db | note | ○ VicRoads: Cl 204.12
e3310be7-0687-5e18-89a7-7d981b202211 | note | Acceptance Criteria - Areas upon which fills are to be constructed, all layers of fill, shall be test rolled in accordance with Section 173. Any unstable areas detected by test rolling shall be rectified. Nominated Authority to be present during all test rolling.
de52e7e0-00e8-5ba4-92d1-5b3f48c76839 | note | ○ Temporary work Design Drawing and equipment design requirements. No waving indication.
2bee136d-1a02-54ee-b59f-03328f1e95ae | note | Method - Visual
1ca82443-a0fd-5c16-9316-59cf217e4a00 | note | Frequency - Each Pad
c1b08e6c-bd16-50ae-a083-c77c8ec046a6 | note | Category - HP
2e477826-92c7-5eb9-8c6d-e16f5c4a96b0 | note | Responsibility - SE/Site Supervisor, Nominated Authority
30546adb-7c36-5170-898e-0fd6b1cdfa69 | note | Verifying Documents - This ITP
c29a820a-d04c-5485-b2ba-ecb309068054 | date | Date Completed:
162e4f80-0b6a-4242-a26d-212df9d7d70b | signoff | AUTHORITY HOLDPOINT
2db3cd01-80b0-49cf-aa9a-b52bfe8b0e10 | checkpoint | 4.3 - Fill, Compaction and testing
8ec9b841-fe04-5464-8234-34540cd30dd2 | note | Reference - Temporary Works Design Drawings
c7256d83-b66c-563b-82b5-5555a49c9782 | note | ○ VicRoads: Cl 204.10, Cl 204.13
5713f72a-422c-53c2-83e3-15ead007ce1e | note | Acceptance Criteria - Bearing Test to support piling rig (as indicated in temporary works design).
d79ae416-6b6d-5c70-9bdd-333c7848ffab | note | ○ Testing and acceptance of compaction and moisture content as per VicRoads Cl 204.13
5d7b176c-d660-5162-a52b-6d19cb5c6ea0 | note | ○ Attach: compaction test results
520a73f9-0e45-58c5-969d-a81c48bc6926 | note | Method - Test
ea21164a-914b-5815-90e8-451b225bd531 | note | Frequency - Each Pad
8aa4a104-b1bc-5e3b-9d08-b78665756f88 | note | Category - HP
70805d25-0222-5295-868c-7fb5da8383a2 | note | Responsibility - SE/PE
573a8f2e-9a8b-5529-9f27-d7f5117cd7e2 | note | Verifying Documents - NATA Bearing Test Report, Compaction Test Results
39c86840-306a-589b-8624-c2c3fbb25504 | date | Date Completed:
a70bd764-d323-4a4d-abc4-ee2105ce822c | signoff | AUTHORITY HOLDPOINT
840eb8e1-7540-44d8-93d1-1171475fa4eb | checkpoint | 4.4 - Service Protection
b358233a-2ffe-5a55-8262-617dd598ecb3 | note | Reference - Asset Protection Design
7bdc9fc8-a18c-5133-851c-85ed27305c9b | note | Acceptance Criteria - Install asset protection as required in Asset Protection Design
5ee8b092-a9a9-512e-8136-bf1eed4f8741 | note | Method - Test
33ba8d79-bcdd-592e-8d50-a3b0a9439cf7 | note | Frequency - Powercor
79200578-308d-5e4f-8393-d0409ba4fa62 | note | Category - HP
10f76771-bc7c-5bf1-9a7b-73ce326c9759 | note | Responsibility - SE/PE
d2faa4e6-b51f-557c-8a46-68cf9887c54c | note | Verifying Documents - This ITP
7aa1deaa-6367-5029-9351-95a259d7249d | date | Date Completed:
65053786-6474-48d3-b2d7-3a68bad44e0e | signoff | AUTHORITY HOLDPOINT
64f45762-264d-4838-ac19-ce47e8f106f6 | checkpoint | 4.5 - Verify survey conformance
1b3fd39f-d317-5371-b70d-dd3cf7eb8bd0 | note | Reference - Temporary Works Design Drawings
3343d1bb-ea55-52aa-8d3f-de5f5e7d29a4 | note | ○ VicRoads: Cl 204.03
bd3315a2-66d0-5278-b65f-cec5f9042763 | note | Acceptance Criteria - Construction Tolerances finished ground level ± 40mm or equipment requirements
2b476cd3-a3db-568c-a9c5-e091d5f5f6bf | note | ○ Attach: Survey report
bcef38e4-4ecd-51d3-a968-871baeb9ee7b | note | Method - Visual
b5d4b62d-b296-5feb-a38a-4b57eecb29d6 | note | Frequency - Each Pad
26e034ed-8c99-5ed6-9856-bdc0002300b5 | note | Category - IP
690f8459-a6d2-5b9b-9ad6-dc21d4f495ba | note | Responsibility - SE/Site Supervisor
f84f89fe-edb4-5402-a401-88abc9fd2375 | note | Verifying Documents - This ITP, Survey report
024641af-0615-595a-b854-c239425be936 | date | Date Completed:
c30c93c8-cf78-418a-b09c-2427e8cfbec5 | section | 5. Post-construction / Post-Installations Activities
b3c2708f-bc1b-4d01-b9c2-1365930f9327 | checkpoint | 5.1 - Geotechnical Report
08724d17-c481-5150-950f-855738abd148 | note | Reference - IFC Drawings, Temporary Works Design Drawings
fd043854-2f92-5a00-80d5-592e69b47e9f | note | ○ VicRoads: Section 204, Section 173
eceda683-4a91-57b7-aab9-bf4e229fef1d | note | Acceptance Criteria - Geotechnical report to be conducted to ensure piling pad suitable for requirements
b331b9cb-b9c2-568f-a5d6-d3795af36da7 | note | ○ Attach: Geotechnical report
82a67f0c-30ea-5939-9fa3-e9842a1d1172 | note | Method - Test
4ac341bf-2965-5231-a614-459671160e1f | note | Frequency - Each Pad
adb851c1-ee18-5ec6-b8e7-faf15df517fa | note | Category - HP
05e4f4e0-f3dc-511d-8bcf-211391a5e92a | note | Responsibility - SE/PE
74025b38-49d3-5954-ba9d-5222ed5cb007 | note | Verifying Documents - Geotechnical report
2d67a041-b849-50d5-b1dd-4decc63c36fe | date | Date Completed:
36d4827e-db04-41bc-87ce-5e3a712b31c3 | signoff | AUTHORITY HOLDPOINT
ffec893a-bcb0-4527-a147-a8401b30e3b3 | checkpoint | Final Inspection
f60d3b44-bdc4-5483-a4a3-1eee406a90d2 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
f2c6bfbe-7e9f-550a-9f3b-0b2d944a2cab | textbox | Name:
5466dd46-1483-57be-849f-5da2107f5ef1 | textbox | Position:
1821eef4-2034-564b-b8c0-9cdd5deec7cb | textbox | Date Completed:
4715b8ca-53c5-4a71-a8c7-6aaacf8ee79d | signoff | Sign ITP
51a0938e-5a7c-4842-ac32-0e92b7284f53 | checklist | ITP-267-STR-FRMS-Bored Piling Rev 0 | itp | ITP-267-STR-FRMS-Bored Piling | d5370d5f-8cee-4eb6-9dbc-1f93b3bb9849
435e7f8a-5dd5-4adc-845d-f3de14e4bf60 | section | 1. Referenced Documentation
30fa9eb1-54d5-49e9-8e49-8bf1f4ed4137 | checkpoint-no-value | Referenced Documentation
c42192aa-d4b5-5fd9-9bcf-d6d26f64b415 | note | Document Title: ITP-267-STR-FRMS-Bored Piling
4a149bdc-a898-555a-b57b-02ce2e96c536 | note | ITP Description: Bored Piling
0b1b98dc-dfc0-5e31-abb0-06ea5f514dbe | note | Discipline (e.g. CIV/STR/RAIL): 267-STR-FRMS
b447205f-b276-5eae-bd24-d749727294cc | note | Revision Number: 0
033a7805-f177-51bc-a6f1-19333f4804e5 | note | Revision Date: 2/05/2025
80b5a59f-7751-57ac-9975-b32315bd1ea0 | note | ITP created by: Josiah Butter
7f0283b6-3b6c-58d5-aff6-cfbcf080fc1a | note | ITP approved for use by: Pradeep Talasila
19416434-8edb-5b3b-bb18-ef5d1c749279 | note | 1.1 - Non Dependent
027bb428-8631-5a05-895f-3a6eb52843a6 | note | Reference - VicRoads Section 606 - July 2017
e1f22c95-788a-57b2-847a-1ec70d82c09c | note | ○ VicRoads Section 610 - Feb 2020
78fa03c9-1c7e-5c6c-a2bf-abddca5c947e | note | ○ VicRoads Section 611 - November 2018
fdc10993-56e6-5d21-8455-860de80aea5c | note | ○ AS2159-2009
abdb3328-664b-52ae-b666-b4859b03999c | note | ○ AS3810.1 2018
2d26dcf1-fa76-5e00-9117-fcae26cc6822 | note | ○ AS5100.3-2017
c6a2b365-012a-4c53-8aed-a7f45829f6de | section | 2. Preliminaries - Materials
12056908-d89c-4491-8cd4-ab76777de4ce | checkpoint | 2.1 - Concrete Mix
7c14343e-7743-5514-a7b2-28d0aa243fa0 | note | Reference - 610.07 Table 610.071
72d0bc57-f998-5ec2-8740-d821aa174d05 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
9885072b-f0d7-5880-bb50-99eafdc51c52 | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
23c8186c-a8ac-528b-8e40-8323405c115f | textbox | Enter: Teambinder Material Approval number
88cf4aae-e7e5-51c0-b02d-7a97245c4c3b | note | Method - Document Review
b70dea5b-3586-59d2-8069-70d293a3efa7 | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
847abc86-a9d0-5537-8a0e-3c24ed6417d8 | note | Category - HP
3765b982-9736-5bb4-86c4-6d484739744e | note | Responsibility - Nominated Authority
dc8b91d4-957a-5132-b873-f3745886a745 | note | Verifying Documents - ConQA Hold Point Release
25333d61-7583-59e4-a9df-4e9df2c28158 | date | Date Completed:
ae74bb3a-4bd7-467b-bb3b-b7e3319284d6 | signoff | AUTHORITY HOLDPOINT
9fcf6047-94d3-4ee5-bd7a-3b6c96315ce9 | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
f80239cf-9cba-5bf5-9bca-994f92041c24 | note | Reference - 611.05 (a)
902b81ce-0cc9-537a-9b95-e1a6333bae21 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
dcc05a48-9bde-56be-9d67-ea3cb68e57c7 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
b97fe18e-df0b-545b-bdc4-19d0be7360b7 | textbox | Enter: Teambinder Material Approval number
b11fa3fc-bee7-56d3-ac2f-f6e03ee18f65 | note | Method - Document Review
54782826-e19b-5f9b-a1ba-6894214a8f41 | note | Frequency - Once for each supplier, 14 days of award of contract
befb7c7e-f08a-58bb-b83f-3c8f6f512fa9 | note | Category - HP
c0970602-acb3-52a5-bd72-541132490305 | note | Responsibility - Nominated Authority
d65de8c9-2e08-5484-96d6-ba755f264e8e | note | Verifying Documents - This ITP
270bc07e-e3bc-5b4c-aa26-87d304dcacb2 | date | Date Completed:
878d6fd1-36cd-46ae-82ae-a85e96078e73 | signoff | AUTHORITY HOLDPOINT
9d1878a7-2a54-4050-ad08-db83fa7076c2 | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
85a32269-5387-5c83-b580-92c1e23052e5 | note | Reference - 610.26 (a)
94599cad-7c6f-5670-8b2e-4def75379a0d | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
25d39b40-3577-573d-b08e-818b8833e39b | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
21305f13-31fc-54d0-beb7-82e3b46602cf | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
d2839496-436f-5689-9b13-e8527d6dd1e1 | textbox | Enter: Teambinder Material Approval number
9ee6e29a-327b-5d1c-98ae-920efa3a277e | note | Method - Document Review
c7744c6f-0c9a-5935-836d-89e27877f0bb | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
3e6bd23f-6c22-5475-aaad-ce64f476da33 | note | Category - HP
7b99f4bb-bc62-5649-8a0c-f695f8ff9762 | note | Responsibility - Nominated Authority
bacccb94-e0eb-5ec9-8acc-570cbf9b6a2c | note | Verifying Documents - This ITP
bae7ee77-23c4-5bf5-af08-814963fed4bb | date | Date Completed:
27a3acbf-130c-4084-8ecb-ef4712f04635 | signoff | AUTHORITY HOLDPOINT
1fa3923d-d93f-4420-b92f-5d06da68ecfb | section | 3. Preliminaries - Procedures & Documentation
1f839cc2-8102-44dc-b782-03a5ba0554b5 | checkpoint | 3.1 - Working Platform certification
fb1e6fda-e25c-588a-bb68-8ced28388598 | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement. As per seperate ITP.
ac96c0c7-65dd-5a54-8e14-c8d34216c7a6 | note | Method - Document Review
aa82f468-4153-5fb1-985d-2edb622d7351 | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
0b2b4e85-4e21-5451-9fc6-9b918c7f8039 | note | Category - HP
f98e7eb5-ea77-576f-af7f-ca1a9843471c | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
6005782c-6484-597d-983a-9555b4ca4559 | note | Verifying Documents - This ITP
1fcfc16d-bc1d-5d4e-be22-7a8bb25ec295 | date | Date Completed:
78084f4a-903e-4635-9d1d-fc6b1291ec75 | signoff | AUTHORITY HOLDPOINT
2ed64138-2dfa-4cbf-9403-c8c90d2a8bf2 | checkpoint | 3.2 - Piling Operations Work Procedure
8771e1d3-99d4-543a-8d20-06f2803de72c | note | Reference - 606.03 (a)
54b29904-0052-5a97-83a7-7b7ff559c578 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
ff13ba77-7ae6-5711-9aa8-789d09f80056 | textbox | Enter: Teambinder Approval number
3b22c06a-f83a-5a63-b129-62d1a3cb28a5 | note | Method - Document Review
ad48d824-6d4b-541b-80d4-5036e3fa8ae9 | note | Frequency - Once, 4 weeks prior to the commencement of piling
79ac8390-0cc5-5b6e-a7b7-f4673af222c9 | note | Category - HP
646dfeb7-60f9-50dc-a606-7b0783367e2f | note | Responsibility - Nominated Authority
b38468ad-6f75-5929-ab4c-3f091822766d | note | Verifying Documents - ConQA Hold Point Release
c3aa1e8c-cfdf-5e2e-86f2-a90a09c38d32 | date | Date Completed:
ab436573-4bef-468b-b6f8-7089c687ddd3 | signoff | AUTHORITY HOLDPOINT
46c77438-fe19-4fa5-8f2f-f648e7f68d51 | checkpoint | 3.3 - Temporary Steel Casings
f2260bef-66f5-5d1b-a844-081b366c1c92 | note | Reference - 606.03 (b)
483e8d91-b587-5305-a2fd-c1c325c23329 | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
fb06f25c-ace3-54d3-bf50-c5f05640c54b | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
52c12008-73dd-5f5e-a82e-0a95b2c944be | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
01535239-65ee-52a9-9d1b-c865d828e571 | textbox | Enter: Teambinder Approval number
671af1dc-ed58-504f-828c-712883b6a145 | note | Method - Document Review
ffb93f20-995c-52ef-b8c6-a9821152f729 | note | Frequency - Where applicable, once, prior to use
29d1b714-6536-5eee-b2db-fb5a9b33d579 | note | Category - HP
8c015494-e3b2-59a7-b1e2-d3e16d42cbe4 | note | Responsibility - Nominated Authority
7d31613b-a8dd-510f-a5d9-3d5caf6ece16 | note | Verifying Documents - This ITP
c1ec556c-9bc0-597d-a3a5-6ff2bd77653a | date | Date Completed:
64853616-50f4-41d1-a01c-4bac45dc788d | signoff | AUTHORITY HOLDPOINT
a3a53d7d-d540-473a-b33c-b5b5697f0b5d | checkpoint | 3.4 - Casting Under Water Procedure
90e7abeb-be51-5474-98f7-8adfae857f47 | note | Reference - 606.06 (a)
8ac96d7c-aad4-5886-a362-43efb867cd0e | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
a47c18dd-a701-5259-a756-4531461c98a3 | textbox | Enter: Teambinder Approval number
76183c08-e292-58c4-9586-8a057371bb2e | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
d5e1068d-a1d8-5eb1-a202-94ae9b7c2170 | note | Method - Document Review
b940b74d-0d12-55e5-bbc0-c248649cc5a4 | note | Frequency - Where applicable, once, prior to placement of concrete
0bb768a8-ca64-55cc-901c-28beff573fab | note | Category - HP
e95cbd9b-d724-5fd0-a912-b7f6198e9e82 | note | Responsibility - Nominated Authority
68102d5e-340e-5cb7-a67a-6d4880346e3c | note | Verifying Documents - This ITP
c99ad835-8e33-5eb7-a45b-d42e98362489 | date | Date Completed:
86b06215-d81c-42a5-b82e-62a567e280e3 | signoff | AUTHORITY HOLDPOINT
30c57c0b-11f9-4143-b78a-8cb131b542b3 | checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
5bd57911-a860-5371-9ad9-4f36b66fcafb | note | Reference - 606.03 ( c)
4ceaff01-88de-562d-aa8d-6b93d86ed933 | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
56596b34-2765-58e0-9a84-035c3782dc1e | textbox | Enter: Teambinder Approval number
4a02bbdd-2243-587b-84e1-582727a94982 | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
7fa466e5-c170-522c-beb0-4cc68db3db3a | note | Method - Document Review
49b94234-61bc-55e5-8619-8ad6bb3eb1d3 | note | Frequency - Where applicable, once, prior to commencement of boring
b93fa872-4a50-5385-b300-90dac5414418 | note | Category - HP
82370923-87a4-5092-ac16-776b425aab96 | note | Responsibility - Nominated Authority
837ee51f-a679-5d87-a777-b1c8c0d5b90c | note | Verifying Documents - This ITP
de75a829-1146-5bfe-8e18-35330cb974a7 | date | Date Completed:
6b1a7b40-6bf0-432e-ac60-c0a1f6bc8df0 | signoff | AUTHORITY HOLDPOINT
3851dcde-845d-475e-bced-70897db25916 | checkpoint | 3.6 - Dynamic Pile Testing Procedure
4b14f575-9bd0-5865-8343-d890b48f6b91 | note | Reference - 606.07 (c)
03554a4f-a135-5720-8de1-a556af3ec582 | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
c3b43415-36d3-5716-9308-55ba043a8086 | textbox | Enter: Teambinder Approval number
e29cef1a-0105-57c2-bd2f-bd42fe996635 | note | Method - Document Review
1861d998-9bd2-58df-bc67-68eda96c358b | note | Frequency - Once, prior to testing
f197b01e-b9c3-509a-af31-a86c9d62138f | note | Category - HP
20f84387-1a36-502b-b4b8-a5cbae3937f0 | note | Responsibility - Nominated Authority
df915e5f-f599-58b2-be90-089b61c2c41b | note | Verifying Documents - This ITP
3545f83e-5315-5192-9e7e-3c51b17ff25d | date | Date Completed:
fa3cc0ee-67eb-4798-9252-af96400ea939 | signoff | AUTHORITY HOLDPOINT
866809d7-2705-4ce8-a6dc-99c35a576c46 | checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
5cd54c6a-d4cc-561d-ae62-b6aaa55976be | note | Reference - 606.07
9f7bc0fc-13dc-5d15-9f54-56a173995b4a | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
713d5da3-fbb7-580a-99e2-774af3f91c1e | note | ○ Details of the consultant to be submitted for review to the Nominated Authority.
bf909260-7659-58c1-b2a8-33acf05c437c | textbox | Enter: Teambinder Approval number
54b8ec0a-8ae1-500e-83cb-42566eff4cd5 | note | Method - Document Review
b4a812a9-b3e0-52d6-a713-7bd5dfb88001 | note | Frequency - Once, two weeks prior to testing
dfa790fe-3411-5de7-b78f-c8c2754e215c | note | Category - HP
e00d8a7c-c8a3-5036-8bb0-5a9e1fc14585 | note | Responsibility - Nominated Authority
ddb27f53-1cd2-533a-863b-4b1a09d363d3 | note | Verifying Documents - ConQA Hold Point Release
230973a1-bbcc-5a97-b19e-69dddf3c3669 | date | Date Completed:
6ae6eae7-e15b-47e3-b3b9-31fb6437c244 | signoff | AUTHORITY HOLDPOINT
fb078936-8ee1-47fc-b3a6-1e335ae2293b | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
d625b266-00c4-558e-b742-405037f6ee3e | note | Reference - 611.13 (a), AS/NZS1554.3, Clauses 3.3.2 & 3.3.3, 611.14 (b)
1c7978e2-55e0-5341-8909-94169f84c081 | note | Acceptance Criteria - Welding of splices in steel reinforcement, including to other steelwork and to continuity bar reinforcement, shall not commence until the welding specification & qualifications (including macro inspection) have been approved by Nominated Authority.
146419c3-8237-50bb-ab22-691c2a383f62 | textbox | Enter: Teambinder Approval number
bac1702d-6829-5e88-9a4a-aaee1f4c3a27 | note | Method - Document Review
33ef7f1c-d0dc-557c-b0cc-6648e4c59d82 | note | Frequency - Where applicable, once, prior to welding
0c181595-17db-5af0-b7b1-5a01b84a124b | note | Category - HP
07968312-5bcf-554a-b83b-ed4b56d13a02 | note | Responsibility - Nominated Authority
c24203f4-4b0e-5e6c-9d06-23d4ce4b2e9b | note | Verifying Documents - ConQA Hold Point Release
471c12b7-7193-52a9-8c7a-0b9395d7aae0 | date | Date Completed:
26a885a8-11ac-43cc-a22e-250f3ba1fec4 | signoff | AUTHORITY HOLDPOINT
8bba4dfe-ee56-497f-9277-ec64e0816b5b | section | 4. Pre-construction Activities
4b042224-418a-4a61-8dce-560511d39b8f | checkpoint | 4.1 - IFC Drawings
e0aa027c-2e70-5598-81c6-cb64ffb639e8 | note | Reference - MRPA Quality Management Plan
4e3a1cc5-c2d1-58d7-b081-7e494015c87d | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
a75919d5-7ce8-5003-b4be-a4eecb9ee297 | note | Method - Document Review
829596f6-0f5b-54e0-8164-6cd414682a32 | note | Frequency - Prior to starting Works and at regular intervals
a7055d5b-7b3b-5841-abf8-8d4f3e5d70ef | note | Category - HP*
167ada3e-6e21-50c9-a861-87d771d67901 | note | Responsibility - All
d0dc9b62-2f93-5c9b-95a2-070455dc0b08 | note | Verifying Documents - This ITP
572f422f-5092-54bb-9738-86bfa64e97aa | date | Date Completed:
462067f0-ead4-4818-bd2f-047f8688e8d1 | checkpoint | 4.2 - Survey Set-out
2fac1b1b-5268-5ec8-a37c-cdeb08e48d5a | note | Reference - IFC Drawings 606.08 (a - c)
3bf0eb46-dee1-56be-93d1-29b9358f176a | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
c9acb43d-9b26-5da9-b833-bad92b8aafaf | note | ○ Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
5a6d2740-34c0-5b13-9b87-aae9e235bfea | note | Method - Measure, Visual
5f1e3e2f-dbf2-53b2-943d-486176937d17 | note | Frequency - Each pile
5d28d873-e73f-5223-963d-09cce1d4bf78 | note | Category - IP
5569445a-d2e7-5e7f-a9c7-254fce4122d5 | note | Responsibility - Surveyor, SE
3fda7043-8ee1-5007-ac32-94489f5b677e | note | Verifying Documents - This ITP
1affec24-38b9-5f6c-94be-ddc380f64fac | date | Date Completed:
1da87081-de1f-4db3-8c96-c1000e0ead51 | checkpoint | 4.3 - Protection of Adjacent Piles
791fa5cd-7c60-513e-aab3-1bcb17afb7e4 | note | Reference - 606.04
b6c20e89-fb8f-55ea-b4da-10c8163f2c56 | note | Acceptance Criteria - Pile construction shall not:
5075920d-5689-57ea-9990-d045777208f2 | note | i. result in damage to adjacent newly cast piles due to ground vibration.
b8529006-8e77-5164-adba-0406714a08db | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
431073ed-a1a7-5825-8729-03e3f223fffd | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
7a3d8b86-afef-5075-a3fd-0b6610aad167 | note | Method - Measure, Visual
bb1a647c-416b-576e-89ca-5cdfebbdb43f | note | Frequency - Each pile
40096995-c9d6-5c49-adf9-2cc439ec151a | note | Category - HP*
ee59f1dc-2e23-547d-8986-197219a9579a | note | Responsibility - SPE/PE
3a2c33ac-ae69-579f-93a7-8cef4cdbbef0 | note | Verifying Documents - This ITP
789b749e-9d5d-502e-9f32-24e86ac80242 | date | Date Completed:
d4500907-a759-4da9-aa95-45a9e5452650 | section | 5. Construction Activities
c0a1e21d-9be2-4f5f-b1cb-f9f969014792 | checkpoint | 5.1 - Boring Operations
ca0fc4f2-972a-575c-99e1-41e33ac0765e | note | Reference - IFC Drawings 606.03 (a)
1c5b31d7-3856-5072-a64f-94ce651dac82 | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
c9546d7a-bc1a-5578-96e8-2be7c6b14b86 | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
9edf0955-bcb0-5942-b796-68128e946dde | note | ○ Excavation clean and de-watered (where applicable) for inspection.
8260ede7-e29f-55f0-a3d7-bb628b2441bc | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
ac869461-4b5f-57b0-9c5e-ad4ecbc229b8 | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
8b842d80-0b27-5196-b48c-f7ee6bac620a | note | Method - Measure, Visual
75fd0f1f-0253-551b-8229-4df690a34caf | note | Frequency - Each pile
5bf06b63-dd8b-5a31-b7d4-28ef7778734b | note | Category - IP
87d1f1b9-be51-5f94-b6db-5fba3802729f | note | Responsibility - Surveyor, SE/PE/SPE
f0c4e915-3bcf-5304-9464-26b7fad0535e | note | Verifying Documents - This ITP
2341677c-0503-5786-9022-d8862dab65a3 | date | Date Completed:
b9f41d5d-345c-4302-9377-8741f6d4894e | checkpoint | 5.2 - Formwork Extension
f958d514-0845-5f81-810f-504220c29596 | note | Reference - IFC Drawings
4c91eb24-85b1-5171-8731-dd05716cded5 | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
abb3c275-3270-5474-98c4-c53fde4d639b | note | Method - Measure, Visual
69bc9516-9345-51fc-81c8-d8c6b129955b | note | Frequency - Where applicable, each pile
3cc9d363-6b3b-586a-8b37-850bb670340b | note | Category - IP
9f2c0a3d-71af-5c3a-8950-874d88f27e91 | note | Responsibility - Surveyor, SE/PE/SPE
adea69dd-f446-537b-a242-8d87b19105c5 | note | Verifying Documents - This ITP
24bdba8e-2a8e-53b0-9819-08e55259d7de | date | Date Completed:
2ffa00dd-eb3f-45cc-b73b-f73d93f4b426 | checkpoint | 5.3 - Inspection of Pile Excavation
7c5436d3-d090-5a78-9bb9-6ea3a6f7d500 | note | Reference - 606.05
3810a66d-5454-5f46-952f-6c807dce6e67 | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
09dff56f-d687-5f6d-b559-491bc26a111c | note | ○ Attach: Geotechnical Field Sheet or Report
d37b9f4b-4d72-59e3-8f14-65287abbd0a7 | note | Method - Measure, Visual
db5719d9-4cb4-548b-ab42-f76afcc1b764 | note | Frequency - Each pile
40bfaba2-7065-54cf-bcb0-32b7c36ea8ac | note | Category - HP
fa3a9286-6a99-5888-a864-989c4dc6d7ce | note | Responsibility - Geotechnical Engineer
c7c7f450-ab7b-521d-ba8a-afdf5414f4e7 | note | Verifying Documents - ConQA Hold Point Release
fcd7b6db-e9b8-5f15-98df-946167a0b7a0 | date | Date Completed:
ab88190c-a67c-4b18-b83e-4730b165cad2 | signoff | AUTHORITY HOLDPOINT
2d39ae0f-d5a5-41ff-9f77-3d4de5642f6b | checkpoint | 5.4 - Reinforcement - Placement
33bf6f19-5883-5446-97df-fa29c7ddd9c4 | note | Reference - IFC Drawings
181641b1-934f-5a7b-b635-1a6f1f93c6aa | note | ○ 611.06
02a6b400-641a-5c16-9141-e50cd5efd980 | note | ○ 611.09
853c149d-be54-57c7-8182-0f8c780c81b0 | note | ○ 611.10
58e3c049-743d-50e7-b004-dd6b84a6108b | note | ○ 611.11
0b781242-a186-5a1a-8875-9ff34b22c5bc | note | ○ 611.12
1b86fac2-5b6e-55d6-9ebc-37b3d5d0877b | note | ○ 606.06 (a)
50db18fa-a2eb-5e07-b428-2e25b2b1a283 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
f2a7afe5-5f10-54ce-9ad9-e1c107405613 | note | ○ Projecting reinforcement is the correct length and location.
4f69b58a-2ffa-5f01-be60-f36ece0497c9 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
45e6c2c0-95c3-5ab2-b763-a4d428991c1a | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
34fc5458-294c-5b86-9ee3-f3a5518b1dd3 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
b499a474-469c-5d2a-9b61-69b3d87b1832 | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
ace927f8-8805-51b0-8e0d-ed01a68f2abc | note | Method - Measure, Visual
9e0cca1a-9ec9-5101-af08-0e345ab50e52 | note | Frequency - Each pile
48076c0e-4dd9-5025-8555-2b2685422c6e | note | Category - IP
5314361c-87a6-51be-b06f-5000f59bf73f | note | Responsibility - Foreman, SE/PE/SPE
8110201a-45d9-56d3-971c-9b8534e7aaf4 | note | Verifying Documents - This ITP
6efd9af8-eaec-5433-8bd3-c82580f279b8 | date | Date Completed:
7d448237-c9aa-482c-9cbd-9bd411db4c24 | checkpoint | 5.5 - Reinforcement - Electrical Continuity
e91140d7-34b7-5352-b7f8-d9eddfc75f92 | note | Reference - IFC Drawings 610.29 (d), 610.43
8c56f79d-b520-564c-8786-4e18ca340169 | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
ee9c636b-378d-5b88-9283-a4e584deb73c | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
1dcc42f7-8f48-550b-9c62-9dc838b47188 | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
b5dade2c-8e49-50b6-915e-84e53ac4f96b | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
059db058-e56a-5b53-8b11-a7916f800fb6 | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
ac9b2bb9-a40b-5757-a931-4c1dc2639852 | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
01bad09d-5b2c-51a7-88ba-1c0460c20932 | note | Method - Measure, Visual
e5a28103-e1d6-5fe6-8423-dae3a198ea27 | note | Frequency - Where applicable, each pile
af2ee639-45c0-5cf7-82e2-dc57283713f2 | note | Category - IP
85ace568-58fc-5024-ac25-274749faece8 | note | Responsibility - Earthing Engineer, SE/PE/SPE
2a0c4c26-e4e3-5108-80cd-f1c5bc4d3d92 | note | Verifying Documents - This ITP
75f3fd9c-5e19-5a18-b25b-027f3df01799 | date | Date Completed:
1d33ec60-1360-4f0e-ad86-c8b8182488ef | checkpoint | 5.6 - Cast-in Items
e016e99a-9cc4-528b-beff-c0a32141fda7 | note | Reference - IFC Drawings
aae87dea-211c-5f1c-962b-60cbcbb51c26 | note | ○ 610.46 (a), Table 610.462
3802e9e6-309b-5871-b012-c7394ac6604e | note | ○ 610.47 (a), Table 610.472
31f1f6dd-8e3b-5090-a6f2-289a457e41c5 | note | ○ AS3810.1 Table 3.3.6.2
095c28ff-6103-56fe-be1c-16a6bd28aa76 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
3db3869a-38c3-5c55-87fe-7b0864c73db1 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
395202ca-60d2-57aa-aefe-2d7d6450b562 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
91a03891-b6e4-567e-8ebf-51580338f80f | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
17e2b36c-25f2-58e4-9d04-d1db9e3fb9ce | note | Placement tolerances to comply with the IFC drawings, if not specified, use the following:
7a34b9e1-c050-5e06-aa10-e909106399f1 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
48520b6a-935e-5a41-a49a-66120d532f5e | note | ii. Running dimensions of a group of the above = ±6mm
831cbe10-8238-517a-8f15-89d433033db7 | note | iii. Ducts and conduit location = ±12mm
3c9ab8b2-4076-5929-9bb1-59b7967bafb2 | note | iv. Diameter of ducts and conduits = ±3mm
22167460-c994-5cc5-87b0-40ebbaae2151 | note | Method - Measure, Visual
6e0c6107-604c-59d0-aeb0-e0ceec076ff7 | note | Frequency - Where applicable, each pile
4a918ca1-f798-503d-a9b0-bf418f1a8599 | note | Category - IP
c9c27a21-7634-5e92-a9fd-f6ed4bd67f8a | note | Responsibility - Foreman, SE/PE/SPE
9a8d07a2-9513-56d8-b2a6-1f29f225154e | note | Verifying Documents - This ITP
08187822-35aa-54ee-8902-67a221366568 | date | Date Completed:
862c139a-20e9-4b32-982d-d2a4efbf406a | checkpoint | 5.7 - Pre-pour Inspection
983f716d-0697-5633-895b-88e730b94d3a | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
9e936641-885d-5268-90b5-b62d634d6c08 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
37e92b26-ba32-5530-a9c4-b9a008c8aa73 | note | ○ All foreign material has been completely removed from the excavation.
a4270691-53d3-5066-bf7f-b64ce7f79ac8 | note | Method - Measure, Visual
15da5614-f30a-5ea7-ae80-19a8eeee59a1 | note | Frequency - Each pile
f3f997aa-5c64-5654-8e3f-0712dfef5399 | note | Category - HP
cfff0408-4825-5fe3-bedb-87578dad629e | note | Responsibility - Nominated Authority
654703b4-e6f7-5401-961f-d9e9790f1575 | note | Verifying Documents - ConQA Hold Point Release
259d350d-8b4d-560f-897c-a2307ee952a6 | date | Date Completed:
7bf63a9c-e332-4606-bdde-7e6af2d42767 | signoff | AUTHORITY HOLDPOINT
a75c698c-aca8-43ac-b16d-8933a025129c | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
23dceafd-060c-5524-823f-9fd092598ff9 | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
09d7bcba-a0c6-526f-88dd-dd005da6b557 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
2ab41394-c260-5629-8bfc-026ede19ec37 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
7794fb8c-e884-5c1d-ad25-c26aac933cec | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
16034cd0-3ba3-5e95-84e3-a1d9ee5078e2 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
f94f0d11-856b-5455-a360-96235f455a88 | note | ○ Record: Required information on the Concrete Pour Record.
d71279a2-6025-5e51-b162-ca7d70fbff50 | note | Method - Measure, Visual
c7711ef4-6626-562c-a88f-41d97dd41ef9 | note | Frequency - Each pile
bbd8f6e4-5c36-5ab3-91ca-dc4b964bedf1 | note | Category - IP
34641f33-b9ef-5755-bc5e-eb554df0f420 | note | Responsibility - Foreman, SE/PE/SPE
4a3849dd-c10b-52eb-b8c0-4b4afef308ba | note | Verifying Documents - This ITP
211ecde0-b509-55d1-a561-4924881c80b8 | date | Date Completed:
7957d5d3-d55c-456c-ac44-71ac3a819751 | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
5f3a85f7-cad2-53e8-967c-6e619a367988 | note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
22ae426c-2eda-5507-a129-da984d66f170 | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
5758f4d1-f0da-5c05-afc7-06904de2b81a | note | 0m³ to 10m³ = 1 sample
201eb709-4fa5-5705-87f0-80c9efcc0f65 | note | 10m³ to 25m³ = 2 samples
c79729cf-83da-5674-86c7-9fabc021d739 | note | 25m³ to 50m³ = 3 samples
aabcb1c0-c828-549d-bb2f-1d68829d53c0 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
c03202df-1419-5067-ad99-6220cd2754fd | note | ○ For each additional 50m³ an additional sample shall be taken.
abd6bfdc-ed19-5316-8dac-bf5e41322a60 | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
7eaf15e7-52ea-5595-944b-d3b737cd760d | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
d478d006-7e2e-5815-9f3e-033d535f6ba6 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
ff087650-de92-5daa-8740-3d008358c2ef | note | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
c68fce88-f48c-52ee-83ba-dfd3f5924f3c | note | ○ Record: Required information on the Concrete Pour Record.
4aed8c0b-b4ba-5787-b16c-016ca35e268b | note | Method - Test
e1fa54eb-21ef-54da-85c2-1b3658fb5640 | note | Frequency - Each pile
7d22103b-8fba-56b6-a80b-ed27612b7375 | note | Category - IP
95fcf654-e5f7-5f5d-abad-e8ebb6220b81 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
85b1b33e-ccfa-5638-9cec-cf1b42ae67ad | note | Verifying Documents - This ITP
27cc5878-52fd-51ce-ae5c-5c82bfcb2e2e | date | Date Completed:
5908f7b5-c425-461a-ac6b-da9619d31d20 | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
7ca7f11f-47c2-58f8-b7a5-a8159ce82bfd | note | Reference - 610.13 (b)
e656649b-1670-59f2-852b-f6e9829495d2 | note | Acceptance Criteria - Spread range = 550mm to 750mm
c2d7db66-c97f-5fd3-ab20-dee25575a1f1 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
1ff8bcf1-891d-5576-a37b-57b37634a071 | note | ○ Passability = ≤10mm (aggregate height differential)
60e27b89-5d07-530c-b20d-63a782ad0d91 | note | ○ Record: Required information on the Concrete Pour Record.
7649e75a-5e94-55f8-9fba-f9d2c04e63ea | note | Method - Test
8487ac1a-03de-52d2-b3fb-b3b73c46ec14 | note | Frequency - Each sample of Self-compacting Concrete
65f8df8e-ab31-5da2-a838-744e49f74aff | note | Category - IP
38bf445e-7fdf-575e-a289-51895dbc2157 | note | Responsibility - Concrete Tester
9394c2a5-34ad-5047-a3a2-8d44975dc8ff | note | Verifying Documents - This ITP
b088edef-b38b-51f5-95c3-12d2273a889e | date | Date Completed:
aa971382-c0ee-4787-9b09-3429ffc9144b | checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
bf9ee21d-4811-545c-b646-033bf3aaec94 | note | Reference - Site Sampling & Testing Procedure 610.16
f08d2395-221a-5213-b028-d75c55ce830e | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
0b84023a-fdfb-53a9-b1f3-33b6cfdef7ab | note | ○ Record: Required information on the Concrete Pour Record.
232a06a8-fd56-5aa4-b3d7-e003791990a0 | note | Method - Test
76ad34c5-5660-5a97-b228-21b73c4994f6 | note | Frequency - Each sample
19ee1aaf-4ebd-5b3c-b2b2-83865561f40c | note | Category - IP
aa3ca17f-73e2-53cb-a0eb-675ba436d124 | note | Responsibility - Concrete Tester
c85c4ef8-cb6d-54f1-b691-4bf27d16e5d8 | note | Verifying Documents - This ITP
d082d75b-a7c4-50a1-81d7-e1c19043ada4 | date | Date Completed:
f0fdcc3a-7d20-4eeb-b29b-43c2901224b2 | checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
867cf334-f6a9-5e7e-8217-2e43c7167e8a | note | Reference - Piling Quality Procedure 610.18 (a) & (b), 610.18 (d) (i), 606.06 (a & b)
0d76fb5b-8cb4-5f49-92d1-7b9438ebd244 | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
3d0266cf-295f-533a-ad10-4e9c17ffaa3a | note | ○ All concrete batches are traceable.
afab8f41-4035-5c16-a7dc-7ad364759827 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
18599cf0-1688-527b-a50a-d4010d038e9b | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
6e8de64d-ad9a-5a6c-b00d-069960717f6b | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
cd3f3af1-85f6-5afc-ad72-9b038cb8fb09 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
39fbde60-84a4-5111-9896-52eeda25d6cf | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
5a50386a-8d0c-5a4d-9458-447900445dfb | note | ○ Record: Required information on the Concrete Pour Record.
78ddb646-4eb0-5f02-99a6-a24c5e25051d | note | ○ Attach: Concrete Pour Record
c4bbd2bf-51c1-56f2-833f-e098cd879349 | note | ○ Attach: Concrete Dockets
2dbeaf36-c6c1-5aef-94d2-a17f61c6a7e5 | note | Method - Visual
5ff0bc44-ac52-5c8d-8303-42e2022feb78 | note | Frequency - Each load
2c21c035-9f07-589e-b2d3-223f8238da62 | note | Category - SP
8e566f94-49eb-595e-9c55-9d0d404cf01f | note | Responsibility - Foreman, SE/PE/SPE
0f99d48d-a787-5282-9358-df07a2d759fc | note | Verifying Documents -
43f8ee68-b3cd-5cd4-b3ca-2de8a31dcbc8 | date | Date Completed:
68b4b292-a263-476a-81b3-0b47669a1fcf | checkpoint | 5.13 - Surface Finishes
87ba1e24-01db-5877-991e-4bda2c378b85 | note | Reference - IFC Drawings 610.31, 610.20
9cc7b9c8-8e4e-5ef6-9bce-c813d6b7921a | note | Acceptance Criteria - Surface finish as per IFC drawings.
23ee7d8f-26bd-57d7-89d9-f980344fde9c | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
377e837e-277c-52c4-9acc-2f4dfcff4711 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
b65abd0b-a91f-53ae-a89b-f9fcd40645e4 | note | Method - Visual
68152aca-b50a-5056-a20b-a604799baac5 | note | Frequency - Each pile
f1c61d1f-139c-5a22-9bc9-d774825eb62c | note | Category - IP
eecf091e-a775-5248-a30a-9de5c41c478b | note | Responsibility - Foreman, SE/PE/SPE
5519d932-d486-5c8a-b83f-a4339468f7ed | note | Verifying Documents - This ITP
1da00348-96b3-54c8-a3c0-b80ac5f438b7 | date | Date Completed:
b004006b-a13a-4058-9ee8-2001099f4ea3 | section | 6. Post-construction Activities
247dc9b9-950f-460f-ad17-195212ba90ef | checkpoint | 6.1 - Pile Trimming
9473882f-e0ed-5a01-a819-c660e5d419de | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
128dbafc-d3c7-58b4-ba7b-056d90259ea4 | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
9acfd89f-fe66-5081-87b8-89cf4ba594ca | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
a55939c7-e7b5-5446-9bf1-f0c314251687 | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
312ad7d3-00e8-51a0-8844-376a70ec3782 | note | Method - Measure, Visual
48f7f275-a4ba-52df-819e-6859857e5318 | note | Frequency - Where applicable, each pile
c1860af6-74ba-5cf1-b2fd-76d0e2157f84 | note | Category - IP
9365a3f6-58fe-5ab1-bc7f-d7901f94ff31 | note | Responsibility - SE/PE/SPE
37f2ed67-88fd-55f4-8d21-ca9a16889260 | note | Verifying Documents - This ITP
e80280b8-cc14-59bd-a30a-90179e83f766 | date | Date Completed:
ad01b2fe-521e-4f7f-8296-3c57bfa13dd1 | checkpoint | 6.2 - Compressive Strength Test Results
06f4facf-b7bf-53f1-a2ab-79e5279e1a11 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
e7b33a4f-d82b-50f3-a6cd-77a09718583b | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
b1cc0559-308a-51ea-ad03-c2a16e2e7b82 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
0b2f8ce9-5970-5033-a9ec-f9e454d0b95d | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
a7539862-476d-55d2-84c1-671e005fe226 | note | ○ Attach: Compressive Strength Test Results
95a2bf9b-50b4-531b-a54e-6741f6469172 | note | Method - Document Review
78ce8f63-9b50-5ce1-be3c-cc8828bb1de5 | note | Frequency - Each cylinder
7758229d-bae1-5f3d-9a0e-4f64a1629e91 | note | Category - IP
e3731ec7-f5fd-5781-8dd4-2515b97ebb34 | note | Responsibility - SE/PE/SPE
876b4966-3302-5ebb-9dd4-6333e5941702 | note | Verifying Documents - This ITP
0459d605-13ac-5f12-83ea-3d1d3532f792 | date | Date Completed:
d95797ea-0c38-4b3d-9d44-bcfb13f21cd3 | checkpoint | 6.3 - Pile Integrity Testing
55261091-5f1c-5bd6-9194-64391e6df3e9 | note | Reference - 606.07 (a, d & e), AS2159 Clause 8.8
837121a8-ce4c-5d50-8368-006121ef6e0e | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
b88a093d-c4b5-5462-9e1b-51e549bcf255 | note | ○ Cross-sectional area = ≥95%
4393e93b-47df-52bd-9699-d34a7712f396 | note | ○ If any test fails, all piles shall be tested.
321edbaf-b182-5302-a4b1-27d039e26db1 | note | ○ Attach: Pile Integrity Test Report
66f0ca30-aa6a-5de8-b87f-01cec0a86ea7 | note | Method - Document Review
a63a4c09-d97a-5bfb-88e1-e3a4000ee522 | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass
30eefc79-a063-5827-af04-b2cf185183cf | note | Category - IP
93954098-6d7c-5975-ab40-a70dea945674 | note | Responsibility - Testing Consultant, SE/PE/SPE
715da633-5979-5307-8c40-067100f15477 | note | Verifying Documents - This ITP
fc4d9870-1b36-562d-aa6c-dc22cfc67966 | date | Date Completed:
901ff121-50f9-4415-95f0-0d7abaeacec4 | checkpoint | 6.4 - Static Load Testing
86194a13-ae51-5106-9681-fb396693ed07 | note | Reference - IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
89997f7d-84af-5c22-972d-9ed1878bec4f | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
f559336e-56d9-5786-85ea-ba3d5cd28576 | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
5abbeab7-c1cb-5ce7-9e41-cb764c5caf88 | note | ii. Creep rate = <2mm / log cycle of time at the test load
b3d5bccb-f6cc-58bf-a2e6-7f2191975afe | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
b362a65e-0a0a-5cdc-b838-b93b71aa6325 | note | ○ Attach: Static Load Test Report
bcf2a017-f7db-5153-ba96-da929e9f60a9 | note | Method - Document Review
a0cc013a-7b89-5c9f-98b4-9bc5cc59bc8f | note | Frequency - Where applicable, as shown on the IFC Drawings
0345b044-0238-54a4-95eb-344d62ed6a37 | note | Category - IP
3aa2acb3-2d50-55da-a9b4-507e02944871 | note | Responsibility - Testing Consultant, SE/PE/SPE
7c2790ce-bcb3-5eef-9655-394ca99c0dd1 | note | Verifying Documents - This ITP
7aad26a0-8d37-5632-9e0e-5d7f3f89f9a5 | date | Date Completed:
11554216-ac48-4b81-8aca-28d6cb7d6bc9 | checkpoint | 6.5 - Dynamic Pile Testing
d122e4ca-8714-596c-866a-13053583e4ed | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
f541d0ee-d9b7-5cbf-a8cc-86db5bf07f2a | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
d5182581-6a16-52a8-8ec8-864bc33f5d56 | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
6a7202c6-5a7b-553a-a6ab-0525f2c854c9 | note | ○ Attach: Dynamic Pile Test Report
0795fc4f-d55e-5694-a77b-a43aa237b3a6 | textbox | Enter:
802b8fde-cede-558e-a856-f8348b18d119 | note | Method - Document Review
6d31b09e-5d5d-5658-942f-6e96d3b073b2 | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles.
323575d9-8332-582a-a6dc-57545b9e68ea | note | Category - IP
69cbb43d-1935-53eb-b97b-e3a3c0ed7249 | note | Responsibility - Testing Consultant, SE/PE/SPE
74d5fa10-87e3-55b0-bbee-105659ecf5b0 | note | Verifying Documents - This ITP
7deb2651-9758-5856-8c7d-8e726bc58fab | date | Date Completed:
926f5eb5-1057-4386-8f78-cbcea00fef45 | checkpoint | 6.6 - As-built Survey
9c7c9c48-be0c-5273-b437-b48d6ef88617 | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
0f2d85fc-489e-567d-b1ee-d09e0f008996 | note | Acceptance Criteria - The following tolerances apply to piles:
c8b2838d-eb23-5f97-9cc4-73cfc5b9af11 | note | i. Pile head plan location = ±75mm
014c78f1-adf5-5afd-8fc0-0100eee9bedc | note | ii. Variance from vertical or rake = 1:100
1f0f5705-91b3-5002-8634-4a40a56c9bad | note | iii. Irregularities in straightness = 1:100
a4bd1ace-c396-59a0-a8d9-64ade45cad45 | note | iv. RL = ±25mm
a6002d04-f491-5721-862a-0ae6340d1493 | note | ○ Attach: Survey As-builts / Survey Report
71eb6b2c-b8f8-56b6-b5eb-71f8dc48edb3 | note | Method - Document Review
cc76191f-f7df-5713-89b7-bdd9bfc049cf | note | Frequency - Each pile
f15864e5-f319-558a-8876-e9f07bff20ee | note | Category - IP
07bc7d11-1b0b-5269-bb49-251b0b40037b | note | Responsibility - Surveyor, SE/PE/SPE
c207afdb-6896-562a-82d2-315e041b9194 | note | Verifying Documents - This ITP
927aeaea-4268-523b-bacd-ae08656b7ca7 | date | Date Completed:
1d3fb12b-c475-4008-9909-ef04014dc824 | checkpoint | 6.7 - Non-conformance Report (NCR) Closure
24b7b3c3-eedc-5eba-962e-b589857ba9e4 | note | Reference - MRPA Quality Management Plan
4c4b7e11-119d-5721-8f14-a4895e583dde | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
c499dd27-22f5-521b-991d-580b24379a91 | note | Method - Document Review
d7d1be25-e6d0-5a9f-aaed-7311c18131f1 | note | Frequency - Once, prior to closure of this lot / element / Work area
5f4cd6da-a8ba-5cf9-8024-e6f729f003d4 | note | Category - HP*
97caee4c-bf39-538b-8f50-1b77d23e7d8e | note | Responsibility - SE/PE/SPE
29e6b6e7-c4fd-57c7-a33a-dcf6c250adb2 | note | Verifying Documents - This ITP
309b4c0a-397b-5022-bb65-f4570ff95212 | date | Date Completed:
6d85b0ba-3548-4e23-a93b-8ed406e9d86b | checkpoint | Final Inspection
9dedd267-76e4-5de4-a9d8-4d42c706fa31 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
c9d96ab9-01d2-529c-8ada-70664b5fde62 | textbox | Name:
ac631226-155f-573b-b6f7-b1044c062a3e | textbox | Position:
734fc24e-72a1-5869-845a-9396519c4032 | textbox | Date Completed:
236eff0f-3994-4b61-b374-88118dda255e | signoff | Sign ITP
a5b2dbf0-d3d2-4a2c-b0fb-986f05d12de0 | checklist | ITP-268-STR-FRMS-Bored Piling sense 600 Rev 0 | itp | ITP-268-STR-FRMS-Bored Piling sense 600 | 6ca1587b-951b-49cb-b329-22459cd02360
f0beb1d4-f941-4fa9-a5d4-9be7fb3bab82 | section | 1. Referenced Documentation
ff6ce369-c074-458f-a874-438b7fc30d53 | checkpoint-no-value | Referenced Documentation
f96bdd90-8b1f-5bae-ba06-252b74605e4a | note | Document Title: ITP-268-STR-FRMS-Bored Piling Sense 600
016aa6e5-ee5d-5ba9-a543-005e18095240 | note | ITP Description: Bored Piling Sense 600
fd73048e-20d9-5641-a040-f3303628cb4f | note | Discipline (e.g. CIV/STR/RAIL): 268-STR-FRMS
0cd9a918-16d0-5fad-8569-ea1d9ed473cb | note | Revision Number: 0
7e350bfd-c200-5aca-ba30-1a6949df26a6 | note | Revision Date: 2/05/2025
622b1747-35ff-5137-9b04-137fab9b6d6b | note | ITP created by: Josiah Butter
df2c63a3-8d90-5132-b3e2-47c4112145f2 | note | ITP approved for use by: Pradeep Talasila
b034ec4e-6553-56e5-bcd9-2eaab2c4c51d | note | 1.1 - Non Dependent
cfd875dc-9b36-50ec-bff2-b87ae4c46f3d | note | Reference - VicRoads Section 606 - July 2017
fc73b02a-7c9c-59ea-9cbb-5b2fde94b3a5 | note | ○ VicRoads Section 610 - Feb 2020
961d1964-b4e9-5324-a76b-ccc1f605e5e1 | note | ○ VicRoads Section 611 - November 2018
bf649b14-da99-51f3-8cfe-01c825d20df9 | note | ○ AS2159-2009
5929a162-b9ee-560b-a91b-80bde7c78cb5 | note | ○ AS3810.1 2018
6ef3ed57-05dc-5a00-976f-07ae24a84f53 | note | ○ AS5100.3-2017
8d68d282-3bbc-5af7-abb0-5c25f7ba2f22 | note | ○ AS/NZS 4671 - 2019
d84b23d1-468f-53aa-bf70-5f80a7ba4bef | note | ○ AS/NZS 1554.3 - 2017
13a57bc0-fc0b-4253-bedf-ef39809a0553 | section | 2. Preliminaries - Materials
3832529b-de39-44fc-b70c-635235b134e2 | checkpoint | 2.1 - Concrete Mix
1b4f8f2e-703d-5dd5-808a-8cbd9863179e | note | Reference - 610.07 Table 610.071
f869898a-25b9-57ea-a130-4b19c7a63a32 | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
f3eb4cb7-c847-5f3c-b0c3-68d9ea50e68e | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
6c43f9e3-28b1-54e4-9930-cf1e1e4bff73 | textbox | Enter: Teambinder Material Approval number
8a13be21-cf6f-5242-ac89-2d01ab772a98 | note | Method - Document Review
d6b8575a-2233-57b7-8c87-ddacb980de8c | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
5e50ba27-4830-5010-b584-83972db23337 | note | Category - HP
9a94eb9d-0659-5068-bd7c-a54be7800030 | note | Responsibility - Nominated Authority
514abd9a-8777-53b1-8707-d0a75f03e558 | note | Verifying Documents - ConQA Hold Point Release
c129d1f9-aa6d-5f5c-8edc-76916c5b6553 | date | Date Completed:
099d7dd2-3cda-42af-aa8a-05aedf822b22 | signoff | AUTHORITY HOLDPOINT
4fbde376-d611-4bed-83c1-e1e006c62e31 | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
38122e36-55d6-5ab9-89cd-eaf3a8a7d089 | note | Reference - 611.05 (a)
8f85d7b2-dab4-5e97-93d9-873f9c05185b | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
85cf3f18-9d9f-5083-8190-59a8b19e63c1 | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
f8b4e03d-529e-522e-a355-e6fe223cea69 | textbox | Enter: Teambinder Material Approval number
01dc995b-a069-502c-94d5-f3b1681e6727 | note | Method - Document Review
162cfe7f-7dce-5a26-a04d-f016af23e91b | note | Frequency - Once for each supplier, 14 days of award of contract
adc6b47c-d25b-50e9-8452-1c0cd75d6901 | note | Category - HP
09a262be-b65c-50cc-8e7d-7a84d3e27fec | note | Responsibility - Nominated Authority
bfc408fd-43a9-5dae-8132-452e81ea7c64 | note | Verifying Documents - This ITP
2c31a85e-c1a0-5a98-83c0-5dcd1afd3344 | date | Date Completed:
c5763d31-a7d7-4735-89c2-5c50e4fae421 | signoff | AUTHORITY HOLDPOINT
c79f691e-0a7a-4b5a-aa57-977bfcb12d5b | checkpoint | 2.3 - Bar Chairs/Aspros/wheels Certification
1fc37625-5b45-53a6-aead-8213d98e5925 | note | Reference - 610.26 (a)
f56b3888-5ab6-553c-9bb8-db2177d34d21 | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demostrate suitablity to prevent excessive deformation under loads.
5cf616aa-2428-5180-98fd-a8838b6110c9 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
bc37c3b9-d6b2-568a-8c64-d23b74c564d9 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
01b0c5ea-85d9-56d7-b569-9198f581fe1f | textbox | Enter: Teambinder Material Approval number
c1c0e07c-7f71-5ddf-8895-1c34ab5a32c5 | note | Method - Document Review
11ae562d-453b-51ea-87fc-89d325024fad | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
65217379-dcc1-587d-b7de-d2af5ed7b38b | note | Category - HP
aa68a034-1997-593c-ae6e-741166b7a9be | note | Responsibility - Nominated Authority
57e5a2f3-2e59-50b4-9190-ff4b21cf7690 | note | Verifying Documents - This ITP
1df1362e-efec-5f82-9388-2481d8ddd628 | date | Date Completed:
f1f01280-af09-4c70-b1bc-e47420aeae06 | signoff | AUTHORITY HOLDPOINT
8ef46d36-7c71-4523-83b5-680478bd8a0b | section | 3. Preliminaries - Procedures & Documentation
eed2425c-7827-44ba-a927-7f3847902a0a | checkpoint | 3.1 - Working Platform certification
952cc9e9-8584-595e-90cf-a814c8ea4ece | note | Acceptance Criteria - Satisfies minimum plant bearing pressures requirement. As per seperate ITP.
570c92a2-5769-5908-bf48-3171d27fef98 | note | Method - Document Review
f43bfaa2-0ac1-56da-be85-f24573b27297 | note | Frequency - Prior to works commencing & after rain event which there is >10mm in a 24hr period.
b23c7b83-29d3-5dcf-bca0-092933c82efa | note | Category - HP
1426723b-2566-5d5a-ad45-445c8e096d09 | note | Responsibility - Piling Contractor/Geotechnical Engineer/Fulton Hogan Engineer
93b817dd-edf7-5ae3-9e1d-7c8869b90fb9 | note | Verifying Documents - This ITP
f556b9e4-4352-5448-ac09-4f625e053209 | date | Date Completed:
9325efce-cba4-4e8b-9ebb-f9fc125bab61 | signoff | AUTHORITY HOLDPOINT
f9f2a4e3-6bbe-446f-804f-bf70e3225440 | checkpoint | 3.2 - Piling Operations Work Procedure
e907538e-9cca-56b9-9f64-80c08d5ced70 | note | Reference - 606.03 (a)
8bbf5546-65dd-58c6-a2cf-ef1a25a5fb15 | note | Acceptance Criteria - Piling operations work procedure to be submitted for review to the Nominated Authority.
a469ce4b-1ea5-5073-a47b-8e1bbfd2ea23 | textbox | Enter: Teambinder Approval number
a1e9981f-a526-52d3-871c-212c383d38a7 | note | Method - Document Review
51760cdb-4487-5f82-b9ea-ff1f12a929aa | note | Frequency - Once, 4 weeks prior to the commencement of piling
957942ce-7b23-5f1b-8396-5c66951cec0d | note | Category - HP
b1f79241-69d4-586c-aa63-58b50fcd3077 | note | Responsibility - Nominated Authority
664e9905-63e4-5443-8547-230b616a472d | note | Verifying Documents - ConQA Hold Point Release
1bb6f5e4-1336-5e7b-8ffd-da4ecb3509d2 | date | Date Completed:
a8999f5d-2658-4943-a168-86d198a42a66 | signoff | AUTHORITY HOLDPOINT
ef5e32a8-e199-4871-ae5d-590762ebe4cb | checkpoint | 3.3 - Temporary Steel Casings
2fb4b513-bd9b-59f6-a6bb-f6e649f60359 | note | Reference - 606.03 (b)
db72b5de-bd11-51a7-a5d3-d92bda196a0d | note | Acceptance Criteria - Temporary steel casings shall be free from holes and distortion with a smooth internal surface without any projections.
481d39f4-93e8-5b49-8ddf-39c347834fcc | note | ○ Any splices in the casings shall be able to withstand any stresses induced during installation & removal.
1474498c-b867-5811-abb5-9117cc81fe86 | note | ○ The casing shall be proof engineered by a proof engineer who is pre-qualified with VicRoads.
863c3ed6-f60f-521d-9134-05952b7f7c77 | textbox | Enter: Teambinder Approval number
71aa2470-9ee8-5ee2-8d47-8f87feaa7ece | note | Method - Document Review
a1f1d22b-acde-5b44-ab06-9d5b3fbe7728 | note | Frequency - Where applicable, once, prior to use
41e46475-9988-5fdd-bd78-76707d8beccc | note | Category - HP
29615d17-dac5-5cc9-93ec-b798e948738c | note | Responsibility - Nominated Authority
c7269b03-4521-5e3d-b440-f1dae6753b71 | note | Verifying Documents - This ITP
e7ba6962-701f-5143-89ca-da9dce61a8b5 | date | Date Completed:
d5bc5408-1c99-4b26-99fc-b33469dba6af | signoff | AUTHORITY HOLDPOINT
02897a28-7c6a-4709-b74f-0fae24ac0864 | checkpoint | 3.4 - Casting Under Water Procedure
f7f5d878-a315-5925-aa7b-1917ef44e718 | note | Reference - 606.06 (a)
490376af-9fcd-50a1-b892-c3c314752073 | note | Acceptance Criteria - Casting under water procedure and methodology for removing mud, loose rock and other debris to be submitted for review to the Nominated Authority.
45087c47-d4bf-5355-b394-833e63beca94 | textbox | Enter: Teambinder Approval number
96fe5790-0e35-5fa0-b697-31efba0b0f29 | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
5cf898b6-1a9f-5fa1-a613-e7ac7ee4e427 | note | Method - Document Review
dfd94dcd-5a52-56b5-8070-612e9bf75871 | note | Frequency - Where applicable, once, prior to placement of concrete
190237b9-e888-515c-b4ad-0163efe17303 | note | Category - HP
8e706e8d-f6f5-5637-b267-765401914881 | note | Responsibility - Nominated Authority
a42e21e7-8fbe-56f4-921c-87466cb8b002 | note | Verifying Documents - This ITP
6d9b0ad9-56d2-5cb4-bd13-e041c500babe | date | Date Completed:
a31048b2-458c-409d-88cb-ae590d85fdcc | signoff | AUTHORITY HOLDPOINT
c817e71c-2640-445d-9341-8cbfe26f9d44 | checkpoint | 3.5 - Boring With Bentonite or Polymer Fluids
347813d1-170e-5778-a8c7-af6b63221c75 | note | Reference - 606.03 ( c)
867d8a4a-c9dd-5e7e-b529-cb981d1dd1ed | note | Acceptance Criteria - Boring conditions under bentonite or polymer fluids alone or in combination with temporary casings to be submitted for approval to the Nominated Authority.
35442369-a52f-5034-9085-1ff7836e7cef | textbox | Enter: Teambinder Approval number
a85cd8e9-9cf0-5141-b7f1-059d5318e5cf | note | ○ Note: Piling Operations Work Procedure may cover this requirement - if so, use the same Teambinder Approval Number if this is the case.
81f10e54-1f95-5739-820b-011bbd676424 | note | Method - Document Review
258c82ac-f6b5-5192-81fd-54d33d479ae6 | note | Frequency - Where applicable, once, prior to commencement of boring
55860538-4b8e-5750-9846-c22b260ca39d | note | Category - HP
94a52586-df27-5990-baa2-1bd9c658c909 | note | Responsibility - Nominated Authority
3857e54f-4bd5-584f-984d-94fbb41189ae | note | Verifying Documents - This ITP
efd1b097-da20-5447-be96-a44ee31eab39 | date | Date Completed:
061382c8-ca92-4322-b5c0-497559990cc4 | signoff | AUTHORITY HOLDPOINT
b9fe3ecf-614f-4472-96c1-6f1d2f832e0a | checkpoint | 3.6 - Dynamic Pile Testing Procedure
850c7a5f-de74-5a54-8fb9-a95a3ea4ee54 | note | Reference - 606.07 (c)
d48cd182-c38c-5492-812e-30d55c370d52 | note | Acceptance Criteria - Details of the proposed pile driving rig, hammer size and drop heights to be submitted for review to the Nominated Authority.
9e1560ed-657c-5c27-90be-77e941bbfd3d | textbox | Enter: Teambinder Approval number
4f6727ea-1407-5c9e-b6ef-e429eaaffa02 | note | Method - Document Review
ea2575c7-20f3-5520-99b5-4e094038a752 | note | Frequency - Once, prior to testing
046d3412-af28-57b3-b6ac-dcda81f7536e | note | Category - HP
810c88ab-53cc-54f1-8fdd-00b142593f65 | note | Responsibility - Nominated Authority
1de32b11-1284-5a85-a6d3-e098b7140e4f | note | Verifying Documents - This ITP
766b7427-126a-50cf-95aa-0ff475e69618 | date | Date Completed:
24e32a84-e972-42f6-9df3-a50d656e322f | signoff | AUTHORITY HOLDPOINT
e08ad1f7-4257-4c78-ad8c-43d5371e8180 | checkpoint | 3.7 - Pre-qualified Pile Testing Consultant
3002ec72-5cb6-58a2-8300-af2f18f19454 | note | Reference - 606.07
4806c34f-cfa6-56fe-9520-a0a9dd3ae34c | note | Acceptance Criteria - All testing shall be undertaken by a Vicroads pre-qualified consultant who is independent of the piling contractor.
35e3666b-87c3-5e19-a4e3-861856e4b238 | note | Details of the consultant to be submitted for review to the Nominated Authority.
280208fd-be1c-532a-8658-0786b28d7d69 | textbox | Enter: Teambinder Approval number
400dbd65-fb9f-5945-b293-8bcb8215b8a0 | note | Method - Document Review
60c51048-8ab4-52b8-b4d4-bf86f0b3802a | note | Frequency - Once, two weeks prior to testing
9613c321-db83-5fb5-8418-80e7e70dda29 | note | Category - HP
d6868382-bcf4-5c5b-9770-3aefebfeb2b6 | note | Responsibility - Nominated Authority
97e25707-5bfb-5086-bbb8-498632663768 | note | Verifying Documents - ConQA Hold Point Release
0a44dedc-b98a-5479-bbae-bbcfc0040bdb | date | Date Completed:
91f4089b-575f-4013-984e-bed53c9ab771 | signoff | AUTHORITY HOLDPOINT
5dd03d17-aa01-4a6e-ad20-3a5e4a7ffb20 | checkpoint | 3.8 - Reinforcement Welding Specifications & Qualifications
8a65824b-3c85-5870-b4e1-bb2dfe28d164 | note | Reference - 611.13 (a)
ec9b16cf-a9d2-5c52-9d3c-3eeb7e5e1755 | note | ○ AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
d29b6f3c-383b-531b-aa79-d3a56a242c63 | note | ○ AS/NZA4671 - 2019, 611.14 (b)
815f7a66-6a11-5564-88c9-db5e18f59903 | note | Acceptance Criteria - All welding procedures shall be provided to the engineer and proof engineer for review for compliance with the design requirements.
f40d2fb0-f209-5386-84b9-0861325a87ac | textbox | Enter: Teambinder Approval number
f28190d4-c596-5291-904b-3ac9589b6450 | note | Method - Document Review
bb4b0d20-e5e3-58a5-9765-e0ce724018b7 | note | Frequency - Where applicable, once, prior to welding
ff3fe475-88d0-5625-8a76-ac9294c48802 | note | Category - HP
318af909-b891-589c-ae77-6d0c4b4e5466 | note | Responsibility - Nominated Authority
7361c69e-f8b3-5e24-8e21-58a098c706a4 | note | Verifying Documents - ConQA Hold Point Release
70c99a98-6783-5a6c-a67b-776ee7472d81 | date | Date Completed:
9975506d-abfd-470d-a92f-994616f6c308 | signoff | AUTHORITY HOLDPOINT
2c1e452f-41c5-493a-8799-f0572efb1f5b | checkpoint | 3.9 - Reinforcement Welding Specifications & Qualifications
8e792134-2539-5bd0-9140-1220ee52582c | note | Reference - 611.13 (a) & (b)
effd5a84-35ac-53cd-92a4-002d9b45aa1a | note | ○ AS/NZS1554.3, Clauses 3.3.2 & 3.3.3
45a18704-d034-529f-9cc1-50531d6382f6 | note | ○ 611.14 (b)
45464154-0e80-5d09-b957-0e2dacb51d80 | note | ○ AS/NZA4671 - 2019
29194632-7b7a-5a74-a339-5e67d42221f1 | note | ○ IFC Drawings
35afbb48-5923-5df6-8576-efd46e4932aa | note | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2
ebf57d70-5e0d-5b4d-9e02-1c92ff6f1a84 | note | Acceptance Criteria - All quality documentation and test results to support the prequalification of the welding procedures shall be provided to the engineer and proof engineer to demonstrate compliance with the design requirements.
2d2fbdf0-d4a6-5914-9577-7c02aec12671 | note | ○ This documentation, along with the engineer's and proof engineer's endorsement, shall be submitted to dtp for review, prior to commencement of welding reinforcement to be used in the structure.
3cc1ff60-4232-5c46-b50c-2fe48951eea8 | note | i. all welded splices for sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017 and the requirements of section 611.14(b). welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
4d130aea-0423-51e9-9584-d494d4bac8fc | note | ii. engineer and qualified welding personnel shall be engaged to develop welding procedures for the welded joints of 600N reinforcement bars for hopkins road bridge, and to propose testing programs for the welded joints;
bffb7f75-c131-54c6-9660-18e80cce3f2e | note | iii. testing of welds shall be performed;
ca4656d4-976c-5537-aa2c-db5ad2e261bb | note | iv. the testing results shall be reviewed by engineer and demonstrate the testing results meet the design requirements for the welded joints;
98b1ea97-4a44-579e-bf88-67e6e993fc88 | note | v. the satisfactory weld testing evidence together with the engineer’s assessment shall be submitted to dtp for review (not endorsement)
94925dcb-7dd0-5cde-af9f-4246ac09e612 | textbox | Enter: Teambinder Approval number
73714edb-f08f-5e33-888a-2044721ff8e1 | note | Method - Document Review
19d2b103-b10d-53a5-990a-3cfb544a328f | note | Frequency - Where applicable, once, prior to welding
2af1ee40-1199-5414-9e9d-95cc1350d71a | note | Category - HP
04eee94d-d77a-5571-b33c-1f6e5183bc8d | note | Responsibility - Nominated Authority
89743df3-6591-583a-b50c-74d9c6382463 | note | Verifying Documents - ConQA Hold Point Release
d1b6faf8-c1d9-53a1-a7d9-8f62f858b56e | date | Date Completed:
19a9cd17-e991-4f3a-813d-af9c445a1f5f | signoff | AUTHORITY HOLDPOINT
75f9f693-0cb3-415f-befa-75d3a56bac5c | section | 4. Pre-construction Activities
2c21df6c-8652-4f7e-963b-3014667acd38 | checkpoint | 4.1 - IFC Drawings
17c4f99d-7d3f-51b4-a8ed-28e913a67c37 | note | Reference - MRPA Quality Management Plan
5969e353-9408-5a96-aa75-7ff6e795ba7d | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
7676ef9f-b427-587b-8bd8-dccc7c03a1ab | note | Method - Document Review
e14a8452-a3e6-5adb-8698-ca6ac9224b9a | note | Frequency - Prior to starting Works and at regular intervals
c5a5c3f8-19b1-5289-ad02-f3ee6a843522 | note | Category - HP*
7dffb01e-ddae-5a41-8621-240011bc30f1 | note | Responsibility - All
946fc74c-f2ae-5c2b-b06d-ae6546c6b954 | note | Verifying Documents - This ITP
e5cb0f25-b030-5a6b-9b1b-9df33d9cecc9 | date | Date Completed:
5ef5bbd1-7aff-49ad-a310-2177bb8aba52 | checkpoint | 4.2 - Survey Set-out
a72ee44b-df24-5848-9386-8a1979dd9589 | note | Reference - IFC Drawings 606.08 (a - c)
76a0824a-f4e2-5c99-b3c1-98cc097fbd87 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet location requirements of ±75mm.
bd021ca0-f3da-543e-b573-6a6feac5b662 | note | ○ Attach: Lot Map, Marked drawing to indicate the location of piles in the Lot
7c92f6ef-f727-5e55-a8e8-31292ca97883 | note | Method - Measure, Visual
ce7bb942-b469-55f9-b8c4-77bb7d65b3a2 | note | Frequency - Each pile
b74ece5d-abd6-5362-99c0-f2014f806b12 | note | Category - IP
0e11d67b-7bbf-5374-9255-cc5deb2ad209 | note | Responsibility - Surveyor, SE
dd334c4d-7044-518a-bab5-6945e59202e1 | note | Verifying Documents - This ITP
2d2f2145-b84c-576d-a462-2d60dcb3a45b | date | Date Completed:
d7ad86a5-f788-4f6a-914d-0aa0740810a7 | checkpoint | 4.3 - Protection of Adjacent Piles
bc93c003-c66a-5247-b95b-fe9fce08bd4d | note | Reference - 606.04
cd1e9236-5d13-52d8-acdd-04911aa43052 | note | Acceptance Criteria - Pile construction shall not:
0f1b603a-5e88-5baf-a1bf-0ce2013fb9a7 | note | i. result in damage to adjacent newly cast piles due to ground vibration.
53d55d67-89cf-511c-b855-5e05a9e0ed35 | note | ii. commence within 2.5m clear distace from newly cast piles if that pile concrete strength <15MPa
12fc5c64-4aea-5187-9423-b6f3eae00caf | note | iii. involve driving or create significant vibration within 9m until that pile strength ≥15MPa and set for a minimum of 24 hours
f06512a1-f920-5afb-b3c3-78373ed9c60c | note | Method - Measure, Visual
fafa49a3-0551-5f75-a97b-382242734db4 | note | Frequency - Each pile
fcb6753b-d8d9-555f-8037-a273d80ddf97 | note | Category - HP*
74367a55-c0f2-5b40-8833-7e3c98d1fd65 | note | Responsibility - SPE/PE
d6eb2e64-5b69-55ac-be76-23de2fdc0b7a | note | Verifying Documents - This ITP
aad20575-819f-53f2-bd27-989364936713 | date | Date Completed:
37041bb8-88db-426b-bd47-aac45472cf85 | section | 5. Construction Activities
f023d485-89ed-47da-84d0-09b839ff7ca9 | checkpoint | 5.1 - Boring Operations
22581c1e-2262-5deb-a711-9c02f656dbf0 | note | Reference - IFC Drawings 606.03 (a)
f835fc23-17c5-5932-bcdd-3a43ea8d0b56 | note | Acceptance Criteria - Boring performed to the required diameter and depths shown on the IFC Drawings under the instruction of an experienced geotechnical engineer.
101d8449-d10b-5394-891f-6ac08eb3b966 | note | ○ Where piles are founded on rock, they shall extend a minimum of 2 x pile diameter into the rock shown on the IFC Drawings.
b58dda33-952b-56bb-a827-430138814a1c | note | ○ Excavation clean and de-watered (where applicable) for inspection.
16ba9a6a-4f5e-5c9e-bc64-7393e0e78b09 | note | ○ Excavation made safe by appropriate means and to be protected from site run-off and loose materials falling in.
3f414491-269c-5423-bbb3-3f4470f16df3 | note | ○ Excavated material to be disposed of as appropriate to maintain a clean site.
23651511-ed58-51f7-9851-bdce25f6a0fd | note | Method - Measure, Visual
e74949b1-c0fd-5818-8d64-2dcc7f202470 | note | Frequency - Each pile
a1d719f2-e84f-5e8c-b7b7-1dcc2f68adde | note | Category - IP
19a13b13-4772-594e-8e8b-ad5d76c12e40 | note | Responsibility - Surveyor, SE/PE/SPE
e44b6545-53eb-5e81-8955-e5334087a82f | note | Verifying Documents - This ITP
fc2e7b1a-142d-51f1-beaf-4ab387589a57 | date | Date Completed:
050f8cdf-f36b-44fa-99a9-38f5a1577d7b | checkpoint | 5.2 - Formwork Extension
39232924-f0a4-599f-91c9-2f60bf03f831 | note | Reference - IFC Drawings
5f30548f-e33b-5d21-80c9-6749c1b8deb8 | note | Acceptance Criteria - Where applicable, formwork shall be used to ensure the top of the pile is at the required RL.
8bd32d08-d1a2-5141-96ad-223926c92475 | note | Method - Measure, Visual
f0dfd22d-843f-597c-8f26-5713b054d68e | note | Frequency - Where applicable, each pile
5512969b-302d-5758-9ae8-0e60117a6f00 | note | Category - IP
c7b0bcbd-416f-53f5-84bb-642703cc6df7 | note | Responsibility - Surveyor, SE/PE/SPE
4d5dfe18-0d9f-54df-89ca-97a8ee8c7c0d | note | Verifying Documents - This ITP
26b133a8-555c-5d71-90d6-76ce749e7f82 | date | Date Completed:
1882f5f1-1aa2-4310-b36d-c251c885cbc7 | checkpoint | 5.3 - Inspection of Pile Excavation
ee15ca6e-c01b-568f-91fd-d9d90f102f5b | note | Reference - 606.05
72a9131a-d584-5b1b-a89d-bed3d5512543 | note | Acceptance Criteria - Pile walls and base to be inspected by the geotechnical engineer to confirm that the geotechnical strength of the materials in the pile wall base have satisfied the design assumptions.
d9d76ced-4bb6-593c-aa4f-0e169ae64f6e | note | ○ Attach: Geotechnical Field Sheet or Report
ceebd7fa-9fec-509f-8e0f-a0bdf9b1e8a6 | note | Method - Measure, Visual
72ddf1a5-44e9-585c-b1a9-92b49de561f5 | note | Frequency - Each pile
02564f05-b38c-5d9d-a82f-570acbbb5090 | note | Category - HP
2d0c1b0f-fbe1-59db-ab97-24e206ee97e8 | note | Responsibility - Geotechnical Engineer
5c9ad718-5744-50fa-8aa2-a45a349438c3 | note | Verifying Documents - ConQA Hold Point Release
e1b00134-1c7e-5258-9aa3-84284fee1687 | date | Date Completed:
d47282ec-2956-425f-a909-580282736c00 | signoff | AUTHORITY HOLDPOINT
4a879625-9362-4129-9c8b-52c1ba1f82a4 | checkpoint | 5.4 - Reinforcement - Placement
5de38543-61e2-5dc8-8e95-3b1eaf2284a7 | note | Reference - IFC Drawings
4c748ecd-9700-5002-8e5f-acfb15447652 | note | ○ 611.06
4237db8a-6944-53d6-9c03-05613dc3fc93 | note | ○ 611.09
f419daf7-5ae7-5c25-b959-dbccc95608fe | note | ○ 611.10
310e1ee9-5fbd-59e4-bda2-ca7ffdca54e6 | note | ○ 611.11
bd136178-d945-5bd9-a7a0-bb4cb404202d | note | ○ 611.12
e9f0ce88-277b-5469-9954-531610ca5706 | note | ○ 606.06 (a)
76535aa1-90ed-534b-9798-146a7e7491a8 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
5aa5fc72-75c6-523e-a915-2b7b91d12f69 | note | ○ Projecting reinforcement is the correct length and location.
4e724548-1333-5989-8838-c2b60ce2147e | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
8e3c52d2-6bf5-5a31-b7d2-6e7574a2d39f | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
005c27d8-793b-5ccc-be6c-d1cd4c43a7ba | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
ea5bbae0-8937-5055-adc2-e2f1041a9ada | note | ○ Bar chairs or wheels used at no greater than 2m centres so that the minimum cover as shown on the structural drawings all around and has been achieved (including tie wire locations).
200aeb55-ed42-53b9-9f09-a02bf83658b3 | note | Method - Measure, Visual
f1596e7b-7dc7-5001-b5e5-73cdefbaf448 | note | Frequency - Each pile
004ee764-fbff-5c8a-a8dd-23017e67177b | note | Category - IP
79b4e645-68f6-574b-b211-661891273c0a | note | Responsibility - Foreman, SE/PE/SPE
8bcfcec9-cb43-53f2-bda0-0f035b09afb6 | note | Verifying Documents - This ITP
66676552-17a7-5142-9704-072391089c5f | date | Date Completed:
374e7ea8-f913-499f-9c47-72ec963b42c4 | checkpoint | 5.5 - Reinforcement - Electrical Continuity
e64f49cd-6ea7-5955-8b67-943fd06ef21e | note | Reference - IFC Drawings
fbfddbcc-5090-5679-bb45-c4168d3303fe | note | ○ 610.29 (d)
4ff87f81-d0dc-532d-8b0c-9b8805615bb2 | note | ○ 610.43
ffbca1ec-441c-5981-8992-e292b2c349ac | note | ○ AS/NZS 1554.3-2017
8bb706a6-4592-5eed-b24e-5d200f511ba9 | note | ○ INFRABUILD SENSE 600 WELDING GUIDELINES T05A V0.2
204dc59e-f261-5921-9de3-46837ad928bb | note | ○ 611.13 (a)
086229ef-de12-5af6-8cc5-e3bacf1575e2 | note | Acceptance Criteria - Pile reinforcement cage to be made electrically continuous by:
483314ba-6bae-51f5-a0ae-be5b97e6c46c | note | i. tack welding 4 no. min. longitudinal bars to all intersections of the helix at 2.0m centres max. (at every intersection is preferable)
5eca2feb-bdcd-5796-b17b-21fac3f4b25d | note | ii. tack welding the selected longitudinal bars at all splices (2 tacks minimum per bar)
39f0eb8c-31c9-5b3b-bfd9-9e27f611aea7 | note | iii. tack welding or fastening the grounding clamps to the longitudinal reinforcement
0ac3927f-f63a-5453-89c8-68886679f2dc | note | ○ Evidence that the resistance across the cage has a maximum value of 0.01Ω / 10,000µΩ is required.
fc6ab540-4362-5151-a52f-371882e52e63 | note | ○ Welding of sense 600 reinforcement shall comply with the requirements of dtp specification 611 and as/nzs 1554.3-2017 with the following modifications:
212258d0-af5e-55f9-bc35-c915494356ea | note | i. tack welding of sense 600 reinforcement is also permitted, provided welding is not within 50mm of the tangent point of a bend in the steel.
eaff1675-238d-56b4-ab68-aae6ec14fe18 | note | ii. all tack welding of sense 600 reinforcement shall be prequalified to as/nzs 1554.3-2017. welding procedures and itp shall be developed following the guidance in the document titled: infrabuild sense 600 welding guidelines t05a v0.2.
69ae8f44-2033-5c94-be1a-f8acc9ca247e | note | ○ Photograph or attach: Ohmmeter reading across the splice or end to end of the reinforcement cage
d1f90ed0-d75d-5c7d-b4c0-fe22fa9ddae2 | note | Method - Measure, Visual
2370527f-b048-5013-9337-d85309e4d11f | note | Frequency - Where applicable, each pile
3ee5b06a-6eb2-50ec-bb6d-cb66b59aa3cf | note | Category - IP
5db1cbb1-fece-51f5-920d-2e25bdde50c3 | note | Responsibility - Earthing Engineer, SE/PE/SPE
3898fa50-2451-5dfa-a2f7-e8855dc33ace | note | Verifying Documents - This ITP
94c49484-c330-591d-b27a-6570404f4265 | date | Date Completed:
d33fde9f-13a8-4c52-89d8-50e0430a4cdc | checkpoint | 5.6 - Cast-in Items
f95e62d8-3fb3-5f23-8727-b8b92bfc05cd | note | Reference - IFC Drawings
01060252-c475-58ae-92db-c267ecae3659 | note | ○ 610.46 (a), Table 610.462
6c74eca9-6175-5baa-b343-604c65fc1238 | note | ○ 610.47 (a), Table 610.472
53f031b6-72d0-5e2e-b392-14bcd74241a1 | note | ○ AS3810.1 Table 3.3.6.2
1b127b76-1494-58c0-86f9-4a69d5039972 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
bcef567a-e8a7-5e33-80c7-7cac006882b0 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
663c34ed-4ca1-5872-9208-d76727a06d77 | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
a3960306-f7c7-56ef-bbef-ab0b6db3e517 | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
fcf24a71-a0f1-5434-ac6e-064d9fc60adb | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
58b55cb3-ed63-5857-a7b3-c651fc6f7aa5 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
152e1b88-76de-5d30-aa16-95839256313a | note | ii. Running dimensions of a group of the above = ±6mm
5553aeb5-98a9-5bbb-a4f4-a5c18a0422c4 | note | iii. Ducts and conduit location = ±12mm
0ed2ef8e-8788-5cd0-aafb-cafe59714b71 | note | iv. Diameter of ducts and conduits = ±3mm
c602b493-414d-54d6-8580-9833f55cbbbb | note | Method - Measure, Visual
03b11ff0-f326-556e-a048-0d995134cc43 | note | Frequency - Where applicable, each pile
691a2e05-4e4e-596f-b86f-209475940915 | note | Category - IP
c805ab1d-880e-599c-b212-545f1dcfdaf3 | note | Responsibility - Foreman, SE/PE/SPE
49a8ccb8-86e1-5e11-b8db-853e8c348dfd | note | Verifying Documents - This ITP
50811d6d-a4e3-5e6b-ab42-889ed77f3870 | date | Date Completed:
5f2447d1-5a6c-477a-a54b-23cb2b3330d1 | checkpoint | 5.7 - Pre-pour Inspection
86a6fce0-1bef-54dc-b21a-9e1f716d6706 | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
301b1d7a-d8ea-5882-909f-8c861456f01a | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
8a11cdfc-b904-5751-9f16-fd69d582ff3b | note | ○ All foreign material has been completely removed from the excavation.
490af41b-56cc-5aaf-9b12-667c6786ef85 | note | Method - Measure, Visual
b37b6bd6-461b-578f-948a-7af744e6b21a | note | Frequency - Each pile
552790ea-545f-54af-9947-3aaf1f73f53d | note | Category - HP
0b2644b3-38bb-5f8d-8a81-e007dbf4429f | note | Responsibility - Nominated Authority
45617795-16b7-59f4-9c65-8f7d737ec8fa | note | Verifying Documents - ConQA Hold Point Release
c6411311-f5e8-5dfb-87f7-57fff82ed720 | date | Date Completed:
db3eb3d2-bf31-4c1d-95ad-4ad7874a3da5 | signoff | AUTHORITY HOLDPOINT
389e1b5a-bef0-453e-a2c1-a95c20442083 | checkpoint | 5.8 - Weather Conditions & Evaporation Limits
74268661-b34a-5d9b-9717-6ccc8a3ea0b1 | note | Reference - Hot and/or Cold Weather Concreting Procedure
b37ec2fe-83d4-566f-82f7-74f51467bfb4 | note | ○ 610.17
9e8693d1-d77e-500f-99b1-27f8fe726f94 | note | ○ 610.17 (a) & (e), Table 610.171
e8a9f86a-b936-522a-8cb8-a88c92a64a9a | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
b28744cb-adfa-5dc8-9ff5-5ee280d7863e | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
3fc6c53d-4f56-54a8-b99a-ab375d5248be | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
c6d6fb96-71eb-54fd-b973-fd7f486f819a | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
02e32752-8518-597c-b32a-b4240e9fc560 | note | ○ Record: Required information on the Concrete Pour Record.
bc9e6386-fb30-506f-a3e3-1b413d8f8f3b | note | Method - Measure, Visual
b36aadd8-d79c-5dec-9057-509160c479d2 | note | Frequency - Each pile
53b34e3a-56f7-5dab-a117-c2ebb138c0b5 | note | Category - IP
74c4ee57-c290-5685-b0fe-f73e2c56da47 | note | Responsibility - Foreman, SE/PE/SPE
28441be7-8e90-50b9-b255-c70309a1587a | note | Verifying Documents - This ITP
545f8216-6e67-5379-9088-5b83c80f9db5 | date | Date Completed:
5c79377a-4d23-403f-ae7c-808692f4b1ec | checkpoint | 5.9 - Concrete Testing - Sampling Frequency
eb646252-1856-5743-89b3-94c69805d76f | note | Reference - Site Sampling & Testing Procedure 610.16 (b), Table 610.161
2be86b12-79d8-5658-9c05-09671ec6488b | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
04238432-0e9c-58f8-a4db-0decb7195d4d | note | 0m³ to 10m³ = 1 sample
9df9f2b0-91d8-5ed4-b09e-b35dd8fbf842 | note | 10m³ to 25m³ = 2 samples
89ef1a50-6300-5e99-95e6-2a5ae2e30d8e | note | 25m³ to 50m³ = 3 samples
15affaef-3742-573c-8fc2-41100b6d1de1 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
a76a3d23-c359-504d-834c-4559239eb094 | note | ○ For each additional 50m³ and additional sample shall be taken.
af33b015-7945-5eb4-ba6b-b455f1fc9061 | note | ○ Where the time interval between the end of discharge of one truckload of concrete and the beginning of discharge of the next truckload exceeds 45 minutes, the minimum number of test samples shall be one (1) per truckload of concrete
b41f4b86-58dd-5b06-91d2-1276308ad209 | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
fc188783-7380-56e3-9267-150808676caa | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
4709599f-bd5f-55ce-b574-674f96bf8251 | note | ○ Note: Additional cylinders may be required for other purposes such as early strength determination of adjacent piles.
b4cbb97b-69cf-59ed-ab83-ae51e6877927 | note | ○ Record: Required information on the Concrete Pour Record.
64ec5da9-f9a0-59f8-ac05-1ddae4406e0a | note | Method - Test
e703df2c-a2e1-5680-8dcd-b87dcdcb4019 | note | Frequency - Each pile
df79fa15-a197-5c30-a11d-6a45e581f9d3 | note | Category - IP
cb44ea2c-4dad-529b-8347-7faa38be8f47 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
d206ba95-079c-577f-a884-ebb509e8af2c | note | Verifying Documents - This ITP
6abd2731-91e4-524e-9b86-34f70dbb4ad1 | date | Date Completed:
75064d5d-4052-4ea2-aeb1-683de6a9734b | checkpoint | 5.10 - Concrete Testing - Spread, Passability & Viscosity
9a756524-62bc-5489-9eba-c0da1b4633c9 | note | Reference - 610.13 (b)
a821da76-0c23-54f2-9ff0-6a438292f67c | note | Acceptance Criteria - Spread range = 550mm to 750mm
6ebe6b60-560b-5580-ae3f-c99da7234dbe | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
39769195-a4c4-52d4-bb92-fb95bd58fac9 | note | ○ Passability = ≤10mm (aggregate height differential)
285e96cc-7d49-589d-b752-7cad4d9a7b44 | note | ○ Record: Required information on the Concrete Pour Record.
7d9b74a9-8b16-5eda-bcf0-e7fce5b75ab6 | note | Method - Test
7f7cd0a9-0e8c-5441-b11d-3ff3b0a27449 | note | Frequency - Each sample of Self-compacting Concrete
b71f24b7-179c-55f5-9558-18eb682fe4ec | note | Category - IP
3753b22b-6343-5e4c-95d9-29679324b284 | note | Responsibility - Concrete Tester
7e1cb746-71b8-5c13-813c-6f657acf1c59 | note | Verifying Documents - This ITP
62f8b1a1-8149-5022-a82f-fd3e466fd324 | date | Date Completed:
f13b70ea-620c-4132-882c-2ec8d463f313 | checkpoint | 5.11 - Concrete Testing - Compressive Strength Cylinders
891e0c19-85fc-5ef0-aede-bda1c142cad0 | note | Reference - Site Sampling & Testing Procedure 610.16
45d72cb7-d241-5463-9243-a443f824386c | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
ffe5f3af-452e-5449-93e9-5ee45657f599 | note | ○ Record: Required information on the Concrete Pour Record.
58e62cf3-6f38-5761-b509-efae901fcc7c | note | Method - Test
3b9b84f2-6528-5972-abc6-0a1c320a8121 | note | Frequency - Each sample
f2e377f2-a7de-5abb-a623-68b310c74e2c | note | Category - IP
730e1d8e-cd0f-5b47-a815-a33d72d062fd | note | Responsibility - Concrete Tester
da11a0fa-3b23-5622-8e62-06e8e7c208b1 | note | Verifying Documents - This ITP
d608f294-a649-5874-9c70-3a576478dc45 | date | Date Completed:
e722a338-e8a6-4a3e-a17f-9a8cce3ef31b | checkpoint | 5.12 - Placement & Compaction (Dry or Wet Excavation Conditions)
ac0c0832-8a41-5b7b-a42c-d33a0a60cbb9 | note | Reference - Piling Quality Procedure
195daace-556b-5893-b94e-2cfdbd35f6dd | note | ○ 610.18 (a) & (b)
5b17fea4-21c4-5803-b19b-6f0cb383099a | note | ○ 610.18 (d) (i)
ec90a352-b9c3-5d15-b750-853e15eb4b2c | note | ○ 606.06 (a & b)
888c7779-f7bd-59a6-b621-395f09e4b043 | note | Acceptance Criteria - Concrete shall be placed within 24 hours of excavation - where this has not been achieved, the internal wall & base of the excavation shall be cleaned to an additional depth of 25mm.
1359a67d-e682-5a4c-b2cd-a4fdedc99506 | note | ○ All concrete batches are traceable.
79725669-fcbb-5c78-8e82-3066f13dc729 | note | ○ Concrete shall be placed through either a tremie pipe or concrete pump and not dropped freely from a height exceeding 2m.
fb20ea61-0cb0-553a-9022-aea863518398 | note | ○ The initial discharge is pumped to waste until a consistent workable mix is discharged.
a70a1bfa-7172-5546-b12e-88e6ae186a27 | note | ○ The ends of the discharge pipe shall not be lifted off the base of the excavation until a 2m head is created, which shall be maintained until the completion of the pour.
d41ca90b-e45f-5da8-8298-3a715c42b4d8 | note | ○ Where a casing is used, it shall be withdrawn with care and at a rate to ensure that the free surface of the concrete is at least 1.5m above the bottom of the casing.
58a466d6-849a-54ce-a343-1406f6f9e83e | note | ○ Pile height is to be 300mm above the cut-off level (or 400mm in wet piles) to allow for breaking back of sound concrete.
c95cd901-7277-5aef-aedb-baa891559072 | note | ○ Record: Required information on the Concrete Pour Record.
a1cf6fc1-704b-59ea-822c-e1ad19f01b80 | note | ○ Attach: Concrete Pour Record
fb8e3358-39a9-554a-960d-866938752979 | note | ○ Attach: Concrete Dockets
4f4c804a-2791-5a19-a98d-5413f4130b5a | note | Method - Visual
a8164927-1c97-5d2d-80d3-6d7facc202ba | note | Frequency - Each load
95f23702-bfad-5e7d-9c31-67f9f58e5a5c | note | Category - SP
112a0020-e10d-5426-91d4-15e26281d2e7 | note | Responsibility - Foreman, SE/PE/SPE
c503e2d8-f665-5cfe-a220-a92016890e78 | note | Verifying Documents -
5198c712-afb0-58fb-a659-acde09722483 | date | Date Completed:
1719f2f4-1bef-4be8-b33f-151af0721ea0 | checkpoint | 5.13 - Surface Finishes
953f7cf8-b868-521b-afa4-67ba96322a99 | note | Reference - IFC Drawings 610.31, 610.20
d69df13c-44dd-5b62-991d-d1c8aba0588c | note | Acceptance Criteria - Surface finish as per IFC drawings.
46c19bc8-9c08-570b-aa9f-d18261193bf9 | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
384cf291-bc61-5746-8e2a-847af271f2a6 | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
83b23d68-66c5-54d5-bb5b-f74ede4b1b2a | note | Method - Visual
6c7e1fd1-8636-5fa1-b375-a77bcba5b3f6 | note | Frequency - Each pile
af73221c-bc6a-567c-b994-80ce6ee3280b | note | Category - IP
b9fe16d7-6b0b-5b09-af5e-0ff83f28d89f | note | Responsibility - Foreman, SE/PE/SPE
7163e078-13b8-57af-9c89-88e0ac519977 | note | Verifying Documents - This ITP
d30578d8-0064-560f-ac6c-ebc07b59ff47 | date | Date Completed:
dd364e0d-c935-47cc-b62c-f381e4f8b1a5 | section | 6. Post-construction Activities
2fad433c-20d3-4ed4-80d1-38ba14e9b7c0 | checkpoint | 6.1 - Pile Trimming
19ca1ac8-e61e-5139-9cc8-8577c27bf90d | note | Reference - IFC Drawings AS2159 Clause 7.2.2 - 3, 606.06 (a & b)
58bcafc6-6cb6-57ee-a118-c15262c0f29e | note | Acceptance Criteria - Piles shall not be broken back until a minimum of 24 hours after completion of the placement of concrete.
860ce893-7bf5-53d1-8eb0-fa301810b14b | note | ○ Care shall be taken to ensure that the full cross-sectional area of the pile is at the required RL without any cracking or damage.
e7444788-6d6a-5439-bc32-522a80c2a135 | note | ○ Any weak or damaged concrete shall be removed back to sound concrete.
7bf1328d-d552-575b-9fbb-6708688c68c6 | note | Method - Measure, Visual
30130723-abd0-56ec-a3b8-2e6e751e8ee7 | note | Frequency - Where applicable, each pile
8b29925d-b46e-573a-81e0-5b2d0e3ffbd8 | note | Category - IP
e5d669a5-b1c2-53c2-b52b-cf7f1859a8c2 | note | Responsibility - SE/PE/SPE
7b9380fc-3d19-5e09-ad14-afaf342516cb | note | Verifying Documents - This ITP
2408b9b0-ca1a-5ae7-a045-33d3f10a0071 | date | Date Completed:
99f563a9-ce6e-4242-85b3-9defd728ef8b | checkpoint | 6.2 - Compressive Strength Test Results
91eb09bd-59a8-507c-885b-4e20d73c4c24 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
356caf49-3522-5376-8ee3-60c77f0934d2 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
8fd42ea9-2b5f-5a28-9264-fd9cd7276ff6 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
3958faa0-6462-5cf8-9720-5138d2431b19 | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
a7e20c87-bb77-5a29-9a3f-929c68f9f56b | note | ○ Attach: Compressive Strength Test Results
2b1d9e5e-2fca-50d2-9213-e1f523ad3cc1 | note | Method - Document Review
9a86e05f-b396-51fb-aec4-c4ec08cbc447 | note | Frequency - Each cylinder
2cd0af32-3bd0-5c37-8546-00421166adb4 | note | Category - IP
a9e24619-31cd-5edf-a1fd-28016bda9ee2 | note | Responsibility - SE/PE/SPE
c264f031-830c-523b-8906-3160f5feb390 | note | Verifying Documents - This ITP
c2a03054-af15-5c77-8ffe-7428e44db036 | date | Date Completed:
b0d2baa4-8f49-4175-a7f5-94da50842e32 | checkpoint | 6.3 - Pile Integrity Testing
ebd66e69-e010-5ebd-94d9-ed008ce229a4 | note | Reference - 606.07 (a, d & e), AS2159 Clause 8.8
33af9551-995c-5c4c-839d-0110aaca45c7 | note | Acceptance Criteria - Pile integrity testing shall be conducted after the concrete strength has reached 25MPa but not less than 7 days from casting.
16429239-7834-5d6e-893d-df010415595c | note | ○ Cross-sectional area = ≥95%
e834926d-91dd-5007-9054-30a829cb7914 | note | ○ If any test fails, all piles shall be tested.
4319586a-4fc9-557d-9897-5f96909549be | note | ○ Attach: Pile Integrity Test Report
20e1e326-c51c-526d-af46-2aea908849b1 | note | Method - Document Review
b405d20c-5ec5-559c-9800-2f19bef3302b | note | Frequency - Piles #1 - #6. Reduced to 1 test per 3 piles if the first 6 tests pass.
053d4e12-3ee1-5dcb-bf08-2aa6955dae6a | note | Category - IP
cac61ead-a4bd-58be-a4ea-5790879cc134 | note | Responsibility - Testing Consultant, SE/PE/SPE
102a80f2-9abf-5e6b-aebd-64bbd41ed95d | note | Verifying Documents - This ITP
702fa5a8-9127-5ae8-b648-76ba75807bd4 | date | Date Completed:
71fc39be-4e2b-46fc-a3b5-d31b494dd80b | checkpoint | 6.4 - Static Load Testing
4e144e56-9b3c-52db-9e68-ff7e61dfbf45 | note | Reference - IFC Drawings 606.07 (b, d & e), AS2159 Clause 8.4
3f11863f-164d-50d3-a17a-fb03c88a9cb0 | note | Acceptance Criteria - Static load testing to be conducted on the designated piles as shown on the IFC drawings after the concrete strength has reached the 28 day compressive strength.
9d713109-54eb-5982-99ed-8ef725960b45 | note | i. Displacement vs Time Graph = linear or decreasing rate of creep
ad657833-321b-53c8-932f-c06d03e4e1c1 | note | ii. Creep rate = <2mm / log cycle of time at the test load
3c3f7a6d-38f7-5dcc-a67e-3c08ccedaad5 | note | iii. Maximum pile settlement and lateral displacement at the design load = < values on IFC drawings
3af10cd1-7165-5f8e-ba7b-44dccb39a9e3 | note | ○ Attach: Static Load Test Report
d44c1f57-07c4-52e6-8324-c3524a57323d | note | Method - Document Review
069cbc5c-49c7-560a-877c-6866bd0f9bd7 | note | Frequency - Where applicable, as shown on the IFC Drawings
6748d616-c0a6-5116-8650-f3cb2de48dda | note | Category - IP
468cc566-8932-5bf5-bb26-5aa0d46896fe | note | Responsibility - Testing Consultant, SE/PE/SPE
f98ba51f-f8a3-5d83-99e2-3b59fd13a387 | note | Verifying Documents - This ITP
e7d3883d-0510-55f2-a681-462c3a00d998 | date | Date Completed:
7c9ae22c-3dbc-42ca-bc77-f73a42199e29 | checkpoint | 6.5 - Dynamic Pile Testing
ade73c45-38ea-5adc-ba9f-37ff2fe5ca25 | note | Reference - 606.07 (c, d & e), AS2159 Clause 8.7
74e1861e-d570-56f5-a09a-47890928b657 | note | Acceptance Criteria - Dynamic pile testing shall be conducted after the concrete strength has reached the 28 day compressive strength.
60979b08-2d13-5051-abe3-3e252c303600 | note | ○ Measured Ultimate capacity = ≥ values on IFC drawings
b390d9ab-0947-5531-9426-8d0a53344df5 | note | ○ Attach: Dynamic Pile Test Report
45ffbf44-840a-5b74-90dd-f3ba510eee9e | note | Method - Document Review
7fe075f1-12a7-59e9-b841-cd1d4131c2fe | note | Frequency - Where applicable, 1 test per pile cap / abutment, where pile toe RL varies >2m from the test pile. At least 1 test per 10 piles.
4d171d8e-e9f5-56fb-8ac4-d05d7ee94694 | note | Category - IP
c3f79e2c-f857-566f-acfd-c36e337ad371 | note | Responsibility - Testing Consultant, SE/PE/SPE
31f11d5b-7736-5358-93a7-8d2b485d1bcb | note | Verifying Documents - This ITP
a426f2d0-cf31-553c-a801-8bc41f31c2e0 | date | Date Completed:
c064c1fc-4b9e-4b11-b5b7-ae08b185e345 | checkpoint | 6.6 - As-built Survey
789be2ed-54b7-59e3-a9f9-3cf891f5b1d6 | note | Reference - IFC Drawings 606.08 (a - c), AS2159 Clause 7.2.2
ca03147e-10da-50f0-ab71-f9f38223f1d9 | note | Acceptance Criteria - The following tolerances apply to piles:
3da6af1f-c972-52b4-ad05-308f55deb70e | note | i. Pile head plan location = ±75mm
ac8b0398-c0ee-51f9-bd49-6b508cc112d5 | note | ii. Variance from vertical or rake = 1:100
9b8e9cb0-72e4-5ef3-a475-a7b3cc0b74d3 | note | iii. Irregularities in straightness = 1:100
2cac849e-d713-5dab-92b6-46b6ee437cfa | note | iv. RL = ±25mm
46c60d0d-aad0-53fc-be2d-5ef99698083d | note | ○ Attach: Survey As-builts / Survey Report
495215f8-1cf2-5674-acd4-25b509d96346 | note | Method - Document Review
599951c7-ada8-5dcf-85b1-18e250dac8d0 | note | Frequency - Each pile
8ee4f0d4-b856-53b8-b864-8235f4ced908 | note | Category - IP
0a980bf6-856c-5bb6-abf2-462ea0805beb | note | Responsibility - Surveyor, SE/PE/SPE
9a310ead-4c2f-5fd3-8bb0-0cbdfcdb91eb | note | Verifying Documents - This ITP
059cceb9-99e9-5d1d-892d-265712d9256e | date | Date Completed:
7c891099-c57b-4ef9-a07a-5bc80feb1b86 | checkpoint | 6.7 - Non-conformance Report (NCR) Closure
8551c307-97d3-508a-a13e-33f95c06d593 | note | Reference - MRPA Quality Management Plan
5c228490-2e1d-5a27-90c3-5a3414387170 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
7986c0c0-c262-5c8a-9845-5307770d2a66 | note | Method - Document Review
13319960-4b3b-592b-bf16-3df923dca604 | note | Frequency - Once, prior to closure of this lot / element / Work area
377df5d5-04e4-5147-a601-220a6db951d4 | note | Category - HP*
ab1625de-524f-50a6-814b-9c08e3c19cb7 | note | Responsibility - SE/PE/SPE
d7c40061-754a-5099-b3cb-e25ba58f2265 | note | Verifying Documents - This ITP
ed57e47d-8b53-5be4-a630-7137f20492f7 | date | Date Completed:
484cc427-f2c4-4eb8-8203-9408248b59ff | checkpoint | Final Inspection
31f94f7f-7ef1-55cd-9edb-1c82489638fe | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
14f73813-3dd1-5f0b-972f-4c25912c7a6d | textbox | Name:
77e96872-e9d3-5d22-b0a8-4b508ce8d3ed | textbox | Position:
fd62f41e-52b9-588a-8413-271a75c587e0 | textbox | Date Completed:
7712f1ad-b047-42cb-bca9-34d9d73c65aa | signoff | Sign ITP
4704e5b0-e103-4e0b-b629-e0f2992adc01 | checklist | ITP-271-CIV-FER-Permanent Farm Fencing Rev 0 | itp | ITP-271-CIV-FER-Permanent Farm Fencing | 296e3d0b-7065-4a70-926e-c377012b7971
93ac8a16-5cfc-4a8a-9c88-1d1b7e8b76ee | section | 1. Referenced Documentation
62f296d9-141c-406e-9e29-e214298779a0 | checkpoint-no-value | Referenced Documentation
2e582424-5660-5f36-b409-1a6cbc860344 | note | Document Title: ITP-271- CIV-Permanent Farm Fencing
b53f48dc-b106-575b-aca6-4c84a8a1bfbe | note | ITP Description: Permanent Farm Fencing
18cc5d3e-f42e-5edc-b5e9-436408b9c2da | note | Discipline (e.g. CIV/STR/RAIL): 271- CIV
fa154c50-dd72-5c71-8da2-7329f30740a6 | note | Revision Number: 0
29ee1fc0-7113-571a-b451-48dd5a12dec7 | note | Revision Date: 9/05/2025
a8dc86ed-54bf-5432-8826-401789cbf570 | note | ITP created by: Kamel Alshobaki
123c3593-9823-5e35-a1cb-bc0e5b93825c | note | ITP approved for use by: Pradeep Talasila
bbce0117-8108-516d-a069-71d5e06fd0af | note | 1.1 - Non Dependent
44add86b-6c90-5108-9865-984f728f0e31 | note | Reference - IFC Drawings
67b202f2-e290-55ac-8f68-1d3ed05729a3 | note | 1.2 - Non Dependent
46e9552a-e1bb-599f-b4f9-d8a846970b93 | note | Reference - VicRoads Drawing No. SD3151
09154a50-97f4-56e6-849f-9dfcfba96fe4 | note | ○ VicRoads Drawing No. SD3111
d7563715-5e59-5698-aad7-0148886c7b3b | note | ○ VicRoads Drawing No. SD3161
8e3b8a0d-4b05-4de0-80e5-a73d024182d4 | section | 2. Materials
0423bf28-d7c5-4ae9-8cad-4b415aa0dfd1 | checkpoint | 2.1 - Timber
dfe18bdf-8411-5afb-b9d7-8b2ad62ea672 | note | Reference - IFC Drawings SD3111
e92293ae-5d04-5627-bbb5-aee44f1c7655 | note | Acceptance Criteria - Untreated Timber and Treated Timber according to Vicroads SD3111.
d639e566-94e2-58ac-adf2-e1e4a887609f | note | Method - Document Review
f9a3521d-a171-5de0-9587-d300a251631a | note | Frequency - All elements
4f3db731-9638-58f9-9ebb-78a8110b0ba9 | note | Category - IP
e38af469-eea6-515c-a412-60aceeb3ba50 | note | Responsibility - SE/Site Supervisor
c50c6283-2ed8-5a6b-857f-70d60460c88c | date | Date Completed:
4f071fff-10bc-4995-800f-32fde54c3bfc | checkpoint | 2.2 - Concrete
946ed2ea-5623-5f43-b33e-4d65fce92d34 | note | Reference - IFC Drawings AS 1379 & SD3111 & SD3161
64a2b247-6995-58ee-b4ef-ec1e87915d69 | note | Acceptance Criteria - Shall be 20 MPa concrete to be used as per IFC drawings & Vicroads SD3111 & SD3161 and AS1379.
d397bbef-8caa-51c6-b8ba-116459f66a68 | note | Method - Document Review
f8f8eb9e-360b-5fd3-85e5-34c351ddb1f4 | note | Frequency - Each Mix
856443a5-8117-5e95-b538-3f2c9f14698a | note | Category - IP
825ca7fa-aa28-5444-a6f9-b9ee8f2276d2 | note | Responsibility - SE/Site Supervisor
9165a5fc-b838-5ffb-a823-d58f10f74ca7 | date | Date Completed:
5f995db9-4d48-45ec-a924-08c610cc5a03 | checkpoint | 2.3 - Steel components including wires and posts.
5c62b927-1505-5637-b049-f26e973be333 | note | Reference - IFC Drawings SD3111
b7f0a314-2c7c-5456-840f-3a5ff02cf839 | note | Acceptance Criteria - All Steel must comply with Australian Standards.
a8465531-7ebe-5752-9f46-aaf3220576da | note | ○ Steel section sizes must be checked on site.
b2a1b44a-c778-583a-b3dd-95ed54ce1126 | note | ○ Star Pickets according to Vicroads SD3111.
e773e550-392c-5b3b-bd95-d28788ed2c91 | note | Method - Document review, Visual and Measure
1da12167-ad45-55f7-904c-a0e17294d89c | note | Frequency - All elements
2a58c34c-a0d5-5e3c-9803-f89ae55dcb6d | note | Category - IP
e8780edb-2a50-5112-afd4-6dee7fbe43db | note | Responsibility - SE/Site Supervisor
bce802ce-ef63-5f2d-9173-1981d4adb159 | note | Verifying Documents - Supplier Certificate of Compliance
a839b433-6bec-53a6-94f9-cec851f1c754 | date | Date Completed:
b1e5e3fa-6125-49f7-8b08-f00f92aedeac | section | 3. Pre-construction / Pre-installation Activities
214ebcf3-3cbb-4fd8-9425-bec79fff6478 | checkpoint | 3.1 - Survey Set-out
d320f9ba-07de-5ad0-90d7-198bf9983643 | note | Reference - IFC Drawings
9ca28854-27e6-526c-9db4-d4d260720629 | note | Acceptance Criteria - Survey to set out the following but not limited to: existing services, footing points and fence start and end points.
276a6e5f-0e04-5c1c-8540-6c0597c62937 | note | ○ Offset checked against the running edge prior to installation of posts.
5e46bcd8-4b2b-5eb3-80ee-07efb0bcc025 | note | Method - Visual and Measure
a864e0b0-a32a-5e2e-a2ce-6ee170f4dbfc | note | Frequency - Each element
6638f740-4de4-5287-a2d7-b2f2429c1a8a | note | Category - IP
89067a99-74d2-5151-a855-d06c4a082190 | note | Responsibility - Surveyor, SE/PE
5639dbc0-ab46-5959-b58d-9f1517d6437c | note | Verifying Documents - This ITP
5ac0c0f3-1cf1-5ff8-b2ee-17821e49d48e | date | Date Completed:
f6504831-8f00-410f-8a11-95c0dad91b5f | section | 4.
c8e46e88-63b7-4038-8061-3d8aaa8416ea | checkpoint | 4.1 - Excavation works
6b72b09f-7939-5040-8260-dd3ee68d530f | note | Reference - IFC Drawings
6b48e192-fea1-5d3a-8e54-7a2572660927 | note | Acceptance Criteria - Excavation completed by auger outside of service working limits.
1400bab0-50bb-581d-9e88-9bd99e9f0111 | note | ○ Follow asset owners guidelines for work around their service.
cd38371f-2928-5dd9-b27f-b62ad97772ad | note | Method - Visual
1b606e63-e51a-5c12-87bf-04282d9bc768 | note | Frequency - Each fence footing
a14f8f1a-d892-5c75-a0b5-75b17aef4538 | note | Category - IP
88790881-e39a-5614-a144-6c5fe3b53a87 | note | Responsibility - SE/Site Supervisor
47f8f7a1-1b77-54d0-bf6f-8711fbb9a32f | note | Verifying Documents - This ITP
84fbdee8-47ae-5548-8d42-a643c0d4b945 | date | Date Completed:
8be2c8bb-d424-4e38-bb3a-f94f6b6111ef | checkpoint | 4.2 - Ground Conditions
0286e434-a2cb-5a36-a357-3d658066b6ae | note | Reference - IFC Drawings
6f7030e3-561c-5815-b561-721760dbdc16 | note | Acceptance Criteria - All post foundations to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
fa254438-178c-5af1-bbb9-872175d34a90 | note | ○ If the ground material on site does not meet the design assumptions, the Geotechnical Engineer shall be notified to determine if design change is required.
9bfbdf07-243c-5dc4-b309-1ab3181b825d | note | Method - Visual
248d753b-55bb-5938-ad5c-4f95c9e58e93 | note | Frequency - Each post
67a1db84-e695-5614-89db-9ab6eadab01f | note | Category - IP
efe5145f-ddda-594a-b032-01a510a4b7ec | note | Responsibility - SE/Site Supervisor
3e096f6b-9feb-5534-9b34-2501aff72231 | note | Verifying Documents - This ITP
0bfb1356-5f8c-5647-9744-dc3b1a6034e9 | date | Date Completed:
36ff7390-e2c3-41b5-ad00-ca6c92ca39f6 | checkpoint | 4.3 - Fence Installation
1913f493-1282-5061-8b4f-ef2bb9e276cf | note | Reference - IFC Drawings AS 1379, SD3111
dcbae07a-ea59-52a3-a8f5-98503381e439 | note | Acceptance Criteria - Timber posts shall be set in dug or drilled holes.
c8cadedc-5076-5b51-b390-804b8c62c32d | note | ○ Posts shall be set solidly on star picket and any space left around the posts shall be backfilled and the backfilling compacted.
0d112aed-9224-58c0-ba85-7b005bea0169 | note | ○ Concrete Shall be 20MPA strength grade complying with the requirements of AS 1379/1991.
2c037a8c-0163-5751-9c4d-daeea693d8af | note | Method - Measure
d17ca4ae-0662-5cb7-91ee-ce657ec0ce2a | note | Frequency - Each post
3de88938-dde8-5d8e-a13e-528b0908ee28 | note | Category - IP
e228f730-bdf4-5d5d-b99a-3cb5eaec41d9 | note | Responsibility - SE/Site Supervisor
f9ebcf24-0537-56ca-8b00-12df0b95f302 | note | Verifying Documents - This ITP, Concrete Dockets
e87d86ce-3859-5a0c-8220-aa54f5a4b448 | date | Date Completed:
9b870188-7c98-4d8d-a3d9-351abc45de01 | checkpoint | 4.3 - Timber Post Intallation
b6393917-c8f1-5c8c-8c53-0a1f4fae0b6b | note | Reference - IFC Drawings AS 1379, SD3111
a4a971f6-b39a-55c8-af18-eab0e76be67f | note | Acceptance Criteria - Timber intermediate post to be used at not more than 40m intervals and at a minimum length of 1800mm long.
6a8dd27d-c442-59c2-a3a3-436c9b4c9745 | note | ○ Timbers 2 x 1175 Long to be spaced evenly in pannel and clipped or tied to wires as sepcificed.
2eef4ae1-74a6-5462-830d-31e04ee87319 | note | Method - Measure
5875070d-117b-5b90-9ee2-a54444911f20 | note | Frequency - Each post
2a5a6101-5455-5bbd-855d-8e163ce0ab82 | note | Category - IP
d898c38e-02d1-5120-b04d-a55550ec14c3 | note | Responsibility - SE/Site Supervisor
0f2a1327-9d95-53b8-bed8-b2b6d899f831 | note | Verifying Documents - This ITP
504af6d3-5b5b-5c83-a8bf-a9fe137c0729 | date | Date Completed:
786889d7-c332-4751-9025-85f50f21eccb | checkpoint | 4.4 - Strainer Assemblies and wire installation
7057dab5-e4b0-598c-bc4e-def686196bd1 | note | Reference - SD3111
877c769f-2acc-5c45-83f8-f2574f577516 | note | Acceptance Criteria - High tensile wires to be either reeved through holes bored in posts or stapled to post.
6313a9cb-84b6-5355-a532-6f98d4906c3f | note | — Wires to be placed at 150mm from each other for the first 3 wires from the ground level and increase to 175mm, 200mm and 250mm for the top 3 wires.
0ca67a6c-8ed2-5dd7-81fc-38e8e94c5024 | note | — First wire should be at minimum 25mm or maximum 150mm from the ground level.
5900fe38-60b8-5f56-859f-2b61f381ee6f | note | — Maximum height for the top wire should 1150mm from the ground level.
b6de11e0-d9a8-5799-a9c5-db1d6b03fa83 | note | — Optional, galvanised hight tensile barbed wire can be used for wire number 3.
9305e456-ab51-5e65-b6a4-3bf0c66a6c3b | note | — Total of 7 wires must be installed for the fence.
0adca48b-24f9-5907-ba30-e2df7045a144 | note | Method - Visual
4a5e929e-13f7-55b2-8887-1e232b81f340 | note | Frequency - Each element
56449f44-8f80-5511-8f84-7e6e8a96bb3d | note | Category - IP
88d9cf4b-8bdc-5a14-aacf-c3144326ea7a | note | Responsibility - SE/Site Supervisor
05762145-5f60-55b4-a91b-b5897f5361af | note | Verifying Documents - This ITP
a5ae16b5-4477-5af0-bb12-edd1fb534e04 | date | Date Completed:
f20c14e9-8bd7-4ba1-9509-abb848f2ea43 | section | 5. Post-construction / Post-installation Activities
c2c40660-b62c-4549-9189-49d61c481709 | checkpoint | 5.1 - As-Built Survey
ce5c41b2-b45a-539c-8043-10168140eda0 | note | Reference - IFC Drawings
34fa612f-e6d9-5557-a429-ec54b172d545 | note | Acceptance Criteria - Posts are to be checked for verticality and ensure spacings do not exceed standards.
78963b88-307f-5e70-b9c9-16183c35b6e1 | note | Method - Measure
658714df-60c3-5beb-a28f-6aa2cb12e932 | note | Frequency - Each lot
a9b56e6f-f025-50c8-8478-cd6126e3ac14 | note | Category - IP
c6760617-9971-5f6d-a080-b80a4c307ffa | note | Responsibility - SE/Site Supervisor
b5dc295d-0544-5667-850b-6fbce949b5cf | note | Verifying Documents - This ITP
1ab7992e-455b-5102-b480-e01e60e3765a | date | Date Completed:
4bbbb02e-a2b9-4fee-b87b-875c1b55f566 | checkpoint | 5.2 - Non-conformance Report (NCR) Closure
d45147f4-5841-5806-8acc-d193d589a731 | note | Reference - MRPA Quality Management Plan
09f05dc9-6fe5-5394-a66f-4dd685c0c223 | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
f0fbf723-8937-5f5b-a425-c2ff4c5311b1 | note | Method - Document Review
25bc80b5-d78d-5612-9abd-760c2bab95bb | note | Frequency - Once, prior to closure of this lot / element / Work area
4c41e86a-8e26-5689-9456-98308099a5c9 | note | Category - IP
b427bf80-f30b-5566-9842-29bf8a430bbf | note | Responsibility - SE/PE/SPE
d646fe75-5ef5-51c5-b866-de7df4bd35ec | note | Verifying Documents - This ITP
6bb103c6-15bd-5167-b015-976764542f29 | date | Date Completed:
0d7c8fe2-78ec-477f-94fd-8c7e5d0d287b | checkpoint | Final Inspection
7f5b1b8f-88b2-5ab9-ae41-eddfe4f2a761 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
789146ab-bc41-56c4-a006-4e79f1939553 | textbox | Name:
58827b40-ecfb-5569-a46c-0bdf3f4f641f | textbox | Position:
e463c496-44c2-5442-841d-f198081d5eec | textbox | Date Completed:
c4f85ba3-07b7-4800-8bbf-75294fbacbec | signoff | Sign ITP
467bffb1-51a9-448c-b1f2-179da0018dfc | checklist | ITP-283-STR-FRMS-Structural Concrete Rev 0 | itp | ITP-283-STR-FRMS-Structural Concrete | 8d318a5b-4a30-40c1-9fc9-7561765f88ad
13f09b09-d797-42c6-9833-6a74e76576c3 | section | 1. Referenced Documentation
90f46b2f-0fa1-4db0-9158-fb5ac5d8020b | checkpoint-no-value | Referenced Documentation
74ff3cc7-bccb-5889-8905-c1c1f498b80d | note | Document Title: ITP-283-STR-FRMS-Structural Concrete
1039cb86-73b5-5e27-8088-650c4d2f65bc | note | ITP Description: Structural Concrete
84d23b00-628e-54f1-9920-35e35a05269c | note | Discipline (e.g. CIV/STR/RAIL): 283-STR-FRMS
f9b70e0f-7fc9-51e9-ac85-6ee2255fd0d0 | note | Revision Number: 0
ccbdbf62-c09d-5f50-91a7-ac2cec09a71f | note | Revision Date: 3/06/2025
7a56c1ed-db6f-5093-b3fc-eb88030127e9 | note | ITP created by: Butter Josiah
0c9e1f2e-0e90-581f-8f40-c78c439f0c04 | note | ITP approved for use by: Pradeep Talasila
7dc0d9e9-230e-56d1-b423-f32bb56184dd | note | 1.1 - Non Dependent
e3e8e58e-8647-5055-b4a3-1f8c40274442 | note | Reference - VicRoads Section 602 October 2007
dda047c4-15a1-5f7c-bf23-d3d35004257b | note | 1.2 - Non Dependent
16c281b3-e1b0-58c7-8756-572e483712c2 | note | Reference - VicRoads Section 610 February 2020
92016e40-94b9-5388-b9b6-096efbea3d5f | note | 1.3 - Non Dependent
d0b8dab4-49fe-5985-9588-838d56b7d5bb | note | Reference - VicRoads Section 611 November 2018
4d38f6b9-3f1a-54fd-bf57-96389e624bad | note | 1.4 - Non Dependent
49941915-4f8e-5925-b391-9cb618bbdec9 | note | Reference - VicRoads Section 614 June 2017
b9b2b86a-0f3c-5eae-9a6a-0783a6af045e | note | 1.5 - Non Dependent
95f3ae20-1e9f-5fb3-9424-6509db5a8609 | note | Reference - AS3810.1 2018
8474c11f-3c35-4718-8c73-1f83a3301b54 | section | 2. Preliminaries - Materials
bf3c4a54-907f-43b5-a202-ff625af31986 | checkpoint | 2.1 - Concrete Mix
ddc9dbff-b35f-5404-9440-462c0642cfb3 | note | Reference - 610.07, Table 610.071 IFC Drawings
a0e92020-2e1f-5b77-8efd-e80b75c3900c | note | Acceptance Criteria - Concrete Mix is Registered with VicRoads.
c1445cc0-f10d-5ade-9310-6c7227eff99c | note | ○ Concrete mix meets strength, grade, and maximum aggregate size as detailed on drawings.
76330c02-518b-5636-9cb8-23840a0a637f | textbox | Enter: Teambinder Material Approval number
e016f9c1-bdca-5927-b31e-62fb9990a869 | note | Method - Document Review
a8dc7a8c-dcff-5cfc-ba33-7805732b50db | note | Frequency - Once, for each mix design, 4 weeks prior to placement of concrete
1d8203a6-7380-5c9f-b2b6-855c02186831 | note | Category - HP
8ad4cea8-1a72-5aca-bec5-da3e2d454c99 | note | Responsibility - Nominated Authority
42ed31b2-cfe7-51c6-90da-bda04bf89263 | note | Verifying Documents - ConQA Hold Point Release
da170f60-2e84-5562-b01d-a3bb78d6933e | date | Date Completed:
c69c6406-e6d0-4be9-b458-b6e0616a8d01 | signoff | AUTHORITY HOLDPOINT
8922dd87-244f-477e-a6d8-209c60ac959c | checkpoint | 2.2 - ACRS Certification (for Reinforcement)
da58b9d1-6e26-502a-b330-ec1ad3fcb509 | note | Reference - 611.05 (a)
56241682-b9e9-55cc-8e2a-f72c3e1afdc7 | note | Acceptance Criteria - Current ACRS certification for materials and for bar processing.
46ac9cbc-95bd-5dde-adb4-3e77b05cb57f | note | ○ Note: ACRS certificate may cover both aspects or be for each separate portion (e.g 1 for the material supplier and another for the bar processor (bending, cropping and delivery)
91a21578-a9bd-5e4e-9230-e1c59d1eeea3 | textbox | Enter: Teambinder Material Approval number
2e1bdb56-ad2a-5ac6-b307-79b539ecb7f1 | note | Method - Document Review
07265096-c238-5c3f-b15f-84c71a6716a7 | note | Frequency - Once for each supplier, 14 days of award of contract
29db0de6-e03c-5b28-9127-923278a3942f | note | Category - HP
b935596a-46da-57d2-8460-f6da8ae8571e | note | Responsibility - Nominated Authority
74cfc36c-252d-53c3-8d85-d79fc2a9ef70 | note | Verifying Documents - This ITP
3605373a-5054-545f-90b2-03334e2b120b | date | Date Completed:
f18dd2f4-fd37-465c-a973-ed0c2e1bc5a2 | signoff | AUTHORITY HOLDPOINT
5465d7ac-f061-4fcc-95f4-00e3cfb61fc8 | checkpoint | 2.3 - Bar Chairs/Aspros Certification
586b862d-9151-5f53-b338-3e544ad10ed1 | note | Reference - 610.26 (a)
a372d729-c805-5311-9565-27f67c2cb01c | note | Acceptance Criteria - Plastic bar chairs, wheels, and spacers require bi-annual testing to demonstrate suitability to prevent excessive deformation under loads.
7199169f-fbf2-5706-8e38-4a0b50f614e2 | note | ○ Concrete aspros require annual compressive strength and soluble salt testing is required.
eb9915b9-861f-5007-bc1e-dc62a1ce0b13 | note | ○ Relevant test reports demonstrating compliance to this clause shall be submitted for review to the Nominated Authority.
eb8179ce-6727-58cf-9010-643398d29cc0 | textbox | Enter: Teambinder Material Approval number
c1bbdb59-1a1a-5c3b-96b1-1efa9160af30 | note | Method - Document Review
c722fbd1-82a0-53a3-be00-395b53629ab7 | note | Frequency - Once for each supplier, 14 days prior to placement of reinforcement
eff1768b-1c01-5fd2-a794-133d963cab9f | note | Category - HP
a94df637-3eb0-5b7f-aedb-5dfbbfdff2ec | note | Responsibility - Nominated Authority
cb33e5ac-e5b0-503e-ac87-b1aae2bc44b0 | note | Verifying Documents - This ITP
a38f60a6-7dcd-59f9-aef9-d50ab6f4e6f7 | date | Date Completed:
059dc7ae-6edd-4b43-82ff-725fbe1bc24a | signoff | AUTHORITY HOLDPOINT
fc0d7afc-b7b6-48ce-bf63-dfc1f328fa04 | checkpoint | 2.4 - Evaporative Retardant
97284960-52f6-5191-b4d3-41e3ece91a5a | note | Reference - 610.17 (f)
e1f82ac2-f05a-59b2-9aa4-8ae36cee5eef | note | Acceptance Criteria - Details of evaporative retardant, application procedure (including application rates) to be submitted for review to the Nominated Authority.
3038d70c-0226-5a8b-953c-ed12cd859de4 | textbox | Enter: Teambinder Material Approval number
779d2db8-b985-55be-83ba-6e66c01cca6e | note | Method - Document Review
0deda3bc-f0dd-5548-8b99-bbf88782bcc2 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
2d0686b3-029f-5fc4-9fe0-9b16f7557f68 | note | Category - HP
dc30859d-e99b-5ffc-91fe-cf24448e6b92 | note | Responsibility - Nominated Authority
4aca72d1-8d45-56eb-9e08-eb6aa09741d1 | note | Verifying Documents - This ITP
bb905d0e-b816-5cb4-afc2-d3328d46fbda | date | Date Completed:
4022f238-7210-4e51-afb2-5e7d67b4d6d5 | signoff | AUTHORITY HOLDPOINT
c12a7a64-bafd-42f2-a416-2fdd87aa4ea1 | checkpoint | 2.5 - Curing Compound
4090207c-ba59-56b2-98bf-4d442b3542e6 | note | Reference - 610.23 (d)
8960cc49-299c-5cb5-95ca-1b0d36263438 | note | Acceptance Criteria - Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
09e5d0cb-5f5c-5fc3-bd27-544e0acb3680 | textbox | Enter: Teambinder Material Approval number
61c4f335-4c93-5556-912c-da53fbc58bed | note | Method - Document Review
0dc106cd-eb8d-574d-8805-023fa4ee4217 | note | Frequency - Once, for each product, 4 weeks prior to placement of concrete
a99bc66f-566f-5a3c-8d63-438e9b5d7b9c | note | Category - HP
8bfea018-cc5f-5737-baa5-49ca3aec71fc | note | Responsibility - Nominated Authority
88ec030e-5b91-5c38-887e-f84b0082cc4e | note | Verifying Documents - This ITP
84405324-1a5e-52ab-8fcd-880b2b0a06c5 | date | Date Completed:
6c1f6039-325b-4017-8e47-1b861868b2d0 | signoff | AUTHORITY HOLDPOINT
c2beea8f-8606-4076-9541-06a53d6d5d1d | section | 3. Preliminaries - Procedures & Documentation
f99ff49e-148b-41ae-8020-455c58046c82 | checkpoint | 3.1 - Concrete Placement and Compaction Work Method Statements
a1bdacd6-f97a-593c-9af7-bbe930456cd0 | note | Reference - 610.18 (a) (i)
bd4c00ce-0381-5397-8d9e-90f41c652bbe | note | Acceptance Criteria - Concrete placement and compaction WMS to be submitted for review to the Nominated Authority.
f2282b0b-8d06-56ee-9d15-89cfcd1c5c1a | textbox | Enter: Teambinder Approval number
612d36b4-57fa-56b8-b8a3-24263b9e9fd0 | note | Method - Document Review
c6c362d0-e222-5e43-8a3a-ade0dcb55c26 | note | Frequency - Once, 4 weeks prior to placement of concrete
c767bf4e-d2f2-54ff-a61d-47a1ab7fc877 | note | Category - HP
84059861-29f4-5b01-886e-412dcbb52859 | note | Responsibility - Nominated Authority
414f6f82-5145-5981-b5b0-e17fecb2ca91 | note | Verifying Documents - ConQA Hold Point Release
f05c7a14-4e2b-52a3-b2e3-92fa2772c6a0 | date | Date Completed:
9cc99788-c8bd-4086-aeaa-9665cb5d7ff2 | signoff | AUTHORITY HOLDPOINT
51da44ce-0a7f-47f8-8173-c9223672f4bd | checkpoint | 3.2 - Concrete Sampling and Testing Procedure
8ed8bd9c-9509-5192-8bc6-8a3efe6b7566 | note | Reference - 610.18 (a) (v)
0ee4e1a7-6ee7-525d-b637-4c91dbbc9d86 | note | Acceptance Criteria - Concrete sampling and testing procedure to be submitted for review to the Nominated Authority.
42875fa8-6bdc-5c49-b9c7-b01c591f499e | textbox | Enter: Teambinder Approval number
f02f43ab-809f-5d0a-a2f9-e2e1d188c05e | note | Method - Document Review
b733e924-dd86-53a4-bc75-6a74d4f2ea83 | note | Frequency - Once, 4 weeks prior to placement of concrete
75e94362-15ba-5285-a640-3e8aa0a2c747 | note | Category - HP
094e5f0d-558c-5a3e-8834-3b1d92889e50 | note | Responsibility - Nominated Authority
4781b818-085c-5e40-aa65-716d3866b7a1 | note | Verifying Documents - ConQA Hold Point Release
a7d94fc2-41f6-5dc4-9c23-a612b087cea1 | date | Date Completed:
1b51a61e-f633-4d97-8ef8-9a59dc69dcaf | signoff | AUTHORITY HOLDPOINT
af08e26b-384d-4a0d-8b32-6ccbfff97385 | checkpoint | 3.3 - Concrete Placement and Compaction Toolbox Meeting
790c9ddb-c80c-55ee-afbb-fb4ad19ad90c | note | Reference - 610.18 (a) (iv)
20b798ac-4518-5fba-9c60-003ffa738f1c | note | Acceptance Criteria - Concrete placement and compaction toolbox meeting held to discuss the quality requirements.
9519dcfd-2279-58f3-8bd0-37616835a74c | note | ○ Minutes of this meeting to be submitted to the Nominated Authority.
7647b007-d64f-5f2e-965d-a0ccbad2d432 | textbox | Enter: Teambinder Approval number
c6230224-77fb-5319-9173-5086906e096e | note | Method - Document Review
a2696abd-1c41-5c27-a062-ccdd86765769 | note | Frequency - Once, 4 weeks prior to placement of concrete
e8dd0f20-ac2a-523f-ac2b-d0b1890a9090 | note | Category - HP
a5a0d126-ac2f-57b8-91ed-3de7841a6c16 | note | Responsibility - Nominated Authority
c593e6bc-3b4f-51b6-a87e-ce19127f36a6 | note | Verifying Documents - ConQA Hold Point Release
3710cbdb-239c-59d4-973f-92d20c939c4d | date | Date Completed:
b68188f9-2b98-4733-871a-e0cd51877637 | signoff | AUTHORITY HOLDPOINT
f1bb2841-b5e2-4bf6-a5af-8654304db305 | checkpoint | 3.4 - Hot and/or Cold Weather Concreting Procedure
cc07809d-1d64-5990-b749-7e057561836f | note | Reference - 610.17 (a)
d49aa3d8-c742-5a0d-adf4-a04692f38d1c | note | Acceptance Criteria - Hot and/or cold weather concreting procedure to be submitted for review to the Nominated Authority.
a06a05c3-64e7-565f-a446-fa6d80b0ef0e | textbox | Enter: Teambinder Approval number
4b18977e-a5a4-54fd-a15a-bee45dc1c15c | note | Method - Document Review
33b2e15c-424e-590a-af44-a99c80bdff05 | note | Frequency - Once, 2 weeks prior to placement of concrete
07b9c176-3284-529c-b35a-ca24196eb100 | note | Category - HP
3189123d-d21b-54da-ba35-a2edea1149c3 | note | Responsibility - Nominated Authority
3283c68f-f840-5eb7-8eec-de244a85994e | note | Verifying Documents - This ITP
ab68b9c9-5bbb-5b30-9b65-7538ee4e7f44 | date | Date Completed:
78ce644b-dd3e-4298-8c9d-e4b946d7d13c | signoff | AUTHORITY HOLDPOINT
beb8f4eb-9395-42f7-ab03-e8d223488a70 | checkpoint | 3.5 - Curing Methodology (for Concrete and Grout)
5270e87e-0606-53e5-9dde-39bcd0411fc0 | note | Reference - 610.23 (a)
a6e6de8a-2f6c-585d-a10d-46dd82cb0095 | note | Acceptance Criteria - Curing methodology/procedure to be submitted for review to the Nominated Authority.
16151c82-4897-5c69-bec2-2b3e8b443112 | textbox | Enter: Teambinder Approval number
e1836bbe-c37e-58de-8070-2755eeba84bc | note | Method - Document Review
e5d14415-3884-5431-93ee-d53b7524425e | note | Frequency - Once, 4 weeks prior to placement of concrete
7c50eb9f-9c74-5e53-add2-4854c0283208 | note | Category - HP
bb04e038-750b-54ea-a7df-39d22b508d87 | note | Responsibility - Nominated Authority
96b24aa9-4040-541c-833e-ab53d03b5663 | note | Verifying Documents - ConQA Hold Point Release
97a8469b-6602-5723-afd6-2ff854a4fe04 | date | Date Completed:
3a1e6f5e-93d6-4cf3-bdf7-1c125c56fb57 | signoff | AUTHORITY HOLDPOINT
9ba2b7b6-0fb5-4d9f-ab3a-2fd4abe88de1 | checkpoint | 3.6 - Concrete Drilling Procedure
7ec4cfd5-0250-5a23-8cee-27398bc14deb | note | Reference - 610.46
d0b054d6-6945-567f-9b58-cb351a57e0f8 | note | Acceptance Criteria - Where holes are to be drilled into existing (new or old) concrete members, the locations shall positioned to avoid striking any existing reinforcing bars, tendons and services.
14f2ba11-a4c0-5143-be78-23bbb31fae59 | note | ○ The planned locations and drilling procedure shall be submitted for review to the Nominated Authority.
e853d43a-86c4-5ba0-b6a0-a5c0355d33e1 | textbox | Enter: Teambinder Approval number
5c800a82-ab53-5c1d-a45f-eee76934b74b | note | Method - Document Review
89c7386f-16c8-5288-a9fa-323b0ee13c7f | note | Frequency - Where applicable, once, 2 days prior to drilling
8ac20fd3-588d-57b6-9ee1-4eadfc67f4e5 | note | Category - HP
ccf08a8d-16ab-5e94-bcf8-a1cb5b287d3c | note | Responsibility - Nominated Authority
7c316568-09e9-592a-bb3c-5c15a0375848 | note | Verifying Documents - ConQA Hold Point Release
7a96c410-b245-5bd2-9d25-635f25899217 | date | Date Completed:
d8e89245-7a24-4d1e-86e9-1c39681be8ff | signoff | AUTHORITY HOLDPOINT
69469c4d-b98e-42e4-a5c1-c38226794934 | checkpoint | 3.7 - Temprature difference measuring-Calibration
8155736d-b916-5358-821b-a96e4a9385af | note | Reference - MRPA Quality Management Plan
383f221f-52d7-5a1a-bca8-e24d484ee19e | note | Acceptance Criteria - Calibration records are valid and up to date.
22c81c3f-62e0-516f-ab67-48e60883bfca | note | ○ Attach: Calibration certificate
d61d883b-c83c-501d-bdd7-06398423b442 | note | Method - Document review
2e1133ed-a367-5d93-9001-2e9b66d77531 | note | Frequency - Where applicable
3a0031aa-5e2b-5f25-8fe8-72065e882e26 | note | Category - HP*
899b6279-3449-54b0-a638-1579ba25acdd | note | Responsibility - PE
ae55a10a-1b02-5bd7-8eb3-9af584171f55 | note | Verifying Documents - This ITP, Attached calibration certificate
3fe672e7-613a-57a1-a5c0-653867e211ef | date | Date Completed:
848e4fa9-efe9-4fff-a7af-78eeb01e13af | section | 4. Pre-construction Activities
162ee76b-b937-4591-93ab-031f6fcfba2b | checkpoint | 4.1 - IFC Drawings
099a34b0-72fb-5bd2-b7b7-ee058240fdca | note | Reference - MRPA Quality Management Plan
0f796597-1fa5-5eb6-a8cb-ede559da931a | note | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
740e2dcf-a959-55f5-a7d2-8e9340a6a72e | note | Method - Document Review
a3d6e1cc-246b-5703-8f8a-9c2e35d58501 | note | Frequency - Prior to starting Works and at regular intervals
d664dbb5-f5f7-50d4-8579-acc50fe90ae2 | note | Category - HP*
047b7766-4f22-5fde-ad84-a29ddb5e9655 | note | Responsibility - All
62133164-c539-5aac-90d7-0654374cee50 | note | Verifying Documents - This ITP
a3b5f1ba-e3fc-5329-a40e-fcf5a2d2e549 | date | Date Completed:
1751665f-c523-4e07-9a68-ac01022e66f4 | checkpoint | 4.2 - Survey Set-out
2d206af1-f3d0-5272-b2eb-8fb99e2d3256 | note | Reference - IFC Drawings 610.47 (a), Table 610.472
6ec969f3-a452-58b8-979c-0bd1e1bc7f61 | note | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.462 as applicable to the element.
39b25d0c-bd89-591f-819c-eacf192cf124 | note | ○ Attach: Lot Map, Marked up drawing which shows the Lot Location and extent
bf40aa50-7765-51a7-acb1-2ffe09607628 | note | Method - Measure, Visual
4bd3b975-0154-553d-b17d-cd6228f59eac | note | Frequency - Each element
5cae731b-0a05-5668-a0cd-a661d7b04614 | note | Category - IP
c1cc4c4f-a2c4-574d-ba11-a3f84045fe14 | note | Responsibility - Surveyor, SE/PE
c789e97e-a538-5e20-a4ce-4535f310d517 | note | Verifying Documents - This ITP
c9c29cef-e4b4-5eda-91c6-d2af1839f509 | date | Date Completed:
2847119f-b037-4a04-afd8-899d5df4334e | checkpoint | 4.3 - Excavation support
eee539d4-4532-5628-afab-e5d7175e0d04 | note | Reference - 602.02
d8e2287a-ae9e-5a98-9468-355e66705405 | note | Acceptance Criteria - For excavations adjacent to railway property, alongside roadways, in or alongside waterways, and excavations deeper than 1.5 m, the Contractor shall submit to the Nominated Authority for review detailed drawings of bracing and/or sheeting proposals, including design calculations and methods of construction and removal.
8b900946-ddde-5a4e-a0dc-db341cc8e3ee | textbox | Enter: Teambinder Approval number
cddbf1a2-a121-591b-96c6-205131c55d95 | note | Method - Document Review
b2ef1b2c-2a20-5083-93cb-86323c7239ee | note | Frequency - Where applicable, not less than 10 business days prior to excavation
00c50163-e3b8-5054-a142-fecd58686aec | note | Category - WP
5379720b-95bf-58db-bb07-ffdaacbff1f9 | note | Responsibility - SE/PE/SPE
1896d09c-26a0-5ec5-bec8-60335fac3dd8 | note | Verifying Documents - ConQA Hold Point Release
3a450b7a-ecf5-55dd-93c8-f7690d1dfd44 | date | Date Completed:
73010867-d4f5-4ddb-b0c8-c91a4b304986 | checkpoint | 4.4 - Excavation Inspection
8ae7a2b0-f3ea-5956-8e9b-873b0d2366ed | note | Reference - 602.03
5e1d8c50-693c-5ef4-b4d2-c33fac625350 | note | Acceptance Criteria - Blinding concrete shall not be placed until the bottom of the excavation has been reviewed by the Nominated Authority.
d4cbe1ee-ae15-5333-bf7a-2bd086d560a5 | note | Method - Visual
04438f7e-b194-5b61-ab98-4f58087b2767 | note | Frequency - Where applicable, prior to placing blinding concrete
5c77de2f-3d0e-55d3-b4f2-0e14ff0d4d3c | note | Category - HP
758ddad6-97d7-5f98-915a-cacb0e97ee5b | note | Responsibility - Nominated Authority
1ac822ce-e16c-5a1e-8e01-4c98c1058434 | note | Verifying Documents - ConQA Hold Point Release
dadfad92-f7d4-505c-aa56-63f8251f850b | date | Date Completed:
342c0ef4-8b7c-4b07-a359-2c939323c54f | signoff | AUTHORITY HOLDPOINT
42df0f31-15c8-42e6-b1e2-fefb30621925 | section | 5. Construction Activities
133a61f7-bb9d-43e0-8151-6bf4a095eb86 | checkpoint | 5.1 - Formwork Design and Construction
b37ac461-7b2f-5637-9928-daa92f26b62a | note | Reference - IFC Drawings 614.04, 614.05, 614.06
b76a020b-ee08-5455-91ba-e385fc64601c | note | Acceptance Criteria - Designed and constructed in such a manner so it can be removed without damage to the concrete.
10260dd9-aad8-5412-ac07-ec7f0a59efcf | note | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
8bae3c25-4dad-5e82-9449-2bfa0717632c | note | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
79e279c4-84d5-54bd-9783-f9f3c07f5013 | note | Method - Document Review, Visual, Measure
41560d08-a9d6-509c-9439-524d5332edd8 | note | Frequency - Each type of element
f1e72f92-2477-5bcf-bd98-d3ca6ca8b60a | note | Category - IP
70749780-2dc4-52be-a0a2-d13c9a04192f | note | Responsibility - Temporary Works Designer, Proof Engineer, SE/PE/SPE
3703eef5-6c1b-5655-a5e6-22544df67759 | note | Verifying Documents - This ITP
25578fee-e457-5c29-a93e-c468e3320c7f | date | Date Completed:
6c6969a0-a4ae-4830-81c4-84bc4c372863 | checkpoint | 5.2 - Formwork Certification - Formwork Inspection (Members Greater than 2m)
e34b5662-d645-552b-bf7f-197b414a8f18 | note | Reference - 614.08
95f45f46-c0a8-5d61-9ecf-1a9c12099499 | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
697f64ca-3d27-5011-989c-af997b1026e9 | note | ○ Walls with heights greater than 2.0 metres
a57c76e7-9970-57fc-aaf1-18a131f171ae | note | ○ Any member for which self-compacting concrete is proposed.
e8ca6da6-5219-5295-9022-2a19de2306a1 | note | ○ Attach: Attachment A
1dab2694-5507-516e-af5f-ee3625c96a80 | note | ○ Attach: Attachment B
6b4edc2e-b36a-5a79-8bbd-aa93d109dc62 | note | Method - Document Review, Visual, Measure
b0b0ac8b-a60c-5c7d-b6ae-6d615e78496e | note | Frequency - Each element (where greater than 2m)
3d9c12b0-2a68-5c1f-ab58-3ec1efb5ff69 | note | Category - HP
bb6dbc68-d5bd-5826-b551-af5d4b4ca97b | note | Responsibility - Temporary Works Designer, Proof Engineer
de11423f-a80a-58b0-adbe-2fd557983383 | note | Verifying Documents - ConQA Hold Point Release
4ff552c3-7425-59c7-80f6-1b4d895d2950 | date | Date Completed:
17612ea6-6185-4ed6-bffc-1fb9dc9446ec | signoff | AUTHORITY HOLDPOINT
7f4b10bd-4d09-4cc8-8893-02f7a2efb3c7 | checkpoint | 5.3 - Formwork Certification - Formwork Inspection (Members Less than or Equal to 2m)
a8e649ee-fc55-58ad-95e2-0c98e59e4c3d | note | Reference - 614.08
197067fd-a787-5b21-8ab9-da51744001fe | note | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Formwork Inspection of the constructed formwork has been reviewed by the Nominated Authority
4128e2dd-f79d-5c87-a9ea-d7d8f95c9699 | note | ○ Walls with heights less than 2.0 metres
d1ba3318-56c3-5b0f-b493-f1c433861df7 | note | ○ Attach: Attachment C
577b9a7b-de99-5ca0-bae9-0f337ce6210e | note | Method - Document Review, Visual, Measure
4e4144ca-9876-5596-9933-b83667309437 | note | Frequency - Each element (where 2m or less)
0005dff0-6c68-54e3-8b44-9a2d30bbe2bd | note | Category - HP
d2aaa16e-8edf-5e02-a825-228adfe0efa2 | note | Responsibility - Temporary Works Designer, Proof Engineer
a2148290-f093-512e-b6c4-5331a9b8c06c | note | Verifying Documents - ConQA Hold Point Release
72f358f2-e0a1-5121-9bec-ca16330edb52 | date | Date Completed:
1e5a27b2-c7bd-4d2d-a5af-e720f9d0111e | signoff | AUTHORITY HOLDPOINT
b8a68121-3f9b-4961-87fb-90c96a58c84e | checkpoint | 5.4 - Pre-pour Survey
cad3a55d-ab4b-53ea-b44b-fd87a5f4b4ef | note | Reference - 610.47 (a), Table 610.472
ede4d83b-1505-52c4-bfd6-7b9aec549f15 | note | Acceptance Criteria - A pre-pour survey carried out by a surveyor.
9b69470f-262d-518f-b18a-a4384ceb7a7f | note | ○ Erected formwork within the tolerances as per the table 610.462 as applicable to the element.
fbf35db7-3a0f-50f6-95f1-58f0b9062712 | note | Method - Measure, Visual
de17f010-c628-5246-b6e6-baedaddf7d0e | note | Frequency - Each element
33edd866-fb13-5270-a4d2-2ad425023c73 | note | Category - HP*
8a1a9a03-2477-59e6-b99e-6fc1fef6adb9 | note | Responsibility - Surveyor, SE/PE/SPE
fc3534a9-1484-57fc-aa79-9f1b7f3aae8e | note | Verifying Documents - This ITP
20283121-98eb-5517-8f8e-8740cbc432a0 | date | Date Completed:
f0e37797-48a6-4084-a5c6-22368784b506 | checkpoint | 5.5 - Reinforcement Placement
f7bca32a-951f-5ce0-83b3-139f33153f7a | note | Reference - IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
58aae7e1-f6a5-5e85-929f-94aec84de754 | note | Acceptance Criteria - The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
b0f68420-2227-59f4-a7d2-c8d1932e8baa | note | ○ Projecting reinforcement is the correct length and location.
f0ab104b-46d8-5335-ad99-1b1c565bd058 | note | ○ Splice lengths achieve the minimum length and are in contact for this length.
d79ed4c7-07b2-5d80-bec6-519c8990746a | note | ○ The reinforcement surface condition is free from dirt, debris and damage.
9e335e84-a61b-501e-b2e6-140504c22060 | note | ○ The resulting cage securely held with sufficient ties to limit displacement or deformation during the concrete pour.
5cbee63f-bd8d-5a59-b63d-2dfd18540f13 | note | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
1f4b0f31-8e83-5816-a9f9-f7909a7b5bf0 | note | Method - Measure, Visual
0795fefc-b989-5bdd-98a7-42606767a96a | note | Frequency - Each element
98cbe582-4e7b-5ac5-910f-960374ab47a3 | note | Category - IP
588087dd-cb08-5af3-84d4-d79f2b3c419b | note | Responsibility - Foreman, SE/PE/SPE
21c56fbb-52ca-5927-824d-dbe63c010960 | note | Verifying Documents - This ITP
091aba1e-f0ab-5eab-b515-3c7a4c0fefd8 | date | Date Completed:
0f471b38-aede-48e7-b289-8c3d3e8a583a | checkpoint | 5.6 - Cast-in Items
0ff77a39-4e87-5afa-8232-5a4c29f7d293 | note | Reference - IFC Drawings 610.47 (a), Table 610.472, AS3810.1 Table 3.3.6.2
e7b27211-02df-5627-a55f-a68f9a1016f8 | note | Acceptance Criteria - All cast-in items are the correct type, grade, quantity, size, orientation and location as shown on the structural drawings and are securely fastened or restrained to withstand impact and pressure during the concreting operations to prevent dislodgement.
9bb502cb-a547-5bba-a0c6-ff5ac4f74661 | note | ○ Any exposed threads, conduits, ducts or voids shall be protected by suitable means to prevent concrete or grout ingress.
191ba927-22f5-5607-8cec-5f9ad827048c | note | ○ Tack welding of any cast-in items shall be performed by someone pre-qualified to do so.
06dcd5ff-ce93-51a6-8c40-2cd23e1634eb | note | ○ Grout tubes shall be fastened at regular intervals to prevent kinking.
b3ee77a7-241f-5dff-b4d5-b60e400fda06 | note | ○ Placement tolerances to comply with the IFC drawings, if not specified, use the following:
06de3f2c-b0cc-5952-a986-9dde68ac1960 | note | i. Bolts, ferrules, projecting bars & couplers = ±3mm
7e3a65ef-6b31-54b4-ae26-bb83a9db50c3 | note | ii. Running dimensions of a group of the above = ±6mm
76c7a902-fb16-53e0-bade-253ae31acd8a | note | iii. Ducts and conduit location = ±12mm
4bcec090-033d-559e-ad76-1362ba1ea6a6 | note | iv. Diameter of ducts and conduits = ±3mm
47959073-ea12-57d0-999e-1b9bfb7d9b99 | note | Method - Measure, Visual
bf641980-d85b-5515-b997-927d8d31bd29 | note | Frequency - Where applicable, each element
317fcd04-cf2d-5c74-b137-649f53b0e3f5 | note | Category - IP
e79e1482-1c37-52ee-b0e8-b76dda7d0427 | note | Responsibility - Foreman, SE/PE/SPE
242636ec-7e13-5ae2-8779-08d4107df724 | note | Verifying Documents - This ITP
8f7f99e2-7471-5889-983f-c88b40f001db | date | Date Completed:
b848c858-226c-4368-902e-3c94940a9324 | checkpoint | 5.7 - Thermal Differential Monitoring
9dd03924-990a-5b4c-b380-23be45f8428e | note | Reference - 610.22
ac3e45eb-d364-5cef-9e70-c1487ae32051 | note | Acceptance Criteria - Thermal differential monitoring thermocouples installed.
23c9f4c5-ae9e-5da0-8e3b-f3f79d1d59a2 | note | ○ Only applicable if the element has:
4ead1d97-7086-512a-8250-4ed1d72975a5 | note | i. The least dimension of a member exceeds 500 mm or
b1071fa7-61c6-5cd3-918a-002a2b4e07e4 | note | ii. One or more faces being restrained by previously hardened concrete or other external constraints.
a9729091-f1e0-56a4-9833-570c444f4f13 | note | ○ Temperature differential monitoring shall be undertaken on at least one representative member from each type of large and restrained members, provided that any required control measures to reduce the differential temperature within the specified limits is adopted for the subsequent construction of members of the same type.
f5ed92c0-7581-5896-a5d9-5495fe7be25b | note | Method - Measure
5208b753-5171-58f0-b6e4-8de1fec78107 | note | Frequency - Where applicable, each element
fbefc1b7-b14e-5b0c-a0f7-cf2fc211d87d | note | Category - IP
f687d9b6-ef04-565f-9020-c10ad9a233fb | note | Responsibility - Foreman, SE/PE/SPE
133e46da-fc1a-5ed7-becf-af4214608e51 | note | Verifying Documents - This ITP
b9763525-604d-5e20-bf6c-3999a0026d11 | date | Date Completed:
b3f7b486-d051-4a3a-af71-cb6bd486d40c | checkpoint | 5.8 - Pre-pour Inspection
98d1f9b5-88d8-5136-b004-510611254c8f | note | Reference - IFC Drawings 610.18 (a) (ii) & (iii)
65430fce-67bc-5b3f-86b2-a65c6a812412 | note | Acceptance Criteria - Evidence that the forms, reinforcement, electrical continuity and other cast-in items conforming to the requirements of this specification and the drawings has been reviewed by the Nominated Authority
2ced1846-cd93-52fe-b659-ff7c7fc1522e | note | ○ All foreign material has been completely removed from the forms.
d7db1b16-b455-5241-aed0-5c84b44fff97 | note | ○ ATTACH: Pre-Pour Checklist
0dc4b8b0-92cc-5659-adbe-c6eb271b0298 | note | Method - Measure, Visual
171fefca-20f3-5036-a158-3593848c00d5 | note | Frequency - Each element
2fc7c5bc-9762-562b-9587-5059e694ac42 | note | Category - HP
1cef56b9-93e2-5264-ba3f-b37a83594c27 | note | Responsibility - Nominated Authority
360297b4-adc4-5ba4-9b53-b14deb990ac9 | note | Verifying Documents - ConQA Hold Point Release, Pre-pour checklist
2f600380-918b-5c7a-959e-3ba6b9d8f7d1 | date | Date Completed:
e4c54f75-a51c-4a93-8470-1df24657f73e | signoff | AUTHORITY HOLDPOINT
86636490-7bbd-46f0-ba40-4ab9d1144b4a | checkpoint | 5.9 - Weather Conditions & Evaporation Limits
0fab4ee8-0ec3-5d4d-ae73-4c51ba0feb4b | note | Reference - Hot and/or Cold Weather Concreting Procedure 610.17, 610.17 (a) & (e) Table 610.171
1b6b2ee2-9ae4-52ed-bb49-b0840d8128f6 | note | Acceptance Criteria - All freshly finished concrete surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
8627ce04-5682-5a07-ac8f-5fb0827a39fb | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
364ff5ce-ee89-58d1-950e-8316668808e6 | note | ○ The air temperature, relative humidity, concrete temperature and wind velocity are measured to determine the evaporation rate of water from the concrete.
0e8e0abf-d406-5dc5-a58e-e2548df0cbc0 | note | ○ When the evaporation rate exceeds 0.50 kg/m²/hr apply evaporation retardant at the rates specified on the manufacturer’s TDS.
e17fc98c-4576-5073-ae7f-7ae1e10a26bc | note | ○ Record: Required information on the Concrete Pour Record.
fb633b6b-3357-5e3e-a290-c693b39b5665 | note | Method - Measure, Visual
f207d7ed-0f68-5b73-ad6f-1856344b8c06 | note | Frequency - Each element
214f6316-dec5-5d54-8190-de91e1d2bc8c | note | Category - IP
8ced4e89-3218-53b1-b9f8-375ad06c963e | note | Responsibility - Foreman, SE/PE/SPE
b39dc073-259a-5164-bbd6-81fc27102d23 | note | Verifying Documents - This ITP, Concrete Pour Record
ee4eeacc-f6bd-5d24-89c0-81fe394f5a52 | date | Date Completed:
09f6b52e-6c5b-4053-a8dd-d34427dff37d | checkpoint | 5.10 - Concrete Testing - Sampling Frequency
89e614b8-03ea-5a28-bf8e-fc6cf3b9fc49 | note | Reference - Site Sampling & Testing Procedure 610.16 (b)
40e34e55-1543-5744-b505-c778b1162fbe | note | Acceptance Criteria - Concrete cast in one continuous operation to be tested at a frequency as shown below:
eaf525b1-3981-5237-ab5b-94eaac1c4a26 | note | 0m³ to 10m³ = 1 sample
15f5ced4-260f-5221-a837-ed33c8fb6d6f | note | 10m³ to 25m³ = 2 samples
c42907bd-e030-5499-af15-1500b10a0688 | note | 25m³ to 50m³ = 3 samples
7afe3086-7e37-51d4-9ace-d022cb2478c4 | note | 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
ac2e62c1-2dd0-5b0e-8f41-13e98f87e202 | note | ○ For each additional 50m³ and additional sample shall be taken.
7371c2dd-5cc2-523d-947a-ad8f823c97c4 | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
e163feca-198c-5360-9edc-5d5b4b453f6b | note | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
0dbdc003-eb0e-50bf-b7fe-7dd283cc9766 | note | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
6d17f2bd-8617-581f-991c-d330e16742e2 | note | ○ Note: Additional cylinders may be required for other purposes such as early trafficking or removal of formwork.
e3b05aa4-b9b4-59ff-a343-1af9e6f1a49d | note | ○ Record: Required information on the Concrete Pour Record.
51c5369f-5381-5387-a889-200d75c86a18 | note | Method - Test
51d562c5-9a20-5506-ad22-181465f7e84c | note | Frequency - Each element
deee187a-75ed-5627-8c43-8daa4ced6096 | note | Category - IP
89e996d9-3ce1-5f88-9873-569ad9c5b9d8 | note | Responsibility - Concrete Tester, Foreman, SE/PE/SPE
7757e693-9ecd-5528-b7b4-6ecc63503a80 | note | Verifying Documents - This ITP, Concrete Pour Record
2d09fd01-736b-591d-a9f4-702625229f7a | date | Date Completed:
ab7ca3d5-8c57-4a69-a37e-9f846eb032c2 | checkpoint | 5.11 - Concrete Testing - Slump
c4de8aa1-6332-5d7f-bfdf-db998c97585a | note | Reference - 610.16 (c)
307235df-6dc1-537f-b097-8350c01a9c8a | note | Acceptance Criteria - Slump testing tolerances =
0cf254d7-b62e-5648-9eaa-012141ba9d73 | note | <60mm = ±10mm
694fffd1-213e-55f2-a040-9ebcee779cac | note | ≥60mm to ≤80mm = ±15mm
3b4d7fed-833e-5575-b848-4bf54d4bf963 | note | >80mm to ≤110mm = ±20mm
931e714e-76e0-5475-a66a-8aa6cfa16cb1 | note | >110mm to ≤150mm = ±30mm
ad7723af-9145-5f6f-9b7a-a7b63f1fd520 | note | >150mm = ±40mm
411786cd-1619-59a2-8108-e841413eab59 | note | ○ Record: Required information on the Concrete Pour Record.
783528e2-d2a8-5caa-915d-3b8f814b6539 | note | Method - Test
d377ecd9-9ae8-543f-8198-222959ed2079 | note | Frequency - Each sample of Standard or Superplasticised Concrete
c69fe61c-4d05-59e6-b68e-9e4482636d6d | note | Category - IP
9334102e-bd83-5285-b5fe-32a8cb577b5e | note | Responsibility - Concrete Tester
cabe5590-3574-5c82-b943-0d7b78ea00df | note | Verifying Documents - This ITP, Concrete Pour Record
ea0e9832-be6c-5efa-9bf7-4e4dffc0af97 | date | Date Completed:
dabff83d-a3f5-4204-ad68-0083fd0fb287 | checkpoint | 5.12 - Concrete Testing - Spread, Passability & Viscosity
0d0f175b-b929-5eb0-8160-990add6957f2 | note | Reference - 610.13 (b)
4d5d475e-67ba-5270-b2ef-d3eb1e430f01 | note | Acceptance Criteria - Spread range = 550mm to 750mm
29dfcba3-5418-571a-9d2b-097d8087c0c9 | note | ○ T500 = 2 seconds to 5 seconds (to reach a spread of 500mm)
51816efb-def2-5d71-8dea-67d371f478dd | note | ○ Passability = ≤10mm (aggregate height differential)
0fc2ea70-1d7b-5962-b003-fd6d075be166 | note | ○ Record: Required information on the Concrete Pour Record.
2be2c726-6481-525d-8ec0-8174337b2bde | note | Method - Test
ef9823db-f1c0-5877-ae5c-861dd8a8b792 | note | Frequency - Each sample of Self-compacting Concrete
4352ec16-0f6a-5d2e-8d82-d3c0f2001ee2 | note | Category - IP
d69448c4-1faa-5f5c-8740-0f847729c9e2 | note | Responsibility - Concrete Tester
b8edf989-5b5e-5931-ac5a-237a229df4f7 | note | Verifying Documents - This ITP, Concrete Pour Record
5c662d72-24a8-5c60-aeee-333558bd3f24 | date | Date Completed:
82636ed7-9bfe-4822-a083-ca90692cc3a0 | checkpoint | 5.13 - Concrete Testing - Compressive Strength Cylinders
89b1af37-22d3-5769-bbff-d55839410e2e | note | Reference - Site Sampling & Testing Procedure
c605e777-6f39-5b23-a41c-668ddda11548 | note | Acceptance Criteria - Correct quantity of cylinders manufactured per sample.
7409bbb1-7d1c-5255-b5f7-a4bb157d6af7 | note | ○ Record: Required information on the Concrete Pour Record.
a2c12512-5e5a-5965-85c9-c7d6c9569b65 | note | Method - Test
f3d5ba9d-12b3-58a0-8118-55479fd17141 | note | Frequency - Each sample
be0f3432-3cd2-5e1e-b98d-3c7cddacbbb3 | note | Category - IP
4a35ce18-7a40-500b-ac96-d314667e0e6e | note | Responsibility - Concrete Tester
cc51f46c-b46d-50a6-afba-bac540875164 | note | Verifying Documents - This ITP
afda5e2a-0646-5c83-8a78-0d889e52302e | date | Date Completed:
18e696bc-8ae9-4686-aa93-3b96889416e0 | checkpoint | 5.14 - Supply & Discharge Rates
f1cd5d21-94b5-5d19-8486-25de0d07e9d1 | note | Reference - 610.13 (a) & (f)
28397da4-a969-54ab-835e-a552e8b36b4c | note | Acceptance Criteria - Concrete is supplied at an adequate rate to ensure no cold joints are formed.
2b28a7a8-53a2-5fe3-8e6b-68c5dda8f880 | note | ○ No water is to be added once discharge commences.
8e65a8a9-a6a0-5812-b5ed-239ab04170f2 | note | ○ Maximum time between batching trucks is 25 minutes.
cc96dc01-419c-59e5-98db-b7143d0d881b | note | ○ Maximum elapsed time for discharge (including compaction) is 60 minutes from batching unless the mix design has an extension using set retardants.
d84f91f9-9e2e-526b-abeb-15415afd7889 | note | ○ Concrete that stiffens or is showing signs of stiffening shall not be used.
f35f6c77-0ce1-515c-8d0b-9a162feb7188 | note | ○ Record: Required information on the Concrete Pour Record.
3de7b32c-8eb5-59cf-8903-204671ba064d | note | Method - Measure, Visual
c21969db-0195-5cea-852d-80ce02e54930 | note | Frequency - Each load
f108934d-16ff-5f83-a642-f850ed55a1b1 | note | Category - IP
af478976-0357-5a5f-a5d3-35da25140768 | note | Responsibility - Foreman, SE/PE/SPE
7d3e74b6-f471-5dc8-9353-ed833bd716f2 | note | Verifying Documents - This ITP, Concrete Pour Record
580f4b95-db16-526c-9905-9547831d71f3 | date | Date Completed:
421ff2ee-7ba3-4b1c-9129-66d1c8ddd4cb | checkpoint | 5.15 - Placement & Compaction
aeb58787-4e23-53a2-9bf8-6d47f5046827 | note | Reference - Placement & Compaction Work Procedure 610.18 (a) & (b), 610.18 (d) (i)
306321a2-5e68-5c77-8ac3-fbcbac7d6695 | note | Acceptance Criteria - All concrete batches are traceable.
9635dcdc-f625-53d9-b544-69862703cbc7 | note | ○ Where concrete pumps are used, the initial discharge is pumped to waste until a consistent workable mix is discharged.
69d003f5-a68d-568c-95cc-683e77a0ce93 | note | ○ Concrete is not dropped freely from a height exceeding 2m.
1e2214e2-2201-5674-a8ca-0877648e78a9 | note | ○ Concrete is not moved horizontally by use of vibrators.
30ede342-5645-552c-bf9f-2ba7266180ef | note | ○ Adequate compaction is ensured
207d6efe-1007-55e1-9acb-57233932b9bd | note | ○ Care has been taken to fill every part of the form and force concrete under and around reinforcement and embedments.
efded372-e0b2-58ee-a503-4ca2008cefc3 | note | ○ Concrete layers are not more than 350mm
2bfb88f4-a334-5643-a1c1-686615ca4c1d | note | ○ Internal vibrators are inserted at spacing not exceeding the manufacturer's zone of influence.
e2fbd61b-b007-5918-94ae-9831079c068e | note | ○ Vibration continued at each point until air bubbles cease to emerge from the concrete.
fa5a0517-5480-559b-88eb-149bf8442c1a | note | ○ Attach: Concrete Pour Record
ceba85af-f79c-5ee0-95f3-7829c4189c13 | note | ○ Attach: Concrete Dockets
5b9e62fe-6fa6-5571-a0ca-648622ff0ed7 | note | Method - Visual
62f8d779-a476-5e6d-95b2-eceea9188cce | note | Frequency - Each load
7c84ccfc-fc78-5ceb-ac8c-53aa1e207465 | note | Category - SP
afa92682-2818-5dc5-981e-df59e4fb8aa4 | note | Responsibility - Foreman, SE/PE/SPE
bdab3cbf-a232-5de1-971d-60de341f61f5 | note | Verifying Documents - This ITP, Concrete Pour Record
24483ed4-3f84-5fce-b828-6c173f4e534c | date | Date Completed:
f7ce49cb-0449-43ae-b715-24e3499d178d | checkpoint | 5.16 - Surface Finishes
990f5e6a-60da-586d-9228-34687d616e8a | note | Reference - IFC Drawings 610.31, 610.20
70f5c7b8-5ffc-516d-88fc-b3bc4a9e32e5 | note | Acceptance Criteria - Surface finish as per IFC drawings.
4d236d6a-03a9-58e9-b8ef-a2c0257468bc | note | ○ Where surface finish is not detailed, the VicRoads class finishes will apply as per 610.31.
09decca7-6aba-53ad-8dc4-853f7b8cfffd | note | ○ Construction joints shall be roughened in locations shown on the drawings - any proposed changes to construction joints shall be subject to approval from the Nominated Authority.
8653a3e3-b17f-58cd-a8b2-86d7a9d2971d | note | Method - Visual
4e1ea3eb-1645-5f67-9dce-57a6361b8413 | note | Frequency - Each element
1866286c-802c-56a1-bd50-ea6230018679 | note | Category - IP
beed3ef0-3b8d-514a-9fda-191f56b0d7c3 | note | Responsibility - Foreman, SE/PE/SPE
14a890f0-090d-53bc-93af-dfeea22216e8 | note | Verifying Documents - This ITP
ae99b426-a22b-5407-ba80-7be7508470be | date | Date Completed:
72a44695-07e0-4616-a0f3-919eeaeb7335 | checkpoint | 5.17 - Curing-Top Surface
9b1e2076-1d23-5a6f-b78f-f24ec3c1f988 | note | Reference - IFC Drawings
6e12d54e-53d1-5ded-bd7e-783bfec7a615 | note | Acceptance Criteria - Top surface of the pier and abutment walls shall be water ponded for at least 72 hours following initial set. Alternatively the top surface of the pier and abutment walls may be covered with thermal blankets for at least 72 hours and then treated with a curing compound.
40b742fa-b420-5aaf-9ca7-132e94fcb558 | note | Method - Visual
3bda9b31-a0f5-5823-a087-28b62a008d7a | note | Frequency - Each element
bc45b4a4-b572-52fd-8a68-006e0710c913 | note | Category - IP
dcac9494-d8b7-5afd-afd5-1c0c284257f9 | note | Responsibility - Foreman, SE/PE/SPE
56aea463-1518-5593-aed2-d2cdb72eadc4 | note | Verifying Documents - This ITP
0dd8accf-5b2e-51f2-9bd1-4bc04d69f611 | date | Date Completed:
5ae51f0a-286b-4417-ae11-97dd397d8238 | checkpoint | 5.18 - Curing after formwork removal
f05258e8-8010-51e6-8b02-87e5d6ad0245 | note | Reference - IFC Drawings
441d3516-419c-5a0c-a401-145b17b33cb6 | note | Acceptance Criteria - After formwork removal, seal curing shall be applied to all exposed concrete surfaces to achieve overall of 7 days equivalent wet curing
dc6c6174-5385-5308-9ed3-9ada6773b51b | note | Method - Visual
69e80b90-fa24-5d85-93eb-74cc7ec81ff8 | note | Frequency - Each element
fd8265c7-d840-5060-ac34-6fe50f302538 | note | Category - IP
20c7c73c-e90a-56e6-b1d4-5986948d57b4 | note | Responsibility - SE
51a5f7f7-7616-5411-b8c8-42bbeac2edfe | note | Verifying Documents - Thip ITP
bb3c6b88-5e49-5971-90c9-bf11a748509a | date | Date Completed:
9e61657f-89e4-4c07-8e93-4215cb800222 | section | 6. Post-construction Activities
a4290fdd-80aa-4e8c-954b-f531b83d0ad8 | checkpoint | 6.1 - Thermal Differential Monitoring
39c73cbe-a68b-55a0-95b5-416987391a96 | note | Reference - 610.22
861cec3d-5370-5bf9-ab01-9a1ceae2cf4e | note | Acceptance Criteria - Maximum thermal differential between the core and exposed surface not to exceed 20°C.
8f1a87b9-fb70-5adc-8103-e15b975ea4a3 | note | ○ Only applicable if the element has:
110fed3e-d86b-5379-bcb2-cf74fb4ccc4f | note | i. The least dimension of a member exceeds 500 mm
ba94d19a-0270-5d0c-a036-9977cd5d6402 | note | ii. one or more faces being restrained by previously hardened concrete or other external constraints.
d6ecc212-4f38-545c-a480-9750db3c223c | note | ○ Attach: Thermal Monitoring Report
c935a497-6083-5a29-9009-c694ec7280d9 | note | Method - Document Review
6e43dad4-def7-5801-ba9d-c9a515a02fe2 | note | Frequency - Where applicable, each element
e4785036-85f5-51e2-901b-73f6d9c5bedd | note | Category - IP
379b451b-28ed-5400-ae17-ce9f461dbe6c | note | Responsibility - Foreman, SE/PE/SPE
9adf038d-1bcf-5eaf-ab30-3c6be359d6ca | note | Verifying Documents - This ITP
1f6ffe53-d8b2-51bf-b1ae-0970961d4a73 | date | Date Completed:
8eb1b793-82eb-4b10-8872-0d5dc0344101 | checkpoint | 6.2 - Early Age Compressive Strength Test Results - Removal of Formwork
bf942c90-85ad-52c1-a0e6-77f13c494dfa | note | Reference - IFC Drawings
6a7627da-6330-5582-ad97-709bcd242cb0 | note | Acceptance Criteria - Formwork shall be removed not earlier than 72 hours. Formwork shall not be removed when the ambient temprature is less than 10 degrees
bb46ff0a-98ba-58cb-8460-a26b7782d86a | note | ○ Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
27896ac9-b325-5f4d-89bd-c3de7a2ffb45 | note | Method - Document Review
ca75b619-025c-56aa-adec-243dbc5773a6 | note | Frequency - Where applicable, each element
5a343be3-5ed4-5a94-8d95-4a24eb12b296 | note | Category - IP
92c3c7a1-fba9-59e0-bed4-3a8c7772c3cc | note | Responsibility - Foreman, SE/PE/SPE
864304f8-e33b-5007-a47e-d86a8ef06a1b | note | Verifying Documents - This ITP
e2106798-764d-5be9-aa7f-5e77ab064f4f | date | Date Completed:
cd5294b1-379a-4c5a-81be-4efe63c68e1c | checkpoint | 6.3 - Surface Inspection - Cracks
6436ceb4-ce9f-5d4d-b385-996a5f66f653 | note | Reference - 610.24
70e495f6-ec2c-5fab-9906-8f705d539cc8 | note | Acceptance Criteria - No cracks greater than 0.2mm (exposure classification B1)
ba58fbd1-2348-5435-9083-3fe7036428fe | note | ○ If cracking is observed follow Structural Concrete Crack Repair ITP for investigation and repair.
4bdfc2b3-00a4-55bf-904e-3e441f8dbcc9 | note | Method - Visual, Measure
b9612208-dc6f-5b62-9432-561cf30e83ed | note | Frequency - Each element
ccc066f9-6cb2-5d15-8afa-5e950c616e1a | note | Category - IP
07ee9d3f-6ae0-5888-aba2-c5eece159b35 | note | Responsibility - SE/PE/SPE
aac0e94a-e027-5d7b-a01b-82f17b9dce75 | note | Verifying Documents - This ITP
6e794ce2-e62e-5c42-b566-74c9a22c53b5 | date | Date Completed:
27130e4c-a0e7-4f4a-a5bf-cb0d8711a57d | checkpoint | 6.4 - Surface Inspection - Surface Finish
de7095a7-f9cc-549f-942d-2d8c505b6d95 | note | Reference - IFC Drawings 610.31 (a) - (n), 610.32
21513f50-97de-558d-b181-b5715c2fc6c8 | note | Acceptance Criteria - Comply with the IFC drawings and specifications.
d4905604-65ce-5774-9536-c89f5decff73 | note | ○ Where surface finishes are non-conforming follow Structural Concrete Patch Repair ITP for investigation and repair.
3f79cf29-f845-5180-abb3-a7dc60584e14 | note | Method - Visual
a0d760c2-c7df-57f5-a416-0cb3fa5ed412 | note | Frequency - Each element
9dc976fa-f179-5724-9163-26d96e62f4cf | note | Category - IP
8d854176-9460-5ad5-8c1b-6ee3ecbd57b3 | note | Responsibility - SE/PE/SPE
cbced6ce-2658-5a4e-902d-bf102e664fd6 | note | Verifying Documents - This ITP
75fbc1da-5c96-5072-8c70-82916d7988ea | date | Date Completed:
f4ba03cb-653a-4b98-8fae-e3b087155112 | checkpoint | 6.5 - Measurement of Concrete Cover
bd0f313e-50c9-5bed-8c90-720eceb4c4d0 | note | Reference - 610.34
ac736c3b-2d01-57da-9103-77251891ff98 | note | Acceptance Criteria - Concrete covermeter check one 3m² test area for every 25m² exterior surface area.
f11183ce-bd62-5ed7-aee5-87b2f64c965a | note | ○ Minimum 10 no. measurements recorded in each area.
8428efb3-9e0a-5ee5-81c7-94ab878a943f | note | ○ Where low cover is identified, an assessment to evaluate the influence on durability of the structure is submitted to the Nominated Authority.
5c94bbef-bfe7-5707-b0bf-029857bbdbe5 | note | ○ Attach: Covermeter Check Record
fbc6a89a-1667-53d8-bef1-de9e4602b15b | note | Method - Measure
fba4ab78-4f10-5781-af1b-a12ad2113fdf | note | Frequency - Each element
1e4b724c-fd9c-5221-b2cd-243704739e2a | note | Category - IP
be40ee85-a9e7-5745-bab4-0128fabead86 | note | Responsibility - SE/PE/SPE
0ae8fa37-549b-5614-af3d-6e0b63caf00d | note | Verifying Documents - This ITP
14dfd775-dd3c-5513-8dcc-9400bd326c11 | date | Date Completed:
484bcae7-8406-4cdd-b481-58f1957d86f8 | checkpoint | 6.6 - Early Age Compressive Strength Results - Placement of Fill Against Concrete
c56526b1-ac0d-5d94-80c7-a8483adc06f0 | note | Reference - Early Loading and Trafficking of Decks and Approach Slab Procedure 610.35
c6c17da0-defb-52e5-a2a2-f4ad9469c0b7 | note | Acceptance Criteria - Fill is not placed against concrete within 14 days of pour.
dbd2ac8d-2ec9-5739-a8eb-d0d290875c43 | note | ○ Proposed placement of fill prior to 14 days - follow the Early Loading and Trafficking of Decks and Approach Slabs Procedure.
1fa033fe-c96d-553f-a40c-c80ef088b567 | note | ○ Attach: Concrete Test Results or Maturity Test Results
8d7e7a2f-dbcd-5e20-b45a-c3fd1d9b6a24 | note | Method - Document Review
938e403e-32f0-50e5-8366-1a2ed66a643e | note | Frequency - Where applicable, each substructure element
b2dba8b4-279a-5637-ad3f-6a0b9cfd5f79 | note | Category - SP
64fab92f-9ef1-5b76-b39c-9e2e3673b122 | note | Responsibility - Foreman, SE/PE/SPE
f7c68ba8-a580-510c-93c2-bed0d58f03cc | note | Verifying Documents - This ITP
1080d268-764c-5856-aa77-e3cf2f16fac6 | date | Date Completed:
ee00de4a-a7d2-47ac-a7f6-704a0a12e7ae | checkpoint | 6.7 - Compressive Strength Test Results
9a015ea5-4c65-57b1-bb4d-4aa5112991f2 | note | Reference - IFC Drawings Table 610.05.051, 610.16 (g)
b1392925-8f71-5b3c-ab5b-67b8d25c2033 | note | Acceptance Criteria - 7 day compressive strength to comply with table 610.051 for early indication that the strength is tracking correctly.
212059b3-50b0-5f0a-b135-39bca5c5b2eb | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength.
348a5810-e1ac-5183-b94f-09021e1f2a8f | note | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
363a42b8-82f3-5f7e-b42a-bf40b12aed02 | note | ○ Attach: Compressive Strength Test Results
950c89d5-fb59-573e-8f8a-bf9ba68ac90a | note | Method - Document Review
a676da46-0bfe-5473-a52b-c5bf4309bb00 | note | Frequency - Each cylinder
6957fae1-513d-52e7-bf44-2408194ddc0d | note | Category - IP
34198180-3a52-5e6f-9127-bdeb10d18065 | note | Responsibility - SE/PE/SPE
c94f5dc2-bdfc-538f-81de-1905b9eaf020 | note | Verifying Documents - This ITP
f9fd9d35-e856-59c8-9178-0322bc00dbbb | date | Date Completed:
73700eca-1222-4087-b080-73379724a218 | checkpoint | 6.8 - As-built Survey
b65bc36c-f1fa-5f60-b6c2-1cdeddd660ba | note | Reference - IFC Drawings 610.47, Table 610.472
fd8aa517-4a88-56d8-a895-7b6bda7e1007 | note | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.462 as applicable to the element.
600fe458-98fc-5437-9369-c4a6c43393b2 | note | ○ Attach: Survey As-builts / Survey Report
792cec96-c2f6-5e77-825d-598a2a904dc9 | note | Method - Document Review
e94fe6b6-6556-5718-9b03-c90b1446bad1 | note | Frequency - Each element
a27d0a20-d285-5257-bfeb-9cbe86755bf9 | note | Category - IP
da7d1cab-98df-5f9b-839d-e8302b2b6d6a | note | Responsibility - Surveyor, SE/PE/SPE
ba0f75b2-60fe-5676-bce2-d6848b03ef03 | note | Verifying Documents - This ITP
cc63ef5c-3c49-5505-a867-55fc33496cdf | date | Date Completed:
cbe05295-b52b-4f08-8e4f-0db5deb03a24 | checkpoint | 6.9 - Non-conformance Report (NCR) Closure
d4001a66-9761-50f2-9e9d-2a801417cc36 | note | Reference - MRPA Quality Management Plan
cb2554bf-ce0b-514c-9cc3-29f82261b12c | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
3802f1b1-0998-597a-875f-dfb22d368217 | note | Method - Document Review
7343dd6f-2f78-57f4-90ab-c3f138f9d50c | note | Frequency - Once, prior to closure of this lot / element / Work area
c7893321-9d06-54c8-9221-2cbc7934ebcf | note | Category - HP*
38170445-fa83-50ba-94f1-3bcec1a63b51 | note | Responsibility - SE/PE/SPE
82afbb0d-c093-5cfa-8596-a2a82bdb13ae | note | Verifying Documents - This ITP
9907b804-1c3e-5a52-922c-ffc521d55c16 | date | Date Completed:
150f2c32-8a9a-4865-867a-ab65751f3950 | checkpoint | Final Inspection
9420fd19-f0d1-5bc4-9c7f-e2f9e62ad819 | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed above have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
16b1dc38-fdbe-5227-98b8-2a389007fbeb | textbox | Name:
f6767b5d-fe83-5fa7-828a-3a9783f5cb0f | textbox | Position:
430574b9-b102-5e51-a485-a733bc26786d | textbox | Date Completed:
bad27300-ffd2-408e-be8d-512b23d31275 | signoff | Sign ITP