## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-309-STR-FRMS-Steel Structures Installation | itp |  |  |  |  | ITP-309-STR-FRMS-Steel Structures Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-309-STR-FRMS-Steel Structures Installation
label | ITP Description: Steel Structures Installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 3/09/2025
label | ITP created by: Jaidyn Kempster
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VR Section 610 Feburary 2020
label | ○ VR Section 630 January 2022
label | ○ VR Section 631 June 2017
label | ○ IFC Drawings AS 1252.1, AS 1110.1 , AS 1110.2, AS 1112.1, AS 4100, AS/NZS 5131
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Steel Material Compliance
label | Reference - Section 630.071 IFC Drawing
label | Acceptance Criteria - Steel should demonstrating compliance to the relevant steel product standards listed in Table 630.071, including all impact test values when appropriate.
label | ○ The test certificates shall be related to the steel by trademarks and heat number.
label | ○ Collate: Steel manufacturer’s Certificate of Product Compliance and all related test certificates and upload in a TeamBinder Lot
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Fasteners
label | Reference - Section 630.21 IFC Drawing
label | ○ AS 1252.1
label | ○ AS 1110.1
label | ○ AS 1110.2
label | ○ AS 1112.1
label | Acceptance Criteria - Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1252.1, AS 1110.1, AS 1110.2 and AS 1112.1
label | ○ Collate: Bolt manufacturer's Certificate of Product Comliance and related documentation and upload in a TeamBinder Lot.
textbox | Enter: Teambinder Material Approval number
label | Method - Document review
label | Frequency - Each component
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Base Plate Structural Grout or Mortar
label | Reference - IFC Drawings Section 610.33
label | Acceptance Criteria - Product to be selected based on the following criteria:
label | i. Shall be self shrinkage compensating proprietary products with a consistancy appropriate for required use as per 610.33
label | ii. Must have a minimum of 28 days compressive strength, of not less than 50MPa as per IFC drawings.
label | iii. Cementeous grouts shall be as a minimum Type C Class dual shrinkage compensating as per 610.33
label | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings
label | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Surface Finishes
label | Reference - IFC Drawings Section 631.05
label | Acceptance Criteria - At least 14 days prior to commencing the protective treatment of steelwork, the Contractor shall submit to the Superintendent for review the information outline in section 631.05, for all proposed coating system
label | (a) coating system, including hot-dip galvanizing if specified on the drawings. If hot-dip galvanizing is the only coating required, no further information is required to be submitted;
label | (b) type of coatings;
label | (c) name of paint manufacturer;
label | (d) product names of paints;
label | (e) technical data sheets and Material Safety Data Sheets (MSDS) for all paints;
label | (f) documentary evidence from the manufacturer certifying compliance of paints with relevant specifications;
label | (g) details of work to be carried out by shop treatment and those to be carried out by field treatment;
label | (h) for field works, details of work methods, containment processes and environment controls;
label | (i) details of solvent cleaning solution and soluble salt removal procedures;
label | (j) abrasive to be used for abrasive blast cleaning;
label | (k) analysis certificate for non-metallic abrasives; and
label | (l) paint application conditions, including but not limited to -
label | — (i) the maximum and minimum ambient temperature,
label | — (ii) the maximum and minimum temperature of surfaces to be painted,
label | — (iii) maximum and minimum (if applicable) relative humidity,
label | — (iv) minimum difference between temperature of surface to be painted and the dew point, and
label | — (v) minimum and/or maximum time between application of successive coats.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product, prior to placement of product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Procedures
checkpoint | 3.1 - Fabrication and welding
label | Reference - Section 630.03 AS/NZS 5131
label | Acceptance Criteria - The fabrication and welding procedures, and ITPs shall be submitted to the Superintendent one month prior to fabrication.
label | ○ Attach: Subcontractor Fabrication and welding ITP and Procedures
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 1 month prior to installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Weld Repairing of Steel
label | Reference - Section 630.07
label | Acceptance Criteria - The use of any weld repaired steel, including welding to make up member length, shall not commence until approval to proceed is given by the Superintendent.
label | Method - Verbal
label | Frequency - Prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Non-Destructive and Dimesion Inspections
label | Reference - Section 630.18
label | Acceptance Criteria - The subcontractor shall submit test certificates for all non-destructive inspections and dimension inspections to the Superintendent for review at least two days prior to the steelwork being transported for protective treatment.
label | ○ Attach: Subcontractor test certificates for all non-destructive and dimesion inspection.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 2 days prior to protective treatment
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Handling, Transport and Erection of Structural Steel Element
label | Reference - Section 630.09 AS/NZS 5131
label | Acceptance Criteria - Methods of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | ○ An installation methodology and ITP in accordance with AS 5131 shall be submitted one (1) month prior to installation. As a minimum, the installation methodology shall include the following procedures below, when appropriate:
label | (a) Lifting procedures for each component; transport to and handling on site
label | (b) Bolt tightening procedures for snug tight bolting
label | (c) Procedures for grouting of base plates
label | (d) Procedures for ensuring that components are erected in the correct sequence and position.
label | ○ Attach: Subcontractor Installation ITP and Procedures
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 1 month prior to installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Preliminaries - Fabrication Documentation
checkpoint | 4.1 - Steel Fabrication Certification
label | Reference - Section 630.03 AS/NZS 5131
label | Acceptance Criteria - Details of the steel fabrication, including the appropriate certifications and any arrangements where the fabrication of steelwork is further subcontracted to a third party certified fabricator, must be submitted to the superintendant, at least 14 days prior to commencement of fabrication of steelwork.
label | ○ The Contractor shall submit evidence of certification of the steel fabricator to:
label | (a) Construction Category CC2, CC3 or CC4 of AS/NZS 5131, as applicable to the works or to parts of the works, and
label | (b) AS/NZS ISO 3834.2 for work requiring Construction Category CC3 or CC4; or to AS/NZS ISO 3834.3 for work requiring Construction Category CC2.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 14 Days prior to fabrication
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Shop Drawing Verification
label | Reference - Section 630.04
label | Acceptance Criteria - Prior to fabrication, the shop drawings shall be reviewed by a competent Structural Steel Designer to verify that the critical to quality requirements are complied with and that the design intent is achieved. Evidence of this review and the competency of the reviewer shall be submitted to the Superintendent prior to fabrication.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - Prior to fabrication
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Cambering, Straightening and Forms
label | Reference - Section 630.11
label | Acceptance Criteria - The work instruction for cambering, straightening or forming, as appropriate shall be submitted to the Superintendent for review at least seven working days prior to commencement of these activities.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 7 working days prior to activity
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Welding Procedure Qualification
label | Reference - Section 630.14 AS 2205.5.1
label | Acceptance Criteria - Documentary evidence of the results of welding procedure testing, assessment against the acceptance criteria, and an approved Welding Procedure Specification (WPS and PQR) for each of the weld procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding.
label | ○ A photograph of the etched surface of all weld macro-tests, to AS 2205.5.1, at a magnification of x1, or greater, shall be submitted to the Superintendent with the test results.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 5 days prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Welding Operator Qualification
label | Reference - Section 630.15
label | Acceptance Criteria - Documentary evidence of welding operator qualification through testing or assessment for each of the welding procedures to be used in the welding of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of welding.
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 5 days prior to welding
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Steel Fastening Procedure
label | Reference - Section 630.20, Section 630.21 AS/NZS 5131
label | Acceptance Criteria - The Contractor shall submit to the Superintendent the bolt manufacturer’s Certificate of Product Compliance and all related test certificates demonstrating compliance of the supplied bolt assemblies to the relevant bolt product standards: AS/NZS 1252.1, AS 1110.1, AS 1110.2 and AS 1112.1, as appropriate , and including assembly testing to AS/NZS 1252.1 when appropriate.
label | ○ The test certificates shall be related to the bolts by manufacturer or supplier, batch and heat number, and manufacturing lot number.
label | ○ A documented work method statement (WMS) shall be prepared for each bolting operation. The bolting WMS shall include:
label | i. The fastener requirements
label | ii. The results of slip factor testing for high friction joints
label | iii. A snug-tightening sequence
label | iv. A high-friction tensioning sequence when appropriate
label | v. Processes for assessment against the acceptance criteria
label | vi. When appropriate, the specific requirements for use of direct tension.
label | ○ The bolting WMS for each of the procedures to be used in the bolting of the steelwork shall be submitted to the Superintendent for review at least five working days prior to commencement of bolting.
label | ○ Approval to use direct-tension indicator devices shall be obtained from the Superintendent at least 14 days prior to the use of such devices on bolting on the steelwork, and shall be used in accordance to manufacturer's instructions and AS/NZS5131
textbox | Enter: Teambinder Approval number
label | Method - Document Review
label | Frequency - 14 days prior to fastening
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5. Installation Activities
checkpoint | 5.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 - Materials Inspection Checklist - Steel
label | Reference - IFC Drawings Section 630
label | Acceptance Criteria - General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 - Materials Inspection Checklist - Fasteners
label | Reference - IFC Drawings Section 630
label | Acceptance Criteria - Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.4 - Materials Inspection Checklist - Galvanising
label | Reference - IFC Drawings Section 631
label | Acceptance Criteria - Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 - Materials Inspection Checklist - Surface Finish
label | Reference - IFC Drawings Section 631
label | Acceptance Criteria - Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 - Servey Set-out
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements as per IFC drawings.
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - Surveyor, SE/PE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.1 - Bearing / Mounting Surface Preparation
label | Reference - IFC Drawings Section 630.21c, Product TDS
label | Acceptance Criteria - Ensure the bearing surface is clean and free from all oil, dirt, loose scale, loose rust, burrs, fins and any other defects on the surfaces of contact, that will prevent solid seating of the parts in the snug-tight condition.
label | ○ For a friction-type connection, the surfaces shall be clean as-rolled surfaces or equivalent and shall be free from plant, lacquer, glavanizing or other applied finish, unless the applied finish has been tested to establish the riction coefficient or slip factor.
label | Method - Measure, Visual
label | Frequency - Where applicable, each installation location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.2 - Structural Steel Handling
label | Reference - Section 630.09, Section 631.14 AS/NZS 5131
label | Acceptance Criteria - The method of handling, transporting and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | ○ All installation and erection of steel structures shall comply with the requirements of AS/NZS 5131.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 - Structural Steel Erection
label | Reference - AS4100, AS/NZS 5131 Section 630.12
label | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
label | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.4 - Fastener Tightening - Snug Tight Condition
label | Reference - IFC Drawings Section 630.09, Section 630.21 AS/NZS 5131
label | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | ○ For posts base plates, the arrangement is to be (from the base plate):
label | — Base Plate
label | — Washer as specified
label | — Lock Nut as specified
label | — Nut
label | — Bolt protrusion (1 clear tread)
label | ○ Washers shall cover the hole or slotted hole completely by 0.5 x holes diameter.
label | ○ Tapered washers shall be positioned as specified.
label | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | Method - Measure, Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 - Survey Conformance
label | Reference - IFC Drawings AS4100, AS/NZS 5131
label | Acceptance Criteria - Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = -15 mm, +5 mm
label | ○ Departure from plan position = ±6mm
label | ○ Departure from bolt group spacing = ±6mm
label | ○ Bolt group spacings <= 25mm in 30m
label | ○ Projection of bolt = +25mm, -5mm
label | ○ Location of column = ±7mm
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - HP*
label | Responsibility - SE/PE/SPE, Surveyor
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.6 - Base Plate Formwork Construction & Placement
label | Reference - IFC Drawings
label | Acceptance Criteria - Dimensions as per drawings to achieve the profile. Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | Method - Measure, Visual
label | Frequency - Each post location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.7 - Pre-soaking Concrete Surface for Grout
label | Reference - Product TDS
label | Acceptance Criteria - Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | Method - Visual
label | Frequency - Each post location
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.8 - Weather Conditions
label | Reference - Section 610.17, VR Table 610.171
label | Acceptance Criteria - Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Record: Required information on the Grout Pour Record.3
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.9 - Mixing Product
label | Reference - Product TDS Section 610.28
label | Acceptance Criteria - Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
textbox | Enter: Required information on the Grout Pour Record.
label | Method - Measure, Visual
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.10 - Product Testing - Compressive Strength Cubes
label | Reference - Section 610.28 IFC Drawings
label | Acceptance Criteria - Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | ○ Testing is to be in accordance with the following frequencies:
label | — First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | — Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
textbox | Enter: Required information on the Grout Pour Record.
label | Method - Test
label | Frequency - Each lot
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.11 - Placement & Compaction
label | Reference - Product TDS
label | Acceptance Criteria - All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
textbox | Enter: Required information on the Grout Pour Record
label | Method - Visual
label | Frequency - Each post location
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.12 - Surface Finishes & Protection of Works
label | Reference - IFC Drawings Section 610.17
label | Acceptance Criteria - If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | Method - Visual
label | Frequency - Where applicable, each post location
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.13 - Curing
label | Reference - Curing Methodology 610.23 Table 610.231
label | Acceptance Criteria - Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | Method - Visual
label | Frequency - Where applicable, each post location
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.14 - Architectural Steel Erection
label | Reference - AS4100 Clause 15.2.3, AS/NZS 5131 Clause 11.5.7, 630.12
label | Acceptance Criteria - Place steel component into position, ensuring that it is plumb, level and square
label | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
label | Method - Measure, Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.15 - Architectural Steel Erection-Fasteners
label | Reference - IFC Drawings Section VR 630
label | Acceptance Criteria - Place bolts, washers and nuts as detailed on the IFC Drawings.
label | ○ For architectural/Security screens, the arrangement is to be (from themounting post):
label | — Post
label | — Washer (s) as specified
label | — insulating washer
label | — insulating bush
label | — Insulating washer
label | — washer as specified
label | — Lock nut
label | — Nut
label | — Bolt protrusion (1 clear tread)
label | Method - Measure, Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 5.16 - Installation of Electrical Isolation Materials
label | Reference - IFC Drawings
label | Acceptance Criteria - Installation of Electrical Isolation Material in locations specified on the IFC drawings (where applicable).
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
section | 6. Post-installation Activities
checkpoint | 6.1 - Inspection of Coating
label | Reference - IFC Drawings Section 630
label | Acceptance Criteria - After installation Works are complete, inspect the steel element for damage to the coatings.
label | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | Method - Visual
label | Frequency - Each component
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | Structural Steel Components
label | Reference - IFC Drawings, MRPA Quality Management Plan Section 630.22
label | Acceptance Criteria - Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | ○ Typically this consists of but not limited to:
label | i. Certificate of Compliance
label | ii. Completed Fabrication ITP
label | iii. Weld Procedure Specifications
label | iv. Weld Procedure Qualifications
label | v. Welder Qualifications
label | vi. Material Certificates and traceability
label | vii. Quality Assurance check sheets
label | viii. Welding Consumable batch certificates
label | ix. Coating certificate(s)
label | x. Non-destructive Testing (NDT) Reports
label | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | ○ Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each component
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Conqa HP Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Compressive Strength Test Results
label | Reference - IFC Drawings, Product TDS Section 610
label | Acceptance Criteria - 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | ○ Attach: Compressive Strength Test Results
label | Method - Document Review
label | Frequency - Each Sample
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.3 - As-built Survey
label | Reference - IFC Drawings AS/NZS 5131
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | ○ Departure from RL = ±10mm
label | ○ Departure from plan position = ±6mm
label | ○ Departure from alignment = ±6mm
label | ○ Irregularities in alignment = 25mm in 30m
label | ○ Projection of bolt = +25mm, 5mm
label | ○ Location of beam = ±3mm
label | ○ Location of column = height/500, 10mm max.
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 6.4 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP