## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-297-STR-FRMS-Precast Barriers and Kerbs Installation | itp |  |  |  |  | ITP-297-STR-FRMS-Precast Barriers and Kerbs Installation Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-297-STR-FRMS-Precast Barrier and Kerbs Installation
label | ITP Description: FRMS-Precast Barrier and Kerbs Installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 3/09/2025
label | ITP created by: Jaidyn Kempster
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 610 Feb 2020
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 620 May 2009
label | 1.3 - Non Dependent
label | Reference - VicRoads Section 630 October 2013
label | 1.4 - Non Dependent
label | Reference - VicRoads Section 670 October 2013
label | 1.5 - Non Dependent
label | Reference - VicRoads Section 671 October 2013
label | 1.6 - Non Dependent
label | Reference - MRP-AURE-TRANS-004790-MRP-DPK-103-00-CBR-0030
label | 1.7 - Non Dependent
label | Reference - MRP-AURE-TRANS-004818-MRP-DPK-103-00-CSF-0032
label | 1.8 - Non Dependent
label | Reference - SD3901
section | 2. Preliminaries - Materials
checkpoint | 2.1 - Grout
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Details of the grout to be placed between adjacent barriers and lifting lug/anchor recess to be submitted for review to the Nominated Authority.
label | ○ Grout shall be non shrink and shall have a 28 day characteristic strength of 50MPa UNO. Grout shall acheive a minimun 80% of the 28 days strength prior to loading.
label | ○ Lifting lug/anchor recess to be filled with 40MPa minimum strength grout or approved equivalent
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each product
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Preliminaries - Documents
checkpoint | 3.1 - IFC Drawings
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | Method - Document Review
label | Frequency - Prior to starting Works and at regular intervals
label | Category - HP*
label | Responsibility - All
label | Verifying Documents - This ITP Signed Off
date | Date Completed:
checkpoint | 3.2 - Precast Elements
label | Reference - IFC Drawings VR 610
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Post-pour check sheet / ITP
label | vi. Covermeter check record
label | vii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast
label | ○ These documents are typically stored in a MDR Lot in Team Binder.
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Bridge Deck / Foundation Compressive Strength
label | Reference - 671.03, 610.32
label | Acceptance Criteria - For Precast elements installed on bridge deck, check that the 7 day compressive strength as shown on the IFC Drawings has been achieved.
label | ○ Further to the requirements of clause 610.16 and clause 610.23, bridge decks, deck overlays and approach slabs shall not be loaded or opened to traffic until the concrete is at least 4 days (96 hours) old and not before a minimum compressive strength of 32 MPa after casting has been achieved.
label | Method - Document Review
label | Frequency - Each installation location
label | Category - HP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-installation Activities
checkpoint | 4.1 - Survey Set-out of Precast Elements
label | Reference - IFC Drawings
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances.
label | ○ Where anchor bolts are cast in to the concrete, ensure that these are within tolerance.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Installation Activities
checkpoint | 5.1 - Precast Handling
label | Reference - 620.07 Crane Lift Study
label | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Precast Placement
label | Reference - IFC Drawings VR 671.06
label | Acceptance Criteria - Precast elements shall be placed onto the hold-down bolt locations and not released from the crane until sufficiently braced or restrained by bolted connection, in accordance with the approved temporary works design and/or IFC drawings.
label | Adjustments to be made to achieve following tolerances:
label | ○ VR 670.05, for all medium performance barriers
label | (a) Departure from plan position: ±25 mm
label | (b) Departure from alignment: ±5 mm
label | (c) Irregularities in alignment: ±3 mm in 3 m
label | (d) Variation in joint gap width: ±3 mm
label | (e) Concrete cover: 0 to +5mm
label | ○ SD3902, for all TL rated barriers
label | (a) Departure from plan position: ±20 mm
label | (b) Departure from alignment: ±20 mm
label | (c) Seperation between barriers: 10mm ±5mm
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Hold-down Bracket Fastener Tightening - Snug Tight Condition (4.6/S & 8.8/S)
label | Reference - IFC Drawings 630.21 (a) & (b), AS5131 Clause 8.3
label | Acceptance Criteria - Place washers and nuts onto the embedded thread as detailed on the IFC Drawings.
label | ○ Tapered washers shall be positioned if the surfaces are on a slope of 1:20 or greater.
label | ○ Tighten with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | ○ Note the drawings only show 1 nut, however but will need a lock nut also to conform to standard
label | Method - Visual
label | Frequency - Where applicable, each bolted connection
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Precast Traceability
label | Reference - 620.09
label | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | ○ Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 6. Post-installation Activities
checkpoint | 6.1 - Flowable Grout Pour
label | Reference - IFC Drawings
label | Acceptance Criteria - Grout shall be poured at connections between adjacent barriers and in the gap between the precast element and top of the bridge deck, at a height of 100mm.
label | ○ Lifting lug/anchor recess to be filled with 40MPa minimum strength grout or approved equivalent.
label | ○ Complete: Grout Pedestals & Bearings ITP
label | Method - Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Grout Pedestals & Bearings ITP
date | Date Completed:
checkpoint | 6.2 - As-built Survey
label | Reference - IFC Drawings VR 671.06, SD3902
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per:
label | ○ VR 670.05, for all medium performance barriers
label | (a) Departure from plan position: ±25 mm
label | (b) Departure from alignment: ±5 mm
label | (c) Irregularities in alignment: ±3 mm in 3 m
label | (d) Variation in joint gap width: ±3 mm
label | (e) Concrete cover: 0 to +5mm
label | ○ SD3902, for all TL rated barriers
label | (a) Departure from plan position: ±20 mm
label | (b) Departure from alignment: ±20 mm
label | (c) Seperation between barriers: 10mm ±5mm
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-310-STR-FRMS-Painting | itp |  |  |  |  | ITP-310-STR-FRMS-Painting Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-297-STR-FRMS-Precast Barrier and Kerbs Installation
label | ITP Description: FRMS-Precast Barrier and Kerbs Installation
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 0
label | Revision Date: 3/09/2025
label | ITP created by: Jaidyn Kempster
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Standard Section 685
label | 1.2 - Non Dependent
label | Reference - VicRoads Standard Section 686
label | 1.3 - Non Dependent
label | Reference - IFC Drawings
section | 2. Preliminaries
checkpoint | 2.1 - Anti-graffiti System Selection
label | Reference - IFC Drawings, Coating System TDS
label | ○ VicRoads:
label | — Section 685.04
label | — Section 685.06 (a)(b)
label | — Section 686.04
label | — Section 686.05 (a)(e)
label | Acceptance Criteria - The system shall be selected based on the following criteria:
label | i. be either a film-forming or a penetrant system
label | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | vi. application thicknesses (film-forming): WFT total = 175µm min. DFT total = 100µm min. when anti-graffiti coating is also used as anti-carbonation, then DFT total = 150µm min.
label | vii. adhesion to substrate (film-forming): 0.75MPa min.
label | viii. application rate (penetrants) as per the minimum thickness on the manufacturer's TDS
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Once, for each coating system, 14 days prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Decorative & Anti-carbonation System Selection
label | Reference - IFC Drawings, Coating System TDS
label | ○ VicRoads:
label | — Section 686.04
label | — Section 686.05 (a)(b)
label | — Table 686.051
label | Acceptance Criteria - The system shall be selected based on the following criteria:
label | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to last for 10 years of outdoor exposure
label | vi. application thicknesses: WFT per coat = enough to achieve the total DFT = 150µm min.
label | vii. adhesion to substrate: 0.75MPa min.
label | viii. able to bridge cracks up to 0.3mm wide
label | ix. able to be re-coated within 24 hours
label | x. have a minimum pot life of 1 hour
label | xi. compatibility to an alkaline surface
label | xii. equivalent air thickness >150m, equivalent concrete thickness >450mm, CO2 diffusion coefficient <2 x 10^-7 cm2/s, Water vapour equivalent air layer <4m
textbox | Enter: TeamBinder Material approval No.
label | Method - Document Review
label | Frequency - Once, for each coating system, 21 days prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Quality Documentation
label | Reference - IFC Drawings, Coating System TDS, Cleaning System TDS
label | ○ VicRoads:
label | — Section 685
label | — Section 686
label | Acceptance Criteria - The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
textbox | Enter: TeamBinder Hold Point Approval No.
label | Method - Document Review
label | Frequency - Once for each coating system
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Personnel & Equipment
label | Reference - IFC Drawings
label | ○ VicRoads:
label | — Section 685.16
label | — Section 686.19
label | Acceptance Criteria - Application personnel and sub-contractors shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques for anti-graffiti coating. For all other coating, Application personnel shall have a minimum of 2 years experience. The supervisor shall have a minimum of 5 years experience and must remain present at all times. Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | Method - Document Review
label | Frequency - Once, prior to application
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.5 - Protection of Adjacent Works & property
label | Reference - VicRoads:
label | — Section 685.17
label | — Section 686.10
label | Acceptance Criteria - Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes. No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place. Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | Method - Visual and Document Review
label | Frequency - Where applicable, 2 days prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Minimum Concrete Curing Period
label | Reference - VicRoads:
label | — Section 685.08
label | — Section 686.16
label | Acceptance Criteria - Concrete shall not be coated until the minimum concrete curing times have elapsed: Standard cured concrete = 28 days, Accelerated cured concrete = 14 days, Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | ○ Note: All durations may be reduced by 50% if the moisture content is less than 10% when measured with a calibrated moisture meter.
label | Method - Visual and Document Review
label | Frequency - Once, prior to application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Trial Application Inspection
label | Reference - VicRoads:
label | — Section 685.11
label | — Section 686.13
label | Acceptance Criteria - A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate, 14 days prior to the commencement of coating work. Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
textbox | Enter: TeamBinder Hold Point Approval No.
label | Method - Visual and Document Review
label | Frequency - Once for each coating system, 14 days prior to full coating application
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3. Pre-Application Activities
checkpoint | 3.1 - Material Records
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.10
label | — Section 686.12
label | Acceptance Criteria - Materials shall be brought to site in unopened, sealed containers, clearly marked with: the manufacturer's name & address product reference batch number quantity manufactured in the batch date of manufacture
label | ○ Product beyond the manufacturer's shelf life shall not be used. Each product shall be traceable to final location.
label | Method - Visual
label | Frequency - Prior to application
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Weather Conditions
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.09
label | — Section 685.12 (a)
label | — Section 686.11
label | — Section 686.14 (a)(iii)
label | Acceptance Criteria - Coating systems shall not be applied under any of the following conditions:
label | i. windy conditions where spray/splatter may be generated
label | ii. when wind-borne debris is likely to contaminate the uncured surface
label | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | ○ Weather conditions are to be recorded.
label | Method - Visual and Measure
label | Frequency - Prior to application and every 4 hours each shift
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - Surface Preparation
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.05
label | — Section 686.06
label | Acceptance Criteria - The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means. The surface shall then be flushed with water. Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | Method - Visual
label | Frequency - Once, prior to application
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.4 - Surface Moisture Testing
label | Reference - VicRoads:
label | — Section 685.12 (a)
label | — Section 686.14 (a)(iii)
label | Acceptance Criteria - The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS. Surface moisture conditions are to be recorded.
label | Method - Test
label | Frequency - Prior to application, test 1m2
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Application Activities
checkpoint | 4.1 - Method of Application
label | Reference - Coating System TDS, Surface Cleaner TDS
label | ○ VicRoads:
label | — Section 685.07
label | — Section 686.07
label | — Section 686.09
label | Acceptance Criteria - Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved. Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified. For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application. Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | Method - Visual and Measure
label | Frequency - Each coat
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Wet Film Thickness Testing
label | Reference - Coating System TDS
label | ○ VicRoads:
label | — Section 685.12 (b)(ii)
label | — Section 686.14 (b)(ii)
label | Acceptance Criteria - Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | ○ Attach: WFT Test Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Inspection & Defect Identification
label | Reference - VicRoads:
label | — Section 685.07
label | — Section 685.13 (d)
label | — Section 686.07
label | — Section 686.15
label | Acceptance Criteria - The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats. Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | Method - Visual
label | Frequency - After each coat
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.4 - Drying & Curing
label | Reference - Coating System TDS
label | ○ VicRoads:
label | — Section 685.17
label | — Section 686.09
label | Acceptance Criteria - Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | Method - Visual
label | Frequency - After each coat
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-application Activities
checkpoint | 5.1 - Clean-up & Waste Disposal
label | Reference - VicRoads:
label | — Section 685.07 (c)
label | — Section 686.10
label | Acceptance Criteria - All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated. All rubbish and remaining coating products shall be removed from site.
label | Method - Visual
label | Frequency - At completion of works
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.2 - Dry-Film Thickness Testing
label | Reference - VicRoads:
label | — Section 685.12 (b)(iii)
label | — Section 686.14 (b)(iii)
label | Acceptance Criteria - The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
label | i. Anti-graffiti system = 100µm
label | ii. Decorative & anti-carbonation = 150µm
label | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
label | iv. Atmospheric & splash zone (dual protective) = 200µm
label | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
label | ○ Attach: DFT Test Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.3 - Adhesion Bond Strength Testing
label | Reference - VicRoads:
label | — Section 685.12 (b)(i)
label | — Section 686.14 (b)(i)
label | Acceptance Criteria - A minimum of 14 days after application, the bond-strengths between: i. the coating system to the substrate, and ii. Separate coating layers shall be tested using 50mmØ aluminium dollies. The subsequent results shall be greater than 0.75MPa.
label | ○ Attach: Adhesive Bond Strength Testing Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Penetration Depth Testing
label | Reference - VicRoads:
label | — Section 685.12 (b)(v)
label | — Section 686.14 (b)(v)
label | Acceptance Criteria - Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration. The subsequent results shall be:
label | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
label | ii. Silane, Solid Silane or Silane Cream = 5mm min.
label | iii. Silane-Siloxane or Siloxane = 3mm min.
label | ○ Attach: Penetration Depth Testing Results
label | Method - Test
label | Frequency - Where applicable, 3 no. tests every 50m2 or part thereof
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Non-conforming Coatings
label | Reference - VicRoads:
label | — Section 685.14
label | — Section 686.17
label | Acceptance Criteria - Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired. Such Work may include removal of the coating, surface preparation and re-application. Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | Method - Visual
label | Frequency - Where required
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.6 - Coating Application Guarantee
label | Reference - VicRoads:
label | — Section 685.06 (b)
label | — Section 686.05 (a)
label | Acceptance Criteria - Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | ○ Attach: Coating Application Guarantee
label | Method - Document Review
label | Frequency - At completion of works
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Repair to Damaged Coating
label | Reference - VicRoads:
label | — Section 686.17
label | Acceptance Criteria - Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | Method - Visual
label | Frequency - Where required
label | Category - IP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.8 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot
label | Category - HP
label | Responsibility - SE/PE/Site Supervisor
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP