## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-291STR-HOP-Precast Bridge Beams (Supply & Installation)
ITP Description: |  | HOP-Precast Bridge Beams (Supply & Installation)
Document Number (in Teambinder): |  | 291
Discipline (e.g. CIV/STR/RAIL: |  | STR
Revision Number: |  | 2
Revision Date: |  | 2025-08-05
ITP created by: |  | Manwel Kalyana
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Hopkins Only
Inspection & Test Plan - Precast Bridge Beams (Supply & Installation)
|  |  | Document No.: | 291 |  |  |  |  | Revision: | 2
Date:
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 169 July 1993 VicRoads Section 610 Feb 2020 VicRoads Section 613 June 2017 VicRoads Section 620 May 2009 VicRoads Section 622 November 2018 VicRoads Section 630 Jan 2023 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries
2.1 | Precast Elements | IFC Drawings 610.46 (a), Table 610.463 (November 2018) 610.47 (a) Table 610.473 (Feb 2020) 620.03 | Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of: i. Certificate of Compliance / Birth Certificate ii. Compressive strength test results iii. Precast Lifting Design iv. Pre-pour check sheet / ITP v. Pre-stressing check sheet / ITP vi. Post-pour check sheet / ITP vii. Covermeter check record viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.463 (November 2018) / 610.473 (March/June 2019). Note: Different revisions of 610 have different clause numbers Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here) | Document Review | Each element | IP | PE/SE/SPE | This ITP
2 | Preliminaries (Continued)
2.2 | Temporary Works Designs | 610.27 613.04 613.05 613.16 | All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design. Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority. Attach: Temporary Works Design Attach: Attachment A Attach: Attachment B | Document Review | Where applicable, once, 5 days prior to installation | HP | Nominated Authority | ConQA Hold Point Release
2.3 | Crosshead / Pedestal Tolerances | Survey As-builts / Survey Report 610.472 (x) | Re-check that the As-built dimensional tolerances comply with the requirements below: Reduced level ±2.5mm Variation from grade across the width of individual pedestals shall not exceed 1 in 200 Deviation from flat surface ±1mm | Document Review | Each element | IP | PE/SE/SPE | This ITP
2.4 | Crosshead / Pedestal Compressive Strength | IFC Drawings Compressive Strength Results | Re-check that the minimum required compressive strength as shown on the IFC Drawings has been achieved. | Document Review | Each element | IP | SE/PE/SPE | This ITP
3 | Pre-installation Activities
3.1 | Survey Set-out of Precast Elements | IFC Drawings Table 610.473 (Feb 2020) | Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (Feb 2020) as applicable to the element. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
3.2 | Elastomeric Bearings | IFC Drawings | Where applicable. Complete: Elastomeric Bearings (Supply & Installation) ITP before proceeding with this ITP. | Document Review Visual | Where applicable | IP | SE/PE/SPE | This ITP
3.3 | HDPE Bearing Shim Placement (for integrally cast beams) | IFC Drawings | Place the bearing shims (or variety of shims) to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances. Note: The minimum and maximum thicknesses of the HDPE bearing shims as this will determine the product for the grouting activities. | Measure Visual | Where applicable, each bearing location | IP | Surveyor SE/PE/SPE | This ITP
3.4 | Materials Inspection Checklist | 620.06 620.07 MRPA Quality Management Plan | General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings. Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to). Elements shall have unique identification and orientation marked (if applicable). Complete: Materials Inspection Checklist in ConQA | Measure Visual | Each element | IP | SE/PE/SPE | This ITP
3.5 | Tapper Plates | 630 IFC | The method of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations. All installation and erection of the steel structure shall comply with the requirements of AS/NZS 5131. Ensuring that the orientation of the installed base plates on the beams complies with AS/NZS 5131 and VR630. | Document Review | Each Plate | HP* | SE/PE | This ITP
4 | Installation Activities
4.1 | Precast Handling | 620.07 Crane Lift Study | Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times. | Visual | Each element | IP | SE/PE/SPE | This ITP
4.2 | Precast Placement | IFC Drawings 610.27 | Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings. The nominal gap between elements is as per the IFC Drawings. | Measure Visual | Each element | IP | Surveyor SE/PE/SPE | This ITP
4.3 | Precast Traceability | 620.09 | All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number. Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report | Visual | Each element | IP | SE/PE/SPE | This ITP
5 | Post-installation Activities
5.1 | Falsework Certification | 613.12 | The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above) Attach: Attachment B | Visual Document Review | Once, immediately following the installation and prior to any Work commencing on the members | HP | Nominated Authority | ConQA Hold Point Release
5.2 | Flowable Grout Pour (for integrally cast beams) | IFC Drawings | Where applicable, the gap between the bottom of the precast element's soffit and top of the crosshead should be grouted. Complete: Grout Pedestals & Bearings ITP | Visual Document Review | Where applicable | IP | Surveyor SE/PE/SPE | Grout Pedestals & Bearings ITP
5.3 | As-built Survey | IFC Drawings 610.47 (a) Table 610.472 Feb 2020 | Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.472 (Feb 2020) as applicable to the element. Attach: Survey As-builts / Survey Report | Document Review | Each element | IP | Surveyor SE/PE/SPE | This ITP
5.4 | Removal of Falsework | Temporary Works Design 613.16 | Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above). Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for and repair. | Visual Document Review | Where applicable, each element | IP | SE/PE/SPE | This ITP
5.5 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /