## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-291-STR-HOP Precast Bridge Beams (Supply & Installation) | itp |  |  |  |  | ITP-291-STR-HOP Precast Bridge Beams (Supply & Installation) Rev 2
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-291-STR-HOP-Precast Bridge Beams (Supply & Installation)
label | ITP Description: HOP-Precast Bridge Beams (Supply & Installation)
label | Discipline (e.g. CIV/STR/RAIL): STR
label | Revision Number: 2
label | Revision Date: 5/08/2025
label | ITP created by: Manwel Kalyana
label | ITP approved for use by: Pradeep Talasila
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 169 July 1993
label | ○ VicRoads Section 610 Feb 2020
label | ○ VicRoads Section 613 June 2017
label | ○ VicRoads Section 620 May 2009
label | ○ VicRoads Section 622 November 2018
label | ○ VicRoads Section 630 Jan 2023
section | 2. Preliminaries
checkpoint | 2.1 - Precast Elements
label | Reference - IFC Drawings
label | ○ 610.46 (a), Table 610.463 (November 2018)
label | ○ 610.47 (a), Table 610.473 (Feb 2020)
label | ○ 620.03
label | Acceptance Criteria - Precast supplier is required to provide the following Quality Assurance documentation for each element, typically this consists of:
label | i. Certificate of Compliance / Birth Certificate
label | ii. Compressive strength test results
label | iii. Precast Lifting Design
label | iv. Pre-pour check sheet / ITP
label | v. Pre-stressing check sheet / ITP
label | vi. Post-pour check sheet / ITP
label | vii. Covermeter check record
label | viii. Record of dimensional measurements to demonstrate compliance with dimensional tolerances of precast and bearing plates (where applicable) shown on table 610.463 (November 2018) / 610.473 (March/June 2019).
label | ○ Note: Different revisions of 610 have different clause numbers
label | ○ Collate: Precast Quality Assurance Documentation so it can be uploaded into Teambinder (don't attach it here)
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.2 - Temporary Works Designs
label | Reference - 610.27, 613.04, 613.05, 613.16
label | Acceptance Criteria - All temporary works (such as propping the precast elements) shall be designed and certified by an Engineer who has qualifications admitting to Corporate Membership of the Institution of Engineers, Australia, with a minimum of five years experience in structural design.
label | ○ Details of the design, inclusive of the proposed release of the falsework, shall be submitted for review to the Nominated Authority.
label | ○ Attach: Temporary Works Design
label | ○ Attach: Attachment A
label | ○ Attach: Attachment B
label | Method - Document Review
label | Frequency - Where applicable, once, 5 days prior to installation
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Crosshead / Pedestal Tolerances
label | Reference - Survey As-builts / Survey Report 610.472 (x)
label | Acceptance Criteria - Re-check that the As-built dimensional tolerances comply with the requirements below:
label | ○ Reduced level ±2.5mm
label | ○ Variation from grade across the width of individual pedestals shall not exceed 1 in 200
label | ○ Deviation from flat surface ±1mm
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - PE/SE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 2.4 - Crosshead / Pedestal Compressive Strength
label | Reference - IFC Drawings, Compressive Strength Results
label | Acceptance Criteria - Re-check that the minimum required compressive strength as shown on the IFC Drawings has been achieved.
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 3. Pre-installation Activities
checkpoint | 3.1 - Survey Set-out of Precast Elements
label | Reference - IFC Drawings Table 610.473 (Feb 2020)
label | Acceptance Criteria - Survey activities undertaken to ensure and validate that all Works meet level and location requirements within the tolerances as per the table 610.473 (Feb 2020) as applicable to the element.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.2 - Elastomeric Bearings
label | Reference - IFC Drawings
label | Acceptance Criteria - Where applicable.
label | ○ Complete: Elastomeric Bearings (Supply & Installation) ITP before proceeding with this ITP.
label | Method - Document Review, Visual
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.3 - HDPE Bearing Shim Placement (for integrally cast beams)
label | Reference - IFC Drawings
label | Acceptance Criteria - Place the bearing shims (or variety of shims) to the survey marks and to the required thickness to achieve compliance with the IFC Drawings and tolerances.
label | ○ Note: The minimum and maximum thicknesses of the HDPE bearing shims as this will determine the product for the grouting activities.
label | Method - Measure, Visual
label | Frequency - Where applicable, each bearing location
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.4 - Materials Inspection Checklist
label | Reference - 620.06, 620.07 MRPA Quality Management Plan
label | Acceptance Criteria - General inspection of precast elements for defects including cracks, damage, exposed reinforcement and where applicable, damage to coatings.
label | ○ Confirm that the cast in lifters (anchors or loops) are the correct size and orientation as per the Precast Lifting Design (they should be clearly labelled on the end to be connected to).
label | ○ Elements shall have unique identification and orientation marked (if applicable).
label | ○ Complete: Materials Inspection Checklist in ConQA
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 3.5 - Tapper Plates
label | Reference - 630 IFC
label | Acceptance Criteria - The method of handling, transporting and erection of the steelwork shall be such that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | ○ All installation and erection of the steel structure shall comply with the requirements of AS/NZS 5131.
label | ○ Ensuring that the orientation of the installed base plates on the beams complies with AS/NZS 5131 and VR630.
label | Method - Document Review
label | Frequency - Each Plate
label | Category - HP*
label | Responsibility - SE/PE
label | Verifying Documents - This ITP
date | Date Completed:
section | 4. Installation Activities
checkpoint | 4.1 - Precast Handling
label | Reference - 620.07 Crane Lift Study
label | Acceptance Criteria - Unless otherwise specified, precast elements shall be lifted using the lifting points provided and supported with the top surface uppermost at all times.
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.2 - Precast Placement
label | Reference - IFC Drawings 610.27
label | Acceptance Criteria - Precast elements shall be placed onto the bearings/bearing shims and not released from the crane until sufficiently braced in accordance with the approved temporary works design and/or IFC drawings.
label | ○ The nominal gap between elements is as per the IFC Drawings.
label | Method - Measure, Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 4.3 - Precast Traceability
label | Reference - 620.09
label | Acceptance Criteria - All manufactured precast elements shall be traced from the completion of manufacture to their final location by a unique identification number.
label | ○ Record: The final location of each precast element, showing individual ID and date installed onto the Red-line Drawings or Survey Report
label | Method - Visual
label | Frequency - Each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Post-installation Activities
checkpoint | 5.1 - Falsework Certification
label | Reference - 613.12
label | Acceptance Criteria - The application of any load shall not proceed until the Certificate of Compliance - Falsework Inspection of the constructed falsework has been reviewed by the Nominated Authority (from 2.5 above)
label | ○ Attach: Attachment B
label | Method - Visual, Document Review
label | Frequency - Once, immediately following the installation and prior to any Work commencing on the members
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Flowable Grout Pour (for integrally cast beams)
label | Reference - IFC Drawings
label | Acceptance Criteria - Where applicable, the gap between the bottom of the precast element's soffit and top of the crosshead should be grouted.
label | ○ Complete: Grout Pedestals & Bearings ITP
label | Method - Visual, Document Review
label | Frequency - Where applicable
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - Grout Pedestals & Bearings ITP
date | Date Completed:
checkpoint | 5.3 - As-built Survey
label | Reference - IFC Drawings 610.47 (a), Table 610.472 Feb 2020
label | Acceptance Criteria - Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the table 610.472 (Feb 2020) as applicable to the element.
label | ○ Attach: Survey As-builts / Survey Report
label | Method - Document Review
label | Frequency - Each element
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.4 - Removal of Falsework
label | Reference - Temporary Works Design 613.16
label | Acceptance Criteria - Falsework shall be removed in an even and gradual process as shown in the falsework design (from 2.4 above).
label | ○ Where holes have been drilled into surrounding concrete elements for fixings and restraints, follow the Structural Concrete Patch Repair ITP for and repair.
label | Method - Visual, Document Review
label | Frequency - Where applicable, each element
label | Category - IP
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | 5.5 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP