## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-001 - Pre-commencement of works | itp | ITP-001 - Pre-commencement of works |  | b2b782f2-b9c0-484f-bd36-258583f36a87
| section | 1 - Construction - General
| checkpoint | 1.1 - Design Drawings
71f67fa0-3c0c-5410-b36f-a53aa2cf003e | note | FREQUENCY: Prior to commencing any activity
5ba9f83b-5485-5049-a103-a7435b22c22a | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
6926dfb8-0a9d-5b33-9e67-4cc3d1ff92f9 | note | REFERENCE DOCUMENTS: IFC Drawings
abb2cee6-0650-5422-8913-c1058c2fb5d9 | note | INSPECTION/TEST METHOD: Visual inspection
003a9366-de6a-5501-a83f-d51e112e7f79 | note | RECORD OF CONFORMITY: ITP Signed
71ceb833-7216-5b6f-b832-bcb3ccd22cfd | note | IHP
789d74a0-a661-5145-932b-ba96ea5b035c | note | RESPONSIBILITY: Site Engineer / Site Foreman
6f34cd9c-2a60-5668-99b7-09c452e6edc3 | date | Date Completed:
| checkpoint | 1.2 - Service Locating / Permits
9d2f334d-0ac7-5a39-adb5-6fd0f7821fe1 | note | FREQUENCY: Prior to commencing any activity
41f88291-1d88-5e10-8940-7323883f59f3 | note | ACCEPTANCE CRITERIA: Lodge DBYD application prior to works commence and obtain any relevant permits applicable to the works. DBYD to be renewed every 30 days.
67f60d93-d491-5bca-a573-0b378759e51f | note | ○ All nominated/aﬀected services from the DBYD application must be located/potholed prior to commencement of works.
793bc6b7-154e-552b-b804-2f6e23bd4747 | note | ○ Works identified within the vicinity of the powerlines to ensure distance exclusions are followed & spotter used, if required.
691b6b32-ff92-5287-a8e7-5e07179f105c | note | REFERENCE DOCUMENTS: DBYD Information
9588dbfa-abe1-50b5-99bf-610cd26b0b26 | note | INSPECTION/TEST METHOD: Visual inspection
4138b927-5501-5454-b549-5bb13f63f95e | note | RECORD OF CONFORMITY: ITP Signed
ec052246-986f-5a95-a569-6075de724284 | note | IHP
fd7ca7cd-0e60-56da-950b-e07bc900db20 | note | RESPONSIBILITY: Site Engineer / Site Foreman
850656a2-b4f5-54dc-870c-88582a9349a6 | date | Date Completed:
| checkpoint | 1.3 - Commencement of work
31f58227-fcf1-5095-b58b-8eb019d9433e | note | FREQUENCY: Prior to commencing any activity
7dce5cd7-8e2f-55f3-ad86-b18d813aca55 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence work on site before the following documents have been submitted to the Superintendent and the Superintendent has authorised release of the Hold Point:
b4769e92-e18a-56bb-b07d-04176b58a9c4 | note | (a) Public Liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
50738ca6-b15e-5687-893c-fa6aafbee9bc | note | (b) Health and Safety Co-ordination Plan
3b373e3d-a03c-50eb-a02b-b4d25d67c2be | note | (c) Environmental Management Plan for initial works
565b1dce-2dfa-5257-86eb-e623517edb61 | note | (d) Project Management Plan
76364f59-ec0c-5219-9c7e-ff82a3ff5e93 | note | (e) Quality Management Plan
f80239e4-e68b-5085-a26e-d06f683c446e | note | (f) Safety Management Plan
792bc617-c02a-5fd4-80b6-3a9f4e16e05f | note | REFERENCE DOCUMENTS: VicRoads Standard Section 160, 166, 167, 168 & 176
14423c9b-fb6f-5dd0-be84-9d5cbb985541 | note | INSPECTION/TEST METHOD: Visual Inspection
d415731a-b7b1-519d-9668-0094d5105afb | note | RECORD OF CONFORMITY: ITP Signed
65ca0342-21fe-5a3f-b8de-58376e46cbc6 | note | HP
b42ce6ec-732f-5ae1-9c53-23f4e406e85c | note | RESPONSIBILITY: Site Engineer
fade3f06-e748-5c6f-a93d-cce89631f532 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Traffic Management
| checkpoint | 2.1 - Submission of the TMP to the Superintendent
6dafe5a2-007c-5ece-9e46-02528f1491ab | note | FREQUENCY: Prior to commencing any activity
9d3c1f08-6841-56f5-9cc2-0493f7aef2f7 | note | ACCEPTANCE CRITERIA: The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point.
8484f2d4-e331-5ccd-bd63-7b62f0bde49c | note | REFERENCE DOCUMENTS: TMP VicRoads Standard Section 166.08
b0cee672-ac1b-5e7b-84d3-45d800cefb3c | note | INSPECTION/TEST METHOD: Visual Inspection
efc45edb-677d-5715-929e-eb3d58110832 | note | RECORD OF CONFORMITY: ITP Signed
517fee34-2d61-5624-bd6a-a25decba0e28 | note | HP
88e574d1-6129-55a8-a537-df4f9c4c46ff | note | RESPONSIBILITY: Site Engineer
015d5882-5fa7-5fff-b7e8-2ec5094889cc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Detours and Side Tracks (a) Side Tracks (b) Detours
baada508-963d-5d74-a243-42d372b7526e | note | FREQUENCY: Prior to commencing any activity
574acc95-20bd-5401-90ab-ee51358ffd07 | note | ACCEPTANCE CRITERIA: Traffic shall not be diverted on to any side track until permission to use such side track has been given by the Superintendent.
d2f5d684-d013-5a57-b923-e2ff1cc99810 | note | – Permission has been given by the Superintendent and Ballarat City Council.
934ae2b5-46f0-5135-87ab-23d6e96aa995 | note | ○ Where VicRoads as well as the Contractor has some responsibility for the restoration of any detours or sidetracks, the Contractor shall not commence any restoration work until the Contractor has submitted details of the work to be undertaken to the Superintendent for review.
d8a242e1-f8c8-56a4-b37a-e280af830071 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166.17 (a) & (b)
8aadc036-8faf-5316-8881-03d6dbc5f83c | note | INSPECTION/TEST METHOD: Inspection
dfaa8a00-0022-557f-a7be-0a3d631b93da | note | RECORD OF CONFORMITY: ITP Signed
5add69eb-d152-5fda-8488-ac2a94e03e12 | note | HP
21697a79-613e-57eb-91ed-33860604b39c | note | RESPONSIBILITY: Site Engineer
47811331-f564-55e2-b68a-682965bc5522 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Traffic Management Documentation
5373dc24-2a23-5057-9cf9-8d71dbee888b | note | FREQUENCY: Prior to commencing any activity
7688489e-b135-5a1f-b0be-520047906fd1 | note | ACCEPTANCE CRITERIA: Ensure all TGS plans have been reviewed and deemed acceptable for the project. Obtain MoA approval for any road impacts or closures.
90078d00-0aa6-5e55-8f99-4c43cc947229 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166
7386f294-bd15-520d-b0aa-a069146c4a1a | note | INSPECTION/TEST METHOD: Visual Inspection
f8fc7989-ad76-509a-a9a3-d81df6181eff | note | RECORD OF CONFORMITY: ITP Signed
bb9e493c-8d4b-5eb4-8122-8f05dc54edb9 | note | IHP
849bdc8f-2de8-56af-856c-339a9e9ba27c | note | RESPONSIBILITY: Site Engineer / Site Foreman
499980b5-b6d0-5321-ad26-86de5a772fbe | date | Date Completed:
| section | 3 - Health and Safety
| checkpoint | 3.1 - Occupational Health & Safety Management Implementation
92fc0108-7d22-5da7-8c54-358811e4193a | note | FREQUENCY: Prior to commencing any activity
7d05095e-f725-5d80-9344-1443ec5eeed1 | note | ACCEPTANCE CRITERIA: Signed Safe Work Method Statement (SWMS) in place. All personnel including Subcontractors must complete Site Induction prior to arriving on site.
166267d2-5c3b-51b4-855e-ef242c78f7e9 | note | REFERENCE DOCUMENTS: Site Specific SWMS
dd46dae3-5c1e-5ed5-9903-e39e47e4ecea | note | INSPECTION/TEST METHOD: Inspection
598e5bf7-c44c-52e3-90e8-63c38f4ea2b6 | note | RECORD OF CONFORMITY: ITP Signed, SWMS
1baa6e8d-728f-5635-98a9-57eab385655d | note | IHP
39a1b7fa-b9b9-5ebd-8e58-9219fd81e0ae | note | RESPONSIBILITY: Site Engineer / Site Foreman
6d8ac50c-b571-5ef0-8b76-62e4606ccdab | date | Date Completed:
| checkpoint | 3.2 - Health and Safety Co-ordination Plan and Declaration
287f6297-c135-5d68-bbb0-287037827499 | note | FREQUENCY: Prior to commencing any activity
ec0f5113-66ed-5d88-a14a-95c15c38bf40 | note | ACCEPTANCE CRITERIA: The Contractor shall, not less than 5 working days prior to commencing work, submit to the Superintendent:
30e62d4d-4f51-5508-906e-f2177ab0d154 | note | (a) a reviewed Health and Safety Co-ordination Plan; and
439a128c-3954-5f0f-bad5-ea3ecfc730c8 | note | (b) a signed HSCP Declaration by an OH&S consultant/advisor that the HSCP meets all the necessary requirements. The Declaration shall be in accordance with the proforma included in the appendices of this Specification.
5e721d20-0c0e-5f9a-b748-ce206e7f5b25 | note | (c) a completed VicRoads HSCP Checklist with Contractor’s responses for each checklist item requirement.
c61dffe3-41a0-5c3d-927a-46f0f6965460 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 168.05 (c)
17fc43f7-a39c-5a27-8a85-c35a28dbe7aa | note | INSPECTION/TEST METHOD: Submission
1d7d5406-59aa-51e5-a67d-3d0293280208 | note | RECORD OF CONFORMITY: ITP Signed, Safety Management Plan
c68e3f82-86e7-5c5d-8854-31367d89b2db | note | HP
397028b3-d3cd-57bd-8652-31e15a27cee2 | note | RESPONSIBILITY: Site Engineer
5ae63acf-7e72-52d4-94c4-81595df3ff86 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Environmental Management
| checkpoint | 4.1 - Environmental Impacts, Aspects & Risk Assessment Implementation
b6bec204-787a-517b-b78a-adce929c572a | note | FREQUENCY: Prior to commencing any activity
aca4d08a-3fa6-5a7e-9f0d-6fac652d8818 | note | ACCEPTANCE CRITERIA: All environmental controls implemented in accordance with the Contract Environmental Impacts, Aspects & Risk Assessment.
1ca89072-75d0-5f64-ae01-436602ebcd9e | note | REFERENCE DOCUMENTS: EMP & A&I
d4dcf6f1-0147-50a2-8bc5-518bc74a7316 | note | INSPECTION/TEST METHOD: Visual Inspection
9d49244b-c4bf-5290-ac99-f367795493f7 | note | RECORD OF CONFORMITY: ITP Signed
52596b90-1eea-5f19-aa8d-c3bd5e8327ab | note | IHP
7134d9c2-8c7e-5bd4-bfe8-2f2de70aa6ac | note | RESPONSIBILITY: Site Engineer / Site Foreman
caf89e73-6c2d-5226-8fcf-ae5e1fed00f0 | date | Date Completed:
| checkpoint | 4.2 - Environmental Management Plans
c5fcc76f-b5e0-5b87-8786-bdcbff149c40 | note | FREQUENCY: Prior to commencing any activity
7ba7aaf1-5d36-5fb5-b7da-8bfc92cf5fab | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review an Environmental Management Plan not less than 2 weeks prior to the commencement of work. Work shall not commence until:
8e1a1448-b873-593a-8c4f-8a4d717033ea | note | – the Superintendent is satisfied that the Plan meets the requirements of this specification; and
c12a87a1-6b30-5d66-ba65-c0134f101112 | note | – the controls detailed in the Plan are implemented; and
34c92903-daa0-5bed-bee4-74050b8b6ccc | note | – the Superintendent has authorised release of the Hold Point.
3468b1ff-b169-5293-bee0-8abdea704671 | note | – Limit of works identified in applicable SWMS.
43f1af8a-8d9f-5d55-9ee6-da9d6ced58cf | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.A3, VicRoads Standard Section 177.A3
8f1fa4ba-8733-50bf-8356-c14cf9c8a815 | note | INSPECTION/TEST METHOD: Submission
4f5320e7-b5c9-58f1-b936-eb7042d28da9 | note | RECORD OF CONFORMITY: EMP, ITP Signed
768327c5-e74d-5367-bae1-6064e1d3fdb5 | note | HP
62690deb-bc4b-5a3d-9a43-11aae90cfa01 | note | RESPONSIBILITY: Site Engineer/Superintendent
de3de897-433e-54f7-afa0-a7f4e1a3192a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Flora and Fauna
f4ed8012-e420-5f24-9945-f7f46586fa74 | note | FREQUENCY: Prior to commencing any activity
e9a49f3f-b429-5f2d-8f58-b2fcdbf246a0 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to conﬁrm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones.
6096fe62-4c3f-5cab-9e9b-0891276ac64d | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.I1, VicRoads Standard Section 177.I1(c)
96c46da1-bdf6-53c3-ada3-321b53493a5b | note | INSPECTION/TEST METHOD: Visual Inspection
923d0d39-3da8-507a-8030-055063917ada | note | RECORD OF CONFORMITY: ITP Signed, Relevant permits, No Go Zone Signage
5c1b4d8a-db4c-5d6d-9bf1-4d2e9297e502 | note | HP
67a12f5b-772a-58ee-83d6-9dbf71969e32 | note | RESPONSIBILITY: Site Engineer
ad00577e-018b-5ace-bf00-47afdd52a575 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Erosion and Sediment Control
0fba206b-310a-54cb-a5bb-ec2cf76ed4d6 | note | FREQUENCY: Prior to commencing any activity if applicable
916fd968-b194-55e8-ab8b-e2735d1db74a | note | ACCEPTANCE CRITERIA: The Contractor shall provide the necessary environmental controls as nominated on the approved Environmental Management Plan and identified on site.
01ac8212-0c29-590f-9946-dd5f0aa9df1f | note | REFERENCE DOCUMENTS: VicRoads Standard Section 177.D1(c)
f350f765-79cb-58ed-bf7c-3f99aa59327f | note | INSPECTION/TEST METHOD: Visual Inspection
5e797361-fa9b-52aa-96d2-5e90d2df5157 | note | RECORD OF CONFORMITY: ITP Signed
70a7127e-7861-567a-9e22-474255eb9bf3 | note | IHP
a3e0d071-8894-5e24-b029-c5bc0af33f2a | note | RESPONSIBILITY: Site Engineer / Site Foreman
ad85d4b1-d3d5-5f18-80d3-18c502ac5a20 | date | Date Completed:
| section | 5 - Stakeholder and Community Engagement
| checkpoint | 5.1 - Residents have been informed
316685bc-4737-567a-bc18-5a3946cffe70 | note | FREQUENCY: Prior to commencing any activity
50eb6384-e739-57c3-81c9-1945f921ca5b | note | ACCEPTANCE CRITERIA: Residents impacted by construction works are to be notified by letter drop of the construction taking place, the timeframe of the works and information on how the works will affect them.
987bb6cc-1bcc-502c-961d-d3b0bef464d7 | note | REFERENCE DOCUMENTS: Letterdrop
870b9c6a-e30f-59da-a48c-ddaaf8cb2c3f | note | INSPECTION/TEST METHOD: Visual Inspection
521900c4-261a-5bf5-8da5-6d904be3195f | note | RECORD OF CONFORMITY: ITP Signed
111801b8-29ae-5e07-a891-bebe9f48c27d | note | HP*
802c72f7-12fc-5649-b41e-cbe8b4560bf5 | note | RESPONSIBILITY: Site Engineer
b552a11f-cae1-5b3a-a492-d6446e5c6c5d | date | Date Completed:
| checkpoint | Final Inspection
cdcb2dc5-ba5c-5b4f-ba4b-f02fc2866e7a | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
dffb1d2c-3dd3-545c-88eb-886f9111977a | textbox | Print Name:
0b52550b-543b-582b-baea-35c0879929e5 | textbox | Position:
a20568eb-a297-5f0b-a3e9-d3ed2308f90a | date | Date:
| checklist | ITP-002 - Stormwater Drainage Red Boundary Rev. 3 | itp | ITP-002 - Stormwater Drainage Red Boundary |  | ee1232b3-3608-425a-ab86-3f9ed85941a9
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
92b5803c-ecde-5c1a-8913-e060d13a3cd4 | note | FREQUENCY: Prior to commencing any activity
4a9b0cdc-1959-551c-9bef-de7a60dc9639 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct and complete set of IFC Drawings.
2a6d6d46-e013-5e5f-99a8-5040ef87ef26 | note | REFERENCE DOCUMENTS: IFC Drawings
1f12873e-e873-5583-bd1a-82356b31e5e0 | note | INSPECTION/TEST METHOD: Visual inspection
b5a8b69f-82f9-5854-a63b-4787a844a91c | note | RECORD OF CONFORMITY: ITP Signed
db3486e8-3c27-5eed-82b5-cf223b43662e | note | IHP
d04d97b8-09b6-55cb-a3d2-c63262f1997f | note | RESPONSIBILITY: Site Engineer / Site Foreman
3bf321f8-31f7-5974-b359-660af1e6b1bc | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
8ec38fb8-8208-5ac1-b7da-b56e2e7f9ad7 | note | FREQUENCY: Prior to commencing any activity
27a91f17-b935-5071-a981-53361f605ba9 | note | ACCEPTANCE CRITERIA: Ensure all relevant project documentation has been submitted and approved by Superintendent including SMP, PMP, EMP, QMP, TMP and SEQ documentation.
aa519f0a-4d9d-5f8b-8860-e3ac9c0a7e82 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP & SEQ
54faa71f-ca00-5b53-95d4-723b1b113093 | note | INSPECTION/TEST METHOD: Visual Inspection
6fe19b9b-8eff-5862-80dc-7ae34d6aef13 | note | RECORD OF CONFORMITY: ITP Signed
5da4e081-3cd9-59e9-98be-440a7a4262e6 | note | HP
1f9ac07e-b28a-55ea-97aa-a62b22491a81 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a14fa94c-12ad-5f39-81ca-355023ca07a0 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.3 - Purchase and delivery of pre-cast drainage components
b6d079c2-ffe2-561c-8137-1afd00f238c0 | note | FREQUENCY: Each Delivery
157f5a62-e7e1-5a22-ac63-7627225671ef | note | ACCEPTANCE CRITERIA: Precast materials to be used for construction have been inspected and are free from defects or damage.
37e75d16-817f-56f3-829c-4f1b0f5f6a20 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.05
47e7309a-1c4a-5062-b94b-c402a84083be | note | INSPECTION/TEST METHOD: Visual Inspection
68e03e93-dea9-5fc8-a8ab-12279565fb5e | note | RECORD OF CONFORMITY: ITP Signed
e3e23673-9f61-543a-9a1c-d6dfd789edd0 | note | WP
58f933d8-455b-5d03-a600-0b531a786c3d | note | RESPONSIBILITY: Site Engineer
6aadae2c-7081-5412-b77d-13bda39d21f1 | date | Date Completed:
| checkpoint | 1.5 - Backfill material Classification
cba2c869-b8f4-5b35-b1e5-a51b0a8891e3 | note | FREQUENCY: Prior to start
96323ad3-53c5-5c86-8aa2-15a72b28b169 | note | ACCEPTANCE CRITERIA: Approved compacted backfill within bedding zone to be 20mm Class 3 Fine Crushed Rock as nominated on the IFC Design Drawings
a2202f38-a013-5920-a724-f48bdb0afc48 | note | REFERENCE DOCUMENTS: Dwg No. SD-D8-1 Sheet 5
09b07888-4881-5637-b02c-a688daf872ed | note | INSPECTION/TEST METHOD: Verify
3c316903-d6cb-5c11-ae54-de6c216ee5fb | note | RECORD OF CONFORMITY: Test Reports from supplier
52e4303b-0563-5cf6-b540-50d26bb5f373 | note | TP
8af0b073-52ac-585b-84c0-c739965cc962 | note | RESPONSIBILITY: Site Engineer
8bda9679-5576-526c-b50d-c92e874ca86e | date | Date Completed:
| checkpoint | 1.6 - Mortar material classification
f743a5a2-a243-537a-804f-1e912b5393e8 | note | FREQUENCY: Prior to start
473e6876-fd77-5c36-baa4-8715a2128e17 | note | ACCEPTANCE CRITERIA: Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause 610.32.
b49f17b7-09bc-5ee1-8e03-e39a71103106 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.09 (e)
4cc20e7a-4e84-5a83-81f0-563803431ea4 | note | INSPECTION/TEST METHOD: Verify
edb45b60-78c7-5a41-adbf-4a8d970190da | note | RECORD OF CONFORMITY: Test Reports from supplier
babbf1d5-1aa7-500a-82dc-5cafa23bcab9 | note | TP
2a79e483-70fb-5340-a9b3-8f836cadadf5 | note | RESPONSIBILITY: Site Engineer
a1fedf30-ae0c-5024-95fb-38d5f73793fc | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
1a2433c8-fe6f-5e33-b20b-c3c7d2480adc | note | FREQUENCY: Each lot
33fd66e5-376b-5e98-8d8a-36cc8608df47 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
2a898508-6529-5380-974f-4e38129ea65d | note | ○ Plant and equipment shall be appropriate for the task.
3f4bc39d-213d-5ce6-a276-6385eba28dd1 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
1c407d8f-f6a5-516b-ad53-0e70409128b8 | note | REFERENCE DOCUMENTS: Excavation permit
95e2f576-e1cf-5989-93ec-941d4771c3dd | note | INSPECTION/TEST METHOD: Verify
3c25d792-bdd1-534e-a289-4da9c7434120 | note | RECORD OF CONFORMITY: ITP Signed
9fba15a6-5eea-54c6-a33b-99b823572483 | note | IHP
913e3826-ed05-5f43-a86e-4af9b407dcb8 | note | RESPONSIBILITY: Site Engineer
b831db7b-b36e-5697-b0cb-94cb5c238f60 | date | Date Completed:
| checkpoint | 2.12 - Conformity with Drawings
8fe786b1-781b-5cde-9fd5-777c03ae4090 | note | FREQUENCY: Prior to Excavation
15abdcc0-c9ae-55cc-ba16-3d0281f3a8c2 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the pits and drainage lines the Contractor shall conﬁrm the position of all drainage components with the Superintendent.
529e7593-6acf-5d3d-bfc3-8fdbd652d58b | note | Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
bec9b3f6-286c-5e19-ada9-4191ecbe6fb1 | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
4e0b4aa6-b3c2-57a2-b723-5a7006b69f03 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
ad253d3b-f4a9-5cd6-bfce-b1fdb93c6d7e | note | (c) invert level of pipes at pits ±50 mm
9a66854b-3a80-5143-9fc4-582d8204b52c | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:200
ed23ae9d-2af3-553a-8589-b6a0632fca25 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.09
25d9fadc-0c75-5f02-98be-775102ef8070 | note | INSPECTION/TEST METHOD: Visual Inspection
bd8459bf-aa76-519a-a10d-a82a7c70851e | note | RECORD OF CONFORMITY: ITP Signed
9daca64f-02fd-5537-bd4e-1d39ff30d58e | note | HP
6e23942a-d840-5e5b-a9b9-587a930a74bb | note | RESPONSIBILITY: Site Engineer/ Superintendent
6297ba05-5a65-5b01-8054-f5e656630ff6 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.13 - Excavation
8afd23e5-8cf9-5c94-b943-0b57d1be3178 | note | FREQUENCY: Each Trench
569e677b-22eb-5e82-8f42-71866d8b7656 | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm.
ce0c75fc-af42-56f1-8c11-7fa9753360f2 | note | REFERENCE DOCUMENTS: VicRoads Standard Section Table 701.151
eaa665c8-4777-5b72-a95b-00872ac0d0d8 | note | INSPECTION/TEST METHOD: Visual Inspection
3f89f6b8-cfb9-59cc-8ed9-d698d64d680d | note | RECORD OF CONFORMITY: ITP Signed
a4afa369-e5fd-5ba8-a519-eb24a9d1866a | note | HP
caef567c-8513-5e50-b5d0-ac27e6f0ed59 | note | RESPONSIBILITY: Site Engineer/ Superintendent
8fcf8ecb-4ede-53c5-9056-8b66c860e7b4 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.14 - Compact base of trench
e577b0d1-0a5b-53f0-a459-2e545cee50fd | note | FREQUENCY: Each Trench
972a2eaf-3b64-5674-aaba-a59512e860c2 | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant.
a628a73b-f7c2-5a57-b4c6-4e6f7b0706a7 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.15
7f7ca13d-52fa-5f7c-ad5e-d6364a164c86 | note | INSPECTION/TEST METHOD: Visual Inspection
1a25addc-1594-5554-b3eb-876e12073f4e | note | RECORD OF CONFORMITY: ITP Signed
f816f50b-1df2-58b6-af2b-cc06ba064a01 | note | WP
506873a0-66c2-57bc-9430-47aea15b417f | note | RESPONSIBILITY: Site Engineer
115c19d0-c997-59c1-999f-c29c90de04bb | date | Date Completed:
| checkpoint | 2.15 - Placement of Bedding Material
81776113-44e6-55a9-abd5-11aa0fa772ea | note | FREQUENCY: Each Trench
36077229-bf3c-56a3-9682-d913ca4a0376 | note | ACCEPTANCE CRITERIA: Bedding material shall be compacted to no less than the below thickness:
fbe97370-7a74-568c-ba96-2cb70ef7ad1b | note | ○ 100mm where D < 1500mm
2de9259f-7bbf-5550-863a-640966e57d84 | note | ○ 150mm where D > 1500mm
c9f779f2-75dc-5dcc-bdb7-c8e604418944 | note | – where D is the nominal pipe diameter or culvert width.
37f01784-a19c-596b-9e31-a31eda42b854 | note | REFERENCE DOCUMENTS: Dwg No. SD-D8-1 Sheet 5
1ff80589-5c47-5cd9-afb5-37cb6501fee6 | note | INSPECTION/TEST METHOD: Visual Inspection
e4ad711f-8b4d-5939-a036-962b49565e31 | note | RECORD OF CONFORMITY: ITP Signed
52788bde-6305-5c3d-88da-addbe6694c2d | note | WP
e6a352ae-d9a3-5bb0-a41a-f97f6ce71168 | note | RESPONSIBILITY: Site Engineer
5bd33542-10e6-5bde-93f3-a8962b7242a9 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.16 - Laying of Pipes
d7a1f9a6-d927-5c82-a6d2-4e744c4c049c | note | FREQUENCY: Each Line
d547fbf6-be7a-549d-9901-f21cc7848d17 | note | ACCEPTANCE CRITERIA: Laying of pipes shall not commence until the Contractor has verified that pipe bedding complies with the lines and levels of the design drawings and that pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively.
191c1185-866e-58fe-a1ce-02b012cc98bf | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.17
08ee6b1f-16b2-5b63-8944-af80a1962036 | note | INSPECTION/TEST METHOD: Visual Inspection
ab569857-06dc-5f90-9b59-1a556e96da2e | note | RECORD OF CONFORMITY: ITP Signed
b5eef12e-87de-5312-965d-c64f1cfaceb2 | note | IHP
7392f788-dc20-5cc0-b984-812d5a7dea2b | note | RESPONSIBILITY: Site Engineer
522fe3e9-c79f-590b-81d2-e41b6bc8d616 | date | Date Completed:
| checkpoint | 2.17 - Jointing Pipe Sections
140e3b5e-d3df-56a9-835d-0122dce8c21f | note | FREQUENCY: Each Line
1119934e-d288-59af-9557-e602fbee646c | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance with manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
1d99ce26-8fa8-529c-8adb-d564789f4bdf | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.18
56d54f42-0573-5a00-a160-5216bd6dbdd2 | note | INSPECTION/TEST METHOD: Visual Inspection
ae318daf-2879-581a-9a79-80bc6cbb959e | note | RECORD OF CONFORMITY: ITP Signed
11c3d88f-5309-54b1-b378-b4dff1fd69ec | note | WP
7135b048-e240-56c8-92f4-66223890a75f | note | RESPONSIBILITY: Site Engineer / Site Foreman
62e158a7-9353-5814-8a84-995963ed8085 | date | Date Completed:
| checkpoint | 2.18 - Jointing to Pits
815edd43-71db-5bef-bc99-6c91e944c982 | note | FREQUENCY: Each Pit
efa5c46b-8820-523c-b6ee-cddd6e8c5f12 | note | ACCEPTANCE CRITERIA: The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33.
d31106dd-f514-5cf6-b34d-92a509b94ba6 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.15
f2296d96-0a27-558a-a6a0-b3c1ead55069 | note | INSPECTION/TEST METHOD: Visual Inspection
d857f4e2-14c7-5dd1-9c6a-96956f1cd6f0 | note | RECORD OF CONFORMITY: ITP Signed
6aeba472-6bbb-523b-88ca-5eb3aea013d6 | note | WP
33f20e85-05dc-5838-9b65-8cacd35fd422 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a297ded3-5e5b-5e3b-83c5-2753b03d1a37 | date | Date Completed:
| checkpoint | 2.19 - Place & compact backfill material over pipes
b9bba853-6427-523a-aea1-85f6dcdd6598 | note | FREQUENCY: Each Lot
83c6e429-7d89-5548-845e-d1feb79845cf | note | ACCEPTANCE CRITERIA: Unless the pipe is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
29f43813-9e50-5bec-b06a-e0304bf5f0d1 | note | (i) Culvert Under Area not to be Paved
563b6836-083f-5fe3-ae79-fe2f7420621d | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
1f77e592-d963-5b7b-8fe9-116482098147 | note | (ii) Culvert under area not to be paved
c993169c-48e2-5f89-847f-f11b94450650 | note | ○ The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
eb1c4d9b-9bfb-5370-a349-44bca2c83a01 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.19, Dwg No. SD-D8-1 Sheet 5
212306e2-5aeb-5277-ae39-c92d60167881 | note | INSPECTION/TEST METHOD: Visual Inspection
8ce99433-92c3-59e1-ac1e-75eab4191548 | note | RECORD OF CONFORMITY: ITP Signed
92b64b88-c838-522a-815d-a5ef4b00d437 | note | IHP
a5b485e5-3659-5660-a9ec-327a276c995d | note | RESPONSIBILITY: Site Engineer / Site Foreman
12fb1f99-f352-5cd2-9c8e-6940b877aef2 | date | Date Completed:
| checkpoint | 2.20 - Place & compact backfill material around pits
c2bf2dc6-f6d3-54e6-9d37-cd298f1f6029 | note | FREQUENCY: Each Pit
38846dc6-cfb6-527d-b81b-dedaf10e67af | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment
4b6755d3-9352-5896-863f-ee0b9de4779a | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.18
880bb187-7745-5d38-a9a5-314dd5a94576 | note | INSPECTION/TEST METHOD: Visual Inspection
90ac7629-39ec-590c-ba28-be7483712fc4 | note | RECORD OF CONFORMITY: ITP Signed
dc2f5528-6f6d-5653-8eeb-568389539240 | note | WP
28738aab-5d89-548f-b5fc-90ac0b8efb6d | note | RESPONSIBILITY: Site Engineer / Site Foreman
957c9b19-212b-5dbf-9baa-ae101135c96a | date | Date Completed:
| checkpoint | 2.21 - Backfilling with 3% cement stabilised
a974d987-27c9-5db3-8713-101db9e76fa6 | note | FREQUENCY: Each Trench
7bbdc090-a928-536f-a2cb-c6fc42d47eaf | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised FCR with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
68f38afc-75ca-5aa6-ae91-2347455753e1 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.19 (c)
79f18705-132d-5510-ae20-ff394cf5bc2b | note | INSPECTION/TEST METHOD: Visual Inspection
387846f3-d347-5d70-80ed-4f187dcccc5c | note | RECORD OF CONFORMITY: ITP Signed
c0322943-2c19-57da-b779-09e8351f2ba5 | note | WP
dc513974-81a4-52f7-9688-3c09c5b404b2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8f820513-2620-5bd3-8ca3-db50ec71702d | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.22 - Step Irons & Ladders
472db2f0-ea00-5063-907e-fc0e72fe9c1a | note | FREQUENCY: Each Pit
9b90aeb4-1783-59c9-a9bb-41a4a5f4e083 | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0 m deep shall be fitted with step irons or ladders in accordance with AS 1657 and this Section.
42e0f439-3ca2-59b6-95c9-88c059876cee | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.12
67400060-9825-5f18-b093-c52e814b7cec | note | INSPECTION/TEST METHOD: Visual Inspection
c9a8ba17-b650-5ab6-9643-741b670fb04a | note | RECORD OF CONFORMITY: ITP Signed
d80dfed6-06ce-51d7-a736-1081cd4b2cad | note | WP
05f3362f-5987-58e0-a3d4-ef6e6a2293ab | note | RESPONSIBILITY: Site Engineer / Site Foreman
b3b0c000-9388-57b3-874a-539babc101bb | date | Date Completed:
| checkpoint | 2.23 - Construction Tolerances
a4d7fd78-2a31-556d-87c9-3e94ca8a8859 | note | FREQUENCY: Each Lot
b66261c1-8180-5a50-8933-f34ac7f385c8 | note | ACCEPTANCE CRITERIA: The tolerances listed in Clause 610.47 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
7c959603-5160-5e9c-8b1f-781fff03d139 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.19
e9c7dfdc-a19e-54fb-9486-76bb635ebfc5 | note | INSPECTION/TEST METHOD: Visual Inspection
49ec9052-a5c7-555d-9caa-42bdc5201281 | note | RECORD OF CONFORMITY: ITP Signed
dbfc6001-6b38-509b-8821-c13e0e8e46ec | note | WP
f097e294-491c-517c-b2fd-5bb39802acbf | note | RESPONSIBILITY: Site Engineer / Site Foreman
6dbcfda5-0c7b-533b-85f8-dfc0d8873523 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
11c5c22f-c480-5d26-981d-2c4658287145 | note | FREQUENCY: Each Lot
2d2a265c-1b83-5979-b6d9-e35eafdf10fd | note | ACCEPTANCE CRITERIA: The Contractor shall test the bedding and backfill material at a frequency as shown in Table 701.291 to ensure that all materials comply with the specified requirements.
a78ee5cc-9aa3-557f-b442-9bb486a022d0 | note | REFERENCE DOCUMENTS: VicRoads Standard Section Table 701.291
c1543386-4b70-5823-ace9-1270e6d2572b | note | INSPECTION/TEST METHOD: Verify
c309668a-754f-5c6c-94a7-d86d82944aeb | note | RECORD OF CONFORMITY: Test Reports
a1193ab3-98c4-5fac-9e0f-361b79df5deb | note | TP
131ca47b-df80-582d-b4f5-d085c37f2525 | note | RESPONSIBILITY: Site Engineer
d5371580-bba1-582e-89d4-6e14bff269e0 | date | Date Completed:
| checkpoint | 3.2 - CCTV inspection
6affff7f-3df8-5d9a-8d53-f5d4a5b0f61d | note | FREQUENCY: Each Lot
3110e656-fc06-50fd-8a42-195361eb934c | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
5c884636-031b-5ba5-baf5-c63c8754d8ac | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.3
268892ff-8a23-5e71-a720-1543a6351ae4 | note | INSPECTION/TEST METHOD: Visual inspection
c5ab1c90-210d-5cc4-a264-a8ecca3db4ad | note | RECORD OF CONFORMITY: CCTV Report
278ce320-49f3-59e0-afa7-edeb88fb158a | note | HP
67ada8ab-ad31-5f1b-982d-cec81de36330 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a0dab19b-f3ec-513a-8ebe-fdfa592a165d | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.3 - Repairs
ab66148d-e27b-5096-baad-04a078536c23 | note | FREQUENCY: Each Lot
c1d73921-ad91-512c-baec-11b3ab597f27 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
6aa713fa-df40-5b0f-8e6f-0b7c4f743217 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.31
bf0b947d-d133-5f11-95f4-eee4437bb044 | note | INSPECTION/TEST METHOD: Verify
f67aeb5a-1047-55c8-b41e-4174defc7963 | note | RECORD OF CONFORMITY: ITP Signed
207934c1-475b-5c5e-afee-f3f7295a6aa0 | note | IP
2657ad5f-4b38-59b7-9703-6117654166b3 | note | RESPONSIBILITY: Site Engineer
134bff99-88e4-5bc3-b8ff-d34e3d82a864 | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
8f934e83-a7b6-5793-9b6e-4828fc8122e7 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4d8a85e5-df00-52a1-b5e3-dd1c35b11070 | textbox | Print Name:
5162ccbe-c600-5246-99a4-7ba978716daf | textbox | Position:
4b1de4bb-04a4-542f-9a23-0b7facdebf45 | date | Date:
| checklist | ITP-003a - Sub-Base Construction Road Widening FCR Class 1 | itp | ITP-003a - Sub-Base Construction Road Widening FCR Class 1 |  | e7827601-e422-4b87-ac95-6413b7a18127
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
b711b4fc-803f-594b-9ddc-6f0fb30520d0 | note | FREQUENCY: Prior to commencing any activity
09578a7e-7117-5c56-9c83-a3acde27379d | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
a2c14d4b-ba1b-57b7-9668-2c5379ee2b9e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
44919a08-5a51-57c0-b7aa-7a15701f0174 | note | INSPECTION/TEST METHOD: Visual inspection
9c564579-944a-545a-a7a7-bd403771565a | note | RECORD OF CONFORMITY: This ITP signed
5eb9e0f4-4272-5f51-a30f-e79cc059c5c4 | note | WP
304367df-c127-5a60-b1bc-82741537cb69 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c1569626-6be5-5898-b159-dbcdf1937f4a | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
2311dcbb-47f4-5b0d-a821-6fe224a6b21f | note | FREQUENCY: Prior to commencing any activity
1951b716-0e7a-5faf-a12d-28ebc70d402a | note | ACCEPTANCE CRITERIA: Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
f2002156-4741-5a83-a0d2-c33115a4696c | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
f1571a56-a64a-5da5-a70d-aba50e5403ca | note | INSPECTION/TEST METHOD: Document Review
09120203-9db0-58a0-8600-61bea71fb2ef | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
d5782dc5-44ec-5869-b3f3-1977079682f1 | note | HP*
f3e8a7b0-8fd1-5e4a-bcc9-467876aee5cb | note | RESPONSIBILITY: Site Engineer
ca1f01d7-b381-5475-9755-19e6d8906c21 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
9f5279f6-45db-5cd9-92a1-733ac354aa65 | note | FREQUENCY: Prior to commencing any activity
7df80f2a-2768-5c7c-a9d4-901552c8c0f2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
5af994fb-5386-5c3c-a403-f70c9e3e4ff6 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
107b52aa-77fd-540d-8609-23faacb7333d | note | INSPECTION/TEST METHOD: Visual Inspection
58c40735-cb6e-5fd8-aba7-061113251d46 | note | RECORD OF CONFORMITY: This ITP signed
f3d704c8-549f-5dfc-9be1-c9d978a1e562 | note | HP*
9d7ade7e-af4b-59df-85cc-f5b3ce2f783c | note | RESPONSIBILITY: Site Engineer / Site Foreman
e15f136c-d0a7-5331-b6c7-fc7f64918f20 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Transverse Joints
f77c83af-ffbe-5d41-9e3b-7df29b0bbe20 | note | FREQUENCY: Check prior to placing material
39b0e9ea-c876-5839-bb88-d00c679364af | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
f3cb46c1-d420-5f55-9ea8-5386bfbc7a3a | note | REFERENCE DOCUMENTS: Cl.304.08 (a), Cl.304.08 (c)
a1b2b160-c140-5997-88de-6bcd7bddd42a | note | INSPECTION/TEST METHOD: Visual Inspection
211d6580-bfb6-5d25-b87d-594ce9145727 | note | RECORD OF CONFORMITY: This ITP signed off
8409602b-d232-5191-b293-c74eb8147145 | note | IP
6d38672a-1f5a-5099-b9a3-1db498e9ff47 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6ce05148-3308-5b5e-89be-031c6bd48b25 | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
6795b31c-90e8-58e5-9d85-32e959f8991d | note | FREQUENCY: Check prior to placing material
ed9f1012-0e5e-52bf-b3dd-7d2020b33ea3 | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
ea90854f-384f-5be4-9e27-0f49d1bd608a | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
5c5aa8fd-0776-5177-a064-92a9d0d063ab | note | INSPECTION/TEST METHOD: Visual Inspection
2378fb60-e145-5275-af3d-0d29a568a648 | note | RECORD OF CONFORMITY: This ITP signed off
27cda9e5-867e-519e-9cac-1fe8a0aa21d8 | note | IP
ac3789cc-8b7a-570f-be36-1c833545ed58 | note | RESPONSIBILITY: Site Engineer / Site Foreman
724af1ba-760d-509a-9486-27ab28ce064e | date | Date Completed:
| checkpoint | 2.3 - Lot Size
c22ec9df-eaf2-5a5c-9f83-0cb8b9388f9a | note | FREQUENCY: Check prior to placing material
ca56e1e9-2719-5fa6-9c92-9116ec89480b | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
fb8c9f96-4369-5b30-a594-7584ff0ddffb | note | REFERENCE DOCUMENTS: Cl.304.09 (b)(ii) Table 304.121
877029f3-17a5-50ac-818b-f40341783c08 | note | INSPECTION/TEST METHOD: Site Inspection
9df5c1e7-ad51-5bc7-8121-e5cf500b1852 | note | RECORD OF CONFORMITY: Signed ITP
e8c7584d-04a3-5bc1-a7c2-ce5884f2effc | note | IP
bbeb73da-bd6f-5e5d-8c08-e1783246d65a | note | RESPONSIBILITY: Site Engineer / Site Foreman
d7976d09-b2fe-5bb0-9f0a-08d69aee65da | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness
a9fdcc5c-f542-56ea-96d8-191ee9e87754 | note | FREQUENCY: Each Lot
3c7f004f-871f-5a2c-b5ec-19290bd8cfc0 | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
8567d8c6-71f5-55af-877c-7d2fda92fb0a | note | REFERENCE DOCUMENTS: Cl 304.07b
f0ba6c75-18c8-583f-87f5-f4b6628f5942 | note | INSPECTION/TEST METHOD: Site Inspection
e41be137-224d-50f8-a754-84b67bdacc95 | note | RECORD OF CONFORMITY: Signed ITP
2a12b1b9-5617-5b8a-a07e-fe2bb3854123 | note | IP
1c6eaca1-78cc-54f5-853f-65adb0fba351 | note | RESPONSIBILITY: Site Engineer
a71f29b7-63ca-5301-867e-9f1bceec543e | date | Date Completed:
| checkpoint | 2.5 - Proof Rolling
98466deb-0b8b-5784-b2e5-3cf7aba85840 | note | FREQUENCY: Proof Roll each layer
cce9d2b5-a6b0-5516-aca2-a5fc0f755334 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
0b1dd0b9-16c3-5dde-8f68-0085e3e52512 | note | ○ Static > 12T
d8d4fc10-4fed-5c53-9f6e-4df369558ecd | note | ○ Pneumatic > 20T
c6d0c980-8a3a-58ea-a306-9affac69092e | note | REFERENCE DOCUMENTS: 173.03
03331167-9a3f-5507-bebb-7055ed84b0dd | note | INSPECTION/TEST METHOD: Visual inspection
dcf7f23c-d4c2-5d38-a915-5392631592d2 | note | RECORD OF CONFORMITY: This ITP signed off
266f224e-1af0-5215-af6b-3db6761b9573 | note | HP/ WP
3754bb4c-69f3-508c-b42f-611b4dc2bffc | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
a4053e4a-e78d-5293-b7f7-ab2cd176d274 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
bea0c97c-bd30-56f1-bd16-d48dfa2f93a6 | note | FREQUENCY: Prior to Testing
1c9d3f20-0f28-5a83-b147-dda01144461b | note | ACCEPTANCE CRITERIA: Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
8ce894fd-0805-5df6-bda1-d51e990200f3 | note | REFERENCE DOCUMENTS: Cl.304.09 Cl.304.12 Table 304.121
487c9091-9c70-52fc-9df8-04e1c086467b | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
300bf5e9-0f55-52f2-aefd-f0231068cad3 | note | RECORD OF CONFORMITY: Signed ITP
6b2107bc-535d-5ec7-b62f-5fc943b7278b | note | AP
e892746c-8b46-5113-9d52-5f7b01a56f30 | note | RESPONSIBILITY: Project Engineer
48f16204-91eb-5730-a101-02dd540f379b | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.2 - Compaction Testing
1ba7f8b7-7ed9-5d5a-b94c-66499ba0233d | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
03de0bf7-5ac0-53ce-b25e-1a05c4528884 | note | ACCEPTANCE CRITERIA: Modified Maximum Density Ratio of not less than 97% Class 1 FCR for road pavement as per Contract Drawings SD-D8-1 sheet 5
45cbbce0-c8a8-51e0-b78e-aa76db282db5 | note | REFERENCE DOCUMENTS: Contract Drawings (SD-D8-1)
75143404-718a-5d98-9838-5b2d3f11bd35 | note | INSPECTION/TEST METHOD: Test point
b9d0584f-54b0-5d30-904b-11e17ee855ff | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
1cf50118-7a1c-595a-8df5-0c5ce3debac4 | note | TP
d49e246a-3cbc-5152-9fc1-74f542f0a7fd | note | RESPONSIBILITY: Site Engineer
e20660cf-3c14-5279-b8cd-892a65fff683 | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection (Photo attached)
54862296-1348-55a7-84c5-eaa42ec29074 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d2142ecb-6720-5f10-a3f2-0fc4370c23a2 | textbox | Print Name:
147133c3-e8f3-5ba5-92f1-aae4f76d5984 | textbox | Position:
dbafcd44-fa1f-5212-8c0b-9023770f9549 | date | Date:
| checklist | ITP-003b - Sub-Base Construction Road Widening FCR Class 3 | itp | ITP-003b - Sub-Base Construction Road Widening FCR Class 3 |  | 80c352f8-b60c-4785-9d6a-68fcd660a955
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
dd264901-cc34-5554-882f-3bd944f12075 | note | FREQUENCY: Prior to commencing any activity
264bea10-2052-5a17-951f-708f33e00ddb | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
c82cbdca-4af0-5db2-a9e2-243eb7ba694f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c375de51-57c4-532f-bd61-a43491b41218 | note | INSPECTION/TEST METHOD: Visual inspection
bb71baa0-e9b8-545b-9468-5164abf9f3b1 | note | RECORD OF CONFORMITY: This ITP signed
2851f473-96e0-5a21-bf46-4649d4803fb2 | note | WP
5d828f92-628b-5f63-ae44-ea97c9478bc7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5c324705-8a6e-5303-8636-7e50bfb5228a | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
53d8fbdf-2333-5f31-ad4c-5bda31a5419a | note | FREQUENCY: Prior to commencing any activity
9493b9be-59b7-5bdb-80c2-2108a4f0c26c | note | ACCEPTANCE CRITERIA: Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
fb8e79a6-7061-5d7a-a020-409ac0dcd9cb | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
5419d012-1b89-59d0-bdc7-edb1dbb207d2 | note | INSPECTION/TEST METHOD: Document Review
8df1b2d7-4344-5968-86e0-8daf2435283d | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
bf9a2486-c841-58e1-a3c9-2b3d9a765529 | note | HP*
e09027fa-b60f-52a7-8436-e78b0112402f | note | RESPONSIBILITY: Site Engineer
85b20840-f2f1-53ef-97b5-22301f21d7df | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
f74460cf-218c-5dca-b729-e01c12c89449 | note | FREQUENCY: Prior to commencing any activity
e8bf1309-6b02-5dec-8bf2-1bcf4cf082e8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
0d14787a-17fd-51bf-8671-02d89932fd93 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
089f4c23-1c9f-503d-981c-d2e7ce12db72 | note | INSPECTION/TEST METHOD: Visual Inspection
fd91c9f7-6585-59e8-9b8d-65deee48b380 | note | RECORD OF CONFORMITY: This ITP signed
4a65e859-5e6d-5927-9f96-ebc87a9e756a | note | HP*
4426b07b-dc00-54ec-bddf-9327f2493d7d | note | RESPONSIBILITY: Site Engineer / Site Foreman
09ba1f64-54f3-5129-9e1f-3c6715c20733 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Transverse Joints
a51e87af-622c-5a10-966b-9f3e0b9d2837 | note | FREQUENCY: Check prior to placing material
6c0e4a68-2320-5bc8-aa05-36303de1453d | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
fac03789-0ee6-5436-b28b-563d19253db8 | note | REFERENCE DOCUMENTS: Cl.304.08 (a), Cl.304.08 (c)
70f45035-ed70-591a-b344-d1243b6d8a25 | note | INSPECTION/TEST METHOD: Visual Inspection
d03ce2a0-08af-5645-8238-854d1fd162aa | note | RECORD OF CONFORMITY: This ITP signed off
f83c9648-3b95-51b2-b10d-2c1922a68976 | note | IP
0acaffc2-0fb0-544c-8327-766c1a326685 | note | RESPONSIBILITY: Site Engineer / Site Foreman
a4ff5627-1b1e-5efd-8490-e4cd1c99f3cd | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
23e12d33-ce23-567a-b588-ef30f8f9723d | note | FREQUENCY: Check prior to placing material
9c69b88e-629b-5fa4-a303-5210267ba195 | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
8288122f-cfaf-5f82-80a5-8b4c60804ca8 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
51480374-9192-54e7-adf1-5eff4521285c | note | INSPECTION/TEST METHOD: Visual Inspection
67835350-ef42-5b35-a031-f3a3bad42daa | note | RECORD OF CONFORMITY: This ITP signed off
2184e5ff-6395-5a80-92a8-aaeb86edddbb | note | IP
d77cef2e-eafc-52aa-9a20-a4ba4adc6e3a | note | RESPONSIBILITY: Site Engineer / Site Foreman
1f6c3b27-0732-5170-8472-6acebc7bbdac | date | Date Completed:
| checkpoint | 2.3 - Lot Size
8b05b8f9-dfde-533b-a4db-43b3e15ae1e4 | note | FREQUENCY: Check prior to placing material
0b67af17-dc2e-5bbd-a81b-d135d00df90d | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
5a43f5f4-9bf7-5385-9426-e9dd6a537b07 | note | REFERENCE DOCUMENTS: Cl.304.09 (b)(ii) Table 304.121
bb1b3bd8-36b4-5e9d-a32d-f90c5e47f7c7 | note | INSPECTION/TEST METHOD: Site Inspection
59e9431e-58c8-511c-92c4-56d4fb953b71 | note | RECORD OF CONFORMITY: Signed ITP
79685a01-e7c8-55aa-874e-466d433ea103 | note | IP
86cb08f2-1244-5c08-b7fa-fa9ef5754677 | note | RESPONSIBILITY: Site Engineer / Site Foreman
22ee1de4-3679-5c44-bf1d-6082cedc5f9b | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness
a66bdfce-bf55-5a44-904a-4102781500e5 | note | FREQUENCY: Each Lot
11eaf65b-4905-5cdd-a249-18a420909e14 | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
16464eb1-9f2e-5b4a-bba7-f880df2f9ac7 | note | REFERENCE DOCUMENTS: Cl 304.07b Contract Drawing 2022-95 Sheet 02
281b05ef-7770-5710-a01a-258a2ae46ece | note | INSPECTION/TEST METHOD: Site Inspection
d65ab854-0a15-58a7-a2b0-95518ad2de99 | note | RECORD OF CONFORMITY: Signed ITP
de36a954-c73d-5150-9bfc-f84c04283d26 | note | IP
6fb71ee8-b62b-5ab2-ba07-039649702ade | note | RESPONSIBILITY: Site Engineer
6e44f855-0326-5548-b0e6-44f25758c602 | date | Date Completed:
| checkpoint | 2.5 - Proof Rolling
e71ddaba-b187-5d47-b8b7-c63040949877 | note | FREQUENCY: Proof Roll each layer
2dc78e92-b69c-5764-9874-41320cc9e85b | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
869bbee5-1d8d-5317-8125-5d58a885a854 | note | ○ Static > 12T
97558f47-eaef-5f44-8ae8-92efa67c6d00 | note | ○ Pneumatic > 20T
73104400-3783-56d7-bcaa-04282cbdb4a6 | note | REFERENCE DOCUMENTS: 173.03
3e5bf8d4-165a-583b-9ab2-cf7b9a26a186 | note | INSPECTION/TEST METHOD: Visual inspection
26809348-9e0d-5b58-956d-525fa4be9fd9 | note | RECORD OF CONFORMITY: This ITP signed off
01ad1183-9fbc-5ad1-8d3c-bc43d7b0a1d8 | note | HP/ WP
79d87a06-01ec-5894-9186-633edaba6aed | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
74a078d9-525a-521c-91c2-21e7755c181a | date | Date Completed:
| signoff | Request Signature
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
2ce41c9f-9ebb-5761-a9bd-12941eaadc14 | note | FREQUENCY: Prior to Testing
dbb09720-ab53-5cb7-9b8d-71d98f4442c9 | note | ACCEPTANCE CRITERIA: Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
2452b0c8-e7c5-5cf5-b778-b4b35764d2a8 | note | REFERENCE DOCUMENTS: Cl.304.09 Cl.304.12 Table 304.121
7daefb29-c694-55fb-a98d-0de790583915 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
45cc446a-f306-59ae-acfc-c9672ade9088 | note | RECORD OF CONFORMITY: Signed ITP
3a4d2c08-9fef-51c7-92a5-cc2b36b441a8 | note | AP
f847eb36-b9ef-52c6-89da-4d05640b4170 | note | RESPONSIBILITY: Project Engineer
021aef31-d194-59a2-af80-ef44f1b68de1 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.2 - Compaction Testing
504b102c-adef-56ab-9cc2-e4cfdb16b34c | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
1631b533-4fa3-5b06-82ef-52198751dc5f | note | ACCEPTANCE CRITERIA: Modified Maximum Density Ratio of not less than 97% Class 3 FCR for road pavement as per Contract Drawings SD-D8-1 sheet 5
01765627-5107-53f0-8409-4329193c2490 | note | REFERENCE DOCUMENTS: Contract Drawings (SD-D8-1)
24ea25d1-06b5-53f0-8ab2-2482350f5df3 | note | INSPECTION/TEST METHOD: Test point
e7d241b8-b6cc-52b9-8759-2e300117331c | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
056f7744-fcdc-52d1-93cc-7feebd2ea4b3 | note | TP
579e9380-5d58-5c2f-94ce-7295260322f8 | note | RESPONSIBILITY: Site Engineer
007cae29-52d4-58d2-8e52-f67a9555587c | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection (Photo attached)
035db24a-a237-5ad7-ad88-a04ebcbe95fc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
efe91afb-d64c-5c05-a606-df45cdddfd5a | textbox | Print Name:
13ebe277-b4ae-50fe-a015-ca4d89e445f8 | textbox | Position:
a01700d6-dd66-5fe5-a9e1-edc1f5b9bb97 | date | Date:
| checklist | ITP-003c - Sub-Base Construction - FCR Class 3 | itp | ITP-003c - Sub-Base Construction - FCR Class 3 |  | 369aef94-5f5d-46ac-b5dd-43d64640841e
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
823255ef-65f6-5be5-925c-80d191cc063a | note | FREQUENCY: Prior to commencing any activity
335c823e-47a2-5533-beae-7709b95e42c6 | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
2cdf0b8d-9e9c-5c16-87d9-252f39fcfd6e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b8e5f180-8a23-53af-8822-f2d619388a9b | note | INSPECTION/TEST METHOD: Visual inspection
344e0325-046c-5aa4-be43-4cb97114c094 | note | RECORD OF CONFORMITY: This ITP signed
7c9b8ef5-ff60-53d7-8251-2c606070257f | note | WP
79465ac8-28dd-5b08-a140-e39f1a1b3ea6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6b4a6d68-249d-5df4-8a8a-1ee73add63f9 | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
5bcbf0b7-8864-57c8-98f3-40250e3e9615 | note | FREQUENCY: Prior to commencing any activity
e00abe7c-ee8f-579b-8ac4-be0525fedd7d | note | ACCEPTANCE CRITERIA: Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
050fb88f-7479-56b6-935f-bb4ad2e50d32 | note | REFERENCE DOCUMENTS: Cl 812.04 RC 500.02
5a74e656-adf9-5bd3-bdcc-1ab17a2c978e | note | INSPECTION/TEST METHOD: Document Review
68ab3626-e9ef-5be4-ae13-7d52100e5c78 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
705cad47-302c-570c-8102-38298a0d0f49 | note | HP*
1ff004d0-8a3c-5188-9f12-a01575082d6b | note | RESPONSIBILITY: Site Engineer
fcb72167-9a9b-51b9-aa14-76322d227bf2 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
55a3cd9c-3ae2-521f-9e1c-ca09f337e974 | note | FREQUENCY: Prior to commencing any activity
07302d0d-4001-5b66-912e-51c36d95ea9a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
3124e3fa-836a-5b02-8d3c-7d400400329f | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
0724d2f8-f4a8-526a-a969-09f6e8dde7b1 | note | INSPECTION/TEST METHOD: Visual Inspection
906f0a56-7da2-59d8-8382-efe0941cfcdc | note | RECORD OF CONFORMITY: This ITP signed
0359c709-e4a8-59be-b108-f18e3768b6f3 | note | HP*
43df0d5a-1629-575f-92f1-d33fe965debb | note | RESPONSIBILITY: Site Engineer / Site Foreman
c1b847d6-1eb2-5b41-9397-39a06e6300f7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Transverse Joints
86f8810b-875d-56fd-8a4f-d425153ce527 | note | FREQUENCY: Check prior to placing material
a3bfab7e-5237-5ab4-b341-65b60918f7dd | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints. Transverse joints shall be offset from one layer to next by not less than 2 metres.
93ec0cb8-225c-578f-a351-ddf2e192203f | note | REFERENCE DOCUMENTS: Cl.304.08 (a), Cl.304.08 (c)
8c4dcf41-4022-5ecd-8bd3-6c37f96a1e28 | note | INSPECTION/TEST METHOD: Visual Inspection
30859e73-cff4-5290-aec5-8fc1d69b12d9 | note | RECORD OF CONFORMITY: This ITP signed off
4e955302-6d77-533c-8d60-e1862433ffe0 | note | IP
a3664000-bacc-507f-9b13-71d337f193b4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
68587018-35e2-5c2c-a031-09e897b5f10c | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
5af557f6-572f-582e-a00f-23325fc62ee6 | note | FREQUENCY: Check prior to placing material
314b7202-b5ad-5861-94e8-c29fbb23a0f0 | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints. Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
2765321e-cb30-5169-a4b6-85a4fcd8ee31 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
6824778b-c801-56cc-a6aa-a304f9462980 | note | INSPECTION/TEST METHOD: Visual Inspection
22c97e33-feae-54fd-b7c9-aeb69b9d3437 | note | RECORD OF CONFORMITY: This ITP signed off
51a9ec0c-bfd4-5e00-8693-aa92125f7cf1 | note | IP
6431cbe1-14c3-5b20-b575-0a5003e2438d | note | RESPONSIBILITY: Site Engineer / Site Foreman
f19fb88f-0970-5edd-b3d6-78f09298826e | date | Date Completed:
| checkpoint | 2.3 - Lot Size
22d46f49-4347-5a43-b7df-1142afa07c27 | note | FREQUENCY: Check prior to placing material
857e1bbf-c489-585e-ac06-d45740ed8026 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
c04b1d8b-32fa-50e5-af63-0541c66f580e | note | REFERENCE DOCUMENTS: . Cl.304.09 (b)(ii) Table 304.121
5d610d17-250e-57b5-9234-ac227265033b | note | INSPECTION/TEST METHOD: Site Inspection
c45486bf-11a4-5f08-9faa-33848e8ede36 | note | RECORD OF CONFORMITY: Signed ITP
0334e700-4e00-56e0-b710-5ed0ec6f246c | note | IP
b973983b-51ec-535f-b2ed-c0584022871a | note | RESPONSIBILITY: Site Engineer / Site Foreman
03d3d623-94da-598b-b109-a3dc485c556e | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness
eeba5497-4374-58a7-a999-d51787a70394 | note | FREQUENCY: Each Lot
40f246c8-ce83-58f7-8433-8ddea0298724 | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
7f3da001-322f-5d20-aaa6-22d791ea405f | note | REFERENCE DOCUMENTS: Cl 304.07b Contract Drawing 2022-95 Sheet 02
5fb70742-1ae3-5f46-b4eb-df16083bd06b | note | INSPECTION/TEST METHOD: Site Inspection
e5d4082a-654d-5f72-8fd8-bb713bec444c | note | RECORD OF CONFORMITY: Signed ITP
d20c3a1e-eab0-5124-8d5b-6d32899f372b | note | IP
d495ed27-98ea-5f98-92ce-d21be3083cbe | note | RESPONSIBILITY: Site Engineer
ebaf2a76-3f03-5e1a-b28f-b2a8a07b4a82 | date | Date Completed:
| checkpoint | 2.5 - Proof Rolling
e6a22f26-da94-57d9-b4ef-ed736ecc9a68 | note | FREQUENCY: Proof Roll each layer
2106649e-aa46-5949-9fe1-b5ebd6257dc6 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
6397490a-d193-54f5-a66d-52b58a6e50a9 | note | ○ Static > 12T
681ab493-5f21-50c5-b798-617a4af94f41 | note | ○ Pneumatic > 20T
01065861-0709-5a67-8a4f-ba4c8ecf08cc | note | REFERENCE DOCUMENTS: 173.03
402738c4-6f93-515a-b6d9-a320eddc2046 | note | INSPECTION/TEST METHOD: Visual inspection
128d86e5-026c-5550-873b-5bb55022322e | note | RECORD OF CONFORMITY: This ITP signed off
4acc714f-ee8f-534c-8b10-3b0f7bdb4f76 | note | HP/ WP
ac25fe0f-977a-5a2f-80cf-0ce21fb55bd2 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
6127f5a7-dc98-5c72-8aad-5237c538e199 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
4e7556e9-295d-559e-a908-3f5a0612e98d | note | FREQUENCY: Prior to Testing
c9a05b3c-8a64-5aca-86d2-bee88500be84 | note | ACCEPTANCE CRITERIA: Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
0e2ad632-3efe-5ae2-9b9f-57e04cf9e453 | note | REFERENCE DOCUMENTS: Cl.304.09 Cl.304.12 Table 304.121
217dea72-dc5d-592d-9ce9-094afba5868e | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
f1f4af05-fceb-5db4-9a95-f97cad17884a | note | RECORD OF CONFORMITY: Signed ITP
1d25db12-c5d8-533c-994f-606bfd3ef8c1 | note | AP
f3910e85-1679-57f7-a463-bb98427b626a | note | RESPONSIBILITY: Project Engineer
4689b3c8-6938-5a38-9e74-1b39e05a4c0c | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.2 - Compaction Testing
82b58fd3-4a94-5b40-9002-88b3d171d668 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
45498a89-6e18-5951-8e58-50415a93e7d5 | note | ACCEPTANCE CRITERIA: Modified Maximum Density Ratio of not less than 97% Class 3 FCR for subbase as per Contract Drawings SD-D8-1 sheet 5
5060a2f1-5f17-5883-a5d2-526ffa39194a | note | REFERENCE DOCUMENTS: Contract Drawings (SD-D8-1)
563870c7-7d1f-5dd6-967d-9b29ef0e8b91 | note | INSPECTION/TEST METHOD: Test point
c378e88d-f584-589e-aac6-05b9b6e42722 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
a3e8ba71-ed3d-5a64-a594-b7ca38bc86de | note | TP
d68f89de-df77-5618-b412-ea756e666b82 | note | RESPONSIBILITY: Site Engineer
1b673517-1c86-54bf-b162-d2fd8d4c355d | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection (Photo attached)
af340416-ae4f-560a-aa2e-74ec6b3dfcc9 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ee365008-bbea-503f-a2c0-ff3fb3e83df7 | textbox | Print Name:
7c7e82fc-b3a8-5e67-a802-5d05055f2397 | textbox | Position:
67a4dacb-4f86-5dff-a662-8dee43db4d40 | date | Date:
| checklist | ITP-004 - Kerb and Channel | itp | ITP-004 - Kerb and Channel |  | b01be915-66a3-4305-95f7-097d4c253e78
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
4acf4db4-85d0-53dd-83a6-14258bce601d | note | FREQUENCY: Prior to commencing any activity
21071434-d8f1-5112-a281-3509fbbc032a | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
862a83bf-2796-5421-931e-04ff91346c34 | note | – using the correct and complete set of drawings
176ccfc4-b8b5-58fa-a417-49248fb96199 | note | – all drawings are the latest revision
eca96db0-8bb7-548d-8c0a-f43c88b0a9d5 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
af77b83b-d3ae-5f4e-a33c-5b533f30717f | note | INSPECTION/TEST METHOD: Visual inspection
353abd60-89f1-5d6b-8e6b-6ba181f2fe0e | note | RECORD OF CONFORMITY: ITP Signed
6dd0035c-e2aa-5b50-b3fb-467900c1b533 | note | HP*
b0ebbb48-8fea-5867-b143-003efa13ed99 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
07d05a41-9941-5638-a017-acc0da7e978d | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Implementation of all measures and controls
15058fc3-2bad-558a-9809-8cc65b77be06 | note | FREQUENCY: Prior to commencing any activity
9544bb38-075a-507b-92ad-b425217836dd | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
e815f62a-cb99-5f67-bf99-2ca964a68142 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
9f0efe45-fd75-58df-a845-d4f92282db59 | note | INSPECTION/TEST METHOD: Visual inspection
771f1599-2e4c-5dd2-bdd4-88de386c51df | note | RECORD OF CONFORMITY: ITP Signed
cf76cfe1-cd8f-5a33-bc1f-f73bdb11a915 | note | IP
e8e8d70d-5b30-5d8f-a972-18137adc552f | note | RESPONSIBILITY: Site Engineer/ Site Foreman
339ec417-dab6-5122-932d-3f124437e926 | date | Date Completed:
| checkpoint | 1.3 - Mix Design
1d9b11ad-cfb9-5229-b5ed-f73d7d6caa91 | note | FREQUENCY: Prior to commencing any activity
ea213bd2-2d69-5991-bd39-2909d48d3eda | note | ACCEPTANCE CRITERIA: Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
ded85c47-7f49-5d5c-9340-41552ee96e85 | note | REFERENCE DOCUMENTS: AS 1379, Cl 703.07, 703.05, 703.23
eefc794c-95b8-5c15-87fb-3d6a9ef15073 | note | INSPECTION/TEST METHOD: Verify
e73edc6f-f805-5236-82ae-1d9f36a52ead | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
2651335d-98eb-5a56-ba15-19808ee46aca | note | HP*/ WP
6d557368-967b-570f-a18c-d5cec2521870 | note | RESPONSIBILITY: Site Engineer/ Superintendent
9f33fc26-b5f9-5ca4-af1c-7a79a5f50bdc | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
47e499ba-3300-503a-9910-7dcdb9177620 | note | FREQUENCY: Prior to start
65457499-b84a-5283-8804-b2efb388b0d3 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out.
779d5b9b-2f08-51ca-9fb7-2d1d78d7d410 | note | ○ The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work.
5dc3640b-4239-50b0-80b3-deaa7241082e | note | ○ No survey/level pegs to be removed by any persons until completion of works.
469aa5e5-8001-5459-987a-386fae567634 | note | REFERENCE DOCUMENTS: Cl 703.17
4c890916-3d76-51eb-b490-c27643307abf | note | INSPECTION/TEST METHOD: Verify
5f5b3b9d-800a-5923-9f70-882228e25ce0 | note | RECORD OF CONFORMITY: ITP Signed
c62d771e-98fa-5330-a380-e786c1026cca | note | HP
ab1c87f9-68fe-56a3-9ee0-649a5bf97799 | note | RESPONSIBILITY: Site Engineer/ Superintendent
4a0bae53-5261-50ff-ae0b-80d929574fc1 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Temporary Drainage Provisions
94e3f158-cb68-507b-baf1-b59702f6efa9 | note | FREQUENCY: If Required
7f8da91a-8422-52cf-b7e4-074b6a265f86 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
d77a5c6f-5afb-5b85-a6a7-69bb77d659d0 | note | REFERENCE DOCUMENTS: Cl 703.18
2d6215e1-be08-5444-b629-f8c9db6c6f98 | note | INSPECTION/TEST METHOD: Visual inspection
503d4d7b-34f5-52d8-bd56-4606e041ff4a | note | RECORD OF CONFORMITY: ITP Signed
1d4fe8e8-4ec5-5851-a8fe-327a3fb78323 | note | WP
04795bd0-c913-50a9-8a9d-672fd61724f7 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3d4c9f0b-b66a-52ec-b055-9463ca4021ad | date | Date Completed:
| checkpoint | 2.3 - Bedding
62905640-91b4-57a1-8413-ea5e8384d779 | note | FREQUENCY: Each lot
784259c6-b389-5b50-b2cf-e88bf43bbdff | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
e5881019-9487-5558-bbc0-3f4fccaacaed | note | ○ 20mm Class 3 shall be used and compacted to a thickness of not less than 100mm.
3c47d6aa-aaed-59fd-aeb8-a75b907e1c1f | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
3740dd58-b415-5f19-96ee-bb3c0fab64e5 | note | REFERENCE DOCUMENTS: Cl 703.21 IFC Drawing SD-K1 Sheet 06
0ef309df-28b5-5421-b58c-444fdbde1d8d | note | INSPECTION/TEST METHOD: Visual inspection
d101de7d-ba72-53c7-8e68-180025a38a77 | note | RECORD OF CONFORMITY: ITP Signed
0e25f4b9-9599-5022-8821-dd1076f72ccb | note | WP
d00bec9d-125b-5df0-a3dc-b186b0b4bb0f | note | RESPONSIBILITY: Site Engineer/ Superintendent
dff36e93-2095-5bd5-9edd-fd64a8a218d0 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Pre-concrete check
e4a12277-33bb-5dfc-94b7-0313fd54ef31 | note | FREQUENCY: Each lot
beecb81b-4001-5b4e-8ee4-6fdbe413d36b | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
1b64357e-0d55-5da8-b63e-5f65f13c5f3e | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
177e869d-5ee3-5624-a6a5-c620b26999c5 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
2c11bb22-6703-5d7b-b3f7-eb4b2239ab22 | note | ○ Formwork - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
69083568-52a0-5e3a-91a1-6e541a35cc1e | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
647d108d-70fc-5af6-a4b0-ce32572257fd | note | REFERENCE DOCUMENTS: Cl 703.08 610.17(a)(b)(c) 703.12
3390025d-6d7d-512b-a3c5-e96ccae5c64a | note | INSPECTION/TEST METHOD: Verify
243aba71-a494-5a86-9440-8e02dfa16773 | note | RECORD OF CONFORMITY: ITP Signed
5c2755e3-a669-5a1b-8ddd-90ba661908f2 | textbox | ○ Ambient Temperature |  |  | °C
709a269d-e852-5255-b102-5c414f82ca4d | textbox | ○ Concrete Temperature |  |  | °C
467a3145-dadc-5d62-a99e-8e0533af554a | note | HP*/ WP
30b82ea3-8a26-54b2-8332-8caaf6aeaf9b | note | RESPONSIBILITY: Site Engineer/ Superintendent
d711b67f-38ff-530f-8caa-8f3e19abd431 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Kerb Concrete Mixture/Strength
3d8dc82d-c087-5f59-8695-78690833896a | note | FREQUENCY: Each Lot
13b19547-b3db-5550-86fd-fac780267576 | note | ACCEPTANCE CRITERIA: Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
becb598b-f448-5bd6-9aa5-5c64e061bb3f | note | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete
4c4bc31d-69fb-5b64-86ae-26343aaf84b9 | note | REFERENCE DOCUMENTS: Cl 703.05(b)
ef8cce71-9d08-5395-9ee4-0b1020b998ac | note | Attach photo of Concrete Docket
f2de8cfc-1a8c-57a5-b11d-9536ab1b4eca | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.6 - Finish Surfaces
0538b4c9-2a11-5583-8542-25f30f06ff22 | note | FREQUENCY: Each Lot
85aae7a6-443e-5e7d-9282-6a6d81f67700 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
7a8f27a7-172b-5d37-856c-a833269235b6 | note | ○ Concrete to have a neat appearance and uniform colour.
9cff47ca-cb78-51f6-b501-9a89ca74dcce | note | REFERENCE DOCUMENTS: Cl 703.25
23c72d48-e0e2-517a-b15d-e6ae296690bd | note | INSPECTION/TEST METHOD: Visual inspection
de38c5f8-1cb4-5f9c-b50e-f5e6fde2e4f8 | note | RECORD OF CONFORMITY: ITP Signed
b3796feb-6efc-5fda-84ac-1bb226df6af7 | note | IP
7e1c6422-8728-588c-8b07-3aeae08ae66b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
164bbc00-0287-5e38-bf3a-b631ab39b6bb | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.7 - Tolerances
ab0548c7-91b2-5785-af6c-7f17a500a2ed | note | FREQUENCY: Each Lot
70cfd985-6556-507c-8635-411b578f3174 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3.
ef9419a0-6afe-5ed0-ab0c-f216d9a69d45 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
e909b83c-8d73-5378-9ccc-041ba74501e2 | note | REFERENCE DOCUMENTS: Cl 703.15
7d578d47-2bdc-5be0-a9f5-53d807d423b1 | note | INSPECTION/TEST METHOD: Verify
b19b5f85-8c11-5f76-b53c-db968003dffe | note | RECORD OF CONFORMITY: ITP Signed
30b5c40a-66a3-5038-b7f8-c065c912a1a2 | note | SCP
ddf18cac-f417-5ea6-b94d-f0297fc5cb76 | note | RESPONSIBILITY: Site Engineer/ Surveyor
6022ca24-b38c-58c7-9b7a-e939a7ed8e46 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.8 - Joints
7fde9ae9-25ec-547f-a3c9-bc82da49332f | note | FREQUENCY: Each joint
cfb6af25-3a51-56d6-839e-7163659d8960 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
05eaf8b6-ffb2-5497-aa3c-e55489a39738 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
4aa29344-066a-5ae7-983c-ab9aca61e4bd | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
88267233-6905-5cfa-b2cb-e910128663ad | note | REFERENCE DOCUMENTS: Cl 703.26
15bf70f4-1237-5216-b444-93675678ff03 | note | INSPECTION/TEST METHOD: Verify
b8b41044-7e29-5bb8-8583-36b40d5145f9 | note | RECORD OF CONFORMITY: ITP Signed
0c056258-774d-5c04-9724-87a6b3f1942c | note | IP
5e7d6a41-e753-5415-be35-25335a81a71e | note | RESPONSIBILITY: Site Engineer/ Site Foreman
a609ce60-a05e-5cc4-8de4-4c8b9a38309f | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.9 - Curing
63d4fd0b-b7d3-53f4-98a3-ccb9a29c4300 | note | FREQUENCY: Each Lot
669b9569-4ca6-5527-bb9f-5591c63aee41 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete, with the exception of concrete edgings which shall be cured for a period of not less than three days after placing the concrete.
d1b0abb7-fd63-53c5-969f-3fdb242b6979 | note | ○ Concrete will be cured by method of wet hessian.
98f007ac-196c-5b6f-857e-3655982da5ad | note | REFERENCE DOCUMENTS: Cl 703.1
70979072-2770-5168-9963-d8df34cd042f | note | INSPECTION/TEST METHOD: Verify
bad1a805-cb64-527c-92ff-38d8a9e73641 | note | RECORD OF CONFORMITY: ITP Signed
9506a58b-9fdb-5edc-a21e-53fdb847ba77 | note | IP
3cb565d7-57af-5890-86ee-273cd93f8c0d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3a07d5b3-89cc-57b8-9399-6659acecbadb | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.10 - Backfilling
0c8cdd73-9e5e-5f7d-acc5-41931f8f4bf5 | note | FREQUENCY: Each Lot
3c31f0b9-dbb8-504e-9f62-71fc81f5480d | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
cebb4105-124e-5484-9c11-a195b33a2bd6 | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
d46d79f7-1d2f-5965-8fe7-04400df6461c | note | ○ Layers shall not exceed 150mm compacted depth.
a6eb681b-bdb3-5221-a31f-28c2f9f2817f | note | REFERENCE DOCUMENTS: Cl 703.29
21762d1a-66bb-51f4-a820-67afb8482a5b | note | INSPECTION/TEST METHOD: Verify
a67dc9e6-031d-5c7b-9557-d6549d65f0b4 | note | RECORD OF CONFORMITY: ITP Signed
f72d1810-8276-55c7-9095-ffefec970790 | note | IP
9d642b5f-0b28-5eb0-baec-0a8b81b3a403 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c389d8c0-4527-5ac0-ba63-12d3be09b8f7 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.11 - Cracking of Concrete
6dcf6001-1a51-52f1-a551-d4cc4c8bb493 | note | FREQUENCY: Following Completion
635bbd05-14a0-50b2-ad67-a336df427604 | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance.
f74ef5c8-b1c5-5670-9fcb-3427db8daac8 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 – Repair of Concrete Cracks, as directed by the Superintendent.
61395598-bab7-54c2-b6a2-da0be5f337b0 | note | ○ For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
a077fb92-5d55-5ed2-bfb8-2c0eff6f4f52 | note | (a) constructed on compacted bedding;
0f56ccb0-2c40-5d7f-afd7-bfc50f82d09c | note | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
db761660-3775-5d3d-aa28-e93583fb40b8 | note | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections.
4e9971a5-2872-570f-a507-1c11208f6abc | note | REFERENCE DOCUMENTS: Cl 703.30 Section 687
1050489c-02f3-5e3d-9a5c-6e3b6481f39a | note | INSPECTION/TEST METHOD: Verify
4e0d580f-1a64-5243-92ef-ee6c8adaddfe | note | RECORD OF CONFORMITY: ITP Signed
34d3cae7-cfc2-54ef-a3b4-f746ee2dd65a | note | IP
68cbf9c4-d6b7-5a5b-81a1-95d00bef0226 | note | RESPONSIBILITY: Site Engineer
fb75eeba-9ba2-52d6-8ec5-7b0a009da417 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Survey data captured for as-built purposes
5ecc02b8-c430-5188-afd3-22ea759e7b40 | note | FREQUENCY: Completion of each lot
cc691c7e-523f-5871-934d-ec0eda3ca19e | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
83ead9e6-02a6-5931-a888-faea41a2eb33 | note | ○ As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
7f6c6a80-ebf0-5bfb-af0c-473df94e9c4a | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
25ee2c86-8149-5720-a41b-35d174ca5267 | note | INSPECTION/TEST METHOD: Document review
1ac5b7d8-7f51-5960-8f3e-e133e79f1a38 | note | RECORD OF CONFORMITY: As-built survey records
d78b6743-cb63-5ab8-bd1d-cc9d9cb2530c | note | SCP
1eb4c548-c656-5b0c-a2f7-2d5605566dc0 | note | RESPONSIBILITY: Project Engineer/ Surveyor
2fb0397f-c549-5308-877d-960790368f50 | date | Date Completed:
| checkpoint | Final Inspection
83f363f7-1ec8-5527-ad43-4cf9e230e102 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d318fbb6-13c7-5c56-b1d6-2b51b75f5a95 | textbox | Print Name:
50757137-7081-58c8-a119-fc63b2bab169 | textbox | Position:
e86e1d45-d643-53d5-8189-cd491af5c7f6 | date | Date:
| checklist | ITP-005 - General Concrete Paving | itp | ITP-005 - General Concrete Paving |  | 52a289f8-f857-4c0a-94bd-bb24e8d285a5
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
9dfa0b1c-a60c-53ba-aec7-10d2afdf912f | note | FREQUENCY: Prior to commencing any activity
fe8dc595-66af-5be6-af71-494404e7cedc | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
4899ec1d-f94f-5f35-a512-3541d0b5ccf1 | note | – using the correct and complete set of drawings
9011a2e2-6c30-5d87-baed-f9313665b839 | note | – all drawings are the latest revision
9a93bb3f-2b9a-57c6-8327-56f28dc20b52 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b84a9870-f088-55a5-a6a2-44a3a1a34bbc | note | INSPECTION/TEST METHOD: Visual inspection
6dcc8564-3d21-5064-971d-52925a130929 | note | RECORD OF CONFORMITY: ITP Signed
07d19dff-f9a9-56ba-a157-8bc1a74365be | note | HP*
d933909e-b080-54d4-8323-0390e4348f4d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
7176d55b-09d4-5cbd-8e3c-4bf92682ca9e | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
882d1c81-3988-5daf-9377-6688a1902547 | note | FREQUENCY: Prior to commencing any activity
e975764d-5030-5e29-a6fd-f9c6e91d90f3 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
40c50c9c-bc4b-5b9e-a870-6a0b5cc659c8 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
827f55f1-8c51-5e83-b712-1d4d7b1c26de | note | INSPECTION/TEST METHOD: Visual inspection
9bcfa0d6-938b-50ed-a91d-fb536d5f6ccc | note | RECORD OF CONFORMITY: ITP Signed
bcea0d53-573a-5e8e-b952-a8263efeea74 | note | IP
351fe95e-235e-5d6f-9771-9ef99de15f83 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
7787bab9-8b36-54ca-84d8-c7c5f5a0ad99 | date | Date Completed:
| checkpoint | 1.3 - Survey and Set Out
f8cbd436-fcc5-5433-9170-1db97e9ccffa | note | FREQUENCY: Prior to commencing any activity
5cb28167-a6f5-5fcc-8800-b0bb2b5edf96 | note | ACCEPTANCE CRITERIA: Current design model available for machine control.
d906978e-59a6-51af-b38d-9a163550db32 | note | ○ Clearly mark limit of works, chainage, offsets, cut/fill level etc. (if required)
c60308e9-a690-52ad-93ab-1e4589d4e58b | note | ○ Design drawings must be IFC status
79282539-f955-5fb7-815a-182be35e0739 | note | REFERENCE DOCUMENTS: IFC Drawings
8ea9f488-c9cd-5595-8c65-0d0beecb49f5 | note | INSPECTION/TEST METHOD: Verify
9b86855e-6bdc-5b7c-ab97-79b1a8ffdd7e | note | RECORD OF CONFORMITY: Site Inspection
7e64c733-949c-5e6f-afdc-9e9839f39496 | note | HP*/ WP
8e741214-5c2f-507f-8357-68af284fe6d5 | note | RESPONSIBILITY: Site Engineer/ Superintendent
08cff51f-e102-5f30-934d-37f14a78fdb8 | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
50fae5f0-ab1a-5589-8c10-de1e3c76f03c | note | FREQUENCY: Prior to start
7ba08ee7-4197-51d2-9a91-f6396334ead2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
f17a94a8-314e-5d39-b3ea-a323bce8c90a | note | REFERENCE DOCUMENTS: Cl 703.17
22635647-a654-5f19-935a-eabe86875a43 | note | INSPECTION/TEST METHOD: Verify
5424d148-a035-5bfc-a0fc-6f239eaf721b | note | RECORD OF CONFORMITY: ITP Signed
c32ef0f1-388c-5edc-972e-98354c063c8e | note | HP
c22be85e-c460-56ef-9e46-09aea317b565 | note | RESPONSIBILITY: Site Engineer/ Superintendent
02966aac-58b8-5864-b529-d20b6d50ba46 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Excavation and foundation
433589b2-bb18-5530-94d1-548c7fa0a09a | note | FREQUENCY: Each lot as required
3eaf03b6-0cc2-58e7-8bdf-336806b84b6d | note | ACCEPTANCE CRITERIA: Box out to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
df4480cc-4a7a-5dc3-9be2-6bed81639379 | note | ○ Foundation true to grade and cross section as shown on the drawings by filling and excavating as necessary.
2493a7eb-59b5-59cf-acee-9c80ac6f7829 | note | REFERENCE DOCUMENTS: Cl 703.20, Cl703.21
a6c27b84-79da-54a7-ae55-b67d65065655 | note | INSPECTION/TEST METHOD: Visual inspection
2c0af8a9-b128-51ab-af0c-383d89039924 | note | RECORD OF CONFORMITY: ITP Signed
3c0c0296-32ee-58b8-b8ed-37f8e69c0a14 | note | WP
9e6024ec-1881-5d94-a9bf-5fa02c5bca4f | note | RESPONSIBILITY: Site Engineer/ Site Foreman
d7a3a740-16e2-5d4f-aaab-47bddc698df9 | date | Date Completed:
| checkpoint | 2.3 - Bedding materials and compaction
fa14db51-e393-5e7c-aa2a-5508b4d8428b | note | FREQUENCY: Each lot, Prior to concrete placement
f4983830-bc9a-52b9-bd71-100dac435f8c | note | ACCEPTANCE CRITERIA: Bedding material shall be compacted size 20mm Class 3 Crushed Rock or Class 3 crushed concrete.
eaf37fb9-a72a-5a95-92b5-0adb429639ab | note | ○ Immediately before concrete is placed, bedding shall be moist but with no free water on the surface. Comply to Table 820.041, Table 820.071.
61de496d-fa01-5296-a672-59b03c105cd4 | note | REFERENCE DOCUMENTS: Cl 703.21 Table 820.041, Table 820.071, IFC Drawings - SD-K3-1
90aa834c-f9e5-5f30-9ee4-7dd6e605ce37 | note | INSPECTION/TEST METHOD: Visual inspection
3e8c73a3-e0e9-5081-86ec-90f6ff315c0d | note | RECORD OF CONFORMITY: ITP Signed
a5736778-19c6-58c5-add4-4ac3ba3830e0 | note | WP
c00d4c6b-2677-5bb0-b748-a733026e435d | note | RESPONSIBILITY: Site Engineer/ Superintendent
bdc5eb87-ad7c-5af4-9f8b-ef61605fe0e1 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Bedding depths (compacted)
cc691b50-b814-540e-ad5e-0a01f2d93216 | note | FREQUENCY: Each lot
fc84f26a-a348-5408-a5ae-46bfe8baf7a4 | note | ACCEPTANCE CRITERIA: 1. Edgings:
c4e45aee-8eed-5ba4-b823-b45caeb1b912 | note | ○ When constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
a1a76dd9-56b8-52c6-b88a-a38abea9bad6 | note | ○ When not constructed over pavement layers, bedding ≥ 100 mm compacted thickness.
b473cd86-68e3-5a99-a52f-ddfb05314a83 | note | 2. Shared use paths:
b2a8a015-229e-51fe-966b-1f0989c1db3c | note | ○ bedding ≥ 150 mm compacted thickness.
117373b1-750c-5cde-a466-fe9b72716345 | note | 3. Footpaths & Driveways:
e0f1464a-e128-5c70-a511-5716281b0790 | note | ○ bedding ≥ 100 mm compacted thickness
e60001ad-e2b4-516f-9862-efc66623519b | note | REFERENCE DOCUMENTS: Cl 703.21 (a), Cl703.21(b), Cl703.21(c) IFC drawings
9dc9160e-4f27-5bff-a132-1be157dbd24b | note | INSPECTION/TEST METHOD: Visual inspection
6f07b703-5754-5347-b701-3def03d7c531 | note | RECORD OF CONFORMITY: ITP Signed
0f2b0a7b-94f5-5cdb-8303-3a55ac21d970 | note | HP*/ WP
13100e62-dc05-5e69-ac35-e3f851801c4d | note | RESPONSIBILITY: Site Engineer/ Superintendent
3cf05e0f-5c82-5f77-a172-ec3ea71e204c | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Ambient weather for concreting
6619ba79-4d42-5707-996f-187094d0d528 | note | FREQUENCY: Each Lot
a759d951-007b-583a-9a9b-2d4f65dbba3a | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of Clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for Restrictions and treatments to be applied for concreting in hot, cold and wet weather.
5e4e4752-9a86-574f-9513-46fb50f04b49 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
1bc10116-1206-5dbd-b3a7-86d1d1b229b6 | note | ○ Ambient temperature not to be less than 5°C and no more than 35°C.
cf274603-a2ad-5fa4-8787-f8c379383e30 | note | REFERENCE DOCUMENTS: Cl 703.013 AS/NZS 4671, AS/NZS 4680
6645a120-6d1a-5f3f-bfcc-b08371da5027 | note | INSPECTION/TEST METHOD: All measures in accordance with relevant documentation
a765838a-009e-53b8-b184-97278f470cf1 | note | RECORD OF CONFORMITY: Verify
912ac415-f15a-554e-9637-d287ae710a11 | note | WP
e98448b6-dcfe-57dd-90ba-aae30902defa | note | RESPONSIBILITY: Site Engineer
91f1f83f-5195-5739-abec-8966a58c1458 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Steel reinforcing grade and placement
4ea2a302-bbbd-56a7-ac8c-744c4ddd62e6 | note | FREQUENCY: Each lot
3866ae28-3cb9-54d2-8f86-9c2b4c295fbb | note | ACCEPTANCE CRITERIA: 1. Steel reinforcement shall comply with the relevant requirements of AS/NZS 4671
480af7c0-41ec-5d59-bc68-315022f35170 | note | 2. Concrete is to be reinforced by F72 mesh and with a cover of 40 mm as per the drawings SD-K3-1.
4b2ab755-65f3-538a-9a46-4dee82c5afe5 | note | 3. Support reinforcing using either concrete or plastic chairs.
856d3ec7-aff9-50bd-8930-f399b9514472 | note | 4. Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used as support.
00b58865-31fd-5ee7-aed9-de68e44b18a6 | note | 5. Galvanising where specified shall be in accordance with the requirements of AS/NZS 4680.
94b86c32-53c6-5afc-863a-0808e07ff213 | note | REFERENCE DOCUMENTS: Cl 703.013 AS/NZS 4671, AS/NZS 4680 IFC Drawing
54cea9e3-399d-53a2-9608-272de13c53aa | note | INSPECTION/TEST METHOD: Site Inspection
78aba398-ea7f-516c-a319-7c37b173b94f | note | RECORD OF CONFORMITY: ITP Signed
7521634a-859d-5626-93e3-5c2052841c9b | note | WP
936c3aef-451a-57f9-9f3f-df5599aa58f7 | note | RESPONSIBILITY: Site Engineer
af67645d-068d-515b-a40d-7cb56d599481 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.6 - Formwork
2cad4065-eb1e-5053-ae5c-a88e5f7f19b5 | note | FREQUENCY: Each Lot
11e134d0-2b66-5acf-8f97-46a8aea7b15f | note | ACCEPTANCE CRITERIA: Materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610. Joints in formwork shall be constructed such that loss of mortar is prevented.
43b1d84e-a761-54bc-9657-67bc0176632a | note | ○ Formwork shall not be stripped until the minimum times specified in AS 3610 Table 5.4.1 have elapsed from the time of completion of the placing of concrete. The minimum time shall also not be less than:
9d4feb31-2171-5f60-ba9a-7ff7ae7b9eff | note | (a) 2 days for vertical formwork on external surfaces; and
a6193cf8-9ad7-501c-8e23-b65361ab7703 | note | (b) 1 day for vertical forms on permanently hidden surfaces.
d901fc56-eb2d-5071-a7cd-38afea6682b7 | note | REFERENCE DOCUMENTS: Cl 703.12 AS3610
2de34158-9838-552a-b917-1757abec92f9 | note | INSPECTION/TEST METHOD: Visual inspection
e515c212-8c61-508b-a116-6c12c295a0eb | note | RECORD OF CONFORMITY: ITP Signed
c0a17f2d-aba2-5d4d-8a9a-6b2fb9309c38 | note | WP
624d5078-4d89-500a-a659-a980c9e8fbbb | note | RESPONSIBILITY: Site Engineer/ Site Foreman
0cb708d1-e14d-557d-9b0d-6aacc9fcb641 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.7 - Concrete Placement and Compaction
6a413523-f8d3-573f-b905-85605932b810 | note | FREQUENCY: Each Lot
e7fb199d-9208-5004-8836-d4c762886d73 | note | ACCEPTANCE CRITERIA: Concrete strength to comply with detail on IFC drawings and AS 1379
27ebfe53-e3c6-5965-b23f-dfab9dd1e778 | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment’s and into corners of formwork or excavations to produce a dense concrete free from voids. Workable concrete mixes are exempt from vibration requirement.
be202886-8301-5e36-8d62-d1c135951d30 | note | ○ Concrete testing frequency in accordance with 610 requirements.
bc1773eb-56c8-5288-9e05-4c84d6aba547 | note | REFERENCE DOCUMENTS: IFC drawings Cl 703.01, Cl 703.08, Cl 610.16 AS 1379
42e0dae0-06e8-5a58-becd-5c033336e5a2 | note | INSPECTION/TEST METHOD: Visual inspection
1c60ee62-8f6c-5ded-a477-b7dab5cb5aa4 | note | RECORD OF CONFORMITY: ITP Signed
04f9eec6-10e7-503c-96bb-e3866385fcda | note | WP
6be6eb21-5bf2-51bd-bd32-8351f3318b02 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
07b09f67-2caf-51ce-9c88-827123b3c492 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.8 - Surface Finish
6e044f8f-eb93-552f-a4ca-1b2a669b4cfe | note | FREQUENCY: Each Lot
099df5a1-2ee4-579b-a628-a9eaf82e7bf7 | note | ACCEPTANCE CRITERIA: Exposed surfaces shall be treated as follows:
437ff27b-4be7-55fc-912c-73201f40f19d | note | a) Edgings
a29f1141-632b-57c9-9adb-4233ddc3ce8a | note | ○ All edgings rendered to a thickness ≤ 3 mm, within 30 minutes of placing or extruding concrete. Mortar shall consist of two parts of fine aggregate, one part of cement, and sufficient water to produce a mix of suitable consistency.
70213de0-eee4-5c6d-ab53-d99fd2b06433 | note | (b) Footpaths, other Surfacings and Shared Use Paths
b7da9a12-9655-5fbe-8a2d-14bd946ef3e8 | note | ○ Concrete compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top, struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
22449a33-0191-5744-b9f2-655af917ed52 | note | ○ All edges sharp and clean, and bullnoses regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
8a0259d7-005c-598d-8869-c90563eb9d12 | note | ○ Permanently hidden concrete surfaces have a Class 4 surface finish.
ea6033d2-35c6-5eb9-aac7-c60b609a2f3c | note | ○ All other concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces.
8e66a9ab-321a-570f-b8d7-9c47e78501fc | note | REFERENCE DOCUMENTS: Cl 703.25
22024e62-4d81-5e7e-9e1c-ffc866859b26 | note | INSPECTION/TEST METHOD: Visual inspection
e236f99f-a23d-55b4-a266-acddb6895155 | note | RECORD OF CONFORMITY: ITP Signed
2073021b-6673-5a40-9383-93ad0a9c3c6e | note | WP
c79435e0-c628-5026-a00b-0ea04ad70bf9 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
9990bf92-6575-55ee-bf1c-20c8953bca8d | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.9 - Joints
a2c8ce58-894f-5029-89a0-f8bf46019a31 | note | FREQUENCY: Each Lot
80cf8fd7-efbf-5b43-a4fb-122d6145626d | note | ACCEPTANCE CRITERIA: Transverse joints constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
c2134938-420c-5d30-98ee-75ba2b4835a2 | note | a) Edgings
54132ccc-1f8a-59cb-bb0e-2190dccaf024 | note | i) Traverse Joints – constructed at regular intervals ≤ 2.5m. Templates for edging using fixed forms shall be removed as soon as practical after finishing work. Resultant slot in edging shall be tooled to a depth of 20mm, and produce a groove ≥ 5 mm wide, following which a vertical cut shall be made through the base of the groove to a depth ≥ 50 mm from the surface.
4c96a319-705f-5b92-a7bd-09d9ad17aa6d | note | ii) Expansion Joints – placed at junctions with bridges, shall be 15 mm wide and filled with cork/bituminous impregnated particle board strip extending for the full width and depth of edging. Fill placed in position before concrete and held during placing of concrete.
9922ee04-b9aa-5365-9f90-3b6026d59b63 | note | b) Footpaths
2015ec91-749e-5f33-b1d6-4afe26b1b5d6 | note | i) Expansion Joints
16ec48ab-4d1f-5786-a0d7-c7fc6ed229f6 | note | ○ Expansion joints placed at intervals ≤ 10 m. Expansion joint shall be 15 mm wide, filled with cork/bituminous impregnated particle board strip extending for full width and depth of paving. Filler shall be placed before concrete is placed and held in position during concreting.
ab7b2b7e-f595-5d8c-9f2b-ade5fe8f4495 | note | ii) Control Joints
7995fe10-f377-5d02-9591-a69bcdb29224 | note | ○ Control joints at least 25% of paving thickness deep, 5 mm wide at 2.5 m intervals within 4 hours of placing concrete when air temperature is between 20 degrees and 35 degrees and within 24 hours when air temperature is < 20 degrees.
b7eecff8-d2ad-589e-a2eb-b6da180aef4e | note | c) Between concrete paving and shared use path
f7f2554f-52b1-5a51-b198-b21e62e598fb | note | ○ Except on narrow medians (< 2.0 m wide) surfaced full width, bonding between the concrete paving or shared use path and the edging prevented by painting the back of the edging with bitumen, or by a bituminous felt material between edging and concrete paving/shared use path.
514e2144-dd93-554a-a052-10aa37a6c394 | note | REFERENCE DOCUMENTS: Cl 703.26 (a), Cl 703.26 (b), Cl 703.26 (c)
4ae62e63-3638-52be-86d9-ba49b28830f6 | note | INSPECTION/TEST METHOD: Visual inspection
deb6fd05-1e8c-55c4-8fa0-b935f17a7e57 | note | RECORD OF CONFORMITY: ITP Signed
71ba2577-1272-50a1-8ba8-4b2e7277e6d1 | note | WP
b773991a-4280-533e-bae7-3be38bb7f02e | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ab07767a-5e51-51bb-b604-b4bbe32abd95 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.10 - Curing
dc63a4d3-f0dc-5b1a-9ae6-b007d30efd0b | note | FREQUENCY: Each Lot
9ea2cdc4-8f95-5684-b104-de75242075d9 | note | ACCEPTANCE CRITERIA: Match existing fixtures to within 5mm (pit covers, etc).
e7aa8cb3-1ad7-5647-98c0-37fdaeabafa0 | note | ○ Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point.
1bf181c1-b942-5d80-9a2e-b3928864ede7 | note | ○ Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm.
57a55eab-b39b-52e8-a4bb-d0b434848679 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges
0c5c3529-56e2-509a-80ca-5c87ac9e3dde | note | REFERENCE DOCUMENTS: Cl 703.10
c4aaa64d-6361-527f-8e0a-6b51b78b31d7 | note | INSPECTION/TEST METHOD: Verify
b300d4e2-3c3e-55d3-85a2-9f3a164b85a5 | note | RECORD OF CONFORMITY: ITP Signed
4741acf5-0be0-5655-9396-d9f2b478f549 | note | IP
3b52d40f-cba1-58cc-a272-ad8dcd746c5d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
26308ca5-453e-5954-850a-db5a59468b5c | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.11 - Tolerances online, level and shape
c02ca50b-aeb9-5945-ac20-57cd28d878a6 | note | FREQUENCY: Each Lot
2e033f1a-40dc-5661-940a-863c1ed7f156 | note | ACCEPTANCE CRITERIA: Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point.
03950c8b-3b7d-596c-a0c9-436937d5079d | note | ○ Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
5723f4b8-3a0a-539b-83e1-6e70d1b6e822 | note | REFERENCE DOCUMENTS: Cl 703.15 (a), Cl 703.15 (b), Cl703.15 (c)
9e503135-a108-5622-ab60-ea67dbfb1429 | note | INSPECTION/TEST METHOD: Visual inspection
737cdcdc-5344-5df6-8ccb-29fb1dfbb842 | note | RECORD OF CONFORMITY: ITP Signed
25a39c57-720b-5caf-9459-77a78038387c | note | IP
e5ef65c5-13dd-51ff-a472-075b1c26d9eb | note | RESPONSIBILITY: Site Engineer
ab8564a1-6d6b-5ae7-8ef9-43dd4d417f25 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.12 - Concrete repairs
84dd10d6-05d1-58d5-a340-bffda56a6003 | note | FREQUENCY: Each Lot
8a6bd171-d422-50c0-9944-a472ed47076d | note | ACCEPTANCE CRITERIA: Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
4c9dcb69-f152-56cc-9079-bf7b3792e581 | note | REFERENCE DOCUMENTS: CL 703.08
780a81f0-5a29-57b9-8f44-f96fa68aa9c2 | note | INSPECTION/TEST METHOD: Visual inspection
d6a6398a-9369-579a-93bd-39770b02b919 | note | RECORD OF CONFORMITY: ITP Signed
f66cc6b8-e407-5417-8651-479a8d7e3ed0 | note | WP
8ca7b58e-7d4c-5062-b7b7-20da2bc8aabd | note | RESPONSIBILITY: Site Engineer/ Superintendent
c87bf22b-22b6-5ffa-9060-0a222e8c5222 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Verification and Lot records complete
de99e6b2-5e9a-579e-b6c2-5299f5bc8ac5 | note | FREQUENCY: Completion of each lot
a7b9f6d5-ea03-53ca-8b3f-648334d9c71e | note | ACCEPTANCE CRITERIA: Completed work checklists, inspection and test results and contractor conformance records progressively and permanently saved and stored as soon as possible after they are received. Completed lot records are transferred to the Quality Team for final record verification prior to being closed
284befea-3e7d-5ee0-ba12-3a7e1bfe72a1 | note | REFERENCE DOCUMENTS: Test Certificates, QA Plan
a144e6e5-353b-5720-8382-ebdb7dfd711f | note | INSPECTION/TEST METHOD: Document review
eadfd9dc-3f16-5add-9ba8-025aaea91aaa | note | RECORD OF CONFORMITY: ITP Signed
2a9e311c-bacc-5499-91ca-96aeb95cacbc | note | TP
7c6eba6d-4b27-5a0c-88b6-7805a871cf8f | note | RESPONSIBILITY: Project Engineer/ Site Engineer
e219d346-6e27-50c0-918a-68c786aa6539 | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection (Photo attached)
eb9cf821-081a-516f-b0df-8da57a8b4dbb | note | Attach photo of concrete docket and finishing before submission
438ff4c2-92ab-5371-a2ad-53cffb5b16f5 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
8bac8e66-ad18-5586-82af-8fb48ce84883 | textbox | Print Name:
74a4d878-cdd9-57e6-a585-b78a9b63daa8 | textbox | Position:
fc30e707-536b-5143-8a5c-0683338dea62 | date | Date:
| checklist | ITP-006 - Hot Mix Asphalt | itp | ITP-006 - Hot Mix Asphalt |  | 8e270947-6e32-4009-b58d-2d9e8a44db21
| section | 1 - Construction Works
| checkpoint | 1.1 - Submission of Mix Design
1fbdc192-7ffb-5985-9e7e-377343771a66 | textbox | Type |  |  | Asphalt
3a78645a-afc9-547f-986e-025f6d89b805 | textbox | Nominal Size |  |  | mm
211f722a-1266-567c-bae5-630ca302db0a | note | FREQUENCY: Prior to commencing paving
fbedba76-85a6-5c68-8664-3cdd2b275a3c | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix.
53c13f62-01c1-5247-9af3-f98e1a2ddebf | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
749215b5-af30-58e2-8ad0-3a57ebcbf459 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
55d3395b-3d12-59cb-a0ae-67395f9073ba | note | RECORD OF CONFORMITY: VR approval, Completed ITP
fd344c38-9841-550b-94ea-8588a58e8989 | note | HP
16f1cb56-2291-5615-b355-7594026dfa1f | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
8a6762c7-f523-507b-bca4-dd869eda969f | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Implementation of all measures and controls
eb7008dd-bc5f-5a3f-bd80-e4fc01225bc6 | note | FREQUENCY: Prior to commencing any activity
3dc6676e-3ecf-5f93-9ff4-17f0808d9bdb | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
3e4a114b-8146-59df-ac52-0ddf8323108a | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
d957db18-9c5e-527b-b0de-3139910a944f | note | INSPECTION/TEST METHOD: Visual Inspection
e38af462-c74c-57d2-91a0-0c37531ef315 | note | RECORD OF CONFORMITY: This ITP signed off
97c8e374-985b-585b-812f-ed2aab8b5532 | note | HP*
882c6404-1ca9-5b44-858d-646da6e2e81a | note | RESPONSIBILITY: Site Engineer / Site Foreman
980d76c2-1baf-50a0-a245-d8b84af3fc47 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.3 - Site Inspection and Base Condition
1ac19419-1667-5767-8f68-53f61071d52e | note | FREQUENCY: Prior to commencing paving
5a254854-85e9-50f3-be4a-8976169e7926 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
b987fe6b-a466-5405-88e6-18662560dbf4 | note | ○ Material and compaction test certificates conform for pavement
9bfda02a-e05f-5a7b-8dd5-0212bc6b469a | note | REFERENCE DOCUMENTS: 407.14 AS2150 10.1, AS2150 10.3
b8c1a5bc-de07-5900-9fed-98fe5b8e3d9b | note | INSPECTION/TEST METHOD: Visual Inspection
610706b3-2c02-5ba7-922c-cc102077123e | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Base Course Checklist
ce1446e6-db45-5a2a-88f1-c23a406b91fe | note | HP
865ee840-5b50-5d88-ba2d-2936f570bc82 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
1edce017-59a8-5a99-9225-7537373964a8 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.4 - Dryback
2004202b-3010-5e7b-a03f-717121b35e18 | note | FREQUENCY: Prior to commencing paving
aae9f732-597d-5aa4-a45c-55d15b2bb958 | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
1c93fdf6-6ae3-5233-a226-ca8b3ade6b3c | note | ○ 6 randomly selected test sites per lot required
2f557825-c43b-5d44-9873-1c2a5310d5bb | note | ○ If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
1329ea55-1d5a-559e-bf61-9a766ef639fe | note | ○ If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
8669dabd-cd12-50cd-ab34-9625e22146ba | note | ○ Testing schedule in accordance with 310.03 (c)
8359ea12-360e-5624-a88c-d22b4b52310c | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b) Table 310.031, 310.03(c) Table 310.032
64c85721-43fe-5f4e-b770-155282667295 | note | INSPECTION/TEST METHOD: Verify
18499b8c-324b-5806-8b15-007455880b54 | note | RECORD OF CONFORMITY: ITP Signed off
0a4d760c-1588-5542-ad11-4d058b0d6555 | note | TP
58794149-601a-52a4-b6e0-3af6f02166a5 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
68b064dd-3264-5e20-9ed0-320f17675baf | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.5 - Ambient Conditions for Placing
69757931-6c71-5fb8-9baa-31a7d300a369 | note | FREQUENCY: Prior to commencing paving
c31da1ee-f2ad-5cf9-abfe-39b9426792c6 | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
237904d9-d327-5d6e-876a-8953b75d7618 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
19fab8e9-c99c-50c5-ae89-6ada60fa6756 | note | REFERENCE DOCUMENTS: 407.17(a)
b2a2a9fd-1b10-5cda-81bb-3712a3d9ca5b | note | INSPECTION/TEST METHOD: Verify
93e783a0-481d-58b3-9b5e-d89d9479527a | note | RECORD OF CONFORMITY: Thermometer
d96d4387-6f06-5ad8-9050-968b77d7263d | note | IP
1f752aed-02e2-5e34-9d6f-147bfbbe3ebd | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
04898c58-4574-5cfd-90b2-c8f2392651c9 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.6 - Planning of Joints
2b4f2fe2-b456-5c05-935d-d35df94f548a | note | FREQUENCY: Prior to commencing paving
1128cece-ea68-50d9-a716-938942c7d440 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
3b63bb12-2b25-55f6-9b87-6b0c3777ed60 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
25848811-745a-5ad6-9aae-9e8e4e7bd000 | note | ○ Longitudinal Joints Offset from layer to layer by at least
7127a11a-74ed-510d-a1cc-2dd8ee362ae4 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
5d3271ca-b098-5d71-9697-09decb8f9787 | note | REFERENCE DOCUMENTS: 407.21 IFC Drawings
2db808a4-77c5-5f2d-8e72-c7af752cd3d6 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
0e2f50da-439b-5cbf-97cf-6a700b65a9d1 | note | RECORD OF CONFORMITY: Paving Plan
14efc4b7-0fd5-5265-944d-0b931e3d3731 | note | WP
4e47f5cb-4aea-587e-a731-4a4c0c7cb62c | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
1a813cfd-99b2-559a-8b0e-eeef93196ab7 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.7 - Longitudinal Joints with existing Pavement
b8c501cc-8dce-56f8-ae16-54298ed3ea55 | note | FREQUENCY: Prior to commencing paving
79caa03f-90cd-5e95-a705-fb56fbab31bb | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
c81eafcc-de59-587a-aa1c-51765e6d0400 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
fa6ada4c-aa76-56df-a132-cf86ae484720 | note | REFERENCE DOCUMENTS: 407.21 (c)
474f6841-5a8d-5030-9c27-00e5ff7b9af4 | note | INSPECTION/TEST METHOD: Visual Inspection
5e37a9cc-72a0-5926-904e-5fc913000176 | note | RECORD OF CONFORMITY: ITP Signed
f822c950-1abd-5abe-9dc9-8e065d1d89a5 | note | WP
ed085894-9c76-53e7-ad94-470d6ee501de | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
29b3245d-656d-55e0-be96-ee251d182c1d | date | Date Completed:
| signoff | Request Signature
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Frequency of Inspection and Testing at the Mixing Plant
43cd2b01-a63d-52ea-b7b3-8eab87384c97 | note | FREQUENCY: As per Table 407.151
57cefd0b-b5c4-5547-a1da-62ab03fea8b4 | note | ACCEPTANCE CRITERIA: The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product.
cc7b4a60-4c56-511e-9d6d-0405a72726b5 | note | REFERENCE DOCUMENTS: 407.151
fb42450b-d5a6-5021-a214-9dc116538fb6 | note | INSPECTION/TEST METHOD: Test Inspection
a30c054e-69b3-587a-b20a-9b66cebeadd4 | note | RECORD OF CONFORMITY: ITP Signed
d5f89b46-0085-52db-ac3b-b46405757743 | note | TP
5909c8e7-60af-5dc7-8fab-ce76603a9b62 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
9c4ae2f5-fabf-5170-94d9-00f76b45bd68 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Tack Coat
b5799577-0584-575c-935b-97278dc8c867 | note | FREQUENCY: Prior to commencing paving
113f85a9-e1da-5b80-b4a5-7b6d05c94b11 | note | ACCEPTANCE CRITERIA: As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed.
549c4401-715e-5bc9-9743-d9753ebd666e | note | ○ Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm.
f30e0685-a4f1-5262-a93c-0f0e0a1ded6d | note | ○ Tack coat to be sprayed on existing asphalt joints.
156f793b-10d6-50f9-8b77-6e337cdf3fe7 | note | ○ Tack coat must be allowed to turn from brown to black before paving.
a585a353-f754-5c48-bb57-a5d1786655c1 | note | ○ If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
9197d5f4-8d57-5c29-9981-3885af41e028 | note | REFERENCE DOCUMENTS: 407.19 AS2150 11
0a3c65ff-c0c1-5375-bbb3-d8b28f3bb6bf | note | INSPECTION/TEST METHOD: Visual Inspection
222e7bb2-e461-5344-a0d1-37f7b2b97722 | note | RECORD OF CONFORMITY: Spray area
35388d96-5541-5bf3-81b2-241242afb0ef | note | WP
9b72a53a-fc8c-57fd-a5b7-a023280555e3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2cd525fc-5e49-52f7-a318-a1aae4670e60 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Commencement of Placing
89208b88-44d1-5e98-bd01-ba3e93bde3f1 | note | FREQUENCY: Prior to commencing Paving
11f58d4f-719b-5e46-a548-f205b1323282 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
79d6ad6a-eda7-5d93-9442-f77c652d9f98 | note | REFERENCE DOCUMENTS: 407.23
c4f830ec-0605-504b-9d10-7ea504d36332 | note | INSPECTION/TEST METHOD: Visual Inspection
f9199b29-8de0-53f9-aea9-06a25d096531 | note | RECORD OF CONFORMITY: ITP Signed
feabdb25-bedf-5eae-b182-68c9eb48ff33 | note | HP
9955e159-2279-5cc9-bcd0-64c7dd72acaf | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
58f4a209-05aa-5390-bc57-042d2316c0e5 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Mix Design Confirmation
ba39c1e3-a601-5a9c-a213-d224fac5e070 | note | FREQUENCY: Each lot
73f8c0cf-b6ae-5faa-bcb3-bb74f2bdd6ab | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
1bdf4535-a62c-530d-bb6a-566f22f2a25e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
76fc8bd6-9890-50b5-90ad-ab6b5fc723e6 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
99510df5-3d6c-5472-9aa3-682c4bf6cbc4 | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
c10f6999-b2c8-5bcc-85e8-3afb8613f570 | note | HP*
150dd8f1-1021-581e-b49f-e044ad45a50f | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
117da3ed-b4f8-53bf-b0ee-c50375d060f2 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Delivery of Mix
5b703761-b64e-53e7-913d-e3e5e0298b29 | note | FREQUENCY: Each load
7d56c26b-dedf-5649-b934-491ef95936a9 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
e7a9b8fe-9073-5764-b858-e460f53fd973 | note | REFERENCE DOCUMENTS: 407.11
724984e7-c86a-54e7-a79c-cf1d11a321d4 | note | INSPECTION/TEST METHOD: Visual Inspection
52b95f95-ea0b-519f-bf3a-78a62549c935 | note | RECORD OF CONFORMITY: Delivery Docket
1f9561d8-7623-5364-b57e-e226c79f9d3c | note | WP
e1ceb99f-0b5f-5a66-8f0a-672daf530d06 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d78c4113-cbd0-5174-8e5a-8904300f72a8 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.6 - Traceability
c306062f-b193-5a61-87d5-b699268cb352 | note | FREQUENCY: Each lot
d939a8d8-3d0f-54e5-8c8c-6e941ff4dab0 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
ac640425-958c-553f-95df-74b649c75386 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
035ebc65-0e5f-5960-91a6-2195c5063c88 | note | INSPECTION/TEST METHOD: Verify
a93a2a30-0e99-5ea4-8c14-47bdb6e1e01a | note | RECORD OF CONFORMITY: Daily Lot Record
f4b0d7cc-dc45-5e82-9d43-628616c950cd | note | IP
9a0e6c0e-ac69-5e40-b65e-a499ac18c88e | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
54dac80e-9e20-5c14-92ba-3be5d948123e | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.7 - Layer Thickness and Level Control
3df90887-ac3f-57d2-ac4a-f5210a24090d | note | FREQUENCY: Regularly during paving
4b5d1af5-3b0a-5a4b-8de1-1487ab29ec5b | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
307dda03-fabd-514f-8634-0d95fd58a8d7 | note | REFERENCE DOCUMENTS: IFC Drawings
2b4bbc25-df51-55f1-b746-94c9417fa09e | note | INSPECTION/TEST METHOD: Verify
730af56b-d2eb-5faa-914a-064360122459 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
4168f0da-ba25-57d1-88ae-c49477e46ba2 | note | WP
6676df6c-b81b-5b64-bdd6-a572e71c813d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
c7430d43-2415-589e-b237-fbd573d9b8bc | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.8 - Paver Stoppages
e6b6c3be-edad-50d4-a61b-77ed2ed4a08d | note | FREQUENCY: If paver stops
72ce359c-32bb-5fdd-9ddf-cc1ae4ed93d0 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
8477823c-754d-56f7-a369-c0c96d125c41 | note | REFERENCE DOCUMENTS: 407.25 (c)
89389233-1ad0-52a6-8ccb-ad40c6a2668e | note | INSPECTION/TEST METHOD: Verify
ad2914fc-0ab7-5cf9-b3d5-a35e4ee8c1e3 | note | RECORD OF CONFORMITY: Thermometer
0eb16373-0498-5e93-8067-759496404bb8 | note | WP
a61df1d1-19ba-5f3d-a0d4-29d7e7a8e671 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6ceea884-597e-5669-b748-29d2b6ee2ebe | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.9 - Surface Finish of Wearing Course
5ff7345f-905c-5db8-9140-30ac71bb8791 | note | FREQUENCY: During paving and after final roll
43b57ce2-d10d-53d8-ab54-da324e6c1c86 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
a4b62b51-7701-5429-a59b-8caa56693ad2 | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
e2f1bea4-6314-5972-9112-dfd4fdac2d56 | note | INSPECTION/TEST METHOD: Visual Inspection
8d1aaa66-344e-57ec-ad21-7ac7274315b3 | note | RECORD OF CONFORMITY: ITP Signed
a2348ed7-0b1a-5dc1-9574-56e8307858cf | note | WP
b824a4de-0806-5c29-8990-7cdb1bf34498 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
4ac4bec6-09b1-5e20-83f4-8bba086e95b8 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.10 - Kerb and Channel
2c289372-b2d4-5612-bf12-d3b2c5756cd2 | note | FREQUENCY: During paving and after final roll
23f0af71-bb15-5c9c-bf7a-95ea232b0f19 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
4a5c11cd-2778-5777-b1ff-f18943cfe057 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
1c839ff5-3ac8-5d8c-ac77-39017b31cb2d | note | INSPECTION/TEST METHOD: Visual Inspection
7f3db558-5041-5500-a4be-fd1523de76b5 | note | RECORD OF CONFORMITY: ITP Signed
13714e27-d594-50cb-a668-938ebb5fd27e | note | WP
0989cffb-1e6c-5a71-8ed9-1262ee40a13a | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
74c13b99-909d-5a71-8e2e-f797c1ac08c3 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.11 - Alignment of layers not placed against concrete edge
ce2080df-250d-58b3-ba0c-1a5dc36efb4f | note | FREQUENCY: During paving and at completion of work
d5d43f8f-58de-5be1-b375-065cacb834cc | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
c0c29d98-0e28-5e16-8c4f-744abd223875 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
5fea8852-b8ed-5256-99bd-8ca21148e30e | note | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
783edc0b-d430-563d-b791-807e5a6336e5 | note | INSPECTION/TEST METHOD: Visual Inspection
fb620a1f-dbaf-5edf-9dab-00d6421a0102 | note | RECORD OF CONFORMITY: ITP Signed
b3447d44-f944-5ca7-b318-347f3c12677c | note | IP
43c1e984-bc51-51df-b71d-557dcd954879 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
3ca50d8a-6875-5bd3-aadf-01cad6ea70a5 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.12 - Width of layers not placed against concrete edge
05f6ad58-8eb7-5a3e-8ed6-e5b9d4a9c2a7 | note | FREQUENCY: During paving and at completion of work
f3edf0c5-2e8f-54f1-a473-f4667d62e421 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
8babf2ba-bfc6-59d9-b91a-2bfc9a5c838b | note | ○ The average width over any 300m shall not be less than the design or specified width
b0b14e44-eb7d-5149-ad5e-7442348eba3f | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
5f816ff8-b13a-5a3d-8076-19967f99d37a | note | INSPECTION/TEST METHOD: Visual Inspection
2797a66a-f4e7-55e2-9f34-0dbce9206324 | note | RECORD OF CONFORMITY: ITP Signed
cc4b55c3-91f7-5071-9d86-8d1c63d9e068 | note | IP
08a5367a-88a2-5523-87d2-230e670b1650 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b4903727-46f7-5118-9f5a-d66627ab15a4 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
a45e8fa4-52e8-5262-a3a6-411361c91f76 | note | FREQUENCY: Per Lot
d91d51f7-8503-55d8-ad72-a6a2cea03261 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
a497c52c-cea1-5292-a40e-923b29ce13d2 | note | ○ 94.0% or greater Accept lot
bfbfcf26-443b-5338-b463-0a7593750a69 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
acf35c2f-48d4-5485-a080-eef22328ed71 | note | REFERENCE DOCUMENTS: Table 407.271
c257074a-80bc-5ea9-8c29-1172c4472b71 | note | INSPECTION/TEST METHOD: Verify
ba870e8f-4b6a-55c8-b8f3-5a3c1b664795 | note | RECORD OF CONFORMITY: Test Report
fe42e9e1-0057-574c-b83b-20fdd76e7121 | note | TP
0945e5fa-9245-5676-a3a1-d87664bef238 | note | RESPONSIBILITY: Site Engineer/ Lab Technician
c7baf01c-c18f-5837-b186-b35bb72410ca | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.2 - Level Conformance
6aa0cda3-6d00-556b-84a8-7bfdbd75e361 | note | FREQUENCY: Per 4,000m2 at completion of work
ca20906c-709c-538e-989d-a455522b6f81 | note | ACCEPTANCE CRITERIA: Scale B
d7f7f8b7-2a6d-554e-8cf1-53dcd7ca1079 | note | Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm
d3669b3d-fb09-55b1-ac6f-0ebd73dc6384 | note | ○ Minimum number of measurements per lot is 40
ba605747-f1a3-5153-abdc-f13b1631c99b | note | (ii) Kerb and Channel
135de963-490e-525e-ac01-0bea91eebaaf | note | ○ Refer to Item 2.10 of this ITP
cf020510-24bf-5d45-9337-83ffe4814eb9 | note | REFERENCE DOCUMENTS: Table 407.293, Table 407.292
171a7dd7-f2bb-58ad-adad-3bd772dece4d | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
65ada317-879a-5dd1-87ff-6d7a8f066830 | note | RECORD OF CONFORMITY: Survey Conformance
8f52af4a-2a95-5353-8425-216a3d712918 | note | SCP
5b65085c-d6fc-513b-a009-e30aab8b53ef | note | RESPONSIBILITY: Site Engineer/ Surveyor
2e479b1d-8ebd-5e91-820d-9ff3e167cc4e | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection (Photo attached)
87832722-e051-5b34-8cb6-bb5fbe7732f1 | note | Attach photo of Asphalt Docket and finish surface before submission
a0a7efa8-3004-54c3-ace4-b30342855a84 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
24b9cd22-1b74-572f-a11c-542b5ecbcfd7 | textbox | Print Name:
438aeb3f-7667-5b3a-a9df-c56981502183 | textbox | Position:
ae8474fa-c261-5dcc-923c-28ab9ddde5fe | date | Date:
| checklist | ITP-007 - Pavement Markings | itp | ITP-007 - Pavement Markings |  | ff78f8e5-d9ca-4369-b4e4-4ebe7d54a0b9
| section | 1 - General
| checkpoint | 1.1 - Check for correct documentation
1e3fe707-2747-57d0-b4e3-407545b2107b | note | FREQUENCY: Prior to commencing any activity
2d975673-695f-5752-a225-36b4b1ce544e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c19bcd6c-334b-565e-a43d-ee50339aa6bb | note | – using the correct and complete set of drawings
254a73a4-2121-5db5-afd1-af284eb6aba0 | note | – all drawings are the latest revision
8518a4c8-8a45-5b7e-a1d0-767e99d50fd2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f857a35e-ef28-5a50-ae47-b3c199af633f | note | INSPECTION/TEST METHOD: Visual inspection
0f0f4ea4-fe28-59c1-b8ec-3dbcb494c607 | note | RECORD OF CONFORMITY: This ITP signed
b7d9d54b-c0bb-584d-b59e-d1e3382c7633 | note | HP*
b0919216-6226-56a8-97ef-7d541b34d779 | note | RESPONSIBILITY: Site Engineer / Site Foreman
8d4931ba-3ec0-5af2-8bbb-18334a0950fe | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Line marking conformance
d279207b-8523-59c8-a72e-d12f785aaaca | note | FREQUENCY: Prior to commencing any activity
b44b1376-5754-511d-aef7-7445b81ae37c | note | ACCEPTANCE CRITERIA: Materials to be used must conform with the specification
52939369-d4e1-54ac-a389-f76b0b11ce7e | note | REFERENCE DOCUMENTS: Cl 721.A05 IFC Drawing
763d51a8-2c2e-5cf5-b337-14071a182f21 | note | INSPECTION/TEST METHOD: Record Review
d276442d-1b8c-52b8-8325-c9967d333057 | note | RECORD OF CONFORMITY: This ITP signed
12475ae4-e89d-5a94-8416-ab8dbaa1408a | note | IP
96cc7af7-e2e0-58a9-8d32-fe428a4d8820 | note | RESPONSIBILITY: Contractor Representative
eb2a8fea-02a5-5689-9251-35ffdf56ede1 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.3 - Site Preparation
9271ffe3-5975-594a-a610-0c35dfc0e259 | note | FREQUENCY: Prior to commencing any activity
524aabf8-3413-52f6-98e5-8e22bff998bb | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings
7eff477c-7db6-570e-ab37-66ecaa2019ef | note | REFERENCE DOCUMENTS: Cl 721.A06
2b38d992-5d6c-5444-8083-fbe186aaea2d | note | INSPECTION/TEST METHOD: Visual inspection
fafb3e42-dae4-5efa-b0ea-4410a0ce8ab4 | note | RECORD OF CONFORMITY: This ITP signed
ade33ead-2369-5e50-8254-363e0275a730 | note | IP
1d10b2ef-f0a7-5c93-8dee-07d517450efa | note | RESPONSIBILITY: Contractor Representative
2ee21cce-822f-524b-901a-715c3a781aff | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.4 - Set-out of Pavement Markings
d187359d-de3e-53a7-ac3e-064ac5b292cc | note | FREQUENCY: Prior to commencing any activity
48a1aa09-f734-536e-b55e-a48236db326c | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
552887ec-8fae-51b1-b6eb-b0d7712c77b3 | note | REFERENCE DOCUMENTS: Cl 721.A09
ec82af28-410c-5845-b2ad-f8b84460c589 | note | INSPECTION/TEST METHOD: Visual inspection
386ef792-f800-5378-b865-c29edbb5a28c | note | RECORD OF CONFORMITY: This ITP signed
d1ca708d-c4f6-50be-aba4-74f5fd01fcdc | note | IP
4784ae0e-59f2-5346-930f-2abecb30b0c8 | note | RESPONSIBILITY: Contractor Representative
478ade9f-7408-5913-824a-e4a495e23cbe | date | Date Completed:
| signoff | Request Signature
| section | 2 - Pavement Markings
| checkpoint | 2.1 - Acceptance of Work
ee53f4f5-fcc7-5dcf-b068-f3e559891a70 | note | FREQUENCY: Each Lot as required
aa07f1be-8f92-5e28-b3bd-30de0a123b63 | note | ACCEPTANCE CRITERIA: Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
c2ed11ec-f80c-5566-ad5a-9206ed536f92 | note | REFERENCE DOCUMENTS: 721.A12
91860dc3-f6b0-5417-afd6-9d40dce90b12 | note | INSPECTION/TEST METHOD: Visual Inspection
88a7eced-9aaa-5f1b-b2d3-e2af3e136953 | note | RECORD OF CONFORMITY: This ITP signed
08febdb1-501a-54a6-99cd-8a5176239bdc | note | HP
0a21a602-0016-526e-9a59-b918a85609d5 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
7548ac6c-7243-58c3-8f9d-65225399e66c | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Position of Markings
16e70135-9a11-527c-bd4a-bfe0673497dc | note | FREQUENCY: Each Lot as required
49346c79-1df2-54ff-92e1-c080704d0a0d | note | ACCEPTANCE CRITERIA: All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03.
9dd8f343-85ce-5b2c-b460-f9737f47a693 | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
9d19178f-58da-5a7f-ac09-a4356d7b31d6 | note | REFERENCE DOCUMENTS: 721.B05
966a0386-7a45-58e0-8ef8-8417fe8c634a | note | INSPECTION/TEST METHOD: Visual Inspection
f4d5fdee-c9c3-5aee-9761-4792d1f8eeb1 | note | RECORD OF CONFORMITY: This ITP Signed
1e17f07e-b7eb-5063-818b-530424c36028 | note | HP
feedf948-f970-5dc1-8e26-1c9a5de54fa4 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
acd51e7d-23ad-570c-b155-f8e808743615 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Installation of Linemarking
af2a4760-bba8-597c-90dd-df73a06a66c1 | note | FREQUENCY: During Construction
b4dd834d-db65-5de9-b088-10deb0296f24 | note | ACCEPTANCE CRITERIA: Line marking installed as per the IFC drawings
9f1b3e30-d6a9-597c-b285-60a051c68311 | note | REFERENCE DOCUMENTS: IFC Drawings
e03da82f-fb2f-52d2-9e04-b7860de4a346 | note | INSPECTION/TEST METHOD: Visual inspection
f1c6d327-5678-54ac-a984-65a95224d824 | note | RECORD OF CONFORMITY: This ITP Signed
89799be8-6d54-50ce-bc23-ccfe83fc272b | note | IP*
ae76761b-621a-5487-a350-9e650e431abd | note | RESPONSIBILITY: Site Engineer / Site Foreman
b1317423-9065-501c-a4dd-5d4b5245c5e7 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Sign Installation
| checkpoint | 3.1 - Completion Inspection
6be96dab-19bf-559e-8be7-6a2070b3498d | note | FREQUENCY: Each Lot as required
e73a234a-4d5c-5c68-9804-cdf0c6fe3902 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects.
da1983a9-c082-524d-9892-9ab31d2888a3 | note | ○ Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles.
3e788b7b-ce92-581e-b024-baa8e15eae19 | note | INSPECTION/TEST METHOD: Visual inspection
0d6f664a-dd59-5a60-82ca-7dc5e9d89229 | note | RECORD OF CONFORMITY: This ITP Signed
68323bc1-8fd4-5a3f-9382-cd0aee748262 | note | WP
27e27656-139c-5326-885b-fa89e4fb99b7 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
53a74876-020b-5daf-941c-471667a7f033 | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
2cb4089f-b245-5cdf-84ac-cf65bf80fc6e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f3eb1132-ef81-5a17-8916-bf79272b9d9e | textbox | Print Name:
f2bb555d-cdb0-54ae-9076-42dc08465f4f | textbox | Position:
eaf6a4db-762e-5852-8182-8d582c9b5d0c | date | Date:
| checklist | ITP-008 - Landscaping - Irrigation | itp | ITP-008 - Landscaping - Irrigation |  | fa939fa6-c96e-4649-a55a-d6052a566a60
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Pre-commencement meeting
0aa97620-d429-5877-a5c3-e66b243c1abd | note | FREQUENCY: Pre-commencement meeting
4bb8f018-2b99-5123-9d12-154eac5519ef | note | ACCEPTANCE CRITERIA: Hold a pre-commencement meeting with council's representative prior to commencing any landscaping activities
72b6dae5-537e-5026-9d84-0e68edbd3543 | note | REFERENCE DOCUMENTS: IFC Drawings
66a48ba6-eff0-5dbb-8060-d0c395789f4a | note | INSPECTION/TEST METHOD: Verify
d244e97b-72e6-57a9-99a5-f9387b2d8d51 | note | RECORD OF CONFORMITY: ITP Signed
dd1b572d-eded-5d13-864f-e56950e06abd | note | HP
833cc907-8009-5418-98ac-effe776bd866 | note | RESPONSIBILITY: superintendent/ Site Engineer
9bc8256c-a6ac-5738-ad75-b6fa75792d1a | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Check for correct documentation
29703db1-5d9e-5967-a94d-6fe7561f5b50 | note | FREQUENCY: Prior to commencing any activity
00eea3ad-e6c5-5e96-b9f4-1e9e9dc2179f | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
3357a972-8f62-5c00-87eb-5e7b66d75218 | note | – using the correct and complete set of drawings
e5c77aaf-57d7-5afe-a0a3-c15fa802419f | note | – all drawings are the latest revision
84035350-951c-52ed-bc10-c52ca1a1fda8 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d4a027f6-28a7-57e3-ace3-50f04dd45753 | note | INSPECTION/TEST METHOD: Visual inspection
c4cff4eb-02c8-5f71-9c01-f9dc830bc198 | note | RECORD OF CONFORMITY: ITP Signed
9f048913-65fc-5aac-848c-062c27ad8f32 | note | HP*
079ffb93-9f9c-5f8d-a15c-d3844f9f735b | note | RESPONSIBILITY: Site Engineer /Site Foreman
b13e95d3-aa6f-520c-8e13-5d09a7882d2d | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
e8180798-eccd-58a6-906e-0aaffb4c5935 | note | FREQUENCY: Prior to commencing any activity
15aede06-16fb-5e52-87c0-f0d4502abb97 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
ca245212-e98e-5f81-adbe-7993bb78232d | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
c228f339-0729-56da-8e31-0bfc8c1695d2 | note | INSPECTION/TEST METHOD: Visual inspection
44077336-3538-5bbc-9fa0-ee729fba1ce9 | note | RECORD OF CONFORMITY: ITP Signed
3fc551b8-bffe-5332-90b1-aa6ceb038f75 | note | IP
92ef9060-43ec-5c0c-97b8-61f066df9733 | note | RESPONSIBILITY: Site Engineer / Site Foreman
71bec3be-b613-571d-8038-89467fbfd3c7 | date | Date Completed:
| checkpoint | 1.4 - Irrigation System
50f4d8e8-2deb-5b07-be72-3ff87c972f90 | note | FREQUENCY: Prior to commencing any activity
e3ee8ad7-3159-5a85-b316-376fcdcc1c26 | note | ACCEPTANCE CRITERIA: The contractor shall get the design approval from City of Ballarat on the irrigation system prior to commencing the activity
f9f9aba5-719a-5462-b042-6070e4f62457 | note | REFERENCE DOCUMENTS: Landscape Specification Cl 7.1
69da497d-8645-5bde-ba04-9a4f1ced75cc | note | INSPECTION/TEST METHOD: Verify
bf6e53db-e99d-5f63-9268-690fec88faec | note | RECORD OF CONFORMITY: ITP Signed
5f5f1e72-9bd4-5778-a8a5-7349522659af | note | HP
a7eb16c8-b421-5be1-a930-7fff7b7273a2 | note | RESPONSIBILITY: Superintendent/ Site Engineer
700a1fda-d802-5be2-8c80-0e19388e8363 | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
446e1d36-e8c3-515b-ba25-89d297f414da | note | FREQUENCY: Prior to start
f50157a3-fdae-50f6-9496-9c54d327463b | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work.
dabed84e-1ac1-5056-915e-87611f738ae4 | note | ○ No survey/level pegs to be removed by any persons until completion of works.
cf06ae0d-8410-5c78-a13f-f172716573e3 | note | REFERENCE DOCUMENTS: Cl 703.17
caabbc30-f733-53d2-af86-7fc85ad44ade | note | INSPECTION/TEST METHOD: Verify
7ab03be9-2dff-5da6-9f5d-52498dea8ddb | note | RECORD OF CONFORMITY: ITP Signed
7f747450-3f7e-5835-8499-0fd4cb1c3c0d | note | HP
e0f71e89-f3bb-5f39-ac9c-005f74fd536b | note | RESPONSIBILITY: Site Engineer/ Superintendent
324d9026-9180-51d9-8887-2973d95caf98 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Stripping of Topsoil
2db417bc-0f30-59c6-a601-73f8e76f0854 | note | FREQUENCY: As required
5a47dd21-ed9c-50f4-a13b-abb0f8c05b23 | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation:
0aba3ce2-fbd3-591d-adc4-9956f4c2e54d | note | (a) defined by the line through batter points extended to include any rounding and any surface and catch drains;
608bf9c2-75ad-5745-9840-6f1841789356 | note | (b) by a means which avoids contamination with subsoil and does not increase the extent of unstable areas; and
46fda475-a8ca-50db-a476-fd0831474d3d | note | (c) placed in stockpile or prepared areas.
50b57650-07d7-5d8d-96a7-091978823399 | note | ○ Unless there is an excess of topsoil to be removed from site, topsoil shall not be removed from the site.
574eb44c-5e59-5d13-a989-98e83539f1ff | note | ○ The Contractor shall treat and manage site topsoil before stripping, and after spreading, to remove and/or minimise the spread of weeds and other pathogens and pest organisms throughout the site.
3fafcd6c-6424-57c9-a811-583e6f806128 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re spread as soon as practicable.
6f3b659c-3e68-5119-b299-8277b0ff107e | note | ○ Stripped surfaces shall be graded to an even self draining surface.
32c35475-31bf-54fe-ad88-64cf67597c24 | note | REFERENCE DOCUMENTS: Cl 204.05
ac3f01cd-5f36-5c54-949c-7dfef0cc547d | note | INSPECTION/TEST METHOD: Visual inspection
a7c6119a-f005-5145-b6b3-d721768a02f9 | note | RECORD OF CONFORMITY: ITP Signed
646968ef-242e-5039-8285-c7b5c8ae5bdb | note | IP
42107672-2623-5af6-8b9f-d0a7743dcb40 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
31ec4836-fbca-515f-8720-340bf60aae00 | date | Date Completed:
| checkpoint | 2.3 - Topsoiling
622afe83-c5be-506f-8e26-78d76c9b2f09 | note | FREQUENCY: As Required
97932b78-0f42-532c-b09b-64081d26a3ba | note | ACCEPTANCE CRITERIA: Topsoiling shall not be placed over cut and fill areas until the Contractor has verified that such areas comply with the requirements in Clause 204.03
9fcf6bab-4dc6-51bb-8c0d-998795530cc3 | note | ○ All unpaved cut and fill areas within the limits of the batters, including batter roundings but excluding cut batters steeper than 1.5 to 1 (horizontal to vertical), and any other area disturbed by the Contractor's operations, shall be topsoiled to the following thicknesses measured normal to the slope:
ad2019c3-8632-522b-b0b5-0da082db8e36 | note | (a) batters with slopes of 2 to 1 (horizontal to vertical) or steeper 50 mm minimum
0e0fdf8a-8291-5c7a-90c5-d1773a357c3d | note | (b) tree and shrub plantation bed areas other than (a) above - 100 mm minimum
e4309d30-4d77-5be8-a149-0281275ddea4 | note | (c) verges: In areas without kerb and channel or concrete edging strips the depth of topsoil shall vary uniformly from 50 mm deep at the outside edge of verge to 20 mm deep within 100 mm of the edge of seal or asphalt surface treatment
a7d575ff-5d74-5ec4-84eb-d543e0729687 | note | (d) all other areas 75 mm minimum.
7c8ed25e-81e3-5441-a25e-04ffb03eb650 | note | ○ Topsoil shall be placed and levelled but not compacted except for verge areas, which shall be compacted. Topsoil on batters shall be placed so as to prevent rilling.
ed896264-6960-5226-9e52-3dc6463af391 | note | ○ The surface level of topsoil shall match the finished surface level, or level of back of kerb or concrete edging, as appropriate.
0fe16983-99f8-5dea-837d-cb4b375c172f | note | REFERENCE DOCUMENTS: Cl 204.17
d8440b59-e59e-537b-a8e7-62f38727bcc6 | note | INSPECTION/TEST METHOD: Inspect
fe2af0ce-7d0b-5c63-acce-cd4c7ff09434 | note | RECORD OF CONFORMITY: This ITP Signed
0f6c5c8a-e250-565f-b699-1b9d7f7869f3 | note | IP
09c39577-b1b6-5be0-8d89-253d9c22eea8 | note | RESPONSIBILITY: Site Foreman
4e8ffdbe-0e6c-5628-ba9c-6af1763044bf | date | Date Completed:
| checkpoint | 2.4 - Tree Clearing
8398b98d-872a-5e74-be03-1d8efbae2f0b | note | FREQUENCY: As Required
1d77e6e8-ad4d-58de-9f49-cfcc1a4834fc | note | ACCEPTANCE CRITERIA: The Contractor shall seek the Superintendent's approval prior to the removal of any tree. An inspection of the tree by the Superintendent or the Superintendent's environmental representative, along with the City of Ballarat is required.
94e067e6-55e1-533f-8261-b52e3336f899 | note | REFERENCE DOCUMENTS: Cl 200.1
5693e7d0-3b32-5fae-ab1d-ff2b0bb873a0 | note | INSPECTION/TEST METHOD: Verify
4faf8b4b-0bad-5b55-9c80-44cfa8519ae7 | note | RECORD OF CONFORMITY: This ITP Signed
43f8b2d9-ad34-5cd8-a871-e09753c0e45d | note | HP*
d3972adb-85f5-58ac-8193-fb23c86454cf | note | RESPONSIBILITY: Site Foreman / Site Engineer
5119ccf7-b48a-5538-933e-764b10eaa5cf | date | Date Completed:
| checkpoint | 2.5 - Hard infrastructure preparation
8c96208c-99b3-56db-94ed-58d609c75eec | note | FREQUENCY: Each Lot
874a69a0-eee1-5cd9-be72-98b5991ffe71 | note | ACCEPTANCE CRITERIA: Footings excavation – Site excavation shall be excavation within the limits. The Contractor shall conduct its operations such that the area outside the limits of the excavation is not unduly disturbed.
0afce0a6-7a59-5111-b612-4012a2e6228f | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
39c506fa-e3ff-5fd9-8c19-92fcbc9bbd08 | note | ○ Reinforcement for pavement/footing – All steel reinforcement shall be securely held during placing and compacting of the concrete.
eb5d0658-dbcf-5c2e-ad64-571a12f32878 | note | REFERENCE DOCUMENTS: Cl 204.06 (d), Cl 204.10 (b), CL610.26 (a)
8d9bd2fc-65d9-58bf-a7a0-c0a0998e5b8d | note | INSPECTION/TEST METHOD: Site Inspection
c28708a7-22f4-51ce-bc1f-ac9b0a905c6d | note | RECORD OF CONFORMITY: This ITP Signed
143d5e26-9414-5ee3-a19a-b50a58cfdc75 | note | HP
6af6d6f7-16e1-5061-ac6b-73667572f283 | note | RESPONSIBILITY: Superintendent/ Site Engineer
0cc603e5-8b30-500a-81b6-bdc3ea0dbba9 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Soil Preparation
17555b03-aee5-5111-959a-4c649ea216e8 | note | FREQUENCY: Each Lot
13260231-b044-5a27-9273-fab9fe1aaeec | note | ACCEPTANCE CRITERIA: All the necessary soil/garden bed preparation shall be approved by the superintendent prior to planting.
3fb49c26-7e60-5e65-8de2-cf5644164dde | note | ○ The planting soil should be prepared in accordance with the Tree Planting Detail and the landscape specification plan.
db661ea1-882a-57c4-a7b1-6b0f4a4e20e8 | note | REFERENCE DOCUMENTS: Cl 720.10
cf174546-dab8-5c6d-84d9-3b467f3b6dc7 | note | INSPECTION/TEST METHOD: Site Inspection
b65f80d8-60fe-530a-a162-4a4993d9320b | note | RECORD OF CONFORMITY: ITP Signed
c5382900-bdab-5f2e-9557-ba87713ee714 | note | HP
fedde168-1202-5638-bb9c-5e9cbc1a6356 | note | RESPONSIBILITY: Superintendent/ Site Engineer
6e3f5a0b-414e-538d-ac05-4101c4eef5e5 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.6 - Plant Stock
3a9d1877-b41c-5ff5-8f07-c7ca1555e2be | note | FREQUENCY: Each Lot
abafd8fc-8a70-5600-8560-d9537185e8f1 | note | ACCEPTANCE CRITERIA: All of the trees and garden bed plants shall be inspected and approved by the council representative prior to plantation
de4cbdfb-f850-56ca-86af-a49ce4e6893a | note | ○ At the nursery ensure that individual trees and batches are clearly labelled with the species name and cultivar / variety / provenance where appropriate
5de39a65-5cdb-5254-9d4e-11f67d7b8d2f | note | ○ Hardwood stakes, as per details are to be installed immediately after planting.
66a55652-9a93-5611-80dc-604d78fa853e | note | ○ Stakes are to be driven 600mm into the ground or deep enough to ensure that the stake will remain stable and vertical.
eb16a418-fd0d-5cbe-99a5-8698cd522078 | note | REFERENCE DOCUMENTS: Cl 720.04
f7588dc5-7173-5d73-85bf-e23bae61dbe2 | note | INSPECTION/TEST METHOD: Visual inspection
19e69aa2-d04f-5e69-bb35-2d6225d83943 | note | RECORD OF CONFORMITY: ITP Signed
03e558a8-93cd-50a0-96e8-9e72991f5c01 | note | HP
453ba9b3-a466-5b5f-9ee0-fd163fc105fb | note | RESPONSIBILITY: Superintendent/ Site Engineer
5d5a9d8b-1443-552d-aac6-64738835ff64 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.7 - Mulching
4d7638e7-3da1-5c02-95d5-90e057cf7fe3 | note | FREQUENCY: Each Lot
f38f8424-7dd8-5310-b913-b81a4f68191d | note | ACCEPTANCE CRITERIA: After topsoil placement and planting-out of the plant material in all garden beds, supply and spread mulch to an average compacted depth of 75mm. The mulch shall be free from soil clods, rocks and all other non-organic matter.
878da14c-bb4a-5b17-9ed6-d1e5291d7e9b | note | REFERENCE DOCUMENTS: Cl 720.08
0599f05d-57f4-5f8e-a441-8caede18ebf4 | note | INSPECTION/TEST METHOD: Visual inspection
a6aca764-388b-5de2-8275-fce20063943b | note | RECORD OF CONFORMITY: ITP Signed
3b260dcd-198a-5681-bf81-60d8622e934e | note | HP
bd0b4b49-6748-5177-9a43-e09105054965 | note | RESPONSIBILITY: Superintendent/ Site Engineer
7456e127-3e32-51cb-ab74-09f5995fc5d8 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Practical Completion
b70422ef-6cae-583e-ad65-6467fb0e2fdd | note | FREQUENCY: Completion of each lot
42aa7639-3847-52f8-86a1-3390062ea1fa | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design.
74615a2b-3c93-5a11-983f-abbea0175acd | note | ○ As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
203dd2d5-b4ce-53fc-802c-a3e1cc884a3d | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
861a1bac-f9dc-505d-89cd-d75823251878 | note | INSPECTION/TEST METHOD: Document review
7c20c7df-1028-5920-92f7-b410efaa9edf | note | RECORD OF CONFORMITY: As-built survey records
3b50ca1f-49ab-519e-878a-dd3b730ec3c6 | note | SCP
6f113501-abcb-513d-b5d7-0401cacf6651 | note | RESPONSIBILITY: Project Engineer/ Surveyor
4d5dc1ae-2d89-5bfb-9dfe-a8ed88e07e47 | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
40934d8f-6233-5e41-8b0b-4900f6250574 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d89be922-6468-5842-a2a1-d59967c29b8c | textbox | Print Name:
c94d119e-8749-50cd-8d9e-3df2a997419a | textbox | Position:
da5decb8-6239-5bf8-9cfe-9942f0c4beaf | date | Date:
| checklist | ITP-009 - Spray Seal | itp | ITP-009 - Spray Seal |  | 181b530d-e8ab-4362-bd2d-e0de5c7a9dd2
| section | 1 - Materials
| checkpoint | 1.1 - Bitumen
1c320ccc-4112-50a7-9893-3248ca569b3b | note | FREQUENCY: Test cert upon request
8ea83e79-45a9-5756-964e-c3589994468d | note | ACCEPTANCE CRITERIA: AS (Section 175) for residual bitumen for pavements
fa34262a-660d-5541-9e02-4a94135282d4 | note | REFERENCE DOCUMENTS: 408.08 (a)
a537d84f-40bc-5422-b66d-adf0c42706c3 | note | INSPECTION/TEST METHOD: Verify
8e1a27dc-d88b-5898-b340-3a3641b8a6e2 | note | RECORD OF CONFORMITY: ITP Signed Off
974dcd99-eb89-57d4-93ca-27b1a52ac719 | note | IP
aed4a9fc-3401-5349-9687-bc9c0b6a1b4c | note | RESPONSIBILITY: Lab Manager
6cc5113e-6dba-50cd-98f9-dea4f49d5fdb | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 1.2 - Bitumen Emulsion
322fa6d6-1ae8-5464-8e79-45342bd3151a | note | FREQUENCY: Test cert upon request
5b886449-51ed-5de2-bdce-aaf3de7db5f3 | note | ACCEPTANCE CRITERIA: ARS or CRS comply with AS (Section 175) – Bitumen emulsions for the construction and maintenance of pavements
630494d4-9ef3-5d54-be40-0ab19da78080 | note | REFERENCE DOCUMENTS: 408.08 (b)
959271e8-4caf-586f-99af-25fc317d1695 | note | INSPECTION/TEST METHOD: Verify
6da0b77b-33d1-5950-b417-bce391409ee9 | note | RECORD OF CONFORMITY: This ITP Sign off
77748bbc-c1c8-5fc0-b78e-655b71314fe7 | note | IP
d4580455-12b4-5156-aa14-c125ad40ed73 | note | RESPONSIBILITY: Lab Manager
83c0d9e2-8f1a-5389-b54f-4321f1473547 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 1.3 - PMB
76a2ffb5-a277-5402-8781-d1dc7eefcd7d | note | FREQUENCY: Test cert upon request
4026a8b4-e390-5a5c-b8c4-6d9be720cb3c | note | ACCEPTANCE CRITERIA: Austroads Specification Framework for Polymer Modified Binders and Multigrade Bitumen’s (AGPT/T190 - section 175) & table 408.161. Alternative PMB'S shall not be used without approval by Superintendent. Evidence of satisfactory field performance for 3 years required.
2b0cc9cd-e4c9-5a98-9819-ede7fd854bc6 | note | ○ (i) HSS - S10e,S35e,10Pts CR, or alternative approved by superintendent
8b99972f-1f43-5304-88f6-42b1a8d86c28 | note | ○ Field Produced CR - >5pts by mass of binder, Carrier oil <4Pts by volume of binder
2f6be102-ec18-5fee-a245-6debcf3cfb60 | note | ○ (ii)SAM - S45R,S20e,18Pts CR or alternative as approved by the superintendent
5171df09-d814-56f0-826f-daef5d5a013c | note | ○ Field Produced CR - >18pts by mass of binder, Carrier oil <4Pts by volume of binder
f977bd59-dcc6-5e04-b87b-d94d6050dd6e | note | ○ (iii)SAMI - S25e,20PtsCR or alternative as approved by the superintendent
d9f5abdd-6110-5cdf-a1e6-d639df29ec34 | note | ○ Field Produced CR - >20pts by mass of binder, Carrier oil <4Pts by volume of binder
4ab21922-7c1a-595d-92a0-92c94e513a80 | note | ○ XSS treatments – Class S20E,S45R or S15RF or alternative as approved by the Superintendent.
fb1eb0f8-0bb2-5cb4-bc63-70fc5124a409 | note | ○ XSS treatments are applied as a double/double application and the same binder shall be used for both applications.
b5f20d93-f664-5ad3-ae9a-f7bcbffbd0e3 | note | REFERENCE DOCUMENTS: 408.08 (d)
7ce0f854-74d1-501b-8ae3-c12ba272425b | note | INSPECTION/TEST METHOD: Verify
dc017814-6f35-51fd-9b28-c25e8046d384 | note | RECORD OF CONFORMITY: ITP Signed Off
53ee54f4-ab6d-574b-a50b-1c13710d98d5 | note | IP
24de6c2c-cc0b-58dd-9e2e-a6a88693d074 | note | RESPONSIBILITY: Lab Manager
7ad5557f-e300-5e82-bf0c-df1e503f2a1c | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 1.4 - Primer
8ed3b6b9-dd7e-5ebe-a563-9546e4e91cdd | note | FREQUENCY: Test cert upon request
f392a921-e69a-55e1-a4a3-e956407d9a65 | note | ACCEPTANCE CRITERIA: Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
fb7616cb-80e6-50d3-942c-65d157672a31 | note | REFERENCE DOCUMENTS: 408.08 (e)
6adaa7c8-0a04-5b12-9d4f-61583b9464e2 | note | INSPECTION/TEST METHOD: Verify
c0066ccf-f9f5-5846-879c-f199dac894a2 | note | RECORD OF CONFORMITY: ITP Signed Off
e6a856e4-309f-52ab-859e-4df484738a0f | note | IP
8b8e68ee-9b0d-5952-aefe-31e9a01df761 | note | RESPONSIBILITY: Lab Manager
c8a68f0b-bbed-5676-bf46-a000ddc0011c | date | Date Completed:
| signoff | Request Signoff
| section | 2 - Aggregate
| checkpoint | 2.1 - Aggregate Specification
c83fb3ca-1c33-5a3a-977b-06afba2ccd88 | note | FREQUENCY: Maximum lot size 350t of same class and size
de0db115-52ee-5857-9645-e0f1a454a386 | note | ACCEPTANCE CRITERIA: VicRoads Standard Specification Sections:
bec90e80-c07c-5706-bf03-74a3f70a461e | note | ○ 801 - Source Rock, 831 - Aggregate & 832 - Sands
fd29cc05-0da0-5ae0-923f-6c7b4096941d | note | REFERENCE DOCUMENTS: 408.11 (a)
7895e364-0db2-5896-ad0b-567fa94f58ef | note | INSPECTION/TEST METHOD: Verify
d440abaf-b25d-5de2-a51e-065711772a85 | note | RECORD OF CONFORMITY: ITP Signed Off
5bed4b47-ee64-5222-8177-2da3f62f8099 | note | HP*
33e9a439-cdcf-5456-83ab-bfc420032b27 | note | RESPONSIBILITY: Lab Manager
b22c1256-ff6f-5d81-8905-3f80418be99f | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 2.2 - Precoating
f9a53189-194e-5ece-83fa-28f860d499d6 | note | FREQUENCY: All works carried out
048e8635-2aeb-58aa-9caa-31d3e0f8846f | note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate from supplier or field precoated aggregate from stacksite.
4c225305-d7f3-56e0-b3f4-6941f4f3f78c | note | ○ Aggregate shall be uniformly precoated to the satisfaction of the Superintendent.
1218ce74-cf29-590f-b8d4-e32b971db46c | note | REFERENCE DOCUMENTS: 408.11 (b)
d6eb4e34-6b96-523e-88c1-be612e80b61a | note | INSPECTION/TEST METHOD: Verify
af5163d2-924b-5d39-968e-9b1406a93fdb | note | RECORD OF CONFORMITY: ITP Signed Off
86071c8e-652c-5c81-b4a4-db3f4bb0500f | note | IP
f16a69eb-a374-5a23-87e7-620492658b4e | note | RESPONSIBILITY: Supervisor
ebf0da9c-7d97-5898-bca6-497a0d7c274e | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 2.3 - Removal of loose aggregate
ad0fda2f-7c31-55c1-ba6a-2c697090fdaf | note | FREQUENCY: All works carried out
b42ace14-1efc-5b93-9c64-ff4fad4205f9 | note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
ff8fce44-4466-56f5-9c7b-51d54e0e9068 | note | ○ NB: For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
2eb2dbf0-e82a-5a6c-b2f0-f456fc5f0555 | note | REFERENCE DOCUMENTS: 408.14
f166755e-346c-5da6-b30c-623ce4f6cf3d | note | INSPECTION/TEST METHOD: Verify
b0b56dc8-c88d-57fd-9b61-5e58f6e48382 | note | RECORD OF CONFORMITY: ITP Signed Off
0f145d28-43c3-56d5-9f4e-046c9f2797a4 | note | IP
2f8d385e-dc6a-5c68-b1ee-a1fbaed68afe | note | RESPONSIBILITY: Supervisor
38b8d528-e6a5-5dd6-85b8-77617ef5f4eb | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 2.4 - Stack Site
4e96346f-734c-5a20-a533-5642d3fb8bb5 | note | FREQUENCY: Prior to commencing works
72931112-d748-5df0-bd88-2c64dc8c962c | note | ACCEPTANCE CRITERIA: Stack sites to be approved by Superintendent.
da0ce4fa-261d-58be-a8fb-ed339b1b6e68 | note | ○ Stack site to be at Kent Street where road is closed.
770d8c06-90d7-5222-9fc6-4196ee95d5c0 | note | REFERENCE DOCUMENTS: 408.12
e3229b25-9322-507b-bf21-13fa6308bd22 | note | INSPECTION/TEST METHOD: Verify
aa2002a9-1ed9-56b4-8ce0-55f0d9251fba | note | RECORD OF CONFORMITY: ITP Signed Off
621f63d0-b62c-504f-b804-abf2e6318ebe | note | IP
646df50c-154f-5068-be34-f16dd2f35d12 | note | RESPONSIBILITY: Supervisor
9624ef96-212a-5e70-9d29-ac0ca267826c | date | Date Completed:
| signoff | Request Signoff
| section | 3 - Operation
| checkpoint | 3.1 - Rates of Application
dfa61704-15f2-5ef2-b774-5d703eea80fc | note | FREQUENCY: All works carried out
a460a3a7-7710-53fa-ac0f-9ac794b811ee | note | ACCEPTANCE CRITERIA: In accordance with the current Update of the Austroads Sprayed Seal Design Method
ee8ecb09-92a4-5529-a6f1-bf838207ee31 | note | ○ (Section 175) rates of application - residual binder at 15 C
fee342df-a54a-5828-9bdd-b0f40b3c6d2d | note | ○ Traffic Data and default rates -Table 3040.066 (Traffic Volumes)
4ece7572-6568-5f67-8e5d-861e8d76db34 | note | ○ 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
93209d34-d95c-58c9-ac74-8e1758dc7575 | note | REFERENCE DOCUMENTS: 408.15 (a)
4d9b10ff-f002-5d79-b03b-96d913f560f2 | note | INSPECTION/TEST METHOD: Verify
df66d467-e37f-56a0-a2d7-c8b63cecd493 | note | RECORD OF CONFORMITY: ITP Signed Off
59bd4a76-793a-52af-8646-388849891bd2 | note | HP
0e522ae4-d15e-5435-b0b6-c390914b3e68 | note | RESPONSIBILITY: Site/Project Engineer
3a329e00-a54c-59da-bb93-4f3e87a3c734 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.2 - Surface Pre-treatment
0dd2895f-255f-585f-8173-aa0b853b7557 | note | FREQUENCY: All works carried out
da9339e8-68bf-5d4c-899e-e47bbde63520 | note | ACCEPTANCE CRITERIA: Refer Table 408.171, 408.132, 408.133
e60fa7b2-3eb0-54c1-b2f4-5cba0d2ae44c | note | REFERENCE DOCUMENTS: 408.13 (b)
361c70ff-4d64-54a4-a7e1-4d56e3a0b4e1 | note | INSPECTION/TEST METHOD: Verify
7c65fa39-84b3-5f89-b51a-83ae7d85ecbd | note | RECORD OF CONFORMITY: ITP Signed Off
11206297-7ab4-50d3-97b7-0ec002381eca | note | IP
8261341f-a6cb-5669-96ac-1e04c2b3db19 | note | RESPONSIBILITY: Supervisor
c0d5078d-8ef7-5a2c-adf2-a8b308505d1c | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.3 - Calibration of Bitumen Sprayer
781d45c5-c67f-5b1c-9e39-e0db4d1248f5 | note | FREQUENCY: Prior to commencing works
b0178832-a170-5df8-b893-e00644e31e76 | note | ACCEPTANCE CRITERIA: Calibration Certificate to be provided
1bd91800-c2fe-5f90-8f84-67f9dc34b783 | note | REFERENCE DOCUMENTS: 408.07
0dbf7f06-0085-58fd-987f-7cdc4fb0b063 | note | INSPECTION/TEST METHOD: Verify
7c97c8f2-5237-5d11-9a89-c3ad6b8debd2 | note | RECORD OF CONFORMITY: ITP Signed Off
f7ff68e5-8ddd-5c68-ba61-b841b89258e0 | note | WP
a2c95043-9577-55ee-bcfa-a620c2faafc9 | note | RESPONSIBILITY: Supervisor
5fa3f82d-3b12-5d48-8797-7b9757f4cf12 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.4 - Commencement of works
6ff61b49-a0de-5dd0-9ef9-d4f52d7cec4a | note | FREQUENCY: Prior to commencing works
9c9144f8-5dae-53f3-9e76-a88ec4a75690 | note | ACCEPTANCE CRITERIA: NB: Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing. This includes a review of the material and evidence that the pavement passes compaction testing to Superintendents approval.
7f88560d-b600-59e2-bbc2-d949aa861c6e | note | ○ Primersealing shall not be carried out within 12 hours of forecast rain.
e599a8b7-42b6-5599-9bb7-9b5123a19bce | note | REFERENCE DOCUMENTS: 408.04
ebcdb9d7-129f-5334-b4bd-6e7b00136dd7 | note | INSPECTION/TEST METHOD: Verify
e3569ebc-2c4d-56d8-b47b-26810a719d04 | note | RECORD OF CONFORMITY: ITP Signed Off, QD2190370 Sealing Checklist
f3b2fc08-7c5b-5a66-8072-e064ff68c7dd | note | HP
71c4d89a-20f6-5046-b51c-b1edd1417774 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor / Superintendent
bc5d2d6c-3141-5093-b8c4-0b42d57a8163 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.5 - Records
45c1103e-c1f6-5858-961a-b33d8ccb0641 | note | FREQUENCY: Each Lot
7e33c6e5-8f13-52a4-b666-64f6444ec1f7 | note | ACCEPTANCE CRITERIA: Job completed within spec requirements.
471a4173-e0a2-524e-b7fe-2a019bbf382a | note | ○ Job completion report, i.e. Spray Sheets to be submitted within 7 days of completion of sealing works
36194217-5817-5b76-9997-deafd7e2cd93 | note | REFERENCE DOCUMENTS: 408.17
a890ad7c-f323-52f9-81a2-d583127e2ad4 | note | INSPECTION/TEST METHOD: Verify
0f36a9ec-c6df-52d7-ac95-b89aa398e10a | note | RECORD OF CONFORMITY: ITP Signed Off, Spray Sheets, Section 408 Attachment A
344d201a-b473-55b3-aea6-0992d346176a | note | WP
0ae8a20e-664b-5cff-8da6-4424d7b41e5c | note | RESPONSIBILITY: Site/Project Engineer
87bf210f-8faf-5723-9cec-f995947498dc | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.6 - Acceptance of work- Binder rates
e18cd8e6-01ae-5ae1-8dc3-e82c52ccce9a | note | FREQUENCY: Each Lot
312c0fea-f7a3-5332-bf94-7fa927a50f26 | note | ACCEPTANCE CRITERIA: Actual vs design rates. Variation between actual & design assessed by Table 408.121
54e89f4a-b49c-583f-8eba-73d4f48ca3a2 | note | ○ ie. Variation from the Design Rates of Application for Bituminous Material < 0.1 l/m² below the design rate of application
0cfb7f19-1ea1-51dd-b013-8ac162dc64d7 | note | REFERENCE DOCUMENTS: 408.15 (a)
f3659a52-aea2-5fe6-99e3-dc9c28e148de | note | INSPECTION/TEST METHOD: Verify
a79ff40b-8a5c-560b-a135-a1930b939e68 | note | RECORD OF CONFORMITY: ITP Signed Off
4a4fe0bc-f022-5321-ae2a-9a0956569f9a | note | IP
16cfe6d8-2d8b-5a70-b84f-241aee5880d4 | note | RESPONSIBILITY: Site/Project Engineer
2d30b1ae-301f-5a13-8994-dd764f95f45f | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.7 - Acceptance of work- Surface Texture
cfa60be6-de6b-516d-9ce8-9fc861e6809e | note | FREQUENCY: Each Lot
d7946149-8a1e-5700-abb5-d4da5c8a6d0c | note | ACCEPTANCE CRITERIA: Acceptance - visual assessment or (where required) as per Table 408.122
3c39b19e-86a2-51d8-9152-ffb6ce44c787 | note | ○ ie. 7mm Primerseal Mean Texture Depth between 1.0mm to 2.0mm
d6e5c2c4-c738-5d7b-98a0-d9ca93494cc9 | note | REFERENCE DOCUMENTS: 408.15 (b)
9010a337-7ef0-5355-93ff-fe988486c4a6 | note | INSPECTION/TEST METHOD: Verify
38bb024c-28b6-5a31-8fec-7eee78848dde | note | RECORD OF CONFORMITY: ITP Signed Off
974dcfed-2b74-5192-853c-ff8e0caf8305 | note | IP
050544bf-4da7-58a9-9706-3b6695af6cc9 | note | RESPONSIBILITY: Site/Project Engineer
18c10265-9d35-5d9d-ae13-176c7d387d58 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.8 - Acceptance of work- Aggregate retention
5b44db28-850f-5219-b949-1547e433ffb3 | note | FREQUENCY: Each Lot
a7a8e14b-bb49-52fc-b801-55d9428276b9 | note | ACCEPTANCE CRITERIA: Acceptance -visual assessment or (where required) as per Table 408.123
4952a68a-bc1f-5b3c-8ba7-6b403b3f2856 | note | ○ Degree of Aggregate Stripping is 0 - 2
3f02b467-a36d-5abc-b1de-7cec77a9b0e4 | note | REFERENCE DOCUMENTS: 408.15 (c)
2f8935a5-9929-53f5-ab40-937a96351624 | note | INSPECTION/TEST METHOD: Verify
82854608-e73c-5bcc-894c-3e816f04ced1 | note | RECORD OF CONFORMITY: ITP Signed Off
ac5c2adf-f702-5d6c-98c7-fc28283512ba | note | IP
e5ea5ba2-d7ea-5f70-8793-23d0efbce76d | note | RESPONSIBILITY: Site/Project Engineer
b6d43765-cb57-5f68-a382-ce87e36e48ff | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.09 - Acceptance of work- Visual Uniformity
2723c94c-d114-5d5c-b599-681ee7a5eff2 | note | FREQUENCY: Each Lot
0a40e990-df54-5521-acc5-3bef1bc53f3c | note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
4b136af6-b98f-5d5e-a4d9-6593fff24d63 | note | REFERENCE DOCUMENTS: 408.15 (d)
3178b4ad-39cd-5a07-b2c0-7935c76afe2a | note | INSPECTION/TEST METHOD: Verify
d3dedd83-1b53-5186-b194-28ade5fce20d | note | RECORD OF CONFORMITY: ITP Signed Off
247d7491-3377-5367-95b1-94829bfe313a | note | IP
fc8fbd09-39dd-5756-a789-facbf9c1bfd0 | note | RESPONSIBILITY: Site/Project Engineer
bd0d7c1a-c490-598e-926f-090c881b2c8f | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.10 - Maintenance of seals
597d0de3-e0dd-5074-87ff-6420678863fa | note | FREQUENCY: All works carried out
920b157e-4cae-54bf-b822-eac0c902c3eb | note | ACCEPTANCE CRITERIA: The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period.
58e449b1-88d9-5787-a805-8ca8d27a1693 | note | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work.
3182349d-8e42-5a0e-a7f5-e6c841a82ff5 | note | REFERENCE DOCUMENTS: 408.16
7ab76304-986f-5afa-b7cb-06db13a726a4 | note | INSPECTION/TEST METHOD: Verify
81fc50fc-c480-5b21-a222-20524fa1c868 | note | RECORD OF CONFORMITY: ITP Signed Off
c7fa59b9-35fe-560a-9592-b791fdd775bc | note | HP
0993bb77-f622-5a44-be87-01ce8d979b7f | note | RESPONSIBILITY: Site/Project Engineer, Superintendent
3d316132-3a99-5169-bad7-40a62df63e79 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.11 - Maintenance of seals
46f45e6c-21ec-5ac8-87c9-a547d384b63a | note | FREQUENCY: All works carried out
e26c824b-d2b6-5278-858d-e0f8b1515a81 | note | ACCEPTANCE CRITERIA: Where the treatment for protection or repair of a seal involves the application of a further seal coat, the Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work.
78913b58-e2f0-5f4d-95df-1fd53dfa273b | note | REFERENCE DOCUMENTS: 408.16
ee4232e5-2f18-5769-8549-0252d67b2335 | note | INSPECTION/TEST METHOD: Verify
95535a06-0cd5-59b7-a2ca-190a98c4a67e | note | RECORD OF CONFORMITY: ITP Signed Off
bd25e734-8e34-5171-ab91-cbcc8c11cf2b | note | HP
013d775c-7f57-5dc7-8f53-2235e6c51748 | note | RESPONSIBILITY: Site/Project Engineer
becc25cc-75ae-5040-9364-50b37e76c2e3 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.12 - Defects Liability Period
35bed519-6519-5c4b-8c74-a68025f5a6a1 | note | FREQUENCY: All works carried out
7edc0806-4d19-5cb0-9241-982be8ebc89f | note | ACCEPTANCE CRITERIA: All defects should be rectified six months prior to the conclusion of the Defects liability period. As stated in 408.15
232658d9-ab0c-5f3f-bb3f-06d566d1349d | note | ○ The Contractor shall carry out at least two inspections of each job during the Defects Liability Period and provide a condition report to the Superintendent. The condition report shall detail the condition of the seal, any defects and the proposed corrective action.
b86510c6-f60f-5968-872c-75f17d26eeb3 | note | REFERENCE DOCUMENTS: 408.18
1bf3934a-842c-5f2d-bbb2-d38c63e26c9f | note | INSPECTION/TEST METHOD: Verify
fe664115-97ac-58c4-859c-6384843db22a | note | RECORD OF CONFORMITY: ITP Signed off
0367d4b4-3c87-518d-9be1-a5919f173d95 | note | WP
9aba7af0-f823-5d9d-b3de-19b5ef137705 | note | RESPONSIBILITY: Site/Project Engineer
5ce2acfa-8843-5109-8215-dc2c4669eec9 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.13 - Dryback
e07dc4de-08e2-51cd-8830-fa38800a4ac7 | note | FREQUENCY: Each Lot
67fa635a-2531-5e84-b149-24949c6e75b5 | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
15dfa832-1328-5722-b8d7-1d38fd114430 | note | ○ 6 randomly selected test sites per lot required
bbc3d159-722d-55ad-a581-82130262bda4 | note | ○ If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
a5eba919-5c13-5490-9dc3-0200e6d3e52c | note | ○ If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
ca60a863-d8c9-5821-8cfd-bb06fe805202 | note | ○ Testing shall be undertaken no more than 24 hours before primersealing.
2a2ec4b8-94ad-5be7-a6e0-300cc7629a02 | note | ○ Testing schedule in accordance with 310.03 (c) and QD2190370 Sealing Checklist
fd324dc2-7d15-5b61-b344-f97357b65f37 | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b) Table 310.031, 310.03(c) Table 310.032
ab2bd603-27e9-5136-887b-f038455ce78d | note | INSPECTION/TEST METHOD: Verify
242f3b27-f389-531c-b68c-6ab5dcdd48b7 | note | RECORD OF CONFORMITY: ITP Signed off
2e15b5a3-30b2-569a-a766-63e9a4099f28 | note | TP
e9fccd56-f963-5c47-b8a8-1eee3d12c635 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
491d4380-b125-5052-a1ef-8406026f5bff | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.14 - Ride Quality
6d4fa00c-d6e0-56c0-996c-df6ff48d58e8 | note | FREQUENCY: Each Lot
e60e8cc3-0199-5379-aa0b-acf7c1c98480 | note | ACCEPTANCE CRITERIA: Ride quality measurement shall be undertaken within 3 months of the completion of primerseal and prior to practical completion being awarded by the Superintendent.
17b4c667-627e-5f13-9270-f6464c1ec4dd | note | ○ The finished surface of the Primersealed pavement shall have a smooth longitudinal profile and comply with the minimum ride qaulity requirements of Scale C road as specified in Table 180.092.
744fa3fe-1d5c-5e8f-aa74-788eee316a96 | note | – Maximum Individual Lane Roughness Value for any 100 m Subsection = 2.70 m/km/lane
70c9c1ea-d8f1-5e78-8211-31407896a240 | note | – Maximum Mean Lane Roughness Value for Lot = 2.00 n/km/lane
e53e632d-6310-5dbb-8bc2-282c1be9bf02 | note | – Maximum length of lot is 2km of continuous traffic lane
9017ebdc-2cc7-5255-bd97-f78cc68261d9 | note | REFERENCE DOCUMENTS: 180.04, 180.092
c123dee8-05c1-5342-a08b-109e98fb808f | note | INSPECTION/TEST METHOD: Verify
d461db92-b294-53ee-9eb6-bfe173f27e6b | note | RECORD OF CONFORMITY: ITP Signed off
a1717c09-ee5b-57d4-ac61-6d3ca5d39481 | note | TP
bc031e1e-3791-518e-988e-423b1102f235 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
f6d59338-fe2b-5ab9-b1c1-d3fe9238e3a9 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | Final Inspection
c0f92f9a-ec48-5503-bb22-b298a8a39d3f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7fbd1c42-6130-501c-8412-fbf4f5eff5cf | textbox | Print Name:
5ec17492-0eb6-5d57-8702-6b6989188d3f | textbox | Position:
e269e436-7563-5dd7-adc7-d0752c351239 | date | Date: