## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-001 - Pre-commencement of works | itp | ITP-001 - Pre-commencement of works |  | 7e75dad7-05b0-4b4a-839f-2ccc88bf2653
| section | 1 - Construction - General
| checkpoint | 1.1 - Design Drawings
ef78582b-cf8b-511c-a466-3d576ca0d678 | note | FREQUENCY: Prior to commencing any activity
be13fa40-00b6-596f-aca4-c9e1d2b12560 | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
35cd3411-aa98-5b31-9ebd-6cae1e6d65da | note | REFERENCE DOCUMENTS: IFC Drawings
9569fba4-5118-560c-a1f3-ee35c2513d65 | note | INSPECTION/TEST METHOD: Visual inspection
6f85d1af-6651-57bb-aa47-7d6f163da6a8 | note | RECORD OF CONFORMITY: ITP Signed
b8f00a98-a449-597f-8f8a-4b4a81d8dbc6 | note | IHP
b5f1079b-8c63-5acb-acd0-71e5f029462b | note | RESPONSIBILITY: Site Engineer / Site Foreman
282107d1-a0e1-5f23-9e23-aebc73e6b1b4 | date | Date Completed:
| checkpoint | 1.2 - Service Locating / Permits
430c54f2-321c-58e9-a7fe-269ef14e929f | note | FREQUENCY: Prior to commencing any activity
6b63ef4d-5f46-5de1-afcd-c2bfe7e5455a | note | ACCEPTANCE CRITERIA: Lodge DBYD application prior to works commence and obtain any relevant permits applicable to the works. DBYD to be renewed every 30 days.
5ee8f73d-d35b-5bcd-bd73-5e8bc2126bc2 | note | ○ All nominated/aﬀected services from the DBYD application must be located/potholed prior to commencement of works.
1eb47062-46a5-5f0e-a370-f1af7e8e6b63 | note | ○ Works identified within the vicinity of the powerlines to ensure distance exclusions are followed & spotter used, if required.
0e0a3e8d-169d-56ae-810d-35e64dc4e5f9 | note | REFERENCE DOCUMENTS: DBYD Information
26cb49a2-40af-58c0-a85b-061311158cd0 | note | INSPECTION/TEST METHOD: Visual inspection
060d7efa-7b6d-50fb-bd2e-0761eff93a72 | note | RECORD OF CONFORMITY: ITP Signed
1c2062ba-d191-545d-85be-75cb69add35b | note | IHP
e21b9616-d448-5446-b13e-c4015236e47f | note | RESPONSIBILITY: Site Engineer / Site Foreman
bc41217a-b29a-5674-b7be-c960ae6b96e1 | date | Date Completed:
| checkpoint | 1.3 - Commencement of work
12d4df68-8793-5131-a436-cd8d215467f4 | note | FREQUENCY: Prior to commencing any activity
f471d535-1b9a-56c2-b115-d75642c7e097 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence work on site before the following documents have been submitted to the Superintendent and the Superintendent has authorised release of the Hold Point:
2e636ac7-2b94-5b54-bb28-b5e3181268ee | note | (a) Public Liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
f6542d9f-ca97-5933-8231-518e27dca617 | note | (b) Health and Safety Co-ordination Plan
8ca7931f-d432-58ee-8f9d-f1050fbd7ffa | note | (c) Environmental Management Plan for initial works
c389e556-89b0-58bf-983f-8b3b6423b16e | note | (d) Project Management Plan
a2e5d44a-481c-599d-b87f-46c231ed75d2 | note | (e) Quality Management Plan
ae8207cf-3e41-5817-be36-dafe92f7fa1f | note | (f) Safety Management Plan
c362e3d9-c0a9-565c-b963-81a9dca73bb4 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 160, 166, 167, 168 & 176
5ae1bbaf-b8cc-5918-896f-74030f3a0d86 | note | INSPECTION/TEST METHOD: Visual Inspection
0bbe69bf-0131-5763-aace-7a6ee526c85a | note | RECORD OF CONFORMITY: ITP Signed
21ea7b69-b432-563b-a7fe-e36cf01f9cde | note | HP
abf1a4c5-9d70-574a-a177-04a91ec5990a | note | RESPONSIBILITY: Site Engineer
9b02bc07-8fae-5a84-bdb1-a0fe80359465 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Traffic Management
| checkpoint | 2.1 - Submission of the TMP to the Superintendent
5410b5c3-976b-5e48-908a-147df1a6a962 | note | FREQUENCY: Prior to commencing any activity
fd3b69b2-0a8a-5023-9fb6-095e2de68e78 | note | ACCEPTANCE CRITERIA: The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point.
1e68bfa3-936e-5b3b-970c-87f3ccf7fe76 | note | REFERENCE DOCUMENTS: TMP, VicRoads Standard Section 166.08
0637759c-253f-55b0-a346-e887c88351a5 | note | INSPECTION/TEST METHOD: Visual Inspection
369d4f3b-e3d1-58cc-a249-5dc75c162a3b | note | RECORD OF CONFORMITY: ITP Signed
59729f18-018b-5455-a6fb-1b6ef30733c0 | note | HP
7673bcbe-4869-5e13-a312-a2c0f496d694 | note | RESPONSIBILITY: Site Engineer
028c1518-25bd-5c51-8a09-e24bd2736a36 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Detours and Side Tracks (a) Side Tracks, (b) Detours
4f706fe0-15fa-5bcf-ac76-dae87379f88c | note | FREQUENCY: Prior to commencing any activity
7534f393-73ba-54ab-a982-e8c8634c82fd | note | ACCEPTANCE CRITERIA: Traffic shall not be diverted on to any side track until permission to use such side track has been given by the Superintendent.
15e9e411-b23f-5942-ae66-d8c023f0ca3a | note | – Permission has been given by the Superintendent and Ballarat City Council.
04c9a070-e4b7-5936-963c-4183d68897e8 | note | ○ Where VicRoads as well as the Contractor has some responsibility for the restoration of any detours or sidetracks, the Contractor shall not commence any restoration work until the Contractor has submitted details of the work to be undertaken to the Superintendent for review.
4462e449-538a-5013-8f41-23dbb2d2e8a9 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166.17 (a) & (b)
b5420330-d1e0-52c8-9323-32bf2420e980 | note | INSPECTION/TEST METHOD: Inspection
1f7f2631-bd59-51a1-9722-d13c8b4368ea | note | RECORD OF CONFORMITY: ITP Signed
dcd860d9-e028-50d5-9a2b-e9c44097959e | note | HP
de328422-4a13-5b18-8191-2ac4a63317b8 | note | RESPONSIBILITY: Site Engineer
9cee23e8-fb48-5400-ba8c-668aab7e3ca9 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Traffic Management Documentation
b627f37c-5b36-527f-ba29-2eb374d655fc | note | FREQUENCY: Prior to commencing any activity
862cb4ad-1b92-5bb7-954b-ecddd09f1309 | note | ACCEPTANCE CRITERIA: Ensure all TGS plans have been reviewed and deemed acceptable for the project. Obtain MoA approval for any road impacts or closures.
729c8cc5-5bd1-5619-9712-265a4752b55d | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166
23729023-edfc-5b96-9d58-bf7e73ebc350 | note | INSPECTION/TEST METHOD: Visual Inspection
c33814d2-fd32-5536-9608-d2026db76db3 | note | RECORD OF CONFORMITY: ITP Signed
64953b9b-31b2-5dac-8308-d93ac0062e11 | note | IHP
6b8a3e63-b1e3-56ce-a7ce-808e2a3b194c | note | RESPONSIBILITY: Site Engineer / Site Foreman
33d58c8d-d693-5199-bb90-83aca5a7c05c | date | Date Completed:
| section | 3 - Health and Safety
| checkpoint | 3.1 - Occupational Health & Safety Management Implementation
4aa2c408-0efc-595a-af19-594ac40b34f7 | note | FREQUENCY: Prior to commencing any activity
d9b1c51d-f054-55c5-9c51-c3f64085e5d9 | note | ACCEPTANCE CRITERIA: Signed Safe Work Method Statement (SWMS) in place. All personnel including Subcontractors must complete Site Induction prior to arriving on site.
a97e4701-d1fb-52c9-b6ce-d7c80bc94b8d | note | REFERENCE DOCUMENTS: Site Specific SWMS
c9058d60-db3a-5a94-9286-1f18061da3f8 | note | INSPECTION/TEST METHOD: Inspection
326d4cc0-b349-5c3d-b6b1-9edfcfa9d145 | note | RECORD OF CONFORMITY: ITP Signed, SWMS
98d6f494-9ebd-5f5d-ac26-348b05b4eda5 | note | IHP
ff9136c9-c428-5c13-9878-3e73e589dbab | note | RESPONSIBILITY: Site Engineer / Site Foreman
73449734-907e-55b0-8115-498f1e1d6474 | date | Date Completed:
| checkpoint | 3.2 - Health and Safety Co-ordination Plan and Declaration
f40dff29-eb87-51ff-bd6c-32f55381a78a | note | FREQUENCY: Prior to commencing any activity
d7628394-ce6d-5d6a-a440-2f36f623cfcc | note | ACCEPTANCE CRITERIA: The Contractor shall, not less than 5 working days prior to commencing work, submit to the Superintendent:
99ee9fc5-9413-562e-a986-dad6ef75ad62 | note | (a) a reviewed Health and Safety Co-ordination Plan; and
918abdf4-b107-53c9-870a-4ba73752759f | note | (b) a signed HSCP Declaration by an OH&S consultant/advisor that the HSCP meets all the necessary requirements. The Declaration shall be in accordance with the proforma included in the appendices of this Specification.
212c3003-f418-5093-bcb4-72b54a37c553 | note | (c) a completed VicRoads HSCP Checklist with Contractor’s responses for each checklist item requirement.
7c90392b-6ca3-5683-b39e-7f00fe2950ae | note | REFERENCE DOCUMENTS: VicRoads Standard Section 168.05 (c)
ca1c2433-a237-531b-aea2-7375f2ad6fb7 | note | INSPECTION/TEST METHOD: Submission
8fd1f519-3dd5-54d7-896e-4d5186a2be52 | note | RECORD OF CONFORMITY: ITP Signed, Safety Management Plan
c4e6aae8-32a2-51c5-acda-1a0a7b0d69c8 | note | HP
87682bd1-9ccc-557c-8159-effbcb95590e | note | RESPONSIBILITY: Site Engineer
dc9a6f45-12c2-5271-9952-8702b2694cfb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Environmental Management
| checkpoint | 4.1 - Environmental Impacts, Aspects & Risk Assessment Implementation
acd6b783-e15f-5b8e-a9a8-bfc7edb67999 | note | FREQUENCY: Prior to commencing any activity
bcb924e6-3ea3-59c2-8f3c-61f40b76c231 | note | ACCEPTANCE CRITERIA: All environmental controls implemented in accordance with the Contract Environmental Impacts, Aspects & Risk Assessment.
8870f23d-f85e-55e8-9954-9be1937fba3f | note | REFERENCE DOCUMENTS: EMP & A&I
12163dd6-dc41-5217-ac62-fdc1ec4fe5bf | note | INSPECTION/TEST METHOD: Visual Inspection
2d0a449e-45c1-5094-a284-b8c6f39bbc4c | note | RECORD OF CONFORMITY: ITP Signed
947cd06b-003a-55b5-bef3-c216813116f0 | note | IHP
cd898bd0-7d6b-5fae-93a6-4e0bf81f60e4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
1d5fe614-0ef2-5d11-9463-c9a0d1b3b685 | date | Date Completed:
| checkpoint | 4.2 - Environmental Management Plans
9dad0767-89cb-5d6b-b887-d9ac4745cf58 | note | FREQUENCY: Prior to commencing any activity
19d7b801-0a26-5267-9b7c-db67084efd0d | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review an Environmental Management Plan not less than 2 weeks prior to the commencement of work. Work shall not commence until:
3a950254-fc43-5ace-8953-172a1e8c0b7b | note | – the Superintendent is satisfied that the Plan meets the requirements of this specification; and
a8b812bd-98b9-5fab-9978-7f4fb2ba6cec | note | – the controls detailed in the Plan are implemented; and
d009f905-8b50-55de-8113-4cc916ea67ea | note | – the Superintendent has authorised release of the Hold Point.
f2315b8f-267a-56c1-be2c-4006ad96d5c6 | note | – Limit of works identified in applicable SWMS.
cd24dc22-2fdb-530c-b98f-d91fab435d44 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.A3, VicRoads Standard Section 177.A3
8fa5e67d-58dd-5afb-b0ac-f5d504bf732b | note | INSPECTION/TEST METHOD: Submission
1bd17015-9e55-55c7-826b-cffccb88d0b9 | note | RECORD OF CONFORMITY: EMP, ITP Signed
e5e0342b-e26b-5281-b8d6-94a70ca55d01 | note | HP
28861a54-3908-5c5b-a70a-f516dcc45a7f | note | RESPONSIBILITY: Site Engineer/Superintendent
2a2bf56d-fee3-5b8b-b67b-e29488797fce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Flora and Fauna
7fac8a2b-0982-5263-a577-d4b2df500756 | note | FREQUENCY: Prior to commencing any activity
978c5b1c-c1ad-530d-b21f-f949cfdc6d5c | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to conﬁrm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones.
36be6012-cfe3-54c4-ac3c-f38df6249c3b | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.I1, VicRoads Standard Section 177.I1(c)
7444744c-fa6f-5c2e-a237-ed89d8b718fd | note | INSPECTION/TEST METHOD: Visual Inspection
fed875ab-c809-5039-97c9-1313f862fd4b | note | RECORD OF CONFORMITY: ITP Signed, Relevant permits, No Go Zone Signage
b6771031-1a80-52da-90ae-6baccc655f0b | note | HP
e03113c3-178f-5052-bd2d-9cc7b6cfb973 | note | RESPONSIBILITY: Site Engineer
92c81c8e-1d80-5dfa-9d88-96262da22c29 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Erosion and Sediment Control
a68d9d42-29de-5f7f-877c-8d03451c9cb1 | note | FREQUENCY: Prior to commencing any activity if applicable
d98331e0-db37-5638-b170-ecd15c416182 | note | ACCEPTANCE CRITERIA: The Contractor shall provide the necessary environmental controls as nominated on the approved Environmental Management Plan and identified on site.
dd1258d4-fd17-5cf4-82c1-ca7f6f05681c | note | REFERENCE DOCUMENTS: VicRoads Standard Section 177.D1(c)
137f7a6d-4564-5a45-8c75-79e7815e8d9a | note | INSPECTION/TEST METHOD: Visual Inspection
8bc76de2-794d-5933-b0ba-53b97b2dc978 | note | RECORD OF CONFORMITY: ITP Signed
67f8a512-c74c-5195-b318-923caa1ff2e1 | note | IHP
fd257102-bdd1-5f29-8742-1f1a905a125b | note | RESPONSIBILITY: Site Engineer / Site Foreman
1a9709ec-573a-55a7-8f2a-9ce5011af90d | date | Date Completed:
| section | 5 - Stakeholder and Community Engagement
| checkpoint | 5.1 - Residents have been informed
139ef1a8-28a2-50a4-b2de-374d2201e9de | note | FREQUENCY: Prior to commencing any activity
2828fb78-2153-5f20-a26c-d296d5eb0f6f | note | ACCEPTANCE CRITERIA: Residents impacted by construction works are to be notified by letter drop of the construction taking place, the timeframe of the works and information on how the works will affect them.
00d2fb93-0fbf-5186-9a22-9d92d6d4ec80 | note | REFERENCE DOCUMENTS: Letterdrop
78facefe-203a-5c04-aac1-4e9c33511fcf | note | INSPECTION/TEST METHOD: Visual Inspection
09fe2ae5-09ad-5c03-836a-2e2e39d1dd22 | note | RECORD OF CONFORMITY: ITP Signed
3e698a02-0392-51d1-b9a9-973b9631037e | note | HP*
1335e141-aeb4-5ed3-889a-ee9c3e65b608 | note | RESPONSIBILITY: Site Engineer
016ff884-5211-5e10-a419-618f623bcfca | date | Date Completed:
| checkpoint | Final Inspection
d70498f0-3eda-5c9a-9a92-324840d75313 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
029c9a23-56e0-5cb5-9a54-440dfff06c1f | textbox | Print Name:
93f481f4-557a-5a65-98f4-95347456af1c | textbox | Position:
9502b2b9-985f-5e9d-b90d-eaf2477832f0 | date | Date:
| checklist | ITP-002 - Stormwater Drainage Rev.3 | itp | ITP-002 - Stormwater Drainage |  | 3bb82801-9891-4197-a1e1-de37efce04bf
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
efb0aa49-8b38-5d63-a19b-d7cb4bbf5be5 | note | FREQUENCY: Prior to commencing any activity
29365f8a-7072-533d-902c-6ea3216a2bc5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct and complete set of IFC Drawings.
8c3a18cc-0e0b-5549-ad4b-953ab2d7b0b4 | note | REFERENCE DOCUMENTS: IFC Drawings
a1e1c73a-8021-5fb8-98dd-f2fbc97ecbdc | note | INSPECTION/TEST METHOD: Visual inspection
aa5cc3e2-d97e-5675-a947-e9361ddef5e0 | note | RECORD OF CONFORMITY: ITP Signed
c8617338-8622-5598-ac18-f99084938361 | note | IHP
f39d4d2d-b731-57b2-b125-4c18346143f7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
ad73da23-bff8-555c-bd56-fe8d15bad4b8 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
b2e9efad-2770-56c0-a5a9-44b42733b5fb | note | FREQUENCY: Prior to commencing any activity
20e47a61-2b7f-5007-afdd-3f1d62cee73d | note | ACCEPTANCE CRITERIA: Ensure all relevant project documentation has been submitted and approved by Superintendent including SMP, PMP, EMP, QMP, TMP and SEQ documentation.
6a18e801-eed8-5abf-b371-12174cc429e5 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP & SEQ
af714711-2781-5bfa-9924-2cb768628a36 | note | INSPECTION/TEST METHOD: Visual Inspection
1259a2a1-c771-51d0-a9f7-a1837db298fa | note | RECORD OF CONFORMITY: ITP Signed
44704e66-f8ac-512b-8274-b7e22c264557 | note | HP
f20d6df7-efbe-514f-9b3c-1b80963068d1 | note | RESPONSIBILITY: Site Engineer/ Superintendent
22d6643c-0c6a-5555-8f2a-8792d7da7b09 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.3 - Purchase and delivery of pre-cast drainage components
cdda52c0-7932-5f7e-ba19-cdf36d2473bd | note | FREQUENCY: Each Delivery
529448c4-fd4e-5f26-be73-105e1456a0f1 | note | ACCEPTANCE CRITERIA: Precast materials to be used for construction have been inspected and are free from defects or damage.
745f040c-a43d-5987-a0cc-8ea0d6a73baa | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.05
3652beb0-2cd2-53b1-83b6-031e659e1e93 | note | INSPECTION/TEST METHOD: Visual Inspection
9bdcd18e-b3e8-5774-bffb-b9ea235c75fc | note | RECORD OF CONFORMITY: ITP Signed
8652ec80-a89e-5f2e-817e-200dad240ceb | note | WP
82cf0db3-6c83-5287-bea5-4415c28d193a | note | RESPONSIBILITY: Site Engineer
a5ab99c0-757f-5e74-8538-f046b37dee09 | date | Date Completed:
| checkpoint | 1.5 - Backfill material Classification
5e155bc1-f6c6-5ddb-84a1-33ff4630fa51 | note | FREQUENCY: Prior to start
180756d9-1eae-5bbc-8df1-e80be41ac167 | note | ACCEPTANCE CRITERIA: Approved compacted backfill within bedding zone to be 20mm Class 3 Fine Crushed Rock as nominated on the IFC Design Drawings
327e0c50-ed9a-5433-aa23-efa98220e111 | note | REFERENCE DOCUMENTS: Dwg No. 2021-01 Sheet 1
c5c1e803-a9f6-50b4-a424-9fb05d66bd1e | note | INSPECTION/TEST METHOD: Verify
b77dcfce-54c9-56bc-ba16-f767cfca065c | note | RECORD OF CONFORMITY: Test Reports from supplier
33df889a-daf1-5b23-9838-8be9e2d3e8b0 | note | TP
2f1b80cd-cc9f-5c30-ae96-5d58d3696acc | note | RESPONSIBILITY: Site Engineer
49897166-5376-588b-9cff-81df9313ace4 | date | Date Completed:
| checkpoint | 1.6 - Mortar material classification
cf6d6c19-94e5-5b29-a275-0413cc356759 | note | FREQUENCY: Prior to start
201d3053-9328-5de9-9a93-7b4f55b5a8b9 | note | ACCEPTANCE CRITERIA: Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause 610.32.
d459f3d7-776f-58d5-a836-21a055167ccd | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.09 (e)
21aa9be1-1caf-5316-b85b-1268d8059ec8 | note | INSPECTION/TEST METHOD: Verify
146a140f-2ace-5945-8d48-136229e45fe1 | note | RECORD OF CONFORMITY: Test Reports from supplier
06c92d4d-eea1-527d-ad55-244cb7bcc2b8 | note | TP
ade3eb86-b92b-5555-bdb8-884942943c23 | note | RESPONSIBILITY: Site Engineer
9f3a8056-a065-5716-bec4-38ce255cb8c3 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
a9d6ac03-4a83-5a28-9159-2089a1f0c152 | note | FREQUENCY: Each lot
3ff42aba-a8e8-5b41-a673-3e32938ec5f7 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
64620ceb-b73d-56f8-8500-420a79f0a62e | note | ○ Plant and equipment shall be appropriate for the task.
08eb8985-f487-55a6-8943-ba6df32aff1e | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
c4824ec9-89a3-5ee7-a122-66168b7c55ff | note | REFERENCE DOCUMENTS: Excavation permit
31359d78-3716-571a-b64a-b4fad95a5a1b | note | INSPECTION/TEST METHOD: Verify
02ec4e99-dad8-5eb2-9696-535c5719420d | note | RECORD OF CONFORMITY: ITP Signed
4e1d8ec2-db9e-5c4f-bb06-ef9d61397982 | note | IHP
d4271429-0352-5ab9-b92f-db3b1443541f | note | RESPONSIBILITY: Site Engineer
487867f6-744e-5dcf-8fa9-52462802fc3b | date | Date Completed:
| checkpoint | 2.2 - Conformity with Drawings
9bb1467e-c74a-53d1-84a5-f88ea7c20617 | note | FREQUENCY: Prior to Excavation
870b50f3-67c3-5cfa-9582-658e323e3652 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the pits and drainage lines the Contractor shall conﬁrm the position of all drainage components with the Superintendent.
a6d96ec0-eb06-556c-9c7a-7d24ba27e9d6 | note | – Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
c48f477b-9fad-50f0-af21-c664476a91ff | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
6b00447e-04b5-5e35-8b7b-e17a2d6b364c | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
099c8763-a1fd-5fc1-81a8-bda5c0af1076 | note | (c) invert level of pipes at pits ±50 mm
ad83d56b-4303-5f94-bc30-d029d7e7ade8 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:200
ef9352da-0ea6-509f-bc70-1317e33ae905 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.09
ba40e3fb-af1e-544f-a74f-0bbd54447d10 | note | INSPECTION/TEST METHOD: Visual Inspection
0ee00675-e620-5349-bebd-d2bc40aede9e | note | RECORD OF CONFORMITY: ITP Signed
b53d5dd3-e350-5c4e-87ff-4243a972ab4b | note | HP
402e8718-da0b-55d8-bb71-32259851093b | note | RESPONSIBILITY: Site Engineer/ Superintendent
d0ee71c0-d1c3-5baf-98d0-3933ea5f772a | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Excavation
cceb93de-9030-5b44-878d-c5aefbb16f61 | note | FREQUENCY: Each Trench
e69e4592-5e86-5c74-aa73-b40411eff8ba | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm.
7252bf62-a213-52b9-82e1-cf70c75894e7 | note | REFERENCE DOCUMENTS: VicRoads Standard Section Table 701.151
a0e2d43e-bfc0-56ee-adc8-80d503692ed8 | note | INSPECTION/TEST METHOD: Visual Inspection
3b8a6b91-1220-542b-95b0-9d9ebb607049 | note | RECORD OF CONFORMITY: ITP Signed
442cdbb2-4e3d-5b38-b326-89fcc59a1443 | note | HP
ab38704a-82fe-5303-9a0d-e357ddb65645 | note | RESPONSIBILITY: Site Engineer/ Superintendent
21d07714-b58d-55c1-9a83-b2fe8e5ad1d7 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Compact base of trench
4af5b7dd-78cc-594b-b208-040b965abf6a | note | FREQUENCY: Each Trench
0a4f961f-64e9-5670-b1c8-241ccfb44d5d | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant.
f3d7804a-3e39-5932-b8df-b56d1a0c1318 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.15
4bcb5aee-688e-51d0-b47a-b337a9496407 | note | INSPECTION/TEST METHOD: Visual Inspection
a473d711-6387-5889-a890-d3b146f1a49e | note | RECORD OF CONFORMITY: ITP Signed
23351b6e-156d-5ed9-a49a-033cd4a51ae2 | note | WP
51e777c6-5f3f-55c2-aa05-b1c586a666fa | note | RESPONSIBILITY: Site Engineer
2c703253-14dc-54d8-959e-be2b405241d4 | date | Date Completed:
| checkpoint | 2.5 - Placement of Bedding Material
69210fcf-45c3-5094-850e-a67384556d56 | note | FREQUENCY: Each Trench
d242bdc9-be65-566d-b551-629bd2116ee2 | note | ACCEPTANCE CRITERIA: Bedding material shall be compacted to no less than the below thickness:
657cfdff-3c4a-527c-be72-f63961a07434 | note | ○ 100mm where D < 1500mm
c5832961-2028-5b62-b3d4-18161d801666 | note | ○ 150mm where D > 1500mm
00ff0557-c8c7-5eae-8440-a180f1e9e8d2 | note | – where D is the nominal pipe diameter or culvert width.
6103666d-32ce-5750-9ad3-8e32a8f28897 | note | REFERENCE DOCUMENTS: Dwg No. SD-D8-1 Sheet 5
f3751d24-43e7-57d4-a28f-97608b9ef969 | note | INSPECTION/TEST METHOD: Visual Inspection
9b56275e-4739-54e2-843e-cf95caa849b5 | note | RECORD OF CONFORMITY: ITP Signed
a1e5819a-ddd5-5bac-be59-6724e67d3bd6 | note | WP
076abb55-1e95-595c-a757-3f526a589c73 | note | RESPONSIBILITY: Site Engineer
bb6a6439-f021-5e18-a320-24b07e9a129b | date | Date Completed:
| checkpoint | 2.6 - Laying of Pipes
a3318a74-2f02-59d1-b8d4-f54bb88265c3 | note | FREQUENCY: Each Line
b11e3107-43e0-52c9-bd37-854bf85d204f | note | ACCEPTANCE CRITERIA: Laying of pipes shall not commence until the Contractor has verified that pipe bedding complies with the lines and levels of the design drawings and that pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively.
41aaa0b6-1a41-59b2-a5d1-5331d29f0399 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.17
5729fca9-0d59-5668-af3b-328bd1b89790 | note | INSPECTION/TEST METHOD: Visual Inspection
769051e9-f124-5c1e-918e-35fbc527a83a | note | RECORD OF CONFORMITY: ITP Signed
2a7a9106-365b-5c5e-a38d-bdb018c67989 | note | IHP
5c2a8904-2403-5d8a-8acc-30afa3bf69ef | note | RESPONSIBILITY: Site Engineer
c934815e-e919-5800-ac3b-cd712320d5b4 | date | Date Completed:
| checkpoint | 2.7 - Jointing Pipe Sections
48dc99de-49d6-5081-8251-6af763729d5f | note | FREQUENCY: Each Line
a522dd3b-1fac-5c4f-9a43-7d7d1ed79d61 | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance with manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
b9ec57eb-40e5-5aae-b464-2c845be056cb | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.18
ad5a3c18-7207-5313-8673-8905e4b83715 | note | INSPECTION/TEST METHOD: Visual Inspection
78bb08b9-730e-5bb2-b9e5-8bc09525b28f | note | RECORD OF CONFORMITY: ITP Signed
5f296ec4-9104-567c-a14f-6d862a315149 | note | WP
800bab92-554e-5aee-8ca4-0cb224651d20 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cfe0b155-e981-54ed-a96b-550e6d09ba5f | date | Date Completed:
| checkpoint | 2.8 - Jointing to Pits
b62528e4-2124-5278-a383-a97013a7a853 | note | FREQUENCY: Each Pit
3ab802fa-f552-527a-9a45-7ff46236b3df | note | ACCEPTANCE CRITERIA: The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33.
ec4f8d94-a406-5329-90fd-18d1722986c0 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.15
f493b306-8674-5b8b-ae4f-be93ef0eb940 | note | INSPECTION/TEST METHOD: Visual Inspection
838b6ae8-d584-5dbb-8080-e4a6ab5936e3 | note | RECORD OF CONFORMITY: ITP Signed
d240111e-d037-5b0e-8c36-521cea622fa0 | note | WP
af700079-fb5a-5246-a897-8609990b8549 | note | RESPONSIBILITY: Site Engineer / Site Foreman
cb05ba14-3784-5407-b2a1-e98c8ed29b8a | date | Date Completed:
| checkpoint | 2.9 - Place & compact backfill material over pipes
f0c80b9e-2c34-569d-aa2e-bf71fdc0d0a0 | note | FREQUENCY: Each Lot
f42a0bdf-1d31-5f6a-b2bb-a6a874235057 | note | ACCEPTANCE CRITERIA: Unless the pipe is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
a89e73b4-e249-5d24-967d-dc4c0ab5774f | note | (i) Culvert Under Area not to be Paved: The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
d6ab90a3-e163-5a74-88c0-ff88aabf9e76 | note | (ii) Culvert under area not to be paved: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
77e89e0e-0f4b-56c3-acba-5154b5326435 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.19, Dwg No. SD-D8-1 Sheet 5
6087735b-a89c-5283-b59b-0ab5939c28ee | note | INSPECTION/TEST METHOD: Visual Inspection
09541039-c5cf-5ea5-86a1-858930441681 | note | RECORD OF CONFORMITY: ITP Signed
24e8c9e9-fbbc-5e32-8e38-748640a5b847 | note | IHP
0b45058f-9689-589b-aa48-36b85337bcff | note | RESPONSIBILITY: Site Engineer / Site Foreman
5c9a185a-b91a-5c01-bd98-ccea885f5a33 | date | Date Completed:
| checkpoint | 2.10 - Place & compact backfill material around pits
eec81dc6-0ae5-595e-9192-71299db5df43 | note | FREQUENCY: Each Pit
21b1363e-7439-554a-9fca-20065838bb06 | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment
9d5c0c5b-97b2-5bec-b891-267bdaaa58fb | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.18
de81fa97-577f-5dcb-88a9-4b2f627acda5 | note | INSPECTION/TEST METHOD: Visual Inspection
ff425563-da96-53e8-8d92-fadea1698be4 | note | RECORD OF CONFORMITY: ITP Signed
764211af-4464-5054-9228-2a232ab39771 | note | WP
ddfe6ea4-4581-5a7b-ae5e-08650b7f885c | note | RESPONSIBILITY: Site Engineer / Site Foreman
bf6aac3c-6ffb-5b6f-8efc-7f2ef6417682 | date | Date Completed:
| checkpoint | 2.11 - Backfilling with 3% cement stabilised
a459758c-bc5e-52d2-997f-ebf5ec651772 | note | FREQUENCY: Each Trench
8bec77c4-fcb2-57c5-897a-f646fc7b8dd0 | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised FCR with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
031644b1-c05d-50e5-aca5-23ce9c95d34c | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.19 (c)
3da9f0e8-88ee-5610-982d-652c05202855 | note | INSPECTION/TEST METHOD: Visual Inspection
f854810d-6c5e-5794-aeaf-0a6bb13f2712 | note | RECORD OF CONFORMITY: ITP Signed
af547e94-01ef-511f-a849-099b867cc750 | note | WP
71e5e5c8-c1cb-593e-bd8b-60de34d72222 | note | RESPONSIBILITY: Site Engineer / Site Foreman
596bb4ff-227f-596c-8f50-6baee656e44e | date | Date Completed:
| checkpoint | 2.12 - Step Irons & Ladders
0818dc87-b08c-54ac-911d-f15ed3f8c686 | note | FREQUENCY: Each Pit
b79f3f70-8f9d-5a7b-9566-a02e0459c3e1 | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0 m deep shall be fitted with step irons or ladders in accordance with AS 1657 and this Section.
11516a01-639b-5f5f-953b-14d0d97b228a | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.12
c0d9e029-db72-5264-b0a2-4a8bc86cd820 | note | INSPECTION/TEST METHOD: Visual Inspection
2b85b002-ad59-5855-8513-d41c5ba731a7 | note | RECORD OF CONFORMITY: ITP Signed
44fa5efe-1f77-5f60-8ce9-888cf2ac8129 | note | WP
5fdd2951-9472-5dbf-91e4-3c0d5bbe05ae | note | RESPONSIBILITY: Site Engineer / Site Foreman
1718258c-7b3b-5dfb-99b4-ea4784e3b700 | date | Date Completed:
| checkpoint | 2.13 - Construction Tolerances
8864fb52-6245-5eb1-adf5-89affb109aef | note | FREQUENCY: Each Lot
6ba09cad-2f17-5443-ac51-3744205c6bd8 | note | ACCEPTANCE CRITERIA: The tolerances listed in Clause 610.47 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
6f836377-e8bb-5e7a-b25e-f2cb532de4a0 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.19
cdeda58c-5cd2-5a3f-be01-1e5e04acb04e | note | INSPECTION/TEST METHOD: Visual Inspection
1a92dae6-fd20-5080-84f6-954a3591cd26 | note | RECORD OF CONFORMITY: ITP Signed
78b3e54f-e927-5ff4-aedc-e1465f5cdfd2 | note | WP
6f9a8558-4cad-5be1-8cbb-d4fc68eef6a4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
f0e44afa-291b-52ec-9f2d-e8660b846a48 | date | Date Completed:
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
aa91138e-9590-5908-acee-2a8d3431ae61 | note | FREQUENCY: Each Lot
2803694b-28e0-5802-806e-8e200f9334f4 | note | ACCEPTANCE CRITERIA: The Contractor shall test the bedding and backfill material at a frequency as shown in Table 701.291 to ensure that all materials comply with the specified requirements.
f1f8fe9c-2668-5f12-9c19-c76638e18bc6 | note | REFERENCE DOCUMENTS: VicRoads Standard Section Table 701.291
69f605e8-bfa5-589f-8e1b-7eee6d87c0f6 | note | INSPECTION/TEST METHOD: Verify
256ba32c-8457-5780-a073-c317b5eec228 | note | RECORD OF CONFORMITY: Test Reports
fad6afbd-ade2-573c-b11d-e749192c5a7d | note | TP
16082725-ca12-5faa-b743-0a6b212196fb | note | RESPONSIBILITY: Site Engineer
7ce3cac7-87e3-5b6c-a04e-75fd8c02fbd2 | date | Date Completed:
| checkpoint | 3.2 - CCTV inspection
278b9c1b-5469-5de6-b13a-80ad474ad2ce | note | FREQUENCY: Each Lot
4533c949-23dd-56c1-ba22-731357112e6b | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
04638220-dc85-5b26-be47-d5e952ffe0a0 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.3
c267e23a-ca79-5bc1-b825-a766439d3d72 | note | INSPECTION/TEST METHOD: Visual inspection
af4c43d4-cf85-5bd6-b969-8fb5b5f1ff58 | note | RECORD OF CONFORMITY: CCTV Report
e12f7453-f817-5ece-91de-4142eb939808 | note | HP
bdc112c0-1b0f-5767-844d-248c423c4d7c | note | RESPONSIBILITY: Site Engineer/ Superintendent
cb635259-f303-55c7-bc20-a6f8f6f96173 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.3 - Repairs
a9f06ffe-8326-55df-bb9f-de88dd69408c | note | FREQUENCY: Each Lot
f225d2bb-62f5-589f-ba9a-796091bfa6c3 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
686ca80f-0f2d-58ae-bc9e-7b3f2a269249 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.31
61e303c6-ff02-5dd3-8ea8-5dce1e12b599 | note | INSPECTION/TEST METHOD: Verify
2b324f88-ad6b-5c2c-a352-1e800435a76c | note | RECORD OF CONFORMITY: ITP Signed
c19306c5-abdc-5bf8-bff5-60282fd6255c | note | IP
5d377e1e-9aea-5a95-8d58-b77123863476 | note | RESPONSIBILITY: Site Engineer/Superintendent
2a97a3ff-65ec-5c60-8582-92e8184bb9cc | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
cbe7579c-a674-5414-b090-49f5d8ef7276 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
12942072-3058-52ab-b526-3de8f8552846 | textbox | Print Name:
16c36941-896f-525d-b28e-50c8651f7c87 | textbox | Position:
b5b9668e-aceb-5140-81d1-74fc44597349 | date | Date:
| checklist | ITP-003 - Subgrade Preparation | itp | ITP-003 - Subgrade Preparation |  | ad6913a4-daa4-4d21-bb59-9b199b90a303
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
1d0fbee8-3383-5bf9-928f-25f13f3b365d | note | FREQUENCY: Prior to commencing any activity
ba1f7c61-2f97-5f03-91bb-14241115e508 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
aa1e2b28-feab-589b-98ee-a1fa749426a9 | note | – using the correct and complete set of drawings
f5007799-9cdc-5de2-9eff-66e6d086d4e8 | note | – all drawings are the latest revision
19f4d24d-df78-5514-ba71-643f09b4147f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
be94ebdd-70ab-56e4-81ec-d7987c883398 | note | INSPECTION/TEST METHOD: Visual inspection
041ab8c5-0bfe-51e4-a348-ee870e166a83 | note | RECORD OF CONFORMITY: This ITP signed off
4b0b8624-351b-51c7-a17b-f0d3165db0cc | note | HP*
f83efd59-e753-5ebd-83f2-aaddba1ae56e | note | RESPONSIBILITY: Site Engineer / Site Foreman
fbbdd944-9f55-58d7-a2fe-5cc367d9b691 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
7586f9a9-925c-5d05-8a1f-1bedbcab4433 | note | FREQUENCY: Prior to commencing any activity
e097a3b4-41fa-55d5-ad62-700088bdfd0b | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
0ce74379-1a3b-51e6-9ac0-a1a5dc24f500 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
5353f9aa-d815-521b-8637-02ebdadc02f1 | note | INSPECTION/TEST METHOD: Visual Inspection
7b6644c5-fc3f-582f-af61-234beb02e3d1 | note | RECORD OF CONFORMITY: This ITP signed off
7c26c030-14c5-59d7-afeb-b4943ae4d8cf | note | HP*
d7054964-c3cb-5013-aa86-96d9d132be9d | note | RESPONSIBILITY: Site Engineer / Site Foreman
e6417e83-0f70-5407-b0b8-73c0994878d7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
d67f9718-b9b5-536f-98e4-b66fe4f6f249 | note | FREQUENCY: Prior to commencement of excavation
53087338-3691-588e-b1fd-a7b43b74bc53 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
5d4227cd-9f12-51b5-8d13-19a121834257 | note | REFERENCE DOCUMENTS: Work Procedure
adf958e8-b93b-5097-9c33-ac2fc3a945d9 | note | INSPECTION/TEST METHOD: Verify
b75b29c5-421a-5a56-8bb0-6899f6cec753 | note | RECORD OF CONFORMITY: This ITP signed
12d4be69-9241-560d-a35f-e44373fd3ebd | note | IP
fe7bddda-747e-5f01-8905-e95d47197585 | note | RESPONSIBILITY: Site Engineer/ Surveyor
f7003609-a8b5-52e2-a901-5cd848d8406e | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
8e921500-cce7-522f-ab69-f361893f12a3 | note | FREQUENCY: Each lot
68a1b683-e812-5c10-8b98-ee3c10b9777f | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
b6977cc2-9eb7-5753-b9ef-666288936b6c | note | ○ Plant and equipment shall be appropriate for the task.
4cd1cada-397b-58f7-a112-f38a91e7c504 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
1efb04ac-9935-5f46-9555-2775ada7d5d3 | note | REFERENCE DOCUMENTS: Excavation permit
56252833-75fd-58a6-b720-fd6f26c3c112 | note | INSPECTION/TEST METHOD: Verify
c8e78bc8-9c85-5d31-ae0f-aabae382137a | note | RECORD OF CONFORMITY: This ITP Signed Off
8d341e46-bd6c-54e6-a258-30695ac1053a | note | HP*
f1312e18-0514-5972-ae0c-0f13a4d3676a | note | RESPONSIBILITY: Site Engineer / Site Supervisor
cf941502-7559-5c8d-8d78-fe23cc85a5f3 | date | Date Completed:
| checkpoint | 2.3 - Subgrade Material Properties
082b5eaa-d9d3-5e30-9f7a-ea53433e1568 | note | FREQUENCY: Each Lot
8b6f9b57-ff32-54ac-83b0-d4fa393af38d | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
f41c8269-dddf-5c4a-98c5-7e5e9c63e32b | note | ○ If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
11fb1061-fc13-5c21-a272-2e4cb658e59f | note | REFERENCE DOCUMENTS: Cl 204.06e
3ef9425c-3b78-53a5-b803-cd244cb5a4c1 | note | INSPECTION/TEST METHOD: Test Point
1409e85e-ddd0-5291-b0e2-96b076c7fdd1 | note | RECORD OF CONFORMITY: Test Reports
2808a61c-79bc-5479-bc3c-a2b48deef94f | note | TP
d09a429e-bff6-592d-bc3c-cf29a95c2e0c | note | RESPONSIBILITY: Site Engineer / Site Supervisor
a83dd765-0ab8-5342-b484-b886f49e7002 | date | Date Completed:
| checkpoint | 2.4 - Inspection of Subgrade Material
788653b6-5b3b-5e62-88e6-cb7f3abe2f9a | note | FREQUENCY: Each lot
ca57755f-fa99-5d08-ae4c-db873a50bea8 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
fe3b811c-df85-5390-b630-96c018cb60e0 | note | REFERENCE DOCUMENTS: Cl 204.06c
7b93ee00-be6b-5bd6-b8aa-1e8d2ea5a7cc | note | INSPECTION/TEST METHOD: Verify
a35f6a2b-340d-5b1a-852b-25d714828147 | note | RECORD OF CONFORMITY: This ITP Signed Off
60688238-4c53-5f6c-8e32-a3db91b7644f | note | HP
75e573e4-176e-5343-958b-9cef9b52b639 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
007e943d-c8a8-53ae-8a97-df8ef375b4e7 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.5 - Material classified as silt
14b3b9e6-dfdf-5976-b348-d37005ae08dd | note | FREQUENCY: Prior to Commencing
c781522c-cb43-52f9-9808-dfbd829adb4b | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
b79e7607-2560-557b-8b5d-87c317b41d97 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b)
a2bb8ace-d6cb-5f3e-8594-d623061adafa | note | INSPECTION/TEST METHOD: Document Review
3014fca4-3687-5d43-b7da-4ba6743db4ec | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/records
2f61a3e5-b6e1-5a59-b2e9-e083ed7d4a40 | note | HP
0c823502-888c-52ca-8994-4c3e9a94665a | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
f9b807f7-6634-5bca-a664-c02e0b3ff424 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
951bd435-efd5-560e-8749-63a90b59c197 | note | FREQUENCY: Prior construction of the regulating layer
f1e5ac9d-76cf-5063-bb82-82b2e4890e9d | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
ee52dfbb-4427-55b9-a4e7-63d20b454cbb | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
45fcd720-b9cf-5447-8d1b-fde1af9be58e | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
a79c65d4-57fd-5aa0-b308-96c2b9c4ebda | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
5544506a-cbd5-5f24-b991-168b3994ea18 | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
bbaeee08-6b73-50c7-b9e9-77f7b1dffe09 | note | HP
b009252f-de05-5645-a505-03ca01afffbd | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
741aa5f3-dc91-51a1-a8bb-b19c2df6b5c0 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.7 - Unsuitable Material
c028deb3-bd2b-5233-bd96-5bd526d205a8 | note | FREQUENCY: Each Lot
367d2689-e38a-5d4b-a0ca-d07640e6e5bb | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
e16bd05f-d52c-5d81-bfd6-39b13bd22524 | note | – As per RFQ Section 200, Clause 200.3, the unsuitable material shall be jointly inspected by the Superintendent to determine the extent of the rehabilitation required.
22912137-61bc-50dd-a698-6a43cc4bf8ff | note | – Backfill of excavated area shall be with Type A material.
c55c4bc7-d675-50bf-b54a-07ad89e02c47 | note | REFERENCE DOCUMENTS: 204.07(d), RFQ Section 200, Cl 200.3
5ae90706-f1f8-58b0-9ae6-67f44a8d38b1 | note | INSPECTION/TEST METHOD: Visual Inspection
a5e1476e-af9e-5422-952a-e2d076b9ce95 | note | RECORD OF CONFORMITY: This ITP Signed Off
571eead6-45a0-5d28-b21a-fa09e0eae577 | note | HP
9f653d99-d200-5c4d-ae00-b6e7478623ce | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
dd40d59c-6c89-593c-8d9b-a39c7de84cdf | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.8 - Groundwater
c89fe1f1-28d1-54fb-a49c-8f057aba14e4 | note | FREQUENCY: Each Lot
2f1f6166-b307-5fe5-80a8-3296717cdfb0 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
ce769d8b-5d86-5d6c-a78d-e9cfb9a9e9a2 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
9a346da2-fe52-5182-8660-78ed2d55155e | note | REFERENCE DOCUMENTS: 204.06 (h)
86b20980-f235-582a-a2b9-e4f4aedcc80d | note | INSPECTION/TEST METHOD: Visual inspection
3e16fb49-4505-56bb-a048-e276e0e7a039 | note | RECORD OF CONFORMITY: This ITP signed off
00ebc5df-9002-5407-84eb-ab68edcce2bd | note | HP
3afd9255-8ec4-5776-b31d-b30de1885753 | note | RESPONSIBILITY: Site Engineer/ Superintendent
cb6066ad-20c8-53a9-8e78-0f1f8cabc13b | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.9 - Subgrade Level and Shape
62ca0608-ff4b-504b-88d0-3dc96462a941 | note | FREQUENCY:
7734e078-3f1f-563c-8995-0bed248d220e | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
457b48b5-935b-5572-97f0-ac59ab00e962 | note | Scale B:
cd9fca50-1d13-5a69-bdb9-3a2a1710cbca | note | ○ Measurements per lot = 40
e4fa4549-c902-5b4f-bff6-f71af99d83cb | note | Surface level tolerances:
ff46d3b9-2de3-58d2-98ba-3fdd17acb270 | note | ○ Range x = +5, -25mm
d5ae94d4-b107-514c-93f5-95d4382a068f | note | ○ Standard Deviation = 15mm
477ba564-0eb8-5d70-b4d7-97757cfb7f35 | note | REFERENCE DOCUMENTS: 204.03(g), Table 204.031
5fc3fa81-873f-5112-b772-64531f9eb4af | note | INSPECTION/TEST METHOD: Survey
c8476226-772c-58cd-b7ce-c40021c3d8df | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
2b6df124-ee9f-5be3-a6f0-d8ec0bfffe97 | note | SCP
eb84ae28-cdfe-5286-96dc-1d447050e645 | note | RESPONSIBILITY: Site Engineer / Surveyor
0d1e147f-37ec-552b-b99d-8ea42698edf4 | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Proof Rolling
c07c4ea6-db18-514a-ad59-a14f74a09908 | note | FREQUENCY: Each Lot
2831dc8c-e5d6-5278-88dc-48f8228cfd4b | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
4ead81b1-a0ba-5d85-bbea-c77326dbd485 | note | REFERENCE DOCUMENTS: Section 173
c003997d-3dd4-579c-ad08-19c906a600bb | note | INSPECTION/TEST METHOD: Visual Inspection
101fc022-db2b-589e-9119-c86b6da63db7 | note | RECORD OF CONFORMITY: This ITP signed off
ca276e36-e2ed-5201-aafc-c8782c4479a4 | note | HP*, WP
c7f1b5c4-2a64-58a2-b66e-e2a0820c0480 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
a1e379c9-b5c9-52b1-aeb3-2089c0bfcdba | date | Date Completed:
| signoff | Signature Required
| checkpoint | 3.2 - Compaction Testing
3f7ec775-eb73-5afb-aa89-c691c796235f | note | FREQUENCY: Each Lot
5c117415-6e29-5306-be76-cbe81cf7b091 | note | ACCEPTANCE CRITERIA: Scale B
158ee682-8e96-5b70-81ee-c9c1b9016f12 | note | ○ All Type A Material = minimum mean value of density ratio = 98%
a7e81b9d-582e-5f2a-a7bd-a38bc4a9ea6c | note | ○ Ripped and re-compacted material below Cut Floor Level = minimum mean value of density ratio = 98%
13b8c96b-025b-57b6-86d3-625fa385a90d | note | REFERENCE DOCUMENTS: Table 204.131
7f144695-0276-55c3-be0c-d4ca4382d0f8 | note | INSPECTION/TEST METHOD: Test Point
d25fe6cd-2235-5cc2-9388-ae10f092cd4c | note | RECORD OF CONFORMITY: Test Records, Lot Register
c3347baa-eea8-5c41-ae59-192c5bd0abf2 | note | TP
bb2fb5f9-fa85-50d7-b29e-7694fbd66fb6 | note | RESPONSIBILITY: Site Engineer
c6adaaf9-0b28-5d4c-be02-d4c5169acf78 | date | Date Completed:
| signoff | Signature Required
| checkpoint | Final Inspection
f31ecf13-a462-519c-b0b0-6558c3496b94 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
681ee33a-2949-57b6-919c-cff447942ffe | textbox | Print Name:
342b000c-4ee3-598c-aa67-f867cf676074 | textbox | Position:
a4d645e2-8dcd-5d9e-814e-624d282d0f68 | date | Date:
| checklist | ITP-003a - Sub-Base Construction | itp | ITP-003a - Sub-Base Construction |  | 1ca5d64c-02c9-4adc-921e-4a676892f617
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
79579c20-ccbd-5da1-b538-66f6be218115 | note | FREQUENCY: Prior to commencing any activity
1622f108-c836-524e-b66b-53c079a72792 | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
1c1c4d84-b157-5315-b130-5c622ddb0d98 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
0b313cb7-058c-5edf-ab13-e3c271bc833c | note | INSPECTION/TEST METHOD: Visual inspection
cc57be8c-2074-5b05-b1c0-2d38273228d5 | note | RECORD OF CONFORMITY: This ITP signed
3575249f-444e-58dd-b27f-9ffb2e995897 | note | WP
fad7155b-ff9d-5b39-86b6-e8b1c108ac1a | note | RESPONSIBILITY: Site Engineer / Site Foreman
4dd3539e-c531-5dc3-9ef3-595c6084d66d | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
13b658ca-6551-5baf-8893-f0cdbbbc526a | note | FREQUENCY: Prior to commencing any activity
d09d14cb-dfb5-5557-bbd0-5fc5c3b4acec | note | ACCEPTANCE CRITERIA: Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
5da82730-22dd-5470-a3bb-22894fa2643a | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
c59c2e69-6b8d-576d-b699-7fdfd171aa34 | note | INSPECTION/TEST METHOD: Document Review
1b8cae77-6285-581e-b638-b09a3f730edf | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
60751f30-f99b-5436-8f3c-306151f593a4 | note | HP*
06609aae-4c61-5cf2-891c-d904a4e6deb8 | note | RESPONSIBILITY: Site Engineer
b3e25d8a-9f0b-5226-a6da-423300952ae9 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
2ce44622-d803-5166-92d2-9a088c32c13f | note | FREQUENCY: Prior to commencing any activity
19c08732-88c5-5f26-92fd-170cdb9d02b0 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
aa63610a-b599-56ba-bbfe-fa4ac3e8260a | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
e2beeac3-2cf5-50d3-b273-74676729bc69 | note | INSPECTION/TEST METHOD: Visual Inspection
ef756af7-f132-577b-8e29-64f8f3ea3b3c | note | RECORD OF CONFORMITY: This ITP signed
a7708332-e976-5b32-8b50-f3e1bc4bb276 | note | HP*
7fc62674-4078-5454-905d-f6daa170dbf7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
87942380-f493-51b1-981e-1f21c272e03f | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Transverse Joints
edb35fd4-e058-598f-8d34-dbfecea6f054 | note | FREQUENCY: Check prior to placing material
aaf75f3b-1a52-56b2-a445-5c121588f0fc | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints
351c5e18-584d-5bb0-9798-c16d9157cd6a | note | ○ Transverse joints shall be offset from one layer to next by not less than 2 metres
3cdcf979-d252-513a-871b-706ec71e2ac2 | note | REFERENCE DOCUMENTS: Cl.304.08 (a),Cl.304.08 (c)
876c7a82-0f7e-5f47-86f3-29f97cb19fcd | note | INSPECTION/TEST METHOD: Visual Inspection
67362aeb-5c14-5fc5-8c96-0a8240ebc108 | note | RECORD OF CONFORMITY: This ITP signed off
bd59a5f9-8196-58bb-915b-5ac892155b82 | note | IP
76c1880a-d8a5-514b-9af6-d22b9efb4648 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b9720443-2388-57ad-9443-3a7bc7c4b082 | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
8710c318-28bb-5954-9410-08079befd2c7 | note | FREQUENCY: Check prior to placing material
3c0926c9-17dc-5ab8-a6b6-0177d20562cd | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
c367e7dd-b2f7-58e8-8dd2-c883c0bc5cbb | note | ○ Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
c778b40a-9122-5520-a5f0-362177df0a8a | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
16f99eb8-c9c7-570b-bb1d-48a7a06ab6f7 | note | INSPECTION/TEST METHOD: Visual Inspection
5e0537d5-657e-52bb-91b5-b52618d7c0a9 | note | RECORD OF CONFORMITY: This ITP signed off
ae2b588a-f39f-57f2-8668-caf2a666d65e | note | IP
1937fefa-e7a2-5239-afe6-2662089ab953 | note | RESPONSIBILITY: Site Engineer / Site Foreman
851f2865-2b29-5f56-9bfe-a71096779b0e | date | Date Completed:
| checkpoint | 2.3 - Lot Size
7ca07670-b402-5123-8db2-48867f6ed0a8 | note | FREQUENCY: Check prior to placing material
d122ea7a-e1e2-5ee8-aa30-7cf627951aa2 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
e29a64ec-469f-5144-9d12-31cd99b4d765 | note | REFERENCE DOCUMENTS: . Cl.304.09 (b)(ii), Table 304.121
4c6703f8-c329-505d-970f-641c8531fa32 | note | INSPECTION/TEST METHOD: Site Inspection
5b191234-899a-5783-ac9c-62aba8a8d1b4 | note | RECORD OF CONFORMITY: Signed ITP
9181ef51-8cb4-5d3e-9c05-341c600f5e04 | note | IP
7de093e5-b9b0-5090-85ff-8928eb4a8d0e | note | RESPONSIBILITY: Site Engineer / Site Foreman
83d1db4c-c418-5ef7-8190-114cbad68fea | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness
033238fc-f7ef-540c-8758-a2c9ca7aeb2b | note | FREQUENCY: Each Lot
64fd8bd4-9a8a-5e4f-bcff-e9747273cfaa | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
540bd8fd-3a3e-563f-8bc9-881b1b1a1b68 | note | REFERENCE DOCUMENTS: Cl 304.07b
fe39f3b8-3827-51ce-9941-c96686004872 | note | INSPECTION/TEST METHOD: Site Inspection
a133f09e-d925-57fb-a0ac-b4309c35cce2 | note | RECORD OF CONFORMITY: Signed ITP
c2b5a30b-d8c2-5763-babe-cbc52da1377d | note | IP
9fdfd4c3-5c99-5a35-b961-fa3fdaf33e56 | note | RESPONSIBILITY: Site Engineer
aa997459-6548-5571-a230-ee2e7254b034 | date | Date Completed:
| checkpoint | 2.5 - Proof Rolling
cf3631e1-adfa-5d65-9385-26f6ba4a23af | note | FREQUENCY: Proof Roll each layer
87d57c04-9968-5c68-9cec-6620d67dfdbd | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
18c900b3-3f3d-55b6-8ee1-20ca371ab731 | note | ○ Static > 12T
70affe28-9c96-5b4c-a30d-a1c76e747490 | note | ○ Pneumatic > 20T
8168096a-3bad-51ec-b163-21e03dc8a81c | note | REFERENCE DOCUMENTS: 173.03
5c808518-f0be-59f6-8f80-eb84dc09e5e3 | note | INSPECTION/TEST METHOD: Visual inspection
dcadf6fb-75c3-5f78-92ca-b46025eb402c | note | RECORD OF CONFORMITY: This ITP signed off
a1b44514-1e01-5bcc-8980-3c0c99cf4748 | note | HP/ WP
e4108e20-4733-58b4-aff4-2c76025f5099 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
7acbbb19-000c-56eb-9789-b9622229509a | date | Date Completed:
| signoff | Signature Required
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
3cd19c0a-3d5b-5843-b737-99db270cc8c4 | note | FREQUENCY: Prior to Testing
233efb85-571b-5787-8ee1-5ce968971e79 | note | ACCEPTANCE CRITERIA: Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
54aa1e9c-f727-53f4-909a-bf8a6990acad | note | REFERENCE DOCUMENTS: Cl.304.09, Cl.304.12, Table 304.121
97cfdca4-3547-5149-9063-e9b8463ce792 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
2d8a9ecf-6ba5-56e1-9992-6c48f322e027 | note | RECORD OF CONFORMITY: Signed ITP
87cd144d-a23e-5801-a3db-a36225c37f95 | note | AP
213d531d-ef07-563e-a2ce-3933774431ec | note | RESPONSIBILITY: Project Engineer
6e95e309-7b8d-59b8-a97d-0056d530c67f | date | Date Completed:
| signoff | Signature Required
| checkpoint | 3.2 - Compaction Testing
3de941e5-5d0a-5276-9e01-00dee32ffe9c | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
c68c39ba-18bc-5c76-a7df-d4aab0e680a4 | note | ACCEPTANCE CRITERIA: Modified Maximum Density Ratio of not less than 97% & 98% for Class 3 FCR & Class 1 FCR respectively for road pavement as per Contract Drawings 2021-01 sheet 1
a6d1a914-4924-5a0b-aa50-e999b68b4bb0 | note | REFERENCE DOCUMENTS: Contract Drawings (2021-01)
3f1ff5d0-f129-5c1f-9891-51fbe1181022 | note | INSPECTION/TEST METHOD: Test point
c6434ac8-d511-54a0-a257-f7836c47df34 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
43558c15-ea8c-58f2-8ae3-a32bb3dd9391 | note | TP
3fac5bc9-502a-5682-9e0e-f533d9cb6588 | note | RESPONSIBILITY: Site Engineer
b26e2e3f-cfc9-5512-9e7a-8cc9a0b2a6a5 | date | Date Completed:
| signoff | Signature Required
| checkpoint | Final Inspection
084a7e18-1724-5322-a8c0-54a4eb23891d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5f4a391a-7ff2-5084-a4e9-6292ac7de3d4 | textbox | Print Name:
24b8b443-49a1-596a-b8a4-1e44017617b1 | textbox | Position:
ffd7edf0-52e4-5eba-aaba-089cca114505 | date | Date:
| checklist | ITP-004 - Kerb and Channel | itp | ITP-004 - Kerb and Channel |  | 59b89191-9691-44f7-8b1c-1c912d916011
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
93e141e1-d5b8-5fa4-b370-d55bd4b35d3f | note | FREQUENCY: Prior to commencing any activity
ab374436-4cbc-5152-a821-2f7badcd5159 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
542b4483-46bd-51fe-bc07-4192ff7ced7a | note | – using the correct and complete set of drawings
902a5ae2-b340-5d41-9a88-b7347e87175c | note | – all drawings are the latest revision
2b3e15d5-876f-50f0-997f-6427e3e226d2 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
f03cd76c-2f33-5250-a20b-f4d1592f18bc | note | INSPECTION/TEST METHOD: Visual inspection
d7aaead4-50e1-5f68-b15c-af2f85ef0814 | note | RECORD OF CONFORMITY: ITP Signed
4fa2c78e-852e-5038-b4ed-2bfab056ae9a | note | HP*
620dca21-3cfa-55e1-9959-fe06e5479c54 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ac35573c-6297-5638-bee1-ceabb89a013d | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
0318efe8-e737-5cda-a77e-6aa3e15efedb | note | FREQUENCY: Prior to commencing any activity
03735cd9-178a-5428-a5c6-bf931a2526d6 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
86242d9c-0ed8-587f-9e5a-6004eed6189a | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
cce7c730-24bb-571a-ab44-39d972695b58 | note | INSPECTION/TEST METHOD: Visual inspection
affada82-65d6-550c-9bd5-93305d25411e | note | RECORD OF CONFORMITY: ITP Signed
551df8a1-82ae-5ed6-9895-599a79370e47 | note | IP
eb38af4e-6bf2-5610-b1ac-3a83772487e8 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
efe9aa5b-1d4d-5712-9d4e-cc146758fd4b | date | Date Completed:
| checkpoint | 1.3 - Mix Design
111ad1d5-34ac-5d3d-8e10-677fe29615dc | note | FREQUENCY: Prior to commencing any activity
b1ea27e7-cce8-553e-ba2a-9425c6ee4372 | note | ACCEPTANCE CRITERIA: Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
5535054a-48f6-5197-b30f-c06c04bfdcf3 | note | REFERENCE DOCUMENTS: AS 1379, Cl 703.07, 703.05, 703.23
bfb4220a-7130-5a99-bde5-f67bae44e665 | note | INSPECTION/TEST METHOD: Verify
b714c945-9153-5c44-b561-96ccd4b24333 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
89cca9fe-b847-5a57-b02e-698bbbdff2cc | note | HP*/ WP
0fa40a7d-42fc-5380-bc41-161f67d49015 | note | RESPONSIBILITY: Site Engineer/ Superintendent
c917ac7a-3a24-5633-a9c3-6b70982b3b39 | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
569a6806-e1df-5d5b-91ad-dbf4c65b9dea | note | FREQUENCY: Prior to start
54f050c2-6733-5035-b577-864cbc940c3d | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
37bfa05d-969a-550d-864c-7225c6b93322 | note | REFERENCE DOCUMENTS: Cl 703.17
610aa308-c704-5b2b-8a74-be163d9bc889 | note | INSPECTION/TEST METHOD: Verify
32dfc41b-42f3-5727-9559-c6337c86ce98 | note | RECORD OF CONFORMITY: ITP Signed
d9161209-0c86-518b-a61c-f65777bf4bd1 | note | HP
a9b459f5-db18-5c1d-be2f-42720b03e55d | note | RESPONSIBILITY: Site Engineer/ Superintendent
2ee6b7be-fc13-5682-bf57-c2fe51eec1ec | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Temporary Drainage Provisions
69c10eb6-690d-5d6f-8e54-6f68d902b241 | note | FREQUENCY: If Required
e87b1248-d1c1-5bd2-98cf-9015655c3e66 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
d90793ba-475c-5961-bdfb-498a9c2a4d60 | note | REFERENCE DOCUMENTS: Cl 703.18
70cd61fe-2eef-55ea-9886-c44aee37c84f | note | INSPECTION/TEST METHOD: Visual inspection
f868a514-e2dd-553d-b286-b292e64e02e0 | note | RECORD OF CONFORMITY: ITP Signed
3316d7f1-9ca0-5721-81c1-2249866cc7c5 | note | WP
214fb744-2ecb-53f1-8194-aa444d66c6b4 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
a3742281-7481-5cf6-9bb0-ce9e7a505f12 | date | Date Completed:
| checkpoint | 2.3 - Bedding
0574d795-354f-5b37-a3f6-0a96c05ac29e | note | FREQUENCY: Each lot
9375e1f5-8ea8-5311-81a4-379de20d9b8a | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
9dbd7413-176a-5cb3-a031-55e12b59c485 | note | ○ 20mm Class 3 shall be used and compacted to a thickness of not less than 100mm.
443961b3-ded8-5263-9b49-4715355978d3 | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
dd2145b9-41b7-50a8-8322-69c37a4acfc3 | note | REFERENCE DOCUMENTS: Cl 703.21, IFC Drawing SD-K1 Sheet 06
0b8294e0-2829-5f45-beae-7804ea38ab96 | note | INSPECTION/TEST METHOD: Visual inspection
f93867bc-0509-54e9-916c-b69eb87fe687 | note | RECORD OF CONFORMITY: ITP Signed
030c0123-e6a7-56d1-a743-d03701199f7d | note | WP
37e77552-7263-528c-99d9-fc8e636d127d | note | RESPONSIBILITY: Site Engineer/ Superintendent
41f6da57-9d84-5980-b09e-67f590836c27 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Pre-concrete check
0cdbb956-25b4-51a7-b5b9-f8f16ec9e0ed | note | FREQUENCY: Each lot
b81d7bb0-55ce-58c7-aa5e-9c83ba8afc35 | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
b8df43ec-b3bc-5546-baa1-fe66728fb68a | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
4b614f53-7915-5a96-b8fb-1f600b1bc08b | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
ab08ae43-ab48-52a7-a697-115c5c19df13 | note | ○ Formwork - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
4febdc20-f282-5d95-a9f2-f4907df77113 | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
766f5b88-9a15-5a5f-95c6-8d21f4c15dec | note | REFERENCE DOCUMENTS: Cl 703.08, 610.17(a)(b)(c), 703.12
408b5c55-e502-520a-b24c-0a3ac4827648 | note | INSPECTION/TEST METHOD: Verify
34526590-b886-577f-b732-49f9c7a0ffe7 | note | RECORD OF CONFORMITY: ITP Signed
456be256-c559-5e3b-ab07-147c8eb4a838 | textbox | Ambient Temperature |  |  | °C
f17b4719-5630-575f-a85e-e59f5bbf1540 | textbox | Concrete Temperature |  |  | °C
efa8807a-7d05-5fff-a834-f6ae58714b84 | note | HP*/ WP
7cca5cd4-42d0-51d2-87e4-56df23bdb030 | note | RESPONSIBILITY: Site Engineer/ Superintendent
a00f696c-6417-561c-b2bf-711105350956 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Kerb Concrete Mixture/Strength
79072fd6-81c7-5a94-88f7-2741df5a81fb | note | FREQUENCY: Each Lot
2a5b8ad0-6a87-5fba-bbcc-3d64a8269881 | note | ACCEPTANCE CRITERIA: Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
236f03ab-2030-5cb6-ba3f-df02f9433f79 | note | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete
16d4174c-9957-57da-895c-5c4a064299f6 | note | REFERENCE DOCUMENTS: Cl 703.05(b)
3fca20b3-bcd2-5365-9daa-cea8aadf36c1 | note | INSPECTION/TEST METHOD: Verify
bc20caa5-a653-5664-a87f-8a756400c098 | note | RECORD OF CONFORMITY: Test Record
e524a592-1827-52ed-bef7-6c7896114c3f | date | Date Completed:
| checkpoint | 2.5 - Concrete Placement
7e446cc4-3f99-5e72-bb55-f548281d778d | note | FREQUENCY: Each lot
b57b8f15-9e9c-5d7b-9994-1dcf0e316f54 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
a7d82a24-d6d5-5485-bf21-09e751e140ab | note | REFERENCE DOCUMENTS: Cl 703.23
948f02ed-c88e-5896-8760-b6b6ae008c6e | note | INSPECTION/TEST METHOD: Site Inspection
32722eed-6c7b-54b5-b6c3-3c807061ab12 | note | RECORD OF CONFORMITY: ITP Signed
0cd0bc34-fa12-5a7a-a4d7-feae0bae6f9d | note | IP
f212d044-acd4-565d-b715-00b547e9541d | note | RESPONSIBILITY: Site Engineer
b57f44a8-7790-55ee-9491-263a3ced5c81 | date | Date Completed:
| checkpoint | 2.6 - Finish Surfaces
46a82cb2-2b87-539d-82c7-f030ff8e7e45 | note | FREQUENCY: Each Lot
8618b95e-bf1a-583c-b9ab-588653e2a199 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
28be220a-27d3-5184-9f43-a3db3f3ebd78 | note | ○ Concrete to have a neat appearance and uniform colour.
e9726c65-2d56-5fb1-a7bf-6322230841f0 | note | REFERENCE DOCUMENTS: Cl 703.25
0ffa63a5-d5c4-5f72-b7ef-645f1a35ae0d | note | INSPECTION/TEST METHOD: Visual inspection
f80acc9d-f1ef-5724-822a-55259dd3a697 | note | RECORD OF CONFORMITY: ITP Signed
7451d043-03d7-50b5-88cd-2fdce1923e53 | note | IP
76b565a6-1a9c-5faa-963d-7d56a1ddcd05 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
dd7a1476-5741-5183-8c11-dba92fb45959 | date | Date Completed:
| checkpoint | 2.7 - Tolerances
f0ed6063-ec75-5790-96f3-3782074452a0 | note | FREQUENCY: Each Lot
2d231f6c-f107-59e0-aa9c-81dfa0b6faf8 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3.
0aa4955b-1ecf-57de-a777-a8cd73b20b00 | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
9bde2a7a-8d11-59ef-aa21-5198218ec30e | note | REFERENCE DOCUMENTS: Cl 703.15
47f7120c-59ed-5db3-adb3-be0fcf694778 | note | INSPECTION/TEST METHOD: Verify
b3b4d7f9-a9bd-5062-bd71-08f1f1b10da1 | note | RECORD OF CONFORMITY: ITP Signed
6890a3a5-d5a5-54f8-85d9-303c5d455f3e | note | SCP
b538aef2-7bd5-559b-b342-a572f9bce5c5 | note | RESPONSIBILITY: Site Engineer/ Surveyor
be0baa13-d5b4-5d61-b7bc-fad05f0786d9 | date | Date Completed:
| checkpoint | 2.8 - Joints
de287296-5535-5de9-b722-faef1c5137fb | note | FREQUENCY: Each joint
0c3231a5-cff4-5a50-b837-51faaabad7f5 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
f86ffd18-050d-5efc-aac5-3b6e6093ea73 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
78e93af9-86c4-5046-a995-47aeae925467 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
52a3bdee-795a-5d37-a4f8-fd4884333448 | note | REFERENCE DOCUMENTS: Cl 703.26
90b4985e-3195-5c79-9315-b7e9f49db0be | note | INSPECTION/TEST METHOD: Verify
36e63dde-2854-57ef-99a4-d6d260b9fc01 | note | RECORD OF CONFORMITY: ITP Signed
71d524f3-8c4f-5bb5-8e4c-b0b5c501cd31 | note | IP
06f2dfc3-2829-5e34-bb6a-29aff1263b2c | note | RESPONSIBILITY: Site Engineer/ Site Foreman
be8afd6f-d410-5d35-9953-df46a65b9514 | date | Date Completed:
| checkpoint | 2.9 - Curing
6f26025d-4e31-5116-8e92-6ec9f368c8ec | note | FREQUENCY: Each Lot
338f7d65-f3b8-553f-bcb9-a88ab47a3a3c | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete, with the exception of concrete edgings which shall be cured for a period of not less than three days after placing the concrete.
78da4f3d-0ad4-54f3-acf9-024edc1a613c | note | ○ Concrete will be cured by method of wet hessian.
f5de197d-78ba-523e-9258-d032cedc872f | note | REFERENCE DOCUMENTS: Cl 703.1
9509d27b-ada5-5821-b1f4-488341e184d2 | note | INSPECTION/TEST METHOD: Verify
a5036e89-461e-598d-9a00-21380c72e618 | note | RECORD OF CONFORMITY: ITP Signed
050766b8-e716-5dcb-8181-dc8c6be13232 | note | IP
97875dd7-2aa3-5764-b108-76a76ad36ad8 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f0e8be0b-cfe5-5499-bbaa-b3dfb5429f37 | date | Date Completed:
| checkpoint | 2.10 - Backfilling
fb9bc93d-ea34-5fd8-bf10-506852428eef | note | FREQUENCY: Each Lot
45f2d2ed-baf6-564d-a201-2a87ba7ebaf5 | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
00a75584-faea-58bf-a717-822f0e2139c6 | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
d9bd9d6e-08b1-5db1-88a8-8d0e0e8871ad | note | ○ Layers shall not exceed 150mm compacted depth.
4435924f-62ec-5115-aea4-29f1a24590bf | note | REFERENCE DOCUMENTS: Cl 703.29
b901fbd4-1a12-5d97-9af2-bf9df9205a25 | note | INSPECTION/TEST METHOD: Verify
55ccea3b-3716-5086-8fd9-0fab0252a60d | note | RECORD OF CONFORMITY: ITP Signed
286a6806-acc8-5020-b667-88abb07562d8 | note | IP
ddbd7f07-e5ee-5e28-903f-583700ed7748 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
d6408828-fbc9-5f74-a22a-f98c30a1f2a5 | date | Date Completed:
| checkpoint | 2.11 - Cracking of Concrete
b6b7e1f8-1929-56f8-ab54-cd8bc6f5ac38 | note | FREQUENCY: Following Completion
93f797da-ba91-5eae-acd4-d46def4286ba | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance.
9ad12248-f88b-5269-910e-f0101c315812 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 – Repair of Concrete Cracks, as directed by the Superintendent.
5115ca18-def4-5d93-b384-5f8a5cced444 | note | For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
3894865c-6172-5e5e-becf-d6eeac31fa2d | note | (a) constructed on compacted bedding;
95f173cb-c839-5a31-8ee5-c77b2ce7abfc | note | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
9df08199-62e9-511c-8a24-f4c26d5969da | note | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections.
9fd9ed17-9445-5308-a6d6-2a04c0740b28 | note | REFERENCE DOCUMENTS: Cl 703.30, Section 687
58b14548-0d29-53fc-a876-263552b52564 | note | INSPECTION/TEST METHOD: Verify
0d72ef4d-39cb-59fa-abac-6f223a3ac114 | note | RECORD OF CONFORMITY: ITP Signed
dc770e64-79af-5d9b-9943-74f6a4634ec0 | note | IP
d835c4c7-8e24-530a-a1db-93a0af046ecb | note | RESPONSIBILITY: Site Engineer
44bca34e-d3a8-595b-9765-fb5287175788 | date | Date Completed:
| section | 3 - Completion
| checkpoint | 3.1 - Survey data captured for as-built purposes
8d71d853-6f07-5d97-81a4-ef8bcfd8abb4 | note | FREQUENCY: Completion of each lot
6845b389-7839-5052-9a08-b6313f05ad63 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
d2154227-397a-5948-9f12-56941da85c04 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
cee70fc6-8b91-5b87-a01c-e9744cdf7300 | note | INSPECTION/TEST METHOD: Document review
8728a5e6-ff5a-53ef-8cb2-c261869bda39 | note | RECORD OF CONFORMITY: As-built survey records
0e990432-cc69-5aea-b364-4e8df65299b5 | note | SCP
fb752deb-a99c-5bf4-b5f7-4593f30da09a | note | RESPONSIBILITY: Project Engineer/ Surveyor
4f4384f9-8b8b-59b1-9d02-0a8829786597 | date | Date Completed:
| checkpoint | Final Inspection
7696139f-1767-5714-9f50-6287fddd75dc | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e4586bef-6162-502b-bf1a-8c69b00c7bf4 | textbox | Print Name:
35011070-eab5-5243-8b39-8b651f8bc068 | textbox | Position:
c783289d-81e1-5102-9f97-a0e846d248aa | date | Date:
| checklist | ITP-005 - General Concrete Paving | itp | ITP-005 - General Concrete Paving |  | 5c137fb4-2209-4687-8966-367dff301176
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
aa75e8f9-655e-5866-a100-473b443f716e | note | FREQUENCY: Prior to commencing any activity
b8136947-6f9d-5e61-956b-4ef7dc99aa07 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6f35ba0a-8b28-500a-bac6-3f596cf5f99d | note | – using the correct and complete set of drawings
c1801135-256c-5010-83a5-e5283d0ad7a7 | note | – all drawings are the latest revision
f0cd82f4-7d93-5c23-80bb-6b205ca0bd74 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
374e76c9-5f20-5888-beb5-14390af76dae | note | INSPECTION/TEST METHOD: Visual inspection
4492d7c8-10dc-59be-866f-44284772952c | note | RECORD OF CONFORMITY: ITP Signed
13e6f2e7-3bf7-5b17-9d91-d20934878727 | note | HP*
b9434f7e-d74a-5586-8e7f-8e0b381212af | note | RESPONSIBILITY: Site Engineer/ Site Foreman
663c2e88-a1ae-51e7-9726-16e402d8695b | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
4e0ad8d5-9671-5220-a7c4-a5ace380bb58 | note | FREQUENCY: Prior to commencing any activity
efbdd25d-73c5-5bf3-9b9b-59b72806f487 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
8a06712c-494f-5a14-a5a1-40ca52692984 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
da351867-11c1-50f9-ad38-0ee304d1fecb | note | INSPECTION/TEST METHOD: Visual inspection
a78785b0-3e39-5a4c-8d39-91c6800a72c2 | note | RECORD OF CONFORMITY: ITP Signed
ba92aa0c-bcb0-5699-a70d-d787089074db | note | IP
2ccd19fb-13da-5fd9-a399-807c170840f9 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
c41aee7f-eae7-50a2-b032-4e5954a9c6ef | date | Date Completed:
| checkpoint | 1.3 - Survey and Set Out
55bd0560-f6e0-5d44-bb7c-815a1bf31a48 | note | FREQUENCY: Prior to commencing any activity
12abf71b-dab1-5f04-91cd-b16785d8c3f9 | note | ACCEPTANCE CRITERIA: Current design model available for machine control.
b1fed755-0647-525d-bbdf-fb5d95e15bfd | note | ○ Clearly mark limit of works, chainage, offsets, cut/fill level etc. (if required)
12633760-2f9a-5ab1-af86-b30eb5cb4396 | note | ○ Design drawings must be IFC status
e7c13580-a91e-582e-b368-d44f5a06ecb5 | note | REFERENCE DOCUMENTS: IFC Drawings
3aae966c-f24e-51cf-bfbb-94b265d7c7ad | note | INSPECTION/TEST METHOD: Verify
a3f04b07-ebbf-58bc-87c2-acd646a671e0 | note | RECORD OF CONFORMITY: Site Inspection
c13b3e03-08b3-5cc8-934a-a67f9f1d31b9 | note | HP*/ WP
4ab66e02-b7bf-5e45-b744-f628dc3c5f4c | note | RESPONSIBILITY: Site Engineer/ Superintendent
9f7172e6-210e-5b80-8190-7dfae7875de4 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
824b50bd-666e-5f36-9007-4023958b5822 | note | FREQUENCY: Prior to start
223f00e1-6fd3-5bae-af9e-6d556b167e97 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
a142ea7f-fab3-5ab8-b8ee-7eaad2cc382b | note | REFERENCE DOCUMENTS: Cl 703.17
6a4edc1c-8948-5144-8df8-e389a4f60f76 | note | INSPECTION/TEST METHOD: Verify
15b6e3a2-2ebc-5c75-a84f-a1d349f7777c | note | RECORD OF CONFORMITY: ITP Signed
8312b2f0-26c9-591f-920f-16e15ec0a86f | note | HP
900f3e44-071d-5634-b1da-badb94ce5ccf | note | RESPONSIBILITY: Site Engineer/ Superintendent
028eee7c-2d7e-548a-98bc-6be7fdf67590 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Excavation and foundation
9b59a986-317c-5926-9813-7ab765e1b916 | note | FREQUENCY: Each lot as required
560c6dd4-28a7-52be-953e-ca860be4b4d4 | note | ACCEPTANCE CRITERIA: Box out to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
b06a0075-9633-514b-9265-427ab82bfc7f | note | ○ Foundation true to grade and cross section as shown on the drawings by filling and excavating as necessary.
ad9ff0ed-73de-5fa2-827d-a0715ea85f74 | note | REFERENCE DOCUMENTS: Cl 703.20, Cl703.21
97e5211d-dd53-5ac7-a0d6-1384ace3d08a | note | INSPECTION/TEST METHOD: Visual inspection
d809922e-1a52-5345-8830-d1528b563c33 | note | RECORD OF CONFORMITY: ITP Signed
06053a61-8115-525a-8057-183897b9d127 | note | WP
49790e3b-22a5-5073-b5ba-95cb6583515a | note | RESPONSIBILITY: Site Engineer/ Site Foreman
6193f9b5-9851-5129-9278-24dc77b2b8df | date | Date Completed:
| checkpoint | 2.3 - Bedding materials and compaction
04cf7941-5096-5ef9-a2f5-639c33446112 | note | FREQUENCY: Each lot, Prior to concrete placement
2764e2f1-0beb-50cd-ba4a-6fca129d45ba | note | ACCEPTANCE CRITERIA: Bedding material shall be compacted size 20mm Class 3 Crushed Rock or Class 3 crushed concrete.
c3a957c1-e2f1-52a2-8c9a-e5bc6919ce9c | note | ○ Immediately before concrete is placed, bedding shall be moist but with no free water on the surface. Comply to Table 820.041, Table 820.071.
35cfacdb-25c3-598a-94a6-af28d2d2fb7f | note | REFERENCE DOCUMENTS: Cl 703.21, Table 820.041, Table 820.071, IFC Drawings - SD-K3-1
383ed8c4-99f9-5fa8-98b3-f362fc1e7f16 | note | INSPECTION/TEST METHOD: Visual inspection
6c8d57de-d0ef-5661-b8a7-bd7adbce6be3 | note | RECORD OF CONFORMITY: ITP Signed
2225249c-6917-5f86-8704-b20dc7698a69 | note | WP
b7e31d54-2b2b-517b-bb62-6ca14b4a09b2 | note | RESPONSIBILITY: Site Engineer/ Superintendent
e355ac72-6bb8-5822-9710-ca9409051c58 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Bedding depths (compacted)
68e6e967-e13c-55d6-9ad7-b15fbf49081a | note | FREQUENCY: Each lot
f3f88aa8-580e-519b-940d-5d32f5a23f8c | note | ACCEPTANCE CRITERIA: 1. Edgings:
5062d338-2a0e-57a3-bc05-a3149f6272ab | note | ○ When constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
ddc16153-e676-5435-92e2-78e8666518f0 | note | ○ When not constructed over pavement layers, bedding ≥ 100 mm compacted thickness.
301932f5-60c0-5f8a-aed1-c4211557cc5d | note | 2. Shared use paths:
27123ddf-4629-52d0-8612-ad8422ee5e16 | note | ○ bedding ≥ 150 mm compacted thickness.
4a4f6a3c-054a-585e-8986-b99b27d985ed | note | 3. Footpaths & Driveways:
149f0fbc-5078-51d8-a5e1-2ff6b2941f92 | note | ○ bedding ≥ 100 mm compacted thickness
581c8286-2ddc-5554-bc19-c057a45ce27a | note | REFERENCE DOCUMENTS: Cl 703.21 (a), Cl703.21(b), Cl703.21(c),IFC drawings
90e4016e-fa2a-5769-8c92-c84a2e137a9f | note | INSPECTION/TEST METHOD: Visual inspection
8a3ed6a9-d612-56d3-bb11-880b6bd85258 | note | RECORD OF CONFORMITY: ITP Signed
ecee117e-d6f1-5048-bd5c-1c763104d08e | note | HP*/ WP
49cef930-895c-5b79-943b-8c9f79b04b52 | note | RESPONSIBILITY: Site Engineer/ Superintendent
346c7b89-9054-58db-8222-c06f994a8711 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Ambient weather for concreting
597f6831-62ae-5fe6-9903-3fbe65233b4e | note | FREQUENCY: Each Lot
a29bc3c3-e620-5f45-9df5-88ecc4af0155 | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of Clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for Restrictions and treatments to be applied for concreting in hot, cold and wet weather.
f3fe5f96-1ab4-5f53-aa6d-0d08684c138c | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
375d7766-d7ef-5a63-8b4f-fc3acbfe5f56 | note | ○ Ambient temperature not to be less than 5°C and no more than 35°C.
2447ea43-a008-5adb-a83a-c0850d0ec8fa | note | REFERENCE DOCUMENTS: Cl 703.013, AS/NZS 4671, AS/NZS 4680
884121ef-865c-566c-92ab-96213b55c0cb | note | INSPECTION/TEST METHOD: All measures in accordance with relevant documentation
a614bef6-7713-5ab6-a747-8755664b5b99 | note | RECORD OF CONFORMITY: Verify
5b1ddf3b-fec2-5bcd-a98c-174d912f7ec6 | note | WP
58bc16ea-3fd7-5866-843f-14918f255efb | note | RESPONSIBILITY: Site Engineer
e3fd951c-acc8-52fa-a48e-9f99185b21f2 | date | Date Completed:
| checkpoint | 2.5 - Steel reinforcing grade and placement
7d8763cf-da25-51df-940d-fa919f3bcb74 | note | FREQUENCY: Each lot
1f3e4000-86f6-55ba-a702-42c6f8f5141e | note | ACCEPTANCE CRITERIA: 1. Steel reinforcement shall comply with the relevant requirements of AS/NZS 4671
9557c752-3e09-5005-a135-2ff46f388b4e | note | 2. Concrete is to be reinforced by F72 mesh and with a cover of 40 mm as per the drawings SD-K3-1.
a7bf9817-9b7e-56ec-a140-f21e79b2b1e9 | note | 3. Support reinforcing using either concrete or plastic chairs.
e20c2cfd-205b-54d8-8cdb-c4ff8a82e963 | note | 4. Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used as support.
4268672e-a180-5150-bf24-0ac48d2cc0a5 | note | 5. Galvanising where specified shall be in accordance with the requirements of AS/NZS 4680.
680ea744-ed52-545c-860a-87bdff447982 | note | REFERENCE DOCUMENTS: Cl 703.013, AS/NZS 4671, AS/NZS 4680, IFC Drawing
0e88e25b-56ac-5a64-bf57-dd0e2556a8ca | note | INSPECTION/TEST METHOD: Site Inspection
6d8c5e4d-eb04-538c-8380-658a7e56ca73 | note | RECORD OF CONFORMITY: ITP Signed
88b0c00a-d779-52b9-a0b1-d3e2d1220f4e | note | WP
5ce19144-8301-517a-b39f-8d0a5366c1ac | note | RESPONSIBILITY: Site Engineer
fd7e18a4-d5fc-5f49-bde3-b5830eef5c1e | date | Date Completed:
| checkpoint | 2.6 - Formwork
85aadd70-a11d-5df2-b7b6-4747baf43b50 | note | FREQUENCY: Each Lot
cb03c5a5-afb5-51d5-b9ca-f24ce74b9b2d | note | ACCEPTANCE CRITERIA: Materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610. Joints in formwork shall be constructed such that loss of mortar is prevented.
4b189d9e-6589-5e8e-bbb1-fffce5c0311b | note | Formwork shall not be stripped until the minimum times specified in AS 3610 Table 5.4.1 have elapsed from the time of completion of the placing of concrete. The minimum time shall also not be less than:
255e90cb-59e4-52b9-9163-4c26a6cc775d | note | (a) 2 days for vertical formwork on external surfaces; and
e1a078e2-79a5-598c-b6cf-9218b74ca441 | note | (b) 1 day for vertical forms on permanently hidden surfaces.
038c57b6-8c47-549f-9e7c-b5ce6dba445b | note | REFERENCE DOCUMENTS: Cl 703.12, AS3610
2f076c22-fc9f-5399-8d94-e94a34913011 | note | INSPECTION/TEST METHOD: Visual inspection
fb11cf79-f29e-5711-82d8-961405a871da | note | RECORD OF CONFORMITY: ITP Signed
6fa2b28f-467f-5dda-8914-c4975c318ffb | note | WP
4e094325-c055-503e-888d-48b3b416c0d6 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
0329790e-9e68-5abf-88a7-6916b5c2b32b | date | Date Completed:
| checkpoint | 2.7 - Concrete Placement and Compaction
fedfde8b-7676-54d5-ae59-fe3770ddb3f4 | note | FREQUENCY: Each Lot
2478a41c-9047-5136-8467-cd8ed8b31fd2 | note | ACCEPTANCE CRITERIA: Concrete strength to comply with detail on IFC drawings and AS 1379
7ef66899-1e2b-5df7-9326-17f116f4d376 | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment’s and into corners of formwork or excavations to produce a dense concrete free from voids. Workable concrete mixes are exempt from vibration requirement. Concrete testing frequency in accordance with 610 requirements.
1aac8c20-d12b-5c11-8894-335f334c4848 | note | REFERENCE DOCUMENTS: IFC drawings, Cl 703.01, Cl 703.08, Cl 610.16, AS 1379
bf9ba745-ce86-51f8-8aa9-74a1e1b16859 | note | INSPECTION/TEST METHOD: Visual inspection
4ff04717-434d-5c6f-86d0-50f18b499c3f | note | RECORD OF CONFORMITY: ITP Signed
41113bf6-97d0-504b-b873-870e26be84b4 | note | WP
b42dcd87-cb94-55e4-824d-ec0142b5a088 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ce9cf8fd-a99c-5c1d-8cb6-5c69e9094109 | date | Date Completed:
| checkpoint | 2.8 - Surface Finish
c4950107-7bde-5bc2-acb7-c7feb7770348 | note | FREQUENCY: Each Lot
2f428be8-38e0-50a7-bf6e-bacb605a9386 | note | ACCEPTANCE CRITERIA: Exposed surfaces shall be treated as follows:
4c816925-7edc-59dd-80f7-cf3034e42498 | note | a) Edgings
605e35f5-7d66-5311-a567-f30e47471a49 | note | ○ All edgings rendered to a thickness ≤ 3 mm, within 30 minutes of placing or extruding concrete. Mortar shall consist of two parts of fine aggregate, one part of cement, and sufficient water to produce a mix of suitable consistency.
e64fa379-417d-5e3b-8d64-db53640feddf | note | (b) Footpaths, other Surfacings and Shared Use Paths
a4d7e05f-7c14-5be3-9061-132e151dd1e4 | note | ○ Concrete compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top, struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
e6e669e1-31bd-57e5-aaf9-7d63214db79f | note | ○ All edges sharp and clean, and bullnoses regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
f8d8acf3-5995-5693-8931-d342ca9f2de6 | note | ○ Permanently hidden concrete surfaces have a Class 4 surface finish.
d3b21a64-42f1-517b-a96a-3110acfe0a76 | note | ○ All other concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces.
a75add22-657a-576b-a4fa-ee45220a4162 | note | REFERENCE DOCUMENTS: Cl 703.25
098abf1c-3aed-5c7d-a0ab-289be0d98f6a | note | INSPECTION/TEST METHOD: Visual inspection
b982b843-ac21-58bd-ba37-7b9068d06350 | note | RECORD OF CONFORMITY: ITP Signed
31a14594-cc52-5a72-803f-e69c521bb778 | note | WP
cc603894-dd80-5bc2-ac09-fd8e2ed4c99c | note | RESPONSIBILITY: Site Engineer/ Site Foreman
01e020a2-8eae-5a99-9aff-c6eb9ea4ee8c | date | Date Completed:
| checkpoint | 2.9 - Joints
6b2f64ec-fc7f-5daa-a09b-e6df86a4fdc8 | note | FREQUENCY: Each Lot
7bcb31be-6b17-520b-80c8-9aa5b8a8a911 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
d299363a-0ffb-5aeb-9493-a3559d1d1f29 | note | a) Edgings
dd591f39-808e-5ff5-99d5-37fd0b0ed492 | note | i) Traverse Joints – constructed at regular intervals ≤ 2.5m. Templates for edging using fixed forms shall be removed as soon as practical after finishing work. Resultant slot in edging shall be tooled to a depth of 20mm, and produce a groove ≥ 5 mm wide, following which a vertical cut shall be made through the base of the groove to a depth ≥ 50 mm from the surface.
76c95e66-6e4f-5ff3-94cf-efc08561491f | note | ii) Expansion Joints – placed at junctions with bridges, shall be 15 mm wide and filled with cork/bituminous impregnated particle board strip extending for the full width and depth of edging. Fill placed in position before concrete and held during placing of concrete.
2c7b113c-a159-55a6-bfb8-5ac2c995ba14 | note | b) Footpaths
bd56ef8d-5547-5936-b0a5-4df3dcb970c1 | note | i) Expansion Joints
e4858184-67dc-5f5d-8dad-078935489dcf | note | ○ Expansion joints placed at intervals ≤ 10 m. Expansion joint shall be 15 mm wide, filled with cork/bituminous impregnated particle board strip extending for full width and depth of paving. Filler shall be placed before concrete is placed and held in position during concreting.
f8014948-9fb0-5589-af26-c114ed97fedc | note | ii) Control Joints
594e55dd-3f86-5b89-98d0-91422a3f05f3 | note | ○ Control joints at least 25% of paving thickness deep, 5 mm wide at 2.5 m intervals within 4 hours of placing concrete when air temperature is between 20 degrees and 35 degrees and within 24 hours when air temperature is < 20 degrees.
0ffdab26-8c91-52e4-930b-4a29aff672a1 | note | c) Between concrete paving and shared use path
7fb3c676-4c30-56f4-9460-938531e596ce | note | ○ Except on narrow medians (< 2.0 m wide) surfaced full width, bonding between the concrete paving or shared use path and the edging prevented by painting the back of the edging with bitumen, or by a bituminous felt material between edging and concrete paving/shared use path.
4e684ae3-fdaf-5905-9d54-a5c4cadbff6c | note | REFERENCE DOCUMENTS: Cl 703.26 (a), Cl 703.26 (b), Cl 703.26 (c)
611894f7-b58e-5cbf-afde-8b8be78d1a45 | note | INSPECTION/TEST METHOD: Visual inspection
8693ee2b-e6e4-5a6b-9acc-327d18787cb4 | note | RECORD OF CONFORMITY: ITP Signed
6350db41-1d5e-5b31-ae67-4eef0c856a0a | note | WP
ecbbc411-a5d6-508d-a08a-91d099f8ff4b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
effb39b7-a2d2-5b68-a58d-14610f8a22b5 | date | Date Completed:
| checkpoint | 2.10 - Curing
caec7330-751e-57ec-9c9c-1a27257bbe33 | note | FREQUENCY: Each Lot
537dd2f9-3f5d-5216-a835-1a136dab8469 | note | ACCEPTANCE CRITERIA: Match existing fixtures to within 5mm (pit covers, etc).
637bdfaf-8cb6-5690-a8b7-3358f2751522 | note | ○ Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point.
7b986099-25d4-5a7c-97b5-0f3112c91a78 | note | ○ Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm.
18578567-14ba-5615-98ff-66e2fc86bc75 | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges
31789769-5894-5f67-b96d-224362642491 | note | REFERENCE DOCUMENTS: Cl 703.10
8eda019f-e9d7-5bdb-b692-aea0bb8ee3e8 | note | INSPECTION/TEST METHOD: Verify
69265240-1f85-57a1-9bca-945f4b7cc620 | note | RECORD OF CONFORMITY: ITP Signed
f35fba92-3c57-58ab-9e52-290d41210ca7 | note | IP
c803f03e-caa8-5194-8c6d-7c751f0affe0 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
85641732-ace4-5950-b19a-b0a0cb9f5fb5 | date | Date Completed:
| checkpoint | 2.11 - Tolerances online, level and shape
21810d3b-b4bf-5a85-8cfd-40b6f981fc57 | note | FREQUENCY: Each Lot
c8efdd1b-25ea-5d87-99bd-50b5178d9473 | note | ACCEPTANCE CRITERIA: Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point.
147602b4-9b2d-5110-ab79-5c8ec44cf3a8 | note | ○ Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
33a4f4d8-26cd-56ca-9cdb-35776c2b3d0e | note | REFERENCE DOCUMENTS: Cl 703.15 (a), Cl 703.15 (b), Cl703.15 (c)
550f0890-e709-5725-a7cd-5245d287b248 | note | INSPECTION/TEST METHOD: Visual inspection
71d48a19-8683-5014-9a1d-d9a68fde8526 | note | RECORD OF CONFORMITY: ITP Signed
036328ac-b087-5938-ba98-e4a16d286686 | note | IP
4da064a5-5a4f-5b37-ab34-09fffec4bfd4 | note | RESPONSIBILITY: Site Engineer
8a817135-9955-5bc0-9b7a-c00f95de8b07 | date | Date Completed:
| checkpoint | 2.12 - Concrete repairs
1669458b-46a9-5f98-9b6b-e06d47f6ea38 | note | FREQUENCY: Each Lot
862c2419-c5ff-5555-b035-d56ee79f671a | note | ACCEPTANCE CRITERIA: Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
fb3eb3ac-a092-5e61-bca3-86e917b2a86d | note | REFERENCE DOCUMENTS: CL 703.08
4ed2ad67-dd09-5b9d-a488-c4d12eb10808 | note | INSPECTION/TEST METHOD: Visual inspection
6634e351-4223-5064-bf17-8ca23fdb836d | note | RECORD OF CONFORMITY: ITP Signed
3c3e4703-30f1-5396-97a2-92ac03073d2f | note | WP
8f9c8aa2-be25-54b6-b2b6-bab2004d6335 | note | RESPONSIBILITY: Site Engineer/ Superintendent
ea75cd8d-9d3a-538d-a81d-af924746bb54 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Verification and Lot records complete
846c0464-13c1-5993-a0b6-14f97fcbe285 | note | FREQUENCY: Completion of each lot
b1f30840-b30e-57e5-b4ee-c097c3953f5f | note | ACCEPTANCE CRITERIA: Completed work checklists, inspection and test results and contractor conformance records progressively and permanently saved and stored as soon as possible after they are received. Completed lot records are transferred to the Quality Team for final record verification prior to being closed
7136c362-55a0-5e2b-abd3-0d11c4ee2392 | note | REFERENCE DOCUMENTS: Test Certificates, QA Plan
d4539259-9793-5eee-9ec3-1a4882c82910 | note | INSPECTION/TEST METHOD: Document review
14d3b406-a008-538d-ad9b-42e5a2133548 | note | RECORD OF CONFORMITY: ITP Signed
1fe8a001-6e43-5df8-84f5-a56848eb528c | note | TP
b61e159b-19b7-5a2e-a076-b5aafb4e9d94 | note | RESPONSIBILITY: Project Engineer/ Site Engineer
f91ff272-aab6-53ca-8b4d-b87b2a05cc5d | date | Date Completed:
| checkpoint | Final Inspection
269695eb-6b5e-5b1b-a63c-c59c8b3b0545 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
d60892fc-ca09-5cb5-9279-13ad91b35d35 | textbox | Print Name:
4aa1c52d-7a70-5401-b2a3-923c75cc5b53 | textbox | Position:
56febc75-7f09-55b5-b643-66d992e534ac | date | Date:
| checklist | ITP-006 - Hot Mix Asphalt | itp | ITP-006 - Hot Mix Asphalt |  | 391c0954-3936-487e-b698-6d297a5126f6
| section | 1 - Construction Works
| checkpoint | 1.1 - Submission of Mix Design (Type Asphalt, mm Nominal Size)
6ce4e51b-a8cd-5a41-9144-ca0b8e611bee | note | FREQUENCY: Prior to commencing paving
40764cc3-d339-5190-816c-7a686711ada6 | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix.
2e4e4e87-002a-5a75-ab2a-2b9077b95f53 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
3687622f-2778-50aa-89b8-e017a04fba87 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
50656df2-ee95-54b8-9a4b-063bf20b2836 | note | RECORD OF CONFORMITY: VR approval, Completed ITP
2e330431-d29a-554f-8430-2b23200fd2a3 | note | HP
7d4c2872-7c91-5f56-a29d-459334350232 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
32e50f61-c1e3-5f30-ab8e-2009b79b4c5e | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Implementation of all measures and controls
e0fa9f39-67c2-5ac4-a0aa-d2b97b8392c1 | note | FREQUENCY: Prior to commencing any activity
1e47a351-f29d-55f3-8e61-d7fe4bbfbf18 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
4c53398b-a6c5-56bf-9693-d030a18d5d93 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
9a8a0bc8-8f1d-57e7-94e1-06119566df1f | note | INSPECTION/TEST METHOD: Visual Inspection
9fcfabe7-6ebc-5e84-bafb-c4959aa72152 | note | RECORD OF CONFORMITY: This ITP signed off
7463f4a5-c41f-55c4-8896-14ee899534a6 | note | HP*
62eeee3e-028f-59c3-a5e0-ae4b413f495d | note | RESPONSIBILITY: Site Engineer / Site Foreman
93e25d69-e227-54cd-932f-18ce17ec40a9 | date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
919bb6c8-6609-571d-9209-005921505fac | note | FREQUENCY: Prior to commencing paving
16530470-96ca-5e11-8af6-94281336b4e3 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
d18e55f3-881d-50d3-bf4b-0bd1b1cdf465 | note | ○ Material and compaction test certificates conform for pavement
a88635a2-a22e-556e-b0ef-4bccf902153a | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
abd5c8e5-ddb9-55a7-9ee7-1701ff774725 | note | INSPECTION/TEST METHOD: Visual Inspection
4e075ea1-fe1a-5b99-bbdc-3bc2e410aef8 | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Base Course Checklist
8acac225-c896-5f70-84b0-633fc789ceb8 | note | HP
c86b25a6-6136-5f99-9f76-6b2b34576281 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
c440e075-acdc-5321-b268-fe5de3b5f9ac | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.4 - Dryback
9bdd28fa-4ae1-5d72-80b7-6410d6225a5a | note | FREQUENCY: Prior to commencing paving
93c5d512-2ca2-58e7-99ca-b3ce2c9b99a5 | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
52d7c8fa-e11e-534a-9bb3-8dede5ecbc83 | note | – 6 randomly selected test sites per lot required
548a3947-d987-5fd6-b683-d809555cbc0e | note | – If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
aae273dc-ab94-5551-a3f5-0095343ba112 | note | – If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
63454963-1708-5629-937f-195c5db43f04 | note | – Testing schedule in accordance with 310.03 (c)
52cb9ce4-143f-532a-8d1e-08e03e9828ca | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b), Table 310.031, 310.03(c), Table 310.032
23b7637c-e93b-5877-8e32-29f377c6e30e | note | INSPECTION/TEST METHOD: Verify
443c6cd5-178d-5586-8755-cb9081f9f13a | note | RECORD OF CONFORMITY: ITP Signed off
fdcb8a3a-ee42-5e9e-85ba-279ca7d61a66 | note | TP
cfa948e4-165c-57ab-9e08-075ec71f5ede | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
70d26832-afdc-5472-aca3-a54067ba2f02 | date | Date Completed:
| checkpoint | 1.5 - Ambient Conditions for Placing
febd41e4-c0c0-50d5-ba79-0a910d6ce477 | note | FREQUENCY: Prior to commencing paving
7032fc75-d43b-5663-993a-4ec4c8b090aa | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
05014729-6b00-590c-ae8b-99a1216883ef | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
3cc25af7-5445-55ff-a0d2-c0b9f4415712 | note | REFERENCE DOCUMENTS: 407.17(a)
11c02d57-3e96-520e-ad7e-18b759b4333f | note | INSPECTION/TEST METHOD: Verify
cad02170-fa02-58e5-be01-d9662d02cdb0 | note | RECORD OF CONFORMITY: Thermometer
b8aa4f87-4632-5f6c-922a-9d16ac88caf0 | note | IP
dbd7f695-c3ba-5e3c-9210-b9f4de488827 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cc136c20-0a6b-5498-be1f-75ef12c7a74a | date | Date Completed:
| checkpoint | 1.6 - Planning of Joints
fac24fcc-7ce3-5e1c-8933-ebbe7456b88c | note | FREQUENCY: Prior to commencing paving
7fff2ec9-8c7f-54c7-a70d-0a9a4a663933 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
39c1db48-a0f5-589b-beaf-ab628c3fd98d | note | ○ Transverse Joints Offset from layer to layer by at least 2m
a80157bb-3bac-5d87-bb1f-31689dab9556 | note | ○ Longitudinal Joints Offset from layer to layer by at least
e051141c-5b17-5837-bb5c-1be87c379520 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
41679541-11c1-55aa-a4bc-1cc7568589cd | note | REFERENCE DOCUMENTS: 407.21, IFC Drawings
52d3c244-2b06-5d18-b510-3f6d72ad67e4 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
7839e128-6484-5bc5-8576-e903e79509fc | note | RECORD OF CONFORMITY: Paving Plan
e76e7671-d015-598f-a38f-418f7c75564c | note | WP
ae64ac03-d5d4-5ad3-8e1d-9d43fdd74876 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
3cec5582-0109-5ccc-98f8-3cfc942bc5c9 | date | Date Completed:
| checkpoint | 1.7 - Longitudinal Joints with existing Pavement
d75be177-1ae1-5ba0-9e39-630a620a6050 | note | FREQUENCY: Prior to commencing paving
0fa02a83-3361-5699-9430-842527499a10 | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
e334f8e4-6dbe-5a49-87b0-dd54e9151cb6 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
65f4209a-f98b-50a8-85ca-d1fd8ef1b7ef | note | REFERENCE DOCUMENTS: 407.21 (c)
ad8906fc-e135-5cc1-a3c1-04551a31cf17 | note | INSPECTION/TEST METHOD: Visual Inspection
85ee6460-fcb7-51aa-a917-ce58524d5b8c | note | RECORD OF CONFORMITY: ITP Signed
712edc5f-d847-535c-afa6-3cffc1a11202 | note | WP
2f6342e2-19bf-5ed1-ab32-ccbfe52084dd | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
c8f73af6-c869-576f-ae9c-e916408df538 | date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Frequency of Inspection and Testing at the Mixing Plant
8bca849b-9525-5c7d-ab1b-d82300c0d777 | note | FREQUENCY: As per Table 407.151
908bd923-d5f1-5270-afc5-c3d1ccced0ef | note | ACCEPTANCE CRITERIA: The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product.
6cb28e84-ca72-522a-8f50-5ef5b656b7c6 | note | REFERENCE DOCUMENTS: 407.151
33c29c90-820a-5377-a447-0f09003610c4 | note | INSPECTION/TEST METHOD: Test Inspection
9bb545e1-9bdb-5da0-9682-8aa368b0b151 | note | RECORD OF CONFORMITY: ITP Signed
509b27fa-7836-53dc-b4a0-48805016820e | note | TP
00930d72-441a-5869-ab67-ff7bb6773703 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
2957d5ab-b848-5bc4-8458-4e1013bcd9e5 | date | Date Completed:
| checkpoint | 2.2 - Tack Coat
a461ffe4-9c7d-5ba2-ae4a-191f676a8833 | note | FREQUENCY: Prior to commencing paving
42bcf77a-bebc-5b5d-913a-5dace1ea021e | note | ACCEPTANCE CRITERIA: As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm.
d3e5b880-bc4a-52e8-9c8d-39cbd94fb2e8 | note | ○ Tack coat to be sprayed on existing asphalt joints.
d44680ef-61ff-57c7-9a36-c26f5bde48d2 | note | ○ Tack coat must be allowed to turn from brown to black before paving.
dfec907c-76a9-511d-bea5-fd1bc5f13f4e | note | ○ If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
afd25df2-f245-514e-a77d-032f317edc45 | note | REFERENCE DOCUMENTS: 407.19, AS2150 11
68cf3ff5-d555-57c2-8873-eee10d3cc7c5 | note | INSPECTION/TEST METHOD: Visual Inspection
c0f2a74d-3d64-5d56-930e-726410bd940b | note | RECORD OF CONFORMITY: Spray area
cca8710c-eaa6-56b1-b5e6-f6f090f4512c | note | WP
bda1cc07-e68b-5bbf-bd83-ef87f1c47c59 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
26c3ba3d-ec4c-569e-82a2-710394e55076 | date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
1b7b5e32-f581-5da0-b70a-62984b40f8ea | note | FREQUENCY: Prior to commencing Paving
532001dc-1ec0-5463-9336-413e7ca1c4f7 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
b4a816e6-9d29-57a0-a661-288e3bff5ce4 | note | REFERENCE DOCUMENTS: 407.23
8ed39a01-69af-59db-9406-6a5eed0fa6ef | note | INSPECTION/TEST METHOD: Visual Inspection
ba566552-a923-5377-8357-f1020e30c6d8 | note | RECORD OF CONFORMITY: ITP Signed
17c34482-3afd-582d-bf18-0e4db1f102ad | note | HP
dfaa65d1-a98d-5801-8f0f-2304ba20ced3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
70c893d4-c0cb-5cf2-9c43-6d649ab60025 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Mix Design Confirmation
bf920119-50bf-53d5-ab75-2458e28039a1 | note | FREQUENCY: Each lot
e3c94680-62b0-56e0-a952-5f7431ac7ea4 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
fbe665a6-e6b1-54c7-b65c-e8b5664cf4ed | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
90ff38c9-4e57-5e48-9bb5-c2c830feab57 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
2e7d5a54-6d90-514b-845b-55ec7e89b1a4 | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
e4d372ba-0f20-5b4e-b547-ab7a15b18436 | note | HP*
b5e61478-d7d4-59ea-8515-193b55a739f0 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d40c2f78-85b2-5b96-9ef0-3fda0b935e7b | date | Date Completed:
| checkpoint | 2.5 - Delivery of Mix
f48026cb-e855-5cf2-95b8-dfcdba90211c | note | FREQUENCY: Each load
2f7f4e16-8b1c-562e-9c50-e7cbb4995482 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
1079646e-d02b-5ee2-910c-04b5ff3b5a0f | note | REFERENCE DOCUMENTS: 407.11
21d4ac7b-2bb3-55cc-bb27-c154d5ed7d8b | note | INSPECTION/TEST METHOD: Visual Inspection
4dda9bf5-a0fb-5ad6-ac9f-90fe42c12509 | note | RECORD OF CONFORMITY: Delivery Docket
b4eda044-b447-560e-98b5-7e9d27a4860f | note | WP
ee596d85-1d9e-5f6e-9d7b-3a889802b944 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
dfec7b6f-45f7-5737-8205-1b098b3238a4 | date | Date Completed:
| checkpoint | 2.6 - Traceability
3b1be0a2-bea6-545c-9e11-4367db121c6f | note | FREQUENCY: Each lot
a4eae31b-b0e7-547b-8f87-9f52428e98f8 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
55b8f273-d8d0-5fc9-aa86-7a22636a8f85 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
5418ad85-471e-5adf-b1fe-e7726ac74699 | note | INSPECTION/TEST METHOD: Verify
dd9c9189-13b4-5309-a1ea-0fd0fabf2f52 | note | RECORD OF CONFORMITY: Daily Lot Record
8f9b7a43-4790-59b8-8b9d-e71ad752e3e8 | note | IP
4c8ac826-24a6-5d46-bf02-baa262d5148d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
136a30f7-711b-5c13-ae86-45ceb86fc7f3 | date | Date Completed:
| checkpoint | 2.7 - Layer Thickness and Level Control
bdf119d0-a340-5414-b5f1-74525548a060 | note | FREQUENCY: Regularly during paving
7cfc69c3-8b21-5539-abdc-316438363d94 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
89a438c3-d378-5abe-8229-e1797178f388 | note | REFERENCE DOCUMENTS: IFC Drawings
a4f481d6-6ddf-58af-8534-f7bdcfed89b2 | note | INSPECTION/TEST METHOD: Verify
c1549aec-0620-5f86-9ac9-afe4833fc6b6 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
387a0382-422f-55fc-be4a-bb0e1e9f1b35 | note | WP
0f5f047a-945c-56d8-9226-5e45eff1a643 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
bbdc9994-9fee-52ca-bc04-f599a34ab643 | date | Date Completed:
| checkpoint | 2.8 - Paver Stoppages
30d5823b-4a1e-5deb-8b32-7cb1b02d21c4 | note | FREQUENCY: If paver stops
7e49275e-c904-5948-8ba1-6481b1ffdf2c | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
705b2f89-559f-535d-b05e-282164050ae0 | note | REFERENCE DOCUMENTS: 407.25 (c)
676d60b4-f0dc-59f9-86da-601b6bca109c | note | INSPECTION/TEST METHOD: Verify
138f9421-efa6-5d5d-9f78-d08257cfc1e1 | note | RECORD OF CONFORMITY: Thermometer
85cffb59-586c-530c-b3a6-3d3b999070d4 | note | WP
aae4a2bd-0d57-5c63-8aaa-3a56a03069b8 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cadeb400-160f-523b-87ae-fc95dff9d2fb | date | Date Completed:
| checkpoint | 2.9 - Surface Finish of Wearing Course
2d30135d-7110-5518-a860-d277e082e39a | note | FREQUENCY: During paving and after final roll
3bf75d95-9887-55a7-a402-1dd8542c33eb | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
9b231f2e-ff47-5e95-b714-a295ea86d2fe | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
75aafbfc-fb33-577d-93ff-e8f98c541bfb | note | INSPECTION/TEST METHOD: Visual Inspection
96ce8ac2-8dab-563f-b063-e79b44e8c959 | note | RECORD OF CONFORMITY: ITP Signed
8000f7d3-ef98-5001-adbd-50b0c4b4d9da | note | WP
04a26896-34aa-5395-b2d3-d667fd353b7d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6c7244ca-b6d0-539e-900d-25f2821f6862 | date | Date Completed:
| checkpoint | 2.10 - Kerb and Channel
144d9f9d-2ab3-5c39-a4de-170a8e8acb36 | note | FREQUENCY: During paving and after final roll
ccb3a5f7-b97e-569b-89c6-a94a1a9869a7 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
e263ac10-5bc7-5b64-a825-1f7a00a93e30 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
f3fb844b-59f5-56a7-b076-978e92dbe7cb | note | INSPECTION/TEST METHOD: Visual Inspection
8b60104b-6a7a-5006-8d3f-146b239828d7 | note | RECORD OF CONFORMITY: ITP Signed
f93fe6bf-2407-5527-a225-d2174ec05216 | note | WP
bbf55836-1441-5e59-9424-15294e3b460a | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
306a4026-e3ff-506c-b20f-772fd96428f3 | date | Date Completed:
| checkpoint | 2.11 - Alignment of layers not placed against concrete edge
783191a3-26d6-5607-9503-32f1717bc7df | note | FREQUENCY: During paving and at completion of work
88dccd3e-355a-5f45-910b-a9baa4bc61b8 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
3ebe02db-f575-595c-a2de-d1f8ec3fa725 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
dfe8f615-17d4-5fd1-a74d-ce73d265a416 | note | REFERENCE DOCUMENTS: 407.29 (a)(iv), Drawings
0e3461a0-ef95-558b-884d-2ee6aabe62b4 | note | INSPECTION/TEST METHOD: Visual Inspection
84dc2fb2-7651-57e2-9d69-09571cbb210f | note | RECORD OF CONFORMITY: ITP Signed
56dd8998-d4b2-5e1b-a260-01af0523e53f | note | IP
3c117f5b-1ca9-5ffa-a3d1-6833259d7428 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
0a60d75c-a8e0-5b09-b28f-e533b797c6ed | date | Date Completed:
| checkpoint | 2.12 - Width of layers not placed against concrete edge
01562806-c6ce-532e-bcb4-bad264057784 | note | FREQUENCY: During paving and at completion of work
9aad9638-e32c-53e2-a3af-4f10d634afde | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
e9fff0a4-17c4-5ba3-a3b2-6d39baa7a333 | note | ○ The average width over any 300m shall not be less than the design or specified width
c51fc2ab-9ce5-5115-a917-ba26716699d0 | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
52eac291-bbe6-522d-a693-4bfe091cffa9 | note | INSPECTION/TEST METHOD: Visual Inspection
cd98e19c-99a0-553d-bfb1-9443f6903b8c | note | RECORD OF CONFORMITY: ITP Signed
b09e4867-780c-577f-91e1-b9655bb29c6a | note | IP
76f4ab50-ff35-5048-9304-753ba51c0e16 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d83cf146-7d7f-542b-80c0-07a069de0a4e | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
3f922d4a-3b1a-5d0c-9830-465a327fe1ff | note | FREQUENCY: Per Lot
76597802-bd74-53d5-a943-99e2a706b986 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
482f2dcf-0eb3-5584-b395-ef9a43a0090c | note | ○ 94.0% or greater Accept lot
0cca0e22-7cf2-51cb-9bde-7f44a0570f77 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
2374624a-dc25-5885-ad52-6fa03a5dac90 | note | REFERENCE DOCUMENTS: Table 407.271
0506cc60-1835-546e-a615-e36b25e17d21 | note | INSPECTION/TEST METHOD: Verify
781f543f-0c6b-5fcf-98b2-d8d508869a8c | note | RECORD OF CONFORMITY: Test Report
f84381b5-5729-52ff-97a4-313320388627 | note | TP
8fbf7144-a9e9-5d64-9344-aa3da9735e23 | note | RESPONSIBILITY: Site Engineer/ Lab Technician
42f9a568-9fec-52aa-9677-ab54867a06fd | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
17315e0d-cb61-570a-a544-0fc3f95ce397 | note | FREQUENCY: Per 4,000m2 at completion of work
bbfc8501-7c92-5cd5-9be7-4b94d1ed548c | note | ACCEPTANCE CRITERIA: Scale B: Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm
be71fd93-297f-5759-8427-6b0337c4b39b | note | ○ Minimum number of measurements per lot is 40
474e21a4-5809-510e-99bd-a06690d8ef22 | note | (ii) Kerb and Channel: Refer to Item 2.10 of this ITP
95666054-3746-5c09-956a-7b546e4695b8 | note | REFERENCE DOCUMENTS: Table 407.293, Table 407.292
4cfdceeb-4833-5c21-b4f0-92db2f886311 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
c050ba4f-7eb2-5ab3-8b8e-22bbd64d024f | note | RECORD OF CONFORMITY: Survey Conformance
4837170b-f260-554a-96a0-aae70ebfa32f | note | SCP
3db04ad9-1980-532c-b133-b0339c908d8f | note | RESPONSIBILITY: Site Engineer/ Surveyor
244cbb06-0da3-521f-af93-18a7ff49ab94 | date | Date Completed:
| checkpoint | Final Inspection
2e7def89-d6cb-553b-841b-29bc47eed33d | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5b414435-7be5-52a4-8e09-72c22b02b971 | textbox | Print Name:
ba9990b0-c79a-5c06-80db-f566f80b883e | textbox | Position:
7d1529ee-cf33-5649-87f0-6c6d69d8a0cc | date | Date:
| checklist | ITP-007 - Pavement Markings | itp | ITP-007 - Pavement Markings |  | 9ba14bf4-3a8d-423f-92c5-fd2b20cdb2f2
| section | 1 - General
| checkpoint | 1.1 - Check for correct documentation
b1c90a3c-8615-53ae-b342-dd27b63a6482 | note | FREQUENCY: Prior to commencing any activity
54d09430-165e-5871-a6eb-af38c1cd55aa | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
51b35e39-bab9-54a1-ac17-090802973551 | note | – using the correct and complete set of drawings
df27fbde-146b-513b-966d-0d4091a81b6d | note | – all drawings are the latest revision
43d933df-1851-51f7-992f-34989eeac27b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
51b67353-834a-56a1-a37a-f378bd03ea6a | note | INSPECTION/TEST METHOD: Visual inspection
ada007dd-fb3f-5f20-a479-9dd10fc74ade | note | RECORD OF CONFORMITY: This ITP signed
d4da6b3e-18dc-5d3a-8208-e115732b7bbc | note | HP*
a2a79de2-53d2-577d-827f-4a7ea63504b8 | note | RESPONSIBILITY: Site Engineer / Site Foreman
6e6184f8-0336-5543-9f14-b6234ac1f252 | date | Date Completed:
| checkpoint | 1.2 - Line marking conformance
476554aa-0a0a-5626-a57e-5a770df93783 | note | FREQUENCY: Prior to commencing any activity
72093897-bc6b-5af1-ac39-2693669b9f1b | note | ACCEPTANCE CRITERIA: Materials to be used must conform with the specification
9456c0a5-ba74-5b05-a519-8865e4646cbb | note | REFERENCE DOCUMENTS: Cl 721.A05, IFC Drawing
9f10851c-c4e3-5bcf-8c74-9ac3796ba828 | note | INSPECTION/TEST METHOD: Record Review
017a663d-4d2c-5c3e-b943-4c9480d31237 | note | RECORD OF CONFORMITY: This ITP signed
8e749043-ac23-5daa-95ba-a370f27eb1f1 | note | IP
8e739a71-7f2d-5da4-a6d5-46c03e70b3f1 | note | RESPONSIBILITY: Contractor Representative
dc1b0f72-e670-5dc9-880e-edbb5c3f890d | date | Date Completed:
| checkpoint | 1.3 - Site Preparation
9b8ebdad-3337-56e3-98a3-7837b4197550 | note | FREQUENCY: Prior to commencing any activity
7df87fd4-19af-5c92-8dd5-6341ba067ec4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings
19d10716-f935-594c-969c-992c4a36472f | note | REFERENCE DOCUMENTS: Cl 721.A06
3d9c7f40-b4f4-5242-b5eb-299d443b3395 | note | INSPECTION/TEST METHOD: Visual inspection
22e34c76-4e3b-50f5-bca5-36703669a21d | note | RECORD OF CONFORMITY: This ITP signed
be8e2b7a-c4c3-56d5-b935-b856f0522b33 | note | IP
ba318583-dcce-58ae-9a15-88c6339d3d8e | note | RESPONSIBILITY: Contractor Representative
c0a3227c-3fd2-52e4-8402-eefb2a8e8534 | date | Date Completed:
| checkpoint | 1.4 - Set-out of Pavement Markings
f6a6625b-a88d-5c0e-ab6c-736aade1f95b | note | FREQUENCY: Prior to commencing any activity
9540f926-dda0-54c0-aaf3-66f7c87e4ccc | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
bd47a7af-ec3e-5ec1-9812-312d3b132e0d | note | REFERENCE DOCUMENTS: Cl 721.A09
86d3e59d-765b-5afc-96fa-8792b3970c3c | note | INSPECTION/TEST METHOD: Visual inspection
6bff27f9-5538-5c47-a0fd-07a29256d1eb | note | RECORD OF CONFORMITY: This ITP signed
d59fa593-53bb-53f7-ad78-3e293676bb4c | note | IP
489b1383-478a-52d0-9933-dc4124058a6a | note | RESPONSIBILITY: Contractor Representative
894fa34a-5fdc-51fd-8e17-2c4e8d16ea98 | date | Date Completed:
| section | 2 - Pavement Markings
| checkpoint | 2.1 - Acceptance of Work
428fad50-95b7-5da3-9457-d3eaac5de2cc | note | FREQUENCY: Each Lot as required
f0ffeab1-021c-5c0d-a9ac-77dae65d54de | note | ACCEPTANCE CRITERIA: Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
63b48046-f39a-5661-be2c-f3b251a7cf66 | note | REFERENCE DOCUMENTS: 721.A12
a592d931-a566-5526-802e-4e163d02ecbe | note | INSPECTION/TEST METHOD: Visual Inspection
f993bf1e-9bfc-579c-ac9b-1bb690598125 | note | RECORD OF CONFORMITY: This ITP signed
2f0190f5-171a-5182-b534-0ec8672c2c72 | note | HP
0b6df03b-7236-5e7e-9a1c-c3140aa7d5f1 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
260fea90-d4b8-5132-80fe-30c549a6ca00 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Position of Markings
98770c54-edae-5264-af3a-17aa275e7a6d | note | FREQUENCY: Each Lot as required
e5685427-40d3-55e6-98c2-2b74cad28ce3 | note | ACCEPTANCE CRITERIA: All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03.
b8ca80b8-2083-5456-80f1-4ae0bef110b8 | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
cde26158-a863-5f60-a07e-1e0ee761d08b | note | REFERENCE DOCUMENTS: 721.B05
6c6afa1b-c0f7-59d6-8077-099697293ff1 | note | INSPECTION/TEST METHOD: Visual Inspection
eb83005f-f9c2-59a5-b356-46830e635099 | note | RECORD OF CONFORMITY: This ITP Signed
ce8b6253-999b-5ef5-84c4-7604833d4bea | note | HP
d8241648-573d-52f7-a3a8-96abc770f744 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
6924cfdb-1c23-5872-b230-b6c191968e29 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Installation of Linemarking
caeb90cc-84a9-5cca-9422-b05d7223df9c | note | FREQUENCY: During Construction
512f7885-de3d-55a3-b099-895f8cb09aef | note | ACCEPTANCE CRITERIA: Line marking installed as per the IFC drawings
1a97de2d-c97d-5f70-883b-4ea9d60f1861 | note | REFERENCE DOCUMENTS: IFC Drawings
640c2f05-c346-5f1e-8f31-47c6dcd64aea | note | INSPECTION/TEST METHOD: Visual inspection
ad4be330-6e0f-5cb7-bcb0-4111c6fb332e | note | RECORD OF CONFORMITY: This ITP Signed
cab4b6ea-bd27-54d9-af2f-9059f6310a90 | note | IP*
17003103-39a7-54d0-8b8b-a2b002bc5ed0 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0a2a1565-bc37-531f-b8ae-578c9b99d151 | date | Date Completed:
| section | 3 - Sign Installation
| checkpoint | 3.1 - Completion Inspection
c2ae7362-933c-5aee-b2ae-6cfa9c30febf | note | FREQUENCY: Each Lot as required
adc3d06e-3d39-5777-9868-3b5eaaddc0b0 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects.
1f0bb2c4-e30f-5d2a-a4d2-3418289d1c61 | note | ○ Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles.
aa028765-6ea6-57c8-b190-3a780324d79b | note | REFERENCE DOCUMENTS:
06445729-ed3b-57d1-917f-a613fce4248a | note | INSPECTION/TEST METHOD: Visual inspection
9b8b45ba-2754-5054-b7ec-532cad0d4a73 | note | RECORD OF CONFORMITY: This ITP Signed
9cc909c1-c37c-5273-98d8-79a87c1be1ad | note | WP
8dbfeccf-4c38-586c-847f-058c7eb244e3 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
c05978f7-009c-52cd-8dc4-3ac370cee26a | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
87023afb-a755-56e8-989e-24e5fb1d7db1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3bdb8cbd-7454-5c30-8437-d82b715ad32f | textbox | Print Name:
12537109-b376-5d0c-8b50-a99ee91acc09 | textbox | Position:
a29495b2-1dd7-53fd-9bc3-dcf33dc74558 | date | Date:
| checklist | ITP-008 - Landscaping - Irrigation | itp | ITP-008 - Landscaping - Irrigation |  | 42245c90-3220-4720-b600-fca80f9c1425
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Pre-commencement meeting
853a0167-927b-5e99-85e0-a057a1a2b886 | note | FREQUENCY: Prior to commencing any activity
cfa4904b-f373-5289-8d67-e648f72bd5e6 | note | ACCEPTANCE CRITERIA: Hold a pre-commencement meeting with council's representative prior to commencing any landscaping activities
09249e30-7f29-5c51-8fc5-a7b03f6fcbfe | note | REFERENCE DOCUMENTS: IFC Drawings
c04fcc6e-4f11-5548-8f6e-6930bebc6087 | note | INSPECTION/TEST METHOD: Verify
31c444e7-54a4-5a95-a497-bbc6f619b9f3 | note | RECORD OF CONFORMITY: ITP Signed
730dc727-0609-55fd-a985-13c28ca0f13e | note | HP
7ee83979-2661-5271-86b3-ecab591e37bb | note | RESPONSIBILITY: superintendent/ Site Engineer
da7b9824-8e29-5558-a38a-7b4f794e3fd1 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Check for correct documentation
56e20228-a53a-5178-8884-118561a9c058 | note | FREQUENCY: Prior to commencing any activity
e094b513-dbce-5b3d-8c58-cb5f6484cfd6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
62228dc7-3fed-5086-aa8d-45cf2c956c6d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
957cad91-c552-597f-8cab-d97c6b24c88a | note | INSPECTION/TEST METHOD: Visual inspection
704feb12-6007-552d-94d0-1653bf4f37c9 | note | RECORD OF CONFORMITY: ITP Signed
e1fdbdf6-9927-5a4b-aa8c-61cd0c5e0340 | note | HP*
99e4f3c7-cc09-5d50-9cf3-c878279733cb | note | RESPONSIBILITY: Site Engineer /Site Foreman
6cfd3a0e-5407-5a16-9153-570ae350e790 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
d76361ca-daad-5766-8b53-10aa597ba293 | note | FREQUENCY: Prior to commencing any activity
7b8a7608-55f0-5319-81b4-7b220714df84 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
e997072e-5546-5ef8-8b77-5e10c6f223df | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
14de4ffc-074e-50d2-b41a-50266a19bb76 | note | INSPECTION/TEST METHOD: Visual inspection
bd047d9e-9196-5e43-8395-61b70addcae1 | note | RECORD OF CONFORMITY: ITP Signed
72cddaed-793e-5660-8abb-cf1fc4c3afd9 | note | IP
22318fed-0fec-5990-b621-9c79fb962cdb | note | RESPONSIBILITY: Site Engineer / Site Foreman
4340a4a7-e78a-5cd2-829a-8ed80d4c6503 | date | Date Completed:
| checkpoint | 1.4 - Irrigation System
7835a9f4-4572-5dc7-8ff0-b240eacc744f | note | FREQUENCY: Prior to commencing any activity
6a639777-00ad-551d-919d-63c889ac529f | note | ACCEPTANCE CRITERIA: The contractor shall get the design approval from City of Ballarat on the irrigation system prior to commencing the activity
4c4a79d9-1362-5c30-8a69-7d3787825c8c | note | REFERENCE DOCUMENTS: Landscape Specification Cl 7.1
575d3083-39d7-5ba0-9e4c-80124006e3fa | note | INSPECTION/TEST METHOD: Verify
2af9f1a6-9f8e-5337-8e1e-91cf0cb8fd48 | note | RECORD OF CONFORMITY: ITP Signed
31b2117f-2af6-5bf8-8cd1-5f72904eff23 | note | HP
5ee3b96f-c63c-5553-9cd2-7e063991765f | note | RESPONSIBILITY: Superintendent/ Site Engineer
e0fa1799-656c-53fb-bf02-aef16aa52ef1 | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
ac5f8ab8-1ec6-57ca-aeb5-41dbea987b4b | note | FREQUENCY: Prior to start
44c1de5d-7f28-5e98-b139-cdf99383118e | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
0febe965-f5e2-598b-aa6a-6fda91d69387 | note | REFERENCE DOCUMENTS: Cl 703.17
3ec51590-b045-5b40-b415-901649a4d929 | note | INSPECTION/TEST METHOD: Verify
7d9b4178-23c4-5664-9992-051efe3b2492 | note | RECORD OF CONFORMITY: ITP Signed
230aa462-a76e-5bbe-a80d-67d3866fd03f | note | HP
0bd6628f-474d-505b-9467-4f96998c9983 | note | RESPONSIBILITY: Site Engineer/ Superintendent
dffd7244-11a6-5d06-a133-cd05676624f8 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Stripping of Topsoil
1e084891-1779-58f4-a1a2-231f1b67c431 | note | FREQUENCY: As required
108d02ef-da52-5c89-a793-b55f32a3ed3d | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation:
67dddc88-5bf5-5397-a00e-ff4b0f781489 | note | (a) defined by the line through batter points extended to include any rounding and any surface and catch drains;
fa3c57a6-9c17-527d-931c-13afaeb2aa5d | note | (b) by a means which avoids contamination with subsoil and does not increase the extent of unstable areas; and
400a637a-3f7b-5e20-a5a7-eeb17614eac0 | note | (c) placed in stockpile or prepared areas.
1a9e2ca0-5bed-545b-b5a7-bc5c39502045 | note | ○ Unless there is an excess of topsoil to be removed from site, topsoil shall not be removed from the site.
6592027f-71d0-593b-992e-2c4b284bcdd1 | note | ○ The Contractor shall treat and manage site topsoil before stripping, and after spreading, to remove and/or minimise the spread of weeds and other pathogens and pest organisms throughout the site.
5db13197-112c-57a2-aae0-82cfe46705bb | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re spread as soon as practicable.
bee860e3-9d12-5146-9b96-c90603c311d9 | note | ○ Stripped surfaces shall be graded to an even self draining surface.
34e625e5-4943-50c3-98b0-93d3a9f3e398 | note | REFERENCE DOCUMENTS: Cl 204.05
5a18440f-aa90-5574-8090-560a5b4838eb | note | INSPECTION/TEST METHOD: Visual inspection
e98756f4-7294-5c04-b24f-903e899888af | note | RECORD OF CONFORMITY: ITP Signed
14b31614-37fe-5ff4-9878-a2b60db4eb2f | note | IP
56d49d6d-8b11-5106-b92e-8e4f3f8ace37 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
1d0442ef-03f3-599d-b1d1-c9d5ed38053c | date | Date Completed:
| checkpoint | 2.3 - Topsoiling
98a03d9c-1cf0-5391-81c3-588c97354309 | note | FREQUENCY: As Required
43a81dbb-7a1d-539a-8d4f-c7817d99a86b | note | ACCEPTANCE CRITERIA: Topsoiling shall not be placed over cut and fill areas until the Contractor has verified that such areas comply with the requirements in Clause 204.03
a607fe23-f7f7-5ad1-b845-a906cefa728a | note | All unpaved cut and fill areas within the limits of the batters, including batter roundings but excluding cut batters steeper than 1.5 to 1 (horizontal to vertical), and any other area disturbed by the Contractor's operations, shall be topsoiled to the following thicknesses measured normal to the slope:
ba954733-8692-58ed-84f4-0b69814d9245 | note | (a) batters with slopes of 2 to 1 (horizontal to vertical) or steeper 50 mm minimum
8d24a76a-b22d-5827-a320-4a0e2ecdc5c9 | note | (b) tree and shrub plantation bed areas other than (a) above - 100 mm minimum
6212fefa-d293-5925-94c0-d44875c04127 | note | (c) verges: In areas without kerb and channel or concrete edging strips the depth of topsoil shall vary uniformly from 50 mm deep at the outside edge of verge to 20 mm deep within 100 mm of the edge of seal or asphalt surface treatment
c74a6cb8-337d-58f1-b5f8-19e0d438e962 | note | (d) all other areas 75 mm minimum.
3f3b44bd-0297-5995-8d24-64de0adbe5fd | note | ○ Topsoil shall be placed and levelled but not compacted except for verge areas, which shall be compacted. Topsoil on batters shall be placed so as to prevent rilling.
a283627a-cc61-5c2f-9b15-e4a091ec059c | note | ○ The surface level of topsoil shall match the finished surface level, or level of back of kerb or concrete edging, as appropriate.
b6d09ee1-05d4-57c3-bf8c-b69861d8ee7e | note | REFERENCE DOCUMENTS: Cl 204.17
38538947-078a-5598-bc05-931962eef3cb | note | INSPECTION/TEST METHOD: Inspect
f209bfcc-bea6-5d84-bcd2-761b1f84b961 | note | RECORD OF CONFORMITY: This ITP Signed
99260e7d-d0e2-568b-92fb-99c01454f6bb | note | IP
50803013-533c-5492-8dfd-8b9f1271a7db | note | RESPONSIBILITY: Site Foreman
196d4498-b984-5cf5-aa53-f4205c7c4268 | date | Date Completed:
| checkpoint | 2.4 - Tree Clearing
b9b231a4-ed76-5dc6-b61b-69a4759b4919 | note | FREQUENCY: As Required
27b9aee9-d15c-5b45-be5c-ae1b4dc7d97d | note | ACCEPTANCE CRITERIA: The Contractor shall seek the Superintendent's approval prior to the removal of any tree. An inspection of the tree by the Superintendent or the Superintendent's environmental representative, along with the City of Ballarat is required.
4122e79c-2e93-5f64-aee7-353906143241 | note | REFERENCE DOCUMENTS: Cl 200.1
519a044a-b0cb-54c8-84e8-f6c897add546 | note | INSPECTION/TEST METHOD: Verify
740d2b8f-6527-5798-be77-c4488913f0fb | note | RECORD OF CONFORMITY: This ITP Signed
dc43cd2d-ce05-5042-90f9-61dbb755482a | note | HP*
be6e4eac-2c04-577e-8a9d-043884002c9c | note | RESPONSIBILITY: Site Foreman / Site Engineer
f5181850-020b-586c-aa6d-78ba577c064b | date | Date Completed:
| checkpoint | 2.5 - Hard infrastructure preparation
1c3fc449-fa29-5c3b-be12-0b1910920e98 | note | FREQUENCY: Each Lot
78e7d991-aee0-5655-8504-62abecf98258 | note | ACCEPTANCE CRITERIA: Footings excavation – Site excavation shall be excavation within the limits. The Contractor shall conduct its operations such that the area outside the limits of the excavation is not unduly disturbed. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
66fe9d2e-9141-53fa-bdd4-03097b8fde71 | note | ○ Reinforcement for pavement/footing – All steel reinforcement shall be securely held during placing and compacting of the concrete.
12ba794e-6009-520c-9615-5e28c716bbfd | note | REFERENCE DOCUMENTS: Cl 204.06 (d), Cl 204.10 (b), CL610.26 (a)
0a93ec14-3373-5990-a46e-e3d265fd021b | note | INSPECTION/TEST METHOD: Site Inspection
d76c06bc-7326-500a-a0e5-bc034f0f96ea | note | RECORD OF CONFORMITY: This ITP Signed
c00fb6cd-a83c-53e8-9819-116b2e28abb9 | note | HP
d5cc7ee8-6b43-522c-9467-976f9ed3b7f3 | note | RESPONSIBILITY: Superintendent/ Site Engineer
3eba5929-4b48-5fc0-971c-2ae0659e6b4e | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Soil Preparation
bfe5a1bd-d69b-55bd-b3ee-d568a8e2a463 | note | FREQUENCY: Each Lot
4e24a9ab-792a-516d-98cf-905f30f6fe19 | note | ACCEPTANCE CRITERIA: All the necessary soil/garden bed preparation shall be approved by the superintendent prior to planting.
c4544e39-d264-584f-a73f-258c2a17f3e7 | note | ○ The planting soil should be prepared in accordance with the Tree Planting Detail and the landscape specification plan.
4eb432b9-657f-56f5-a159-5598165ec8be | note | REFERENCE DOCUMENTS: Cl 720.10
0ed980b9-f74d-540c-99df-f7065d5b6166 | note | INSPECTION/TEST METHOD: Site Inspection
eb810465-f9aa-57b4-b09a-76edb5f23178 | note | RECORD OF CONFORMITY: ITP Signed
b2d88584-e502-5230-9139-77bdb60a3dc4 | note | HP
998a5c8d-48bf-5f77-b5a9-01085dc8fef6 | note | RESPONSIBILITY: Superintendent/ Site Engineer
5156b568-1a68-5457-aa6f-451d41b7f8c4 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.6 - Plant Stock
0a67fe19-a78c-5bd5-8f1d-81e6e576cbd7 | note | FREQUENCY: Each Lot
a2b496e0-bd7e-52f7-9c1a-274b15904672 | note | ACCEPTANCE CRITERIA: All of the trees and garden bed plants shall be inspected and approved by the council representative prior to plantation.At the nursery ensure that individual trees and batches are clearly labelled with the species name and cultivar / variety / provenance where appropriate
f66c6ae6-3a55-5b6e-8209-1217edae141e | note | ○ Hardwood stakes, as per details are to be installed immediately after planting.
db3d2731-070e-574f-b4b1-a5b3b2f8f58f | note | ○ Stakes are to be driven 600mm into the ground or deep enough to ensure that the stake will remain stable and vertical.
184c1505-7e0c-5e38-bece-08828d6a8f03 | note | REFERENCE DOCUMENTS: Cl 720.04
f714766f-17fe-5581-988e-9d42e33748e8 | note | INSPECTION/TEST METHOD: Visual inspection
d4836364-1fc5-53c2-882a-530328bf9d7c | note | RECORD OF CONFORMITY: ITP Signed
c85bf914-6f04-534b-9266-fbb9dbf475f8 | note | HP
7bfbcce9-84e1-5100-b93d-635e57fd7340 | note | RESPONSIBILITY: Superintendent/ Site Engineer
e1db7c1f-43a6-5b11-ab1b-e681502d5aac | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.7 - Mulching
f33cb869-e777-59b9-87ad-745ee8bf1de0 | note | FREQUENCY: Each Lot
f9dea6b9-70af-587a-96c2-d97c710c14b8 | note | ACCEPTANCE CRITERIA: After topsoil placement and planting-out of the plant material in all garden beds, supply and spread mulch to an average compacted depth of 75mm. The mulch shall be free from soil clods, rocks and all other non-organic matter.
32d24f77-f106-52ef-ad59-d5dd4f3408a7 | note | REFERENCE DOCUMENTS: Cl 720.08
ea57ff7f-e87b-537e-8490-5bc8118fa198 | note | INSPECTION/TEST METHOD: Visual inspection
47120751-bf54-5b60-bdf1-a754e8d56ac4 | note | RECORD OF CONFORMITY: ITP Signed
d7a4f5a2-a523-56da-bfa6-62614067ece5 | note | HP
fe723258-5863-5462-aa4b-f21e3c1e44a1 | note | RESPONSIBILITY: Superintendent/ Site Engineer
171273e9-86b5-5e98-817f-db287b0b2d21 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Practical Completion
10b179bb-a3af-5e75-9967-b74b72030c4f | note | FREQUENCY: Completion of each lot
72970fd3-4d96-5900-9b8b-78b00a7042b2 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
f770493f-3c5f-5c08-bf70-d303578cff46 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
29a7f6bf-6aae-533a-a2ae-36318d7bdda1 | note | INSPECTION/TEST METHOD: Document review
8ddb9bd6-5859-5aac-a5f3-3b99d035caa5 | note | RECORD OF CONFORMITY: As-built survey records
824589d8-a101-5f68-b109-52ae1891ba7e | note | SCP
2e78eef8-3521-5b1a-8325-3239ba9b71fc | note | RESPONSIBILITY: Project Engineer/ Surveyor
5b26e1f3-da49-5394-86f1-f502731db1ca | date | Date Completed:
| checkpoint | Final Inspection
e3f74864-64dc-51fc-bb52-901df17bf1cf | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
47fc5c1e-b4d4-534c-b1d2-b84e61c6fdfc | textbox | Print Name:
eb0dcbc0-6d4a-5ec6-9812-9c0f1280ad25 | textbox | Position:
8f9a1919-aaf8-5404-9587-8c4a69357868 | date | Date:
| checklist | ITP-009 - Spray Seal | itp | ITP-009 - Spray Seal |  | 6933ac78-22a3-40aa-a741-fe69352e5390
| section | 1 - Materials
| checkpoint | 1.1 - Bitumen
cf8c2b82-e1f8-5258-8b4a-529134e74555 | note | FREQUENCY: Test cert upon request
1ed522cc-6e99-5a60-b973-81c07a06a928 | note | ACCEPTANCE CRITERIA: AS (Section 175) for residual bitumen for pavements
cd6fcc3e-113f-58b8-a523-c9303060de11 | note | REFERENCE DOCUMENTS: 408.08 (a)
bf18bfde-45a3-506a-9484-d882a9ae6e80 | note | INSPECTION/TEST METHOD: Verify
c2160dd4-f9a9-5ea5-8ac5-bc51a93b7dc1 | note | RECORD OF CONFORMITY: ITP Signed Off
1a47d285-0f69-5fb5-b3da-577590fad08a | note | IP
fca85a99-aeca-522c-91f7-35ae0089b63a | note | RESPONSIBILITY: Lab Manager
62709113-0dae-5ad8-89fc-3c8900618f0b | date | Date Completed:
| checkpoint | 1.2 - Bitumen Emulsion
981e31a6-788b-535b-ab37-97670e0ba70f | note | FREQUENCY: Test cert upon request
862adf3c-ed7c-5dd2-9801-65be47bb6fe7 | note | ACCEPTANCE CRITERIA: ARS or CRS comply with AS (Section 175) – Bitumen emulsions for the construction and maintenance of pavements
f241c6e0-8a92-55cf-8701-bf584ea9c7c9 | note | REFERENCE DOCUMENTS: 408.08 (b)
1848b8b7-6a40-5b71-a5dc-3fa4f0154331 | note | INSPECTION/TEST METHOD: Verify
1f197d29-c296-50c2-a84a-8f838500c2cc | note | RECORD OF CONFORMITY: This ITP Sign off
45a15764-bba0-5565-9d77-d4e654aed857 | note | IP
b379c152-5e0a-5fc1-9bb3-ecb131281613 | note | RESPONSIBILITY: Lab Manager
33e3d0d4-73dd-52aa-a446-6ac8e4cc9c22 | date | Date Completed:
| checkpoint | 1.3 - PMB
b1ffd8bb-099d-5154-9d9e-468ed2c9bfb7 | note | FREQUENCY: Test cert upon request
33fb7864-327f-5a6c-94b3-194d086503cb | note | ACCEPTANCE CRITERIA: Austroads Specification Framework for Polymer Modified Binders and Multigrade Bitumen’s (AGPT/T190 - section 175) & table 408.161. Alternative PMB'S shall not be used without approval by Superintendent. Evidence of satisfactory field performance for 3 years required.
98a4698d-cb6c-5b4f-a588-6cd1735b733a | note | ○ (i) HSS - S10e,S35e,10Pts CR, or alternative approved by superintendent
4dcab687-c0e9-50aa-8fe7-d92d2ff1467e | note | ○ Field Produced CR - >5pts by mass of binder, Carrier oil <4Pts by volume of binder
e66cdce0-a311-529d-b4d9-6e64eac8f45c | note | ○ (ii) SAM - S45R,S20e,18Pts CR or alternative as approved by the superintendent
020effc2-d394-5800-80ef-321aa46fdec6 | note | ○ Field Produced CR - >18pts by mass of binder, Carrier oil <4Pts by volume of binder
ebb329ae-eb2c-5cfe-a7ce-1ee5edf1d90b | note | ○ (iii)SAMI - S25e,20PtsCR or alternative as approved by the superintendent
fd0d5fb2-e6fd-5795-960e-4e6a3334a478 | note | ○ Field Produced CR - >20pts by mass of binder, Carrier oil <4Pts by volume of binder
6681891c-3acd-591a-bb66-a07fa0084d3b | note | ○ XSS treatments – Class S20E,S45R or S15RF or alternative as approved by the Superintendent.
aab1cce7-347e-5112-9478-171010a72ef6 | note | ○ XSS treatments are applied as a double/double application and the same binder shall be used for both applications.
686e338b-70bc-5116-b324-d28390c3c7f3 | note | REFERENCE DOCUMENTS: 408.08 (d)
994c14a3-345c-58ee-a3a0-56f6f63ad710 | note | INSPECTION/TEST METHOD: Verify
620a030c-d75b-5348-81d8-45158d7b30a2 | note | RECORD OF CONFORMITY: ITP Signed Off
0bee2a43-7005-54f9-b34c-6100d7aeee3b | note | IP
71a8a8ec-8548-5992-a8ce-abe5e9aefaea | note | RESPONSIBILITY: Lab Manager
8c75b9e7-a54d-500e-bacb-731fe227e8b0 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 1.4 - Primer
3cb51401-50e7-57c7-abfc-d263def98d8a | note | FREQUENCY: Test cert upon request
4caf649a-6565-571e-b1d6-559ace3885de | note | ACCEPTANCE CRITERIA: Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
b0bfd259-3589-5718-a817-f57ac613700c | note | REFERENCE DOCUMENTS: 408.08 (e)
c9379d87-6136-5e62-a8dc-1e38e80e9fba | note | INSPECTION/TEST METHOD: Verify
ea48b241-6eb0-55ac-ae5c-3497aad1bb01 | note | RECORD OF CONFORMITY: ITP Signed Off
e48b73f9-f0be-5690-88cf-2fcfca068fde | note | IP
3c20b54c-47e9-5213-92da-e3618c34e78c | note | RESPONSIBILITY: Lab Manager
b5ca252d-7c22-56e3-92af-ebabbe7d25c0 | date | Date Completed:
| section | 2 - Aggregate
| checkpoint | 2.1 - Aggregate Specification
5009051a-d136-5a74-8ee6-5ecff7bdc41e | note | FREQUENCY: Maximum lot size 350t of same class and size
5980d4d0-42b3-5005-9430-0588ded912b6 | note | ACCEPTANCE CRITERIA: VicRoads Standard Specification Sections:
cb8af897-fc63-537b-b078-1c11269faacf | note | ○ 801 - Source Rock, 831 - Aggregate & 832 - Sands
387e3d89-560d-5fdf-aaa9-aaf64c7aa338 | note | REFERENCE DOCUMENTS: 408.11 (a)
57e63b05-2cd1-5929-a4c7-bf16a09c1e10 | note | INSPECTION/TEST METHOD: Verify
7ffd3d2a-24d7-5176-9172-2373436964cf | note | RECORD OF CONFORMITY: ITP Signed Off
dcff01eb-07d8-5e21-abd6-08d8019ad7df | note | HP*
5d9b3604-a20f-5832-bde5-4e2da3ac4bca | note | RESPONSIBILITY: Lab Manager
6eda6623-7a77-5190-8bca-2c64307dc037 | date | Date Completed:
| checkpoint | 2.2 - Precoating
cdaa085f-743e-5d28-ac34-81c83bb2cc43 | note | FREQUENCY: All works carried out
de66c749-51bb-5163-ab67-382d196214d2 | note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate from supplier or field precoated aggregate from stacksite.
03b55aca-45ff-5256-ae97-a1a0b0fa5d8b | note | ○ Aggregate shall be uniformly precoated to the satisfaction of the Superintendent.
e39faba2-f206-5ff0-9c52-40ff1d27c19a | note | REFERENCE DOCUMENTS: 408.11 (b)
5860aef0-2a3b-5749-9e7f-7416d65194c7 | note | INSPECTION/TEST METHOD: Verify
f203ddd5-8175-5f42-99d2-870f1ee42317 | note | RECORD OF CONFORMITY: ITP Signed Off
ae535737-a08b-582d-811c-7cb534b00539 | note | IP
49f39891-0d8b-5654-a0e9-5d3bc232defd | note | RESPONSIBILITY: Supervisor
653520c2-560d-58e1-86cf-560e6be7611c | date | Date Completed:
| checkpoint | 2.3 - Removal of loose aggregate
2609bf1b-2d54-52d0-ba7c-0a5491e8b673 | note | FREQUENCY: All works carried out
54d3778d-8ca6-5af9-bac1-328db7db8eeb | note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
1067ff92-1b86-5d19-95ed-c5aab22feec1 | note | ○ NB: For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
86deacdf-fde0-54e1-a637-c0c0c42983f3 | note | REFERENCE DOCUMENTS: 408.14
3f4b1e17-5994-5a96-9eba-c764d3a4bdb0 | note | INSPECTION/TEST METHOD: Verify
ee170694-089a-5174-8439-5f4300e2dc26 | note | RECORD OF CONFORMITY: ITP Signed Off
26a0a3f2-f463-5c9f-ac03-ad773a3fc83d | note | IP
6e795b54-5628-5d51-9d89-be892028fcf3 | note | RESPONSIBILITY: Supervisor
8d48ece0-6612-5514-aa60-673d13db54ce | date | Date Completed:
| checkpoint | 2.4 - Stack Site
06c0ed63-518d-561c-9151-62afdbbfdd24 | note | FREQUENCY: Prior to commencing works
5e055cf7-a985-55c1-9fb1-49d34c901267 | note | ACCEPTANCE CRITERIA: Stack sites to be approved by Superintendent.
1e1a6ab9-52b3-5151-88c9-4ef7dbe15e28 | note | ○ Stack site to be at Kent Street where road is closed.
0a410bcb-daf3-580e-ae5c-e6c7bc07b350 | note | REFERENCE DOCUMENTS: 408.12
b121c911-f247-5559-842d-d4223448c4e9 | note | INSPECTION/TEST METHOD: Verify
b6a5b7e9-df09-5591-8299-9626d28cf89f | note | RECORD OF CONFORMITY: ITP Signed Off
bfcce4c1-8565-5250-aba3-c05af926a226 | note | IP
6385aa14-d7be-549a-9a02-cd56a9c7267c | note | RESPONSIBILITY: Supervisor
996e11ac-cf58-50a3-b88f-dd3706e8878f | date | Date Completed:
| section | 3 - Operation
| checkpoint | 3.1 - Rates of Application
cd5c0359-4d6f-5da6-a622-0bec54ab12ca | note | FREQUENCY: All works carried out
339d5030-9cd3-5452-b798-63ec7aecc061 | note | ACCEPTANCE CRITERIA: In accordance with the current Update of the Austroads Sprayed Seal Design Method (Section 175) rates of application - residual binder at 15 C
7066f44f-61d4-54a4-a3d8-3fe816dfde2a | note | ○ Traffic Data and default rates -Table 3040.066 (Traffic Volumes)
e87ff964-f872-5997-bfee-4e417c46c3cd | note | ○ 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
8d519228-6064-57ec-a4bf-dcda133483d6 | note | REFERENCE DOCUMENTS: 408.15 (a)
fb7b3a98-2b26-52bd-8394-20f8ee5f4374 | note | INSPECTION/TEST METHOD: Verify
7f6027f0-3632-567b-8577-92cea10a040e | note | RECORD OF CONFORMITY: ITP Signed Off
19cd034d-40cb-5935-98ab-12a8bad4c091 | note | HP
1efb6130-35b3-57b7-ac03-86fc959c9362 | note | RESPONSIBILITY: Site/Project Engineer
8ea5fb3a-153e-552c-9391-23377f7bf5c1 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.2 - Surface Pre-treatment
0d76321b-f448-5e6c-a373-78a6e1d59bbc | note | FREQUENCY: All works carried out
f9456d29-0b96-589d-b948-17455c26672b | note | ACCEPTANCE CRITERIA: Refer Table 408.171, 408.132, 408.133
b33c4908-1b12-5a98-8f4c-dbf23068e64b | note | REFERENCE DOCUMENTS: 408.13 (b)
ae9b6564-4669-547d-9168-e74540588729 | note | INSPECTION/TEST METHOD: Verify
008e1d20-eda1-5f20-b607-fe679a3b44f4 | note | RECORD OF CONFORMITY: ITP Signed Off
a41b70c6-85c0-5bc2-87d5-aa591abf4b02 | note | IP
b4db4cc0-242d-518c-a2e0-f367e166a77c | note | RESPONSIBILITY: Supervisor
cb17742a-45a7-5300-999a-af9161b948ea | date | Date Completed:
| checkpoint | 3.3 - Calibration of Bitumen Sprayer
482b31d1-4209-5037-ba5b-9eab7593020c | note | FREQUENCY: Prior to commencing works
fe14a9ba-f695-5bcb-8fa9-020bd34a41d5 | note | ACCEPTANCE CRITERIA: Calibration Certificate to be provided
4ae4ffeb-e90e-55cb-a4fd-f2d5c157b4a1 | note | REFERENCE DOCUMENTS: 408.07
eb7b1adf-5d4c-5ee3-b748-99b489c9191c | note | INSPECTION/TEST METHOD: Verify
06f67010-e7d8-5ab6-9043-030c7625b707 | note | RECORD OF CONFORMITY: ITP Signed Off
0bf464c0-940c-53a4-982b-3d8f1404eb21 | note | WP
6d1156a2-bfc7-5281-b597-da9852674a07 | note | RESPONSIBILITY: Supervisor
257dd25f-d81c-5db5-a797-ef0c141e34d2 | date | Date Completed:
| checkpoint | 3.4 - Commencement of works
1940f20b-b464-5530-a76d-f58fed609f01 | note | FREQUENCY: Prior to commencing works
88e2aea6-1190-55b2-a73d-1faa4b9380a2 | note | ACCEPTANCE CRITERIA: NB: Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing. This includes a review of the material and evidence that the pavement passes compaction testing to Superintendents approval.
3dd8551b-cd46-54d6-ae41-a28fb09a5dad | note | ○ Primersealing shall not be carried out within 12 hours of forecast rain.
d7acd64a-f196-58ba-92a3-014a39d12384 | note | REFERENCE DOCUMENTS: 408.04
f2da6cc6-57cd-5021-a242-5b241a23908b | note | INSPECTION/TEST METHOD: Verify
0263807e-4750-5120-bb53-726f22994f58 | note | RECORD OF CONFORMITY: ITP Signed Off, QD2190370 Sealing Checklist
8d46091d-da67-5530-bfdf-8d8f4bc30253 | note | HP
d22e219c-0208-59fe-825a-7ba92c8721bc | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor / Superintendent
d3cd9ea6-e59a-5acd-9fba-baf07b800c95 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.5 - Records
c1b8fffc-f6a5-50fb-94e0-970fa91e2fd4 | note | FREQUENCY: Each Lot
0b1c0d15-b779-5d77-8178-39166cf0118b | note | ACCEPTANCE CRITERIA: Job completed within spec requirements.
795e729c-97b1-5045-a794-114ec2d2c4b9 | note | ○ Job completion report ,i.e. Spray Sheets to be submitted within 7 days of completion of sealing works
baa4295d-3f64-5c37-901b-82f3b7781c6c | note | REFERENCE DOCUMENTS: 408.17
c3c108cd-18af-5866-941b-007906d398b2 | note | INSPECTION/TEST METHOD: Verify
d7e13d89-ac77-5f7f-b345-3c37468a7ec0 | note | RECORD OF CONFORMITY: ITP Signed Off, Spray Sheets, Section 408 Attachment A
dc212a60-dd23-5e21-af7f-a93a1ce61312 | note | WP
b6ce4572-7f61-5d8f-af4e-1cc3d98e5d33 | note | RESPONSIBILITY: Site/Project Engineer
f1b65d4a-d2f7-52a1-a196-cbefccb5b98c | date | Date Completed:
| checkpoint | 3.6 - Acceptance of work- Binder rates
35803d08-2140-5cf3-bb30-5829415c0230 | note | FREQUENCY: Each Lot
bd227f24-30c7-5f26-b4cc-a9a6404e914e | note | ACCEPTANCE CRITERIA: Actual vs design rates. Variation between actual & design assessed by Table 408.121
d7d87100-9265-5457-a3bd-c69b533cf294 | note | ○ ie. Variation from the Design Rates of Application for Bituminous Material < 0.1 l/m² below the design rate of application
6fe25301-3a7b-591c-85a7-b9e9c6a19d4e | note | REFERENCE DOCUMENTS: 408.15 (a)
7e3cccaa-dcab-5134-b41d-37f4c01657ff | note | INSPECTION/TEST METHOD: Verify
1f63bd85-a8a2-5e28-9135-3601f800539d | note | RECORD OF CONFORMITY: ITP Signed Off
059391f1-01bf-56a0-a9b4-3c3ea59efeb0 | note | IP
26af97d1-4dba-560d-a028-9442863cbbe3 | note | RESPONSIBILITY: Site/Project Engineer
579be6fa-21e1-5757-b54b-cfc75ec74b8c | date | Date Completed:
| checkpoint | 3.7 - Acceptance of work- Surface Texture
2b88e164-a20e-5c51-acf6-93acb3588b66 | note | FREQUENCY: Each Lot
5a39a8f4-4d11-5a2e-8e8a-75630fda8a41 | note | ACCEPTANCE CRITERIA: Acceptance - visual assessment or (where required) as per Table 408.122
e6fdd7fe-974e-5491-b7f5-8294c3f10e15 | note | ○ ie. 7mm Primerseal Mean Texture Depth between 1.0mm to 2.0mm
8bc24240-554f-592f-8141-97bd9b27dd29 | note | REFERENCE DOCUMENTS: 408.15 (b)
6f36e90c-b280-52d2-b687-ed969d07364d | note | INSPECTION/TEST METHOD: Verify
44517dbd-1b67-5883-998e-cd4f1800db58 | note | RECORD OF CONFORMITY: ITP Signed Off
86358662-f551-59ce-89f3-00392b51d4ae | note | IP
52e7b359-60a2-50ca-8552-aa7eda68ebc9 | note | RESPONSIBILITY: Site/Project Engineer
c34cb7aa-8ec9-5ccf-a479-317f58c6f551 | date | Date Completed:
| checkpoint | 3.8 - Acceptance of work- Aggregate retention
11352f66-732a-5fdb-8cc9-4524736bc0e5 | note | FREQUENCY: Each Lot
48d22bdb-1d7f-5e6a-95b1-defdc1379c86 | note | ACCEPTANCE CRITERIA: Acceptance -visual assessment or (where required) as per Table 408.123
d0d5b63c-739d-5ba1-8e8f-4e99e053505c | note | ○ Degree of Aggregate Stripping is 0 - 2
d9d94718-85cc-5bcb-a5b9-3d79d25f283c | note | REFERENCE DOCUMENTS: 408.15 (c)
e3460647-bf3c-536c-8804-ae7a43d692d6 | note | INSPECTION/TEST METHOD: Verify
095c044c-2ba0-5b7b-8df2-c337eacdee2b | note | RECORD OF CONFORMITY: ITP Signed Off
b7afaac4-7472-594a-b188-b2a39492bb1f | note | IP
c35bb559-1260-5561-a085-1ebeba9f0d91 | note | RESPONSIBILITY: Site/Project Engineer
d0f798e8-bf50-558b-b83c-27534e8698c6 | date | Date Completed:
| checkpoint | 3.9 - Acceptance of work- Visual Uniformity
c0eca1d8-9ff0-5d33-8078-65a58bb028f6 | note | FREQUENCY: Each Lot
668b70ab-3f5b-5f81-99df-69b4e94cfa9f | note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
cb2bc0bd-7e94-57f9-ba41-600a811009c1 | note | REFERENCE DOCUMENTS: 408.15 (d)
2259931e-3777-53fc-8319-e313ee4b25b9 | note | INSPECTION/TEST METHOD: Verify
eedd8402-331c-5eb0-b986-e58c983017e3 | note | RECORD OF CONFORMITY: ITP Signed Off
70643e20-5b7b-5d85-867d-c39f4c391a7d | note | IP
bd5368fd-7373-5618-b447-c4f9f1d92a6e | note | RESPONSIBILITY: Site/Project Engineer
134e6799-7ea9-53ed-a111-642abe5d0ad7 | date | Date Completed:
| checkpoint | 3.10 - Maintenance of seals
7ba4553a-d7bc-513c-8a63-a4844a8b614b | note | FREQUENCY: All works carried out
c9a64cca-c902-5c2a-abb9-c5abb1127451 | note | ACCEPTANCE CRITERIA: The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period.
90228f7d-1f6c-5257-b239-621dca8327de | note | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work.
f7782422-9d59-5eec-871f-a1bbca78e960 | note | REFERENCE DOCUMENTS: 408.16
6473d6a1-5c54-5951-a932-be394e5d1c1f | note | INSPECTION/TEST METHOD: Verify
526e2434-107c-5765-acec-b5797d354869 | note | RECORD OF CONFORMITY: ITP Signed Off
35dcc858-743e-5a1c-8fa3-8bc754319a39 | note | HP
bc6c480b-6bef-5e95-ba38-c6e753cc1ff8 | note | RESPONSIBILITY: Site/Project Engineer, Superintendent
b40b5056-45af-57a3-bc75-eded7543f1da | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.11 - Maintenance of seals
b8701a1f-1c68-536a-bb55-cc1a60101f61 | note | FREQUENCY: All works carried out
9e51ae32-6d4c-538d-a5ff-53d324fd381a | note | ACCEPTANCE CRITERIA: Where the treatment for protection or repair of a seal involves the application of a further seal coat, the Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work.
7661befb-b56f-5290-b022-1fa558e57143 | note | REFERENCE DOCUMENTS: 408.16
b6dbda95-7a31-5d55-b1e0-571a8ac43ed2 | note | INSPECTION/TEST METHOD: Verify
a68fabb7-7ec8-5d41-8717-8b0bbe0dcea9 | note | RECORD OF CONFORMITY: ITP Signed Off
f12d1018-0d90-5e50-8c02-0aed21dc34fe | note | HP
401ce194-f804-58ae-880f-907e6ebedd8a | note | RESPONSIBILITY: Site/Project Engineer
17d49fda-e67d-56f2-8595-dc424af22493 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.12 - Defects Liability Period
445e7859-359d-5e05-85fa-4c730cab97f3 | note | FREQUENCY: All works carried out
76274f15-b865-546c-aa6d-78530e30ae51 | note | ACCEPTANCE CRITERIA: All defects should be rectified six months prior to the conclusion of the Defects liability period. As stated in 408.15
eff863f0-7c2a-5658-b8ef-a218c51c67fe | note | ○ The Contractor shall carry out at least two inspections of each job during the Defects Liability Period and provide a condition report to the Superintendent. The condition report shall detail the condition of the seal, any defects and the proposed corrective action.
6be15b0d-f153-515e-9c73-8ccea3088d17 | note | REFERENCE DOCUMENTS: 408.18
7b949f78-ecc1-5d0f-8750-45b11f478498 | note | INSPECTION/TEST METHOD: Verify
569181d2-4d08-5847-bd62-f03c2f92c04f | note | RECORD OF CONFORMITY: ITP Signed off
aa4680ff-feb6-5b55-aac5-399c8c7c7c35 | note | WP
9ee920cd-e08f-500c-8e32-223adf18ba10 | note | RESPONSIBILITY: Site/Project Engineer
2e1021a3-117a-5664-92b7-13eba7bb5e95 | date | Date Completed:
| checkpoint | 3.13 - Dryback
3d316781-ddcc-54b5-84fd-c89474d049af | note | FREQUENCY: Each Lot
164c63b6-264c-560e-ae6d-e762314a1749 | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
5a8b22b4-67a1-567f-b938-6781c737f64e | note | – 6 randomly selected test sites per lot required
1b901cbb-5ec0-53f0-880e-6bfaff674974 | note | – If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
ee3882e9-0494-5515-b472-cd35fa0e9382 | note | – If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
565c61d4-345a-5e05-8eaf-18d303bd356d | note | – Testing shall be undertaken no more than 24 hours before primersealing.
574acc39-b34c-537b-ae46-0488e087ac4a | note | – Testing schedule in accordance with 310.03 (c) and QD2190370 Sealing Checklist
3ec59cd9-bb55-5cd0-ba9b-f542206c4dfa | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b), Table 310.031, 310.03(c), Table 310.032
bf92af0d-3709-5bc8-8ff7-0a8d5ea39cde | note | INSPECTION/TEST METHOD: Verify
27059443-70cd-5e76-a8bb-4fc2b0746e33 | note | RECORD OF CONFORMITY: ITP Signed off
533cafd2-fdb5-5fb3-b330-101a7837696e | note | TP
36a17751-d6fe-5bac-92d6-57078f6fb40e | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
0874526e-3972-55c6-b5e1-910d99c512f7 | date | Date Completed:
| checkpoint | 3.14 - Ride Quality
7c2ebea5-9f14-5a3b-b358-ce50e83b9065 | note | FREQUENCY: Each Lot
659977aa-aeaa-557e-b2d1-50d80d141135 | note | ACCEPTANCE CRITERIA: Ride quality measurement shall be undertaken within 3 months of the completion of primerseal and prior to practical completion being awarded by the Superintendent.
60526126-9725-56e5-aa6d-6f3b8d188fdd | note | ○ The finished surface of the Primersealed pavement shall have a smooth longitudinal profile and comply with the minimum ride qaulity requirements of Scale C road as specified in Table 180.092.
550db4c8-f84e-5cad-b1fb-ad93b8d796ce | note | – Maximum Individual Lane Roughness Value for any 100 m Subsection = 2.70 m/km/lane
e30ab99b-3522-504e-b935-d33597cb6a1e | note | – Maximum Mean Lane Roughness Value for Lot = 2.00 n/km/lane
6ce28f55-61c0-5ea7-897f-9bdb78771ef3 | note | – Maximum length of lot is 2km of continuous traffic lane
d14b5b3c-ca38-5e41-893b-1bc91cacb8dc | note | REFERENCE DOCUMENTS: 180.04, 180.092
fdcf3937-a031-51c0-9563-888ba3011195 | note | INSPECTION/TEST METHOD: Verify
86e7813a-e422-5fb3-89c5-a1d05d413e90 | note | RECORD OF CONFORMITY: ITP Signed off
975ed6c1-f2e0-526c-bca8-c61c92b243ae | note | TP
2832e547-19b8-5ed5-9c7b-aec700e18a4d | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
9df1d72d-d27a-59d0-9674-e5334476d2a5 | date | Date Completed:
| checkpoint | Final Inspection
b6966187-50c9-5401-a753-0d43ac4bc7c4 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bbfa7a50-f25f-5462-bb97-a9b322a234ae | textbox | Print Name:
b89cdb17-6056-5cfb-9f45-dd843a150c09 | textbox | Position:
6dacf4f6-de8f-5626-9ab9-e420f95cadfc | date | Date: