## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | ITP-002
[11 empty] | Revision : 1 | 2024-07-10
Client: |  | City of Ballarat |  | Construction Process: Underground Stormwater Drainage |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Learmonth Street Road Widening & Associated Works |  | Specifications: VicRoads Standard Section 701, 702, 705, City of Ballarat Infrastructure Design Manual & IFC Drawings 2022-95, SD-C4 to SD-R2 |  | Name: | Rakib Hossain | Name: | Hugh Burns |  | Name: | Andrew Cotter
Contract No: |  | Contract No. 2022/23-101 |  | Structure / Component: Underground Stromwater Drainage |  | Signed : | R.H | Signed : |  |  | Signed :
|  |  |  | Location: Cromwell Street |  | Date : | 2024-01-10 | Date : |  |  | Date :
Lot No: | 002 - |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date | COMMENTS FOR CONQA
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are using the correct and complete set of IFC Drawings. | IFC Drawings | Visual inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | Ensure all relevant project documentation has been submitted and approved by Superintendent including SMP, PMP, EMP, QMP, TMP and SEQ documentation. | SMP, PMP, EMP, QMP, TMP & SEQ | Visual Inspection | ITP Signed | HP | Site Engineer/ Superintendent |  |  | N/A |  | Request for Signature
1.3 | Purchase and delivery of pre-cast drainage components |  | Each Delivery | Precast materials to be used for construction have been inspected and are free from defects or damage. | VicRoads Standard Section 701.05 | Visual Inspection | ITP Signed | WP | Site Engineer | N/A |  | N/A
1.5 | Backfill material Classification |  | Prior to start | Approved compacted backfill within bedding zone to be 20mm Class 3 Fine Crushed Rock as nominated on the IFC Design Drawings | Dwg No. 2021-01 Sheet 1 | Verify | Test Reports from supplier | TP | Site Engineer | N/A |  | N/A
1.6 | Mortar material classification |  | Prior to start | Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause 610.32. | VicRoads Standard Section 701.09 (e) | Verify | Test Reports from supplier | TP | Site Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation. | Excavation permit | Verify | ITP Signed | IHP | Site Engineer | N/A |  | N/A
2.2 | Conformity with Drawings |  | Prior to Excavation | Prior to commencement of excavation for the pits and drainage lines the Contractor shall conﬁrm the position of all drainage components with the Superintendent. Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be: (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:200 | VicRoads Standard Section 701.09 | Visual Inspection | ITP Signed | HP | Site Engineer/ Superintendent |  |  | N/A |  | Request for Signature
2.3 | Excavation |  | Each Trench | For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm. | VicRoads Standard Section Table 701.151 | Visual Inspection | ITP Signed | HP | Site Engineer/ Superintendent |  |  | N/A |  | Request for Signature
2.4 | Compact base of trench |  | Each Trench | The base of the trench shall be compacted to refusal using mechanical plant. | VicRoads Standard Section 701.15 | Visual Inspection | ITP Signed | WP | Site Engineer | N/A |  | N/A
2.5 | Placement of Bedding Material |  | Each Trench | Bedding material shall be compacted to no less than the below thickness: - 100mm where D < 1500mm - 150mm where D > 1500mm where D is the nominal pipe diameter or culvert width. | Dwg No. SD-D8-1 Sheet 5 | Visual Inspection | ITP Signed | WP | Site Engineer | N/A |  | N/A
2.6 | Laying of Pipes |  | Each Line | Laying of pipes shall not commence until the Contractor has verified that pipe bedding complies with the lines and levels of the design drawings and that pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively. | VicRoads Standard Section 701.17 | Visual Inspection | ITP Signed | IHP | Site Engineer | N/A |  | N/A
2.7 | Jointing Pipe Sections |  | Each Line | Join pipes with rubber rings in accordance with manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled | VicRoads Standard Section 701.18 | Visual Inspection | ITP Signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.8 | Jointing to Pits |  | Each Pit | The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33. | VicRoads Standard Section 705.15 | Visual Inspection | ITP Signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.9 | Place & compact backfill material over pipes |  | Each Lot | Unless the pipe is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15. (i) Culvert Under Area not to be Paved The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level. (ii) Culvert under area not to be paved The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level. | VicRoads Standard Section 701.19 Dwg No. SD-D8-1 Sheet 5 | Visual Inspection | ITP Signed | IHP | Site Engineer / Site Foreman | N/A |  | N/A
2.1 | Place & compact backfill material around pits |  | Each Pit | Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment | VicRoads Standard Section 705.18 | Visual Inspection | ITP Signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.11 | Backfilling with 3% cement stabilised |  | Each Trench | Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised FCR with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water. | VicRoads Standard Section 701.19 (c) | Visual Inspection | ITP Signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.12 | Step Irons & Ladders |  | Each Pit | Drainage pits greater than 1.0 m deep shall be fitted with step irons or ladders in accordance with AS 1657 and this Section. | VicRoads Standard Section 705.12 | Visual Inspection | ITP Signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
2.13 | Construction Tolerances |  | Each Lot | The tolerances listed in Clause 610.47 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work. | VicRoads Standard Section 705.19 | Visual Inspection | ITP Signed | WP | Site Engineer / Site Foreman | N/A |  | N/A
3 | Testing & Completion
3.1 | Compaction and moisture content of backfill & bedding material |  | Each Lot | The Contractor shall test the bedding and backfill material at a frequency as shown in Table 701.291 to ensure that all materials comply with the specified requirements. | VicRoads Standard Section Table 701.291 | Verify | Test Reports | TP | Site Engineer | N/A |  | N/A
3.2 | CCTV inspection |  | Each Lot | Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia. | VicRoads Standard Section 701.3 | Visual inspection | CCTV Report | HP | Site Engineer/ Superintendent |  |  | N/A |  | Request for Signature
3.3 | Repairs |  | Each Lot | No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures. | VicRoads Standard Section 701.31 | Verify | ITP Signed | IP | Site Engineer/Superintendent | N/A |  | N/A |  | Request for Signature
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
IHP | Internal Hold Point | Work shall not proceed past the IHP until released by Fulton Hogan |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent