## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-003
[11 empty] | Revision : 2 | Date : 10/07/2024
Client: |  | Ballarat City Council |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Learmonth Street Road Widening & Associated Works |  | Subgrade Preperation |  | Name: | Rakib Hossain | Name: | Hugh Burns |  | Name:
Contract No: |  | Contract No. 2023/24-448 |  | Specifications: VicRoads Contract Specification VicRoads Standard Specification Section 204
|  |  |  | Structure / Component: Pavement |  | Signed : | R.H | Signed : |  |  | Signed :
|  |  |  | Location: Learmonth Street |  | Date : | 2024-01-10 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP | PSP, EMP, TMP, JSEA, SWMS, WP | Visual Inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | N/A |  | N/A
2 | Construction Works
2.1 | Survey Set-Out |  | Prior to commencement of excavation | Area has been set out in accordance with the drawings | Work Procedure | Verify | This ITP signed | IP | Site Engineer/ Surveyor | N/A |  | N/A
2.2 | Excavation Permit |  | Each lot | An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation | Excavation permit | Verify | This ITP Signed Off | HP* | Site Engineer / Site Supervisor | N/A |  | N/A
2.3 | Subgrade Material Properties |  | Each Lot | In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%. If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B. | Cl 204.06e | Test Point | Test Reports | TP | Site Engineer / Site Supervisor | N/A |  | N/A
2.4 | Inspection of Subgrade Material |  | Each lot | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04 | Cl 204.06c | Verify | This ITP Signed Off | HP | Site Engineer / Site Supervisor / Superintendent |  |  | N/A
2.5 | Material classified as silt |  | Prior to Commencing | Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent | VicRoads Spec. Cl. 204.04(b) | Document Review | Superintendent satisfied with Stabilisation Signed ITP/ records | HP | Site Engineer / Site Supervisor / Superintendent |  |  | N/A
2.6 | Acceptance of Rock Subgrade (when applicable) |  | Prior construction of the regulating layer | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review. | VicRoads Spec. Cl. 204.06(f) | Site Inspection/ Document Review | Superintendent acceptance Signed ITP | HP | Site Engineer / Site Supervisor / Superintendent |  |  | N/A
2.7 | Unsuitable Material |  | Each Lot | Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review. - As per RFQ Section 200, Clause 200.3, the unsuitable material shall be jointly inspected by the Superintendent to determine the extent of the rehabilitation required. - Backfill of excavated area shall be with Type A material. | 204.07(d) RFQ Section 200, Cl 200.3 | Visual Inspection | This ITP Signed Off | HP | Site Engineer / Site Supervisor / Superintendent |  |  | N/A
2.8 | Groundwater |  | Each Lot | Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater | 204.06 (h) | Visual inspection | This ITP signed off | HP | Site Engineer/ Superintendent |  |  | N/A
2.9 | Subgrade Level and Shape |  |  | Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2. Scale B Measurements per lot = 40 Surface level tolerances: Range x = +5, -25mm Standard Deviation = 15mm | 204.03(g) Table 204.031 | Survey | This ITP signed off; Survey Report | SCP | Site Engineer / Surveyor | N/A |  | N/A
3 | Testing
3.1 | Proof Rolling |  | Each Lot | Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification | Section 173 | Visual Inspection | This ITP signed off | HP* WP | Site Engineer / Site Supervisor / Superintendent |  |  | N/A |  | Signature Required
3.2 | Compaction Testing |  | Each Lot | Scale B All Type A Material = minimum mean value of density ratio = 98% Ripped and re-compacted material below Cut Floor Level = minimum mean value of density ratio = 98% | Table 204.131 | Test Point | Test Records Lot Register | TP | Site Engineer | N/A |  | N/A |  | Signature Required
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.