## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-009
[11 empty] | Revision : 2 | 2024-02-22
Client: |  | City of Ballarat |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Learmonth Street Road Widening & Associated Works |  | Spray Seal |  | Name: | Rakib Hossain | Name: | Hugh Burns |  | Name: | Andrew Cotter
Contract No: |  | Contact No: 2023/24 - 448 |  | Specifications: VicRoads Technical Specification 408 January 2018, Section 310, RFQ
|  |  |  | Structure / Component: Bituminous Surfacing |  | Signed : | R.H. | Signed : | H.B. |  | Signed :
|  |  |  | Location: Learmonth St |  | Date : | 2024-02-22 | Date : | 2024-02-22 |  | Date : | 2024-02-25
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Materials
1.1 | Bitumen |  | Test cert upon request | AS (Section 175) for residual bitumen for pavements | 408.08 (a) | Verify | ITP Signed Off | IP | Lab Manager | N/A |  | N/A
1.2 | Bitumen Emulsion |  | Test cert upon request | ARS or CRS comply with AS (Section 175) – Bitumen emulsions for the construction and maintenance of pavements | 408.08 (b) | Verify | This ITP Sign off | IP | Lab Manager | N/A |  | N/A
1.3 | PMB |  | Test cert upon request | • Austroads Specification Framework for Polymer Modified Binders and Multigrade Bitumen’s (AGPT/T190 - section 175) & table 408.161. Alternative PMB'S shall not be used without approval by Superintendent. Evidence of satisfactory field performance for 3 years required. • (i) HSS - S10e,S35e,10Pts CR, or alternative approved by superintendent • Field Produced CR - >5pts by mass of binder, Carrier oil <4Pts by volume of binder • (ii)SAM - S45R,S20e,18Pts CR or alternative as approved by the superintendent • Field Produced CR - >18pts by mass of binder, Carrier oil <4Pts by volume of binder • (iii)SAMI - S25e,20PtsCR or alternative as approved by the superintendent • Field Produced CR - >20pts by mass of binder, Carrier oil <4Pts by volume of binder • XSS treatments – Class S20E,S45R or S15RF or alternative as approved by the Superintendent. XSS treatments are applied as a double/double application and the same binder shall be used for both applications. | 408.08 (d) | Verify | ITP Signed Off | IP | Lab Manager | N/A |  | N/A | Request Signoff
1.4 | Primer |  | Test cert upon request | Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics. | 408.08 (e) | Verify | ITP Signed Off | IP | Lab Manager | N/A |  | N/A
2 | Aggregate
2.1 | Aggregate Specification |  | Maximum lot size 350t of same class and size | VicRoads Standard Specification Sections: 801 - Source Rock, 831 - Aggregate & 832 - Sands | 408.11 (a) | Verify | ITP Signed Off | HP* | Lab Manager | N/A |  | N/A
2.2 | Precoating |  | All works carried out | Supply plant precoated aggregate from supplier or field precoated aggregate from stacksite. Aggregate shall be uniformly precoated to the satisfaction of the Superintendent. | 408.11 (b) | Verify | ITP Signed Off | IP | Supervisor | N/A |  | N/A
2.3 | Removal of loose aggregate |  | All works carried out | All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent. NB: For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after. | 408.14 | Verify | ITP Signed Off | IP | Supervisor | N/A |  | N/A
2.4 | Stack Site |  | Prior to commencing works | Stack sites to be approved by Superintendent. Stack site to be at Kent Street where road is closed. | 408.12 | Verify | ITP Signed Off | IP | Supervisor | N/A |  | N/A
3 | Operation
3.1 | Rates of Application |  | All works carried out | In accordance with the current Update of the Austroads Sprayed Seal Design Method (Section 175) rates of application - residual binder at 15 C Traffic Data and default rates -Table 3040.066 (Traffic Volumes) 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent. | 408.15 (a) | Verify | ITP Signed Off | HP | Site/Project Engineer |  |  | N/A
3.2 | Surface Pre-treatment |  | All works carried out | Refer Table 408.171, 408.132, 408.133 | 408.13 (b) | Verify | ITP Signed Off | IP | Supervisor | N/A |  | N/A
3.3 | Calibration of Bitumen Sprayer |  | Prior to commencing works | Calibration Certificate to be provided | 408.07 | Verify | ITP Signed Off | WP | Supervisor | N/A |  | N/A
3.4 | Commencement of works |  | Prior to commencing works | NB: Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing. This includes a review of the material and evidence that the pavement passes compaction testing to Superintendents approval. Primersealing shall not be carried out within 12 hours of forecast rain. | 408.04 | Verify | ITP Signed Off QD2190370 Sealing Checklist | HP | Site/Project Engineer/ Supervisor / Superintendent |  |  | N/A | Request Signoff
3.5 | Records |  | Each Lot | Job completed within spec requirements. Job completion report ,i.e. Spray Sheets to be submitted within 7 days of completion of sealing works | 408.17 | Verify | ITP Signed Off Spray Sheets Section 408 Attachment A | WP | Site/Project Engineer | N/A |  | N/A
3.6 | Acceptance of work- Binder rates |  | Each Lot | Actual vs design rates. Variation between actual & design assessed by Table 408.121 ie. Variation from the Design Rates of Application for Bituminous Material < 0.1 l/m² below the design rate of application | 408.15 (a) | Verify | ITP Signed Off | IP | Site/Project Engineer | N/A |  | N/A
3.7 | Acceptance of work- Surface Texture |  | Each Lot | Acceptance - visual assessment or (where required) as per Table 408.122 ie. 7mm Primerseal Mean Texture Depth between 1.0mm to 2.0mm | 408.15 (b) | Verify | ITP Signed Off | IP | Site/Project Engineer | N/A |  | N/A
3.8 | Acceptance of work- Aggregate retention |  | Each Lot | Acceptance -visual assessment or (where required) as per Table 408.123 Degree of Aggregate Stripping is 0 - 2 | 408.15 (c) | Verify | ITP Signed Off | IP | Site/Project Engineer | N/A |  | N/A
3.09 | Acceptance of work- Visual Uniformity |  | Each Lot | Provide a surface with uniform colour, texture and consistent appearance | 408.15 (d) | Verify | ITP Signed Off | IP | Site/Project Engineer | N/A |  | N/A
3.1 | Maintenance of seals |  | All works carried out | The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period. The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work. | 408.16 | Verify | ITP Signed Off | HP | Site/Project Engineer Superintendent |  |  | N/A | Request Signoff
3.11 | Maintenance of seals |  | All works carried out | Where the treatment for protection or repair of a seal involves the application of a further seal coat, the Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work. | 408.16 | Verify | ITP Signed Off | HP | Site/Project Engineer |  |  | N/A
3.12 | Defects Liability Period |  | All works carried out | All defects should be rectified six months prior to the conclusion of the Defects liability period. As stated in 408.15 The Contractor shall carry out at least two inspections of each job during the Defects Liability Period and provide a condition report to the Superintendent. The condition report shall detail the condition of the seal, any defects and the proposed corrective action. | 408.18 | Verify | ITP Signed off | WP | Site/Project Engineer | N/A |  | N/A
3.13 | Dryback |  | Each Lot | Scale B Pavement Dryback and Embedment - 6 randomly selected test sites per lot required - If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required - If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm - Testing shall be undertaken no more than 24 hours before primersealing. - Testing schedule in accordance with 310.03 (c) and QD2190370 Sealing Checklist | 310.03(a) 310.03(b) Table 310.031 310.03(c) Table 310.032 | Verify | ITP Signed off | TP | Site/Project Engineer/ Supervisor | N/A |  | N/A
3.14 | Ride Quality |  | Each Lot | Ride quality measurement shall be undertaken within 3 months of the completion of primerseal and prior to practical completion being awarded by the Superintendent. The finished surface of the Primersealed pavement shall have a smooth longitudinal profile and comply with the minimum ride qaulity requirements of Scale C road as specified in Table 180.092. - Maximum Individual Lane Roughness Value for any 100 m Subsection = 2.70 m/km/lane - Maximum Mean Lane Roughness Value for Lot = 2.00 n/km/lane - Maximum length of lot is 2km of continuous traffic lane | 180.04 180.092 | Verify | ITP Signed off | TP | Site/Project Engineer/ Supervisor | N/A |  | N/A
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent