## Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-002 - Earthworks | itp | ITP-002 - Earthworks |  | a1c13c96-9540-4df8-af90-a6a42142b510
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
63ef06e4-2920-5a35-b5b9-535fc9e300ba | note | FREQUENCY: Prior to commencing any activity
975a3e51-9557-5498-a0e6-f409be88ad10 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
613e7170-9728-5570-9c31-94beb88c7c44 | note | – using the correct and complete set of drawings
8feb9044-c864-5b37-9c61-519e64230102 | note | – all drawings are the latest revision
7ef1083c-e883-5714-9b92-dd73a27abd47 | note | REFERENCE DOCUMENTS: IFC Drawings
c62d4720-bd30-52d5-8674-bf431547ccff | note | METHOD: Visual Inspection
661abbd6-eca8-532e-a3ff-1a64e77beb1b | note | RECORD: Signed ITP
9a9af3b3-4708-566d-a616-369ced59562c | note | IHP
72fb4da4-635e-5a66-ab2f-552827b9e2ba | note | RESPONSIBILITY: SWA Project Manager
51e49a8c-5445-526e-984b-423795089fd5 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
07d8c898-2208-523a-80f7-1387c0f63df8 | note | FREQUENCY: Prior to commencing any activity
0751365c-1d20-5c53-b1bb-3b51d00d3665 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a8f70dba-46e3-5a26-95d6-26e96fae383e | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
1352caef-d602-554b-a7da-1423cabffbbb | note | METHOD: Visual Inspection
a0b75b41-f0dd-5860-96b6-6da3307d8ce6 | note | RECORD: Signed ITP
b53b50a3-f195-5159-859f-bc717daeffdb | note | IHP
06ed450d-b079-5465-9db2-0846a76be876 | note | RESPONSIBILITY: SWA Project Manager
7c543fa3-0593-5ec2-863a-f310fc8ca8f9 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
046dd51c-0175-5459-a6c5-f55a289e5f9f | note | FREQUENCY: Prior to commencement of excavation.
59adf8ec-c302-58b0-9358-84cc178503e2 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
f4ef093d-e2c1-520a-bcb4-4f73075c4346 | note | REFERENCE DOCUMENTS: Work Procedure
6cb1adab-fa85-5394-b96a-55d7a6d14d84 | note | METHOD: Verify
f4f4540d-46e7-5141-aded-2d93b7455cf6 | note | RECORD: Signed ITP
8ef72872-7802-5f59-bf65-b457024a33ac | note | IP
4357050c-8bee-5b9c-851a-a546b7d3e05b | note | RESPONSIBILITY: SWA Project Manager
4f7fa3db-aedc-5e1b-aadc-9eee1d7a7f47 | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
b66700e3-f3fb-5637-82da-e55576bdf4b2 | note | FREQUENCY: Each Lot
19e84c8b-81ad-5fc9-9c1c-2cf7de12c162 | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
ce7a9b89-7a27-5c68-9149-9254a6ab0e3c | note | REFERENCE DOCUMENTS: Excavation Permit
1fcaa11d-5c25-529c-bc7a-fb66f002513e | note | METHOD: Verify
b940a2cc-622a-5268-b6d5-4174d5bfe926 | note | RECORD: Signed ITP
8d23f1bc-479e-5750-b0a8-4dc379f2e99d | note | IHP/IP
19cde785-dfd3-5089-a243-0103582f7314 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
329413a2-cceb-5639-8216-500c4af30ad1 | date | Date Completed:
| checkpoint | 2.3 - Sub grade Material Properties
5fd83012-c466-593d-9c1a-748bded75184 | note | FREQUENCY: Each Lot
afe4b2e2-ed25-5b1b-9af5-d1e138adac8a | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut ﬂoor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
a1ffa119-4d34-5673-9c44-9dc6ea662460 | note | ○ If parameter met, rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
ad5e0754-0df5-5c5e-abad-2aae1ada4c77 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
8ae13c3c-13ac-50c2-8189-e50b75a74f02 | note | METHOD: Site Inspection/Test Report
6d2aaaa3-68de-5559-b12a-b31c9741aade | note | RECORD: Signed ITP & Test Report
07fd6496-84d5-54b1-b081-eab94ff926ce | note | TP/AP
10ab7e0c-4532-54d5-a31a-e33a6cd96b1d | note | RESPONSIBILITY: SWA Project Manager/External testing Company representative/RRV Superintendent
3e8552c4-a105-5534-846a-e1af640e3f76 | date | Date Completed:
| checkpoint | 2.4 - Inspection of Subgrade Material
fc2ff622-f8b0-5225-9a20-3b3fb6fdc287 | note | FREQUENCY: Each Lot
13024377-9a3c-5b23-84e9-ad46c0eb0d37 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to veriﬁcation by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
d2cc98f5-f540-50ae-8a5e-e3e548ef5835 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.06 (e)
0db4cef1-508a-5807-bef9-04f66542a0d3 | note | METHOD: Visual Inspection
76a001cd-1c60-595d-81ea-30fe6d7c513e | note | RECORD: Signed ITP
5b5cb03e-be09-5c3e-ae18-32be5d6e95ec | note | IHP/AP
c06704ae-32fe-5fa2-9cb1-3c0294866db3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
d3926330-b65c-5374-aab5-5164629eeec9 | date | Date Completed:
| checkpoint | 2.5 - Material Classiﬁed as Silt
43018c9f-362c-57f1-a789-d614010c526d | note | FREQUENCY: Prior to commencing
762a0a86-0d34-5b1d-abfa-fa16440eb526 | note | ACCEPTANCE CRITERIA: Material classiﬁed as silt, either before or after compaction, is not acceptable as Type A material without stabilisation to the satisfaction of the Superintendent.
56b42410-7b7a-50f6-b7d5-89d80bb5a441 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (e)
68b0c69e-dc73-5f91-a426-5d5e86656bb2 | note | METHOD: Visual Inspection
5e98c672-e09a-5ac8-982a-016dbe24374d | note | RECORD: Signed ITP
cf5098b9-e705-5cac-a813-266e60de3dc5 | note | IHP/AP
b907f15a-9cc7-564b-8b66-da57e9316eb3 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
a0191669-b753-5b5a-a7a3-8c73f82bad58 | date | Date Completed:
| checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
cb481af3-2357-5cbf-ad97-bc04aed2500c | note | FREQUENCY: Prior construction of the regulating layer.
51f0b093-c186-5f27-a8c3-ccabdfbfd53c | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
8ad4bf0a-5290-51af-a3e5-ee684a223608 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
61cb11b6-7c28-56b9-8dc8-cf645c711174 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.04 (f)
14a6497b-1d6f-5818-8481-9bf14cba7709 | note | METHOD: Site Inspection/ Document Review
d35e44fd-e587-5be6-a24f-718975f149ec | note | RECORD: Signed ITP
49338d4e-2a96-5325-800c-ad111c64dd75 | note | IHP/AP
12cb7c2b-36df-5553-ba6f-24e68e0207a8 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
2b1425cc-b454-5d77-98dd-96bd3b7aa072 | date | Date Completed:
| checkpoint | 2.7 - Unsuitable Material
db94795f-3834-5c1c-91f3-9fc4301600ab | note | FREQUENCY: Each lot as required
702af76c-3a00-56f1-9fd7-7ccc840360ca | note | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review
1b3e2ac5-48c1-5654-bd54-7761b3098b42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (d)
36c5022f-b720-5452-8061-86025516a283 | note | METHOD: Visual Inspection
244ed7f3-e86b-5bac-9517-ea83524d8369 | note | RECORD: Signed ITP & Test Reports
f80bc235-fc80-596b-85fd-e33c182b9bd7 | note | IHP/AP/TP
f10559a8-06b7-5b31-8da5-5968ae7501a7 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
56094748-985f-5079-8f95-88fb28e47e3f | date | Date Completed:
| checkpoint | 2.8 - Groundwater
8e947778-8b84-5100-89f5-2f3fd0129bdf | note | FREQUENCY: Each lot as required
7673e185-bc79-53b7-bcb2-29c2e8a77f19 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
516134ef-d6bb-59c1-8b17-ab08d4c1f88c | note | REFERENCE DOCUMENTS: VcRoads Std Specs 204.07 (h)
d1271fbf-7904-518b-b1e7-07dbd73a020f | note | METHOD: Visual Inspection
5ea962a4-e35d-5646-9f69-39256bf464cd | note | RECORD: Signed ITP & Test Reports
3692b2d5-c7e4-55f3-90a5-cbebc233d986 | note | IHP/AP
cc609a62-4df2-51a4-b6b1-bc840724da7e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
9e689064-6953-575d-8309-6c093fb7d00c | date | Date Completed:
| checkpoint | 2.9 - Trimming and level conformity
61509124-0ebf-5b78-8745-f05a38c4eab4 | note | FREQUENCY: Each lot as required
a17b198b-f0c1-55dd-8a4a-d54afc2b9c1c | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
0d7a5745-75d9-57e4-9081-7b79048b2506 | note | ○ Level tolerances: Range x (Mean value of all measurements) (Scale A) x = +5, -25mm (Scale B )x = +5, -15mm
ad920ce8-f8b7-53b3-8743-60328344a9de | note | ○ Max S (Standard deviation of all readings) (Scale A) = 12 mm (Scale B) = 15 mm
5e252ff1-5950-54c6-bf76-db5a1f002010 | note | ○ No. measurements (Scale A) 80 per lot (Scale B) 40 per lot
87493cb0-d115-51c4-9d1f-759d71102d10 | note | REFERENCE DOCUMENTS: VcRoads Std 204.03 (f,g,h) Table 204.031
d04f4af3-fe8c-5e49-bcac-93f66a7ec19d | note | METHOD: Survey
311b327e-4037-5495-95d9-fdd693c1be25 | note | RECORD: Signed ITP & Survey Report
1018ec42-1b82-5abf-96e9-81d3440f82b4 | note | SCP
92e60c36-bee9-5e0c-8f85-d4a9bc691cf3 | note | RESPONSIBILITY: SWA Project Manager/External Surveyor
3b911a52-4913-54fd-8ba4-e6fcbb275574 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Test Rolling
d3a1bc80-faee-5112-bc75-bec68db18977 | note | FREQUENCY: Each lot as required
4e918e84-6387-53fd-91c4-0ca52044fde4 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep. ( Cl 173) Plant to comply with requirements of Cl 173.03.
5aaa4854-fe7e-5cad-b4e1-74d41e8f3994 | note | ○ Pneumatic tyred plant nominated for test rolling procedures shall have a mass of not less than 20 tonne and shall have a ground contact pressure under either the front or rear wheels of not less than 450 kPa per tyre.
4277ddd7-f14f-588f-b3b9-ea39086bd6ec | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Section173.03 173.03 (ii)
6ba8ef5c-35b4-5365-a45f-95d31a5cef58 | note | METHOD: Visual Inspection
1a0d1f68-b539-5451-b907-0976dddbb2e2 | note | RECORD: Signed ITP
9b6dc80f-3f74-52a8-8bd4-abfbdd979797 | note | IHP/WP
9ead8112-2025-5ed7-be9d-429f573ab070 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
b2ea547c-739f-5d7f-aa8f-212f732da151 | date | Date Completed:
| checkpoint | 3.2 - Compaction Testing
f6a27ea9-f413-5e1c-9775-326bd9c2ee19 | note | FREQUENCY: Each lot as required
cb715b59-c134-524b-89fc-b956d96a3462 | note | ACCEPTANCE CRITERIA: Ripped and re- compacted material below Cut Floor Level = minimum compaction 98%.
e62dc0ef-1dae-5206-971f-c837806fad71 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 98%.
5d92ffe2-2202-5931-b8a7-a03620b229c9 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where ﬁll is to be constructed = minimum compaction 95%.
ce30c178-8296-5470-93d3-337682e65b40 | note | REFERENCE DOCUMENTS: Vicroads Speciﬁcatio n Table 204.131
8cc9c55b-be60-5c5c-a496-fe978d289bd0 | note | METHOD: Compaction Test
1e3b7c0a-b2a1-539a-bacd-7cfd0f0697dc | note | RECORD: Signed ITP & Test Reports
56699200-6334-5d20-84a4-70d33c6231aa | note | IHP/AP/TP
a0e93b15-f5af-5c9a-8e7c-cf39d73bfe28 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representative
bfd3e807-29e4-5f56-ae7a-2ce38924e07a | date | Date Completed:
| checkpoint | Final Inspection
dcd25591-fde7-5bcd-a09b-d3e6d47d71ec | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
16a05b1a-935d-5290-8681-c77a6eab76c0 | textbox | Print Name:
64743c84-a5c9-5c74-99f1-e395de6b42c8 | textbox | Position:
49bd4889-f620-5147-a465-3d6c08b91f49 | date | Date:
| signoff | Sign ITP
| checklist | ITP-002 (A) - Underground Stormwater Drainage Lot 3 RCP | itp | ITP-002 (A) - Underground Stormwater Drainage Lot 3 RCP |  | a2c412b1-1b92-4137-9c55-2867fd30591d
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
51dd7dd8-a85b-5dcb-930d-d47b7bcf3dc7 | note | FREQUENCY: Prior to commencing any activity
647187f0-df7c-5133-b0fa-126e14ca6e8a | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
bb2da068-7ec5-5bc5-89bf-faed538dded6 | note | – using the correct and complete set of drawings
fdb3779e-92b1-5ac4-8462-c1bb762098ed | note | – all drawings are the latest revision
5aa53c63-657a-583d-b58b-a2b65d47b08f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
b537804b-581f-5260-8c68-1e82944c591a | note | INSPECTION/TEST METHOD: Visual inspection
7a2e76cc-fad1-52c7-a14d-90382d9bd17a | note | RECORD OF CONFORMITY: This ITP signed off
63228717-fb8b-5554-a8aa-e2597da534de | note | HP*
6dc690f7-ab97-5f6a-aa9a-7862ee8f48a8 | note | RESPONSIBILITY: Project Engineer / Site Foreman
b65cb122-5489-55e5-9885-be5958fc2dde | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
eb2f6625-e136-5619-b330-6f544e794673 | note | FREQUENCY: Prior to commencing any activity
dd493c3e-a0b7-54f6-b400-6f8ccaea5f87 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
696d12af-75c7-5607-9bb7-bfb3211c8300 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
8429b2c7-2da3-5278-b154-3d053fe63bd9 | note | INSPECTION/TEST METHOD: Visual Inspection
69c34374-47d5-5012-b692-6c9a9753be1d | note | RECORD OF CONFORMITY: This ITP signed off
babf7026-2eb0-515b-a715-d8fb4fa25195 | note | HP*
b44898b7-871e-546d-aca4-3d435bce7d67 | note | RESPONSIBILITY: Project Engineer / Site Foreman
a8c32997-569e-5f93-b068-56b9164962cb | date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
bc1a35da-4c9f-50f4-8840-e01a526573c4 | note | FREQUENCY: Each Delivery
4c516718-0341-57ba-bc66-0545cfa098b1 | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
a4e767ff-eade-552f-8d12-eb912c8d21a5 | note | REFERENCE DOCUMENTS: 701.04b
2adfafff-6ce0-5868-88be-45bdfa380dc4 | note | INSPECTION/TEST METHOD: Visual Inspection
ff1f6612-dffc-50e0-b78b-04cf6daf553c | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
fdae507a-3431-59c2-a68d-20fb7cbafd13 | note | IP
b235f91b-a775-5bb9-b49c-7961c6f8d096 | note | RESPONSIBILITY: Project Engineer
fca82648-e528-5142-9a5d-5809e2d99a7b | date | Date Completed:
| checkpoint | 1.4 - Precast Pipe Compliance
e7b47848-6669-5341-a8ca-266e963d2462 | note | FREQUENCY: Prior to Commencing
b8590370-7856-5cc6-bb34-3662fa84ec45 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
9130df19-1c2d-52ab-9777-2fbfc18deaf8 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
5a10cce7-7070-5c92-8de4-952dd89ce02b | note | REFERENCE DOCUMENTS: VicRoads Spec.
16fed828-0fbb-5f35-b5db-a418bd171e54 | note | ○ Cl.619
f0b1482f-b37c-5bff-9492-d3c8f65ce5c1 | note | ○ Cl. 701.04(a)
b4eb7851-c32d-54d2-8e28-7445b55932bb | note | ○ Cl. 701.04(b)(i)
f8b20b36-33a4-59b2-9321-281e2e14f5f1 | note | ○ Cl. 705.04(d)
dc5e1e60-f705-5bc4-8bc0-0304184e5e3c | note | ○ Cl. 705.11
ba43bacf-d216-5458-8351-dbb55b047c70 | note | ○ AS4058
dec2a97e-3f85-5037-a684-f72388ff0594 | note | ○ AS4680
e0428424-8bb9-5a99-b518-914abe9ec8bb | note | INSPECTION/TEST METHOD: Document review & Site inspection
793e5c72-801b-5e2b-8dd9-93dd16ce6f82 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer certificate or accreditation
974799ca-28f7-5b13-924e-387fbe42777a | note | IP
57641dc8-1ef3-518b-b5d5-cc7501d7ca7d | note | RESPONSIBILITY: Project Engineer
878ec9fd-05b2-5c08-aa8d-058d6c20b68b | date | Date Completed:
| checkpoint | 1.5 - Bedding material classification
c5487be8-d5fa-5894-9046-49282dc30452 | note | FREQUENCY: Prior to start
59c61435-04f8-5ded-9d7d-79d2e403567d | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
5e90943c-dea3-5df5-971f-a6967c7e8501 | note | ○ 100% passing 19mm sieve.
5461efc5-7ad7-5047-8fbe-69a645772c86 | note | ○ 5%-40% passing 0.075mm.
6482f448-6f7f-55de-b53c-57e0e0c05686 | note | ○ PI = 20 max.
ff512a95-4083-58d0-a814-11a8ab6a8105 | note | REFERENCE DOCUMENTS: 701.04e
8d31d7ce-617a-590f-b701-3c6ecfb78498 | note | ○ Table 701.041
700e1b72-b363-50a8-ba1b-8140ad1d1b07 | note | ○ Table 701.042
12039800-e7f1-5fab-8a8e-eb09e9191026 | note | ○ Table 701.231
e8bb1dd6-5e00-592f-9160-5ec76bdbaf09 | note | INSPECTION/TEST METHOD: Verify
1cf5dd1c-08b1-559b-8b71-fbb389512572 | note | RECORD OF CONFORMITY: Test Reports from supplier
c940ec90-d630-512f-91d1-ef54ef8d1e41 | note | TP
3b4217e3-ed69-5893-9374-6c5e20e98f02 | note | RESPONSIBILITY: Project Engineer
2a0fd6a2-5474-5497-8c83-a955fd3775d0 | date | Date Completed:
| checkpoint | 1.6 - Backfill material Classification
5d4850ac-45b4-5de7-8040-92bd69470a20 | note | FREQUENCY: Prior to start
b2c522f9-cfed-52fb-89b9-49573554d3a9 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
bccf0df8-fb6e-578e-bed4-381a23cf5b20 | note | ○ 100% passing 37.5mm sieve.
e034d0f8-995d-56b9-9bd8-1613e409db44 | note | ○ 5%-40% passing 0.075mm sieve.
77b07898-b820-5957-88e6-1da0df3adc5b | note | ○ PI = 20 max.
2542dff4-cb80-5578-9b82-55c0c9af2de4 | note | REFERENCE DOCUMENTS: 701.04e
1e1db4b1-2d1a-5237-a06a-f26851c13e3c | note | ○ Table 701.041
32879f8d-592a-5e2c-8973-3176b346d258 | note | ○ Table 701.042
f11e6678-30f9-5a34-ad3e-0ee75e0abd98 | note | ○ Table 701.231
616da38b-daa1-5b1e-8b91-65387afdba11 | note | INSPECTION/TEST METHOD: Verify
022c2e0a-7a72-5a65-a8ae-8be1bc752329 | note | RECORD OF CONFORMITY: Test Reports from supplier
eb5081ee-e881-5dc1-b3a5-94631c090519 | note | TP
bfa8d99b-db6b-5111-a456-a8e35e41ac7f | note | RESPONSIBILITY: Project Engineer
de67168d-b53d-5759-a7e0-79a1ac34ea6f | date | Date Completed:
| checkpoint | 1.7 - Mortar material classification
a6f54a7b-4283-5fff-b53d-8691f4da0302 | note | FREQUENCY: Prior to start
a6d7ba2a-2ba6-5ebd-b9ac-a0ffc6ba7487 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
0b092c1e-10d2-5517-8f0a-32108d6a69ff | note | REFERENCE DOCUMENTS: 610.33
96ee10f4-ff15-57a3-9d97-1ab81e86c993 | note | INSPECTION/TEST METHOD: Verify
65205e7c-160d-55e7-ac39-51de7951d71c | note | RECORD OF CONFORMITY: Test Reports from supplier
52738b50-a354-523b-831f-939e5e9390f4 | note | TP
90973117-13e8-55a5-8477-03831f15131a | note | RESPONSIBILITY: Project Engineer
02804a7a-a73c-5011-8f6e-f9f3f7a2e28c | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
04df0066-1eac-53ba-aa7f-015931f6ed8b | note | FREQUENCY: Each lot
70ff5de1-9317-5032-90a2-6f89317b8015 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
402c3174-d262-5b1b-a9fe-4ef107497d75 | note | ○ Plant and equipment shall be appropriate for the task.
3fd380b6-c7cb-5049-a67d-0e4a2ce33adb | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
f40991a1-2b82-5201-82c4-e7fd780a9eff | note | REFERENCE DOCUMENTS: Excavation permit
300fd368-7403-5945-95e9-e5454dd3efb5 | note | INSPECTION/TEST METHOD: Verify
fd4f5cf7-bbbe-5804-88f0-fdfb3891c573 | note | RECORD OF CONFORMITY: ITP Signed
af1ca4a9-3447-50cb-8113-5a771c51ca36 | note | HP*
e1ee6330-886f-5e4a-b86c-6afe5264a6d3 | note | RESPONSIBILITY: Project Engineer
c82c69c0-b1c1-52a3-8e3c-9ab06e0038e5 | date | Date Completed:
| checkpoint | 2.2 - Set out drainage
d5799d37-2189-58e2-8581-3c6d14d4b4aa | note | FREQUENCY: Prior to excavation
37fdc80f-dd26-5a4f-b7fe-99c7380ec813 | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
8aff16c1-f124-50aa-ad0d-238a019684e0 | note | REFERENCE DOCUMENTS: Drawings 701.10
ef688ba4-399d-551b-b5a8-3e5de56e1f2b | note | INSPECTION/TEST METHOD: Visual Inspection
0248bf61-a73c-5842-abeb-a5f279f74636 | note | RECORD OF CONFORMITY: ITP Signed
aa3d89f4-a41d-5cc1-867c-afe1b4e509e6 | note | HP
1b53b6a2-3d19-5f3d-8237-bf8dfd3c4090 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
780e31bb-e5e0-5f68-8153-04e7e8e6ad8a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
8526c1d9-1ca1-55f5-ba57-4cd0bf28f721 | note | FREQUENCY: Each Trench
98c556a0-07b8-5d25-ad80-bbbd46c18cd7 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts.
3cadef87-3757-5e78-a6bf-742df5cb5d81 | note | ○ Trench walls to be vertical where practical
fc7983ba-9d62-5b94-b87b-cf602907204b | note | Depth of trench:
b73463ad-6c2d-5715-be9d-6419991db85f | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
b043572d-1ae7-577c-9c4b-c6193760cc8f | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
eba985a5-eb3b-582d-ad35-9fbb7aad7545 | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
b0a0f03a-70c7-5455-a4ea-76cc633a75ea | note | INSPECTION/TEST METHOD: Visual Inspection
52ab706b-17ca-5477-9d10-c1e324b53876 | note | RECORD OF CONFORMITY: ITP Signed
56da03af-067a-5e59-8e9a-e1686767b62a | note | IP
edaddeec-a775-5eec-b5e9-73dfd5e31254 | note | RESPONSIBILITY: Site Foreman
ee52a18a-60f1-5bc6-a467-6c5fa0994575 | date | Date Completed:
| checkpoint | 2.4 - Compact base of trench
e6f3e84e-3d6b-5d17-ad64-5499c2570b5f | note | FREQUENCY: Each Trench
73864c2c-89ee-58a6-9be5-598daf6654c3 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
081085c5-414b-59f5-a628-0f8b37fe21e8 | note | REFERENCE DOCUMENTS: 701.1
8ed2d509-3edc-562f-a25b-36f82212ab06 | note | INSPECTION/TEST METHOD: Visual Inspection
ee88992b-5f63-50b8-859d-a106e89a6a94 | note | RECORD OF CONFORMITY: ITP Signed
06a6e5dd-1732-5e0c-b23c-89a12e2667df | note | IP
b16020dd-7760-578e-b7cf-6e09b83eaef8 | note | RESPONSIBILITY: Project Engineer
9ba825e7-8599-5f2c-b1fb-b3ff7fffef44 | date | Date Completed:
| checkpoint | 2.5 - Place bedding material & compact
07b665e8-e7f9-54da-b761-f0b9fa19706c | note | FREQUENCY: Each Trench
1d0351cc-a646-59f9-85ab-22e7ec378af3 | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
c1682c86-e994-56b2-a1f7-6c34940210fe | note | ○ 100mm under pipes.
e7d7fc59-cbb7-5470-a749-7824d5dcd2b0 | note | ○ 80mm (earth foundation)
249ba5d0-d29e-5521-a7a1-29690d7f8a6a | note | ○ 150mm (rock foundation)
bd13e006-a2da-5753-810b-0e6f900efec9 | note | REFERENCE DOCUMENTS: 701.19
a515cc3a-4ad6-51be-bf41-c82e23dfc922 | note | INSPECTION/TEST METHOD: Visual Inspection
6eb6d214-2a7e-510b-bb23-191a608d246a | note | RECORD OF CONFORMITY: ITP Signed
e785b63b-37a8-5105-91cd-455e6550bcea | note | IP
ac6538c1-21d5-5fe8-9533-b6bd79f618d8 | note | RESPONSIBILITY: Project Engineer
d69081fc-7541-5aab-9055-799f1fd163db | date | Date Completed:
| checkpoint | 2.6 - Place pipes
d6b24f5c-6484-554e-99df-97d83fd40d9b | note | FREQUENCY: Each Line/Pit
bda84fcd-9e81-55c4-8f44-0c1f55d4d755 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
93767ec2-0c80-5fe0-8e18-8d7520d409b3 | note | REFERENCE DOCUMENTS: Drawings 701.17
0ce41cdd-17c9-5410-b3ae-108f6eaafa3d | note | INSPECTION/TEST METHOD: Visual Inspection
55cfa323-fb05-581d-8857-1cb020a1863c | note | RECORD OF CONFORMITY: ITP Signed
22e15843-e037-5916-b67f-e225253a4531 | note | IP
bcb400af-caf1-580e-b931-f71b72b149db | note | RESPONSIBILITY: Project Engineer / Site Foreman
1a7ee792-fb51-58b1-8621-e09838041b5e | date | Date Completed:
| checkpoint | 2.7 - Jointing pipe sections
d137342d-77f7-58fb-aac5-fcd6cca4352d | note | FREQUENCY: Each Line
8238c2cc-4b9e-5fd7-a864-8d0768cc9912 | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
d42705e3-6b7b-5667-bee1-75ce77a66e61 | note | REFERENCE DOCUMENTS: 701.18
26b97741-dbe5-57eb-87eb-0e8c809c3424 | note | INSPECTION/TEST METHOD: Visual Inspection
2a9564d8-3d7f-560a-b8ad-7d18b9b9d829 | note | RECORD OF CONFORMITY: ITP Signed
9fa9cf24-6f76-587d-b5dc-3e7d5f5130be | note | IP
c289f64e-5aad-5c66-b89e-252e68824bcf | note | RESPONSIBILITY: Project Engineer / Site Foreman
4fcffce3-5306-55dc-b973-fc87f40eba56 | date | Date Completed:
| checkpoint | 2.8 - Place & compact backfill material over pipes
42819a20-c712-56d6-bfc0-a0af97f47e97 | note | FREQUENCY: each lot
3974b94a-aed0-50c9-b851-2b5a9a7351d8 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
903b7e9a-ddfc-5b49-8a8a-11a57395f2fd | note | – Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
90843d24-a920-58d2-a29a-200a84d101f9 | note | ○ Loose layer thickness <= 150mm.
c8064c1c-e19f-5890-8d87-19bd3839c77e | note | ○ 1 lot = 150mm layer
da36230f-1da0-567c-a683-1981973f4903 | note | REFERENCE DOCUMENTS: 701.14, 701.15
59f2b7af-3985-5af9-aa14-1885d1d21948 | note | INSPECTION/TEST METHOD: Visual Inspection
d070eee8-7f0c-53ca-bbe4-b97d4a6d5d09 | note | RECORD OF CONFORMITY: ITP Signed
6048d0a9-07f5-5e3f-9ba8-b2bd5f07060f | note | IP
57c90783-44cd-59be-8828-2e50bfe47454 | note | RESPONSIBILITY: Site Engineer / Site Foreman
9079063c-1ddc-53a8-bf85-b1631d61b080 | date | Date Completed:
| checkpoint | 2.9 - Repairs to damaged pipes
50e94297-7cd2-5ff9-95ac-b8b0803e4977 | note | FREQUENCY: Each damaged pipe
5e6e809d-ccf3-5080-a49b-bf1673abe7e3 | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
d8ac13ae-e1fd-56e6-a32d-289dacd9e7c8 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
c99ef9ce-7265-5766-8e6c-dda2c3a47fe1 | note | REFERENCE DOCUMENTS: 701.31
31630342-6edc-5652-8772-fd4a0f0c6313 | note | INSPECTION/TEST METHOD: Verify
f162cb5b-0609-5f10-8cda-f03df1945638 | note | RECORD OF CONFORMITY: ITP Signed
47328ebc-32cd-5341-af91-7454b063e551 | note | HP
41dcd3f8-e6da-51a1-9749-57b8d2169a94 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
c8745284-5d07-5095-8490-2f4be52b7110 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
aace3d9c-062c-57a3-97f1-e37b15529021 | note | FREQUENCY: as required/requested
0de0a44f-28fa-5fa7-946f-845dde7091d1 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
d11eadfa-7763-50e6-a110-1107289cf002 | note | ○ Bedding material shall be compacted using a compaction plated to refusal.
7e8410bf-d25b-5a4d-98e9-e6105220ffea | note | REFERENCE DOCUMENTS: 701.2
f54390a9-7a0e-595e-a31e-351463208580 | note | INSPECTION/TEST METHOD: Verify
1667ee42-8717-5dc7-abeb-a65055c9afac | note | RECORD OF CONFORMITY: Test Reports
891f8667-c0b6-5721-949a-20641e939d11 | note | TP
e1b38540-bf0b-5f18-ab22-6b1eb63f63d0 | note | RESPONSIBILITY: Project Engineer
cb9910b9-1ad0-5ecb-ad2c-addb0440464e | date | Date Completed:
| checkpoint | Final Inspection
e4ac0ffd-20f5-5b54-b475-b59a4677e054 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
bb3ac10a-178c-5cda-8577-422e26446a96 | textbox | Print Name:
b33b2d8d-0837-5cc6-ac4d-4e3a4049e4dd | textbox | Position:
45000800-acf7-5b18-8517-32b46f0e0758 | date | Date:
| checklist | ITP-002 (B) - Underground Stormwater Drainage Lot 1 BC | itp | ITP-002 (B) - Underground Stormwater Drainage Lot 1 BC |  | 1345be66-be57-4169-bd9d-0ce59356ff91
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
2536463d-a98c-5415-9f1c-a952c866356b | note | FREQUENCY: Prior to commencing any activity
ba21d5a7-7a41-5f4b-be92-d088d26dd341 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
29c3623e-c622-5139-b14d-3d6c9e402679 | note | – using the correct and complete set of drawings
74cb5344-2318-5ae2-a8e3-051d1e377c1f | note | – all drawings are the latest revision
5d353f50-448d-528b-a42b-99ecde7b5fdd | note | REFERENCE DOCUMENTS: Drawings and drawing registers
2b0b4e0c-8cbc-5284-a6aa-700335c8c619 | note | INSPECTION/TEST METHOD: Visual inspection
2ad5ef01-97f0-58ba-bb72-5ab56ff73de7 | note | RECORD OF CONFORMITY: This ITP signed off
69e61b87-bbb6-5927-bdac-dd22f5708c92 | note | HP*
af664761-9e18-592c-b0c4-126f9661be63 | note | RESPONSIBILITY: Project Engineer / Site Foreman
8fa2c6de-1bad-5dfb-b038-4f3d071327f3 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
4826a875-ef83-573c-b11b-ca17dc60c2c7 | note | FREQUENCY: Prior to commencing any activity
6a90268c-bddf-591e-9f15-bbcb26ffc326 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
a6c2de27-34a7-52a7-bf67-f9304b328127 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
5c21cd39-c89a-5a92-90db-39642aa27f7c | note | INSPECTION/TEST METHOD: Visual Inspection
5b33b2ba-1eca-5042-9baa-7899b3eb64fd | note | RECORD OF CONFORMITY: This ITP signed off
6e8eaae5-50fd-57b4-bce0-6e1a0a93aa5c | note | HP*
4a6e88b8-b127-5164-92fa-3f98baa65c3a | note | RESPONSIBILITY: Project Engineer / Site Foreman
21102b1f-8856-5763-9ede-a44ba1a3ac72 | date | Date Completed:
| checkpoint | 1.3 - Precast Materials Inspection
c90c6839-1658-5ca1-888d-3c382ec1298e | note | FREQUENCY: Each Delivery
3fe2f94e-80ad-50a0-9a25-4f2d4dfae82f | note | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
bad7c92a-c8cb-5e6d-abed-4199a889f7d6 | note | REFERENCE DOCUMENTS: 701.04b
21f696f7-e852-5ca1-afc4-5562c603f93f | note | INSPECTION/TEST METHOD: Visual Inspection
2615951c-3d22-57f4-b9cc-c167ade002c2 | note | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
cb3804ec-87f6-5f24-92cf-743c1e141048 | note | IP
c32456e5-f33d-52a9-af54-36e3efeae700 | note | RESPONSIBILITY: Project Engineer
965765df-e4c2-5d1a-9ee8-11c707da4481 | date | Date Completed:
| checkpoint | 1.4 - Precast Pipe Compliance
44aedded-2466-57b0-89c5-923c8c8ae598 | note | FREQUENCY: Prior to Commencing
dfd9ad8a-70e5-5d8f-ba1a-4d80793404d8 | note | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
61fd5e22-eb5e-5e09-8a4a-7c9bb96fcf67 | note | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
affbcb3c-1b13-5a0b-a595-322978e00a14 | note | REFERENCE DOCUMENTS: VicRoads Spec.
be660597-f9bd-5f79-819d-258362bc394d | note | ○ Cl.619
a590f6a7-a8cb-5c82-92fc-ef1c274673f9 | note | ○ Cl. 701.04(a)
a0dc6e0c-0003-5f89-9b10-e4388b75925a | note | ○ Cl. 701.04(b)(i)
4a8e1230-198e-533c-aa30-48e4fb86938f | note | ○ Cl. 705.04(d)
05ae2d20-83e6-5231-a9be-82d8703f27ef | note | ○ Cl. 705.11
bb6a9efe-bd79-53c3-8ce8-6dd8602b5c0e | note | ○ AS4058
1e392753-1854-5603-8137-90e6a5cb4320 | note | ○ AS4680
bfb15818-42b0-5621-ae31-30c578fe216d | note | INSPECTION/TEST METHOD: Document review & Site inspection
699a49d7-3e75-5109-b502-9e8a28f26127 | note | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer certificate or accreditation
a6a8eeda-02b0-5966-8216-d6134c0f4965 | note | IP
110afdb7-d6e3-53f6-ae00-fadb12307017 | note | RESPONSIBILITY: Project Engineer
23420c16-75fe-5b21-a5e8-b10ddbf70fb7 | date | Date Completed:
| checkpoint | 1.5 - Bedding material classification
45d26e1d-12f5-54ab-87d1-4c07eb7ceecc | note | FREQUENCY: Prior to start
aa4a0825-6328-5142-9545-cb1046e14f56 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
d7ee63c9-17ed-5826-b065-ed187fd2ef85 | note | ○ 100% passing 19mm sieve.
dc840888-d97c-53a0-93a5-f26d92e2ef7b | note | ○ 5%-40% passing 0.075mm.
22d5b3d3-030b-59a2-a5c5-10f9d90874c7 | note | ○ PI = 20 max.
30b13c90-cc61-5382-900e-855ff34dd260 | note | REFERENCE DOCUMENTS: 701.04e
e8dd8232-e900-5543-99be-161b49e8921a | note | ○ Table 701.041
cdc67256-49e4-52a6-85ea-42bde18303e9 | note | ○ Table 701.042
da7e2d2c-1e43-5c41-9752-93d2aeb6b815 | note | ○ Table 701.231
8de974b7-f1b2-58bd-9c81-730ec12d2934 | note | INSPECTION/TEST METHOD: Verify
55d8aa1b-020b-59a5-9069-3f4e01661d34 | note | RECORD OF CONFORMITY: Test Reports from supplier
89c3391b-aab9-553d-a336-2b827e6cc8ff | note | TP
4e7da943-7dbd-5264-9836-8afacb78945b | note | RESPONSIBILITY: Project Engineer
715c8c84-fc40-5fcc-bc84-f4719f57cb81 | date | Date Completed:
| checkpoint | 1.6 - Backfill material Classification
0844c898-330c-5f4b-8a6b-82f2e41dd8e4 | note | FREQUENCY: Prior to start
60e86109-e712-559f-a215-685adf5e7bd9 | note | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
a6c451a0-cfad-5836-9ba0-2329df5baf0d | note | ○ 100% passing 37.5mm sieve.
373500f3-8e1b-59c1-b3af-6f82878eba29 | note | ○ 5%-40% passing 0.075mm sieve.
792da393-0439-5f1f-add4-2d8e7f8ee0f3 | note | ○ PI = 20 max.
82158ede-ec7c-5071-be27-0e480ab6adf0 | note | REFERENCE DOCUMENTS: 701.04e
7e163cd3-550f-54bf-9a7f-b7ffe3e7cc0d | note | ○ Table 701.041
6caebb7b-7d40-5063-80c9-b089e2effc78 | note | ○ Table 701.042
8b7dd512-5da8-5014-bcf1-8b5b069b2b01 | note | ○ Table 701.231
f16107d7-2030-5c6f-a554-43f859920e3b | note | INSPECTION/TEST METHOD: Verify
3088c4f1-0be6-586a-9732-9efc31d7d763 | note | RECORD OF CONFORMITY: Test Reports from supplier
69151b97-dc75-5726-8672-662d5dc4bc95 | note | TP
5f5ff687-5177-5c62-9640-bbaa97a874e1 | note | RESPONSIBILITY: Project Engineer
8b9806fa-fda0-5a18-afe8-21be012fc5e0 | date | Date Completed:
| checkpoint | 1.7 - Mortar material classification
c83568c7-36bc-5a1f-8c7d-d8a1a968d897 | note | FREQUENCY: Prior to start
3bbe8e1b-fef7-5614-94fa-fb3db555a031 | note | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
0b0c099b-f7f9-5826-878d-ccd8c16b9c3a | note | REFERENCE DOCUMENTS: 610.33
58057e94-c0d7-5698-beca-7097f5e1d46b | note | INSPECTION/TEST METHOD: Verify
efa770cf-d982-5054-b5f8-6b796614b97f | note | RECORD OF CONFORMITY: Test Reports from supplier
793b1357-8258-5f5d-b355-79d501683e7d | note | TP
c956ecd4-1970-51d5-ae9b-a9500be527c0 | note | RESPONSIBILITY: Project Engineer
a2d1487b-ed4a-523e-9617-60629fda7454 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
b4b45cfe-0bbd-5445-babd-7228646eed67 | note | FREQUENCY: Each lot
eeb83a86-24a9-50c5-a7e3-4fe0dc9c08e7 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
3d104af0-f084-507f-966a-e0f96067170b | note | ○ Plant and equipment shall be appropriate for the task.
d6436c3d-ca83-5bed-90c4-3377f821e5bf | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
c9067dd6-9062-541a-98ee-fd42ea55d607 | note | REFERENCE DOCUMENTS: Excavation permit
c623ef64-d987-50ba-9747-b39487bbde93 | note | INSPECTION/TEST METHOD: Verify
543c4abe-e64a-525a-9a18-2f5cafb18955 | note | RECORD OF CONFORMITY: ITP Signed
4d5a617b-5b8b-5772-b140-87625b64f8bf | note | HP*
c0c01f63-cac1-5c2b-be49-a3d3cb4e8317 | note | RESPONSIBILITY: Project Engineer
774141e8-9c5c-5c4e-bc6a-47ac871f57ae | date | Date Completed:
| checkpoint | 2.2 - Set out drainage
100c897f-7b1f-5628-b870-0896b7853127 | note | FREQUENCY: Prior to excavation
fa68948d-d36e-5ba8-a53a-858561a2311a | note | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
9db565ea-adc8-5963-b807-b41e4a226825 | note | REFERENCE DOCUMENTS: Drawings 701.10
a10eaec8-ba1e-5e5e-8d53-de18152d9b3d | note | INSPECTION/TEST METHOD: Visual Inspection
05205336-17fc-5bba-93db-1d5eb63d4322 | note | RECORD OF CONFORMITY: ITP Signed
d9232e98-feac-57c0-a4ef-0b1e31066812 | note | HP
de7ed3c3-66dc-5559-a58a-4ea1223b0c6c | note | RESPONSIBILITY: Engineer / Forman & Superintendent
ec5ba723-3b46-553e-baa7-599588fe379f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Excavation (pipes)
d5b8731f-d9d4-5656-99da-00d9abcf18eb | note | FREQUENCY: Each Trench
2d46719b-f53d-566d-aa83-ea24ce49c6a3 | note | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts.
b049dc18-bb4b-5dd7-b066-883e211505db | note | ○ Trench walls to be vertical where practical
79c3e1fd-1651-5361-abb0-3570e83111c2 | note | Depth of trench:
d27614c8-6a64-5e54-badf-eaab5f878542 | note | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
6025650b-2f08-5588-89f3-138d5c246014 | note | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
bf4c952b-4972-50e8-ac38-11fabd05a77f | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
5308eb25-5306-5075-9839-8fd9a37f8c57 | note | INSPECTION/TEST METHOD: Visual Inspection
0fe0ff87-38de-5b1a-8702-c5a0edcd1d0f | note | RECORD OF CONFORMITY: ITP Signed
056d1f92-9090-5991-a82b-d8551fbd1468 | note | IP
1dd4a752-f556-57b0-b8ab-04bc4aca9419 | note | RESPONSIBILITY: Site Foreman
4813a837-19d8-5403-84ca-65307d8a6d39 | date | Date Completed:
| checkpoint | 2.4 - Compact base of trench
a8fdf003-dfd2-5849-9ab6-0b034dd270aa | note | FREQUENCY: Each Trench
c8b64070-3ff3-50a1-bf57-345bfe4f1dc0 | note | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
ba1bcdb6-4b07-5f31-bfa4-58885a1bb1df | note | REFERENCE DOCUMENTS: 701.1
852c94c4-6f91-59cb-8498-c45fbeb21c9b | note | INSPECTION/TEST METHOD: Visual Inspection
fbf3d258-8973-5e66-ba8d-be613d247ebf | note | RECORD OF CONFORMITY: ITP Signed
644405e6-e65d-54b8-9956-ba1d9af4b408 | note | IP
429bcab5-f2bd-5fa9-83fa-55cd0ebc4181 | note | RESPONSIBILITY: Project Engineer
8dc8e846-811a-5398-9cf4-bd0f93ccd0e1 | date | Date Completed:
| checkpoint | 2.5 - Place bedding material & compact
ce1faded-f0b0-5c69-8490-f67d7434c29d | note | FREQUENCY: Each Trench
b3ae83c3-512b-57cc-9e05-903ad565b053 | note | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
b918eb7e-b0ff-5139-9a12-fb8c34a296eb | note | ○ 100mm under pipes.
54458fd7-b1d4-5eee-921d-42d0fa40f31d | note | ○ 80mm (earth foundation)
de7f0bf6-fa30-5fac-a8f5-ae08a9081233 | note | ○ 150mm (rock foundation)
887f8899-3132-57df-95aa-38a553e1865f | note | REFERENCE DOCUMENTS: 701.19
797175e6-e75b-58a6-aa70-7e9b3e3f326b | note | INSPECTION/TEST METHOD: Visual Inspection
28a578d7-afbe-566a-ac4a-4f2c25b5b7f6 | note | RECORD OF CONFORMITY: ITP Signed
c587e027-82d1-5428-a4b3-0a020731a8c3 | note | IP
7d06fbbc-dfc8-50d3-827f-439f3490da44 | note | RESPONSIBILITY: Project Engineer
f29e8e4f-625f-5b3d-9be4-56a0ab56c9e9 | date | Date Completed:
| checkpoint | 2.6 - Place pipes
06b5fd31-9ff3-599e-90a7-a116a14e2d72 | note | FREQUENCY: Each Line/Pit
fd913ff6-793e-50c5-8fef-8b59f75fe431 | note | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
4c390c6e-5f8a-5359-97c8-6e6a4aecfa6e | note | REFERENCE DOCUMENTS: Drawings 701.17
e4c7d500-1130-5ead-a592-6212f11ad5b2 | note | INSPECTION/TEST METHOD: Visual Inspection
4027998f-f2d4-58b9-b31e-3f7e9d0d2db1 | note | RECORD OF CONFORMITY: ITP Signed
4142da17-a87b-5bce-a747-ce5c7e5ae51c | note | IP
c2773bb2-9571-50e4-8751-c57aa8a6b69d | note | RESPONSIBILITY: Project Engineer / Site Foreman
b320a766-fedb-5cef-bdc9-14a4927e2795 | date | Date Completed:
| checkpoint | 2.7 - Jointing Box culvert sections
643e01b7-cf22-52d0-98db-6f50461cf246 | note | FREQUENCY: Each Line
2a4e47af-5cc4-5e86-824d-433a3504837c | note | ACCEPTANCE CRITERIA: Consecutive sections of box culverts shall be firmly butted together. The top sections shall be matched to the bottom sections and shall not be lapped over adjoining bottom sections. The contact areas between the top and bottom sections shall be mortared. Multi-row box culverts shall be laid with the sections in each row in contact with the sections in the adjacent rows.
7dcce5ad-3558-560e-98ca-879c69755942 | note | REFERENCE DOCUMENTS: 701.17
666be216-2615-5dfd-a82d-c18cdd94bf79 | note | INSPECTION/TEST METHOD: Visual Inspection
4c34d1ed-a6f9-5b5c-b036-b53460d97553 | note | RECORD OF CONFORMITY: ITP Signed
362a28fb-0479-58e5-9811-d73b34363399 | note | IP
b529e285-1cf6-5975-85d7-0b3dd6ecf7d1 | note | RESPONSIBILITY: Project Engineer / Site Foreman
a0217284-963b-5584-8372-68c8998300fc | date | Date Completed:
| checkpoint | 2.8 - Place & compact backfill material over pipes
ba0b3a5f-4318-5a7d-ba37-1719a02f96f3 | note | FREQUENCY: each lot
6ca21e8b-0d04-54d8-9355-d18d5be83638 | note | ACCEPTANCE CRITERIA: Backfill under paved area: fill trench with selected back fill material to subgrade level
c6e40282-d9ff-5bdd-b0d5-b366c56a809b | note | – Backfill under area not paved: Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
fb80167e-f541-5446-b3a9-37d90bb754d1 | note | ○ Loose layer thickness <= 150mm.
e836e066-7523-56be-9635-ab3bc90ff114 | note | ○ 1 lot = 150mm layer
234d4969-e75d-557b-b44e-2a98d2e637c7 | note | REFERENCE DOCUMENTS: 701.14, 701.15
d5fcc955-7b7d-59d9-8d05-5157a06a7e4e | note | INSPECTION/TEST METHOD: Visual Inspection
8716ea03-7225-5e2d-b13c-b02e85b6b256 | note | RECORD OF CONFORMITY: ITP Signed
eecef1cc-e387-5bef-b624-12fe3be567b8 | note | IP
5519b2b0-3fa6-56ec-b247-04551bb30977 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b7d15262-5d60-55e3-93f3-fe5dc7f882a1 | date | Date Completed:
| checkpoint | 2.9 - Repairs to damaged pipes
a0b24665-4647-5f91-ad03-ef1db9b7efd0 | note | FREQUENCY: Each damaged pipe
af15152d-98f2-5ab1-8d4b-29791da9b3fd | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
3b247683-40a0-530c-b239-d4f9c2a8b0d7 | note | ○ All repair procedures undertaken in accordance with Cl 701.25
12d2d3c5-0ab5-5360-a1e2-4eee111e3e45 | note | REFERENCE DOCUMENTS: 701.31
4165ce2f-f509-5d03-940b-68626980881e | note | INSPECTION/TEST METHOD: Verify
ae039418-931b-52d6-ba96-c27b11de234d | note | RECORD OF CONFORMITY: ITP Signed
cf32aff5-40b5-55ba-867f-134203f00aaf | note | HP
338ddd97-fb78-5f3e-87fc-611de75eb079 | note | RESPONSIBILITY: Engineer / Forman & Superintendent
11534f37-f85f-5d64-bb74-420ceaf43694 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
36a06065-24cc-59d8-bf08-f3c324a45cd0 | note | FREQUENCY: as required/requested
76fb3b3e-f87b-5ead-9542-c990f2d08349 | note | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
d014a27b-e40e-5b1b-bb48-869cd1b16402 | note | ○ Bedding material shall be compacted using a compaction plated to refusal.
4fa22a2f-9d87-54f0-a5f6-60f67b0c489d | note | REFERENCE DOCUMENTS: 701.2
0f00ecee-29df-5cda-ae69-38826fbcb662 | note | INSPECTION/TEST METHOD: Verify
17353ef2-e7e9-5601-96bd-ebf876f2c9e0 | note | RECORD OF CONFORMITY: Test Reports
26593690-15d3-5aa5-9c32-b4ee4a21fc4f | note | TP
ca9aef0b-5730-534e-9837-a493505c5257 | note | RESPONSIBILITY: Project Engineer
885384c1-953c-5d7e-9607-d2c4e4dfda0a | date | Date Completed:
| checkpoint | Final Inspection
8389cef5-a07b-56f7-bb2a-b659632792fd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
596c59df-7748-5c70-8e40-b528a813ad49 | textbox | Print Name:
b13b591b-12f9-5a64-a11d-f9f4f9823719 | textbox | Position:
cc5a87f2-e8e7-5331-852b-834cb8f682ab | date | Date:
506fc2e8-be06-4bf8-88a1-f2ee5feda05a | checklist | ITP-004 - Fill with Material Type A | itp | ITP-004 - Fill with Material Type A |  | 16159fb9-e897-41a8-b181-b4adeff1a7eb
a388efa5-1b18-43f7-a9c5-e27b8ad76060 | section | 1 - Preliminary Works
4ad963ff-cb0d-4c74-8809-36710fbdc6f8 | checkpoint | 1.1 - Induction
092292d4-15bb-586a-ace2-16a38ff5f722 | note | FREQUENCY - Prior to Commencing
4322f358-40dd-55d8-93a9-113e17185ee7 | note | ACCEPTANCE CRITERIA - All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
e0b363b1-fd0b-505a-9601-df3449d45a57 | note | REFERENCE DOCUMENTS - Inductions Register
8180d58f-595f-55db-9b59-34871a50ab67 | note | INSPECTION / TEST METHOD - Document review
6ffee687-901a-5eb9-a30b-2e4cb3bb5ac6 | note | RECORD OF CONFORMITY - Site induction signed.
5ce4d602-2966-5cf7-bdb5-8e1abca64552 | note | AP
a5816819-38bc-5490-88fd-4ba1ee498b29 | note | RESPONSIBILITY - Site Engineer / Site Foreman
fa822b8b-2cc4-513e-bb57-d6a25d2d8297 | textbox | Date Completed:
33e21405-5efa-4155-b6d1-61774f0478a0 | checkpoint | 1.2 - Safety measures are in place, Safe Work Method Statement (SWMS) undertaken
80e327c1-65e2-51e4-b773-99470fa53f45 | note | FREQUENCY - Prior to commencing
ae05945d-386f-59c2-a8ee-83badbacb2ba | note | ACCEPTANCE CRITERIA - All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
49931f10-f78a-51fa-94c8-0dd6a09ca18d | note | REFERENCE DOCUMENTS - Health and Safety Co-Ordination Plan
e348eefe-19a1-53bb-bb46-d62d249782e0 | note | INSPECTION / TEST METHOD - Document Review
fad80a3e-c3a9-58a4-a31a-3fbe3cdd9731 | note | RECORD OF CONFORMITY - SWMS(s) signed
36db08d0-1b4f-542e-9a6e-bf35b2a5ea44 | note | HP
dad3aae7-4951-560b-9178-e4b66748ee1b | note | RESPONSIBILITY - Site Engineer, Site Foreman & Superintendent
c294b1cb-c948-5626-89c4-aecbe6c7397b | textbox | Date Completed:
417d25e4-8055-4edd-831c-5d7374d0ac24 | signoff | AUTHORITY HOLDPOINT
b0dc13d8-841f-4181-8a27-9fa83df59fd7 | checkpoint | 1.3 - Check that current revision drawings are being used
9d9ab9b0-011c-51e3-9717-941780819579 | note | FREQUENCY - Prior to Commencing
e859130d-03e7-5a68-9fa4-691c8805542c | note | ACCEPTANCE CRITERIA - Issued For Construction (IFC) and latest available revision used
b4f35564-f6c7-5e96-a9ea-2624a29279c2 | note | REFERENCE DOCUMENTS - Project Drawings / Drawing Register
bda7b552-05c5-5e94-ad0f-7c7aa8a89168 | note | INSPECTION / TEST METHOD - Document review
23b7a438-02f7-5be5-99e0-38c135f60420 | note | RECORD OF CONFORMITY - Latest Revision Drawings
e6c614fe-3c9f-518b-a363-4d4c95427752 | note | AP
f2fad41d-d507-5beb-a85e-c00863b19f65 | note | RESPONSIBILITY - Site Engineer / Site Foreman
0aead87c-69d3-527c-8d3b-f8676c87f5ea | textbox | Date Completed:
3be01fb3-be70-4cd0-9aac-947a96784181 | checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
23ec07f7-3661-5766-b520-57bf0688d538 | note | FREQUENCY - Prior to Commencing
a8ecd16a-eff7-5a8b-9e0b-cbc01c204a19 | note | ACCEPTANCE CRITERIA - All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
6bcc8c1b-fe9e-5c12-beda-1f97ba4bc153 | note | REFERENCE DOCUMENTS - IFC Drawings CEMP CHMP
9c0803bd-609a-5484-914e-0419a6c54a9d | note | INSPECTION / TEST METHOD - Document review & Site inspection
20d28dd2-e7b7-5f3c-b9c2-ef7b5d2b5f73 | note | RECORD OF CONFORMITY - Signed ITP
01f5d257-2606-5883-b274-0ccce427729d | note | IP
6fba8332-8ba0-55f3-b74a-0b48e39b71b4 | note | RESPONSIBILITY - Site Engineer
da1a6bd8-56aa-5b32-bb30-e6b02afd3393 | textbox | Date Completed:
8f5baa4a-248d-4b51-a920-2b324aafbd02 | checkpoint | 1.5 - Excavation Permit issued
77310520-0f4a-5da2-9c10-0ac5cddde9e3 | note | FREQUENCY - Prior to Commencing
48834ef7-3f0f-5021-80e4-eed82779d644 | note | ACCEPTANCE CRITERIA - Current Excavation Permit signed and specific for the area where works will be executed.
b8f3ccdc-0a32-5efa-931c-bc9a7a5a7079 | note | REFERENCE DOCUMENTS - Excavation Permit
3465f5be-532f-5ec4-8870-7c16bfc5b553 | note | INSPECTION / TEST METHOD - Document review
1d413a0e-d5a4-5db9-958c-08035a480bd7 | note | RECORD OF CONFORMITY - Excavation Permit #
86e23d55-8cd3-52c5-abf9-e9b0e29dd93e | note | IP
3958ce12-fc4f-51bb-9b74-fbaf40dfbafd | note | RESPONSIBILITY - Site Engineer
f03d4f56-ca21-552a-8ba3-3d8117c50002 | textbox | Date Completed:
77bfecae-2491-4caa-ab79-69746cb9043a | checkpoint | 1.6 - Verify Material
117a253b-0c1c-5b5b-81ce-b3129082c1d3 | note | FREQUENCY - Prior to Commencing
bd7eb59b-47dc-5b3d-8943-eec3495adcfe | note | ACCEPTANCE CRITERIA - Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material. Type A material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products.
7e594e6a-ede1-5061-bcba-097c6ea8862f | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.06(c) Cl.204.04(c)
4aae9293-4bcd-5494-96f7-f23f0c765681 | note | INSPECTION / TEST METHOD - Site Inspection
9e081b3b-f22e-563c-8502-f10069e45446 | note | RECORD OF CONFORMITY - Test Results Material Category agreed with Superintendent
1c3dfab1-9b71-51fa-b8f3-749d476bf8ee | note | HP
e8f613dc-5f20-5ef1-acd0-f99c9fb40a78 | note | RESPONSIBILITY - Site Engineer & Superintendent
e96977fe-93d0-51b5-9534-427d28132219 | textbox | Date Completed:
141e84d3-7e7c-4f39-b33f-2de9c84c0f81 | signoff | AUTHORITY HOLDPOINT
757260b1-c30d-4a2e-a2ec-c815b4fd2974 | section | 2 - Placing Type A Material
ed6a707b-94bf-4bfa-aba7-eb836728966b | checkpoint | 2.1 - Survey set-out
ecf6a496-8403-5d24-bef5-f55615a452c0 | note | FREQUENCY - Prior to Commencing Excavation
406aa4b7-8a12-56ff-a8db-f4712aec14b5 | note | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
6d23c7ac-fcc4-5f92-9aa4-0cec12536ed5 | note | REFERENCE DOCUMENTS - Latest IFC Drawings
d2aeaa43-6729-5944-a955-d75089c86c5a | note | INSPECTION / TEST METHOD - Site Inspection
3895b507-a93a-5486-8916-7b42ed8e5958 | note | RECORD OF CONFORMITY - Survey records & pegs on the ground
29b0eee0-f293-50ff-94bc-be2b6ce271e2 | note | SCP
ffb8f66a-62eb-5f2e-b1ee-bb9de9053ce3 | note | RESPONSIBILITY - Site Engineer & Surveyor
b08c59c7-8936-5d13-b6ab-6de73ea08331 | textbox | Date Completed:
b1104fdc-d1dc-4463-b645-3cf2d697d796 | checkpoint | 2.2 - Fill Construction
7e38a5dc-5e9f-58eb-a851-63b560cb0a18 | note | FREQUENCY - Prior to Commencing Excavation
215bf3f9-a773-5a25-a503-6f5cc6ddba58 | note | ACCEPTANCE CRITERIA - No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
f79ba15f-8321-5656-b943-8c518bd7aebe | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.10(b)
b7a8fa25-d795-5de4-babd-c45a16693932 | note | INSPECTION / TEST METHOD - Site Inspection
b79384e2-c09a-5075-b231-c2aa6c0af81e | note | RECORD OF CONFORMITY - Area reviewed by Superintendent Signed ITP
1d66fc22-86a6-5060-8d4f-74465948f283 | note | HP
6a9fb5e7-80fd-5eb4-b084-bf412b0fc71f | note | RESPONSIBILITY - Site Engineer & Superintendent
6783bc81-fddf-5f2a-9020-7eece1fbf56c | textbox | Date Completed:
26ce71f9-ef4a-4539-ab32-ed12a3a3fb55 | signoff | AUTHORITY HOLDPOINT
91fe70ef-f9d2-44f4-9708-83355f53f5b8 | checkpoint | 2.3 - Keyed fill layers
1fa34de4-2a18-5bb9-982d-14998bf53f36 | note | FREQUENCY - During Excavation
3ef48af2-d9a1-51c2-bec5-f4dcca761aa4 | note | ACCEPTANCE CRITERIA - Placement surface textured to ensure layers keyed into each other.
556c8749-fe2a-5f93-a503-18c6b4032016 | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.10(d)(i)
be0ac2cc-d036-5d0b-916a-fc22d0623512 | note | INSPECTION / TEST METHOD - Site Inspection
8281b0f1-9996-53b6-a045-24d2df39611b | note | RECORD OF CONFORMITY - Signed ITP
affc4cc8-3ffd-51fb-a8c7-c7e06f4a3c3f | note | IP
a47ce648-64bf-5d3e-83f4-5bb6225ece2d | note | RESPONSIBILITY - Site Engineer
ec999025-1ac8-5b19-8c0f-3d239b05cec8 | textbox | Date Completed:
1aa10b59-4dfb-498e-863d-6bbe3ba32e1b | checkpoint | 2.4 - Layer thickness
3ad939bb-27f6-5f83-a317-6d75974edb3c | note | FREQUENCY - During Excavation
30c23275-03e3-57c9-9c23-89116430a7d6 | note | ACCEPTANCE CRITERIA - Layers placed and spread in uniform compacted layers not thicker than 200mm. A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
f5cbbb6b-2d93-5ddb-848a-2c81420e3e4b | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.10(d)(ii)
37ea741a-281d-5dda-bb75-96fd4aad3aa5 | note | INSPECTION / TEST METHOD - Site Inspection
6b7df041-9787-5596-8cdb-bb0e4c6b7070 | note | RECORD OF CONFORMITY - Signed ITP
81aef6bf-8943-527f-ad6b-e05fd9e75096 | note | IP
3d6a0f66-5e6a-5f6c-9d02-1ea0ea183565 | note | RESPONSIBILITY - Site Engineer
144553bd-4021-5d3b-bbb5-03d92d487fc3 | textbox | Date Completed:
b1456405-fe63-43d7-8c12-ae28b395d0c1 | checkpoint | 2.5 - Proof Roll
e898dc8a-4c95-5bcc-b3d5-0494576d87c6 | note | FREQUENCY - Each Lot (one day's production or 5,000m2, whichever is lesser)
a15e2a2d-fea6-5954-9aa5-c715db0b685e | note | ACCEPTANCE CRITERIA - Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling.
04cdfbd6-cc25-5383-9b42-ecb56469f7f7 | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.12 Cl.173.03
e9eeb962-d992-5ab9-a729-12ab355ea55f | note | INSPECTION / TEST METHOD - Site Inspection
3b91ebdc-f4b7-534b-84f3-dfc64847e903 | note | RECORD OF CONFORMITY - Proof Roll Form completed & signed.
afaa1157-6074-596d-90d6-0712cc35e336 | note | HP
72b0d044-7c2d-5a93-880e-6c205c4f04d2 | note | RESPONSIBILITY - Site Engineer & Superintendent
6f13b350-6ec5-5c4b-b537-7c1ba6cc6f99 | textbox | Date Completed:
2ca7ab6b-d7f6-48a8-8eed-4381c1c39eb4 | signoff | AUTHORITY HOLDPOINT
7a4e1d58-2d34-41cf-9c90-7d8e18108a49 | checkpoint | 2.6 - Preparation of final surface
86ded273-b1ee-543f-9ae4-c28556135206 | note | FREQUENCY - Prior to construction of subgrade layer
b7a75dab-35b5-5b8c-912a-2f780d5c3f23 | note | ACCEPTANCE CRITERIA - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
cab48da2-702b-521a-b558-8da91f503e60 | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.15 Cl. 204.03(g)
a7c6348e-cec6-5daa-aaec-d30ee882c071 | note | INSPECTION / TEST METHOD - Site Inspection
d217da22-ec8c-5e2d-9da2-159954eae5f2 | note | RECORD OF CONFORMITY - Signed ITP
8fa0b6a2-9bb8-52c3-ac18-755fdd75b8af | note | IP
945d184f-7672-55f3-8810-02ec71fd2bf3 | note | RESPONSIBILITY - Site Engineer
7ca5ff58-b88f-5470-98b4-fb167d3fa771 | textbox | Date Completed:
23a0d2dd-264a-49cd-9b21-4f6100cc91a0 | checkpoint | 2.7 - Conformity with Drawings
d99110c9-e795-5a8f-8a39-77447ffdf367 | note | FREQUENCY - Prior to construction of subgrade layer
74b3a7e9-804c-56ae-ad10-bf1eac49f89d | note | ACCEPTANCE CRITERIA - Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specified in IFC drawings
3f7f6f33-8d60-50ed-9136-d499e5e01acf | note | REFERENCE DOCUMENTS - VicRoads Spec. Table 204.03(f)
d6b8bf55-14c3-5746-92fd-8c57742706f1 | note | INSPECTION / TEST METHOD - Site Inspection
95681b0b-d051-5c18-a72a-302250d33459 | note | RECORD OF CONFORMITY - Signed ITP
5de23706-183a-5972-9154-0495e42686b5 | note | IP
00f450f1-a6e2-530f-94f9-8d80ea11915a | note | RESPONSIBILITY - Site Engineer
bc281b03-4ecc-5b51-a0b2-e9ad0684dae6 | textbox | Date Completed:
3a878a63-8cab-4e13-9dee-cc50b593eee8 | section | 3 - Testing
01bbbfbf-6271-4b9e-9e32-1018a6a1d6c6 | checkpoint | 3.1 - Compaction Testing
d316f013-dec1-53cd-bef8-c7ceb0168d8d | note | FREQUENCY - Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent.
4d91e464-56a2-5aa1-b200-e63edc585e28 | note | ACCEPTANCE CRITERIA - Type A Material placed more than 400 mm below top of Type A Material should be compacted to 97% of MDD. Type A Material placed within 400 mm of top of Type A Material should be compacted to 99% MDD.
7c1ec7a8-1f6b-58f8-912e-07c6452bee7e | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl.204.13(a) Cl.204.13(b) Table 204.131 Table 204.142
cec910af-d338-528c-a2d6-f7177e43ddd7 | note | INSPECTION / TEST METHOD - Site Inspection
47916cd8-de40-502c-9145-aec629ede182 | note | RECORD OF CONFORMITY - Compaction Test Records
f02f99f0-19d5-5386-bcf2-8f24dcfd4d09 | note | TP
e29f29e5-a849-5ce9-bfed-edec52a637b2 | note | RESPONSIBILITY - Site Engineer
f8608682-8784-5da8-af62-5721c0e0c038 | textbox | Date Completed:
15e09b02-bf11-4024-b6a5-a9e41d6cf6f2 | checkpoint | 3.2 - Maximum Particle Size
09686da8-2f90-5256-ad6f-aa382e01077b | note | FREQUENCY - Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements.
a3be693b-ff1f-50d7-9973-8d8a1ff19d17 | note | ACCEPTANCE CRITERIA - Maximum particle size should be 150mm when soil is within 400mm of the top of Type A soil, and 400 mm at depths greater than 400 mm below the top of Type A material.
942f4680-33f4-5b86-a401-bb5a527a69d8 | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.04(c) Cl.204.14(a)
7087832a-8573-54bf-b809-e1da3049e162 | note | INSPECTION / TEST METHOD - Site Inspection
571a7c6a-927f-5e84-adb0-6a64c05cafb0 | note | RECORD OF CONFORMITY - Maximum Particle Size Test Records
60a19aca-4eb4-5855-a01e-c7599c74d58a | note | TP
0a2616ec-5ea1-52ee-b390-f1fdd8001ae2 | note | RESPONSIBILITY - Site Engineer
adc4a030-ed7f-577f-bcaf-1f94a595f54a | textbox | Date Completed:
58916af9-5eb5-4a4c-8bc6-291a3ee3ca65 | checkpoint | 3.3 - CBR/Swell
75944d88-b825-5028-8200-57eff97ff3ca | note | FREQUENCY - The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frequency (every 8 lots) for future lots shall be agreed with the Superintendent
dbf2fe33-d58f-5fe8-be83-fcf618b938e8 | note | ACCEPTANCE CRITERIA - CBR: ≥ 2%, Swell: < 2.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent).
f95267b8-41ce-55fe-a102-d2a17e176399 | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.14 Cl. 204.04(c) Table 204.141
6e34f420-0484-548d-8ae5-48b36e63af95 | note | INSPECTION / TEST METHOD - Site Inspection
51d7e656-a68d-5962-bc93-5000bc3ca5bc | note | RECORD OF CONFORMITY - CBR/Swell Test Records
fa19d7b6-d0b4-5d75-a047-f79477c8ba8e | note | TP
6a93b071-fccb-5ac7-b1b3-ee06c6af1fad | note | RESPONSIBILITY - Site Engineer
95e77839-dfd7-534f-a753-0dd7454395fa | textbox | Date Completed:
5b5f652b-798e-484d-bb39-774974866639 | checkpoint | 3.4 - Atterberg Limit Tests
26cdfe7e-2388-52f5-8b55-fa3b06f266d8 | note | FREQUENCY - 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frequency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent
5321889e-96fa-5e98-8db4-4ab98ac1d8d1 | note | ACCEPTANCE CRITERIA - Ensure that soil post-compaction is not classified as silt
9013c6c4-379a-596b-a98d-69f386fe2e21 | note | REFERENCE DOCUMENTS - VicRoads Spec. Cl. 204.14 Table 204.141
2fe33851-fdc2-540a-87a8-41f1fd4c6b6b | note | INSPECTION / TEST METHOD - Site Inspection
95ae398d-7c58-5db7-94b7-fc0a4fa91f0f | note | RECORD OF CONFORMITY - PI Test Records
e6b8be3a-a34d-5e46-9751-e6cd4eff593a | note | TP
c1da1638-fba5-574b-8790-13eeaeabd9f4 | note | RESPONSIBILITY - Site Engineer
ceaeb0f6-6ee0-55ae-bc76-07c9e8d37e29 | textbox | Date Completed:
17372b6b-e810-425d-8bc7-537acb49ad22 | checkpoint | Final Inspection
09fd8379-cbb0-5eb2-8457-fbf61837b3ee | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
cc09dda2-8309-5301-8e76-ad2ff712e627 | textbox | Print Name:
952e7891-d893-57f3-8d24-66bb454a4c5b | textbox | Position:
bceacb61-def1-59e4-9fe1-b66f44234cf6 | date | Date:
0350e23a-3a63-4693-ae28-617892aac4ba | signoff | Sign ITP
| checklist | ITP-004 - Fill with Material Type B Lot 1 | itp | ITP-004 - Fill with Material Type B Lot 1 |  | 4a9492f0-98c8-427e-8912-5e622fda4e4a
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
2f52dbd1-c6fd-5e28-8a14-14cd3be888d4 | note | FREQUENCY: Prior to Commencing
1c55d984-acfa-5c4d-bc2d-f3cf8056b131 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Ballarto Rd & Lyrebird Dr Project site
81f8219b-5ee6-5ef5-af29-82420f3df49a | note | REFERENCE DOCUMENTS: Inductions Register
13578761-6d13-59f0-9a59-9ea814707d5c | note | INSPECTION/TEST METHOD: Document review
c040f769-490e-525a-9761-c573687ce217 | note | RECORD OF CONFORMITY: Site induction signed.
41c249fb-eeaa-512c-82d2-1d74a6cb80ab | note | AP
f2a6a26b-922d-5037-ac50-bed90c2d6faa | note | RESPONSIBILITY: Site Engineer / Site Foreman
64819518-76fe-5c5f-9a49-e1422a985da3 | date | Date Completed:
| checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
0263cc7c-81f9-5fac-be47-d3f434ba82f4 | note | FREQUENCY: Prior to commencing
854aac22-31b4-5b56-9769-3bf2254c6d92 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
e7c53a95-725d-5ff7-9028-ddeda54b8122 | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
6574d15a-d080-5bab-a40a-6d28a76093c0 | note | INSPECTION/TEST METHOD: Document Review
c53f65e0-9756-5b33-8df3-9050132a0509 | note | RECORD OF CONFORMITY: SWMS(s) signed
ce2b2887-b3e3-5435-b499-8f9490d7273a | note | HP
dd8bbf64-1948-596a-93b5-956001d0df5c | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
8b5a88f0-fe3f-5ef1-977a-90278f81188b | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
0a8388bf-9eb2-5fd8-b64b-cd2967c5c11b | note | FREQUENCY: Prior to Commencing
2b65a652-e5e0-5076-8280-8030f2499da5 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
74c3a6b1-286f-5d3e-8d4c-7a0bdff6d812 | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
cb7e6300-bed2-5fa9-9c37-6e265ad7dd70 | note | INSPECTION/TEST METHOD: Document review
a77bb758-23ef-5d0c-bc21-8629910f42ef | note | RECORD OF CONFORMITY: Latest Revision Drawings
af57e0f8-5f64-5fb7-9a6b-8d4b0104433b | note | AP
e2989f62-d353-5133-909e-70486c5cb764 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e45a588e-d6c4-57e4-8786-3a9f82112dde | date | Date Completed:
| checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
d790351a-78d7-5651-95a8-5df64f6c448d | note | FREQUENCY: Prior to Commencing
c9f0ec28-addd-56b0-85d4-b95789f67280 | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
da260589-8536-53a0-9a57-c3da206e35b5 | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
09cd2202-bcca-58c2-97f5-c605307cd176 | note | INSPECTION/TEST METHOD: Document review & Site inspection
082898fc-1ee0-5b02-a620-ee2ac4125a1e | note | RECORD OF CONFORMITY: Signed ITP
87043b92-cd97-5b15-ad7b-446fc88baf6f | note | IP
f8619566-1cec-528e-9026-1c8e581a6b02 | note | RESPONSIBILITY: Site Engineer
1110ebc7-904f-5903-9443-156be638932d | date | Date Completed:
| checkpoint | 1.5 - Excavation Permit issued
2e0b4ab7-037a-5135-8531-d6e67e098a9a | note | FREQUENCY: Prior to Commencing
8819c634-f865-55ea-ab11-0c8bdc7fdb5d | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
c09b3853-dd3e-52c7-9b8c-c265d260c0f1 | note | REFERENCE DOCUMENTS: Excavation Permit
1d80b050-719a-5b5c-9438-ade4a23141fa | note | INSPECTION/TEST METHOD: Document review
ce4b2369-0018-5784-8aa9-b2d5f7b33179 | note | RECORD OF CONFORMITY: Excavation Permit #
67fd2e9e-4187-5775-8297-4a4911501608 | note | IP
78f15105-0e2c-5986-b4dd-b8afd6aee49e | note | RESPONSIBILITY: Site Engineer
e9a08077-9d89-5de4-9a7b-d0664ae3069f | date | Date Completed:
| checkpoint | 1.6 - Verify Material
99eaee79-cfaa-5c83-921a-e8a7084468ea | note | FREQUENCY: Prior to Commencing
1a8f39ad-e320-5b60-9a71-fc9f63cb3bd3 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and FH shall inspect each type of material encountered and subject to verification by appropriate laboratory testing and agree on the category of the material.
d3c233b1-113b-5d80-9cee-ff6a8faf77ff | note | ○ Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter such as bricks, concrete, glass, plastic, timber, steel or steel by-products.
8d5a269b-7c2e-5e79-8732-1344a8d09bb4 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(c), Cl.204.04(c)
8d183863-a017-5905-9519-2ae45428b7d7 | note | INSPECTION/TEST METHOD: Site Inspection
68ed7212-a221-5f7e-bfd4-2a790cfdce4c | note | RECORD OF CONFORMITY: Test Results, Material Category agreed with Superintendent
fbc690e6-cae2-5464-9a34-a30c5818b0b8 | note | HP
efb174b2-4c89-5437-af1e-12f0c6b636ec | note | RESPONSIBILITY: Site Engineer & Superintendent
4b057e0d-3462-523d-b47c-df04f2cc83b0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Placing Type B Material
| checkpoint | 2.1 - Survey set-out
3b34e28d-27b9-5273-92cb-afcb4a738335 | note | FREQUENCY: Prior to Commencing Excavation
90942cf8-e222-5d21-9f31-9f7900d5802d | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used
3b8b31aa-50c6-5db5-9342-15be3bd5e0f7 | note | REFERENCE DOCUMENTS: Latest IFC Drawings
0719f5aa-47b2-5950-8cf3-25bc47b4ea5b | note | INSPECTION/TEST METHOD: Site Inspection
cfbe6cc9-d8c7-5a6d-8379-1a3f924e0002 | note | RECORD OF CONFORMITY: Survey records & pegs on the ground
af6383b8-b795-5167-bdf4-6e82e0493a08 | note | SCP
a1e8d88a-9059-54bf-888b-05d187283f17 | note | RESPONSIBILITY: Site Engineer & Surveyor
1459f32b-8e08-5592-94b8-44c73a42bb36 | date | Date Completed:
| checkpoint | 2.2 - Fill Construction
e09f884b-9dce-55d0-a91a-709dcad9def4 | note | FREQUENCY: Prior to Commencing Excavation
15e38645-a114-5d18-a88d-b79efbd299f5 | note | ACCEPTANCE CRITERIA: No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent
3c74e560-fbb9-5305-b6e8-5566f5caf0f2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
b732bd91-0da0-5d17-a5f9-3d10dab7645d | note | INSPECTION/TEST METHOD: Site Inspection
319954c0-33dd-5957-a14b-45355612552e | note | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
6031eddd-6199-5329-bb8f-102b36e212d6 | note | HP
b207f867-b929-5247-9757-8444b90d1ae6 | note | RESPONSIBILITY: Site Engineer & Superintendent
de6962b5-826c-57dd-b1df-6d9155e21fc0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Keyed fill layers
b7b2188b-a630-578d-94d2-91e1d047f29b | note | FREQUENCY: During Excavation
ae31a2f1-c43e-50e4-ae7c-3928760e2821 | note | ACCEPTANCE CRITERIA: Placement surface textured to ensure layers keyed into each other.
9fc227d0-bdbc-5ff8-884c-633ee5578079 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(i)
aa867c9a-2265-5a4b-a5a1-86d370559074 | note | INSPECTION/TEST METHOD: Site Inspection
346e493b-cd41-54ec-9328-4e01de88c8ed | note | RECORD OF CONFORMITY: Signed ITP
89d8f2fe-6ec6-5e62-bb07-7086d820715b | note | IP
8433f16d-cbcf-5c41-a4e2-14c14ee6a84d | note | RESPONSIBILITY: Site Engineer
37b9818e-0320-588e-a7d5-68e666f21425 | date | Date Completed:
| checkpoint | 2.4 - Layer thickness
cb4901ce-241a-5b42-a50f-31e129a951c6 | note | FREQUENCY: During Excavation
610903da-ae8c-5975-8c67-ecf6a8813e8a | note | ACCEPTANCE CRITERIA: Layers placed and spread in uniform compacted layers not thicker than 200mm.
6b93fcc1-4315-5f9e-a9fd-b7196cf916a1 | note | ○ A procedure shall be established to verify that compacted layers do not exceed the specified maximum thickness. Verification records must provide evidence of measurements taken at least every three layers in consistent locations across the filled areas, and must be retained with the lot records.
00f55569-ffc2-5b7e-a40e-2bbfd6bceddd | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(d)(ii)
75ee8cdf-6c30-5e3a-89b5-81d4ee5f190a | note | INSPECTION/TEST METHOD: Site Inspection
9abb4213-23df-59c5-a757-d862b62a0584 | note | RECORD OF CONFORMITY: Signed ITP
225d1479-96d6-530f-a15c-aff1b66f800c | note | IP
af3ddbc0-2c66-5a8b-a85e-22785ff6892b | note | RESPONSIBILITY: Site Engineer
4282b85c-4edd-522e-812a-83a70a32a6bf | date | Date Completed:
| checkpoint | 2.5 - Proof Roll
adf9c58d-a581-5cdb-9816-fd79b2442910 | note | FREQUENCY: Each Lot (one day's production or 5,000m2, whichever is lesser)
c17738b2-d41a-581a-93b6-e3640cf8b3d9 | note | ACCEPTANCE CRITERIA: Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173.
a8093ec4-49b6-5784-9a89-f4b4aaead02c | note | ○ Superintendent to be present during all test rolling.
61dd883e-a6d6-5e4a-855a-46c693fe8197 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.12, Cl.173.03
31db51e5-795f-58fc-bc09-ffaad0073591 | note | INSPECTION/TEST METHOD: Site Inspection
5af5ef43-3e19-5a57-a9cd-ac59a5402e30 | note | RECORD OF CONFORMITY: Proof Roll Form completed & signed.
153b0f00-737d-5080-906e-e4f82609a976 | note | WP
0fa15414-e34a-515d-88cd-7e9be8da407b | note | RESPONSIBILITY: Site Engineer & Superintendent
3cea19cd-a13b-58c3-8dd6-b2f80efbf746 | date | Date Completed:
| checkpoint | 2.6 - Preparation of final surface
e9ee5a78-35a0-5c15-ab3a-f16618df146a | note | FREQUENCY: Prior to construction of subgrade layer
172eb9da-2bba-5559-afce-366e855b4e12 | note | ACCEPTANCE CRITERIA: The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
a047295c-891f-5956-b800-a890be2adf15 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.15, Cl. 204.03(g)
4909fd2d-833a-55cd-bd2a-c655aa3ce440 | note | INSPECTION/TEST METHOD: Site Inspection
1de870f6-bb7d-50a5-8a55-51a08763c102 | note | RECORD OF CONFORMITY: Signed ITP
522f24d0-a0a1-5042-8664-48a4903cde10 | note | IP
f57b73f8-bc11-5c19-a7dd-6a4962a26a96 | note | RESPONSIBILITY: Site Engineer
6277c054-4284-538d-a10d-1fff2b2135aa | date | Date Completed:
| checkpoint | 2.7 - Conformity with Drawings
ffab89f2-da3d-5768-b6b3-32d04b2a24bf | note | FREQUENCY: Prior to construction of subgrade layer
40b8945f-24c9-57ac-8e78-505dda146d64 | note | ACCEPTANCE CRITERIA: Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water. Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings
93b44f01-c62a-5fa9-a0c0-01498679108f | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.03(f)
7b83b5e5-4a62-5604-9084-9639f571787b | note | INSPECTION/TEST METHOD: Site Inspection
321dd472-3442-5eca-b23f-501d1f84b1d1 | note | RECORD OF CONFORMITY: Signed ITP
887164d9-edaf-5bd4-b76f-d6421f331731 | note | IP
ff22a8a6-63b8-5ec9-9aeb-905fbf4214c8 | note | RESPONSIBILITY: Site Engineer
396a01b1-655e-54d7-bb2d-872a13da75ea | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction Testing
a6647f47-40f2-5c30-b37d-c3a8a7d87f57 | note | FREQUENCY: Initially test every lot until three consecutive achieve passing results. If achieved, minimum frequency of testing from Table 204.142 of VicRoads must be agreed with Superintendent.
87de31bc-787a-5154-85e5-fa7ebd698563 | note | ACCEPTANCE CRITERIA: Type B Material placed more than 400 mm below top of Type B Material should be compacted to 97% of MDD. Type B Material placed within 400 mm of top of Type B Material should be compacted to 99% MDD.
d040bd57-64a2-5585-b7f6-86049e9f6ade | note | REFERENCE DOCUMENTS: VicRoads Spec.
284d25ab-9c02-585d-9631-0830074699de | note | ○ Cl.204.13(a)
a6526423-b4a6-5a65-995d-edf04a5514be | note | ○ Cl.204.13(b)
211552a1-3869-5d47-9790-52e9b47ed7af | note | ○ Table 204.131
0c278018-7fa5-5ae9-b190-841792673b47 | note | ○ Table 204.142
fdddf7b4-ec91-583a-ae24-a15821daa86a | note | INSPECTION/TEST METHOD: Site Inspection
01b89973-1938-586b-9c48-5fa24737564e | note | RECORD OF CONFORMITY: Compaction Test Records
47d94eed-8538-5dd4-971c-45a0468d83ab | note | TP
17932203-c273-53b9-aafe-43bed7b1baf6 | note | RESPONSIBILITY: Site Engineer
f7d4c199-4993-5e18-946f-ed5780a428de | date | Date Completed:
| checkpoint | 3.2 - Maximum Particle Size
0afb426f-e7b9-5e33-b76e-6a98d7f70bfa | note | FREQUENCY: Test every lot (one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements.
ed2ed9be-4ff8-5e9d-8670-7e855f135a17 | note | ACCEPTANCE CRITERIA: Maximum particle size should be 150mm when soil is within 400mm of the top of Type B soil, and 400 mm at depths greater than 400 mm below the top of Type B material.
c14f8fc8-f010-5fd6-8886-321a1658a24a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c), Cl.204.14(a)
6c260c5a-422e-5d23-ba1b-42bd42d04e95 | note | INSPECTION/TEST METHOD: Site Inspection
bc035155-40aa-5e55-b519-09cdcf68c04b | note | RECORD OF CONFORMITY: Maximum Particle Size Test Records
ba966138-7a6a-58b0-a715-1df8071f28e3 | note | TP
b1094c2d-0f1e-5783-a029-a893e6ef73b1 | note | RESPONSIBILITY: Site Engineer
e0ec67a9-1ebf-558a-9374-68d344a3dd5d | date | Date Completed:
| checkpoint | 3.3 - CBR/Swell
35ecc076-dfc4-5b26-9115-413cf3897442 | note | FREQUENCY: The initial lot (one day's production or 10,000m2, whichever is lesser). Reduced testing frecuency (every 8 lots) for future lots shall be agreed with the Superintendent
6cc06bdb-0ea7-5b75-94e6-eea0841dd749 | note | ACCEPTANCE CRITERIA: CBR: ≥ 2%, Swell: < 2.5% swells greater than or equal to 2.5% shall be classified as expansive and approved by the Superintendent).
b2043bc3-2ef4-5459-a916-12526223086d | note | REFERENCE DOCUMENTS: VicRoads Spec.
507a1ff0-5a89-56a2-8222-f4db42bbb71c | note | ○ Cl. 204.14
f888f508-dd6f-53c7-a9fa-a6112ea17646 | note | ○ Cl. 204.04(c)
7aca86da-9921-55be-9ec2-564b43e60e69 | note | ○ Table 204.141
ec1b31da-31aa-5ff1-9642-f1f623d2adc7 | note | INSPECTION/TEST METHOD: Site Inspection
68e12ff3-fc1e-59db-9197-2fc10ca64fb2 | note | RECORD OF CONFORMITY: CBR/Swell Test Records
d9588e25-5c76-5dfa-a55a-707194b3c8e9 | note | TP
9eb28479-6b7d-55b2-8bb1-ec910e2d9104 | note | RESPONSIBILITY: Site Engineer
d2b7289e-358d-5f6f-8a0c-026f33442b6e | date | Date Completed:
| checkpoint | 3.4 - Atterberg Limit Tests
ef9e07e2-6594-5047-a247-bf1b4bece040 | note | FREQUENCY: 1 Test per 2 lots (each lot is one day's production or 10,000m2, whichever is lesser) until 3 consecutive lots have achieved specified requirements. Reduced testing frecuency (1 test per every 4 lots) for future lots shall be agreed with the Superintendent
760cef5b-c44a-533e-9d23-8c7fd17def86 | note | ACCEPTANCE CRITERIA: Ensure that soil post-compaction is not classified as silt
fb21e16d-5ea1-5379-a259-e493a9e8d3e1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.14 Table 204.141
83cf9eb1-1892-57e9-8a9d-f7c1a23d7c24 | note | INSPECTION/TEST METHOD: Site Inspection
e7774e3c-abd2-5fcf-9a02-40868bffa366 | note | RECORD OF CONFORMITY: PI Test Records
d2984e4f-ac97-553a-b0ec-068100e9cb21 | note | TP
c2512cdd-c376-55f8-a0aa-fa8bae40e400 | note | RESPONSIBILITY: Site Engineer
b709c862-b41b-5d9f-9652-d13125e87ee2 | date | Date Completed:
| checkpoint | Final Inspection
51a260a0-0367-58b0-9ab8-c64501c1749e | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
7a9f9bfe-f464-583c-91fe-fd9141f8e615 | textbox | Print Name:
8d1466ad-f149-5015-bee6-4109eba6249d | textbox | Position:
e44508ab-2ea8-5410-822f-1baa2287e334 | date | Date:
| checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage |  | 555a15e2-c394-4195-b3b7-2def244e05c1
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
ff7f771d-f196-5e94-89c0-d98ee7bccdc5 | note | FREQUENCY: Prior to commencing works
f1e48edd-754f-5254-98e2-0d81f4bf1295 | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
846dc3d1-3f0d-548b-88ce-ec81a4516cfc | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
3b32932d-65ad-5802-8d9b-f12f832e80a9 | note | METHOD: Visual Inspection
9af47316-48b4-5e62-a789-d9cb5127c919 | note | RECORD: Signed ITP
09237390-a739-5faf-b772-8dade004f4a6 | note | IHP
7c013968-a164-5048-9bf4-0e39e513a1eb | note | RESPONSIBILITY: SWA Project Manager
30b0e11b-b6b1-5617-ae1d-0998085e5877 | date | Date Completed:
| checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
195669b0-1473-5494-a15a-ad3ec8a39b49 | note | FREQUENCY: Approval prior to placement of order
31a43218-3e13-5342-b183-b8ec49858bb2 | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
5700c480-85eb-5218-93a3-706a1f664619 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
dd1103a1-592e-5fa2-a1df-403df97b4a5e | note | METHOD: Review and approval of documentation, Visual inspection
b1ea887b-e0bf-56d9-9b74-1e58a173bb73 | note | RECORD: Signed ITP
87e90362-6a1a-532a-b98e-3458a3a56f01 | note | IHP
ef83053c-2695-53b4-b1cd-2a6e14967af3 | note | RESPONSIBILITY: SWA Project Manager
4eee7202-5202-5afd-a007-1628a7ce0d0f | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
41bc5e39-ebc3-5862-ae41-6030e1febc70 | note | FREQUENCY: Each lot as required
8048936d-695b-5cdd-937b-b38056a05933 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
44adf031-0957-5d70-9ecf-c9728a776289 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
2af47ceb-97b3-5f1e-8621-68cb1577ea32 | note | METHOD: Construction Drawings
4eb6ebae-de34-501e-b1c7-690696fc4379 | note | RECORD: Signed ITP
c1e9b9c5-bfe7-56fc-8315-e88f4513fc5d | note | IHP
0314b7e7-da94-50cc-96a9-00fc9f06bed8 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
b225dc7d-df7d-533f-8ab6-615287710640 | date | Date Completed:
| checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
2253bb94-74fd-544f-b1be-00da20521073 | note | FREQUENCY: Each Lot
d326f21e-5a8e-5f77-b41b-fd03ece16966 | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
91a11db4-0d59-5076-8514-b961491675e5 | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
7af79b61-d7d4-592d-b239-f1ea814f9603 | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
5ccb1813-f18a-572c-ad93-988c6e037d8b | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
d89417c4-1dbd-54c6-a591-3542d3627404 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
6e29027b-260e-5746-8b1e-04e31e593e2a | note | METHOD: Construction Drawings
f646c043-e403-532e-bf52-ac5c9d1595e4 | note | RECORD: Signed ITP
5796186f-716a-5899-afe2-91ea32a06e83 | note | IHP
08433fe9-66f6-596e-b684-be188dd7aa3d | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
f4968ee5-7261-587f-a4c3-61303e64aad8 | date | Date Completed:
| checkpoint | 2.3 - EXCAVATION
eb6a81b1-106b-5f34-acc5-de0ef1dc8f6b | note | FREQUENCY: Each Lot
d37c6318-756c-531a-b22b-17daa23f131a | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
5f543bae-e0ac-5b82-80d5-ad5d368ef555 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
239f74ed-19b8-5b33-a3e6-4f71c526e866 | note | METHOD: On-site Measurement
c5554e91-31f3-535b-a926-8a87cca0db04 | note | RECORD: Signed ITP & Drainage Checklist
a828992a-5878-5fea-a175-7d8ac53ec858 | note | WP
33b10b9d-3efd-5adc-aff9-bbe3d9ff2872 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
d8375f6f-ff33-5a15-b156-fb2952ca0d6e | date | Date Completed:
| checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
25edea32-d970-5686-9c14-edca3b9efbfc | note | FREQUENCY: Each Lot
eb66c574-bb8f-5179-b2c3-6a00493b25af | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
3388aab4-97b7-511f-94a8-f344513ebbc7 | note | ○ 100 mm where D < 1500 mm
7d4a4a5d-71ea-55d7-af83-c565b0b0ecd2 | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
63c746b0-d9c2-53e3-82b2-3869e08c7f7f | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
1efcf702-d6c4-5fc2-b96a-28f08dfcd303 | note | METHOD: Site Inspection
18a937f2-a3e1-5bfd-80bd-dcaa997371f6 | note | RECORD: Signed ITP
cfb493f4-4784-5d48-844f-4e73bfc61023 | note | WP
bfa05788-6b45-5bad-ac25-11dc14849300 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
164537f7-8e27-51d7-84f9-89a18d28af18 | date | Date Completed:
| checkpoint | 2.5 - PLACEMENT OF FILLING
c1c0360c-17a2-5ff3-bc82-281da7c28cc7 | note | FREQUENCY: Each lot as required
bd9a776e-abe2-546a-b401-bb87129b5561 | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
160d80d9-ff77-5f51-b798-2054f70cd708 | note | (I) Culvert Under Area not to be Paved
0520f71c-d372-5b7a-915f-3b14a6e7c495 | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
288ada38-b0ab-508b-a609-231cf2a5eb01 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
c11628d9-8c2f-547c-a3d4-bd3c29584dbd | note | METHOD: Site Inspection
34d13068-7144-586d-9cb4-8dc1e9561164 | note | RECORD: Signed ITP
fa434381-2d8a-5b79-8a37-a56f27a08b6b | note | WP
95987a52-448a-5ad6-ad46-d0a13403a993 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
96f4d2af-c83c-5fea-88d4-62590757ddd1 | date | Date Completed:
| checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
138dc408-69fc-5f5a-8457-3469d3d95724 | note | FREQUENCY: Each lot as required
9a2feca4-3283-5092-bfd0-a4678f117675 | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
4e9109f9-343f-5fbc-9da1-718231d95947 | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
87e7f08a-f96f-5d07-b90d-aa12b5d88b49 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
62e347ab-b426-508c-ae0c-1024c9cc5cfa | note | METHOD: Visual inspection
d7f8dc8d-3819-5d55-8f64-c2b409877f47 | note | RECORD: Signed ITP
8089c255-87cb-5470-a96e-b2c801bafb1d | note | HP/AP
c3e603f4-4c5b-53b7-8f4f-ee08d4470d78 | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
d5bd297f-9113-5a39-b980-f5e0b8f88b12 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
cd3f9388-74bb-5021-a6db-086733703b09 | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
bf175921-e803-564c-8f3d-1bf7d662556d | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
a88ccc67-6170-5043-a577-bb75f2d995aa | note | REFERENCE DOCUMENTS: NIL
c4b9166f-c4a8-5869-8242-4ff325f26b11 | note | METHOD: Visual inspection
8d82beaf-77e0-5b9c-877d-eefb3b017b03 | note | RECORD: Signed ITP
bdadf9cc-a6a1-5f77-81ee-d96f0df941b1 | note | IHP
d4dafda0-0727-562c-994e-7c2f64c04999 | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
aebf675d-db93-5925-94f6-6aaaedf55e39 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
38f7f3fd-186b-5a94-9d3c-d46cfddc8722 | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
39406688-46e7-5934-88dd-11172fada3d6 | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
fc9b0346-7df2-5e7c-8e79-36472f115322 | note | (b) Backﬁll
84515d71-0f2e-55eb-9c0a-e16782ff187a | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
73d39840-e6d7-5c0b-8fd4-8bafe562197f | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
396e2c2c-1b7b-578c-bd19-8bc8eb1b9057 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
b4b94626-f9df-5024-bf29-1e39dbd6c81e | note | METHOD: Lab Test
74d128c5-1452-5f90-beee-94ceb44c230b | note | RECORD: Signed ITP
3782413a-7cf5-5707-89ed-a514e9b0186e | note | IHP
020dfa56-df5b-5eee-81e0-d26e3b402d1a | note | RESPONSIBILITY: SWA Project Manager
1492241a-2e16-51e4-bc88-241b9eba531f | date | Date Completed:
| checkpoint | Final Inspection
bd0e6189-8169-5e75-838d-b3124d3c7a13 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
0db37f49-dd06-5ab4-9403-1ca4a21edb57 | textbox | Print Name:
f9cbb62d-571f-5bfd-bb23-97eeb63cd4a6 | textbox | Position:
52ce646b-4fd7-5d88-bf27-a1d49b30da0a | date | Date:
| signoff | Sign ITP
| checklist | ITP-005 - Crushed Rock Class 3 (Lot2) | itp | ITP-005 - Crushed Rock Class 3 (Lot2) |  | d7cf7754-dc3b-4383-9851-c5cbf6e51e96
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Crushed Rock Mix design
5df8fd2b-804a-5fdd-8798-137996ecd16e | note | FREQUENCY: Prior to Commencing Work
26d6a5d7-b0ac-533c-a1d1-0390110aca5f | note | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
4f5f962d-aff8-59ca-aef4-e249cc0e63fd | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
858c507c-252b-5c23-9516-fdfe8410b5e6 | note | INSPECTION/TEST METHOD: Document Review
6bfdcc6b-2464-5c87-bb74-1f06a79b4c99 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
a5910a80-6c56-53d9-8fc8-7ac2973807e7 | note | HP*
b6bdf2f3-8562-5905-ad14-114372514d29 | note | RESPONSIBILITY: Project Engineer
e2d958e4-8678-53bc-ae43-b9d83c152969 | date | Date Completed:
| section | 2 - Placing Fill
| checkpoint | 2.1 - Transverse Joints
d433567e-491d-5dac-be39-e738c9e2d543 | note | FREQUENCY: Check prior to placing material
9688c7e8-5ebd-5582-94b3-cf484f8195c2 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
bf1c0df8-1aa4-5355-8bc2-6f9432fc071c | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
a440c872-391c-5f5f-b5dd-92bd4c86b79b | note | INSPECTION/TEST METHOD: Site Inspection
b694529d-347f-53a4-b87e-64b8228a16cc | note | RECORD OF CONFORMITY: Signed ITP
3c671a9b-d1dc-53a4-876b-9a6293e8b4a5 | note | IP
51807ee2-3c30-5313-a27d-9b3daced151c | note | RESPONSIBILITY: Project Engineer
4b617b14-17d3-550b-8f9b-b691228e23f8 | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
7bb272b0-0d94-5b41-9f0a-867a6169eeab | note | FREQUENCY: Check prior to placing material
e5841c53-ed67-56a7-9657-6d73b5f8de07 | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
4e51a026-3eee-5552-a6f7-fc39b55dfe46 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
4549121c-430c-51ff-b310-05bceec742a1 | note | INSPECTION/TEST METHOD: Site Inspection
ccb618b0-478f-5130-a2c6-d98627b66f93 | note | RECORD OF CONFORMITY: Signed ITP
8de080c6-3fa7-53cb-996b-8e567b7f9170 | note | IP
bc7b38eb-d4c2-5478-9a23-f64060ff6f94 | note | RESPONSIBILITY: Project Engineer
2b484de9-ac0a-512b-b933-d4c8a4b99344 | date | Date Completed:
| checkpoint | 2.3 - Lot Size
8bc13945-fd64-5872-9b13-f1d5b2ae0ef9 | note | FREQUENCY: Check prior to placing material
64ebccbb-df2e-57b9-9bf5-41cabbe96a65 | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
4ed09f60-f49c-5149-82cb-7a73489bd6fa | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
6f3b6669-945f-56bf-b0f5-25fdfaa023e0 | note | INSPECTION/TEST METHOD: Site Inspection
6366df16-9d1e-53cd-b170-516d419db823 | note | RECORD OF CONFORMITY: Signed ITP
3ce576ef-ca24-57d4-97a9-c537ab92fce9 | note | IP
314d79b6-5ab1-5062-9c05-d42eaf7ac1a7 | note | RESPONSIBILITY: Project Engineer
db643df3-e130-5724-8f2b-2a8824a151ef | date | Date Completed:
| checkpoint | 2.4 - Proof Roll
9a0b9fa2-f1a0-51ed-8d70-1aa7f50fbb13 | note | FREQUENCY: After placing material
ddeab0ea-ff5b-5602-adb1-3025ac23a16c | note | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
b898c241-973c-5691-a74c-3474e1e49fc7 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
7d734fcc-77c4-53fe-b3f1-096837e540da | note | INSPECTION/TEST METHOD: Site Inspection
b1d15bae-60cd-5336-bea1-57aa1e818af1 | note | RECORD OF CONFORMITY: Signed ITP
77117a51-edc1-5612-bd43-810db7ce75cf | note | WP
c9d30983-dfc4-5f39-bd43-dc69fca63807 | note | RESPONSIBILITY: Project Engineer & Superintendent
222aa8a6-f32b-545e-a39f-483436c19a69 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
d3d4576a-eb68-55fd-842d-f24c80d556fe | note | FREQUENCY: Prior to Testing
4f0e032d-c2af-5483-8acf-2addd96bbf9c | note | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
c939f9e8-560d-5178-8989-b0fe8b9b602e | note | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
63b04594-85b2-53b8-8b0d-dad4456cb43e | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
260e08a8-5768-50fb-ae68-c27971a45f4b | note | ○ VicRoads Spec.
63aee9dc-1451-5c14-bfb6-4bad1729d9ce | note | ○ Cl.304.08 (a)
ef73c914-0d0f-5ee8-b03f-5cab3f259055 | note | ○ Cl.304.11 (b)
4d0c2860-43dd-5669-861b-ff443fab7f70 | note | ○ Cl.304.11 (c)(i)
0069e047-8df9-532f-912b-1c2d8cedc9d2 | note | ○ Table 304.111
26b52ff7-ec44-5cab-b2ba-5f1d578763e6 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
f53bfdb6-5318-5d97-a7a8-695f9706e786 | note | RECORD OF CONFORMITY: Signed ITP
4f480eeb-324a-504b-9e86-bff734a32362 | note | IP
ee65661a-a8a8-50df-b49b-56e812630ed4 | note | RESPONSIBILITY: Project Engineer
3a6431a9-8094-5a63-a85d-9ab25d4d9cbb | date | Date Completed:
| checkpoint | 3.2 - Modified Compactive Effort
32dbe510-6c73-5168-914a-22e24a3ed8ab | note | FREQUENCY: As per 3.1
7f5b3425-b5fd-5d1c-97df-bf17b4b39bcf | note | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 97.0% (Scale B) 1 per every lot
f58dfcac-1dc8-5b87-bb20-1efc50710e10 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
6294bf8b-c9ad-53e3-ab30-29f4db2ba233 | note | INSPECTION/TEST METHOD: Site Inspection
0bd4618e-8363-5ef5-843d-5ceedf151202 | note | RECORD OF CONFORMITY: Test Records
8e935d89-8389-5b3c-89d1-92a9aa716e82 | note | TP
df786c3e-9b92-520d-86e2-ed489ff6ac31 | note | RESPONSIBILITY: Project Engineer
9a648157-18a8-527b-8bd7-62bb5e51d189 | date | Date Completed:
| checkpoint | 3.3 - Survey Level Conformity
9f76a73b-ec77-5401-ab27-fce7452a1806 | note | FREQUENCY: At completion
38e0bd54-a70e-5a40-ba9b-cabef1c8cb0b | note | ACCEPTANCE CRITERIA: Scale B:
d50b4def-6454-5adc-b3d2-e4dbbf57027b | note | ○ Minimum number of measurements per lot: 40 For Upper
689b0c95-7b08-5a7c-aa86-b20ecfee60dd | note | ○ Upper Subbase: Mean + 6mm to - 12mm with a maximum Standard Deviation of 8mm
cad12e62-4647-523a-9cf5-c667aaec4f26 | note | ○ Lower Subbase: Mean +8mm to -16mm with a maximum Standard Deviation of 10mm.
17fe9cb6-7b73-5669-8d7c-eddc6ac3c019 | note | ○ Base: Mean ± 8mm with a maximum Standard Deviation of 8mm.
d1b84624-52fd-5b5e-827d-38aeaca0b5e1 | note | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
6c327eba-1aa6-5bbb-bb91-61eba973e57a | note | INSPECTION/TEST METHOD: Site Inspection
6a97fc61-5224-5ae9-b53e-20f275c8c9d8 | note | RECORD OF CONFORMITY: Test Records
4aa6a648-0463-57b9-a2aa-6846a4dc67d1 | note | TP
debe3581-02cd-55bf-8e1c-b0dc75a5700a | note | RESPONSIBILITY: Project Engineer
06caa7b6-001b-57a0-9f6b-1f515ba05d7b | date | Date Completed:
| checkpoint | Final Inspection
c4af552d-b9a1-5ced-ac96-aa333bd29bbd | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
31263faf-d6ed-5aea-80a2-a4cfb7cdc551 | textbox | Print Name:
26ec9255-13dd-55ee-9a72-64d6906a6102 | textbox | Position:
215f280d-4183-5111-9d27-1521c05eba30 | date | Date:
| checklist | ITP-005 - Flexible Pavement Construction | itp | ITP-005 - Flexible Pavement Construction |  | 8e95ad02-824a-4de1-905c-ed068ecc0ebf
| section | 1 - Preliminary Works
| checkpoint | 1.1 - SET OUT OF WORKS
21a438d3-f799-5869-9ca0-65c3b2e95d5d | note | FREQUENCY: Each lot as required
1d06acbf-a00b-5e03-9db8-c71bc225cc9b | note | ACCEPTANCE CRITERIA: Ensure relevant construction drawing are being used to determine set-out of works.
e7ec4598-5998-59f4-a6da-3f7c62b4d1c4 | note | ○ Ensure all survey pegs are aligned max 40m apart and the oﬀset distances and heights are in accordance with relevant drawings
472ba5b7-b2fb-5b14-afce-13d6e376b05d | note | ○ Refence checking to be conducted with string lines
56cd3848-d046-5659-9cff-3b5220170d1e | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
3c2d0e5c-ad3e-51fb-98da-f6b89fada6e6 | note | METHOD: Survey set-out
46d63712-60bf-5ace-98dd-1bb84e6dab98 | note | RECORD: Signed ITP
21f50034-22b9-5a3f-a7a2-09ceb5f4bd7e | note | SCP
703fbd8e-ae1f-50f0-8dd9-fd0f1075f13b | note | RESPONSIBILITY: SWA Project Manager
2c71cf9a-452c-5dba-96a4-f047f6c8fbae | date | Date Completed:
| checkpoint | 1.2 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
e0c1e4c3-01ae-5a28-a97c-457c30e6c254 | note | FREQUENCY: Prior to commencing any activity
83cee339-0a84-599d-96a0-5475fb179165 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number speciﬁed in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
77b93b7c-0603-5666-8f86-2d17e5e3bf3e | note | REFERENCE DOCUMENTS: Vicroads std sec 204.03
bb1ab119-fea3-5851-ae1a-f1ed4b3d8e0d | note | METHOD: Survey Report
f870a3d7-5a52-5e57-a3ad-fb8808c4ba5c | note | RECORD: Signed ITP
9a11a0fc-62d5-5c21-baed-7d41c3cfb678 | note | IHP
d54a04d6-e5f9-5007-a6a1-5f5743055cd1 | note | RESPONSIBILITY: SWA Project Manager
103858ec-6146-5004-8f4e-cc047cefe7fe | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (a) General
4f049f58-666a-5046-a5a3-8c374b9a2092 | note | FREQUENCY: Each lot as required
890cc7f0-2c5e-5912-a0df-e7880170454d | note | ACCEPTANCE CRITERIA: Material during compaction shall have a moisture content of not less than 85% of optimum. After completion of compaction of a layer, the moisture content of the material in the layer shall be maintained at a moisture content of not less than 85% of optimum until test rolling has been completed.
33ba4406-6891-5a3e-be9b-aeb2dd202059 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
45aafbde-c218-53c8-ba9f-ec8067913673 | note | METHOD: Visual & Laboratory Report
21091960-9352-507b-9d8e-8277980a5e20 | note | RECORD: Signed ITP
6b7d5eae-9cf2-575f-ad7d-b90f11fad58e | note | IHP/AP
80f3b5fd-1d3f-5c4a-af15-dbc902752ec9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
5b1c301b-eca4-5af8-918b-90a5383de1df | date | Date Completed:
| checkpoint | 2.2 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION (b) Material of Nominal Size 40 mm or Less
f0d761e5-1cf1-5154-9067-05b632345722 | note | FREQUENCY: Each Lot
73f4bc54-68aa-56d1-8e9f-b58949ad10f5 | note | ACCEPTANCE CRITERIA: The calculation of density ratio shall be based on tests performed using Modiﬁed compactive eﬀort. The work shall be assessed for compliance with Scale B requirements being not less than 97%. See table 304.081.
58ca41af-e55f-53c8-ac78-0969bd212cab | note | ○ For work to be tested for compliance with Scale B requirements, the number of tests per lot shall be six. See table 304.121.
7298ed6a-a8d2-5300-ad8c-a877189c71ff | note | ○ The maximum thickness of any pavement base layer shall not exceed 150 mm and the maximum thickness of any subbase layer shall not exceed 200 mm.
673b97e8-f973-55cc-a012-7eff9d3dd982 | note | ○ The minimum thickness of any pavement layer shall be 4 times the nominal size of the material.
2d522158-75e2-5ada-b75c-c6d64e3633b6 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08
5a2a1a0f-8eb3-5562-985f-a06d6a3bd2ca | note | METHOD: Laboratory Test Report
38b38ded-4382-55a9-8321-91cce0bafc89 | note | RECORD: Signed ITP
fc050c64-6bbd-5fcc-a1d3-60db57ebc55a | note | IHP/IP/AP
aa41352b-a014-580f-a92f-f3367cc11c4d | note | RESPONSIBILITY: SWA Project Manager/SWA Site supervisor/RRV Superintendent
091e976c-11b3-5010-bec3-26cdfc39bcbf | date | Date Completed:
| checkpoint | 2.3 - TEST ROLL PAVEMENT LAYER
cf26d6d1-0a57-51a5-8998-6140e6be89af | note | FREQUENCY: Each Lot
7021f6a6-d397-5d7a-891b-d587e34330a3 | note | ACCEPTANCE CRITERIA: The Contractor shall not commence placing any ﬁll on the prepared areas until the area has been reviewed by the Superintendent. The Contractor shall provide for the Superintendent to be present during all test rolling.
b77690bb-91cb-57fc-89d4-7c8858b0d4ec | note | REFERENCE DOCUMENTS: VcRoads Std Specs 173.03 & 204.12
ddebae22-3f6e-5344-8a8a-847524cc851a | note | METHOD: Proof roll
5502962f-5656-5b8c-b4cc-be0affcca612 | note | RECORD: Signed ITP & Test Report
1d60d458-0615-5369-8e39-1fa82e4810bb | note | HP/AP
fb4f3192-b1fb-5ea8-99b9-42ab1d8acccb | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
35502628-900b-5e3a-81f1-cd8fab79ff54 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - CONFORMITY WITH DRAWINGS - Random Level Assessment - Scale B Surface Level Requirements
dd9451ef-7628-5777-b511-8406baf71479 | note | FREQUENCY: Each Lot
b5517203-2972-5415-a154-7513e172b6f0 | note | ACCEPTANCE CRITERIA: The surface level of the pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet either Scale B requirements as speciﬁed in Clause 304.12.
93744061-4d1c-5633-81ff-e0fcad3646da | note | ○ Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
7ca6e396-4048-5fbb-a817-d7b9b6aec8eb | note | ○ Each level measurement shall be taken at random locations over the area of the lot in accordance with the VicRoads Test Method and the number of measurements taken within each lot shall not be less than the number speciﬁed in Table 304.061. Surface Level Tolerance as per Table 304.062
8e8eaa68-3058-5d05-bab8-40a44dbc94ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 304.06
1bb3836a-8681-55de-961b-4ea84c3730ab | note | METHOD: Survey report
c9b54e4d-138a-5902-a65d-40167a8a0199 | note | RECORD: Signed ITP
17e955f5-a405-5b78-9b63-88db0449b409 | note | IHP/WP
0ee07f49-db61-5573-aa0e-f85d91236efa | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0e76f698-81d7-554d-acc6-0a5da44178f2 | date | Date Completed:
| checkpoint | Final Inspection
7ac89bf9-222c-5771-bff6-eadc91bf12d7 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations
726d8fff-32d0-5a53-897e-89e54955aa0a | textbox | Print Name:
9fd2b4b9-a3d2-5ac2-ae5f-5981ed4b8a07 | textbox | Position:
2b92b7c0-85c8-53f5-8ecf-7a7cc9248cd9 | date | Date:
| signoff | Sign ITP
| checklist | ITP-006 - Kerb & Channel | itp | ITP-006 - Kerb & Channel |  | a4d29837-c0f6-4b8e-8931-9cd929c359d9
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
406918ce-3cdc-5bf1-b99b-1cc0ce3670a6 | note | FREQUENCY: Prior to commencing any activity
e011307f-87f3-5b57-afc6-849b34cae3d6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
be8c534a-b509-5771-ac62-7b511d66b998 | note | – using the correct and complete set of drawings
c69f4138-b3f7-51db-b97d-ccc326af37c6 | note | – all drawings are the latest revision
822ffbea-10b5-5f82-8ab0-f8c159005040 | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
34936628-eb58-5204-b959-a44867dbf91e | note | METHOD: Drawing Register
79444e64-5635-591e-91f8-b477547447c6 | note | RECORD: Signed ITP
d9bd5ac5-3489-5b71-9430-2ce1611cfa4d | note | IHP
add5cad4-344d-5ff9-9b01-f3492d8fa430 | note | RESPONSIBILITY: Site Supervisor
f8ea5604-b840-516b-b9b6-3986295a792a | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
f1ed7616-4da5-594e-89ed-b752ad56207f | note | FREQUENCY: Prior to commencing any activity
897e971e-0b58-53da-ba2b-45c29e989652 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
a01e5185-92e6-5d8d-a6f3-c9eea4ec684c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c3a498a8-cfc9-5cf9-91bd-4bdad6bfba9d | note | METHOD: Visual Inspection
47148980-a363-51fc-aec0-5235296d4922 | note | RECORD: Signed ITP
bc3fe039-08d6-5b5e-a8c2-555746084963 | note | IP
e13d9d0a-b15d-5f8b-bd51-dc48258f1cb3 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
2a2f6067-9e00-575e-b431-248df43cc440 | date | Date Completed:
| checkpoint | 1.3 - Setting Out
f103293e-2257-5261-bc5c-72da2d09ed65 | note | FREQUENCY: Prior to commencing any activity
2fed43cc-312a-53e7-8a8e-f9ece4210455 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
31f53ffb-c188-501b-9f47-21af8c4b9fd6 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
1688d011-d595-5d40-bfd1-813a57c0c5d8 | note | METHOD: Survey Setout
f132a59f-8e2b-5db4-ac00-1a50c25e51f6 | note | RECORD: Signed ITP
abe4a46c-5cab-59fd-919b-5f5eb81e9ca2 | note | IP
cf7c601a-6eea-58c4-92bf-cbcbc7a6625c | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
941f7e22-16ae-5d20-ab1b-03abed20d5b2 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation
fc4b5e5e-7efc-5785-b195-266e3c5e4d0b | note | FREQUENCY: Check prior to placing material
391c45c5-f8e1-5129-a718-7cde5ad901d0 | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
cd4e7867-48ed-52ef-8f01-7af0c0fe7913 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
395c6ce3-2753-51a3-93ac-2c98f38853b7 | note | METHOD: Survey/Site Inspection
b6a9d6b7-6aa3-5b2d-9e12-f998914f0c63 | note | RECORD: Signed ITP
3851b852-2945-58a2-b5e1-49e85c93b11c | note | IP
2748247b-269e-5276-8976-c1df5a2cb9ee | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
275a27df-78e2-54bb-beba-bccd1405ef56 | date | Date Completed:
| checkpoint | 2.2 - Subgrade Inspection
7419fe17-5292-5f9b-af6e-6ab9f3ed0a53 | note | FREQUENCY: Check prior to placing material
b448cca9-b6ce-5da8-b0e3-7d05f86ef3be | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
0728161c-0c6a-5ff6-b941-64cfbc2b7da1 | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
f39ed3b9-079b-58c8-9755-6fb9aba9ef11 | note | METHOD: Visual Inspection
e468e85e-66dc-585b-991d-a6061a47cd52 | note | RECORD: Signed ITP
68dbdd3b-1e7b-591b-9528-31a809df4c41 | note | IP
ba0308c4-4a24-5f91-9915-59aa7615f963 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
86650319-7ccf-5b27-a073-c105b613572c | date | Date Completed:
| checkpoint | 2.3 - Bedding Preparation
e59e6c97-83db-5648-ac91-397818f406a7 | note | FREQUENCY: Each lot as required
7ba6e700-5771-54d0-8877-7f24e9b6b106 | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
3f13d882-6cd5-5b8c-977a-a1143ab675b9 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
41f35c2c-a05f-520f-a7ec-6ec733bf708f | note | METHOD: Site Inspection
fbe9548a-bbbd-542c-8d90-54fc5c63104e | note | RECORD: Signed ITP
ddd43e43-3217-5d2f-b08d-63fe96bf5a7a | note | IP
fdc53d79-8c28-5630-813c-dcc3012d51a1 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
55becea8-8fc6-5e8f-9292-936708566548 | date | Date Completed:
| checkpoint | 2.4 - Kerb Concrete Mixture/Strength
1a135d14-44b7-59ab-abdf-e5d70cf31fbd | note | FREQUENCY: Each lot as required
3f26fb6f-256e-598e-b9e6-32f4e8b8994e | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
7b5cdbee-30f5-5e93-891b-da9cfc6152a2 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
65ecbc29-e2f8-5f0c-9b01-3b2f4a5cf809 | note | METHOD: Delivery Dockets
257a7f1c-f457-59cb-8c77-b6d58c927c89 | note | RECORD: Signed ITP
87154659-50e1-5da3-a1fe-e622c69d60d0 | note | IP
3593b420-23e2-5fba-aa66-ea5339877f43 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
0655ebfd-b77c-57fd-9155-b251f8b36dbe | date | Date Completed:
| checkpoint | 2.5 - Tolerances on Line, Level & Shape
8e4afeb6-97d5-5635-ad08-b6d52ddb3959 | note | FREQUENCY: Each lot as required
d8372740-cf9d-51c8-aef2-29373cca4e95 | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
9a5ffbb5-5164-51dd-b467-84c02f5bad84 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
6158c054-13b7-53b6-8521-4c14420bbc7b | note | METHOD: Visual Inspection
ba02012e-f3de-5cee-947a-ccc94dab95a8 | note | RECORD: Signed ITP
8bc8d6a9-f2df-5f9f-9f39-9ee3ee69107b | note | IHP
7d102f00-ae1b-5335-bdd7-2293953dcd21 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
fbf4435c-3c54-5df9-91a3-a82a670999a0 | date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel Finish
152a4c81-2200-58c7-8846-475a98e97122 | note | FREQUENCY: Each lot as required
710f7d21-3cbf-56cd-8d40-0e5b7b49ca9e | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
efff80fd-0242-5e39-80b8-c9f8160181d1 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
d850c6d3-a71c-5054-84ea-71aeafd4b346 | note | METHOD: Visual Inspection
76ab2fe7-1bdf-5321-b5f0-3284d7615a29 | note | RECORD: Signed ITP
53219070-0f0e-5f92-92bc-22136a46688c | note | IHP
57dd1aee-e3f5-572b-a8dc-2d732d48fef2 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
394a1dec-5c62-5a2c-8294-8922811baf6e | date | Date Completed:
| checkpoint | 2.7 - Kerb Backﬁll
c74426ba-4f22-5b05-9f10-30fcfc2e71d4 | note | FREQUENCY: Each lot as required
7ca14e0d-b321-5913-b323-51a9714edbf0 | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
53f8edff-f0ea-5e80-bed1-59c7560088b6 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
7bc19819-ca2e-5e79-894d-e29bd539afa5 | note | METHOD: Visual Inspection
080fb305-c66f-556d-a03a-33861058893c | note | RECORD: Signed ITP
2d9a91b8-51ff-5edb-b545-a8456e4f6752 | note | IHP
df133037-dd9a-5711-96ad-bf48ac9a8097 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
6bb7c0a6-e316-5ac0-94bc-a436be1504c3 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction Testing
b307cbbb-e0f3-54c8-a277-335031719f5e | note | FREQUENCY: Each lot as required
2f6160d1-c830-5bc1-b0c3-4f14ddd3bb97 | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
b9b69829-6d11-5e75-9067-7720b2b6557b | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
6adc21e0-8da3-58ab-aefd-8685be89e42b | note | METHOD: Test Point
a92a55bc-a934-53b1-90dd-41b857704a5e | note | RECORD: Signed ITP
55bcf49e-48ab-5bbe-9874-4ef19631138f | note | TP/HP/AP
c3d35af1-f2f2-529e-bd5e-850d1d7fa0be | note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
ccbb13b1-06f1-5589-940d-1c78307f3d56 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
3f41a8b5-9b84-545e-a8f7-47afadee5d0b | note | FREQUENCY: Each lot as required
64bce072-3844-521b-a3a0-5dd2b3a16ba7 | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
e6dbae4c-ba22-505f-9712-e8ae967f620b | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
c07a8be1-b11d-51db-9679-f6b7058ac38c | note | METHOD: Survey Report
a73228ac-bee6-5e95-a53a-30015f0e35a9 | note | RECORD: Signed ITP & Test Reports
e0effab5-22c2-5331-abf3-391f5ddfa888 | note | TP/HP/AP
fb96dc8c-7e23-5fe2-9ae0-dfdbcf9b46db | note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
bc9f3d1f-b1b4-541c-8f87-805c1d330bcc | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
8138864d-4a3b-5bda-986f-6aa83420317b | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
873f6803-4544-5ef3-a4f4-c6a4310767ef | textbox | Print Name:
db859f22-cc9e-5287-af0c-cf55b244179c | textbox | Position:
751dba85-2a55-5a4e-a2b7-ea4dee9eefbc | date | Date:
| signoff | Sign ITP
| checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt |  | 8a26ec7b-47e9-40ba-bcf0-db20d12d50e2
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Site Inspection and Base Conditions
d688b9be-5b87-57c4-9401-8e4ee3044ced | note | FREQUENCY: Prior to commencing paving.
77fe2bc8-1442-5be1-96e4-22b2b5e30898 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
5db3395a-5a33-563d-af34-17c90380b207 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
9f664117-1f46-5641-8a55-271a2941339d | note | METHOD: Visual Inspection
f6b9ce53-7b0e-55f5-bf58-2190378470f2 | note | RECORD: Signed ITP
3149520a-eadf-5e65-84c7-25d8c44897df | note | WP
62204960-fdca-5390-8706-6d46b6c16a02 | note | RESPONSIBILITY: Site supervisor
7a542c34-35be-501d-bef9-f7c96b21f6bf | date | Date Completed:
| checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
0a2ecb52-16f0-520a-a241-548c9b5501b7 | note | FREQUENCY: Prior to commencing paving.
58b668e8-a984-5f99-847e-f7f7849aa2ec | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
21a4db70-16bd-5874-b125-c5d207382d63 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
e74390b4-ae7a-5952-85e9-f515b4722f5a | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c975c47b-f504-5bc5-af6d-5fc2f3139d57 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
b5ace85e-d10c-5e83-8616-5240a88f8e00 | note | METHOD: Calibrated thermometer
05794ef6-1210-5f5e-988c-9e216f5d1c6e | note | RECORD: Signed ITP
1fa6e8b4-45b7-5c03-9bd0-ad631acac909 | note | IP
b320e086-223b-5c4d-a615-12e62920d7f4 | note | RESPONSIBILITY: Project Engineer/Site supervisor
cc06b2f3-d3c5-5b1b-8572-83b09a446a34 | date | Date Completed:
| checkpoint | 1.3 - Surface Preparation
4e54f265-bace-5007-9924-59ff70e7ba9d | note | FREQUENCY: Prior to commencing paving.
3ca451bd-60bc-5aa8-82ff-2fb8f95d4ae6 | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
d7bca43d-b98f-5a72-b645-801e4af922e9 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
b7150c70-7401-5f10-a71c-de2898c7e3a7 | note | METHOD: Sweep Clean and Inspect
6deba588-d573-5826-8f7d-5cf57d2a7308 | note | RECORD: Signed ITP
4f8547f4-8f39-585e-846f-eb93a72dee5f | note | WP
97ac1dbb-d171-51cc-b773-9def1a760570 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
05dbeb64-1a43-5b0f-ab97-a2a9299cfea7 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Application of Tack Coat
2bc89cc0-05fd-5d39-8173-cf3ac73aea87 | note | FREQUENCY: Prior to commencing paving
984a04d0-36e7-50cd-8190-d10f5be69ef0 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
b126fdc9-f32a-5128-a548-41a431071e21 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
a513f9de-8a20-5afb-8cdb-fe7b7bf868e4 | note | METHOD: Visual Inspection & photo evidence
819b6f4c-677c-5939-bf3e-385c4c9c3ddf | note | RECORD: Signed ITP/Spray Record
085a77d8-e12c-5d16-97d2-38661c7775e2 | note | WP
db648bc6-04a9-5f5c-ac17-0872310e84da | note | RESPONSIBILITY: Project Engineer/Site Supervisor
9524c87e-3988-520f-8b62-836e7879ac95 | date | Date Completed:
| checkpoint | 2.2 - Planned Joints
ba46facf-a072-5cc6-93b1-8ddeca9a627d | note | FREQUENCY: Prior to commencing paving
22cc8efb-d9e3-5cfa-9255-9ae523d70f8a | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
ab9a16a0-8110-5e82-9f33-bbb12b923d13 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
95996cce-9371-5937-9658-016a41201d7a | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
3d58eaf1-61e9-5cc6-b381-2f3448a26604 | note | RECORD: Signed ITP/Job Sheet
00d39b2f-424d-567f-bfa5-6a0decd08391 | note | WP
9ec50226-d017-515d-846c-a3e479e4b999 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
dbb35a21-e66d-5201-a4d2-1dff79c94fad | date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
cca105be-6bd6-5600-ac6f-65bcc11a3079 | note | FREQUENCY: Prior to commencing Paving
683db6f9-07e7-55cd-8bb3-bdaa06b97f49 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
068e27e3-051d-572c-8924-d5b1ea8f3f4a | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
b511a1d6-2391-58b3-a195-d66345ed525d | note | METHOD: Visual Inspection
53a5f474-6809-567f-bcda-a795f9214c82 | note | RECORD: Signed ITP
63aeb9c7-da48-5ccd-8879-363cd0e982d5 | note | HP
a51be06b-60e3-5c7c-91e1-0b8ed01b9320 | note | RESPONSIBILITY: SWA Project Engineer
2feae5b8-a61c-5937-9a35-e1a01f92a36d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Delivery of Mix
35c6435e-3596-510a-ab77-9fe4f8e7b182 | note | FREQUENCY: Each Load
8dac07ce-4df2-5efe-83be-bf1ba1081dc2 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
9ef15b20-6680-5bdb-9cfb-9fa375011ac0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
ed145bdc-d3cd-59b4-a60d-32e90a0175ef | note | METHOD: Visual Inspection & Delivery Docket
31350090-570c-5cb2-8a93-d05f68c8ecf7 | note | RECORD: Signed ITP & Production Dockets
01d78e9e-b9b9-5b71-bbd4-212c346d7d27 | note | WP
bec095f5-a796-55ca-b444-42f5b4d59bea | note | RESPONSIBILITY: Project Engineer/Site Supervisor
19cc829a-5c9e-5a21-8524-84978ad9bf59 | date | Date Completed:
| checkpoint | 2.5 - Traceability
82c1addb-3683-5b4c-93c1-01ea48344802 | note | FREQUENCY: Each Load
e1f1bbfe-0d5f-5c7f-83bc-c2f11703b555 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
7b7f2e40-84a3-555e-8ae0-489a7049337d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
ee9c3476-6420-55a6-9993-a2d1de3442f4 | note | METHOD: Project Engineer/Site Supervisor
23c11b58-21bc-500e-a1c6-850486660080 | note | RECORD: Signed ITP & Traceability
e70ee5c4-d130-52b6-a5d5-7af94576eccc | note | IP
9adf5571-8d0c-5fdf-b3ae-6535c2707fa5 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
44a30b4e-f09a-5f2b-bfae-62dff848ba35 | date | Date Completed:
| checkpoint | 2.6 - Layer Thickness and Level Control
ff96ea57-e6b4-5e2f-b266-c33d5fc970c0 | note | FREQUENCY: Regularly during paving
b8b4c9e2-2100-5327-a3a9-c2ab0e694095 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
5a70b30b-e11f-5018-bb87-4345416cb836 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
08d03c8b-a82b-5ccf-8737-a66353e78fcb | note | METHOD: Dips, string line, measurements oﬀ kerb
ad93486a-b761-59b7-8a32-3da121a65202 | note | RECORD: Signed ITP & Traceability
73b78505-8b06-529d-b7e6-0c4856c4aca5 | note | WP
34ac231a-8cb8-5f66-a3c2-d0bf25788dad | note | RESPONSIBILITY: Project Engineer/Site Supervisor
33018af0-6960-5889-8c7c-7c828282672d | date | Date Completed:
| checkpoint | 2.7 - Paver Stoppages
002feb29-adaf-5658-ae69-f5df46cafaf1 | note | FREQUENCY: If paver stops
3e721a1b-0f43-56cf-805a-523cb54c3fba | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
942ba5fa-42f6-5275-9f04-0f4ea0d094da | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
a00ce693-9716-5d75-b53b-2000b9676a84 | note | ○ 40km/h – 20-1
d42553af-6974-50c2-90d8-9801971de2bf | note | ○ 60km/h – 30-1
cac18e2c-74bf-5902-8668-cfd79548b07f | note | ○ 80km/h – 40-1
b5595fd4-381d-5048-8c44-8b281365a04f | note | ○ >80km/h – 50-1
81117fe2-cc8b-5f28-91ac-5bc494815aca | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
b2bc6f2f-ff8b-514c-8300-32611bfa4ad0 | note | METHOD: Thermometer
e73f5314-0277-5e7e-b7d9-f0cf640711b4 | note | RECORD: Signed ITP & Traceability
8a42da44-1238-560a-ad9a-d42ac4ae2cb9 | note | WP
1e0101a2-201b-53fd-bb91-8a1a1ca37140 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8ccf48ab-72e6-5fba-bf7d-c5a8ec70a402 | date | Date Completed:
| checkpoint | 2.8 - Surface Finish of Wearing Course
4dfcca4d-6cd9-5059-96c5-7f49ee738a46 | note | FREQUENCY: During paving and after ﬁnal roll
69febd5b-5b7e-5aaa-8709-463fd2426c24 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
150e0736-0b04-54a4-8e7a-7931c1c79df7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
df87ffeb-c1aa-56b5-83c7-41217ac9ccdf | note | METHOD: Visual Inspection
9fea420f-2c0a-5f15-ba5e-3302a9a34645 | note | RECORD: Signed ITP & Traceability
984f1f0d-073b-5547-9c56-1bad2e6177d0 | note | WP
29c20c6b-d274-509f-bafb-d926f20bdb16 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
ad523783-fc01-5bf0-a6ee-655ee901c821 | date | Date Completed:
| checkpoint | 2.9 - Kerb and Channel
07ca60f3-ee52-57e6-b0dd-5cb66e9cc014 | note | FREQUENCY: During paving and after ﬁnal roll
8645ebc8-f881-5f69-8a08-46d7a3097f08 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
8dd06cfd-fb12-53a9-8ad4-f0e267ff66ff | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
767fd6b1-2d01-5b59-84fe-65c38d519d41 | note | METHOD: Visual Inspection & Measurement
ccbd261d-642c-5fbb-887f-4c9d8bd42bbb | note | RECORD: Signed ITP & Traceability
d7fce216-ea7a-573d-b611-c9e33c6889d4 | note | WP
accfc560-ed8b-54d2-a681-96c53a9c120b | note | RESPONSIBILITY: Project Engineer/Site Supervisor
8429c875-5a5e-5cce-ae99-b0f6f2a50ad8 | date | Date Completed:
| checkpoint | 2.10 - Alignment of layers not placed against concrete edge
627dfba2-fac7-556e-9e93-8665eddfa9ab | note | FREQUENCY: During paving and at completion of work
9f42c967-3d8b-50e2-b03a-b701b4fbb12b | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
cb25d7fe-dae1-5e4a-946c-f9075c8adc68 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
93f531db-bdf6-5972-91cb-a8bcc1019e4c | note | METHOD: Alignment as marked by Surveyor and measured
263cd0dd-a3b4-55bc-b476-0f0d7811254b | note | RECORD: Survey Report
7ad599ca-07d1-5ee5-9751-8cf7ecdc9b38 | note | SCP
7db19754-8f98-5056-befa-eb8448c94030 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
be21af9a-dbbb-5d73-923b-ce2e4ed1d78b | date | Date Completed:
| checkpoint | 2.11 - Width of layers not placed against concrete edge
4a9a14be-2086-57b2-9593-b9bf91e5b5b0 | note | FREQUENCY: During paving and at completion of work
b081645d-0eff-5ff6-94da-c8c81aba66a7 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
5682dcc8-6286-5be5-9903-fe928cd88306 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
e182e220-7601-562e-bf1d-b783541a2e5a | note | METHOD: Measurement
576e1c36-cb82-5e07-add9-c30db9da78dd | note | RECORD: Survey Report
7e12bf87-ce19-57c7-a3cd-c48f136371db | note | IP
701fd94e-b617-5779-a62e-9088f361468c | note | RESPONSIBILITY: Project Engineer/Site Supervisor
e05f32b5-a38f-5191-b348-2b4e005ae60a | date | Date Completed:
| checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
297135e5-ed13-5bf2-b6b3-60822e7847e5 | note | FREQUENCY: During paving and at completion of work
8d32ab87-f6d9-51a3-8e39-5ddb6e23cb82 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
d9f9b24e-9138-5594-8bf9-8d9afacda926 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
08f0e70b-8783-508a-a289-8e3212659fc3 | note | METHOD: Measurement or suﬃcient time has lapsed
68f2edb5-423d-58f6-880b-ffe22f7d8951 | note | RECORD: This ITP
1a9d1188-0fef-5f2d-b2ce-39a176b42ce6 | note | IP
7f4e2eb8-984e-5863-aa73-35bf680251cf | note | RESPONSIBILITY: Project Engineer/Site Supervisor
c0ea7700-500e-5ee0-81ff-63d8cd2a82fc | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction
3ea01a93-90b8-5aad-ab52-1f0ad5c4630d | note | FREQUENCY: Per Lot (6 shot test)
f36c22c2-771b-518e-9f9f-2e96e8204641 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
df530418-75cf-5498-a9e5-98a12f1077d2 | note | ○ 95.0% or greater Accept lot
a885aa2a-d150-5ded-be97-e54e3a8180ee | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
8722fdb1-40ee-5b6c-abb6-5c54ceeb6058 | note | ○ 92.9% or less Remove and replace asphalt
7b0a66d6-9185-5c93-ad10-be01dcf44c4b | note | For layers ≥50mm, if characteristic thickness is:
4c3f1e16-ed84-5603-936e-2256cef26004 | note | ○ 96.0% or greater Accept lot
960a15fd-97c4-5533-bd6b-de6cc1e8d086 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
1ba6fd39-3ae3-5145-8d5c-44343953e3dd | note | ○ 93.9% or less Remove and replace asphalt
e43ae737-0256-515e-8077-48ee79a67f65 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
85937a4b-7422-55a2-b459-567d8e37a27f | note | METHOD: Compaction Testing
48296b9b-c05b-522a-8bdf-b1b3e3e1d468 | note | RECORD: Asphalt Field Compaction Report
c9314ccd-99a3-56e3-99d9-ad7ee2ee0c09 | note | TP
2f032d04-b346-521b-a1d8-8762ffc48592 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
ed7eab13-91ea-5ca6-93e8-5c612059edcf | date | Date Completed:
| checkpoint | 3.2 - Surface Levels
a3b57793-0945-5ea8-9026-0401d2e010c9 | note | FREQUENCY: Each lot as required
c97caed1-4c69-5de5-813f-f2b9636177e1 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
56a92c5a-65bf-53fe-9336-974dfc6b8971 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
d96e15c5-222a-5ebb-9cfc-9599336885ad | note | METHOD: Survey
b93cd5ab-2182-52e5-9651-43d28c3e9ba9 | note | RECORD: Signed ITP & Survey Reports
14cf22b7-2397-5b6a-903e-3f50db452276 | note | SCP
fa364c43-4d29-58d2-9f4a-d9e17cc7dac5 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
d05db9ed-8783-5625-8556-9a307514c7ca | date | Date Completed:
| checkpoint | Final Inspection
17776558-95c5-52a4-b43c-e734ad34c2d6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
12075917-4f55-5e71-a2da-d7268412a15a | textbox | Print Name:
59b83e06-98fd-57f0-a0b3-0202a69fc95c | textbox | Position:
58008f9d-4619-5f03-a977-6d42d33a406f | date | Date:
| signoff | Sign ITP
| checklist | ITP-008 - Cement Treated Subbase Lot 3 (West Layer 1) | itp | ITP-008 - Cement Treated Subbase Lot 3 (West Layer 1) |  | 3b6653d2-c918-4e54-945d-7bd119745f82
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
09762847-d7c6-5770-a22c-e6f24154475d | note | FREQUENCY: Prior to commencing any activity
5349acb5-ab5f-5b36-9533-263f70a24fdd | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
94937d9a-9ff6-5f0a-bb77-fb30e4fcbef7 | note | – using the correct and complete set of drawings
5badbab3-eb28-5c5a-a981-050a338ada21 | note | – all drawings are the latest revision
f836b8ac-7edc-5479-bbcb-279925680f7f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7ea60698-d1f1-5254-9b1a-3f5d63be0268 | note | INSPECTION/TEST METHOD: Visual inspection
f07e5551-2226-5acf-b110-b46d9b55365d | note | RECORD OF CONFORMITY: This ITP signed
f982599d-9c43-5ef6-bc76-0daf3f43807a | note | HP*
a662c63a-5ba6-5e35-9f8f-6d549db4f66f | note | RESPONSIBILITY: Project Engineer / Site Foreman
f80a28a1-d710-53b0-bea4-e9f65e8628ab | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
e79d8d3a-7d99-58b1-ad20-b3a1624ec9ae | note | FREQUENCY: Prior to commencing any activity
8038d651-e583-528a-b7b6-652e9859b5c2 | note | ACCEPTANCE CRITERIA: Material proposed for import for 3% Class 3 CTCR (20mm) meets the requirements of VR Section 812 or 820. Obtain material compliance data from the supplier and submit to VRs for approval
6ad4e860-2bc4-551b-a3a5-3415f2bc0df6 | note | REFERENCE DOCUMENTS: Cl 812.04, Section 820.04 to 820.09, RC 500.02
d5b6dc36-faa5-57c3-8c89-465c8e830e29 | note | INSPECTION/TEST METHOD: Document Review
a59e8260-d93f-55e3-b716-3fda4c64c61e | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval - Quarry Dockets
222bea18-eed4-50b6-b039-65a87006fa9d | note | HP*
584d71ec-b881-566c-ac81-cd16c5043465 | note | RESPONSIBILITY: Project Engineer
b39d953e-f4db-5dff-bd6f-768b066205b1 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
bcc9d73c-23cd-5418-8c28-a5a50dd29f12 | note | FREQUENCY: Prior to commencing any activity
b15ab0a0-4575-5920-a2a3-42b765a127de | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
0789bf41-f988-528c-892c-f9475f710f30 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
8d13c04e-225f-5cd0-a069-695984c9295c | note | INSPECTION/TEST METHOD: Visual Inspection
488ef287-e54d-53ab-93b6-9263daef161d | note | RECORD OF CONFORMITY: This ITP signed
741ec72a-2835-5ea9-8116-91523d140b83 | note | HP*
5b68609c-9630-5c0f-9da4-f499c39cb73a | note | RESPONSIBILITY: Project Engineer / Site Foreman
cf10e91a-ad51-5e2e-946e-1d6956316076 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Materials
5aa4c0e2-4005-5a36-b269-e2387a987ac3 | note | FREQUENCY: Each lot
3c0e169e-e5ed-5842-8849-fd88a9e2c2e9 | note | ACCEPTANCE CRITERIA: The Contractor shall supply all materials required to construct the cementitious treated pavement subbase. The supply of Cementitious Treated Crushed Rock or Cementitious Treated Crushed Concrete shall comply with the requirements of Section 815.
ef641484-274b-594a-b807-e2e1227ddec4 | note | REFERENCE DOCUMENTS: Cl 306.04
5f7456c0-7858-545a-906d-6a68b075a627 | note | INSPECTION/TEST METHOD: Visual Inspection
c31fcef8-da31-5a7d-b373-5c3a1fc59886 | note | RECORD OF CONFORMITY: This ITP signed off
09fd399a-816f-5dae-b7a5-423a48c2620c | note | IP
bfec3a07-7f63-5e70-b0fd-fe726111d855 | note | RESPONSIBILITY: Project Engineer / Site Foreman
a9378d7f-261b-50f6-affd-ff536317f887 | date | Date Completed:
| checkpoint | 2.2 - Moisture Content
b31fba50-3074-588b-b487-b3f029829ada | note | FREQUENCY: Each lot
faf9b287-9b2d-5108-8471-ec097e61765e | note | ACCEPTANCE CRITERIA: The moisture content of the material at the time of spreading and compaction, expressed as a percentage by mass, shall be within plus 0.5% and minus 1.0 % from the Modified optimum moisture content.
6afdfec7-7d6c-5b53-a9a5-df2f73a6f6ef | note | REFERENCE DOCUMENTS: Cl 306.05
afc97435-8c21-53c6-ba29-b3b977b47266 | note | INSPECTION/TEST METHOD: Visual Inspection
b12e0923-4dc1-5b94-9e2e-f57c52048564 | note | RECORD OF CONFORMITY: This ITP signed off
c46ab61d-5938-59a6-b78e-96e56acda8ed | note | IP
af8d63ea-4441-5de8-8edc-a45c06931025 | note | RESPONSIBILITY: Project Engineer / Site Foreman
01d54b49-fa47-5c31-892e-6583004dd7e3 | date | Date Completed:
| checkpoint | 2.3 - Jointing
d32d47db-957f-50a8-a389-a2d917fb3664 | note | FREQUENCY: Each lot
a47067f1-a4c6-5a9f-a3fc-0ad2ebe3c709 | note | ACCEPTANCE CRITERIA: The layout of joints shall conform to the following requirements unless otherwise approved by the Superintendent:
6d2a8500-547e-5cdd-97e3-a68a44933309 | note | (a) material shall be spread in such a manner as to minimise the number of joints;
3e33c74c-e58c-51f4-acaa-321838b1c504 | note | (b) in any layer, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
56cec2b3-b731-5930-b91a-25cdc0f173de | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
a04f2939-85e6-5f98-b37f-a7929a76540b | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
e1155c82-b65e-5739-932f-14f76823a62d | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lane lines or within 300 mm of the centre of a traffic lane.
7cdbf213-bc04-509e-b4ae-d8f76ee1452d | note | REFERENCE DOCUMENTS: Cl 306.08
ce9174ba-e0b7-5022-a179-ec8234368d59 | note | INSPECTION/TEST METHOD: Site Inspection
83eaa20b-5572-5924-b51b-a22ccd30ed55 | note | RECORD OF CONFORMITY: Signed ITP
b88cd557-a159-5289-bbd6-339eea2479b7 | note | IP
682be648-5ad1-5f83-82df-0dd6cd027247 | note | RESPONSIBILITY: Project Engineer / Site Foreman
f590f8aa-e186-5e08-8a5d-7988908d4b46 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Survey Conformance
e61ab7ed-f111-5f0a-9968-322bea5aab2b | note | FREQUENCY: Each lot
764cc02e-5080-553f-9322-3895813c067c | note | ACCEPTANCE CRITERIA: Pavement subbase shall be finished to a smooth and uniform surface and shall, after compaction, conform within the following limits to the levels, lines, grades, thicknesses and cross sections as specified or shown on the drawings.
3d9e2f3a-48e3-53ce-b283-b6abcfc4f20d | note | (a) Width and Alignment
b73c6fc0-c81a-519c-9c72-6c07dc71b29d | note | – The width of pavement measured on each side of the centreline or design line shall not deviate by more than 50 mm from the designed offset when measured at a right angle.
226557b7-99af-51fb-99da-b8e8bbe587da | note | (b) Surface Level of Subgrade and Pavement
37fdbc72-fbb5-5688-a1e2-181f34c9f764 | note | – The surface level of the subgrade and pavement courses shall be measured in accordance with the requirements of Section 173 and every test lot shall meet requirements as specified in Clause 306.031 and 306.032
d22dff11-1608-5dd6-863b-a515a75cbe10 | note | ○ Surface level tolerances: Scale B - Range x = +6, -12mm:
c93b6d60-99f4-5196-a4c2-ba5d35624be9 | note | ○ Scale of Surface level measurement: Scale B - Minimum 40 points per Lot
d674c05f-df4e-5e8c-b835-0781d07e5ed5 | note | REFERENCE DOCUMENTS: Cl 306.031 and CL 306.032
a3454b9f-5fc3-56a7-8b44-45657d7dd849 | note | INSPECTION/TEST METHOD: String Sheets
f724426d-44d1-5362-a035-bdff36e270e6 | note | RECORD OF CONFORMITY: String Report / Visiual and ITP Signoff
e10a83aa-b441-5a3d-a799-1d7f2a14ae3e | note | SCP
a826fcbf-a016-5cf5-a117-28a25f74a55e | note | RESPONSIBILITY: Engineer / Superintendent / foreman
5e92e6b5-e2c0-53f6-b492-f6c346a4d278 | date | Date Completed:
| checkpoint | 3.2 - Compaction
c878b903-50eb-5d26-ba01-f4b13c7f9fcf | note | FREQUENCY: Each lot
e757e039-b700-55aa-851a-187176707905 | note | ACCEPTANCE CRITERIA: The cementitious treated subbase material shall be placed, trimmed to level and fully compacted within the maximum allowable working time specified in Table 306.091 depending on the binder type and the time of year the subbase is being placed. Except for the purpose of curing, no water shall be added to the cementitious treated material.
510ddc88-1c4f-58c8-9814-519ccf222dfe | note | ○ The work represented by the lot will be accepted as far as compaction is concerned if the mean density ratio for the lot is not less than 96.0%.
87e2903a-d5e1-52bb-a99c-485b70c69701 | note | ○ If the mean of the individual density ratio test values for the lot is less than 96.0%, but greater than or equal to 92% the work represented by the lot may be accepted but the method of rectification and/or redesign of the pavement shall be approved by the Superintendent.
cf88bfc3-2e13-549c-a005-c8140dc0652a | note | REFERENCE DOCUMENTS: CL 306.09 and 306.031
2833e09d-b2c9-512f-b65e-ff42d7688129 | note | INSPECTION/TEST METHOD: Compaction test and Visual
0581d552-8e1b-58fb-91b8-f1df151d6d37 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
e6a38008-bbb7-5649-880a-d52de6f1fb12 | note | TP
337a73b5-fb38-51df-85d2-26f0e883d287 | note | RESPONSIBILITY: Engineer / Superintendent / foreman
c2db57b3-232a-5419-aa81-06c8d334d726 | date | Date Completed:
| checkpoint | 3.3 - Curing
789a82f7-e5c3-561f-8c30-7e459a3667ac | note | FREQUENCY: Each lot
d60ef70f-11f5-5d0a-9c36-c2875afde466 | note | ACCEPTANCE CRITERIA: Pavement Design Modulus of 500 MPa or where no Pavement Design Modulus is Specified
61b6f5d4-8e83-5944-af45-cd30e7fdfdae | note | ○ The surface of each compacted layer shall be kept moist for a period of seven days unless covered at an earlier stage with the succeeding layer or with an approved curing membrane.
ee903d94-6b1e-5aed-88a5-31419f972e2d | note | ○ Construction or other traffic shall not use a compacted layer within 24 hours of placement without the approval of the Superintendent.
1beb6b59-178b-5f2e-a741-8ab32aa31a68 | note | ○ The subbase shall be kept in good order and condition and free from contamination.
540cb1ba-de80-5212-ad78-91e8806d80b6 | note | REFERENCE DOCUMENTS: Cl 306.11 and 306.06
d828305d-5dc5-5ba7-8172-ff3f361f058d | note | INSPECTION/TEST METHOD: Compaction test and Visual
b3f16010-f820-5fdc-98ad-05003ec267ae | note | RECORD OF CONFORMITY: This ITP signed off;
a5b5d523-e39c-5a0c-9d77-c1e86dd9111d | note | IP
d884ee62-d89d-5bfe-a115-690168b79ab8 | note | RESPONSIBILITY: Project Engineer / Site Foreman
40633ac8-ca44-507e-a02d-bae208d08f86 | date | Date Completed:
| checkpoint | 3.4 - Test Rolling / Proof Rolling
ebd23b4f-5dc4-50b0-a35a-76a44a33faeb | note | FREQUENCY: Each lot
92441e9d-58a9-5e1f-b8b3-02200193784a | note | ACCEPTANCE CRITERIA: Test rolling may be carried out in accordance with the requirements of Section 173 on the cementitious treated pavement subbase layer within the maximum allowable working time for the relevant binder and time of year as specified in Table 306.091.
3cbe19c1-f7ba-54d0-8a15-6f3d2733c5ba | note | ○ Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification. Proof roll will need to withstand test rolling without visible deformation or springing
55f4b70f-3788-5c21-9336-065722ccc69d | note | REFERENCE DOCUMENTS: CL 306.09
2953633b-8a67-5db6-8e88-bb2d1d3a5442 | note | INSPECTION/TEST METHOD: Visual inspection
006bce5c-36b4-5ae6-b638-78b8f0d7fb7e | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
5a398181-dd79-50d5-9216-63df1b73380d | note | TP
52dcb2f1-4354-51a3-9a92-1f4df7989ede | note | RESPONSIBILITY: Engineer / Superintendent / foreman
15f85cf9-b0bf-5e8f-b191-c98659f1397b | date | Date Completed:
| checkpoint | 3.5 - Dockets
d6308fa4-4cc1-52fe-b5bb-58842c17d956 | note | FREQUENCY: Each lot
f7e7d65f-eec4-5485-b98c-d2ef0253c6ed | note | ACCEPTANCE CRITERIA: Where material is measured by other means and for Lump Sum Contracts, the Contractor shall make delivery dockets available for inspection on request.
988e30c7-4613-59c2-a2e4-17437fb1d218 | note | REFERENCE DOCUMENTS: CL 306.07
c57a184d-2bff-542d-b6ce-c4669259f13b | note | INSPECTION/TEST METHOD: Visual inspection
b1531b3c-f813-5626-89cd-104bd7402154 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
99376b43-2b2d-5861-a00e-8d5cb3410f74 | note | TP
9904a723-8cf9-512a-8147-63f0a82370cb | note | RESPONSIBILITY: Engineer / Superintendent / foreman
933748b0-a48a-5ce7-a617-28fea9e3b39d | date | Date Completed:
| checkpoint | Final Inspection
292b9eee-1f2a-57aa-bb10-582a50a11444 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e5b5c365-89c6-58b1-88c5-d61df618b9e5 | textbox | Print Name:
142e6ba4-374b-58a6-89fa-b78a6f3bda65 | textbox | Position:
94234a5b-32cc-57d1-86a5-f9420bedd832 | date | Date:
| checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking |  | 1de5882a-7dde-4618-bf1c-3daf1cf0a34e
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Line marking Conformance
6decc52f-f238-5406-ab45-b16481be0a0b | note | FREQUENCY: Prior to commencing any activity
7c288dfd-04f6-552e-b391-cad67fc8e389 | note | SPECIFICATION REFERENCE: 721.A05
0eed24db-71c4-56d9-8c7a-215ae2ec8619 | note | ACCEPTANCE CRITERIA: Materials to be used conform with speciﬁcation
fa4c2060-243b-501c-8e2f-27a76b3071ef | note | METHOD: Record Review
6433e9d9-b4ff-5fb3-90fa-e39d594a5687 | note | RECORDS: Material sheet
abe5d130-c2eb-59cf-932e-10707b24b6f6 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
a6bb2cbf-0d23-52b0-b090-753f9c10c343 | date | Date Completed:
| checkpoint | 1.2 - Site preparation
d18fc51f-9df8-57ee-b89e-384f6558a56e | note | FREQUENCY: Prior to commencing any activity
d66cd9af-99fe-503e-b88f-bec56f029177 | note | SPECIFICATION REFERENCE: 721.A06
c4e4e470-6b2e-5cbb-b3a3-fb2a6752d2b4 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings. Removal of any foreign material or debris.
94a82f71-9f08-575c-9f6c-bdbbbe4ed1bd | note | METHOD: Visual and photos
b39132fc-055b-52d3-8708-1e0fd0fa57a5 | note | RECORDS: Photos
c9307376-374c-5ff1-b4c2-6f24de01fc24 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
14672bcf-16ca-5aa0-a5d7-8cfe11bb7f1c | date | Date Completed:
| checkpoint | 1.3 - Set-out of Pavement Markings
7bde258e-74c2-5c81-bf6b-35ad7ddc6081 | note | FREQUENCY: Prior to commencing any activity
de495b17-2a23-56c0-ad33-f7afc9581f62 | note | SPECIFICATION REFERENCE: 721.A09
6e1c40b2-5fcd-51d6-b2b3-7fb4bff75f4c | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
29c9a0d7-fe06-53d9-a7d2-a1303ed045e4 | note | METHOD: Visual and photos
c558960a-0248-57f7-90b1-384e21ba49ad | note | RECORDS: Photos
f1b399a1-dea7-51e6-87f2-19eb06a93111 | note | RESPONSIBILITY: IP - Contractor Representative, HP - SWA Representative
08893043-6dba-527a-9b46-af7ef49a05f5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Installation
| checkpoint | 2.1 - Line marking Installation
c216f09e-e64f-5289-90ff-ea17db6088ce | note | FREQUENCY: During Construction
7b41ef96-e45e-5b58-8eba-c45bf7e440a0 | note | SPECIFICATION REFERENCE: 721.E01
1fbb8408-bf5f-5a16-a62c-f142b6eaf5bb | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
c7f74a36-d531-5906-8184-1de2656be786 | note | METHOD: Visual and photos
2de447ee-5a6f-56df-822b-09690da6d889 | note | RECORDS: Photos
83888801-2031-57f3-9d6e-cf2df5ddddfa | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
ecf7e8c7-cd15-594e-b258-61d9a4262581 | date | Date Completed:
| checkpoint | 2.2 - Glass bead Install
5455461d-d578-5fef-9098-a807025a435f | note | FREQUENCY: During line marking works
129c5718-be6b-5fc0-91c6-c9e6c29be098 | note | SPECIFICATION REFERENCE: 721.E01
ce56130a-5110-595a-aec7-42c6ca9abcef | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a ﬂuid state to ensure embedment. Glass beads to have uniform distribution.
351b2f21-f74a-5d7f-b7a2-9715036c0f93 | note | METHOD: Visual and photos
e9e028e9-191f-54b7-80e9-a5bf175842e5 | note | RECORDS: Photos
6d897b20-0225-53cb-9378-5dd5cfdc8b15 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
66e6e253-8acf-59ac-ae0d-5e39d27d0b8f | date | Date Completed:
| section | 3 - Compliance
| checkpoint | 3.1 - Completion Inspection
a78cba1d-391d-5576-b565-d7c818c9ae63 | note | FREQUENCY: Upon Construction
eca57be0-f036-5a9c-bdf8-e25656d8747b | note | SPECIFICATION REFERENCE: 721.E01
c016ebed-7ed6-50d5-901b-0940617d2880 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects.
d3cc0d09-3bbe-5fda-a526-1c56c0b925f3 | note | ○ Edges and cuts-oﬀs shall be neat and sharp, and there shall be no visible run-oﬀ, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles
89a29f29-226a-5cf8-a981-41a43db99235 | note | METHOD: Visual and photos
e7353a58-a06a-51aa-8a5e-2b88791f02b0 | note | RECORDS: Photos
2139db14-7aa0-5b72-8de0-a3783d940be8 | note | RESPONSIBILITY: IP - Contractor Representative, WP - SWA Representative
453e1ff4-6428-5952-a42b-9d525c515a66 | date | Date Completed:
| checkpoint | Final Inspection
5d9c743b-b1d0-566a-9dda-72569b99b130 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
2275156b-b27e-564c-83c7-e53642e4cd9e | textbox | Print Name:
6b1dd9bd-aca6-522f-9252-6caa596d6f13 | textbox | Position:
3320fbd0-ce9f-544f-b805-702c0f697824 | date | Date:
| signoff | Sign ITP
| checklist | ITP-009 - Road Signage Checklist | itp | ITP-009 - Road Signage Checklist |  | 4a03a7de-8397-44e8-8eb7-36796f59925e
| checkpoint | Inspection Checklist Items
dc9b7c6f-a3ed-5493-8998-dbc970ea3834 | textbox | Sign Code & Dimensions
a917188f-ab1a-5f77-b82e-144aef0167e9 | textbox | Chainage Location
c5198dd8-98c3-59ae-a1b4-113408481183 | textbox | Number & Post per Assembly
2477ad5e-17d6-5890-b4ad-005a3ffec528 | textbox | Mounting Height (H) (mm) & Spacing b/w post(S) (mm)
98565e99-e225-56ba-bf92-09385b9da396 | textbox | Post Hole Depth (D) (mm)
64db3e30-c50c-5fe8-8663-c497b25407f1 | textbox | Fitting Type and Number of Fitting
dd0678d8-3635-54eb-bb12-b59c577f0e13 | date | Footing and Sign Installation Date
9600558b-1bcf-560a-b940-10cd212b3d9d | note | Photos
| checkpoint | Final Inspection
4c619913-70b2-59b9-8e85-7aa07009facc | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
7c9377e4-e5f8-5220-be1f-c2b39c3c57de | textbox | Print Name:
f6476e10-3a1a-5684-898c-a073d3a3fdf6 | textbox | Position:
bd7fa19e-daa1-5a8b-9ef3-03c4d76e0e2f | date | Date:
| signoff | Sign ITP
| checklist | ITP-009 - Subsoil Drainage | itp | ITP-009 - Subsoil Drainage |  | df88446e-4574-4f93-b067-e8b8926cfce2
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Induction
99fc7916-5307-5aac-a180-5331c39d79a7 | note | FREQUENCY: Prior to Commencing
b7848de6-26c1-506c-b009-7e8a7c8b0151 | note | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Fulton Hogan Project site.
896e1b02-5c3b-514a-9034-bf4ca6760a13 | note | REFERENCE DOCUMENTS: Inductions Register
89625b50-8517-5935-be05-4dc4445c4f81 | note | INSPECTION/TEST METHOD: Document review
3965ff27-aa12-565d-b581-844f1998bde9 | note | RECORD OF CONFORMITY: Site induction signed.
76fb42f2-7dfe-55b5-a5fd-33a0e29beb46 | note | AP
0e70867c-5471-5f40-a6b9-061af92d15e3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
36ce9f6e-aeb0-5b83-987a-bd9aa2ace80e | date | Date Completed:
| checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
ad76987a-211c-50e0-8f34-482302087417 | note | FREQUENCY: Prior to commencing
aeb0eb31-65ee-5be7-8875-c445b5060dbc | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
205179b1-12f0-5e56-8674-b1771971f510 | note | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
113dd350-f1b0-5db6-94a9-cfb1399cc3b1 | note | INSPECTION/TEST METHOD: Document Review
5de18d43-96cc-55d0-b3af-a64bae6ca118 | note | RECORD OF CONFORMITY: SWMS(s) signed
24cd90c4-74be-5c9f-bbc9-405dafcda7b2 | note | HP
965f78af-b100-5631-8231-84c44ac9edd7 | note | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
d25bf27a-e8c7-501d-97cb-8b0c651ddac6 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Check that current revision drawings are being used
df7702da-5885-5659-8236-1b228049afd3 | note | FREQUENCY: Prior to Commencing
4fa922fb-cf46-5d12-a87a-83afe540eca3 | note | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
f7f707ca-1996-5cae-b1b2-e67eddb9cedc | note | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
d5113534-cde6-51cd-bb25-0e55cf20fab8 | note | INSPECTION/TEST METHOD: Document review
dd520db7-d787-592a-a264-a5c71205129a | note | RECORD OF CONFORMITY: Latest Revision Drawings
6559d67b-ff3c-57dc-8038-154a91710dea | note | AP
5b6de928-e32e-59c7-8f65-d7b78dd1d477 | note | RESPONSIBILITY: Site Engineer / Site Foreman
2688554e-6620-5c32-afaf-5ade17fccab2 | date | Date Completed:
| checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
6e7ddc56-1bc8-5002-a5d1-ca843c813c6c | note | FREQUENCY: Prior to Commencing
d65029b9-ca28-51f6-b41d-520ef98c8ec8 | note | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
df1b432d-2385-5de4-a099-6f1b85b1b44d | note | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
2fe79453-0446-51b2-95c2-9b5b8b27e2f1 | note | INSPECTION/TEST METHOD: Document review & Site inspection
6fb2d073-76d4-5c95-bfdb-3bb8c8cc1f1d | note | RECORD OF CONFORMITY: Signed ITP
2bab4b1b-40e9-5da1-8fbc-96ddd684aeb0 | note | IP
542087b2-b409-569a-940b-5d8dc6390645 | note | RESPONSIBILITY: Site Engineer
4de5f5d4-72c9-5891-9357-2fab3130969e | date | Date Completed:
| checkpoint | 1.5 - Excavation Permit issued
a444bc6d-bf0d-5227-a89b-565bf427ecd4 | note | FREQUENCY: Prior to Commencing
125bfcf6-c49a-5429-9366-fa4767c6ff60 | note | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
71590664-1368-5777-a47c-28fc77bb9090 | note | REFERENCE DOCUMENTS: Excavation Permit
45f5b9d9-60ad-578e-b9db-c3b81fcac1be | note | INSPECTION/TEST METHOD: Document review
fb300f6a-e38b-5dda-aa04-6c30480f991b | note | RECORD OF CONFORMITY: Excavation Permit #
c4bab993-ddf1-5d12-a291-c6778f33b46a | note | IP
305fd9d3-a30d-50ee-9eaa-922e65aa6306 | note | RESPONSIBILITY: Site Engineer
341b888f-a303-56be-ae14-4c8bb1a62ddd | date | Date Completed:
| checkpoint | 1.6 - Materials
ea760619-3eb5-5582-a11d-8dcbf60d5042 | note | FREQUENCY: Prior to Commencing
30e017f8-3b1a-519d-a829-3708dec4ddca | note | ACCEPTANCE CRITERIA: All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2
379e0074-e95c-5c7a-b432-59768990e26f | note | REFERENCE DOCUMENTS: Project Spec. Cl.3030.05(a)
ceb1d3bd-4e2f-5c0a-9d49-404c3efc26ec | note | INSPECTION/TEST METHOD: Document review
b76dddee-404b-51f9-abb9-457ac50cfa1e | note | RECORD OF CONFORMITY: Signed ITP
9da187ad-626e-5080-9a02-27d7a01d5d7f | note | IP
789c2ef3-4ba7-5d04-ae57-0e4c75588076 | note | RESPONSIBILITY: Site Engineer
d476b1d2-8f9a-5f20-bbd8-566c0632f3f8 | date | Date Completed:
| section | 2 - Drainage Works
| checkpoint | 2.1 - Excavation of Trench
abc6f700-ae14-53a5-8f6a-966cbceabae5 | note | FREQUENCY: When placing drainage
d7614d8b-ae6c-5b21-9099-d8f4bbac8838 | note | ACCEPTANCE CRITERIA: The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed.
0c94ac8a-812d-5490-9389-3969840f24ea | note | ○ Perforated Pipe Crown level to be minimum 200mm below subgrade level.
eb420096-8672-51ec-8631-725e12c8f763 | note | ○ Grade of trench to be not flatter than 1 in 250.
c0930f5b-4f1d-5bde-b6c8-918775937dee | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08, VicRoads Spec. Cl.702.09(a)(b)
71fa75d7-3ba9-5d53-876f-4f4fce8006bd | note | INSPECTION/TEST METHOD: Site inspection
59527ff8-5b0b-5e5e-8030-59ef86ac3380 | note | RECORD OF CONFORMITY: Signed ITP
103b0028-6d8f-5faa-bb12-78caa650af36 | note | HP
de6bfa95-c927-56e2-acdd-4614fb2d699c | note | RESPONSIBILITY: Superintendent / Site Engineer
62816871-2a21-56e4-843e-d97d82082ccb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Use of Geotextile
81e5a155-2f98-5695-8201-bffdfac94a15 | note | FREQUENCY: When placing drainage
31a7e76b-b8b7-5bad-b14a-9726fda9346c | note | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
50e29d2a-b247-5acc-89e4-3a5c8cc83e76 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.08
0e67d36a-9cb4-5d12-99e4-721b26b6b811 | note | INSPECTION/TEST METHOD: Site inspection
2877d553-c8e4-507b-b40f-28a166008681 | note | RECORD OF CONFORMITY: Signed ITP
1646516e-18f6-5a0d-b7ff-16364cefee33 | note | IP
47c97073-2cca-5e3b-9d76-371f3a2d3953 | note | RESPONSIBILITY: Site Engineer
4058f06d-d173-51e3-8770-9b8c6c81eb61 | date | Date Completed:
| checkpoint | 2.3 - Installation of Subsoil Drainage
36166a1a-1a38-53df-958c-8f00b89fca80 | note | FREQUENCY: When placing drainage
8eac74c7-26ea-502a-b558-5ea0dbbb7666 | note | ACCEPTANCE CRITERIA: Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level.
76d398b3-592e-594e-8f19-7e2fa9a047e3 | note | ○ Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe
613e1a3e-2d61-5324-a1d3-b1408a78c366 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(d)
785003ab-1fc7-52fc-a9fa-5ec9a7b01b2a | note | INSPECTION/TEST METHOD: Site inspection
835a846d-12c4-50a3-a6d2-7fb2607be910 | note | RECORD OF CONFORMITY: Signed ITP
5e983fcb-33c5-5526-9d6c-3c2d7eb85a13 | note | IP
04fbc2e7-4f15-5bb4-8e9c-d197e1c4312e | note | RESPONSIBILITY: Site Engineer
3bb25ce0-5fb9-53de-aec9-7244a6cf77f0 | date | Date Completed:
| checkpoint | 2.4 - Placing of Granular Filter Material
48e38883-afc1-5a2a-903c-fee87a04cdba | note | FREQUENCY: When placing drainage
814f0cab-e120-5f08-8d55-1d160ef924a1 | note | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
52ec0960-8501-5eec-92fb-f4cef0ec1a61 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(g)
f6ad9b1f-4445-5b63-909d-a163f983cc10 | note | INSPECTION/TEST METHOD: Document Review
6a34ca60-0429-58c2-8db6-ed039897504f | note | RECORD OF CONFORMITY: Signed ITP
17a31396-af39-57ca-a8f8-16190885fbb8 | note | HP
2f2b826b-ca78-5be1-b16b-75b63c453861 | note | RESPONSIBILITY: Superintendent / Site Engineer
3113e098-0915-575f-ad69-7c724b48d6f0 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Flushing Test
80fd7404-cc1b-5a62-8982-9858fdb753ea | note | FREQUENCY: After drainage is placed
708fd06a-97d5-55cb-8bcb-9ec6ce5e45f3 | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction
181e9073-d3b5-5ac0-9ee6-bdbc0e2c76f2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(h)
01266bb1-0321-5099-b10e-606ec8d6768b | note | INSPECTION/TEST METHOD: Site inspection
baf0dd3f-6f88-57d8-8199-fb745e09a598 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
ca7d0e8e-ddf8-568b-bd7b-7e27a6e0e617 | note | WP
a28d486b-d651-565b-a8c5-ab2d3b315ac8 | note | RESPONSIBILITY: Superintendent / Site Engineer
6ca66f05-e320-5419-9252-474f0e674d46 | date | Date Completed:
| checkpoint | 2.6 - CCTV
406f539c-45c4-51ef-a463-6e622bc7104e | note | FREQUENCY: After drainage is placed
218c5a57-95d9-5747-aa64-c9823a14392b | note | ACCEPTANCE CRITERIA: All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV) to verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects.
bae36210-6434-5b06-b190-ea101c8d0cff | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.09(i)
41abaea3-2a73-5833-8c00-2ccbfa1d8270 | note | INSPECTION/TEST METHOD: Site inspection
e1d21466-3e5f-5708-a9bf-1dbb28db5f50 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
a634b25a-96ad-58af-8ed2-3ec4b7aabedf | note | HP
920e3e74-db06-588e-925f-cf64adb0e940 | note | RESPONSIBILITY: Superintendent / Site Engineer
843a3139-b9cc-5951-b432-9d4fff02ca79 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
891f6215-6fd2-502c-b00e-fe2af2da492f | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b5cbc0a4-a18b-5f69-b685-17397a50f7e5 | textbox | Print Name:
836ede8d-581b-5c48-b21f-c12061bbf358 | textbox | Position:
3c0660bd-af93-5286-8b92-06f0380f3b99 | date | Date:
| checklist | ITP-010 - Guardrail | itp | ITP-010 - Guardrail |  | 959d7f0d-ee74-46fa-a68d-ba7171b95fc3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
0ec57c45-86f2-5bdc-b58b-a216f96427bf | note | FREQUENCY: Prior to commencing any activity
086cb6b8-35d8-503d-979c-02b0754ff62e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
ab817a45-c92b-5e09-af6c-7c7e05ebd0bf | note | – using the correct and complete set of drawings
0e87b665-1836-5f00-8bd9-0aff94e5fb43 | note | – all drawings are the latest revision..
aa50f204-8caf-51f3-b943-d67d410f8d74 | note | REFERENCE DOCUMENTS: Design Drawings
4a0abe65-ea75-56fc-871d-5432bf3fb90c | note | METHOD: Visual Inspection
251f8e93-1153-5553-8544-9e01118b4ab8 | note | RECORD: Signed ITP
03256eb2-10f7-5eb2-acbc-768daed6ab0d | note | IP
82c51713-01e0-5753-b05a-f8bc425c1a90 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
6dcf91aa-ca4f-5cd5-bded-9751eee20558 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
5afcc918-dc4a-558f-aa76-735dfd2c28bb | note | FREQUENCY: Prior to commencing any activity
663cff31-6696-5aa8-af87-521b6453cf31 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS
6a2336c7-2787-58be-84c1-3df28befa56c | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
c37a8318-8c2d-5a69-8c75-a83252fb4bc3 | note | METHOD: Visual Inspection
f341f913-15fa-54c4-97bd-e055ff085002 | note | RECORD: Signed ITP
5742e225-b980-5fa7-b89e-fd6a8e25bfc2 | note | IP
12c453ab-0f00-53a1-9a99-d7a762d45f9b | note | RESPONSIBILITY: Project Manager/ Site Supervisor
179b0df0-6817-59e8-83a9-f173c1ad472a | date | Date Completed:
| checkpoint | 1.3 - Setting Out
4c70ffe9-0fd7-59db-aade-198edbbb95fa | note | FREQUENCY: Prior to commencing any activity
8dd0c908-2af4-5773-b10c-1cdd07379690 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor.
caac9424-8219-5a49-be8c-0b27d7d96fdf | note | ○ Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
f0a37273-72f2-5e02-a92c-218a38f5abef | note | REFERENCE DOCUMENTS: Drawings 708.08
a0b2264e-1557-5811-a657-fa658781abaf | note | METHOD: Document Review
25ba3632-56f1-5b5b-b635-2d5d334c04af | note | RECORD: Signed ITP
f9e669d5-a8fc-5868-88b2-85fd11d2861b | note | IP
5f22be86-56b4-51c7-a4f6-77db6d3b4243 | note | RESPONSIBILITY: Project Manager/ Site Supervisor Superintendent
540fad9a-8918-51a5-bfb3-689327283865 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Supply of materials
07311716-27c3-59bc-8c66-34ff2ec8f1e8 | note | FREQUENCY: Each Delivery
41fd03e0-71a3-5cf0-8d71-d65231baead1 | note | ACCEPTANCE CRITERIA: All materials are to be on VicRoads current accepted products list and conform with the detailed design
8e743b2d-c7ea-5d17-8f27-b941961e81bb | note | REFERENCE DOCUMENTS: 708.04, 708.05 Detailed design
65b15744-9046-51d6-9b49-9c0cb11e31e5 | note | METHOD: Visual Inspection
70bdaa8e-43b7-5dea-8b64-f89f86506728 | note | RECORD: Signed ITP
1e7a1bf2-e8a9-5d1c-bb3b-ec9a92bfb1d2 | note | IP
d5b348f3-513f-539d-9466-d8c71722ef26 | note | RESPONSIBILITY: Project Manager/ Site Supervisor
0c0c4c74-906d-528e-b904-8c78909e065c | date | Date Completed:
| checkpoint | 2.2 - Installation
85a5de76-58b8-5d60-aee8-b55099377790 | note | FREQUENCY: Each lot as required
8db5e8bf-9e53-5d1f-a2c4-2912b045a9c6 | note | ACCEPTANCE CRITERIA: The oﬀset, height and post spacing is to conform with VicRoads speciﬁcations and the detailed design
88f58727-1259-5f70-9b1b-a724f725415a | note | ○ Where the face of guardrail is less that 1m behind back of kerb, the mounting height should be measured from lip of kerb. Otherwise measure from ground level Fasteners are to be snug tightened to AS4100
c5f6a30b-5ebc-515c-b4c2-7a399533416b | note | REFERENCE DOCUMENTS: Detailed design 708.08 SD3661 AS4100
5f83d83c-6406-5083-9409-db6c8a43b72d | note | METHOD: Visual Inspection
fe660ed2-bef8-5c2e-9d8f-c860f088952e | note | RECORD: Signed ITP
b2c24674-080a-5153-8c78-959dfae3b2bb | note | IP
01ba80f2-36ab-5720-b70e-1c3e7a2f224c | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
cd466e90-8a5b-5335-b067-d55ed355d4d9 | date | Date Completed:
| checkpoint | 2.3 - End Treatments
51b415f8-bb9e-5625-823b-01f660682781 | note | FREQUENCY: Each lot as required
57c5859d-5b20-5d54-8805-88afb2bad015 | note | ACCEPTANCE CRITERIA: Guardrail end treatments are to be installed to VicRoads speciﬁcations
0bbb2739-8a95-53a2-ace1-5e372d6aed4b | note | REFERENCE DOCUMENTS: Detailed design 708.08
6ea32cbc-291c-531d-b0a3-17bcdbd44c54 | note | METHOD: Visual Inspection
370fc108-8336-590c-b227-ef32a7bac163 | note | RECORD: Signed ITP
623b922e-10a0-5aee-bbb3-be120111e4dd | note | IP
edfa7fad-f9b0-59fe-badc-78506f6adf76 | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
c070f63d-cad9-520d-a077-313ac75e4be6 | date | Date Completed:
| checkpoint | 2.4 - Motorcycle rub rail
4d5697fd-9c4c-5f8f-a59d-ac37aa7b95a5 | note | FREQUENCY: Each lot as required
a748f548-eee9-5b61-873c-7ce62cbd9938 | note | ACCEPTANCE CRITERIA: Where speciﬁed, motorcycle rub rail is to be installed on the new length of guardrail
237b6204-7728-5f89-802a-f6314a444077 | note | REFERENCE DOCUMENTS: Detailed design 708.09
7509c32b-e1e2-562b-b3f5-6ad6425f2f4d | note | METHOD: Visual Inspection
e6c525e7-02f8-56aa-83bc-8a3ea15886d5 | note | RECORD: Signed ITP
54c65d0e-d8a3-539d-a84c-45b0a1bc4744 | note | IP
6ac946d1-567f-5d9d-8b3d-0ce869d45aaf | note | RESPONSIBILITY: SWA Engineer/Site Supervisor
29a00349-f5ee-5795-8f98-7a256ef90ccf | date | Date Completed:
| checkpoint | Final Inspection
6ca108b5-1937-510e-89f1-beae553f2df9 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
68028ba3-22e7-5c2e-bfd6-3aaf14cc3eb5 | textbox | Print Name:
d1dbdee0-8b8e-5e3e-80e4-a67262f3bc1a | textbox | Position:
59922202-9206-54e2-84fd-08300ad09ec6 | date | Date:
| signoff | Sign ITP
| checklist | ITP-014 - Earthworks and Subgrade Preparation Lot1 (East) | itp | ITP-014 - Earthworks and Subgrade Preparation Lot1 (East) |  | 20a70ec9-4eec-4879-971d-ea10892db417
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
8a775dd1-f693-5de5-9668-5471dd38b858 | note | FREQUENCY: Prior to commencing any activity
7f15375f-b763-59b9-af57-4973fe9cffee | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
5fe85fb2-57c9-5f11-a46a-16c15c66dd7b | note | – using the correct and complete set of drawings
41915e96-5372-5c44-94f5-1b84b28f2d47 | note | – all drawings are the latest revision
9ae67b70-b965-5510-a073-ca2454c0a0c7 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3966b7f4-4c87-558f-99d2-10868325f49c | note | INSPECTION/TEST METHOD: Visual inspection
309875d7-034d-540a-9e88-08a6f785efd8 | note | RECORD OF CONFORMITY: This ITP signed off
bb97017b-8636-5855-9735-c65e542cf151 | note | HP*
218ba34a-98f8-5da7-a50e-0c0045717010 | note | RESPONSIBILITY: Project Engineer / Site Foreman
b684da10-f210-5ba7-9894-a1ca1b0d4951 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
74e0a49c-3ee7-52e1-a481-ef2f0dca33c4 | note | FREQUENCY: Prior to commencing any activity
5a255568-a2a9-54f1-baf9-052574ba8029 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
171168bc-8b91-5d6f-805e-d643b1dff324 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
d01a598c-27f1-57b7-a441-a24749dcd6b1 | note | INSPECTION/TEST METHOD: Visual Inspection
e99852e9-7ea0-501b-bf91-c5165e8a3d70 | note | RECORD OF CONFORMITY: This ITP signed off
13aa8f3f-8f36-5a0e-b002-0f686ef551de | note | HP*
de81b1aa-191b-5d26-9bd9-40be55f6017b | note | RESPONSIBILITY: Project Engineer / Site Foreman
7df3a554-8124-538f-afd1-d61c21aa863e | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
a6c3695d-2531-5cc1-91e1-1d0e4a0e79de | note | FREQUENCY: Prior to commencement of excavation
5bde262a-acfe-523a-b0de-a9c027dbd757 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
ec4584d4-1279-5235-aa63-8a8af5c2b3f9 | note | REFERENCE DOCUMENTS: Work Procedure
1ecc548c-2074-5546-be5a-ad720f2d2874 | note | INSPECTION/TEST METHOD: Verify
92ee3ded-98a3-59f9-aa17-ae3e418a5545 | note | RECORD OF CONFORMITY: This ITP signed
cfb9f335-cf8f-55e5-bc06-5c21a2dfc2ab | note | IP
b1372482-8f58-521a-9c81-91a46d94384a | note | RESPONSIBILITY: Engineer/ Surveyor
0ab96c84-7e8e-5cbe-ace1-ff9567fe35eb | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
5db52b9a-b810-56e5-b74a-0f122adf99e8 | note | FREQUENCY: Lot
3ce1ab84-8f1d-533f-8703-d30c9ca3777d | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
0d5befd2-9943-55d5-b480-03c3d9690473 | note | ○ Plant and equipment shall be appropriate for the task.
774fc3f3-f987-517a-a68b-149e4a0c2ae3 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
e864774f-2353-53ed-8e13-4a232ccc967a | note | REFERENCE DOCUMENTS: Excavation permit
58ff8dbb-d8d6-5864-ba26-f395a4b38f69 | note | INSPECTION/TEST METHOD: Verify
f4ab4416-a295-5e99-9ba2-394ef8e0f2aa | note | RECORD OF CONFORMITY: This ITP Signed Off
35074abc-cb80-50ea-929d-927613bee362 | note | HP*
6a659eb7-0691-5229-8fc2-5e36c7a4bec3 | note | RESPONSIBILITY: Project Engineer
7ae69c46-c454-572d-b0ee-6f9b49d6af54 | date | Date Completed:
| checkpoint | 2.3 - Excavate Pavment to specified depth and dispose material offsite
5ad2edfe-ac7d-574f-a4ff-06f2e2a386ec | note | FREQUENCY: Lot
f35d1886-95af-55f9-86ef-0418f9982069 | note | ACCEPTANCE CRITERIA: Correct levels and profiles achieved based on the tollerances below
747111cb-ff40-5042-b395-41c0406f2cc6 | note | ○ +15, -30mm at subgrade level
211c9392-8337-5eae-b496-9ad8c8b4e793 | note | ○ Cross check with survey pegs and record excavation depths using GPS
98e92282-f715-5f03-963f-c694d1844a56 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
31a14c2c-5480-5ace-ad27-c4ca5489406c | note | INSPECTION/TEST METHOD: String Sheets to be used as no design survey avaliable
811629c0-de7f-569d-856f-c40595f5c244 | note | RECORD OF CONFORMITY: This ITP Sign off and String Sheet Acceptance
9f622b1e-1177-5d29-a5fe-cbded023d16c | note | HP
d00e8e97-3b18-5760-9349-d12be9bfc87a | note | RESPONSIBILITY: Project Engineer
da3ed79d-8ac6-5caa-9d7f-a8aa6fb51709 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Material classified as silt
57756fd9-166e-5ebc-9c2a-77210be56d47 | note | FREQUENCY: Prior to Commencing
35c49237-c918-5846-8977-225f5fcbeff4 | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
7c53585d-7361-5702-a40c-ab0f06357409 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
3b2df51f-2a30-58ab-b58b-07b95ab8fe4c | note | INSPECTION/TEST METHOD: Document Review
39bb56da-7a55-5cfd-87e9-c473eaf67d9c | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
6f82b515-13a7-5fe4-9257-23cfdb0a43bb | note | HP
5f0a58b9-57c4-543d-b01c-52873c8d958f | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
4dc764a5-79d3-5f03-89a0-07142ceeb726 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
6baa7419-47f7-5419-a403-18d4a3a2951e | note | FREQUENCY: Prior construction of the regulating layer
236a6041-c1d8-5a9c-8244-4dae7bc4fbcf | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
768a927e-86ec-5fdb-9185-dd8d762274c6 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
0c985d49-fa6a-5ae6-89b4-6448642c8076 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
e6938dde-f419-57c4-bbbd-55de847dca1a | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
2aff5dff-ad43-5954-94c0-bf506b3373f3 | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
844efe7a-a0fd-588e-8697-14303f5f00d1 | note | HP
adc485fe-523a-5353-94ab-fdf1954cf9ef | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
8fbe3281-61dd-5d4d-af30-f22144f0abdb | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Unsuitable Material
b0f63966-5d08-5ed0-aab0-871660267b4a | note | FREQUENCY: Each Lot
193de2af-f1ac-5ac3-b797-ed7868eed17c | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
b316e722-1014-5485-b092-8316ad26e733 | note | REFERENCE DOCUMENTS: 204.07(d)
771101c5-23a5-55e6-8562-edf7ee5750bc | note | INSPECTION/TEST METHOD: Visual Inspection
0e4c6209-2841-5f85-97b9-60dc2fb3f151 | note | RECORD OF CONFORMITY: This ITP Signed Off
9d6747df-4427-595d-bdf4-170d9e5c89c5 | note | HP
c04ddd05-a8e1-5abd-8318-0fa0b2247322 | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
75212bb6-6970-5138-b423-b77ee38c6e8c | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Groundwater
b722f133-46ed-5d87-8b9a-99cc3234a77e | note | FREQUENCY: Each Lot
aeb7fdb4-6c07-53e4-af0f-83df99b1b7f9 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
1a3140c5-2509-5c35-9399-1fce8e2def91 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
7e349899-8b12-5caf-8620-41f92a3d3b56 | note | REFERENCE DOCUMENTS: 204.06 (h)
d820c398-c6b5-5f67-b2b1-1abb3ee2c38a | note | INSPECTION/TEST METHOD: Visual inspection
429e3661-96d7-513f-b424-249e37a09d2e | note | RECORD OF CONFORMITY: This ITP signed off
d5274ed7-3a7c-54cc-8ff3-b74f5dbe852a | note | HP
8c99ea72-7254-5ef9-8276-723bab02d4ad | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
2616818f-a694-50f7-8b59-17aa38c46ead | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3 - Testing
| checkpoint | 3.1 - Proof Rolling
b39e3fe0-2675-52e3-a233-77e466bdec9f | note | FREQUENCY: Each Lot
a52c7d82-6c75-5895-b538-a1c3bf5f1b09 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
2058a991-922c-5a94-81f1-359992e84981 | note | REFERENCE DOCUMENTS: Cl 204.12 Section 173
c93a13ca-1b1a-5d5f-9d36-4f1f4a330b23 | note | INSPECTION/TEST METHOD: Visual Inspection
2a0eda39-b73b-51e2-b222-49f9aa8a5472 | note | RECORD OF CONFORMITY: This ITP signed off
65443544-577e-5d11-bd3c-2251e5a9077b | note | HP*, WP
6d8d56a6-69f6-5030-bf07-b5c9e4210bbe | note | RESPONSIBILITY: Engineer or Forman / DTP Superintendent
3922ebc8-87e6-5885-8040-062544c58e72 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
3dd5f0f5-b6ef-55cd-9962-a4510d4c4e88 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
23732055-7aa4-5311-a9f3-f40f0c85c619 | textbox | Print Name:
7c8dce47-676a-58d3-abd3-1595169e62db | textbox | Position:
b0a9e3fa-48f9-530d-8093-fa9e96042953 | date | Date:
cb7bf09b-6ab9-46de-add9-c86aa84c0599 | checklist | ITP-015 - Construction of Concrete Paving | itp | ITP-015 Construction of Concrete Paving |  | d5385c10-8208-49f5-b2d2-98529cc67951
51dd78a0-4a1b-4168-a93f-31c10a09c749 | section | 1 - Preliminary Works
b2adecba-e8f0-459f-a7ff-e103c537701d | checkpoint | 1.1 - Check for correct documentation
7d78589b-db11-5bec-b67b-1779294cdd44 | note | FREQUENCY - Prior to commencing any activity
52cffb50-402a-53bd-abe0-c7a11ca79dbe | note | ACCEPTANCE CRITERIA - Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
fb17c6f9-e7db-5264-b516-791684468374 | note | REFERENCE DOCUMENTS - Drawings and drawing registers
523fb45d-23f0-573a-88b7-76756d17dcc2 | note | INSPECTION / TEST METHOD - Visual inspection
d9a9c964-d7fd-5c55-b5a0-e3b5d599372e | note | RECORD OF CONFORMITY - ITP Signed
4a2cc62b-47b3-5494-913f-3b3a22a143d1 | note | HP*
59324c69-77fe-5ded-a703-5958e4c73fb8 | note | RESPONSIBILITY - Project Engineer/ Site Foreman
f0cdb435-c8e1-5c37-9871-eef34ad62c4e | textbox | Date Completed:
572a9dbe-7cb9-45a9-94bf-1b0c23c33b07 | checkpoint | 1.2 - Implementation of all measures and controls
bcc73447-8688-5587-93a8-bbdffc27765a | note | FREQUENCY - Prior to commencing any activity
f3372966-e8ee-5a3f-bd2f-cc8b14d96b25 | note | ACCEPTANCE CRITERIA - All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
ff0ce40d-892e-54b0-af20-8eada1c1a6fe | note | REFERENCE DOCUMENTS - QMP, TMP, JSEA, SWMS, WP
54f56601-66e8-59e1-a02e-8616360e42bf | note | INSPECTION / TEST METHOD - Visual inspection
3143f1c9-e43b-5bf0-9501-cf05a951fc0b | note | RECORD OF CONFORMITY - ITP Signed
6eef6179-7a01-5734-b837-9df277bcab7b | note | HP*
57a1aca1-b9c0-54c0-8048-a6686da36d6d | note | RESPONSIBILITY - Project Engineer/ Site Foreman
1196aff3-4f9f-5150-98a4-ceb7376afef3 | textbox | Date Completed:
e2027d0c-1fc0-4d9b-80fd-125e785a1175 | section | 2 - Construction Works
e890b822-3c4e-4715-a909-45ea19ef50fb | checkpoint | 2.1 - Setting Out
e99e3848-1967-5923-8375-c1a293767d7d | note | FREQUENCY - Prior to start
ec79c019-ab3f-56d4-bd6a-7b65b76812d2 | note | ACCEPTANCE CRITERIA - Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
2350dc6c-8a14-5199-9ce1-7d8b14d0e0e8 | note | REFERENCE DOCUMENTS - 703.17
9500ec52-9c98-5ac9-849e-9d80c4900ed5 | note | INSPECTION / TEST METHOD - Verify
602458e9-c6af-5d88-ba03-58c62325a5ab | note | RECORD OF CONFORMITY - ITP Signed
4166c991-93fa-5225-8b99-1ac12bb79f0c | note | HP
6f8a2550-786a-5a30-a459-afb41e101ea1 | note | RESPONSIBILITY - Project Engineer/ Superintendent
3db7a037-7ac6-5d19-b290-2ca80495f7b7 | textbox | Date Completed:
8337cb33-ba28-4455-8a73-0101f537fb0b | signoff | AUTHORITY HOLDPOINT
2d43095f-d5f3-44a0-a663-098789e92cf0 | checkpoint | 2.2 - Temporary Drainage Provisions
fd0ed8a3-41e8-5fb9-8114-921df2d1c39b | note | FREQUENCY - If Required
8052ad79-e138-50a0-a661-e396ccf589aa | note | ACCEPTANCE CRITERIA - If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
abaa110c-e60a-5fe5-87cb-41a348d4be8f | note | REFERENCE DOCUMENTS - Cl 703.18
a709c154-2dd5-5e61-a3e9-49889846ad82 | note | INSPECTION / TEST METHOD - Visual inspection
38acac9b-4e42-5bd5-a0cd-2a523467bbdf | note | RECORD OF CONFORMITY - ITP Signed
5330f769-2297-53b9-8f1d-afcfb03fc189 | note | WP
2f11b174-998b-5a58-a78c-d3b3bcd89f52 | note | RESPONSIBILITY - Project Engineer/ Site Foreman
8b2b4f5f-a41e-5c5a-9f39-1b569be412b9 | textbox | Date Completed:
73235681-c5f4-4649-ab11-c0e145671696 | checkpoint | 2.3 - Bedding and Reinforcement check
76e61e69-3d87-55e7-82f0-c72433e8fc32 | note | FREQUENCY - Each lot
62031e59-3412-5cd6-a4bc-2eda937812ef | note | ACCEPTANCE CRITERIA - All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 bedding shall be used and compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
46ca26e2-ccbd-5587-ba71-d898d602b674 | note | REFERENCE DOCUMENTS - Cl 703.21
1888e84c-ed78-5cb8-bf42-cd575bc824ac | note | INSPECTION / TEST METHOD - Visual inspection
98470e74-a008-5757-93e5-b156d0673090 | note | RECORD OF CONFORMITY - ITP Signed
d00e3c98-6219-5c7c-90f5-9755a0415c65 | note | HP
2431edce-0765-52ea-89e9-5ff51a2e4152 | note | RESPONSIBILITY - Project Engineer/ Superintendent
9bc978e7-d0e0-5ad3-a3c6-5d6de4fc4b72 | textbox | Date Completed:
8fef807a-30b1-4216-90c3-00d5e6abeb88 | signoff | AUTHORITY HOLDPOINT
dd160ecb-760a-4d9c-ba54-fd0195aa192a | checkpoint | 2.4 - Pre-concrete check
1c8e55a6-d2c4-5984-981c-02224156841a | note | FREQUENCY - Each lot
7b239ab9-bb19-5585-8c61-4f01e5543659 | note | ACCEPTANCE CRITERIA - Bedding shall be moist but shall have no free water on the surface. Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C. Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C. Concrete extrusion machines have minimum cement content of 320kg/m3.
1a683ee5-d022-5206-bd44-cfd4d1c9948c | note | REFERENCE DOCUMENTS - Cl 703.08
27b75737-5a8d-56be-b885-185fe81c8df9 | note | INSPECTION / TEST METHOD - Verify
a84c1488-27cb-5480-acb3-ccba032c05a6 | note | RECORD OF CONFORMITY - ITP Signed Ambient Temperature..... °C Concrete Temperature...... °C
ce3764d0-d194-5a75-becb-ba6c468ab485 | note | HP*/ WP
7863a062-b311-5360-9bf3-c82baff7ee97 | note | RESPONSIBILITY - Project Engineer/ Superintendent
aa2ee860-1c84-5a07-879e-602242e733a1 | textbox | Date Completed:
1747d0bd-caaa-477f-8844-d25da79b3f16 | checkpoint | 2.5 - Concrete Placement
97a1d673-2eb4-508c-a832-4c685ed3e26e | note | FREQUENCY - Each lot
5672a7c6-b850-5020-99b8-41a586bc94a3 | note | ACCEPTANCE CRITERIA - Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
4f92c04b-6355-5eda-85fc-0fc019957751 | note | REFERENCE DOCUMENTS - VicRoads Spec Cl 703.23
9a5a751b-979b-54f8-9732-fb57febecab3 | note | INSPECTION / TEST METHOD - Site Inspection
f7b9d2c6-6a0e-53d2-b6cd-7d25abfa3247 | note | RECORD OF CONFORMITY - ITP Signed
8f539b1e-4911-57a0-87b5-078654b0f900 | note | IP
4e56c8ec-4bb7-5ede-ab07-2b0bc793c7d5 | note | RESPONSIBILITY - Project Engineer
71620869-8552-520f-aa03-e63256f906aa | textbox | Date Completed:
4ec4b650-43f3-41e7-83c2-69ab5b8a8347 | checkpoint | 2.6 - Finish Surfaces
e6d2d825-c63f-5353-b716-f9a0c88e38d7 | note | FREQUENCY - Each Lot
252cec8f-377a-5879-ba83-463b34a4b2c0 | note | ACCEPTANCE CRITERIA - All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively. Unless otherwise stated, 20mm Class 3 bedding shall be used adn compacted to a thickness of not less than 100mm. Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted. Steel reinforcement shall comply with the requirements of AS/NZS 4671, Minimum cover of 50mm
cf5ed4f0-37c6-50f6-9ae8-57c0e75eb6b1 | note | REFERENCE DOCUMENTS - 703.25
ebda6125-7de3-5e75-a7fb-e7da9df354a4 | note | INSPECTION / TEST METHOD - Visual inspection
638b3e63-7afe-55cd-bc43-15970b55e5d5 | note | RECORD OF CONFORMITY - ITP Signed
9934712b-e0f7-512c-89c4-e82c8625d5f6 | note | IP
b8c28c9a-c7fa-5aea-8eeb-c1943dc5e244 | note | RESPONSIBILITY - Site Engineer/ Site Foreman
b690186c-aaac-53ac-9b6a-0ce50d90e6b0 | textbox | Date Completed:
eb5c85f5-980c-411d-8f30-c593cd4a5303 | checkpoint | 2.7 - Joints
d4fa98f3-4c1f-5835-9274-dd62ded91eca | note | FREQUENCY - Each joint
932e44b6-4a4e-5de0-94dd-b77e8ff0e76f | note | ACCEPTANCE CRITERIA - Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section). Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
8fc89117-511b-59f3-8fb7-a97d26f31043 | note | REFERENCE DOCUMENTS - 703.26
04b0c2c7-0ead-586e-bc2e-e1af3da8e667 | note | INSPECTION / TEST METHOD - Verify
77ba3cc1-3abf-5da9-85f5-e4d1c5e750a7 | note | RECORD OF CONFORMITY - ITP Signed
05eef300-c678-5eff-aa13-75551c4bf51c | note | IP
b34def3a-7a2c-5780-854e-3f89a007a220 | note | RESPONSIBILITY - Project Engineer/ Site Foreman
0aba9302-24fd-53fb-81a9-07f707cee5e6 | textbox | Date Completed:
c4ccdf8b-23da-4b7d-8d97-8db7dab09a43 | checkpoint | 2.8 - Backfilling
1309cc54-507d-56ad-831b-a9f912265a74 | note | FREQUENCY - Each Lot
0c54d388-f7f6-529c-a5c4-abe49d4c2a79 | note | ACCEPTANCE CRITERIA - Not earlier than 3 days after casting. Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified. Layers shall not exceed 150mm compacted depth
135330bc-01de-5eae-a39c-02c1c2b107d3 | note | REFERENCE DOCUMENTS - 703.29
f7e727e0-d24a-5128-bab3-3020c68eb975 | note | INSPECTION / TEST METHOD - Verify
cc05f4dd-7ae6-5f12-8a72-6edf582fb09a | note | RECORD OF CONFORMITY - ITP Signed
6aa83af4-4a03-5c74-a18e-ea153f2cd4b6 | note | IP
f2b78353-d211-56e5-a8b4-81da704f6ff8 | note | RESPONSIBILITY - Project Engineer
ff0d1f10-c7f2-5593-8317-51571d97ac49 | textbox | Date Completed:
f0c2409b-957d-41a3-94d4-8278b792cb09 | checkpoint | Final Inspection
b422cef6-d523-538a-bade-1d4f2e875506 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
f57f54c1-701b-5938-9aa6-ffa82d1ebd9a | textbox | Print Name:
d69dec03-351d-5fcc-a301-d2a3a9795f67 | textbox | Position:
11aa90de-977e-5c79-8ca6-8167c9785ab4 | date | Date:
044c3e9b-bdfb-44bd-934e-88bf636a8249 | signoff | Sign ITP
| checklist | ITP-015 - Construction of Kerb and Channel Lot 3 | itp | ITP-015 - Construction of Kerb and Channel Lot 3 |  | 07a9eec2-a998-4dee-8591-682f28d82fcb
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
0db56379-a339-5e11-a21c-4122061e7f49 | note | FREQUENCY: Prior to commencing any activity
29527566-7b92-51e3-a643-a7fa4a20f352 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
a99322ab-f8c5-5a66-a1e7-03588689e7b6 | note | – using the correct and complete set of drawings
e462b4b1-0981-5218-9933-64e40fb5e4a4 | note | – all drawings are the latest revision
e8bdb755-4862-5f92-bf09-6aeca3437864 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
4284e696-77dc-5ad9-b192-6aa1ad08c323 | note | INSPECTION/TEST METHOD: Visual inspection
56b62640-6991-50de-9ed2-f4f55f85eece | note | RECORD OF CONFORMITY: ITP Signed
2cf2cb88-b39c-57ac-aa85-2e15a1da526b | note | HP*
0da10ba5-cfbb-519b-8652-f3689d396589 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
ef800834-6cf1-528d-860c-f1b2145bdffb | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
4b55be1b-f6b5-5d3a-a134-9707d4f54e75 | note | FREQUENCY: Prior to commencing any activity
ffd54dbd-7821-5bfc-a4e2-9ffc1bb639d8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
080bcd35-cb75-535c-9885-0c3ae63239a9 | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
689d1687-c3a1-576e-b417-673c35add27e | note | INSPECTION/TEST METHOD: Visual inspection
c5bec18f-9b03-5efd-aa8c-d6cc61d9937a | note | RECORD OF CONFORMITY: ITP Signed
b5d7cd8d-3c01-58b1-9f7c-a909a381ae1b | note | HP*
e49fb219-40d5-5ba3-abd5-3ef0306ba76a | note | RESPONSIBILITY: Project Engineer/ Site Foreman
258b3f31-151d-5c83-8d96-6a13d9d84331 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
fd44a052-bc32-5b6b-9fc0-044479a7e20d | note | FREQUENCY: Prior to start
5fe58ecb-a6ff-52e6-894d-be49badecf31 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
0ed820e9-d8d3-50eb-81cf-94d6abb27863 | note | REFERENCE DOCUMENTS: 703.17
96f59d35-127d-5687-a64e-ee42ffbf31b2 | note | INSPECTION/TEST METHOD: Verify
a5908340-6b66-535d-a0cd-7c63c04237ee | note | RECORD OF CONFORMITY: ITP Signed
9fb8adae-af2f-5f9b-89b5-c633f0f4151a | note | HP
f9084eed-8d18-53dd-93a1-eab2b983d5a1 | note | RESPONSIBILITY: Project Engineer/ Superintendent
699748c0-7c5d-5d41-b2f0-b6281b8988c1 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Temporary Drainage Provisions
5cdb542e-0eb3-5635-88c2-fc0aadd8cf18 | note | FREQUENCY: If Required
f40d87ae-4027-50e3-9829-aa002f79b7ee | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
761e8dd5-6b80-562a-8e8d-2523d26739c8 | note | REFERENCE DOCUMENTS: Cl 703.18
bb438046-2b16-556b-8e4c-77a4ea4685df | note | INSPECTION/TEST METHOD: Visual inspection
09406120-f627-5f74-891b-cca795644650 | note | RECORD OF CONFORMITY: ITP Signed
e7a06750-5ff5-5fa0-a4b1-dc33f9a3f54e | note | WP
8609281a-25be-5777-b58b-42cf871d7a60 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
2cadd3ea-19fb-596d-a478-8fdbee8d46ac | date | Date Completed:
| checkpoint | 2.3 - Bedding
7d618405-ce27-5080-af1b-930de33dc210 | note | FREQUENCY: Each lot
702dad0a-94cb-5942-ae30-664ae6de69dd | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
839c68c1-d667-5024-9ee9-533350a2442d | note | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
bdb1ab63-1e48-55e5-ab90-f028802de8fc | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
3f69426f-2994-5f7f-890f-fcfb22f165bb | note | REFERENCE DOCUMENTS: Cl 703.21
959c883d-5b27-5b63-ad70-62bb8b869f91 | note | INSPECTION/TEST METHOD: Visual inspection
c055d756-65bc-5867-8228-b8f8ec7b0e5d | note | RECORD OF CONFORMITY: ITP Signed
598cfcc8-e9a5-5d10-b68c-39b591edde1e | note | WP
b6aa4559-86b4-5bfc-896a-5092bf5851b6 | note | RESPONSIBILITY: Project Engineer/ Superintendent
3264a67b-e680-5eea-8c84-1e369ec6373c | date | Date Completed:
| checkpoint | 2.4 - Pre-concrete check
581806b3-8ae4-5b9b-b6de-1e513fb71568 | note | FREQUENCY: Each lot
fee71453-d819-5fba-9966-8c4eb703233b | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
690b3a02-fea0-58e3-a9bf-aa3ae4920dd0 | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
e079d716-25b3-5bff-a036-d6770d7a181e | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
f0b60ac3-13d8-5dff-ab6f-a87d64697500 | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
ab2878c1-8fdf-5cb9-93c0-6b7437b66ebd | note | REFERENCE DOCUMENTS: Cl 703.08
fc51885f-29d6-5b9c-bf25-bde091b6e47b | note | INSPECTION/TEST METHOD: Verify
7919f4ba-7640-5501-bb29-29ea35d08a8e | note | RECORD OF CONFORMITY: ITP Signed
18e92db3-3676-52db-87c5-ce104aee8c39 | textbox | Ambient Temperature |  |  | °C
b2c3a99b-3e06-55ed-a85d-d3b66edf9b9e | textbox | Concrete Temperature |  |  | °C
9d5352dd-672d-5061-aefb-36b318da1684 | note | HP*/ WP
b6c9018f-c362-5276-a302-8359191f2412 | note | RESPONSIBILITY: Project Engineer/ Superintendent
ad979461-9974-5f32-b5e5-ee8eaf56dcb1 | date | Date Completed:
| checkpoint | 2.5 - Concrete Placement
3f1b1724-4662-5425-bbd3-bfb29566718c | note | FREQUENCY: Each lot
338a3805-2e3c-5400-aa85-82487ee8df42 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
07b7fc4e-d562-5b22-97fc-73a2be84a75d | note | REFERENCE DOCUMENTS: VicRoads Spec Cl 703.23
2c3a8195-a38b-5f6c-8698-8732ded6958f | note | INSPECTION/TEST METHOD: Site Inspection
b9d00c0e-98b2-5535-b571-63a177dce1e9 | note | RECORD OF CONFORMITY: ITP Signed
22becfd4-264d-5666-a551-af98b87c30be | note | IP
8b6f5a1d-ee6b-5abb-ae52-01945cdd4352 | note | RESPONSIBILITY: Project Engineer
15f1e64f-85fe-542c-9195-2f3b6ef0a7ea | date | Date Completed:
| checkpoint | 2.6 - Finish Surfaces
4cb80c36-eddc-5d8c-a6a0-d38b435c9fa7 | note | FREQUENCY: Each Lot
7008eb13-a9c5-58f4-81c2-6432bf6ac6c4 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
e4e12d5d-f6fd-53b5-98cb-7f74be695800 | note | ○ Concrete to have a neat appearance and uniform colour
55dec1d8-efb1-51df-98c2-bb12af93e943 | note | REFERENCE DOCUMENTS: 703.25
ce206b9b-1e94-5da6-9c15-8038fd9f3c6a | note | INSPECTION/TEST METHOD: Visual inspection
a103c006-54d8-50ac-bf9c-52a458d2ea79 | note | RECORD OF CONFORMITY: ITP Signed
4ddf0bc9-bd3d-511b-948a-29fb228b0090 | note | IP
4e6a69fc-d572-5e30-93be-2f1961ba3db6 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
4ba9ed35-5a6e-516d-a3b6-1d4d5dd40458 | date | Date Completed:
| checkpoint | 2.7 - Joints
0780babd-6949-5cea-8648-d86d4dedc68c | note | FREQUENCY: Each joint
91915d46-c76c-52c5-a2fa-493bd75c41c9 | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
a2b82c48-ecf0-5ce1-ad77-a95e33c4f487 | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
a75bc4da-7b70-5cd7-95d3-62b46798a771 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
06c1ce70-70a6-5e90-83c5-f6770bb861bc | note | REFERENCE DOCUMENTS: 703.26
41f2d82d-7e29-5be2-9c2a-b28b3f31ba1c | note | INSPECTION/TEST METHOD: Verify
7d154734-ffb1-5942-a1d2-73fdd7da84b6 | note | RECORD OF CONFORMITY: ITP Signed
3b7950c0-474c-5826-89bd-debc8c312f3e | note | IP
2576036e-8358-5c17-be1a-f22c10d8868d | note | RESPONSIBILITY: Project Engineer/ Site Foreman
319e7853-222d-53b3-b771-96675469ef21 | date | Date Completed:
| checkpoint | 2.8 - Backfilling
90b45301-8dc2-5693-82c8-2ce86e697bee | note | FREQUENCY: Each Lot
ea456e6d-43e7-5d03-aba2-8cd5aedba2cd | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
eb82b5f3-7ee0-5685-a76c-454dafd0aa61 | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
59eb3f34-0101-54f8-809c-7b1ba05d9adf | note | ○ Layers shall not exceed 150mm compacted depth
11da8d74-302d-56df-a87a-85cbb4ebadec | note | REFERENCE DOCUMENTS: 703.29
4acece7f-e3f6-54f9-833c-337fbd8f03b5 | note | INSPECTION/TEST METHOD: Verify
be9b6e9e-1d65-55ef-80f4-2812c997fe7b | note | RECORD OF CONFORMITY: ITP Signed
bb548216-d8ba-55e8-bcdd-93e590e971d1 | note | IP
69b0b790-7352-5672-ab7a-7cfd3b8ebdc6 | note | RESPONSIBILITY: Project Engineer
85d69f88-1076-5a9f-90cc-e1e03ceb5aac | date | Date Completed:
| checkpoint | Final Inspection
44816846-c2f8-54c6-8922-6a7d14fd1204 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
beeec65d-b4b6-5171-bc7c-e72e515328ea | textbox | Print Name:
02dea02e-0628-5d71-b4d9-557cedf679ff | textbox | Position:
86bdd75c-dbbd-5f57-8702-cab483a0ec6c | date | Date:
| checklist | ITP-015 - Drainage Checklist | itp | ITP-015 - Drainage Checklist |  | f6cd55d0-eaf3-43cc-a503-3c65808da246
| checkpoint | Pit Details
afd16bda-97e3-5754-8cbb-5ee0a29304bc | textbox | Pit No.
bb7ea087-37fb-5cd4-a859-16092d3bfe5f | textbox | Pit Type
3700b52b-7d10-594f-95f2-b8e9dab30909 | textbox | Dimension
41e518d5-d2c6-5512-b24c-a7bc2898354f | textbox | Inlet Level
2ab54a67-4535-5730-b9c8-a8be2f5c6bb4 | textbox | Outlet Level
c1384ddb-1ec4-550c-bd3c-4778cc89c5c9 | textbox | FSL
290caf0d-9fba-5a85-a0dd-73e9cb030aad | textbox | Pit Depth
| checkpoint | Checklist Items
ac624d40-08bc-5426-9b5b-c423dd5c0b32 | textbox | Drainage Line Number
daa29e46-8508-5a48-b08d-f361bd3ae10f | textbox | Pipe Size
e4639f21-6947-5345-a311-15e53939e1f9 | textbox | Trench Width (mm)
499ecc76-afc3-516c-88d2-3c7a49542bfe | textbox | Minimum Cover (mm)
d2056b63-946c-5f28-b703-ec88f0006d41 | textbox | Beading Depth (mm)
ffd080c2-bbf6-53a0-9d39-930b9730536f | date | Start Date
515a47c7-7afb-50ee-b28d-2539758af222 | date | Finish Date
| checkpoint | Pipe/Pits/End Walls
3cfaf860-9b55-5617-b805-a33a0edf6914 | note | Pipes/Pits/End Wall in sound condition?
d4d0a798-2bbd-5bd2-86b0-698bcc3f625c | date | Start Date
829e1b3b-f075-58d3-bfe4-8c32bdbba046 | date | Finish Date
| checkpoint | Laying Direction
870fdf83-eae7-550c-8b8f-51b95043010a | note | The direction of Laying Satisfactory i.e Collar on Upstream?
ff9b4f1b-9a73-5a34-be7c-4fbdaac7d65d | date | Start Date
a56660c3-2851-551b-b087-3dbea48313df | date | Finish Date
| checkpoint | Rubber Joint
f90311b1-ba4f-5fec-b632-b87d0bcff459 | note | Rubber Joints in Satisfactory condition?
c4ef5e28-032f-5e32-96aa-dea191a1df86 | date | Start Date
3399d266-167e-5a7e-960e-a90cefa99f68 | date | Finish Date
| checkpoint | Gap Filling
97d086c1-dac2-5af5-8835-2f81a6f7f8bc | note | All the holes have been mortared to satisfactory condition?
2d35c2c4-4f3d-540a-b840-2305de4e50f9 | date | Start Date
9d077d7d-e1de-5a54-b9ca-c5dc9f487873 | date | Finish Date
| checkpoint | Step Irons
6448d217-65bd-5977-b378-0e887266a884 | note | Step Irons Installed in the Pit greater than 1000mm?
1a6d2c1e-2d63-5ae4-aa0c-ccdb11fc4325 | date | Start Date
4334c58c-5249-5bd2-82b0-431bad66f96a | date | Finish Date
| checkpoint | Final Inspection
4e42773f-3821-5e50-a586-f0f5f566380c | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
6db91f04-ea88-5494-894e-9f5a266a884d | textbox | Print Name:
2d884928-1d04-5d03-b9a2-196391ae2f4d | textbox | Position:
85dc6342-20eb-5e07-af92-556a8c64f6fc | date | Date:
| signoff | Sign ITP
| checklist | ITP-017 - Sealing Works - Asphalt Laying Works Wearing Course | itp | ITP-017 - Sealing Works - Asphalt Laying Works Wearing Course |  | a605412c-6a63-4696-b72d-10dcdc7e0057
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Submission of Mix Design
4692b87b-7a6c-5408-af4e-f42e3421a462 | note | FREQUENCY: Prior to commencing paving
1d08b2d9-6cc6-50cb-b241-10c2f31b9e5d | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
061523e6-37a2-5f5b-9a7c-acaf1bbea746 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
2ff65277-72ec-5c30-9844-605d9131d72a | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
120a16c7-21e6-52a9-bd8b-24f74e0283bf | note | RECORD OF CONFORMITY: VR approval, Completed ITP
1ed7dbfe-4d1a-525e-9090-c9ce3ea9dc84 | note | HP
ce361e84-2005-55d5-b652-053a58d3f340 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
5f891a24-4ae5-5a48-9f16-593163f84739 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.2 - Implementation of all measures and controls
61c9b126-c5ef-52b4-945f-2b1a7490b237 | note | FREQUENCY: Prior to commencing any activity
ee0ba9bf-059c-5a20-a26c-ff75f94118d1 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
4beffc76-e949-5fd2-926b-31ed8d5c1c3a | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
9a88589e-ae9b-5898-873f-2b79ad260825 | note | INSPECTION/TEST METHOD: Visual Inspection
81a35e4c-cf49-5ae4-be84-664ff1696db3 | note | RECORD OF CONFORMITY: This ITP signed off
f21c07f6-8fc7-5f25-8924-5d54b01cc8fc | note | HP*
c50d3067-be2c-526f-be06-d82d090bc842 | note | RESPONSIBILITY: Site Engineer / Site Foreman
53c9cc0b-a5d8-5aa3-aa45-2886568e14b2 | date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
7e505552-aeb2-53e1-b710-6e19d439d129 | note | FREQUENCY: Prior to commencing paving
cd390876-67ab-5493-a61e-97631561157f | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
cd1667f9-9c47-566e-8f6d-3cac8c602928 | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
703adc7c-a6b8-5210-b2ad-6b995d196f92 | note | INSPECTION/TEST METHOD: Visual Inspection
ffa72f68-f484-51d2-82c1-e2993d0a2759 | note | RECORD OF CONFORMITY: ITP Signed
1d78c97b-b9ab-5d86-9a37-2011a1930ec3 | note | WP
61abe045-75d4-577b-a880-590f6a68c1fb | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
f6711656-9ca9-5d40-973e-32052df04bca | date | Date Completed:
| checkpoint | 1.4 - Ambient Conditions for Placing
d3aca5bd-7ebb-5d55-8576-0cd8e07e63a5 | note | FREQUENCY: Prior to commencing paving
70e44bde-21db-5919-8789-9cc5653e3c2b | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
c40b921b-36c8-5f69-8ba0-d6c2a8038b11 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or
aeea5340-14eb-51a0-a564-1ba53af07b50 | note | ○ 10°C for PMBs & Class 600
ffacdc47-f04f-59b8-9a1a-f7e733c4d177 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
c39eb953-8475-5870-88a6-4b9c2c25f910 | note | REFERENCE DOCUMENTS: 407.13
3eefab4b-3c8a-59ca-b2b1-f840ad03a75f | note | INSPECTION/TEST METHOD: Verify
f941f327-1ea8-5922-baf9-c228808b7fc6 | note | RECORD OF CONFORMITY: Thermometer
f8560b3b-18d7-5136-9ff5-20fc5e43fbd2 | note | IP
a448227d-7f84-5632-bfe3-9a3e8065b586 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
2de09104-109f-5b51-9942-7a3a23727b6b | date | Date Completed:
| checkpoint | 1.5 - Planning of Joints
d5996d7c-4c92-56a3-adbe-da0f614081f2 | note | FREQUENCY: Prior to commencing paving
22d739da-d3f5-5e12-8397-974a45b84bc7 | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
30a787de-5860-5f01-9334-ea6f075a4b88 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
61867d59-a4e9-54df-9660-a6c0b9923587 | note | ○ Longitudinal Joints Offset from layer to layer by at least
c2d8c4ee-efbf-5b0a-912d-2b8bc35523c0 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
85f027d5-0008-5b0a-bfbb-d9a4afe8661f | note | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
295cde18-70b1-5dc0-9769-35447cfc681f | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
9263556d-bdf1-5f68-b8d8-9e2a9f471d24 | note | RECORD OF CONFORMITY: Paving Plan
9eb35678-ba6b-5b5a-810a-8b3b7d0cadc3 | note | WP
2d27e678-ca63-5b56-a389-ac0ff3cc9975 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
f474fe06-ce8f-5d12-bfdd-54d284b7c3f1 | date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Commencement of Placing
b10ccee0-923a-51d1-8f38-7dc923397433 | note | FREQUENCY: Prior to commencing Paving
e3bf4161-83d8-5be6-b762-5eb0feb1bf52 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
3ff09de6-6ea5-5f42-b8d9-4a61aba1f291 | note | REFERENCE DOCUMENTS: 407.18
14818c26-bbbb-53af-bf65-0b4bfef2930d | note | INSPECTION/TEST METHOD: Visual Inspection
b637a0db-395e-5e02-ad51-e373d972a555 | note | RECORD OF CONFORMITY: ITP Signed
6466460b-feaa-5a13-a70f-2bda67fdc69c | note | HP
8ac862fe-b218-55cb-9cab-fe94207906a3 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
6e4ebfdb-300c-5043-9d21-96dc6ee7aca2 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Delivery of Mix
ae323c4f-587e-5170-ad63-5c6391a57df7 | note | FREQUENCY: Each load
7fb1c84e-3a3b-568f-b3e1-b8f601ecdff4 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
4e9a7d8b-d9e3-5c29-bbec-6c78b0066a7a | note | REFERENCE DOCUMENTS: 407.16 Table 407.081
6f567db2-bb93-5fc8-a1fe-b79e37082cb1 | note | INSPECTION/TEST METHOD: Visual Inspection
15a6ac36-856f-51be-9694-c87cb829708c | note | RECORD OF CONFORMITY: Delivery Docket
88082ee5-e877-5887-91ed-ec7751ea84e9 | note | WP
5021cfaf-e8c2-5a0c-b077-a712a4bbc60c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
9ad96c1e-1bb6-5bd4-bc6e-e19627311ec9 | date | Date Completed:
| checkpoint | 2.3 - Traceability
79bc8212-05a6-5052-8490-f48df0575241 | note | FREQUENCY: Each lot
6835db5f-1039-5597-a4e5-bcbe4765afdd | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
675352bb-cff0-52e4-b1d8-00c3bddf99f0 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
4778d115-cfb8-5256-b8c9-a45b42d31bec | note | INSPECTION/TEST METHOD: Verify
316aa784-b8e7-5e44-9ed2-824fac28a7ad | note | RECORD OF CONFORMITY: Daily Lot Record
088cbd46-52dd-59d5-9915-a2bcf9a2687e | note | IP
0bd49da4-98bf-574c-bb93-8f9db99faddc | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
d2c205fb-2f71-58a2-952b-9242d9957ca7 | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness and Level Control
950bb175-84e6-577a-810e-3e8d2c8ff85a | note | FREQUENCY: Regularly during paving
cb0fe24e-a68a-530b-922f-2bc8c13d15b6 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
50ee4c5c-bc75-5960-87d5-2e0679c51649 | note | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
1eec13ec-22d5-5a72-b358-107a95338967 | note | INSPECTION/TEST METHOD: Verify
5f81f8f8-2d8b-5f50-be22-0f71a51d3486 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
dc24ef86-84c5-5418-a739-e3e80e25eaaa | note | WP
6157d4c7-5a44-5226-b364-109b9966e878 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b53cf587-9758-5dcd-9095-0e27de0b38fa | date | Date Completed:
| checkpoint | 2.5 - Surface Finish of Wearing Course
b920a192-3aed-5eae-a8de-b3b6e83c779c | note | FREQUENCY: During paving and after final roll
33dde318-18a1-59f1-8671-ae8be2c7e0e1 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
ea72e623-cb73-5b8d-8f86-c33a2616ef64 | note | REFERENCE DOCUMENTS: 407.23 (a)(i)
90a60236-1e0a-55f3-a314-0d8bf95b9f49 | note | INSPECTION/TEST METHOD: Visual Inspection
54212481-c4e5-502e-a9a7-72bed6ed0779 | note | RECORD OF CONFORMITY: ITP Signed
cf27fe8c-fe0e-54a4-906c-142337e3a26d | note | WP
0d49b6ca-e264-5e8c-879a-98728b49c7d2 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
37ef74d1-1a6b-5110-81cf-6a2cfbf56a64 | date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel
b11d805b-15d8-5b6b-878c-9ef596401838 | note | FREQUENCY: During paving and after final roll
d58fc459-323c-56be-9c90-a9ffaa1640dd | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
a5146ac6-d48a-59ca-84df-939ff847115f | note | REFERENCE DOCUMENTS: 407.23 (a)(ii)
23f803c4-c56b-5846-a8d6-d974bb7e701b | note | INSPECTION/TEST METHOD: Visual Inspection
6be10762-b92c-5f22-84bb-aa4b96199d44 | note | RECORD OF CONFORMITY: ITP Signed
33f7b6e9-2fb7-5513-8b8f-4f793b63d278 | note | WP
e9893d50-bc5c-5da0-abcc-ea145cfd01b4 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
67e49caa-00d5-5a18-b45c-c0ca71102ada | date | Date Completed:
| checkpoint | 2.7 - Alignment of layers not placed against concrete edge
5e5f34f9-4646-5dd8-9c9c-1c4c088819f1 | note | FREQUENCY: During paving and at completion of work
b72359a7-495a-5fbe-aae7-7339d1c5bb8d | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
a54ab0c6-47e5-513a-8003-8480f68d9e69 | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
75bd93c0-cc21-5e76-9106-6badc84b5f05 | note | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
c5cd043a-1b0f-540a-b568-173ed32fc1d9 | note | INSPECTION/TEST METHOD: Visual Inspection
e8a64cf8-22df-5edf-b24d-b344988072dc | note | RECORD OF CONFORMITY: ITP Signed
c528bf6e-d856-56d5-aa21-0ba9921ccac0 | note | IP
beb62355-1d2a-5abd-8dfd-f94fe799ba69 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
cfd1fb93-fc8d-5ac7-a337-ae069adc744b | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
4fc0a644-c053-54d6-8c0d-f3d5f6b732f9 | note | FREQUENCY: Per Lot
d4af723d-ada1-5a75-855e-1f808099bb2a | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
7c115518-05bc-59c4-870e-4fff2c903d4e | note | ○ 94.0% or greater Accept lot
0c205af2-182a-54f3-97ee-8da04e927e02 | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
7f0b22de-217d-59cb-8dda-fb6e07f52ce9 | note | – For layers ≥50mm, if characteristic thickness is:
dfd54da6-abfc-595e-af97-bb89d77c4c7f | note | ○ 96.0% or greater Accept lot
ec6cb276-3cd2-548b-a814-f81cfbd919fc | note | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
6a36741a-efd4-5af0-916d-b5a138fb2bf5 | note | REFERENCE DOCUMENTS: Table 407.221
5a421b23-c3a2-510a-993a-6130df643a8d | note | INSPECTION/TEST METHOD: Verify
e5a7b290-7645-5ea3-942d-f69987830d82 | note | RECORD OF CONFORMITY: Test Report
a5adc420-da35-5c69-938c-408f8ba94b3b | note | TP
2eb11658-0981-5a37-a4a8-07a60e56141f | note | RESPONSIBILITY: Site Engineer/ FH Lab Technician
69d73077-2fa6-5123-8604-afdc7a933b42 | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
4fd8739d-98de-50ea-a0a4-4c10fb736d6d | note | FREQUENCY: Per Lot
28bfc66c-3196-5433-a4ea-f36f69807ac9 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
bb8d0aa0-6aa7-5824-a228-8eb3d0735f45 | note | REFERENCE DOCUMENTS: Table 407.232
9fbef500-efb0-5cec-a1db-a44415bac862 | note | INSPECTION/TEST METHOD: String Sheet
505c6ba6-fafb-5492-9ef7-5b9113140708 | note | RECORD OF CONFORMITY: Survey Conformance
161ad2ed-7c5f-5020-9123-e35b70fb517a | note | SCP
a1d3c2fe-7369-51ce-972a-f89bc502d789 | note | RESPONSIBILITY: Site Engineer/ Supervisor
4680424e-0ad2-5c9a-9f0d-2c8773f1c419 | date | Date Completed:
| checkpoint | Final Inspection
ef7b0f6b-b714-5f56-98a8-a8b28968d4b8 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
645eef4e-747f-5185-9903-a1c0778edc48 | textbox | Print Name:
d12ed089-2cd4-5c41-9969-d1777ef36485 | textbox | Position:
73614502-829a-5ee9-9650-0adbd0368130 | date | Date:
| checklist | ITP-033 - Insitu Concrete Pit | itp | ITP-033 - Insitu Concrete Pit |  | f6d42c31-7f1e-4955-a6b8-5b3d217d24c3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
d2fee0e1-0667-5aba-89f5-b5bb7059e6de | note | FREQUENCY: Prior to commencing any activity
a64c400e-e46a-5b24-b109-97b34ad12fad | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
7f505dc8-a8b2-5fd5-9241-266924951d7f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c6c74848-c69b-592a-8f83-a1c459c22d6d | note | INSPECTION/TEST METHOD: Visual inspection
e82db2aa-1c70-5d14-a3b6-d9e6c058a9ec | note | RECORD OF CONFORMITY: This ITP signed off
164e1381-6df2-5a8f-ba62-694d85764731 | note | HP*
39513db2-915c-5283-95ce-c9fe04352db6 | note | RESPONSIBILITY: Fulton Hogan Engineer
016506ab-0b84-5674-9718-f6eebc0926a5 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
064946f2-4e1d-58d4-a534-db5d51602a3f | note | FREQUENCY: Prior to commencing any activity
3f40ab71-5525-58fd-bbc5-2dc1b1d89cf5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
6f7bd837-d81e-5f8d-a031-954b9f672889 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
7f0149ae-efcd-502c-92b7-1c53e7b2e5d3 | note | INSPECTION/TEST METHOD: Visual Inspection
ab522447-74c3-54ac-9664-e22b6f5feebd | note | RECORD OF CONFORMITY: This ITP signed off
f486f5fb-d69a-5267-8a52-5d684e35e4dc | note | IP
3b1b9766-2d68-5b64-8c84-524936092866 | note | RESPONSIBILITY: Fulton Hogan Engineer
22d469f2-f174-5e34-8eb2-2ce961355fc6 | date | Date Completed:
| checkpoint | 1.3 - Pit material classification
46725239-b535-5ff3-826a-b67452dc2803 | note | FREQUENCY: Each delivery
fc11dd8e-db4a-5ad8-b59c-4c975d3ff6a0 | note | ACCEPTANCE CRITERIA: Concrete used shall have a mininmum strength of 32MPa and be
ce7af96a-fb08-5272-b0f7-5eef2d38da99 | note | ○ Steel fabric shall be F92 reinforcement
bd39df97-3ff4-5f94-a432-04a19538032c | note | REFERENCE DOCUMENTS: SD1131
18f5fe3f-fcd7-56b0-a36e-8b2d0603e8a0 | note | INSPECTION/TEST METHOD: Visual Inspection
90fb1210-ae45-588a-b2a4-b9cbfd516e22 | note | RECORD OF CONFORMITY: This ITP signed off
65963e5c-5aa2-55e8-93e0-d7916a441a53 | note | HP*
f7f88f0d-73b1-566c-8c9a-e29b1bc4e65d | note | RESPONSIBILITY: Fulton Hogan Engineer
c04d68d8-a557-59dc-bd6b-e651b2d9f13e | date | Date Completed:
| checkpoint | 1.4 - Backfill and bedding material classificaiton
136c9d09-c4fb-541f-8dd3-c8f95224a23b | note | FREQUENCY: Prior to start
a8efa5cf-ce5a-5820-82f8-f654dcc6f430 | note | ACCEPTANCE CRITERIA: All crused rock used in the works shall be Class 3, 20mm nominal size.
2b2d3e52-af21-591e-8230-6e9a077c84a7 | note | REFERENCE DOCUMENTS: Cl 18.0
e8bc3937-0293-5a31-bdfb-0fbae98adf7f | note | INSPECTION/TEST METHOD: Verify
992c7840-36a2-5261-a126-e555d1ddbd68 | note | RECORD OF CONFORMITY: Test reports from supplier
26d382bd-e103-515b-8823-b1cd982fec7a | note | HP*
b51ccec8-37c4-5d06-a202-d8bd0c2aa899 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccfc4a0e-9a3d-52fc-bbc1-1c451ee209fe | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Set out pit location
55048f6f-7933-51c9-8f7a-a11dd32e0958 | note | FREQUENCY: Prior to backfilling
654bd121-0cbb-5cbc-9476-679982d18db7 | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings.
90bb07e6-e9f0-5d73-a406-c9bca3c8a780 | note | ○ The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
eb8bef06-39f6-53ef-8a1d-92bfd775ab90 | note | REFERENCE DOCUMENTS: Survey file / Drawings
88a643b3-01ab-5ab5-8503-7d6ce4001ddb | note | INSPECTION/TEST METHOD: Survey Conformance Report
79ac9217-fab2-58ec-a3d9-10e2e9940d77 | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off.
7248f055-07f2-5e6b-b839-2c868689f351 | note | WP
ea7f3493-b614-5ddd-ba7c-3a4d1da4a623 | note | RESPONSIBILITY: Fulton Hogan Engineer
b202e58d-d3d1-5199-8996-5ee668a2960d | date | Date Completed:
| checkpoint | 2.2 - Excavation
79a5442a-3201-562f-b6eb-17437fcb9528 | note | FREQUENCY: Each trench
b185968c-2c95-553b-98c6-608200b56216 | note | ACCEPTANCE CRITERIA: Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed.
9c7841e3-f175-5b83-9a88-eebea22aa2a5 | note | ○ Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m.
c383545d-7918-5b68-a10c-c6f6c0cbabdb | note | ○ No stockpiles within 2m of end of the trench to reduce bearing pressure.
1f094809-4c54-55b8-8cba-9aa8707bb64f | note | REFERENCE DOCUMENTS: Section 705
411e0c00-1395-59f6-b021-b6ca5a4bbf6b | note | INSPECTION/TEST METHOD: Visual Inspection
0cb9023a-905a-51f1-8fbe-94235b418d9e | note | RECORD OF CONFORMITY: This ITP signed off
09fdc915-4b02-53d5-b9ee-bfc68c12b843 | note | IP
da13b012-cf48-582c-8595-1aa380b0e9bc | note | RESPONSIBILITY: Fulton Hogan Foreman
174cefd1-5819-5b98-8d6a-d34142c29599 | date | Date Completed:
| checkpoint | 2.3 - Inspection of trench base
eb50bdd6-09f4-5bee-bfc0-9aba0b3fa4d4 | note | FREQUENCY: Each Lot
9b4034c1-39c5-5c6b-a0d9-fbd50517b782 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
978162dc-17e4-5288-a790-b04af8ebc3d9 | note | REFERENCE DOCUMENTS: Section 701
ddbb48ae-fbd7-58b9-b8db-6fb6fd858ee7 | note | INSPECTION/TEST METHOD: Visual Inspection
6833aa94-5776-5f2b-bd97-51be2f4d19b0 | note | RECORD OF CONFORMITY: This ITP signed off
61782a38-3a2a-57e5-bfb1-f515effe6e7e | note | IP
a677a5c3-d337-54d3-8626-fc102eaa30da | note | RESPONSIBILITY: Fulton Hogan Engineer
ffeccc75-5c3f-522f-869d-398f8c035926 | date | Date Completed:
| checkpoint | 2.4 - Placement of bedding material
a342e09d-ea15-5ad5-b43b-38aec435404e | note | FREQUENCY: Each Lot
01fa77aa-3ea3-511b-beca-7011e057512b | note | ACCEPTANCE CRITERIA: A 100mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
adfe8992-bfd7-5d60-ac04-643135681a5e | note | REFERENCE DOCUMENTS: Section 701
133f2341-0f6b-522e-8773-a5ba92ee9a8e | note | INSPECTION/TEST METHOD: Visual Inspection
03eb5d3f-283f-593a-b386-1f6a7e52e0fe | note | RECORD OF CONFORMITY: This ITP signed off
a8d8401b-d322-52ec-b45d-02bb603cdb09 | note | IP
2cf016c3-0f87-5556-849b-820bef1abe28 | note | RESPONSIBILITY: Fulton Hogan Foreman
ac5f8b37-2697-5173-8c53-6e529ab6d193 | date | Date Completed:
| checkpoint | 2.5 - Concrete pre-pour inspection
61ac588d-ce20-51c4-acc1-631969070418 | note | FREQUENCY: Each Lot
d23a5a8f-904c-579d-bb25-61ae30947f30 | note | ACCEPTANCE CRITERIA: Confirm minimum wall thickness and Mesh Cover as per SD1131. Inspect bedding to confirm is compacted to correct depth and free of as water or debris.
1da0e998-ba11-52d3-bf69-8ff565b45a1f | note | REFERENCE DOCUMENTS: SD1131
27488d6f-8d6c-540d-af27-20253f2f02b6 | note | INSPECTION/TEST METHOD: Visual Inspection
a161e1ad-aba5-5cb7-b205-05df0be2ff2a | note | RECORD OF CONFORMITY: This ITP signed off
9ed64570-479b-5f67-b807-31994b2cca32 | note | WP
a46034cc-3d78-53b2-9c5a-fdd411f3f476 | note | RESPONSIBILITY: Fulton Hogan Engineer / DPT Superintendent
8c7e7de7-e2f1-5673-ba5c-250b73b92309 | date | Date Completed:
| checkpoint | 2.6 - Concrete pour and pit construction
0c94e257-8129-5a67-a06e-edd318d8e54c | note | FREQUENCY: Each Lot
2fe9377b-0292-5946-a3fa-0d5d5208ee0d | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with Vicroads Standard Drawing SD1131.
ccaacd9f-c658-5b4e-ba2b-19a37f48332d | note | ○ All pits are to be constructed in accordance with Vicroads standards 701 &705. Pit should also be constructed in accordance with site specific drawings.
3aa9f6ba-f004-51e6-88e2-531369de32db | note | ○ Concrete Vibrator must be used
30963914-a864-5892-ad9b-afddfa38911c | note | REFERENCE DOCUMENTS: SD1131 Section701 Section705
a2bed984-53c9-542e-9a6d-a77eca7d34f7 | note | INSPECTION/TEST METHOD: Visual inspection
c767312f-e491-5394-a589-b59e738f366a | note | RECORD OF CONFORMITY: This ITP signed off
4a75f487-7517-5823-8c5e-5114ad75b5b8 | note | IP
9ffcdf09-68f8-5c68-8e7a-42f15da67396 | note | RESPONSIBILITY: Fulton Hogan Engineer
2825ab80-68e1-57f4-9e14-b55e9ef50528 | date | Date Completed:
| checkpoint | 2.7 - Pit base shaped with concrete to match pipe invert
d9619fa9-b57e-585d-804e-c1809e45c41b | note | FREQUENCY: Each Lot
71af7179-1c00-578a-a81d-80a2f83a6d74 | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing SD1131
a715f32d-4598-5a62-9331-5eb0a4efefc2 | note | REFERENCE DOCUMENTS: SD1131
98de3688-2ee6-5f1b-8fd4-136d90b70f6f | note | INSPECTION/TEST METHOD: Verify
adb51ced-75db-565d-acce-cd5ad4aa25a2 | note | RECORD OF CONFORMITY: This ITP signed off
beb8e344-197c-5abe-b64d-2e31827672bd | note | IP
fde3592c-0fca-5737-91bf-03bfa9abc154 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce307d7d-c75a-5197-b0d5-23c2777e4aa5 | date | Date Completed:
| checkpoint | 2.8 - Placement of pit covers
9d5ae23b-6759-5d46-9f36-533e37b1b8e0 | note | FREQUENCY: Each Lot
bdcbc5ba-3ec6-5fce-8f1d-45dd1509a696 | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard Vicroads specificed on the drawings of appropriate class.
5b392b55-ee40-54cd-87cd-588e29f65e33 | note | REFERENCE DOCUMENTS: SD1131
7ef934ef-c64a-5f94-842f-ef775064cc6b | note | INSPECTION/TEST METHOD: Verify
f0ff9872-f14c-54a4-be0d-5373c43a1f88 | note | RECORD OF CONFORMITY: This ITP signed off
d2b59316-4ec6-573c-9251-d3c106ab905d | note | IP
36fc8b18-d706-5a2e-8eb6-b93e403d23fb | note | RESPONSIBILITY: Fulton Hogan Engineer
03eafdb7-f816-5aea-905a-ee66944a9eb8 | date | Date Completed:
| checkpoint | Final Inspection
007dd8c3-9290-5348-bd4e-03b8268e9011 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
aaf16f3e-f913-5d27-9239-509113ceaeae | textbox | Print Name:
2f641e6b-c647-5c3b-a01d-36ae1fc246a6 | textbox | Position:
0966e487-29c9-53bb-ae9f-e60c7310789d | date | Date:
| checklist | ITP-045 - General Concrete Paving | itp | ITP-045 - General Concrete Paving |  | 31e44898-df83-4487-b1cc-5d63c9e2acd3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
eee305db-0ad2-5699-b288-4788c2b43125 | note | FREQUENCY: Prior to commencing any activity
c8d7bea0-57cc-583c-9fd9-b621043824cf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6b9c67dd-4cb9-5f4b-9744-4e7527ee10ca | note | – using the correct and complete set of drawings
3efe8d84-93fb-583e-bc2b-451f4118c0b7 | note | – all drawings are the latest revision
31b372e6-c70b-5e8e-b17b-8f237045cce6 | note | REFERENCE DOCUMENTS: IFC Drawings
38ee64f2-e227-5668-bfab-9ec0daf653ba | note | METHOD: Visual Inspection
7f692d85-cf72-5493-8c74-aaef275660b4 | note | RECORD: Signed ITP
45436503-1205-5db6-96ee-9a9e0dfc19a0 | note | IHP
fdd44d80-f5cd-5032-bfb5-8f806677d98e | note | RESPONSIBILITY: SWA Project Manager
8f7436cd-24d0-54e5-af47-eaeee43eef71 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
9f91c3b5-48be-5d37-85a0-8256be9ca02d | note | FREQUENCY: Prior to commencing any activity
93c0e39a-a5f8-5024-8170-a9a032969438 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
0d4b03c9-0adb-53ab-befb-105153d6be76 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
03b7fbd0-c5c4-5500-a36e-404816c634db | note | METHOD: Visual Inspection
0e717617-a77c-522a-8569-c6d075d69eab | note | RECORD: Signed ITP
88dddc8f-70a7-5945-a81b-4cb883b91b85 | note | IHP
2dab62d2-2af2-541a-baa5-45ecddeaafad | note | RESPONSIBILITY: SWA Project Manager
0c45d27c-a007-5bf8-8f0c-28f42159517f | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
abae3e05-7160-545e-a830-bc34f458e2b8 | note | FREQUENCY: Prior to commencement of excavation.
b4301f2d-b7b3-5195-ad81-984de74540b5 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
02d60dce-893c-51bf-a329-de97b920bb44 | note | REFERENCE DOCUMENTS: Work Procedure
97460939-0a43-504b-87a3-7e7a2c0a03e2 | note | METHOD: Verify
f09ee51f-e536-52c2-9ac9-de3e2305bacb | note | RECORD: Signed ITP
12b8d6be-108e-5097-a66e-99ebd8a9eca4 | note | IP
d8157272-ebae-54db-a99c-80b3065efb5e | note | RESPONSIBILITY: SWA Project Manager
02b04572-69a8-53d1-818b-757e80e6a654 | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
03252232-fe2e-5a4d-b036-738dad4895a7 | note | FREQUENCY: Each Lot
8af09b81-6abb-5249-a7bb-ab137bc4f8cb | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
c07e38af-35e2-5e79-b28e-0fc068c3c13e | note | REFERENCE DOCUMENTS: Excavation Permit
4a361387-65a4-5272-b5ec-4388fde85aaf | note | METHOD: Verify
856122d7-7ff0-5172-91bd-85e294e46ccd | note | RECORD: Signed ITP
97cbc96f-7798-5c85-a32b-0160f8864d66 | note | IHP/IP
45a8e1bc-177e-530b-8779-e42edbb64f42 | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
ab6dfcee-9cc6-5b21-bec3-6a58e2b39ce4 | date | Date Completed:
| checkpoint | 2.3 - Formwork
b3b985c0-28db-545c-8d82-3d36a4cfa80e | note | FREQUENCY: Each Lot
9ee77081-b54e-5159-bcb7-ea45c4ac6a7d | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
b760cfe0-e69e-511f-8e5e-33a77b7c533f | note | REFERENCE DOCUMENTS: AS 3610
89f51154-a6d6-5e74-8575-0ab43c80eb8e | note | METHOD: Site Inspection
84f7f7fe-b106-520f-8f37-4718d9860513 | note | RECORD: Signed ITP
e7d3d7a3-84e2-57cf-8274-2b32d9c52d50 | note | IP
ba5a65f5-ec86-5068-a12f-628344a3522f | note | RESPONSIBILITY: SWA Project Manager
43b7d9d1-2223-565c-8c60-93cfb407a4c2 | date | Date Completed:
| checkpoint | 2.4 - Reinforcement
d977ed63-365a-5784-8115-9cb77129d6b8 | note | FREQUENCY: Each Lot
9fbdaaf1-a7a8-5a80-a574-d0f94a16fe47 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
deed33a2-cf34-5341-b812-33d94defdda1 | note | REFERENCE DOCUMENTS: AS/NZS 4671
bb66d9c4-36e8-5292-a3fb-894b1e131ce7 | note | METHOD: Visual Inspection
ab682694-8311-5184-8de8-d53d35473aa8 | note | RECORD: Signed ITP
b7836cc6-a210-5599-aefc-3a2b6b85f24e | note | IP
50cb1299-6081-5559-93fd-20d8e6674e5a | note | RESPONSIBILITY: SWA Project Manager
923e47b5-5730-54a5-aef7-ac426c05fb6c | date | Date Completed:
| checkpoint | 2.5 - Temporary Drainage Provisions
24f4c914-4947-5a8f-8ec7-2ecca6acae77 | note | FREQUENCY: Prior to commencing
3169cfbd-1019-5fc7-a713-0752a938f562 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
a5994913-35dc-5e73-8d0d-3af76faf0e42 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
fa7ae607-c8e0-51db-8357-442afacae9ea | note | METHOD: Visual Inspection
3952a518-6b38-5987-9d53-9f2618de5399 | note | RECORD: Signed ITP
6a994837-f953-506c-b73a-23444f4627ea | note | IHP
b295128c-a848-5bda-828d-6927061ea0f0 | note | RESPONSIBILITY: SWA Project Manager
247db84d-0562-5b5f-b1c7-aadaf6b5769d | date | Date Completed:
| checkpoint | 2.6 - Bedding
b86142db-7ed2-506c-8022-12f89d4cfec4 | note | FREQUENCY: Each lot as required
19ccc43e-9e69-5614-8486-9250ae584e49 | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
f9b52c92-bf19-5eca-a988-d11736b9bb1c | note | ○ Bedding trimmed, moistened, and compacted as necessary
4150a687-4a52-5cb5-9ddf-29e55bdcd3b6 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
58cfa338-2c0a-5856-9c01-9fa94cae0523 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
8a81b5ba-6e5e-562a-b6e7-285e246fd04d | note | METHOD: Site Inspection/ Document Review
fc1ed9dd-34c1-5b3c-abb1-78b58b4fe61c | note | RECORD: Signed ITP
dbd7fe59-b8af-5708-bbd9-5d0d59c7e813 | note | IHP/AP
9424fe40-9803-541f-a6a3-27aa14256388 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
874afa84-ec5a-54d4-8a36-ee27ac2b52a5 | date | Date Completed:
| checkpoint | 2.7 - Concrete Placement
4f7d565d-7f57-5453-b26a-93912bc3bd78 | note | FREQUENCY: Each lot as required
acc00d4e-8e07-599d-a0fd-1db87aff3296 | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
a663f449-dcd3-5701-bddf-3ba323dabc69 | note | ○ Comply with requirements of AS1379
665753b3-3f85-5bc6-9053-cd7aab90e78f | note | ○ Aggregates to comply with Table 703.051
1d6965d9-4404-563d-822a-7be694dfb7ac | note | ○ Extrusion machines cement content ≥ 320kg/m3
fad3e71a-cc88-5f5f-acc7-f5b89e5181d0 | note | ○ Surface pitting < 5mm diameter
9858029a-694f-585c-9191-dd273623ecd9 | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
2d590dc3-87de-56f6-98c5-7ae19cd651e3 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
f6bee428-7f17-5475-aa09-5cfc7aad58e6 | note | METHOD: Visual Inspection
c09aa0fe-5e05-5d2e-9d3d-d1463ffac490 | note | RECORD: Signed ITP & Test Reports
d6565033-d887-5731-ad83-91bb7cb2a0b9 | note | IHP/AP/TP
cd559b5b-f877-5455-b216-12021ee4b89e | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
de0c3ad5-15ba-5d22-acab-0dc1ea949d0e | date | Date Completed:
| checkpoint | 2.8 - Finish Surfaces
97d1d49e-0650-5d7a-a283-fe6beac811b7 | note | FREQUENCY: Each lot as required
2458e28b-0d1d-55df-bf30-2fd7e5864265 | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
01554e45-55e2-573e-8714-8a9355e842ad | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
e383673f-a8cf-5bbc-8153-de67e5b615ec | note | METHOD: Visual Inspection
a9b975bf-17ce-5878-b1d3-1130035dbc29 | note | RECORD: Signed ITP & Test Reports
d787be7c-1b20-5e06-b37a-a68c9f3e271a | note | IHP/AP
9b3c965a-a117-5631-95d7-940e51cba2e9 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
0d0ba586-677c-5291-8567-6edcec752a21 | date | Date Completed:
| checkpoint | 2.9 - Tolerances
7e1f213e-c927-5e3a-bb54-588ffee96534 | note | FREQUENCY: Each lot as required
0039b4cc-3463-5e3d-9747-203a1732f40b | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
c6d108b4-31ec-58dd-a1c9-0fdaf1cdb20e | note | Section dimensions:
76921a82-71b7-50fa-87ca-eb95f7c7e047 | note | ○ Within 5mm and 15mm for width; and
2f686c82-3021-5e91-86dc-383081391768 | note | ○ Within ±3mm for dimensions less than 25mm.
823267a9-7e77-531f-b955-7c5996bd3df5 | note | Concrete footpath:
423372ed-8a34-59a6-bb01-bacb34bc7c0a | note | ○ 150mm thick
1ac7b9db-405b-5a4b-9c53-d41690d3f1d5 | note | ○ SL72 reinforcement
2a0eae66-1f89-55b8-89cd-aca1468ee7b6 | note | Concrete Surfacing:
bd278de7-ae77-531c-8e6a-f98576d30908 | note | ○ Type 1 100mm
6a9a005c-a671-5582-88bc-e979a7ad5656 | note | ○ Type 2 150mm
59281743-6354-57b8-9065-4eb789c31dd4 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
fce9109c-59a6-57b8-a526-a376140eb285 | note | METHOD: Visual Inspection
cfca9fed-4e1f-5b37-ac15-be65df065258 | note | RECORD: Signed ITP
62a919a0-fbce-5427-bb9b-b5a2305a2328 | note | IHP
4f5590ec-c453-5983-b09d-f0a68b59cc58 | note | RESPONSIBILITY: SWA Project Manager
8b537dfe-da43-5a13-906f-d5e10c4d52d7 | date | Date Completed:
| checkpoint | 2.10 - Joints
c0eda2c0-4fdb-5684-a781-2574ebefbc25 | note | FREQUENCY: Each lot as required
a1d0afd5-e008-5fe7-9428-81a406c1d340 | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
00367f8a-f964-588f-ad0e-9aece009add2 | note | ○ Expansion joints at 12.5m regular intervals
c7bb1a40-deab-58bd-a61d-eaff096da0d4 | note | ○ Control joints at 2.5m regular intervals
3b81d342-8743-502f-8d9b-d1fef036eafe | note | ○ 20mm deep and 5mm wide
6890dbdb-92eb-5c26-9d1f-694580d3c34e | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
28b948a1-deba-5b69-86f0-ce86f3b2389d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
9dc6f66e-636b-5095-8f59-286d7cd20127 | note | METHOD: Visual Inspection
2c38b942-8492-52a6-861e-c17e97ea07ab | note | RECORD: Signed ITP
242f470e-e1d3-5f64-9745-98a9bb169abc | note | IHP
a8a79afc-d754-595c-a364-ffc1cd16cfb3 | note | RESPONSIBILITY: SWA Project Manager
398720d9-0b29-530a-9002-bd63a7e02063 | date | Date Completed:
| checkpoint | 2.11 - Backﬁlling
f2fea800-ab53-551b-8af7-686702f2bbeb | note | FREQUENCY: Each lot as required
a9e9f3e1-8090-57d3-89ab-f537973b7684 | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
7bff6008-e82e-5e36-923d-bb08df9da072 | note | ○ Width ≥ 300mm behind edging to top of edging
00c16956-63fb-5a9f-95b5-38084361c3e7 | note | ○ Topsoil placed after 3 days of concrete placement
c4bb5253-c4e9-57f6-9cb7-12ababf9993d | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
cb708d60-148c-5c77-b55b-8c03917beea2 | note | METHOD: Visual Inspection
a52af329-6691-5041-b433-630a748bddb0 | note | RECORD: Signed ITP
c6d14f8b-b636-5e39-bd6c-45c1d8bcbb50 | note | IHP
eb384a0c-84cf-5b91-acb2-e9ce86be90b0 | note | RESPONSIBILITY: SWA Project Manager
8d7ea636-fc0d-536a-8d62-d1c00989f915 | date | Date Completed:
| checkpoint | Final Inspection
b61cd3df-1245-58d3-98da-582d5d4fb73e | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
ca92968e-fd7d-596f-b881-5c495579f796 | textbox | Print Name:
7536c187-d446-55b3-a24c-2c06c642217f | textbox | Position:
b45b5b7b-c0f3-5fb7-92e9-46c8c6e8a06c | date | Date:
| signoff | Sign ITP
| checklist | SWA-013 - Pre - Construction | itp | SWA-013 - Pre - Construction |  | b8738fa3-7d57-47cf-b2b4-798567fc0026
| section | 1.0 - Pre-Construction Checklist
| checkpoint | 1.1 - Communication (1)
6ac75fb9-74e2-5fb2-85a3-84c4b8008c39 | note | ACTIVITY / DESCRIPTION: Community and emergency services
c678d74b-a672-592b-b979-1c99b7f696d5 | date | Date:
| checkpoint | 1.1 - Communication (2)
e55c5068-9fa4-5a1b-aa0a-6de36cbc5bf4 | note | ACTIVITY / DESCRIPTION: Emergency response plan
bda3f06a-3c3c-5018-af54-e0aff08de424 | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (1)
9628d657-61bb-5a84-9ad5-12752bc1064a | note | ACTIVITY / DESCRIPTION: IFC drawings (PDF, hardcopy)
0d71f2f0-26f9-5995-bc5f-ccfbf607e17b | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (2)
f343ec02-718c-59db-ab3a-25e80837e2df | note | ACTIVITY / DESCRIPTION: Digital (CAD) files (Surveyor)
60cef747-332a-5e37-80d6-c09065e0a958 | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (3)
6486ac0a-36f4-5647-8cc9-8c58b9fc2796 | note | ACTIVITY / DESCRIPTION: Budget / Resource arrangement POs (incl. sub-contract agreements)
0951336e-809c-5108-957b-34c50eb0e7de | date | Date:
| checkpoint | 1.2 - Approved Construction Documentation (4)
a291999a-7702-54be-a784-596df5954215 | note | ACTIVITY / DESCRIPTION: Quantities / Specifications
aee31bd7-4cde-5a8f-a5ba-9514c271b1c7 | date | Date:
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (1)
03636c61-da3d-5862-9ef7-a0e61d9ba316 | note | EXTERNAL REFERENCE: Hold Point (HP)
79639933-4198-5797-be20-6f279137add8 | note | ACTIVITY / DESCRIPTION: Residential (ie: structures, access/gate, letterbox, fence)
76df2442-44de-52f2-a7ee-9e1b2db476fd | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (2)
6e875f2f-1f6d-54b8-ad88-e8bac65328d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ad5b0201-e292-57e1-b0be-3814d7cd5e6f | note | ACTIVITY / DESCRIPTION: Business (ie: structures, access/fence/gate, signs/letterbox)
8118ed5e-26cf-5d2f-a5e1-25503267f92e | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.3 - Dilapidation Report (records and photographs) (3)
1825af1f-9911-5784-b310-f67d99f16c75 | note | EXTERNAL REFERENCE: Hold Point (HP)
34872f6b-7c88-59d7-8915-8ea569094049 | note | ACTIVITY / DESCRIPTION: Agricultural (ie: access, livestock, fence/gate)
b9ca6609-db0a-5eaa-9c75-18e375ab6eb3 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Heritage / Cultural listed areas: (1)
67ed8b4e-48f9-57f8-a600-390c9bdd29c2 | note | EXTERNAL REFERENCE: Hold Point (HP)
fa5dd48c-18b6-528b-a52f-0ec372b0b2c3 | note | ACTIVITY / DESCRIPTION: "No Go Zone"
255ffa41-0fb6-50b0-be8a-005e04fba535 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.4 - Heritage / Cultural listed areas: (2)
aa5e5762-73d7-5990-869a-eae524283d11 | note | EXTERNAL REFERENCE: Hold Point (HP)
c0716d5a-f08e-5685-94f9-d746f9de8103 | note | ACTIVITY / DESCRIPTION: Tourist attraction
fb3f411a-7165-5bd9-81c8-65d0947b8412 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (1)
c3537a7b-f353-5fa5-9655-321eb8f210b2 | note | EXTERNAL REFERENCE: Hold Point (HP)
d36c54d2-7b0e-55a0-96df-a1570770f991 | note | ACTIVITY / DESCRIPTION: Flora
63416b39-c036-5c4f-9cdd-9efbf878ddc8 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (2)
e374ec65-344d-5f55-9163-0363f1fc82c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
6874e82f-7eb2-55a8-a9e5-dca3b0fb7d8d | note | ACTIVITY / DESCRIPTION: Fauna
5628aec3-4ec4-5365-a8b6-d9c417458b93 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.5 - Protected Environment (3)
ab221c3f-e8c1-5fcc-9705-0d3c8e189157 | note | EXTERNAL REFERENCE: Hold Point (HP)
f016b3a2-6fac-5fc4-8857-7be2cfcc15e3 | note | ACTIVITY / DESCRIPTION: Water bodies
07f39192-f364-5554-8b65-d980b885953a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (1)
e0f4292e-52b6-5e42-a758-b0de3e089e54 | note | ACTIVITY / DESCRIPTION: Dial Before You Dig
1e1eb03f-76ab-5ba0-855e-bcb622315ec9 | date | Date:
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (2)
2e00c3ff-cbe8-5c74-af86-841465f410a7 | note | ACTIVITY / DESCRIPTION: Excavation Permit
2aec04a3-0aad-5ac9-b793-83d1ef151c2b | date | Date:
| checkpoint | 1.6 - Site Pre-start checklist, and supporting documents (3)
7533acb9-6cc7-596c-a296-26e31d51c11a | note | ACTIVITY / DESCRIPTION: Assess and arrange for Service location
13f705f3-bf35-53d8-8ca7-e84941343889 | date | Date:
| section | 2.0 - Pre-Commencement Checklist
| checkpoint | 2.1 - Traffic Items (1)
55c62a7f-b4ab-5f3c-8def-280e4c917421 | note | ACTIVITY / DESCRIPTION: VMS boards
6ac3d201-2c28-52a7-a8b2-90c414058ae2 | date | Date:
| checkpoint | 2.1 - Traffic Items (2)
5b9dd624-ae8f-581b-8874-6c737a56c425 | note | ACTIVITY / DESCRIPTION: TGS/TMP, MoA
ec18bf29-de58-576d-aabb-a088bed6a4ad | date | Date:
| checkpoint | 2.2 - Site marks / references (1)
502435bf-bca4-55cb-b6da-3dd2a6dd1dcf | note | ACTIVITY / DESCRIPTION: Limit of Works
1705a55f-e283-55eb-a225-cf0b20ff39c8 | date | Date:
| checkpoint | 2.2 - Site marks / references (2)
ce62becc-d90c-520d-97b2-d9ebc15c1536 | note | ACTIVITY / DESCRIPTION: Survey control point
1477e2f0-75ce-520a-97a9-db697eb6aa70 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (1)
1de60d9c-e7ab-5885-a3f6-0366865fff98 | note | ACTIVITY / DESCRIPTION: Sewer, Water
f335f453-2ac9-58b4-b6b4-18bc46f26df7 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (2)
c6d0efd6-f8c1-556b-9d3d-ae7f2b631821 | note | ACTIVITY / DESCRIPTION: Gas, Electricity
102be5f6-8768-518c-93a3-a2c773473a8f | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (3)
75076475-3b85-5121-ac0c-03db0e1eef54 | note | ACTIVITY / DESCRIPTION: Telecommunication
14f8a3e3-f9ec-5544-b28d-605ec91d8327 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (4)
5f3060bb-3bb1-5591-b921-d4f59a6a92a6 | note | ACTIVITY / DESCRIPTION: Drainage (ie: council/shire, Other state authority)
de24c3b0-6b49-5f90-8428-2c576569d3e0 | date | Date:
| checkpoint | 2.3 - Services, inspect/identify clash points: (5)
5cd070f3-4bc2-5d15-82ac-70e37c344a84 | textbox | ACTIVITY / DESCRIPTION: Other specify:
50d772c2-4165-5d56-8320-9c86a7d20b54 | date | Date:
| checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (1)
74683223-37ac-5f0b-9dc8-c59bbbb49457 | textbox | ACTIVITY / DESCRIPTION: O/H and U/G services flagged "No Go Zone"
082b5cea-cbd9-5d32-b47a-12a91485a800 | date | Date:
| checkpoint | 2.4 - Site-Traffic Risk Assessment, including: (2)
2d9b5ac8-2932-551d-afe9-cce406feb1b8 | textbox | ACTIVITY / DESCRIPTION: Trees(s) marked and approved for trimming or removal
6ddf181a-e8b1-5fc9-ab3d-1f6b4ab98b3e | date | Date:
| checkpoint | 2.5 - SWMSs reviewed: (1)
91edcc50-d584-52ff-9a80-5cf97676facd | textbox | ACTIVITY / DESCRIPTION: Site-specific
f484d58c-c0a0-5b74-9e0c-44d3b5f26fef | date | Date:
| checkpoint | 2.5 - SWMSs reviewed: (2)
b108d9a3-d755-5fe7-a3ce-9b4c144ed150 | textbox | ACTIVITY / DESCRIPTION: Spotter required / arranged
241f3d92-8abd-5760-a197-07485a7903e6 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (1)
000ad7b0-a0b3-5691-adc5-5fdb50559397 | textbox | ACTIVITY / DESCRIPTION: Sight and Clearance Distances:
49c34f83-a82c-5d2d-99ae-76a827d686e7 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (2)
845fa20d-5809-53bd-a769-4e8cf144dca5 | textbox | ACTIVITY / DESCRIPTION: Stop-slow areas, spotter, slips, confined space/work at height
8d29808c-5f6e-5d17-ab5d-12701fcc7f8a | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (3)
da8e0f5e-1206-53be-ae77-1b48e2a2c06f | textbox | ACTIVITY / DESCRIPTION: Vehicle access to properties
42516fb7-f459-51b6-a80b-3d181e45b9cf | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (4)
5e983dd6-62b6-5c14-abdf-4a9d516d310a | textbox | ACTIVITY / DESCRIPTION: Proximity to Services: clearance requirements
78bb6672-239a-5d14-9e90-b6fff32dfc28 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (5)
e5327478-ff3b-525b-9d22-e123465c38a6 | textbox | ACTIVITY / DESCRIPTION: Proximity to Water: supply point, watertable/dam/river/coast/port
73da7c40-9c91-5b8e-8574-8dfb3ce76381 | date | Date:
| checkpoint | 2.6 - Site Access (incl. VicRoads pre-commencement - meeting with superintendent) (6)
9b5ae601-5c84-5742-862a-02d344119001 | textbox | ACTIVITY / DESCRIPTION: Site compound/Plant parking, material stockpile area, "dumpsite"
de3f3c7e-21fa-52b6-8b20-c9dea9d405fa | date | Date:
| section | 3.0 - Construction
| checkpoint | 3.1 - Vegetation Removal (1)
c4f91f9b-460b-5bf7-9724-1d68269b5fd8 | note | EXTERNAL REFERENCE: Hold Point (HP)
9a06f88c-d3ba-509b-94eb-73443c6aa6a3 | note | ACTIVITY / DESCRIPTION: Spotter, Traffic Control
24caba61-85bc-5159-b0ec-72a77a683fad | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Vegetation Removal (2)
2440ce69-0b95-549f-bf60-60b1909778d8 | note | EXTERNAL REFERENCE: Hold Point (HP)
87e8fdf3-58d0-5c59-bdc3-c912e2382397 | note | ACTIVITY / DESCRIPTION: Equipment, Access
9b81ac8f-b070-5323-9dca-acfbdb427325 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.1 - Vegetation Removal (3)
ccf59e41-4ab4-5852-a208-c13193b332ce | note | EXTERNAL REFERENCE: Hold Point (HP)
d042cc4b-aab0-544a-85f7-80f1ce6852a5 | note | ACTIVITY / DESCRIPTION: Soil erosion / water contamination
c63da54d-4452-5d56-aa26-80f408262e25 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Contaminated Materials
f1271195-0f83-5568-b48c-aea50c41dd87 | note | ACTIVITY / DESCRIPTION: Contaminated Materials
ffafd4b5-54da-5bfe-801d-00e309038cf1 | date | Date:
| checkpoint | 3.3 - Traffic Items (1)
d3430d21-a698-50e9-8359-dc7188cd9a6e | note | EXTERNAL REFERENCE: Hold Point (HP)
52a94787-19b2-56c7-bb15-816a2990cbb0 | note | ACTIVITY / DESCRIPTION: External review: Road Safety Audit
70f42a74-ee1e-5d54-b8b0-1cde5b68b86f | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.3 - Traffic Items (2)
ec7ce81c-2ad7-50f3-9cbc-9f01a126af9d | note | EXTERNAL REFERENCE: Hold Point (HP)
580d0e38-7fdd-5696-a5d5-495e0cc60140 | note | ACTIVITY / DESCRIPTION: Internal review: adjust hold-time (traffic lights / traffic controller), flowbias, identify peak-hour period(s) / public transport / rubbish collection
c346f444-f86f-59e7-8e38-9f9909100dbd | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.4 - Trenching works (1)
941db789-7b82-594b-bb6b-fcef0d6edb67 | note | ACTIVITY / DESCRIPTION: Review escape plan (routes)
6d62af35-d0f5-5ef6-b239-b452fd3decb6 | date | Date:
| checkpoint | 3.4 - Trenching works (2)
b4ecbe1d-c4f4-56b2-aeff-6efdc65fdd2b | note | ACTIVITY / DESCRIPTION: Review ground / water conditions
619cc4c2-86a0-5d57-897a-31c5d6c53318 | date | Date:
| checkpoint | 3.4 - Trenching works (3)
540cea3b-7a41-5fa6-9f28-8540567fd217 | note | ACTIVITY / DESCRIPTION: Indentify Shoring / Benching requirements
12f019cc-0473-5500-a16e-4c48b4fd9135 | date | Date:
| checkpoint | 3.5 - Drainage Works (1)
206c1000-b617-500b-9644-e5b5617da94c | note | ACTIVITY / DESCRIPTION: Assess surface-water impact – flow-path / catchment / outlet
70024a33-18da-5be1-9e03-818c3b557391 | date | Date:
| checkpoint | 3.5 - Drainage Works (2)
d8430f2c-7145-59d6-b01b-4d49402c154c | note | ACTIVITY / DESCRIPTION: Surface drainage (swale drain)
1e06ce8b-b227-5e32-b27a-c39c24c7bb90 | date | Date:
| checkpoint | 3.5 - Drainage Works (3)
4cce8002-4d20-5487-8f39-429bf484f752 | note | ACTIVITY / DESCRIPTION: Sub-surface drain pipe and aggregate (agricultural drains / "agi pipe")
33acb2dc-5580-585c-86fc-a0d62281f5ab | date | Date:
| checkpoint | 3.5 - Drainage Works (4)
ea0ce010-f16e-5655-b25a-79d53b30ded2 | note | ACTIVITY / DESCRIPTION: Review confined space entry
f6040a37-cd0a-5d2b-b12f-5777b19c46ac | date | Date:
| checkpoint | 3.5 - Drainage Works (5)
055373e2-fcd2-5867-bae6-c62a3c9a7c4e | note | ACTIVITY / DESCRIPTION: Review lifting methods (load / equipment / plant / crane)
f396fea9-8948-5986-a2e1-3320dc2bbc80 | date | Date:
| checkpoint | 3.5 - Drainage Works (6)
e5e82d46-11a8-5768-bb45-772759095f7e | note | ACTIVITY / DESCRIPTION: Levels
00326889-24e1-507e-9670-084aaf6e1b9c | date | Date:
| checkpoint | 3.5 - Drainage Works (7)
4398c1aa-7394-5b74-b0bf-a13b96671e33 | note | ACTIVITY / DESCRIPTION: Pit covers / Grates
e659082f-e4d6-5e1d-a61b-b6414277833e | date | Date:
| checkpoint | 3.6 - Structural Items (1)
3b525321-4f28-5639-add6-31ec82bc5df6 | note | EXTERNAL REFERENCE: Hold Point (HP)
be017c29-8f47-5668-bdae-a8405425460c | note | ACTIVITY / DESCRIPTION: Crown units / culvert
395b34ca-3ed7-5d85-be46-515ca8a56d07 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Structural Items (2)
caeee054-0a9f-552c-80b4-84f23d4ffd26 | note | EXTERNAL REFERENCE: Hold Point (HP)
43028459-d569-558f-948f-38217645075c | note | ACTIVITY / DESCRIPTION: Retaining structure works
807220dc-dd15-50c5-a8fc-c003c6fae476 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.6 - Structural Items (3)
0df10fa0-c833-55e1-9193-0d7a4569cbd7 | note | EXTERNAL REFERENCE: Hold Point (HP)
303a4d60-fb15-5276-81ad-fab2e818ecb3 | note | ACTIVITY / DESCRIPTION: Bridge works
a8c8c7d3-a0f9-557d-86f0-ec9e894e650e | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.7 - Concrete kerb works: (1)
85ba550e-6b28-5857-bc5e-ccbab8a99472 | note | ACTIVITY / DESCRIPTION: Alignment / level
ad6260d7-5ed9-59c9-acbc-d5ce0a530454 | date | Date:
| checkpoint | 3.7 - Concrete kerb works: (2)
196e60b1-5cf7-5548-a2a2-2f21dce71563 | note | ACTIVITY / DESCRIPTION: profile / finish
81cc87f6-e6c0-5e62-bc6d-46af70cb2f8e | date | Date:
| checkpoint | 3.8 - Concrete Works (1)
401cdf12-25f0-5fd8-9ee9-30975c3b2303 | note | EXTERNAL REFERENCE: Hold Point (HP)
12a4338e-180e-5542-ae61-a968ebe17b5a | note | ACTIVITY / DESCRIPTION:
30e9d4f6-b44a-5cd4-9e38-c9188dca2b01 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (1)
50a1f3c8-852d-5f7d-a90f-bbe760fbedbf | note | EXTERNAL REFERENCE: Hold Point (HP)
b8b5e787-b8a9-522f-bc42-7971fc89dbbd | note | ACTIVITY / DESCRIPTION: (in-situ & pre-cast) - Bedding material / blinding material
c90c15f0-ebc6-556f-a851-79e244f671c9 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (2)
3d269fdf-cde3-5045-b197-b495c7bf1264 | note | EXTERNAL REFERENCE: Hold Point (HP)
1f8d3ea8-ab2f-5a5a-8252-be864ae88514 | note | ACTIVITY / DESCRIPTION: (in-situ) - Formwork, duct-work
8f5b6cbd-ad5a-5282-b1f1-8450ee22c61c | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (3)
f8c6660a-0b26-5d62-98ea-ddc73be56ed4 | note | EXTERNAL REFERENCE: Hold Point (HP)
e1f3c380-ce16-557f-9480-15d08544bce7 | note | ACTIVITY / DESCRIPTION: (pre-cast) Alignment/dimensions
f7e3ff3c-d599-5193-8553-3425282b40b2 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (4)
538b3710-fbf1-576a-9efb-9cda272d4314 | note | EXTERNAL REFERENCE: Hold Point (HP)
14e24089-3285-5a04-be40-c2f11bbf4886 | note | ACTIVITY / DESCRIPTION: (in-situ) - Rebar layout
b1c808e3-525b-5745-880b-ed644c29343e | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (5)
4362a75c-8d17-58f2-a2b9-37e835138dc9 | note | EXTERNAL REFERENCE: Hold Point (HP)
517c09cb-52a7-55c1-af1d-c19b4061c574 | note | ACTIVITY / DESCRIPTION: (in-situ) - Concrete mix / Compaction / Placement method(s)
ba98caf0-cd34-5675-a817-86ab1e308f91 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (6)
bab3caaf-3e29-5150-9f97-102d3d7e3f11 | note | EXTERNAL REFERENCE: Hold Point (HP)
b0f820c0-a955-5788-bfbb-884b9b202c56 | note | ACTIVITY / DESCRIPTION: (pre-cast) - Lift points / placement method
2088c290-f00d-5619-969f-6f3235b7382d | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (7)
dfe49555-ae54-5b30-b62e-f56301f61a2c | note | EXTERNAL REFERENCE: Hold Point (HP)
d03928cd-fe9d-5ac9-b157-dcd34632c6ea | note | ACTIVITY / DESCRIPTION: (in-situ & precast) - Pre-stress works (where applicable)
ed14191b-2a26-5984-b326-bb45015ed9c3 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.8 - Concrete Works (8)
8884b095-83d5-5ce6-8d8d-80eaf4306d63 | note | EXTERNAL REFERENCE: Hold Point (HP)
17cf4daa-0a6f-5fb4-9b7c-5f129acf634d | note | ACTIVITY / DESCRIPTION: (in-situ & precast) Finish
6e271065-4fde-52f2-8ee8-97b76b48f1f6 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (1)
e73589a9-ec36-54cd-9029-5ee29ce1deec | note | EXTERNAL REFERENCE: Hold Point (HP)
1b3a26cc-7010-5158-ab72-bbdbee1bd096 | note | ACTIVITY / DESCRIPTION: Require in-situ testing / laboratory report (where required)
75b4e119-6301-5b94-b8ce-839b4666ce1f | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (2)
8b2306d3-92b6-5476-83a2-281a1b1190f1 | note | EXTERNAL REFERENCE: Hold Point (HP)
e70bb6c6-d7ea-5908-a5dd-e5a62cd09130 | note | ACTIVITY / DESCRIPTION: Material dockets (ie: Lime / Cement)
f937da68-feb6-5804-b46e-17e5c22c049a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (3)
90496a06-77d2-58e8-a89d-fb4b7d1f7ecf | note | EXTERNAL REFERENCE: Hold Point (HP)
6bce577a-706e-5a14-aafe-da3385ac4755 | note | ACTIVITY / DESCRIPTION: Density results
c1445df0-8e52-5f7f-96e1-74811d8d9e30 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.9 - Unsuitable sub-grade / sub-base / Stabilisation treatment (4)
e51627c3-a02b-5a2c-867d-795095cde3c8 | note | EXTERNAL REFERENCE: Hold Point (HP)
fd110d90-715a-5e18-9914-c7a94602cd50 | note | ACTIVITY / DESCRIPTION: Proof-roll
f3628880-a322-519a-a4fb-4d030a922d59 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (1)
b0e21f3b-781c-567f-9184-cedcd7dba172 | note | EXTERNAL REFERENCE: Hold Point (HP)
5b32bd42-1cfa-5ce5-b6d4-e6b7b8432557 | note | ACTIVITY / DESCRIPTION: Density results
981e0eb1-3b86-5839-a78d-f4ca87dddfb8 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (2)
de3488c1-cb69-51df-9b46-9083c7620eb3 | note | EXTERNAL REFERENCE: Hold Point (HP)
4460a507-b9c6-5ecf-94c7-151aeee07db0 | note | ACTIVITY / DESCRIPTION: Proof-roll / Test Rolling
13da7516-ddc1-5ea8-864c-3925ea208098 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (3)
7f373744-f16a-59ab-8365-8d1b2626e0d1 | note | EXTERNAL REFERENCE: Hold Point (HP)
ebf648f9-2a90-524a-9a17-27d3e7fcc4ed | note | ACTIVITY / DESCRIPTION: Dryback results (NB: required prior to sealing works)
447c7ffb-ccd8-547d-8638-4bf69813c694 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.10 - Pavement Works (4)
3fef4dd5-2ef3-59f8-927a-73fce94b43d5 | note | EXTERNAL REFERENCE: Hold Point (HP)
cf83917c-4162-5eb0-8ed4-456ddbf42093 | note | ACTIVITY / DESCRIPTION: Ball Penetration Test
7f10fe4e-729a-547e-a479-92f014ea1436 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (1)
d038a06b-3e2a-5e9c-bf71-de2b832e1b7f | note | ACTIVITY / DESCRIPTION: Level & Location (ie: clearance requirement)
43daad50-b548-5b48-a1ad-7365ecc21eef | date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (2)
575b00ff-78d5-57f8-a161-2d17d6d112c3 | note | ACTIVITY / DESCRIPTION: Approved equipment for installation
765441c7-7694-5c75-a283-4c365041838c | date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (3)
a46320d2-7f1e-5097-a48d-6447073a73da | note | ACTIVITY / DESCRIPTION: Pit and conduit (ie: clearance requirement)
561ad1d9-de3b-57fe-9f7f-e9a880990643 | date | Date:
| checkpoint | 3.11 - Utility Services, Traffic / Public lights (4)
25963336-1eba-572e-b0e9-e5b299512e7c | note | ACTIVITY / DESCRIPTION: Audits by relevant authority / hand-over procedure
3e25cae7-33e3-5629-9827-724e49802f46 | date | Date:
| checkpoint | 3.12 - Pavement Surface Works (1)
b6eaf2b8-9418-57ed-b6c3-2eacb3f58fb4 | note | EXTERNAL REFERENCE: Hold Point (HP)
0ab970b0-5923-5246-afca-a41d27053472 | note | ACTIVITY / DESCRIPTION: Seal (ie: suitable material, spray-sheet details)
b377244e-049f-565e-b5ab-9b6c17b108f6 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.12 - Pavement Surface Works (2)
b846e4a9-d9b0-5d0f-8d23-23db84ef0d0c | note | EXTERNAL REFERENCE: Hold Point (HP)
9bf5d3da-5e55-5f80-8075-102e2cd4bdbd | note | ACTIVITY / DESCRIPTION: Asphalt (ie: material dockets)
96810742-a4c1-5113-a84e-f2d7a6584165 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.13 - Landscape (1)
398e27fa-a911-566f-a856-c1ead55abbe6 | note | ACTIVITY / DESCRIPTION: Seed / Grass
2afa04d7-980a-5c03-b9a5-80f631a38a8f | date | Date:
| checkpoint | 3.13 - Landscape (2)
087d861a-ac33-5a99-9133-2da489077fdb | note | ACTIVITY / DESCRIPTION: Hydro-seed / Hydromulch
ced50251-08f1-5808-a1b4-ff6e82306766 | date | Date:
| checkpoint | 3.13 - Landscape (3)
851c9681-9923-5889-8551-1992519214c2 | note | ACTIVITY / DESCRIPTION: Street furniture
52496859-46bb-5845-886a-71886ad7d6ba | date | Date:
| checkpoint | 3.13 - Landscape (4)
307cf2ee-fa00-58a1-8d27-d9f5b40676fe | note | ACTIVITY / DESCRIPTION: Maintenance arrangement / period: 3 / 6 / 12 / 18 / 24 months
3d76ca1d-49f4-530b-ae11-4b845347c14c | date | Date:
| section | 4.0 - Practical Completion
| checkpoint | 4.1 - Road Fixtures (1)
a78b448f-3d6b-5115-bf91-68755dbd1d50 | note | EXTERNAL REFERENCE: Hold Point (HP)
491ff107-7508-5ded-bcd7-46dc66d1889c | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
c3234fb8-5a01-54b2-8c31-df4d3772bb61 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1 - Road Fixtures (2)
68e0deb5-ff03-5ad4-a55e-aa978e856497 | note | EXTERNAL REFERENCE: Hold Point (HP)
4c2e81e9-4907-5868-b8d1-d123752e8ef6 | note | ACTIVITY / DESCRIPTION: Signs
2b632d02-8e86-56ae-9497-1942b780189c | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.1 - Road Fixtures (3)
8460d55e-5f83-5331-ab37-22230156ea0b | note | EXTERNAL REFERENCE: Hold Point (HP)
88345f33-bc9b-505b-98a5-80a9327974ed | note | ACTIVITY / DESCRIPTION: Guide posts
30bfad2f-388f-5f9b-92ba-6d644b77d9e8 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (1)
45a477e3-6218-5f97-9aec-324bc41f1015 | note | EXTERNAL REFERENCE: Hold Point (HP)
f7ea3589-d893-5f22-8fb1-b84637152666 | note | ACTIVITY / DESCRIPTION: Guardrail
f44c2698-72a0-5bb0-9da0-24d0e9af787d | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (2)
5816b8bc-7785-502f-93d7-b22dd3287534 | note | EXTERNAL REFERENCE: Hold Point (HP)
6d99b1d0-3c0e-52c2-b183-fbdcf96608c4 | note | ACTIVITY / DESCRIPTION: Wire-rope
d834a3c0-472e-5f71-a98c-db0213e7605a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.2 - Safety Barrier Works (3)
95c4c178-aad0-5b49-958e-e6d0d0d481b1 | note | EXTERNAL REFERENCE: Hold Point (HP)
2d487db0-bf78-5a7f-ad16-57cea40f5505 | note | ACTIVITY / DESCRIPTION: Motorcycle-safe fixtures
c650ada4-30b7-578a-b8e5-f31b1ba00970 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Fences and Gates
8912adce-b3ab-5d7e-8c53-a6455556f9c2 | note | ACTIVITY / DESCRIPTION: Fences and Gates
da41faa5-b8d9-57fb-b5a4-91fce97a9ed7 | date | Date:
| checkpoint | 4.4 - Quality Ride Test
6930f8cd-1a69-5aeb-8223-009d731a03c5 | note | EXTERNAL REFERENCE: Hold Point (HP)
b7076034-b179-54d3-a933-b8d5ceb054f0 | note | ACTIVITY / DESCRIPTION: Quality Ride Test
1284124b-0fc7-5008-9461-e2d2bf5cf373 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| section | 5.0
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (1)
dff99e57-221f-5d1e-8fb6-c9aafa0555bf | note | EXTERNAL REFERENCE: Hold Point (HP)
8eedd16b-1f11-57f6-9019-0bdbc003a50b | note | ACTIVITY / DESCRIPTION: Linemarking & RRPMs
09948306-f65b-5d5a-a0b7-328132f80554 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (2)
4bb23012-1b28-5815-847a-52fce7be4eac | note | EXTERNAL REFERENCE: Hold Point (HP)
de297435-d6a4-5eab-9aaa-3271b9fbf73a | note | ACTIVITY / DESCRIPTION: Signs, guide posts
503f7189-fc53-5a4d-86b7-2acb91f9cf01 | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (3)
39ec032c-277e-50b6-b1aa-1447b14abf8f | note | EXTERNAL REFERENCE: Hold Point (HP)
91679e6d-2a25-531d-9495-cb4792238201 | note | ACTIVITY / DESCRIPTION: Seal / Asphalt surface
136e4b81-c14c-55b1-91b7-266d280b636a | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.1 - End-of-Defects liability period (EDLP): 3 / 6 / 12 / 18 / 24 months (4)
fbce7819-e701-5581-a44f-36c502e9a0d9 | note | EXTERNAL REFERENCE: Hold Point (HP)
4d3ba9f5-d460-5173-b974-75d6edf1a06f | note | ACTIVITY / DESCRIPTION: Landscape (where applicable)
e560aa7e-540e-5ad9-9d8b-16f7d9db106c | date | Date:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
30e35763-5253-53b3-a77e-c12431fd0cb6 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
cb9f02e9-9908-55ca-8cd9-4341da118c0d | textbox | Print Name:
d84717bd-2a80-5c3a-b881-8158314def49 | textbox | Position:
0f7b88f2-0a7d-540b-889a-2ecfe760bed4 | date | Date:
| signoff | Sign ITP