## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-033 - Insitu Concrete Pit | itp | ITP-033 - Insitu Concrete Pit |  | f6d42c31-7f1e-4955-a6b8-5b3d217d24c3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
d2fee0e1-0667-5aba-89f5-b5bb7059e6de | note | FREQUENCY: Prior to commencing any activity
a64c400e-e46a-5b24-b109-97b34ad12fad | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the most current and updated set of complete construction drawings
7f505dc8-a8b2-5fd5-9241-266924951d7f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
c6c74848-c69b-592a-8f83-a1c459c22d6d | note | INSPECTION/TEST METHOD: Visual inspection
e82db2aa-1c70-5d14-a3b6-d9e6c058a9ec | note | RECORD OF CONFORMITY: This ITP signed off
164e1381-6df2-5a8f-ba62-694d85764731 | note | HP*
39513db2-915c-5283-95ce-c9fe04352db6 | note | RESPONSIBILITY: Fulton Hogan Engineer
016506ab-0b84-5674-9718-f6eebc0926a5 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
064946f2-4e1d-58d4-a534-db5d51602a3f | note | FREQUENCY: Prior to commencing any activity
3f40ab71-5525-58fd-bbc5-2dc1b1d89cf5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
6f7bd837-d81e-5f8d-a031-954b9f672889 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
7f0149ae-efcd-502c-92b7-1c53e7b2e5d3 | note | INSPECTION/TEST METHOD: Visual Inspection
ab522447-74c3-54ac-9664-e22b6f5feebd | note | RECORD OF CONFORMITY: This ITP signed off
f486f5fb-d69a-5267-8a52-5d684e35e4dc | note | IP
3b1b9766-2d68-5b64-8c84-524936092866 | note | RESPONSIBILITY: Fulton Hogan Engineer
22d469f2-f174-5e34-8eb2-2ce961355fc6 | date | Date Completed:
| checkpoint | 1.3 - Pit material classification
46725239-b535-5ff3-826a-b67452dc2803 | note | FREQUENCY: Each delivery
fc11dd8e-db4a-5ad8-b59c-4c975d3ff6a0 | note | ACCEPTANCE CRITERIA: Concrete used shall have a mininmum strength of 32MPa and be
ce7af96a-fb08-5272-b0f7-5eef2d38da99 | note | ○ Steel fabric shall be F92 reinforcement
bd39df97-3ff4-5f94-a432-04a19538032c | note | REFERENCE DOCUMENTS: SD1131
18f5fe3f-fcd7-56b0-a36e-8b2d0603e8a0 | note | INSPECTION/TEST METHOD: Visual Inspection
90fb1210-ae45-588a-b2a4-b9cbfd516e22 | note | RECORD OF CONFORMITY: This ITP signed off
65963e5c-5aa2-55e8-93e0-d7916a441a53 | note | HP*
f7f88f0d-73b1-566c-8c9a-e29b1bc4e65d | note | RESPONSIBILITY: Fulton Hogan Engineer
c04d68d8-a557-59dc-bd6b-e651b2d9f13e | date | Date Completed:
| checkpoint | 1.4 - Backfill and bedding material classificaiton
136c9d09-c4fb-541f-8dd3-c8f95224a23b | note | FREQUENCY: Prior to start
a8efa5cf-ce5a-5820-82f8-f654dcc6f430 | note | ACCEPTANCE CRITERIA: All crused rock used in the works shall be Class 3, 20mm nominal size.
2b2d3e52-af21-591e-8230-6e9a077c84a7 | note | REFERENCE DOCUMENTS: Cl 18.0
e8bc3937-0293-5a31-bdfb-0fbae98adf7f | note | INSPECTION/TEST METHOD: Verify
992c7840-36a2-5261-a126-e555d1ddbd68 | note | RECORD OF CONFORMITY: Test reports from supplier
26d382bd-e103-515b-8823-b1cd982fec7a | note | HP*
b51ccec8-37c4-5d06-a202-d8bd0c2aa899 | note | RESPONSIBILITY: Fulton Hogan Engineer
ccfc4a0e-9a3d-52fc-bbc1-1c451ee209fe | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Set out pit location
55048f6f-7933-51c9-8f7a-a11dd32e0958 | note | FREQUENCY: Prior to backfilling
654bd121-0cbb-5cbc-9476-679982d18db7 | note | ACCEPTANCE CRITERIA: The line, level and location of all pits & structures must be in accordance with the provided design drawings.
90bb07e6-e9f0-5d73-a406-c9bca3c8a780 | note | ○ The position of all pits are to be confirmed with the superintendent if ambiguity arises from the drawings.
eb8bef06-39f6-53ef-8a1d-92bfd775ab90 | note | REFERENCE DOCUMENTS: Survey file / Drawings
88a643b3-01ab-5ab5-8503-7d6ce4001ddb | note | INSPECTION/TEST METHOD: Survey Conformance Report
79ac9217-fab2-58ec-a3d9-10e2e9940d77 | note | RECORD OF CONFORMITY: Survey Report. This ITP signed off.
7248f055-07f2-5e6b-b839-2c868689f351 | note | WP
ea7f3493-b614-5ddd-ba7c-3a4d1da4a623 | note | RESPONSIBILITY: Fulton Hogan Engineer
b202e58d-d3d1-5199-8996-5ee668a2960d | date | Date Completed:
| checkpoint | 2.2 - Excavation
79a5442a-3201-562f-b6eb-17437fcb9528 | note | FREQUENCY: Each trench
b185968c-2c95-553b-98c6-608200b56216 | note | ACCEPTANCE CRITERIA: Any trench which may have been excavated to a greater depth than necessary shall be filled into the required level with concrete 1:3:6 mix. Any loose material shall be removed.
9c7841e3-f175-5b83-9a88-eebea22aa2a5 | note | ○ Trench shall be battered, benched or shored in line with WorkSafe code of practice when required by assessment under 1.5m in depth and is mandatory over 1.5m.
c383545d-7918-5b68-a10c-c6f6c0cbabdb | note | ○ No stockpiles within 2m of end of the trench to reduce bearing pressure.
1f094809-4c54-55b8-8cba-9aa8707bb64f | note | REFERENCE DOCUMENTS: Section 705
411e0c00-1395-59f6-b021-b6ca5a4bbf6b | note | INSPECTION/TEST METHOD: Visual Inspection
0cb9023a-905a-51f1-8fbe-94235b418d9e | note | RECORD OF CONFORMITY: This ITP signed off
09fdc915-4b02-53d5-b9ee-bfc68c12b843 | note | IP
da13b012-cf48-582c-8595-1aa380b0e9bc | note | RESPONSIBILITY: Fulton Hogan Foreman
174cefd1-5819-5b98-8d6a-d34142c29599 | date | Date Completed:
| checkpoint | 2.3 - Inspection of trench base
eb50bdd6-09f4-5bee-bfc0-9aba0b3fa4d4 | note | FREQUENCY: Each Lot
9b4034c1-39c5-5c6b-a0d9-fbd50517b782 | note | ACCEPTANCE CRITERIA: Base of the trench shall be inspected prior to placement of bedding.
978162dc-17e4-5288-a790-b04af8ebc3d9 | note | REFERENCE DOCUMENTS: Section 701
ddbb48ae-fbd7-58b9-b8db-6fb6fd858ee7 | note | INSPECTION/TEST METHOD: Visual Inspection
6833aa94-5776-5f2b-bd97-51be2f4d19b0 | note | RECORD OF CONFORMITY: This ITP signed off
61782a38-3a2a-57e5-bfb1-f515effe6e7e | note | IP
a677a5c3-d337-54d3-8626-fc102eaa30da | note | RESPONSIBILITY: Fulton Hogan Engineer
ffeccc75-5c3f-522f-869d-398f8c035926 | date | Date Completed:
| checkpoint | 2.4 - Placement of bedding material
a342e09d-ea15-5ad5-b43b-38aec435404e | note | FREQUENCY: Each Lot
01fa77aa-3ea3-511b-beca-7011e057512b | note | ACCEPTANCE CRITERIA: A 100mm minimum layer of compacted class 3 crushed rock shall be used under base of pit
adfe8992-bfd7-5d60-ac04-643135681a5e | note | REFERENCE DOCUMENTS: Section 701
133f2341-0f6b-522e-8773-a5ba92ee9a8e | note | INSPECTION/TEST METHOD: Visual Inspection
03eb5d3f-283f-593a-b386-1f6a7e52e0fe | note | RECORD OF CONFORMITY: This ITP signed off
a8d8401b-d322-52ec-b45d-02bb603cdb09 | note | IP
2cf016c3-0f87-5556-849b-820bef1abe28 | note | RESPONSIBILITY: Fulton Hogan Foreman
ac5f8b37-2697-5173-8c53-6e529ab6d193 | date | Date Completed:
| checkpoint | 2.5 - Concrete pre-pour inspection
61ac588d-ce20-51c4-acc1-631969070418 | note | FREQUENCY: Each Lot
d23a5a8f-904c-579d-bb25-61ae30947f30 | note | ACCEPTANCE CRITERIA: Confirm minimum wall thickness and Mesh Cover as per SD1131. Inspect bedding to confirm is compacted to correct depth and free of as water or debris.
1da0e998-ba11-52d3-bf69-8ff565b45a1f | note | REFERENCE DOCUMENTS: SD1131
27488d6f-8d6c-540d-af27-20253f2f02b6 | note | INSPECTION/TEST METHOD: Visual Inspection
a161e1ad-aba5-5cb7-b205-05df0be2ff2a | note | RECORD OF CONFORMITY: This ITP signed off
9ed64570-479b-5f67-b807-31994b2cca32 | note | WP
a46034cc-3d78-53b2-9c5a-fdd411f3f476 | note | RESPONSIBILITY: Fulton Hogan Engineer / DPT Superintendent
8c7e7de7-e2f1-5673-ba5c-250b73b92309 | date | Date Completed:
| holdpoint | AUTHORITY HOLDPOINT
| checkpoint | 2.6 - Concrete pour and pit construction
0c94e257-8129-5a67-a06e-edd318d8e54c | note | FREQUENCY: Each Lot
2fe9377b-0292-5946-a3fa-0d5d5208ee0d | note | ACCEPTANCE CRITERIA: All pits are to be constructed in accordance with Vicroads Standard Drawing SD1131.
ccaacd9f-c658-5b4e-ba2b-19a37f48332d | note | ○ All pits are to be constructed in accordance with Vicroads standards 701 &705. Pit should also be constructed in accordance with site specific drawings.
3aa9f6ba-f004-51e6-88e2-531369de32db | note | ○ Concrete Vibrator must be used
30963914-a864-5892-ad9b-afddfa38911c | note | REFERENCE DOCUMENTS: SD1131 Section701 Section705
a2bed984-53c9-542e-9a6d-a77eca7d34f7 | note | INSPECTION/TEST METHOD: Visual inspection
c767312f-e491-5394-a589-b59e738f366a | note | RECORD OF CONFORMITY: This ITP signed off
4a75f487-7517-5823-8c5e-5114ad75b5b8 | note | IP
9ffcdf09-68f8-5c68-8e7a-42f15da67396 | note | RESPONSIBILITY: Fulton Hogan Engineer
2825ab80-68e1-57f4-9e14-b55e9ef50528 | date | Date Completed:
| checkpoint | 2.7 - Pit base shaped with concrete to match pipe invert
d9619fa9-b57e-585d-804e-c1809e45c41b | note | FREQUENCY: Each Lot
71af7179-1c00-578a-a81d-80a2f83a6d74 | note | ACCEPTANCE CRITERIA: Construct as shown on Standard Drawing SD1131
a715f32d-4598-5a62-9331-5eb0a4efefc2 | note | REFERENCE DOCUMENTS: SD1131
98de3688-2ee6-5f1b-8fd4-136d90b70f6f | note | INSPECTION/TEST METHOD: Verify
adb51ced-75db-565d-acce-cd5ad4aa25a2 | note | RECORD OF CONFORMITY: This ITP signed off
beb8e344-197c-5abe-b64d-2e31827672bd | note | IP
fde3592c-0fca-5737-91bf-03bfa9abc154 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce307d7d-c75a-5197-b0d5-23c2777e4aa5 | date | Date Completed:
| checkpoint | 2.8 - Placement of pit covers
9d5ae23b-6759-5d46-9f36-533e37b1b8e0 | note | FREQUENCY: Each Lot
bdcbc5ba-3ec6-5fce-8f1d-45dd1509a696 | note | ACCEPTANCE CRITERIA: All pits shall be fitted with standard Vicroads specificed on the drawings of appropriate class.
5b392b55-ee40-54cd-87cd-588e29f65e33 | note | REFERENCE DOCUMENTS: SD1131
7ef934ef-c64a-5f94-842f-ef775064cc6b | note | INSPECTION/TEST METHOD: Verify
f0ff9872-f14c-54a4-be0d-5373c43a1f88 | note | RECORD OF CONFORMITY: This ITP signed off
d2b59316-4ec6-573c-9251-d3c106ab905d | note | IP
36fc8b18-d706-5a2e-8eb6-b93e403d23fb | note | RESPONSIBILITY: Fulton Hogan Engineer
03eafdb7-f816-5aea-905a-ee66944a9eb8 | date | Date Completed:
| checkpoint | Final Inspection
007dd8c3-9290-5348-bd4e-03b8268e9011 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
aaf16f3e-f913-5d27-9239-509113ceaeae | textbox | Print Name:
2f641e6b-c647-5c3b-a01d-36ae1fc246a6 | textbox | Position:
0966e487-29c9-53bb-ae9f-e60c7310789d | date | Date: