## Table 1
INSPECTION AND TEST PLAN
Supplier: Fulton Hogan |  |  | Asphalt Compliance Testing | [11 empty] | Approved By: Joseph Stella (FHIS Technical Manager)
Revision: 0 Date: 15/07/2024 |  |  | Structure/Component: Department of Transport and Planning (DTP) Dense Graded Asphalt (DGA) Section 407 (July 2023) | [11 empty] | Document No.: FH-ZU2-QU-ITP017
Item No. | Inspection/Test | Frequency |  |  | Acceptance Criteria |  |  |  |  | Reference Documents | Method |  |  | Record |  | Responsibility |  | Checked By
[18 empty] | FH | Date
1 | Production of Asphalt
1.1 | Temperature | Every loaded truck or at intervals of 15 minutes if more than one truck is dispatched in 15 minutes. |  |  | ≤175oC |  |  |  |  | Section 407.11(a), 407.15 | Thermometer |  |  | Load inspection sheet / docket |  | Plant Operator / Technician
1.2 | Temperature | DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | ≤175oC |  |  |  |  | Internal | Thermometer |  |  | Load inspection sheet / test report |  | Technician
1.3 | Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating | Every loaded truck |  |  | >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles |  |  |  |  | Section 407.11 (b) | Visual check |  |  | Load inspection sheet |  | Plant Operator
1.4 | Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating | DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles |  |  |  |  | Internal | Visual check |  |  | Load inspection sheet |  | Technician
1.5 | Maximum density | On every production day |  |  | ± 35 kg/m3 of its 6-point rolling average |  |  |  |  | Section 407.11(e), 407.15 | AS2891.7.1 |  |  | NATA- endorsed test report |  | Technician
1.6 | Binder content | DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | ±0.3% of mix design specification |  |  |  |  | Section 407.10, 407.15, 407.11 | AS2891.3.3 or AGPT/T234 |  |  | NATA- endorsed test report |  | Technician
1.7 | Full sieve analysis | DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | See Table 1 of this document |  |  |  |  | Section 407.10, 407.15, 407.11 | AS2891.3.3 or AGPT/T234 |  |  | NATA- endorsed test report |  | Technician
1.8 | Moisture content | DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes |  |  | ≤0.5% moisture |  |  |  |  | Section 407.11 (b) | RC 211.01 |  |  | NATA- endorsed test report |  | Technician
2 | RAP Testing (1) - RAP Level 1 and 2 (as per Table 407.121 Section 407)
2.1 | Moisture content of RAP | One test per 500 tonnes of RAP |  |  | Not exceeding the maximum moisture content acceptable for the asphalt plant nominated in the RAP Management Plan – Fulton Hogan Infrastructure Services. Any materials with moisture content greater than the nominated moisture content should be allowed to drain before being utilised |  |  |  |  | Section 407.13(c) FH RAP Management Plan Section 3.2 | AS2891.10 |  |  | NATA- endorsed test report |  | Technician / RAP Yard Supervisor
2.2 | Binder content of RAP | One test per 500 tonnes of RAP |  |  | ± 0.5 of target binder content 1 out of 10 consecutive results is allowed outside tolerance |  |  |  |  | Section 407.13(c), 407.11 | AS2891.3.3 |  |  | NATA- endorsed test report |  | Technician/ RAP Yard Supervisor
2.3 | Sieve analysis of RAP | One test per 500 tonnes of RAP |  |  | See Table 2 of this document |  |  |  |  | Section 407.13(c) | AS2891.3.3 |  |  | NATA- endorsed test report |  | Technician/ RAP Yard Supervisor
3 | RAP Testing (1) - RAP Level 2 (as per Table 407.121 Section 407)
3.1 | Binder viscosity | One test per 1000 tonnes lot of RAP used for Level 2 mixes as per Table 407.121 |  |  | Viscosity of the blend of virgin and RAP binder shall fall within the range in table |  |  |  |  | Section 407.13(e) | AGPT/T192 or AS 2341.2, AGPT/T193 |  |  | NATA- endorsed test report |  | RAP Yard Supervisor / Laboratory supervisor
[6 empty] | Specified Binder Class | Binder Blend Viscosity Range (Pa.s @ 60°C)
[6 empty] | C170 | 170 – 240
[6 empty] | C320 | 320 – 500
[6 empty] | C600 | 600 – 880
1: An approved RAP management plan addressing RAP stockpile management, RAP sampling and testing, RAP process control, RAP traceability, RAP binder blend viscosity (RAP Level 2) and asphalt plant capability shall be submitted to DoT at least 14 days prior to the asphalt works. No asphalt containing RAP shall be supplied until DoT approves the management plant. Rc = Characteristic value of the density ratio Rm = Mean density ratio
Note: Samples shall be retained for the period of time it takes to complete the testing and review the result. After this time the samples can be discarded.
INSPECTION AND TEST PLAN
Supplier: Fulton Hogan |  |  | Asphalt Compliance Testing | [11 empty] | Approved By: Joseph Stella (FHIS Technical Manager)
Revision: 0 Date: 15/07/2024 |  |  | Structure/Component: Department of Transport and Planning (DTP) Dense Graded Asphalt (DGA) Section 407 (July 2023) | [11 empty] | Document No.: FH-ZU2-QU-ITP017
Table 1: Production tolerances for mix grading (Table 407.101 in DTP Section 407)
Sieve size AS (mm) |  |  |  | Tolerance on percentage passing (by mass)
|  |  |  | Size 7 |  |  |  |  | Size 10 |  |  |  | Size 14 |  |  |  | Size 20
37.5 |  |  |  | Nil |  |  |  |  | Nil |  |  |  | Nil |  |  |  | Nil
26.5 |  |  |  | Nil |  |  |  |  | Nil |  |  |  | Nil |  |  |  | Nil
19 |  |  |  | Nil |  |  |  |  | Nil |  |  |  | Nil |  |  |  | ± 6
13.2 |  |  |  | Nil |  |  |  |  | Nil |  |  |  | ± 6 |  |  |  | ± 6
9.5 |  |  |  | Nil |  |  |  |  | ± 6 |  |  |  | ± 6 |  |  |  | ± 6
6.70 - 4.75 |  |  |  | ± 6 |  |  |  |  | ± 6 |  |  |  | ± 6 |  |  |  | ± 6
2.36 – 0.600 |  |  |  | ± 5 |  |  |  |  | ± 5 |  |  |  | ± 5 |  |  |  | ± 5
0.300 – 0.150 |  |  |  | ± 3 |  |  |  |  | ± 3 |  |  |  | ± 3 |  |  |  | ± 3
0.075 |  |  |  | ± 1.0 |  |  |  |  | ± 1.0 |  |  |  | ± 1.0 |  |  |  | ± 1.0
1. If post compaction grading is checked by binder extraction and sieve analysis after placement, the positive tolerances shall be increased by one percentage point. Table 2: RAP grading tolerances (Table 407.131 in DTP Section 407)
Description | [7 empty] | Tolerance (from target grading) |  |  |  | Allowable number of results outside of tolerance
Passing 26.5 mm sieve and larger | [7 empty] | ± 10 |  |  |  | 1 out of 5 consecutive results
Passing 4.75 mm to 19.0 mm sieve | [7 empty] | ± 8 |  |  |  | 1 out of 5 consecutive results
Passing 1.18 mm and 2.36 mm | [7 empty] | ± 6 |  |  |  | 1 out of 5 consecutive results
Passing 0.300 mm and 0.600 mm | [7 empty] | ± 5 |  |  |  | 1 out of 5 consecutive results
Passing 0.150 mm | [7 empty] | ± 3 |  |  |  | 1 out of 5 consecutive results
Passing 0.075 mm | [7 empty] | ± 2 |  |  |  | 1 out of 10 consecutive results