## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP017 - Asphalt Production - 14H Mix | itp |  |  |  |  | FH-ZU2-QU-ITP017 - Asphalt Production - 14H Mix - Rev 0
section | 1.0 - Production of Asphalt
checkpoint | 1.1 - Temperature
label | Frequency - Every loaded truck or at intervals of 15 minutes if more than one truck is dispatched in 15 minutes.
label | Acceptance Criteria - ≤175°C
label | Reference Documents - Section 407.11(a), 407.15
label | Method - Thermometer
label | Record - Load inspection sheet / docket
label | Responsibility - Plant Operator / Technician
date | Date Completed:
checkpoint | 1.2 - Temperature
label | Frequency - DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - ≤175°C
label | Reference Documents - Internal
label | Method - Thermometer
label | Record - Load inspection sheet / test report
label | Responsibility - Technician
date | Date Completed:
checkpoint | 1.3 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating
label | Frequency - Every loaded truck
label | Acceptance Criteria - >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles
label | Reference Documents - Section 407.11 (b)
label | Method - Visual check
label | Record - Load inspection sheet
label | Responsibility - Plant Operator
date | Date Completed:
checkpoint | 1.4 - Visual inspection for segregation, uncoated particles, separated binder, excess binder or overheating
label | Frequency - DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - >95% coarse aggregate coated with binder, no obvious separated binder or uncoated particles
label | Reference Documents - Internal
label | Method - Visual check
label | Record - Load inspection sheet
label | Responsibility - Technician
date | Date Completed:
checkpoint | 1.5 - Maximum density
label | Frequency - On every production day
label | Acceptance Criteria - ± 35 kg/m3 of its 6-point rolling average
label | Reference Documents - Section 407.11(e), 407.15
label | Method - AS2891.7.1
label | Record - NATA-endorsed test report
label | Responsibility - Technician
date | Date Completed:
checkpoint | 1.6 - Binder content
label | Frequency - DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - ±0.3% of mix design specification
label | Reference Documents - Section 407.10, 407.15, 407.11
label | Method - AS2891.3.3 or AGPT/T234
label | Record - NATA-endorsed test report
label | Responsibility - Technician
date | Date Completed:
checkpoint | 1.7 - Full sieve analysis
label | Frequency - DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - See Table 1 of this document
label | – – – – – – – – –
label | Table 1: Production tolerances for mix grading (Table 407.101 in DTP Section 407)
label | Sieve size AS (mm) ¦¦ Size 7 ¦¦ Size 10 ¦¦ Size 14 ¦¦ Size 20
label | – – – – – – – – –
label | 37.5 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ Nil
label | 26.5 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ Nil
label | 19 ¦¦ Nil ¦¦ Nil ¦¦ Nil ¦¦ ± 6
label | 13.2 ¦¦ Nil ¦¦ Nil ¦¦ ± 6 ¦¦ ± 6
label | 9.5 ¦¦ Nil ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6
label | 6.70 - 4.75 ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6 ¦¦ ± 6
label | 2.36 – 0.600 ¦¦ ± 5 ¦¦ ± 5 ¦¦ ± 5 ¦¦ ± 5
label | 0.300 – 0.150 ¦¦ ± 3 ¦¦ ± 3 ¦¦ ± 3 ¦¦ ± 3
label | 0.075 ¦¦ ± 1.0 ¦¦ ± 1.0 ¦¦ ± 1.0 ¦¦ ± 1.0
label | – – – – – – – – –
label | Reference Documents - Section 407.10, 407.15, 407.11
label | Method - AS2891.3.3 or AGPT/T234
label | Record - NATA-endorsed test report
label | Responsibility - Technician
date | Date Completed:
checkpoint | 1.8 - Moisture content
label | Frequency - DGA - One test per 250 tonnes (or part thereof) if lot is >40 tonnes
label | Acceptance Criteria - ≤0.5% moisture
label | Reference Documents - Section 407.11 (b)
label | Method - RC 211.01
label | Record - NATA-endorsed test report
label | Responsibility - Technician
date | Date Completed:
section | 2.0 - RAP Testing - RAP Level 1 and 2 (as per Table 407.121 Section 407)
checkpoint | 2.1 - Moisture content of RAP
label | Frequency - One test per 500 tonnes of RAP
label | Acceptance Criteria - Not exceeding the maximum moisture content acceptable for the asphalt plant nominated in the RAP Management Plan – Fulton Hogan Infrastructure Services. Any materials with moisture content greater than the nominated moisture content should be allowed to drain before being utilised
label | Reference Documents - Section 407.13(c), FH RAP, Management Plan Section 3.2
label | Method - AS2891.10
label | Record - NATA-endorsed test report
label | Responsibility - Technician / RAP Yard Supervisor
date | Date Completed:
checkpoint | 2.2 - Binder content of RAP
label | Frequency - One test per 500 tonnes of RAP
label | Acceptance Criteria - ± 0.5 of target binder content
label | ○ 1 out of 10 consecutive results is allowed outside tolerance
label | Reference Documents - Section 407.13(c), 407.11
label | Method - AS2891.3.3
label | Record - NATA-endorsed test report
label | Responsibility - Technician/ RAP Yard Supervisor
date | Date Completed:
checkpoint | 2.3 - Sieve analysis of RAP
label | Frequency - One test per 500 tonnes of RAP
label | Acceptance Criteria - See Table 2 of this document
label | – – – – – – – – –
label | Table 2: RAP grading tolerances (Table 407.131 in DTP Section 407)
label | Description ¦¦ Tolerance (from target grading) ¦¦ Allowable number of results outside of tolerance
label | – – – – – – – – –
label | Passing 26.5 mm sieve and larger ¦¦ ± 10 ¦¦ 1 out of 5 consecutive results
label | Passing 4.75 mm to 19.0 mm sieve ¦¦ ± 8 ¦¦ 1 out of 5 consecutive results
label | Passing 1.18 mm and 2.36 mm ¦¦ ± 6 ¦¦ 1 out of 5 consecutive results
label | Passing 0.300 mm and 0.600 mm ¦¦ ± 5 ¦¦ 1 out of 5 consecutive results
label | Passing 0.150 mm ¦¦ ± 3 ¦¦ 1 out of 5 consecutive results
label | Passing 0.075 mm ¦¦ ± 2 ¦¦ 1 out of 10 consecutive results
label | – – – – – – – – –
label | Reference Documents - Section 407.13(c)
label | Method - AS2891.3.3
label | Record - NATA-endorsed test report
label | Responsibility - Technician/ RAP Yard Supervisor
date | Date Completed:
section | 3.0 - RAP Testing - RAP Level 2 (as per Table 407.121 Section 407)
checkpoint | 3.1 - Binder viscosity
label | Frequency - One test per 1000 tonnes lot of RAP used for Level 2 mixes as per Table 407.121
label | Acceptance Criteria - Viscosity of the blend of virgin and RAP binder shall fall within the range in table
label | – – – – – – – – –
label | Specified Binder Class ¦¦ Binder Blend Viscosity Range (Pa.s @ 60°C)
label | – – – – – – – – –
label | C170 ¦¦ 170 – 240
label | C320 ¦¦ 320 – 500
label | C600 ¦¦ 600 – 880
label | – – – – – – – – –
label | Reference Documents - Section 407.13(e)
label | Method - AGPT/T192 or AS 2341.2, AGPT/T193
label | Record - NATA-endorsed test report
label | Responsibility - RAP Yard Supervisor / Laboratory supervisor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date:
checklist | ITP018 - Asphalt Placement | itp |  |  |  |  | FH-ZU2-QU-ITP018 - Asphalt Placement - Rev 0
section | 1.0 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Current revision of drawings, technical specifications and any other construction documentation is being utilised by Fulton Hogan and subcontractors.
label | ○ Current revisions of these documents to be obtained via Aconex or ACC.
label | Reference Documents - Current Revisions in Aconex or ACC
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing works
label | Acceptance Criteria - All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WMS
label | Reference Documents - PSP, EMP, TMP, SWMS, WMS
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 1.3 - Plant & Equipment Check
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Asphalt plant & equipment meeting the requirements of Project Specification.
label | ○ Pre-Start checks completed by operators of plant and equipment. All plant and equipment are acceptable for use. Any faults are reported. Standby equipment in place where required.
label | Reference Documents - AfPA Sec 7.1 Cl 91-100
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 1.4 - Tack Coat Material Submission
label | Frequency - Prior to commencing works
label | Acceptance Criteria - Details of the proposed tack coat and test certificates shall be submitted to the Contract administrator for review.
label | Reference Documents - Beca Spec 002, 9.4.1, 9.9.1
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Correspond ence
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 2.0 - Tack Coat
checkpoint | 2.1 - Surface Preparation
label | Frequency - Prior to applying tack coat
label | Acceptance Criteria - Immediately before applying the tack coat, all loose and foreign materials shall be removed from the surfaces to approximately 150mm beyond the edge of the area to be coated.
label | ○ Tack coat must not be applied on a wet surface, or when the surface temperature is below 5 degrees Celsius.
label | Reference Documents - Beca Spec 002, 9.5
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Weather Limitations
label | Frequency - Prior to works
label | Acceptance Criteria - Tack coat shall not be applied on a wet surface, or when the surface temperature is below 5°C, or when the weather conditions would prevent the proper application or adhesion of the tack coat.
label | Reference Documents - Beca Spec 002, 9.7
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 2.3 - Application of Tack Coat
label | Frequency - During Works
label | Acceptance Criteria - Tack coat must be applied to the prepared surface at a rate of 0.2-0.3 L/m2 of residual bituminous material, calculated at 25°C.
label | ○ Vertical faces of milled and excavated existing pavement must be thoroughly tack coated by hand lance or other method.
label | ○ Tack coated surfaces must be protected from construction equipment trafficking to the extent reasonably achievable.
label | ○ Asphalt paving must not commence until emulsified tack coat is substantially broken over more than 80% of the surface of the paving run.
label | Reference Documents - Beca Spec 002, 9.9.3, 9.6, AfPA Sec 10.3 Cl153-156
label | Inspection/Test Method - Verify
label | Record of conformity - Spray Rate Record Sheet, This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 2.4 - Test Certificates
label | Frequency - During works
label | Acceptance Criteria - If during the progress of the work the Contractor desires to use other materials or materials from other sources or materials produced from the same source using method of production different from those originally agreed, new samples shall be taken and tested and the results shall be submitted to the Contract Administrator.
label | Reference Documents - Beca Spec 002, 9.9.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Test Reports
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3.0 - Hot Mix Asphalt Placement
checkpoint | 3.1 - Construction Trial
label | Frequency - Prior to commencing works
label | Acceptance Criteria - A construction trial must be completed as per the requirements in the specification.
label | Reference Documents - AfPA Sec, 8.3 & 8.4
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex Reference
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Ambient Conditions for Placing
label | Frequency - Prior to placement
label | Acceptance Criteria - Asphalt must not be produced and constructed during weather, or expected weather, that may be detrimental to the quality of the finished asphalt surface layer(s).
label | ○ If required, where the existing surface temperature is below 15°C, the Contractor must develop and submit cold weather construction procedures for the Contract Administrator approval.
label | Reference Documents - AfPA Sec 10.1 Cl 145-146
label | Inspection/Test Method - Infrared Thermometer
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Surface Preparation
label | Frequency - Prior to placement
label | Acceptance Criteria - The surface on which the asphalt is to be placed has been jointly inspected by the Contract Administrator and the Contractor, and it is agreed to be suitable.
label | Reference Documents - AfPA Sec 10.2 Cl 147
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Asphalt Placement
label | Frequency - During Paving
label | Acceptance Criteria - The following processes to be monitored with the Contract Administrator to confirm consistency with Construction Trial:
label | – Roller patterns
label | – Surface texture within paving lanes
label | – Surface texture at the joints
label | Reference Documents - AfPA Sec 11.4.1
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | WP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 3.5 - Longitudinal Joints
label | Frequency - During Paving
label | Acceptance Criteria - All longitudinal joints shall be constructed as hot joints (exceeding 125°C upon placement of the adjacent paving run) unless restricted by staging constraints or in constrained working areas.
label | ○ Gas fuelled infrared joint heaters may be used to reheat the joint and create a hot joint where the measured temperature has not fallen below 90°C.
label | Reference Documents - Beca Spec 002 10.5, AfPA Sec 10.4.4
label | Inspection/Test Method - Verify, Infrared Thermometer
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer, Site Supervisor
date | Date Completed:
checkpoint | 3.6 - Surface Finish of Wearing Course
label | Frequency - During paving and after final roll
label | Acceptance Criteria - The finished surface of the asphalt must be a tightly bonded, closed textured, surface of uniform appearance, free of dragged areas, cracks, segregation and open textured patches. Joints must be tightly closed. Surface finish must be consistent with the asphalt construction trial.
label | Reference Documents - AfPA Sec 12.4.1 Cl 288-291
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
section | 4.0 - Compaction Testing
checkpoint | 4.1 - Compaction Testing (AfPA Mix)
label | Frequency - See Note 1.
label | Acceptance Criteria - The in-situ air voids content to be determined using calibration between the nuclear density gauge (NDG) and the asphalt cores developed during the Construction Trial.
label | For test locations away from joints:
label | ○ Individual Air Voids: Minimum 2% and Maximum 8%
label | ○ Average Air Voids: Minimum 3% and Maximum 6.5%
label | For test locations on longitudinal joints:
label | ○ Individual Air Voids: Minimum 2% and Maximum 9%
label | ○ Average Air Voids: Minimum 3% and Maximum 7.5%
label | Reference Documents - AfPA Sec 12.4.2 Table 22
label | Inspection/Test Method - Verify
label | Record of conformity - NATA accredited test certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
checkpoint | 4.2 - Compaction Testing (Type H Shoulder Mix)
label | Frequency - See Note 2.
label | Acceptance Criteria - The in-situ air voids content to be determined using calibration between the nuclear density gauge (NDG) and the asphalt cores developed during the Construction Trial.
label | For test locations away from joints:
label | ○ Individual Air Voids: Minimum 2% and Maximum 8%
label | ○ Average Air Voids: Minimum 3% and Maximum 8%
label | For test locations on longitudinal joints:
label | ○ Individual Air Voids: Minimum 2% and Maximum 9%
label | ○ Average Air Voids: Minimum 3% and Maximum 9%
label | Reference Documents - AfPA Sec 12.4.2 Table 22
label | Inspection/Test Method - Verify
label | Record of conformity - NATA accredited test certificate
label | TP
label | Responsibility - Project / Site Engineer, Laboratory Technician
date | Date Completed:
section | 5.0 - Completion
checkpoint | 5.1 - Surface Smoothness Testing
label | Frequency - After completion of pneumatic tyred rolling
label | Acceptance Criteria - The finished surface of the surface layer must not deviate from a 3.5 m straight edge by:
label | – Full Strength Pavement (AfPa Mix)
label | o Longitudinally: Max 4mm
label | o Transversely: Max 6mm
label | – Shoulder Pavement (14H Mix)
label | o Longitudinally: Max 6mm
label | o Transversely: Max 7mm
label | Reference Documents - AfPA Sec 12.4.3 Cl 293.
label | Inspection/Test Method - Visual Inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project / Site Engineer
date | Date Completed:
checkpoint | 5.2 - Finished Surface Levels
label | Frequency - Per Lot & Per Asphalt Layer
label | Acceptance Criteria - Surface level must be as per following:
label | – Full Strength Pavement (AfPa Mix)
label | o ≥95% of the deviations between design surface level and finished surface level must be maximum 7mm.
label | o ≥95% of the finished surface deviations between design surface cross fall and finished surface cross fall must be maximum 0.3%.
label | – Shoulder Pavement (14H Mix) (14H Mix)
label | o ≥90% of the deviations between design surface level and finished surface level must be maximum 7mm.
label | o ≥95% of the finished surface deviations between design surface cross fall and finished surface cross fall must be maximum 0.3%.
label | Reference Documents - AfPA Sec 11.5.1, Sec 12.4.5 Cl 298-299
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Survey Reports
label | SCP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | 5.3 - Surveyed Average Layer Thicknesses
label | Frequency - Per Lot & Per Asphalt Layer
label | Acceptance Criteria - Average layer thickness must not vary by ± 4mm from nominal thickness.
label | Reference Documents - AfPA Sec 11.4.5 Cl 247-248, Sec 12.4.4 Cl 294-295
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed, Survey Reports
label | SCP
label | Responsibility - Project / Site Engineer, Principal’s Representative
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality\System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: