## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-182-STR-SSB-Concrete Coating-Protective and Decorative | itp |  |  |  |  | ITP-182-STR-SSB-Concrete Coating-Protective and Decorative Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-182-STR-SSB-Concrete Coatings (Protective &/or Decorative)
label | ITP Description: SSB-Concrete Coatings (Protective &/or Decorative)
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 182-STR
label | Revision Number: 0
label | Revision Date: 14/04/2021
label | ITP created by: Mike Freeman
label | ITP approved for use by: Mike Freeman
label | 1.1 Non Dependent
label | Reference: VicRoads Section 685 November 2018
label | 1.2 Non Dependent
label | Reference: VicRoads Section 686 November 2018
section | Preliminaries
checkpoint | 2.1 Anti-graffiti System Selection
label | REFERENCE: IFC Drawings
label | ○ Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 685.04
label | ○ 685.06 (a) & (b)
label | ○ 686.04
label | ○ 686.05 (a) & (e)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | i. be either a film-forming or a penetrant system
label | ii. be non-sacrificial, clear OR coloured (as noted on the IFC drawings or specification)
label | iii. be an acrylic copolymer, acrylic epoxy, polyurethane or polyurea type with all coats be of the same brand and compatible
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | vi. application thicknesses (film-forming):
label | – WFT total = 175µm min. OR
label | – WTF per coat = 88µm min.
label | – DFT total = 100µm min.
label | vii. adhesion to substrate (film-forming):
label | – 0.75MPa min.
label | viii. application rate (penetrants)
label | – as per the minimum thickness on the manufacturer's TDS
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each coating system, 14 days prior to application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Decorative & Anti-carbonation System Selection
label | REFERENCE: IFC Drawings
label | ○ Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 686.04
label | ○ 686.05 (a) & (b)
label | ○ Table 686.051
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to last for 10 years of outdoor exposure
label | vi. application thicknesses:
label | – WFT per coat = enough to achieve the total DFT
label | – DFT total = 150µm min.
label | vii. adhesion to substrate:
label | – 0.75MPa min.
label | viii. able to bridge cracks up to 0.3mm wide
label | ix. able to be re-coated within 24 hours
label | x. have a minimum pot life of 1 hour
label | xi. compatibility to an alkaline surface
label | xii. equivalent air thickness >150m
label | xiii. equivalent concrete thickness >450mm
label | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | xv. Water vapour equivalent air layer <4m
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each coating system, 21 days prior to application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Decorative, Anti-carbonation & Anti-graffiti System Selection
label | REFERENCE: IFC Drawings
label | ○ Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 685.04
label | ○ 685.06 (a) & (b)
label | ○ 686.04
label | ○ 686.05 (a) & (b)
label | ○ Table 686.051
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | i. be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification) OR a combination of these to achieve the system
label | ii. be water or acrylic based, solvent-free with all coats compatible with each other
label | iii. have a minimum of 2 coats for the decorative/anti-carbonation component of the system
label | iv. be non-yellowing, colour-fast and not subject to fading
label | v. be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | vi. application thicknesses:
label | – WFT per coat = enough to achieve the total DFT
label | – DFT total = 150µm min.
label | vii. adhesion to substrate:
label | – 0.75MPa min.
label | viii. able to bridge cracks up to 0.3mm wide
label | ix. able to be re-coated within 24 hours
label | x. have a minimum pot life of 1 hour
label | xi. compatibility to an alkaline surface
label | xii. equivalent air thickness >150m
label | xiii. equivalent concrete thickness >450mm
label | xiv. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | xv. Water vapour equivalent air layer <4m
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each coating system, 21 days prior to application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 Atmospheric & Splash Zone (Dual Protective) System Selection
label | REFERENCE: IFC Drawings
label | ○ Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 685.04
label | ○ 685.06 (a) & (b)
label | ○ 686.04
label | ○ 686.05 (a) & (b)
label | ○ Table 686.051
label | ○ 686.05 (c) (i) & (iii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The system shall be selected based on the following criteria:
label | i. be a dual protective coating system, consisting of a pore-lining penetrant and at least 2 coats for the decorative/anti-carbonation film-forming top coat
label | ii. all coats to be compatible with each other
label | Penetrants:
label | iii. active ingredients:
label | – Silane = at least 95%
label | – Solid silane & silane cream = at least 80%
label | – Silane-siloxane & siloxane = not specified
label | iv. application rates:
label | – Silane = 2 applications of 0.3L/m² min.
label | – Solid silane & silane cream = 1 application of 0.4L/m² min.
label | – Silane-siloxane & siloxane = as per the rates on the manufacturer's TDS
label | Film-forming coat:
label | v. to be non-sacrificial, clear or coloured (as noted on the IFC drawings or specification)
label | vi. to be water or acrylic based, solvent-free
label | vii. to be non-yellowing, colour-fast and not subject to fading
label | viii. to be guaranteed to have at least 8 cycles of graffiti defacement and removal from the date of application and last for 10 years of outdoor exposure
label | ix. application thicknesses:
label | – WFT per coat = enough to achieve the total DFT
label | – DFT total = 200µm min.
label | x. adhesion to substrate:
label | – 0.75MPa min.
label | xi. able to bridge cracks up to 0.3mm wide
label | xii. able to be re-coated within 24 hours
label | xiii. have a minimum pot life of 1 hour
label | xiv. compatibility to an alkaline surface
label | xv. equivalent air thickness >150m
label | xvi. equivalent concrete thickness >450mm
label | xvii. CO2 diffusion coefficient <2 x 10-7 cm2/s
label | xviii. Water vapour equivalent air layer <4m
label | xix. Chloride diffusion coefficient <5 x 10-9 cm²/sec
label | xx.Water absorption value >0.01ml m-2 sec-1 at 10 minutes
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each coating system, 21 days prior to application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Work Procedures
label | REFERENCE: 685.05, 686.04
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The quality documentation shall demonstrate compliance with the specifications and is to be submitted for review to the Nominated Authority.
textbox | Enter: Teambinder Hold Point number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each coating system, 21 days prior to application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 Coating Personnel & Equipment
label | REFERENCE: Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 685.16
label | ○ 686.18
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The coatings supervisor and surface preparation personnel shall have a minimum of 5 years experience and demonstrated competency for the preparation and application techniques.
label | ○ Application personnel require 2 years minimum experience.
label | ○ The supervisor shall remain present at all times.
label | ○ Where spaying is the intended application method, the spray equipment shall be fit for purpose, have an airline filter and the nozzle size should match the requirements of the Product's TDS.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to application.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.7 Protection of Adjacent Works & Property
label | REFERENCE: 685.17, 686.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Protection shall be implemented for existing coated surfaces, services, bearings, joints, signs and nameplates during the surface preparation, abrasive blasting and coating application processes.
label | ○ No spraying shall be performed within 10m of buildings, footpaths, roadways, pedestrians or vehicles without protective measures in place.
label | ○ Where these instances are expected, the protective methods shall be submitted for review to the Nominated Authority.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, 2 days prior to application.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.8 Minimum Concrete Curing Period
label | REFERENCE: 685.08, 686.16
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete shall not be coated until the minimum concrete curing times have elapsed:
label | ○ Standard cured concrete = 14 days & moisture content less than 10%, or 28 days
label | ○ Accelerated cured concrete = 14 days
label | ○ Repaired concrete = 14 days (if repaired with a patching product) or 28 days (if repaired with concrete)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to application.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.9 Trial Application (or Past Performance) Inspection
label | REFERENCE: 685.11, 686.13
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: A full coating system, inclusive of any primers, under-coats and sealers, shall be conducted on either a 10m² area of the element to be coated or on a test panel made from the same substrate.
label | ○ Alternatively, close-up photographs or inspection of previous projects, applied by the same coating contractor, using the same system onto the same substrate should suffice this requirement.
label | Attach: Inspection Photographs OR
textbox | Enter: Teambinder Hold Point number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each coating system, 7 days prior to full coating application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-application Activities
checkpoint | 3.1 Material Records
label | REFERENCE: Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 685.10
label | ○ 685.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Materials shall be brought to site in unopened, sealed containers, clearly marked with:
label | ○ the manufacturer's name & address
label | ○ product reference
label | ○ batch number
label | ○ quantity manufactured in the batch
label | ○ date of manufacture
label | ○ Product beyond the manufacturer's shelf life shall not be used.
label | ○ Each product shall be traced to final location.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to application
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.2 Weather Conditions
label | REFERENCE: Coating System TDS
label | ○ Surface Cleaner TDS
label | ○ 685.09
label | ○ 685.12 (a)
label | ○ 686.11
label | ○ 686.14 (a) (iii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Coating systems shall not be applied under any of the following conditions:
label | i. windy conditions where spray/splatter may be generated
label | ii. when wind-borne debris is likely to contaminate the uncured surface
label | iii. when the ambient temperature exceeds 35°C or is below 10°C unless the Coating System TDS states otherwise
label | iv. when the surface temperature of the substrate is less than 3°C above the dew point or exceeding 40°C
label | v. when the relative humidity exceeds 85% or is expected to exceed 85% within 12 hours of coating
label | vi. when rain splatter, water run-off or water deposits onto the surface and affects adhesion to the substrate
label | vii. when the substrate surface is wet or damp (unless it is required for the coating system)
label | ○ Weather conditions are to be recorded.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to application and every 4 hours per shift
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.3 Surface Preparation
label | REFERENCE: Surface Cleaner TDS
label | ○ Coating System TDS
label | ○ 685.05
label | ○ 686.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The surface shall be prepared in accordance with the Coating System TDS, but as a minimum, all dust, dirt and other surface contaminants such as release agents and curing compounds shall be removed by appropriate means.
label | ○ The surface shall then be flushed with water.
label | ○ Any concrete defects exposed during the surface preparation shall be repaired accordingly.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to application.
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.4 Surface Moisture Testing
label | REFERENCE: 685.12 (a), 686.14 (a) (iii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The substrate is free from back water pressure and the surface moisture conditions shall satisfy the Coating System TDS.
label | ○ Surface moisture conditions are to be recorded.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Immediately prior to application, 1 no. test every 50m²
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Application Activities
checkpoint | 4.1 Method of Application
label | REFERENCE: Coating System TDS
label | ○ 685.07
label | ○ 686.07
label | ○ 686.09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Application should be carried out to the Manufacturer's TDS within 24 hours after completing the surface preparation so that the desired, uniform surface finish is achieved.
label | ○ Re-coating shall be within the recommended timeframe from the TDS and only if any defects or damage to the previous layer have been rectified.
label | ○ For penetrants, the material shall be applied at the lowest point, proceeding upwards to higher elevations and saturated enough so that a "wet look" can be observed for at least a few seconds after application.
label | ○ Times of coating(s), material names, locations coated and volumes used shall be recorded.
label | Attach: Coating Application Record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each coat
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Wet Film Thickness (WFT) Testing
label | REFERENCE: Coating System TDS
label | ○ 685.12 (b) (ii)
label | ○ 686.14 (b) (ii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Film-forming anti-graffiti coatings shall have a combined thickness of 175µm, for all other applications, the WFT shall be measured and be in accordance with the Product TDS.
label | Attach: WFT Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Inspection & Defect Identification
label | REFERENCE: 685.07
label | ○ 685.13 (d)
label | ○ 686.07
label | ○ 686.15
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The work shall be inspected for uniformity, colour, gloss, opacity and appearance between coats.
label | ○ Defects such as lumps, bubbles, inclusions, ripples, sags, runs and air holes shall be removed and re-application at those areas may be required.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: After each coat
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Drying and Curing
label | REFERENCE: Coating System TDS
label | ○ 685.17
label | ○ 686.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Coatings shall be protected from adverse conditions, dust and debris during the curing period.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: After each coat
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-application Activities
checkpoint | 5.1 Clean-up & Waste Disposal
label | REFERENCE: 685.09 (c), 686.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All coating drips, smudges and over-spray shall be removed from all surfaces, including surfaces not being treated.
label | ○ All rubbish and remaining coating products shall be removed from site.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: At completion of Works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Dry Film Thickness (DFT) Testing
label | REFERENCE: 685.12 (b) (iii), 686.14 (b) (iii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The total DFT of the system shall be tested to ensure that it meets the required minimum application thicknesses:
label | i. Anti-graffiti system = 100µm
label | Ii. Decorative & anti-carbonation = 150µm
label | iii. Decorative, anti-carbonation & anti-graffiti = 150µm
label | iv. Atmospheric & splash zone (dual protective) = 200µm
label | ○ No more than 15% of the readings shall be less than 90% of the required thickness.
label | Attach: DFT Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Adhesion Bond Strength Testing
label | REFERENCE: 685.12 (b) (i), 686.14 (b) (i)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: A minimum of 14 days after application, the bond-strengths between:
label | i. the coating system to the substrate, and
label | ii. Separate coating layers shall be tested using 50mmØ aluminium dollies.
label | ○ The subsequent results shall be greater than 0.75kPa.
label | Attach: Adhesive Bond Strength Testing Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Penetration Depth Testing
label | REFERENCE: 685.12 (b) (v), 686.14 (b) (v)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where a penetrant is applied, a 50mmØ core sample, 50mm depth, is to be taken and immersed in a fugitive dye to determine the depth of penetration.
label | The subsequent results shall be:
label | i. Sprayed anti-graffiti penetrants = unspecified (as long as it is visible)
label | ii. Silane, Solid Silane or Silane Cream = 5mm min.
label | iii. Silane-Siloxane or Siloxane = 3mm min.
label | Attach: Penetration Depth Testing Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where required, 1 no. test every 50m², 3 tests minimum
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Non-conforming Coatings
label | REFERENCE: 685.14, 686.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Should any of the coating application Work be found to be non-compliant with the specifications, the areas shall be repaired.
label | ○ Such Work may include removal of the coating, surface preparation and re-application.
label | ○ Non-compliant Work includes, coating failure to yellowing, loss of adhesion, penetration of graffiti into the coating, loss of solvent resistance and colour change during the contract liability and/or guarantee period.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where required
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Coating Application Guarantee
label | REFERENCE: 685.06 (b), 686.05 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Application shall be guaranteed to last for 10 years of outdoor exposure and for anti-graffiti coatings, have at least 8 cycles of graffiti defacement and removal from the date of application.
label | Attach: Coating Application Guarantee
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: At completion of Works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: SP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Repair to Damaged Coating
label | REFERENCE: 686.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Any damage to the coating during the construction period shall be repaired to the full extent of the system requirements.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where required
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP
checklist | ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting | itp |  |  |  |  | ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-183-CIV-SSB-Conduits and Pits-MTM Carpark lighting
label | ITP Description: Conduit and Pits- MTM Car Park Lighting
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 13/11/2023
label | ITP created by: Romualdo Magpantay
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: L1-CHE-STD-035
label | 1.3 Non Dependent
label | Reference: AS /NZS 3000
section | Preliminaries
checkpoint | 2.1 Obtain and review manufacturer documentations for the supply of materials
label | ○ LV + HV Conduits
label | ○ Communication Conduits
label | ○ Fixing and Supporting Materials
label | ○ Pits
label | REFERENCE: IFC Drawing, Supplier Specification AS /NZS 3000
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Materials comply with relevant specifications.
label | ○ Obtain conformance certificates and submit to the Nominated Authority prior inclusion into the works.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Inspect supplied items upon delivery
label | REFERENCE: IFC Drawing, Supplier Specification AS /NZS 3000
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Supplied items are to correct spec, class, size and undamaged
label | – – – – – – – – – – – – – – – – –
label | METHOD: Testing
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Electricians, Site /Project Engineer
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 3.1 Excavation of Conduit Trenches & Pits
label | REFERENCE: AS/NZS 3000 clause 3.9, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Install the conduits after earthworks have been completed to subgrade level.
label | ○ Installation of the conduits must be in accordance in the design dwgs.
label | ○ Where the conduits run beneath a road, provide a minimum cover of 500 mm from the top of the conduits to the underside of the pavement; in all other areas, provide a cover of 500 mm to finished surface level.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.2 Sand bedding, laying and backfilling
label | REFERENCE: AS/NZS 3000 clause 3.11.4.5, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Use a min. 50mm compacted sand for bedding if not shown on the design drawings.
label | ○ Lay the conduit on a straight grade and line
label | ○ Compact backfill over the conduits to 100% relative compaction or depend on IFC drawing & pavement design requirements.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.3 Install conduits according to manufacturer’s instructions, relevant drawings and Standards
label | REFERENCE: AS/NZS 3000 clause 3.9, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The works are constructed in accordance with AS/NZS 3000 Wiring Rules and Services and the installation Rules of AS 2067.
label | ○ Conduits are joined together with solvent cement, generally in accordance with clause 4.2 of AS/NZS 2032 and all joints are water tight and free of foreign matter
label | ○ Conduits are inline & positioned evenly
label | ○ Location of each conduit is as per Design Drawings
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.4 Installation of Electrical and Communication Pits
label | REFERENCE: IFC Drawings, L1-CHE-STD-035 section 12.6
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Compliance to IFC Drawings, Schedules & relevant specification:
label | ○ Correct pit as per the IFC drawings
label | ○ Soil underneath pit bedding is to be firmly packed prior to install
label | ○ Bedding according to IFC drawings to be placed
label | ○ Pit orientation is correct
label | ○ Lids & covers to comply with technical specification
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.5 Marker Tapes
label | REFERENCE: AS/NZS 3000 clause 3.11.4.5, IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Wiring systems installed underground shall be identified by an orange marker tape complying AS/NZS 2648.1. Positioned at approximately 50% of depth cover above wiring system or any additional mechanical protection provided that system.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.6 Install draw-in rope to all electrical conduits(if applicable)
label | REFERENCE: IFC Drawings, QA & Work method of statement
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Polypropylene draw-in rope consisting of one continuous length of not less than 4mm dia. in all electrical conduits or specify in methodolody
label | – – – – – – – – – – – – – – – – –
label | METHOD: Inspection
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once,
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post Construction Activies
checkpoint | 4.1 As-built Survey (if required)
label | REFERENCE: As Built Drawings, Asset Change form
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey activities undertaken to validate correct construction
label | Attach: Surevy Report, Engineering Asset From
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Supervisor /PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP
checklist | ITP-184-CIV-SSB-Conduits and Pits-Road | itp |  |  |  |  | ITP-184-CIV-SSB-Conduits and Pits-Road Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-184-CIV-SSB-Conduit & Pits
label | ITP Description: SSB-Conduit & Pits
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 184-CIV
label | Revision Number: 0
label | Revision Date: 13/01/2024
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: VR 733 November 2023
label | 1.2 Non Dependent
label | Reference: AS/NZS 3000:2018 Wiring Rules
section | Preliminaries - Materials
checkpoint | 2.1 Conduits-Electrical
label | REFERENCE: VR 733.04 (a), Table 733.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless otherwise specified, the Contractor shall provide all plastic conduits which shall comply with the following standards as appropriate:
label | – AS 1345 – Identification of pipes, conduits and ducts
label | – AS/NZS 2053 – Conduits and fittings for electrical installations
label | ○ All conduits installed underground for electrical wiring, traffic signals and traffic services shall be heavy duty grade, rigid, solid wall, orange, UPVC conduit to AS/NZS 2053.2.
label | ○ Conduit sizes shall be according to Table VR 733.041
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Conduits-Comms
label | REFERENCE: VR 733.04 (a), Table 733.041
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless otherwise specified, the Contractor shall provide all plastic conduits which shall comply with the following standards as appropriate:
label | – AS 1345 – Identification of pipes, conduits and ducts
label | – AS/NZS 2053 – Conduits and fittings for electrical installations.
label | ○ All conduits installed underground for communication cables shall be heavy duty grade, rigid, solid wall, white UPVC communication conduit complying with AS/NZS 2053.2 and complying with all relevant Australian Communications and Media Authority (ACMA) publications and standards.
label | ○ Conduit sizes shall be according to Table VR 733.041
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Conduits-HDPE
label | REFERENCE: VR 733.04 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The use of HDPE continuous conduit for bored road crossing is permitted.
label | ○ Where HDPE continuous conduit is used for electrical cables, it shall not be smaller in internal diameter than the specified UPVC heavy duty conduit.
label | ○ Conduit sizes shall be according to Table VR 733.041
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Pits and Pit Lids
label | REFERENCE: VR 733.09 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All cable pits, cable pit lids and preformed cable pit lid surrounds shall be DTP Type Approved.
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 Backfill and bedding Material
label | REFERENCE: VR 733.08 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless otherwise specified, materials used for bedding and backfilling shall be free from perishable matter and shall conform with the appropriate grading and plasticity index requirements specified in Table 733.081
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
date | Date Completed:
checkpoint | 2.3 Warning/Marker Tape
label | REFERENCE: AS/NZ 3000, VR 733.06 (c )
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Warning/Marker tapes shall be selected as per wiring rules.
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Material approval in TeamBinder
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 Draw Wires
label | REFERENCE: VR 733.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each conduit for electrical wiring and communication cables shall be provided with one synthetic draw cord not less than 3 mm diameter and with a minimum breaking strain of 1.6 kN.
label | ○ Inspect materials upon delivery and attached delivery dockets.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Grout
label | REFERENCE: VR 733.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The grout mixture shall be suitable for backfilling around conduits carrying low voltage electrical cables and shall have the following properties:
label | – low exothermic temperature generation during curing.
label | – a thermal resistivity (TR) value of less than 1.2K.m/W when fully dried.
label | – a maximum grout flow time through a standard flow cone test of 30 seconds in accordance with AS 1478.2.
label | – compressive strength in the range of 0.5 to 2.0 MPa at 28 days.
label | – a maximum heat of hydration of 35ºC when tested in an insulated 300mm x 300mm cube
textbox | Enter: TeamBinder Material Approval Number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Material Type, Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE, Nominated Authority
label | – – – – – – – – – – – – – – – – –
textbox | VERIFYING DOCUMENTS: Enter: TeamBinder Material Approval Number
date | Date Completed:
section | Prelimnaries - Procedures & Documentation
checkpoint | 3.2 Prequalified Contractor
label | REFERENCE: VR 733.01 (c), VR 733.02 and table VR 733.021
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All works associated with the installation and of all conduits and pits covered under this specification shall be undertaken by contractors that are appropriately pre-qualified as detailed in Table 733.021
label | ○ Electrical conduits, and associated cable pits, installed as part of an electrical installation MUST be installed by, or under the direct supervision of a Pre-qualified and Registered Electrical Contractor.
label | Attach: contractor qualifications
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Boring
label | REFERENCE: VR 733.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Detailed proposals for boring under carriageways shall be submitted to the superintendent for review two weeks prior to the programmed commencement of work.
textbox | Enter: Team Binder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | Pre-Construction Activities
checkpoint | 4.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to set out trench alignment and pits, and establish construction control (alignment and level).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencement of works
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 IFC Drawings
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to commencement of works and at regualr intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction Activities
checkpoint | 5.1 Trench/Bore-Depth
label | REFERENCE: VR 733.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Unless otherwise shown on the drawings or specified, borings and trenches shall comply with the depth requirements specified in Table 733.051.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Trench excavation-Grade
label | REFERENCE: VR 733.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Trench/conduit depth shall be maintained between pits and graded to avoid low points in the conduit run
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Placement of Bedding Sand for Conduits
label | REFERENCE: VR 733.08 (b) (i)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bedding material shall be placed and compacted for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation. Following compaction, the bedding material shall be shaped sufficiently to maintain the conduit in line as the sections are placed in position. Shaping of bedding material is not required for conduits less than 100 mm nominal diameter.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Conduit Placement & Configuration
label | REFERENCE: VR 733.06 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Conduits installed for DTP works shall be installed to the following requirements:
label | (i) all conduits shall terminate in a pit.
label | (ii) only one size and type of conduit shall be used for a complete run between pits; unequal size conduits shall not be joined in the ground.
label | (iii) all conduits shall be temporarily sealed prior to cabling to avoid blockage.
label | (iv) changes in direction of conduit shall only be made at approved cable pits.
label | (v) changes in conduit direction to enable entry into the base of a cable pit may be by means of a sweep bend:
label | ○ Minimum Bend Radius for Electrical UPVC: 600mm
label | ○ Minimum Bend Radius for Communications UPVC: 500mm
label | (vi) elbows and ‘tees’ shall not be used.
label | (vii) all conduit joints shall be correctly prepared and sealed with approved solvent cement.
label | (viii) conduits for detector cables shall be installed as shown in Standard Drawings TC 1207 and TC 1320.
label | (ix) a 50 mm electrical (orange) conduit shall be used to convey the detector feeder cable from the detector pit to the cable pit, as shown in Standard Drawing TC 1207.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Conduits Installation
label | REFERENCE: VR 733.06 (b) (c )
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Conduits installed for traffic signals and other on-road electrical installations shall be installed in accordance with this standard specification, DTP Standard Drawings detailed in Table 733.032 and individual contract documents.
label | ○ Conduits installed on Managed Motorways and freeways shall be installed in accordance with this standard specification, DTP Standard Drawings detailed in Table 733.033 and individual contract documents.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Conduits installation-Inspection
label | REFERENCE: VR 733.08 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Backfilling Bore access
label | REFERENCE: VR 733.05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: before backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Vicual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot where applcable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Backfilling
label | REFERENCE: IFC Drawings, VR 733.08 (b) (c)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: When conduit sections are in position, additional layers of bedding material shall be placed and compacted to a height 150 mm above the bedding previously placed.
label | ○ Unless otherwise specified or shown on the drawings, selected and common backfill shall be placed and compacted as follows under, around, and above the conduit after the sections are bedded.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Marker Tape
label | REFERENCE: VR 733.06 (a), AS/NZS 3000
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: A marker tape with trace wire shall be placed above all conduits in accordance with the Wiring Rules.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Backfilling-Compaction
label | ACCEPTANCE CRITERIA: Unless otherwise specified, bedding and backfill materials shall have during compaction, a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard Compaction test.
label | ○ Bedding and backfill, the whole of which passes the 37.5 mm AS sieve, shall be compacted in layers to a density ratio of not less than 95%.
label | Attach: compaction test results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each day production
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP/Daily compaction test results
date | Date Completed:
checkpoint | Pits and lids installation-Cable pits-Traffic signals and general works
label | REFERENCE: VR 733.09 (d)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cable Pits and Lids for Traffic Signals and other on-road electrical shall be constructed and installed as shown in the drawings detailed in Table 733.091
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Pits and lids installation-Cable pits-Managed Motorways and freeways
label | REFERENCE: VR 733.09 (e )
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cable Pits and Lids for Managed Motorways and freewaysshall be constructed and installed as shown in the drawings detailed in Table 733.092.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Communication Pits for Managed Motorways and freeways
label | REFERENCE: VR 733.09 (f)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Communications pits shall be constructed and installed as shown in the drawings detailed in Table 733.093
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Communication Pits for Arterial Roads
label | REFERENCE: VR 733.09 (g)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Communications pits shall be constructed and installed as shown in the drawings detailed in Table 733.094
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Detector Pits
label | REFERENCE: VR 733.10
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Detector pits for traffic signals shall be installed as shown on the traffic signal plans and as detailed in individual contract documents.
label | ○ Detector pits for freeway data stations or other required purposes shall be installed as detailed in individual contract documents.
label | ○ Detector pits and detector pit covers shall be constructed and installed in accordance with Standard Drawings TC 1310 and TC 1320.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Conduits connection to pits
label | REFERENCE: VR 733.09 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All conduit connections to cable pits shall be neatly made and the ends of the conduits trimmed off and deburred to prevent damage to cables. Pits installed for Managed Motorway installations shall also be fitted with a conduit bush. The area between the conduit and pit wall shall be stopped with a suitable sealant that bonds to the pit wall and the conduit.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Pit installation-Inspection
label | ACCEPTANCE CRITERIA: Before the pit lid surround or pre-formed collar is cemented into position an inspection by the superintendent or representative must be carried out.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This Itp
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 Identification
label | REFERENCE: VR 733.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All conduit locations not identified by pits immediately installed at the ends shall be marked with 75 x 38 mm stakes projecting 0.4 m above the ground, with the top 150 mm painted yellow stakes, or as otherwise agreed by the Superintendent. Conduits under road pavement shall be marked with stakes clear of the road pavement. Conduits not under road pavement shall be marked with stakes at the ends, at changes of direction, and at intervals of not more than 30 m.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.19 Draw Ropes
label | REFERENCE: VR 733.07
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Each conduit for electrical wiring and communication cables shall be provided with one synthetic draw cord not less than 3 mm diameter and with a minimum breaking strain of 1.6 kN.
label | ○ Where the conduit terminates in a pit, not less than 500 mm of the draw cord shall be tied to a marker peg 25 mm x 25 mm, not less than 300 mm long, and left coiled in the pit. A length of 100mm diameter conduit not less than 200mm may be used.
label | ○ Where the conduit does not terminate in a pit, the draw cords shall be tied to a marker peg 100 mm x 100 mm, not less than 400 mm long, driven firmly into the ground with the top 50 mm projecting above finished surface and painted yellow.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Pit
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 As-built Survey
label | REFERENCE: VR 733.13 (i) (ii)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: the contractor shall provide:
label | – As-built’ drawings showing the complete conduit network including conduit types, sizes and depths.
label | – The above ‘As-built’ drawings shall also show all pits, pit types and pit sizes.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Certification
label | REFERENCE: VR 733.13 (iii) (iv)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: the contractor shall provide:
label | – Certificates of electrical safety for all conduits and pits installed.
label | – Documentation demonstrating that all pits and conduits installed, have been installed in accordance with the requirements of this specification.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE, MTM/VicTrack Rep
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
date | Date Completed:
signoff | Sign ITP