## Sheet1
Sikaproof A+ Application
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
Text | Suppoting documentations - e.g location, CIDD alerts etc.
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
Checkpoint | SikaProof A+
Label | Records - Photograph
Label | surveillance point
Checkpoint | Sikaproof Patch - 200B
Label | Records - Photograph
Label | surveillance point
Checkpoint | Sikaproof fixtape- 50
Label | Records - Photograph
Label | surveillance point
Checkpoint | Sikaswell S2
Label | Records - Photograph
Checkpoint | Sikadur 31
Label | Records - Photograph
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | First Of Type Inspection
Label | The first type inspection must be conducted by Sika, waterproofing integrity specialists, and Mirvac representatives.
Label | Record Submissions
Checkpoint | Material Management & Storage
Label | SikaProof A+ must be stored upright in dry, cool conditions away from direct UV and weather exposure. The maximum storage temperature is 55°C.
Label | Record of equipment and tools used
Label | Records - Photograph
Label | Witness Point
Checkpoint | Acceptance of Substrate
Label | The substrate should be sound and even to prevent movement or subsidence during concrete placement.
Label | The substrate should have no protrusions, gaps, or voids greater than 12-15mm. Such imperfections must be filled prior to installation.
Label | Suitable substrates include concrete blinding, formwork, rigid thermal insulation, and plywood sheets.
Label | Penetrations such as plumbing and electrical pipes should be stabilized to prevent movement during membrane and concrete placement.
Label | Ensure the substrate is sound and free of any ponding or pooling water.
Ensure the substrate is sound and capable of providing the required support for the membrane during concrete placement.
Label | Identify cracks less than or equal to 1mm and pre-fill with mastic (refer to project spec). Identify cracks between 1mm and 1.6mm and route out 7mm wide x 13mm deep rebate and fill with backing
Label | Records - Photograph
Label | Witness Point
SECTION | SHEET MEMBRANE APPLICATION - EACH LOCATION
Checkpoint | Bond Breaker - Shopdrawings
Label | Install bond breaker (core flute) on all walls and non-horizontal slopes/batters
Label | Records - Photograph
Label | Witness Point
Checkpoint | Horizontal Application
Label | For Horizontal surfaces: Side lap joints must be min 80mm and end lap joints must be min 150mm. Seal overlaps by heat welding Stagger end laps by min 300mm
Records - Photograph
Label | Witness Point
Checkpoint | Vertical Application
Label | For Shotcrete walls: Side lap joints must be minimum 80mm and end lap must be min 150mm. Seal overlaps by heat welding. Stagger end laps by min 300mm
Label | Records - Photograph
Label | Witness Point
Checkpoint | Service Supports within Slab
Label | For All Services supports within Slab: 2 layers of SikaProof A+ Tape installed over service support bracket with SikaSwell S2 installed ontop of first layer of tape, with second layer of tape installed over
Checkpoint | Pipe Penetrations
For All Pipe penetrations within Slab (Ground Anchors & Dewatering spiers): Floor Sheet membrane to Lap up Pipe with Sikaproof Tape A + Taped over minimum 50mm. Epoxy grout poured around pipe minimum 15mm from the top of the Sheet membrane termination (Highest Point) and 35mm wide Sika Swell A 2010M profiles adhered to substrate with SikaSwell S2
SECTION | MICRO PILE CAP APPLICATION - EACH LOCATION
Label | At pile termination points scribe shape of pile onto membrane (refer to project spec) so that it fits tightly around perimeter of pile. Ensure pile has been cleaned previously of all dirt and loose materials, sharp edges removed, all cracked concrete removed
Label | Install an epoxy cap over entire pile, min 30mm thick (as measured from highest point in top of pile surface) and 50mm overlap onto membrane (around circumference of pile)
Label | Apply 30mm x 30mm bead of epoxy adhesive (refer to project spec) to over seal and lock in membrane and epoxy pile cap
Label | For slabs which do not terminate against a retaining or secant wall, the membrane must be turned up the vertical edge of the slab and Epoxy terminated
Label | Records - Photograph
Label | Hold Point
SECTION | DEWATERING SPEARS - EACH LOCATION
Label | At Spear termination points scribe shape of pile onto membrane (refer to project spec) so that it fits tightly around perimeter of pile. Ensure pile has been cleaned previously of all dirt and loose materials, sharp edges removed, all cracked concrete removed
Label | Install Sikadur 42 over entire pile, min 30mm thick (as measured from highest point in top of pile surface) and 50mm overlap onto membrane (around circumference of pile) Note: top of epoxy cap to have a rough/scabble like finished texture
Label | Install SikaSwell S2 waterstop above Epoxy infill
SECTION | ROCK WALL ANCHOR - EACH LOCATION
Label | On removal of Anchors allow to patch repair with SIka MonoTop - 612
Label | Patch with Sikaproof A+12
Label | Ensure Sikaswell A2010 is installed above and below anchor
Section | QA TESTING - EACH LOCATION
Checkpoint | Inspection
Label | Inspect after installation of reinforcement/finishes to check for any damage to waterproofing and rectify as required.
Label | Records - Photograph
Label | Witness Point
Checkpoint | Testing - Probe hook testing
Label | Undertake Hook testing seems and laps and rectify if failed.
Label | Records - Photograph
Label | Hold Point
SECTION | CONSTRUCTION JOINT DETAILING- EACH LOCATION
CHECKPOINT | Hydrophilic Seal application
Label | Smoothen construction joint by grinding and/or application of waterproof resin epoxy locally under location of hydrophilic.
Label | Install hydrophilic seal over smoothened section of all construction joints. Minimum cover of 80mm
Label | fix hydrophilic seal with sikaswell S2 into place at min 250mm centers. Ensure hydrophilic is fully flat against substrate (no gaps)
Label | Inspect after reinforcement installation to check for any damage to waterproofing and rectify as required
Label | Records - Photograph
Label | Witness Point
SECTION | SIGN OFFS
Checkpoint | Polyseal ITP acceptance Sign off
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman ITP accceptance Sign off
SIGNOFF | Site Engineer/foreman inspection sign off