## Sheet1
Sikaproof P + Application
SECTION | DETAILS
Checkpoint | Attach any relevant documents or photos
text | ITP No.
text | Revision No. & Date
text | Prepared By
text | Reviewed By
text | Approved By
Text | Suppoting documentations - e.g location, CIDD alerts etc.
SECTION | BATCH DETAIL NUMBER OF PRODUCTS - EACH DELIVERY
Checkpoint | Sarnacol 2152
Label | Records - Photograph
Label | surveillance point
Checkpoint | Sikaproof P-1200
Label | Records - Photograph
Label | surveillance point
Checkpoint | Sikadur 31
Label | Records - Photograph
Label | surveillance point
SECTION | PRE COMMENCEMENT - EACH LOCATION
Checkpoint | First Of Type Inspection
Label | The first type inspection must be conducted by Sika, waterproofing integrity specialists, and Mirvac representatives.
Label | Record Submissions
Checkpoint | Material Management & Storage
Label | SikaProof P-1201 must be stored upright in dry, cool conditions away from direct UV and weather exposure. The maximum storage temperature is 55°C.
Label | Records - Photograph
Label | Witness Point
Checkpoint | Acceptance of Substrate
Label | The substrate should be sound and even to prevent movement or subsidence during concrete placement.
Label | The substrate should have no protrusions, gaps, or voids greater than 12-15mm. Such imperfections must be filled prior to installation.
Label | Suitable substrates include concrete blinding, formwork, rigid thermal insulation, and plywood sheets.
Label | Penetrations such as plumbing and electrical pipes should be stabilized to prevent movement during membrane and concrete placement.
Label | Ensure the substrate is sound and free of any ponding or pooling water.
Ensure the substrate is sound and capable of providing the required support for the membrane during concrete placement.
Label | Identify cracks less than or equal to 1mm and pre-fill with mastic (refer to project spec). Identify cracks between 1mm and 1.6mm and route out 7mm wide x 13mm deep rebate and fill with backing
Label | Records - Photograph
Label | Witness Point
SECTION | SHEET MEMBRANE APPLICATION - EACH LOCATION
Checkpoint | Priming - Sarnacol 2152
Label | Mix components A+B together with the correct proportion By volume A:B 100:25 or by weight A:B 100:19 into a suitable mixing pail for at least 3 minutes with a low speed mixer until the material becomes smooth in consistency and a uniform white colour. 2) Pour the whole mix into another clean container and mix again for at least 1 more minute.
Label | Apply Sarnacol 2152 with a notched trowel (minimal 3 mm tooth) onto the entire substrate (no primer required).
Label | Records - Photograph
Label | Witness Point
Checkpoint | Application - SikaProof P -1201
Label | Side lap joints must be min 90mm and glued and overlaped with Sarnacol 2152
Label | Always install Sheets from the lowest to the highest point
Records - Photograph
Label | Witness Point
SECTION | TERMINATION - EACH LOCATION
Label | Heat membrane by torch to activate and apply Sikadur 31 to terminate
Label | Records - Photograph
Label | Hold Point
SECTION | PROTECTION - EACH LOCATION
Label | Protect membrane post application prior to backfilling
Label | Records - Photograph
Label | Witness Point
SECTION | SIGN OFFS
Checkpoint | Polyseal ITP acceptance Sign off
SIGNOFF | Subcontractor inspection sign off
Checkpoint | Site Engineer/foreman ITP accceptance Sign off
SIGNOFF | Site Engineer/foreman inspection sign off