## Sheet1
1.1 | Submission of Mix Design (Type Asphalt, mm Nominal Size) | Prior to commencing paving | Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix. | VicRoads Spec. Cl.407.06 | Correspondence of receipt of mix design | VR approval Completed ITP | HP | Site Engineer/ Asphalt Supervisor / Superintendent | 1.1 - Submission of Mix Design (Type Asphalt, mm Nominal Size) | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06 | INSPECTION/TEST METHOD: Correspondence of receipt of mix design | RECORD OF CONFORMITY: VR approval Completed ITP | HP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent | Date Completed: | 1.1 - Submission of Mix Design (Type Asphalt, mm Nominal Size)
1.2 | Implementation of all measures and controls | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation. | SMP, PMP, EMP, QMP, TMP and SEQ documentation. | Visual Inspection | This ITP signed off | HP* | Site Engineer / Site Foreman | 1.2 - Implementation of all measures and controls | FREQUENCY: Prior to commencing any activity | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation. | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation. | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: This ITP signed off | HP* | RESPONSIBILITY: Site Engineer / Site Foreman | Date Completed: | FREQUENCY: Prior to commencing paving
1.3 | Site Inspection and Base Condition | Prior to commencing paving | Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials. Material and compaction test certificates conform for pavement | 407.14 AS2150 10.1 AS2150 10.3 | Visual Inspection | ITP Signed Test Certificates Base Course Checklist | HP | Site Engineer/ Asphalt Supervisor | 1.3 - Site Inspection and Base Condition | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials. Material and compaction test certificates conform for pavement | REFERENCE DOCUMENTS: 407.14 AS2150 10.1 AS2150 10.3 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed Test Certificates Base Course Checklist | HP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix.
1.4 | Dryback | Prior to commencing paving | Scale B Pavement Dryback and Embedment - 6 randomly selected test sites per lot required - If Mean Moisture Ratio is CHAR(LESS) 60% CHAR(AMP) Maximum of any result is CHAR(LESS) 70% then Ball Penetration not required - If Mean Moisture Ratio is CHAR(LESS) 65% CHAR(AMP) Maximum of any result is CHAR(LESS) 70% then Ball Penetration Maximum individual result is 3mm - Testing schedule in accordance with 310.03 (c) | 310.03(a) 310.03(b) Table 310.031 310.03(c) Table 310.032 | Verify | ITP Signed off | TP | Site/Project Engineer/ Supervisor | 1.4 - Dryback | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment - 6 randomly selected test sites per lot required - If Mean Moisture Ratio is CHAR(LESS) 60% CHAR(AMP) Maximum of any result is CHAR(LESS) 70% then Ball Penetration not required - If Mean Moisture Ratio is CHAR(LESS) 65% CHAR(AMP) Maximum of any result is CHAR(LESS) 70% then Ball Penetration Maximum individual result is 3mm - Testing schedule in accordance with 310.03 (c) | REFERENCE DOCUMENTS: 310.03(a) 310.03(b) Table 310.031 310.03(c) Table 310.032 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: ITP Signed off | TP | RESPONSIBILITY: Site/Project Engineer/ Supervisor | Date Completed: | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
1.5 | Ambient Conditions for Placing | Prior to commencing paving | The majority of the surface area to be paved has a temperature greater than or equal to the following: Wearing Courses: 10°C for conventional binders or 15°C for PMBs | 407.17(a) | Verify | Thermometer | IP | Site Engineer/ Asphalt Supervisor | 1.5 - Ambient Conditions for Placing | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following: Wearing Courses: 10°C for conventional binders or 15°C for PMBs | REFERENCE DOCUMENTS: 407.17(a) | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Thermometer | IP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
1.6 | Planning of Joints | Prior to commencing paving | Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. | 407.21 IFC Drawings | Measure and mark out runs by tape measure or survey | Paving Plan | WP | Project Engineer/ Asphalt Supervisor | 1.6 - Planning of Joints | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. | REFERENCE DOCUMENTS: 407.21 IFC Drawings | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey | RECORD OF CONFORMITY: Paving Plan | WP | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor | Date Completed: | RECORD OF CONFORMITY: VR approval Completed ITP
1.7 | Longitudinal Joints with existing Pavement | Prior to commencing paving | Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer. | 407.21 (c) | Visual Inspection | ITP Signed | WP | Project Engineer/ Asphalt Supervisor | 1.7 - Longitudinal Joints with existing Pavement | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer. | REFERENCE DOCUMENTS: 407.21 (c) | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | WP | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor | Date Completed: | HP
2.1 | Frequency of Inspection and Testing at the Mixing Plant | As per Table 407.151 | The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product. | 407.151 | Test Inspection | ITP Signed | TP | Project Engineer/ Asphalt Supervisor | 2.1 - Frequency of Inspection and Testing at the Mixing Plant | FREQUENCY: As per Table 407.151 | ACCEPTANCE CRITERIA: The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product. | REFERENCE DOCUMENTS: 407.151 | INSPECTION/TEST METHOD: Test Inspection | RECORD OF CONFORMITY: ITP Signed | TP | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor | Date Completed: | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
2.2 | Tack Coat | Prior to commencing paving | As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm. Tack coat to be sprayed on existing asphalt joints. Tack coat must be allowed to turn from brown to black before paving. If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. | 407.19 AS2150 11 | Visual Inspection | Spray area | WP | Site Engineer/ Asphalt Supervisor | 2.2 - Tack Coat | FREQUENCY: Prior to commencing paving | ACCEPTANCE CRITERIA: As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm. Tack coat to be sprayed on existing asphalt joints. Tack coat must be allowed to turn from brown to black before paving. If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. | REFERENCE DOCUMENTS: 407.19 AS2150 11 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Spray area | WP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | Date Completed:
2.3 | Commencement of Placing | Prior to commencing Paving | The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client. | 407.23 | Visual Inspection | ITP Signed | HP | Site Engineer/ Asphalt Supervisor / Superintendent | 2.3 - Commencement of Placing | FREQUENCY: Prior to commencing Paving | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client. | REFERENCE DOCUMENTS: 407.23 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | HP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent | Date Completed: | 1.2 - Implementation of all measures and controls
2.4 | Mix Design Confirmation | Each lot | Check correct mix design as per pavement design has been delivered prior to laying mix. | VicRoads Spec. Cl.407.09 | Visual Inspection CHAR(AMP) Delivery Docket | Delivery docket Completed ITP | HP* | Site Engineer/ Asphalt Supervisor | 2.4 - Mix Design Confirmation | FREQUENCY: Each lot | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix. | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09 | INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Delivery Docket | RECORD OF CONFORMITY: Delivery docket Completed ITP | HP* | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | FREQUENCY: Prior to commencing any activity
2.5 | Delivery of Mix | Each load | Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. | 407.11 | Visual Inspection | Delivery Docket | WP | Site Engineer/ Asphalt Supervisor | 2.5 - Delivery of Mix | FREQUENCY: Each load | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C. | REFERENCE DOCUMENTS: 407.11 | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: Delivery Docket | WP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
2.6 | Traceability | Each lot | Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer | Fulton Hogan Quality Plan | Verify | Daily Lot Record | IP | Site Engineer/ Asphalt Supervisor | 2.6 - Traceability | FREQUENCY: Each lot | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Daily Lot Record | IP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
2.7 | Layer Thickness and Level Control | Regularly during paving | Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications | IFC Drawings | Verify | Dips using ruler or dip stick | WP | Site Engineer/ Asphalt Supervisor | 2.7 - Layer Thickness and Level Control | FREQUENCY: Regularly during paving | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications | REFERENCE DOCUMENTS: IFC Drawings | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Dips using ruler or dip stick | WP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | INSPECTION/TEST METHOD: Visual Inspection
2.8 | Paver Stoppages | If paver stops | A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C | 407.25 (c) | Verify | Thermometer | WP | Site Engineer/ Asphalt Supervisor | 2.8 - Paver Stoppages | FREQUENCY: If paver stops | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C | REFERENCE DOCUMENTS: 407.25 (c) | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Thermometer | WP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | RECORD OF CONFORMITY: This ITP signed off
2.9 | Surface Finish of Wearing Course | During paving and after final roll | The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks | 407.29 (a)(i) | Visual Inspection | ITP Signed | WP | Site Engineer/ Asphalt Supervisor | 2.9 - Surface Finish of Wearing Course | FREQUENCY: During paving and after final roll | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks | REFERENCE DOCUMENTS: 407.29 (a)(i) | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | WP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | HP*
2.1 | Kerb and Channel | During paving and after final roll | The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified | 407.29 (a)(ii) | Visual Inspection | ITP Signed | WP | Site Engineer/ Asphalt Supervisor | 2.1 - Kerb and Channel | FREQUENCY: During paving and after final roll | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified | REFERENCE DOCUMENTS: 407.29 (a)(ii) | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | WP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | RESPONSIBILITY: Site Engineer / Site Foreman
2.11 | Alignment of layers not placed against concrete edge | During paving and at completion of work | The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m | 407.29 (a)(iv) Drawings | Visual Inspection | ITP Signed | IP | Site Engineer/ Asphalt Supervisor | 2.11 - Alignment of layers not placed against concrete edge | FREQUENCY: During paving and at completion of work | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m | REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | Date Completed:
2.12 | Width of layers not placed against concrete edge | During paving and at completion of work | The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300m shall not be less than the design or specified width | 407.29 (a)(v) | Visual Inspection | ITP Signed | IP | Site Engineer/ Asphalt Supervisor | 2.12 - Width of layers not placed against concrete edge | FREQUENCY: During paving and at completion of work | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300m shall not be less than the design or specified width | REFERENCE DOCUMENTS: 407.29 (a)(v) | INSPECTION/TEST METHOD: Visual Inspection | RECORD OF CONFORMITY: ITP Signed | IP | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor | Date Completed: | 1.3 - Site Inspection and Base Condition
3.1 | Compaction | Per Lot | For layers CHAR(LESS)50mm, if characteristic density ratio is: 94.0% or greater Accept lot 91.0% to 93.9% Lot may be accepted at reduced rate | Table 407.271 | Verify | Test Report | TP | Site Engineer/ Lab Technician | 3.1 - Compaction | FREQUENCY: Per Lot | ACCEPTANCE CRITERIA: For layers CHAR(LESS)50mm, if characteristic density ratio is: 94.0% or greater Accept lot 91.0% to 93.9% Lot may be accepted at reduced rate | REFERENCE DOCUMENTS: Table 407.271 | INSPECTION/TEST METHOD: Verify | RECORD OF CONFORMITY: Test Report | TP | RESPONSIBILITY: Site Engineer/ Lab Technician | Date Completed: | FREQUENCY: Prior to commencing paving
3.2 | Level Conformance | Per 4,000m2 at completion of work | Scale B Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm Minimum number of measurements per lot is 40 (ii) Kerb and Channel Refer to Item 2.10 of this ITP | Table 407.293 Table 407.292 | Survey by VicRoads Section 173 | Survey Conformance | SCP | Site Engineer/ Surveyor | 3.2 - Level Conformance | FREQUENCY: Per 4,000m2 at completion of work | ACCEPTANCE CRITERIA: Scale B Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm Minimum number of measurements per lot is 40 (ii) Kerb and Channel Refer to Item 2.10 of this ITP | REFERENCE DOCUMENTS: Table 407.293 Table 407.292 | INSPECTION/TEST METHOD: Survey by VicRoads Section 173 | RECORD OF CONFORMITY: Survey Conformance | SCP | RESPONSIBILITY: Site Engineer/ Surveyor | Date Completed: | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials. Material and compaction test certificates conform for pavement
REFERENCE DOCUMENTS: 407.14 AS2150 10.1 AS2150 10.3
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed Test Certificates Base Course Checklist
HP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
1.4 - Dryback
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment - 6 randomly selected test sites per lot required - If Mean Moisture Ratio is CHAR(LESS) 60% CHAR(AMP) Maximum of any result is CHAR(LESS) 70% then Ball Penetration not required - If Mean Moisture Ratio is CHAR(LESS) 65% CHAR(AMP) Maximum of any result is CHAR(LESS) 70% then Ball Penetration Maximum individual result is 3mm - Testing schedule in accordance with 310.03 (c)
REFERENCE DOCUMENTS: 310.03(a) 310.03(b) Table 310.031 310.03(c) Table 310.032
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: ITP Signed off
TP
RESPONSIBILITY: Site/Project Engineer/ Supervisor
Date Completed:
1.5 - Ambient Conditions for Placing
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following: Wearing Courses: 10°C for conventional binders or 15°C for PMBs
REFERENCE DOCUMENTS: 407.17(a)
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Thermometer
IP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
1.6 - Planning of Joints
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
REFERENCE DOCUMENTS: 407.21 IFC Drawings
INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
RECORD OF CONFORMITY: Paving Plan
WP
RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
Date Completed:
1.7 - Longitudinal Joints with existing Pavement
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer.
REFERENCE DOCUMENTS: 407.21 (c)
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
WP
RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
Date Completed:
2.1 - Frequency of Inspection and Testing at the Mixing Plant
FREQUENCY: As per Table 407.151
ACCEPTANCE CRITERIA: The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product.
REFERENCE DOCUMENTS: 407.151
INSPECTION/TEST METHOD: Test Inspection
RECORD OF CONFORMITY: ITP Signed
TP
RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
Date Completed:
2.2 - Tack Coat
FREQUENCY: Prior to commencing paving
ACCEPTANCE CRITERIA: As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm. Tack coat to be sprayed on existing asphalt joints. Tack coat must be allowed to turn from brown to black before paving. If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
REFERENCE DOCUMENTS: 407.19 AS2150 11
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: Spray area
WP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.3 - Commencement of Placing
FREQUENCY: Prior to commencing Paving
ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
REFERENCE DOCUMENTS: 407.23
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
HP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
Date Completed:
2.4 - Mix Design Confirmation
FREQUENCY: Each lot
ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
INSPECTION/TEST METHOD: Visual Inspection CHAR(AMP) Delivery Docket
RECORD OF CONFORMITY: Delivery docket Completed ITP
HP*
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.5 - Delivery of Mix
FREQUENCY: Each load
ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
REFERENCE DOCUMENTS: 407.11
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: Delivery Docket
WP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.6 - Traceability
FREQUENCY: Each lot
ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Daily Lot Record
IP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.7 - Layer Thickness and Level Control
FREQUENCY: Regularly during paving
ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
REFERENCE DOCUMENTS: IFC Drawings
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Dips using ruler or dip stick
WP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.8 - Paver Stoppages
FREQUENCY: If paver stops
ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
REFERENCE DOCUMENTS: 407.25 (c)
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Thermometer
WP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.9 - Surface Finish of Wearing Course
FREQUENCY: During paving and after final roll
ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
REFERENCE DOCUMENTS: 407.29 (a)(i)
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
WP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.1 - Kerb and Channel
FREQUENCY: During paving and after final roll
ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
REFERENCE DOCUMENTS: 407.29 (a)(ii)
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
WP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.11 - Alignment of layers not placed against concrete edge
FREQUENCY: During paving and at completion of work
ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line. The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
REFERENCE DOCUMENTS: 407.29 (a)(iv) Drawings
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
2.12 - Width of layers not placed against concrete edge
FREQUENCY: During paving and at completion of work
ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm. The average width over any 300m shall not be less than the design or specified width
REFERENCE DOCUMENTS: 407.29 (a)(v)
INSPECTION/TEST METHOD: Visual Inspection
RECORD OF CONFORMITY: ITP Signed
IP
RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
Date Completed:
3.1 - Compaction
FREQUENCY: Per Lot
ACCEPTANCE CRITERIA: For layers CHAR(LESS)50mm, if characteristic density ratio is: 94.0% or greater Accept lot 91.0% to 93.9% Lot may be accepted at reduced rate
REFERENCE DOCUMENTS: Table 407.271
INSPECTION/TEST METHOD: Verify
RECORD OF CONFORMITY: Test Report
TP
RESPONSIBILITY: Site Engineer/ Lab Technician
Date Completed:
3.2 - Level Conformance
FREQUENCY: Per 4,000m2 at completion of work
ACCEPTANCE CRITERIA: Scale B Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm Minimum number of measurements per lot is 40 (ii) Kerb and Channel Refer to Item 2.10 of this ITP
REFERENCE DOCUMENTS: Table 407.293 Table 407.292
INSPECTION/TEST METHOD: Survey by VicRoads Section 173
RECORD OF CONFORMITY: Survey Conformance
SCP
RESPONSIBILITY: Site Engineer/ Surveyor
Date Completed: