## ITP Cover Page
[16 empty] | Pavement & Surfacing Inspection and Test Plan | [7 empty] | Subordinate Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
SECTION 1 – GENERAL DETAILS
Project Name: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | ITP Number: |  |  | 1 | [5 empty] | Subordinate ITP Cover page UPDATE
Project Number: |  |  | DS1205 |  |  |  |  | ITP Status: |  |  | Draft For Approval
ITP Description: |  |  | Pavement & Surfacing ITP |  |  |  |  | Revision: | 1000 |  | A
Contract Number: |  |  | Peacocke Whatukooruru Drive |  |  |  |  | Drawing Sets: |  |  | 146000-002A
Customer: |  |  | Hamilton City Council |  |  |  |  | Specification: |  |  | Project Specification and Appendices.
Quality Specified: |  |  | NZTA Z/1
Review / Update History | [9 empty] | Verification Activity | [6 empty] | Subordinate Inspection and Test Plan Details
Rev: | Status: | Date: |  | Reviewed By: |  | Revision Details: |  |  |  | Activity Key |  |  | Responsibilities Key |  |  |  | Construction Pack Number: |  |  | CP##
A | Draft for Approval | 2022-12-22 |  | Gabriel Cirne |  | First Revieion for Review and Approval |  |  |  | A | Action |  | ENG | Engineer / Engineer's Rep |  |  | Work Area / Chainage / Lot: | [5 empty] | SUB ITP NO. S-
[10 empty] | B | Report by Breach |  | CR | Customer Rep
[10 empty] | C | Check |  | PD | Project Director
[10 empty] | D | Dimension Inspection |  | PM | Project Manager |  |  | Master ITP Details:
[10 empty] | E | Examine |  | OP | Operations Manager |  |  | Review / Update History
[10 empty] | HP | Hold Point (Engineer) |  | HSE | HSE Manager / Rep |  |  | Rev: | Status: | Date: |  | Reviewed By: | Revision Details:
[10 empty] | H | Hold Point (Internal) |  | QM | QA Manager / Rep |  |  | A |  |  |  |  | Subordinate ITP Creation for
[10 empty] | I | Inspection |  | PE | Project Engineer
[10 empty] | M | Monitor on Random Basis |  | SE | Site Engineer
[10 empty] | O | Operation |  | QE | Quality Engineer
[10 empty] | R | Review |  | SUP | Superintendent / Supervisor |  |  | SUB ITP Instructions: 0. Master ITP to be Approved and Accepted 1. Extract Cover page (this page) and Body page to new Workbook 2. Drag and drop the two white cell blocs above into the cover page 3. Assign an ITP Number in Mater ITP Register tab 4. Populate Title Page Details 5. Remove all Inspection points in the Body which do not relate to works 6. Review for approval, submitting to Client / Engineer once internally approved
[10 empty] | S | Subcontractor |  | SV | Surveyor
[10 empty] | V | Visual Verification |  | ITP | Third Party Inspector
[10 empty] | W | Witness Point |  | SPEC | Specialist
SECTION 2A – Master ITP Approval | [7 empty] | SECTION 2B – ITP CLOSEOUT
Position |  | Name: |  |  | Signature: |  | Date: | Position |  | Name: |  | Signature: |  |  | Date:
Downer PM | [7 empty] | Downer PM
Downer QM | [7 empty] | Downer QM
Client (If Applicable) | [7 empty] | Client (If Applicable)

## ITP Master Body
Pavement & Surfacing Inspection and Test Plan
Project: Peacocke Whatukooruru Drive
Number and Revision: DS1205 - 1 - Rev A
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
16.08 | Chipsealing
16.08.01 | Sealing Chip - Source Property Tests and Sampling | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV | TNZ M/6: 2019 - 4 PS - 7.2.8 | IANZ Lab Reports | 10,000m3 | HP | ENG
16.08.02 | Sealing Chip - Production Property Test Sampling | The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6 | TNZ M/6: 2019 - 5 PS - 7.2.8 | IANZ Lab Reports | 500m3 | HP | ENG
16.08.03 | Bitumen | The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification. | NZTA M10:2020 - 2.3.1 NZTA M01-A PS - 7.2.8 | IANZ Lab Reports | Prior to use | H | PE
16.08.04 | Sprayer E-2 certification | E-2 certification and is up to date | BCA E/2 Specification | Certificate | Prior to use | C | PE
16.08.05 | Sealing Design | Chip seal type, chip source, bitumen and/or emulsion grade, % kerosene, AGO and diluents, polymer (if applicable), sand report reports, hot application rate(s) including spray rates | PS 7.3.4. | Design Document | Prior to use | HP | ENG
16.08.06 | Bitumen approval | Applications for approval shall contain the information required by NZTA Q05 clause 4 and the testing information required by Table 5.1 | table 5.1 of NZTA M1:2022 | Report | Prior to use | C | PE
16.08.07 | Bitumen Quality | All bitumens used for road pavements construction, supplied or blended by New Zealand-based bitumen blending facilities shall meet all the requirements of Table 6.1 or M01-A specification for the grade supplied. | table 6.1 of NZTA M1:2022 | Report | at least one test per grade supplied following delivery of a shipment into a bulk blending facility. | C | PE
SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
28.01 | Chipsealing
28.07.01 | Sealing Procedure | Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, and Q/1. | M/1, M/6, M/13, P/3, and Q/1. | Methodology / Construction Pack | Prior to sealing | H | PE
28.07.02 | Sealing Inspection | Before sealing and resealing. A pre-seal walkover with the Engineer to ensure that the surface is swept clean of loose aggregate, dust, dirt and other deleterious matter and the sweepings shall be removed to the satisfaction of the Engineer. | PS - 2.2.16 | Hold Point Release | Min 48h Notice | HP | ENG
28.07.03 | Presealing Requirements | Further to Clause 12 of NZTA B2, the degree of saturation of the basecourse prior to sealing shall be less than 60%. | PS - 7.3.4 | NDM Report | Min 5 Tests per lot 1000m2 max lot size | HP | ENG
28.07.04 | Adhesion Agents | An adhesion agent approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents shall be incorporated in the sealing binder. | TNZ M13 | Site Notes | Prior to sealing | R | SE
28.07.05 | Post Seal Inspections | The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed. | TNZ P3 | Engineers Acceptance | Prior to TM removal and after final sweeping | HP | ENG
28.07.06 | Bedding in Chip | If no traffic on site to bed in Chipseal, 3 days of constant rolling with PTR's and laden HCV's will be applied to bed in the Chipseal. | PS - 7.3.4 | Site Notes | Post Sealing | R | SE
28.07.07 | Surplus Chip Removal | If no traffic on site, removal of surplus chip will occur 2-3 days after rolling has been completed. If traffic on site, sweeping and removal of chip will be within 48hrs. | TNZ P3 | Site notes | 24 hours of completion of any section of seal. | R | SE
28.07.08 | Chipseal Repairs | The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used | TNZ P3 | Approved repair Methodology | Prior to repairs | HP | ENG
28.07.09 | Weather | Ensure that weather is suitable prior to spraying & pavement temperature checked. Pavement surface temperature ≥ 10C. | Requested by BBO | Site Notes | Prior to sealing | C | PE
28.07.10 | Protect Road Furniture | Paper cover any concrete that could get sprayed by bitumen such as kerbs and barriers | NZTA (2005) Chip sealing in New Zealand – 11.2.5. | Site Notes | Prior to sealing | C | PE
28.07.11 | Joins, Overlaps & Hand Spraying | Set up Spray Plan ensuring joins, overlaps and hand spraying is kept to a minimum; joins are not in wheel paths and overlaps are appropriate for curves, channels, straights | NZTA (2005) Chip sealing in New Zealand – Section 11 | Site Notes | Prior to sealing | C | PE
28.07.12 | Binder Temperature | Temp. appropriate to base binder and additives +/- 10 degrees. Daily records | NZTA (2005) Chip sealing in New Zealand – Section 11 | Site Notes | Prior to sealing | C | PE
28.07.13 | Binder Application Rates | Confirm spray rate is correct by comparing actual spray rate to that calculated. Note error in measurement increases as area reduces. Within 0.1l/m² from target on spray run. | Requested by BBO | Site Notes | Daily | C | PE
28.07.14 | Chip Application Rate | Monitor chip spread rate and compared to target, record volume of chip used | NZTA (2005) Chip sealing in New Zealand – Section 11.3.7 | Site Notes | Daily | C | PE