## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Pavement & Surfacing - Sealing - Rev 1 | itp |  |  |  | Yes | ITP - Pavement & Surfacing - Sealing - Rev 1
section | SECTION 16 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL - PAVEMENT AND SURFACING
checkpoint | 16.08.01 - Sealing Chip - Source Property Tests and Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
label | Standard / Specification - TNZ M/6: 2019 - 4, PS - 7.2.8
label | Verifying Document - IANZ Lab Reports
label | Frequency - 10,000m3
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.08.02 - Sealing Chip - Production Property Test Sampling
label | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
label | Standard / Specification - TNZ M/6: 2019 - 5, PS - 7.2.8
label | Verifying Document - IANZ Lab Reports
label | Frequency - 500m3
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.08.03 - Bitumen
label | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
label | Standard / Specification - NZTA M10:2020 - 2.3.1, NZTA M01-A, PS - 7.2.8
label | Verifying Document - IANZ Lab Reports
label | Frequency - Prior to use
label | Activity - H
label | By - PE
checkpoint | 16.08.04 - Sprayer E-2 certification
label | Acceptance / Conformance Criteria - E-2 certification and is up to date
label | Standard / Specification - BCA E/2 Specification
label | Verifying Document - Certificate
label | Frequency - Prior to use
label | Activity - C
label | By - PE
checkpoint | 16.08.05 - Sealing Design
label | Acceptance / Conformance Criteria - Chip seal type, chip source, bitumen and/or emulsion grade, % kerosene, AGO and diluents, polymer (if applicable), sand report reports, hot application rate(s) including spray rates
label | Standard / Specification - PS 7.3.4.
label | Verifying Document - Design Document
label | Frequency - Prior to use
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16.08.06 - Bitumen approval
label | Acceptance / Conformance Criteria - Applications for approval shall contain the information required by NZTA Q05 clause 4 and the testing information required by Table 5.1
label | Standard / Specification - table 5.1 of NZTA M1:2022
label | Verifying Document - Report
label | Frequency - Prior to use
label | Activity - C
label | By - PE
checkpoint | 16.08.07 - Bitumen Quality
label | Acceptance / Conformance Criteria - All bitumens used for road pavements construction, supplied or blended by New Zealand-based bitumen blending facilities shall meet all the requirements of Table 6.1 or M01-A specification for the grade supplied.
label | Standard / Specification - table 6.1 of NZTA M1:2022
label | Verifying Document - Report
label | Frequency - at least one test per grade supplied following delivery of a shipment into a bulk blending facility.
label | Activity - C
label | By - PE
section | SECTION 28 – CONSTRUCTION ACTIVITY – PAVEMENT AND SURFACING
checkpoint | 28.07.01 - Sealing Procedure
label | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, and Q/1.
label | Standard / Specification - M/1, M/6, M/13, P/3, and Q/1.
label | Verifying Document - Methodology / Construction Pack
label | Frequency - Prior to sealing
label | Activity - H
label | By - PE
checkpoint | 28.07.02 - Sealing Inspection
label | Acceptance / Conformance Criteria - Before sealing and resealing. A pre-seal walkover with the Engineer to ensure that the surface is swept clean of loose aggregate, dust, dirt and other deleterious matter and the sweepings shall be removed to the satisfaction of the Engineer.
label | Standard / Specification - PS - 2.2.16
label | Verifying Document - Hold Point Release
label | Frequency - Min 48h Notice
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 28.07.03 - Presealing Requirements
label | Acceptance / Conformance Criteria - Further to Clause 12 of NZTA B2, the degree of saturation of the basecourse prior to sealing shall be less than 60%.
label | Standard / Specification - PS - 7.3.4
label | Verifying Document - NDM Report
label | Frequency - Min 5 Tests per lot 1000m2 max lot size
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 28.07.04 - Adhesion Agents
label | Acceptance / Conformance Criteria - An adhesion agent approved and blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents shall be incorporated in the sealing binder.
label | Standard / Specification - TNZ M13
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - R
label | By - SE
checkpoint | 28.07.05 - Post Seal Inspections
label | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
label | Standard / Specification - TNZ P3
label | Verifying Document - Engineers Acceptance
label | Frequency - Prior to TM removal and after final sweeping
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 28.07.06 - Bedding in Chip
label | Acceptance / Conformance Criteria - If no traffic on site to bed in Chipseal, 3 days of constant rolling with PTR's and laden HCV's will be applied to bed in the Chipseal.
label | Standard / Specification - PS - 7.3.4
label | Verifying Document - Site Notes
label | Frequency - Post Sealing
label | Activity - R
label | By - SE
checkpoint | 28.07.07 - Surplus Chip Removal
label | Acceptance / Conformance Criteria - If no traffic on site, removal of surplus chip will occur 2-3 days after rolling has been completed. If traffic on site, sweeping and removal of chip will be within 48hrs.
label | Standard / Specification - TNZ P3
label | Verifying Document - Site notes
label | Frequency - 24 hours of completion of any section of seal.
label | Activity - R
label | By - SE
checkpoint | 28.07.08 - Chipseal Repairs
label | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used
label | Standard / Specification - TNZ P3
label | Verifying Document - Approved repair Methodology
label | Frequency - Prior to repairs
label | Activity - HP
label | By - ENG
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 28.07.09 - Weather
label | Acceptance / Conformance Criteria - Ensure that weather is suitable prior to spraying & pavement temperature checked. Pavement surface temperature ≥ 10C.
label | Standard / Specification - Requested by BBO
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - C
label | By - PE
checkpoint | 28.07.10 - Protect Road Furniture
label | Acceptance / Conformance Criteria - Paper cover any concrete that could get sprayed by bitumen such as kerbs and barriers
label | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – 11.2.5.
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - C
label | By - PE
checkpoint | 28.07.11 - Joins, Overlaps & Hand Spraying
label | Acceptance / Conformance Criteria - Set up Spray Plan ensuring joins, overlaps and hand spraying is kept to a minimum; joins are not in wheel paths and overlaps are appropriate for curves, channels, straights
label | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - C
label | By - PE
checkpoint | 28.07.12 - Binder Temperature
label | Acceptance / Conformance Criteria - Temp. appropriate to base binder and additives +/- 10 degrees. Daily records
label | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11
label | Verifying Document - Site Notes
label | Frequency - Prior to sealing
label | Activity - C
label | By - PE
checkpoint | 28.07.13 - Binder Application Rates
label | Acceptance / Conformance Criteria - Confirm spray rate is correct by comparing actual spray rate to that calculated. Note error in measurement increases as area reduces. Within 0.1l/m² from target on spray run.
label | Standard / Specification - Requested by BBO
label | Verifying Document - Site Notes
label | Frequency - Daily
label | Activity - C
label | By - PE
checkpoint | 28.07.14 - Chip Application Rate
label | Acceptance / Conformance Criteria - Monitor chip spread rate and compared to target, record volume of chip used
label | Standard / Specification - NZTA (2005) Chip sealing in New Zealand – Section 11.3.7
label | Verifying Document - Site Notes
label | Frequency - Daily
label | Activity - C
label | By - PE