## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Floor framing QA |  |  |  |  | Yes | Floor framing QA | 06899bb2-dd42-4ffe-95b9-8fb228e6bca5
checkpoint-status |  |  | checkpoint | Installer details entered
text | 32701f12-ad0e-515a-a30f-64c50103795b |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Drawings and revisions checked
checkpoint-status |  |  | checkpoint | Jack stud wall installed at correct locations
checkpoint-status |  |  | checkpoint | Joists installed at correct centres
checkpoint-status |  |  | checkpoint | All fixings installed brackets joisthangers ect
checkpoint-status |  |  | checkpoint | Fixing and hold down bolts checked and correct
checkpoint-status |  |  | checkpoint | All relevant nogs installed
checkpoint-status |  |  | checkpoint | All floor framing checks completed.
checkpoint-status |  |  | checkpoint | Report sent to client
checklist-flat |  |  | checklist | QA - Villaboard |  |  |  |  | Yes | QA - Villaboard | 1ba2f0f5-e798-4fa9-ba56-796eea193846
checkpoint-status |  |  | checkpoint | Installer details entered
text | 9368037b-e381-5fda-a699-d6a51699d12e |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 9368037b-e381-5fda-a699-d6a51699d12e |  | button | Is this task Green Star related? | Yes, No, N/A
button | bff025fb-50f0-5878-877b-0894fb532df6 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Framing set out (i.e. stud and nog spacing) correct
checkpoint-status |  |  | checkpoint | Framing set out (i.e. stud and nog spacing) correct
checkpoint-status |  |  | checkpoint | GIB Lining base are secure and flush with each other with no protruding fixings
checkpoint-status |  |  | checkpoint | Gap between Villaboard edges/joints are at 1-2mm maximum
checkpoint-status |  |  | checkpoint | Villaboard must be installed dry
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres (i.e. perimeter and intermediate)
checkpoint-status |  |  | checkpoint | Villaboard report sent through to client
checklist-flat |  |  | checklist | QA - Gib Weatherline |  |  |  |  | Yes | QA - Gib Weatherline | 33f6b1a0-b748-463c-98cd-3ca4b8a58548
checkpoint-status |  |  | checkpoint | Installer details entered
text | 383244cc-1a3f-526e-b648-fe1926a69c62 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Framing set out adequate to support all sheet edges. Stud and nog spacing complies with GIB Weatherline® technical literature i.e. studs must be at a maximum of 400mm or GIB Weatherline® technical literature i.e. studs must be at a maximum of 400mm or
checkpoint-status |  |  | checkpoint | Framing straightness. Nogs flush with studs, studs flush with top/bottom plates and no protruding fixings.
checkpoint-status |  |  | checkpoint | Prior to installation GIB Weatherline® sheets to be kept dry
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres according to GIB Weatherline® technical literature
checkpoint-status |  |  | checkpoint | Sheets overhang the bottom plate on a concrete slab by a minimum of 15mm as per GIB Weatherline® technical literature.
checkpoint-status |  |  | checkpoint | GIB Weatherline® Tape installed to vertical/ horizontal sheet joints, corners, and openings in accordance with GIB Weatherline® technical literature.
checkpoint-status |  |  | checkpoint | Building service penetrations through GIB Weatherline® sheets sealed using Proclima Kaflex or Roflex penetration seal grommets. Proclima installation instructions to be followed.
checkpoint-status |  |  | checkpoint | GIB Weatherline® flashing and sill tapes to be applied on doors and windows as per GIB Weatherline® technical literature.
checkpoint-status |  |  | checkpoint | GIB Weatherline® report sent to client
checklist-sectioned |  |  | checklist | Concrete Pour for Area: |  |  |  |  | Yes | QA - Concrete Pour Checklist | 419e8bae-21c1-432f-9d26-e99640a15aab
checkpoint-group |  |  | section | Installer Details
checkpoint-status |  |  | checkpoint | Installer details entered
text | 36b3295f-e75e-5ee3-b91c-8692e8a2518c |  | textbox | Installer:
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Pour details entered
text | 36b3295f-e75e-5ee3-b91c-8692e8a2518c |  | textbox | Area to be poured (grid lines, location):
text | f16f34bd-89b5-5f95-8970-b4c7948d5c36 |  | textbox | Drawing numbers and revisions
text | 565f2e10-92ba-5173-99cb-71b239990942 |  | textbox | Date of pour
checkpoint-group |  |  | section | Formwork and embedded items
checkpoint-status |  |  | checkpoint | Grids and RLs clearly marked for reference
checkpoint-status |  |  | checkpoint | Formwork - location, heights, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status |  |  | checkpoint | Any rebates / nibs / cast in items are correctly positioned, sized and appropriately fixed in place.
boolean | c0bbf24f-5680-5ef4-86d0-3f2a4bb01b4a |  | tickbox | Hold down bolts checked and correct
boolean | 3b9d31a0-c3fc-5651-b1f4-738491d6283b |  | tickbox | Precast panel starters checked and correct
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork, etc.)
checkpoint-status |  |  | checkpoint | Any control joints / stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | DPM & Connection to other waterproofing completed
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour (excess debris removed)
checkpoint-status |  |  | checkpoint | Concrete ordered - correct mix and strength
text | 0de7805a-38f5-565f-8e4d-b2e6444d9a44 |  | textbox | Mix
text | 87364c26-d0d9-52e1-91c0-7d7847368205 |  | textbox | Strength:
text | cae5e41d-784f-582d-b531-84898e30685a |  | textbox | Summary of Proposed cement mix date and revision checked:
text | 69fb15e8-d642-55e1-b91c-cfb7259d38cf |  | textbox | Structrual services specifications number and revision checked:
checkpoint-status |  |  | checkpoint | Slump test/Spread test (only applicable for special mix)
holdpoint |  |  | signoff | Request Signoff
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
text | 797542dc-3535-56c0-97fa-8f591b0eb16c |  | textbox | Who is placing the concrete
checkpoint-status |  |  | checkpoint | Height and falls checked / confirmed before placement
checkpoint-status |  |  | checkpoint | Cover correct to specification
checkpoint-status |  |  | checkpoint | All concrete checked and correct on arrival (mix and strength)
boolean | dae82be4-9787-5504-85ac-55934e9741ef |  | tickbox | All concrete dockets attached
checkpoint-status |  |  | checkpoint | General photos and observations of concrete placement attached
checkpoint-status |  |  | checkpoint | Heights and falls checked / confirmed after placement
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
checkpoint-status |  |  | checkpoint | Area left clean and tidy
checkpoint-group |  |  | section | Post Pour Checks / Signoff
checkpoint-status |  |  | checkpoint | Any remedial work completed
checkpoint-status |  |  | checkpoint | Concrete Pour completed - all final checks and documentation completed and attached
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - Internal Timber Framing |  |  |  |  | Yes | QA - Internal Timber Framing | 466a8396-0c4b-4950-8e46-3543d78e0667
checkpoint-status |  |  | checkpoint | Installer details entered
text | deab10f4-14c6-519d-a7f7-2907e6fb8075 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | deab10f4-14c6-519d-a7f7-2907e6fb8075 |  | button | Is this task Green Star related? | Yes, No, N/A
button | f8249f54-3ac1-55de-9dc4-aa3bd384ec2e |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
text | 7ef3f72f-87b3-5411-bc8e-18dbc3799501 |  | textbox | Drawing no. and revision
checkpoint-status |  |  | checkpoint | DPC installed, checked and correct as per specification
checkpoint-status |  |  | checkpoint | Wall locations checked, correct and approved as per latest revised drawing
checkpoint-status |  |  | checkpoint | Fixings and hold down bolts checked and correct
checkpoint-status |  |  | checkpoint | All openings (doors / windows etc) checked, correct and approved
boolean | 420dd657-4847-554d-8f7d-88eeb1384389 |  | tickbox | Deflection heads type installed and correct
checkpoint-status |  |  | checkpoint | Wall type checked (straight and plumb) and within tolerance
checkpoint-status |  |  | checkpoint | All relevant nogs (service and special/fixtures) installed, checked and correct
boolean | c0cd9a0c-3391-56c2-9d6f-6898303201e0 |  | tickbox | All other nogs checked and approved
checkpoint-status |  |  | checkpoint | Moisture reading checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | All wall framing checks completed & Inspections carried out
boolean | c3e31429-df65-5906-8ae3-92404343432e |  | tickbox | Relevant inspections completed and attached
checkpoint-status |  |  | checkpoint | Timber framing report sent through to client
holdpoint |  |  | signoff | Request Signoff
checklist-flat |  |  | checklist | Concrete Testing for: |  |  |  |  | Yes | Add - Concrete Testing Results Checklist (V2) | 49280a55-d0b1-499a-9fe9-89525a7efd85
checkpoint-status |  |  | checkpoint | Installer details entered
text | c9959219-cb0e-5bb1-87df-f8c0e4be49b4 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Concrete testing results attached, checked and acceptable
select | c9959219-cb0e-5bb1-87df-f8c0e4be49b4 |  | dropdown | Test Results | 7days, 14days, 28 days, Other (Specify below)
text | ff2a2967-7ded-5fe9-900f-0dca3470fa1d |  | textbox | Test Results Number / Docket Number
text | b021d8db-60b0-5450-a314-e4f80e8f5708 |  | textbox | Date Concrete was poured
text | 824b8e20-68bf-5627-9b8f-83cce2b75d68 |  | textbox | Area Concrete was poured
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - HPL Panel |  |  |  |  | Yes | QA - HPL Panel | 558613d4-ebf4-42e0-9a0a-1fc7280b5e4b
checkpoint-status |  |  | checkpoint | Installer details entered
text | f69976c9-e9bd-5822-8905-c6d2dc04a8b9 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked
checkpoint-status |  |  | checkpoint | Manufacturer’s defects discovered and disclosed before installation
checkpoint-status |  |  | checkpoint | SikaTack Panel Tape and Sikaflex-11 FC applied to panels as adhesive
checkpoint-status |  |  | checkpoint | Set-out height is correct
checkpoint-status |  |  | checkpoint | Gaps between panels and sides are correct.
checkpoint-status |  |  | checkpoint | All vertical side gaps are sealed except for horizontal gaps.
checkpoint-status |  |  | checkpoint | Each panel has been installed straight, flush, levelled and plumb.
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - Perimeter Seat |  |  |  |  | Yes | QA - Perimeter Seat | 57b2feb4-8e6d-4be3-b524-80127411fed1
checkpoint-status |  |  | checkpoint | Installer details entered
text | 3be19864-88e3-5b45-beda-951d60cb54c1 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked
checkpoint-status |  |  | checkpoint | Timber seat manufacturer’s defects discovered and disclosed before installation
checkpoint-status |  |  | checkpoint | Set-out height is correct
checkpoint-status |  |  | checkpoint | Seat constructed straight and levelled
checkpoint-status |  |  | checkpoint | General photos and observations after completion
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - Reinforcing Checklist |  |  |  |  | Yes | QA - Reinforcing Checklist | 5c46de37-8cde-4aa3-be0a-979469267139
checkpoint-status |  |  | checkpoint | Installer details entered
text | 7682a287-55e0-5893-a148-c601c20b32ae |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Work area ready
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-status |  |  | checkpoint | Correct product delivered, reviewed & approved
checkpoint-status |  |  | checkpoint | Correct size & type installed as per design
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Laps correct per size of bar
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size and spacing)
checkpoint-status |  |  | checkpoint | All bars fixed appropriately
checkpoint-status |  |  | checkpoint | Couplers installed at correct height
checkpoint-status |  |  | checkpoint | Cast in plates installed correctly
checkpoint-status |  |  | checkpoint | Any additional items considered, installed & completed e.g. trimmer bars, reid bar couplers, foot plates, drag bars
checkpoint-status |  |  | checkpoint | All excess reinforcing and debris removed - clean & tidy
checkpoint-status |  |  | checkpoint | Reinforcing install completed, send to client
checklist-flat |  |  | checklist | Area: |  |  |  |  | Yes | QA - Drill and Epoxy Reinforcement | 6116712c-66f0-4a95-a9f8-5d72691c3541
checkpoint-status |  |  | checkpoint | Installer details entered
text | 4d68ed07-aaae-56b1-8dae-1f29d1b91a48 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 4d68ed07-aaae-56b1-8dae-1f29d1b91a48 |  | button | Is this task Green Star related? | Yes, No, N/A
button | aa1f3c36-af31-5529-bf68-ab125324fbcc |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Scabbling done to an acceptable level
checkpoint-status |  |  | checkpoint | Drill and Epoxy info entered
text | dbf2a1f1-001f-57ab-b0e8-362f57e44f33 |  | textbox | Type:
text | 3d35bf81-f3ed-5c3e-88e3-ab30af3ae23d |  | textbox | Grid:
text | 3d25ccea-c2b0-59c3-acf3-d71088c2af05 |  | textbox | Level:
text | 78231347-85a1-5a8e-9134-9b12bacfb52c |  | textbox | Epoxy:
text | 54e8275d-545e-5577-b312-fee32ac4bf87 |  | textbox | Date of Inspection:
text | f8b19462-ce88-5e71-9a96-432baddf8a91 |  | textbox | Drawing references:
checkpoint-status |  |  | checkpoint | Drill info
button | 9838fdfb-4db1-5663-be69-118ed1207237 |  | button | Type of Drill Bit | Normal, Hollow
text | 774e94b5-f0ef-5acf-a316-f443ba490a99 |  | textbox | Drill Bit Size (mm):
checkpoint-status |  |  | checkpoint | Hole info
text | 9b34c643-de38-5604-abfe-d037e04cb4a2 |  | textbox | Depth of Hole (mm):
button | bfd0c45e-6056-543f-817c-c0ca7788dc60 |  | button | Cleaning of Hole | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Epoxy Application info
text | 87bcd7a4-ac61-5b23-8987-4e03d31934dc |  | textbox | Type of Epoxy:
button | c9997b2c-311c-5bb5-937e-c8e2ef3f0298 |  | button | Applied with Hilti Dispenser | Electric, Manual
text | 2fc132aa-c1a6-51e7-a01a-dcbb94a82d14 |  | textbox | Weather Conditions:
text | 26dca285-d55f-5950-a783-4dcccb978a1e |  | textbox | Temp:
text | ab3b2873-e7ac-5871-aec2-24e94997e748 |  | textbox | Epoxy depth:
text | 64ecb8f3-b228-56a9-b853-277faa7d8a63 |  | textbox | Size of rebar (mm):
text | 89d36162-69d4-5d6b-9f4b-c6f2dea51cc2 |  | textbox | Curing time:
text | 1e6b8967-6ea2-5091-9d2f-d31cb0167630 |  | textbox | Testing required:
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - Insulation |  |  |  |  | Yes | QA - Insulation | 6f61ea34-d0c5-4887-adaa-21a75682ce4c
checkpoint-status |  |  | checkpoint | Installer details entered
text | 8a62fd43-93cd-5b0d-828e-dc91b74931a2 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 8a62fd43-93cd-5b0d-828e-dc91b74931a2 |  | button | Is this task Green Star related? | Yes, No, N/A
button | 03bd0f36-29bb-5246-875c-aa8d02d2ca44 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
text | e719c48a-f3ba-5ea0-b96f-68bc7f2f5c9b |  | textbox | Area prepared and ready for Insulation install
checkpoint-status |  |  | checkpoint | Product checked on arrival and correct as per specification
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Ensure work is completed as per specification
boolean | bb796678-fd8a-5219-b4be-80a6a9a972a9 |  | tickbox | Insulation pre lining works completed, checked and approved
checkpoint-status |  |  | checkpoint | Insulation report sent through to client
checklist-flat |  |  | checklist | Site Concrete area: |  |  |  |  | Yes | QA - Site Concrete Checklist (V2) | 7b655bac-e299-4673-a5d1-ffc4437e9218
checkpoint-status |  |  | checkpoint | Installer details entered
text | 76abd69c-0249-56f8-a01f-2221e7fe8ab0 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 76abd69c-0249-56f8-a01f-2221e7fe8ab0 |  | button | Is this task Green Star related? | Yes, No, N/A
button | e1f3fec0-5439-5896-9c0d-e7aaa65a61ac |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Excavation depth and location checked and correct
checkpoint-status |  |  | checkpoint | Ground conditions acceptable
checkpoint-status |  |  | checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint-status |  |  | checkpoint | Concrete placed to the correct height
checkpoint-status |  |  | checkpoint | Site concrete pour completed and finish acceptable
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - Wall Finishes |  |  |  |  | Yes | QA - Wall Finishes | 7b8468f9-d600-4420-8e33-cb7019eadac7
checkpoint-status |  |  | checkpoint | Installer details entered
text | 550275e0-3aa0-51bc-bb52-2c30bef64363 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Item installed by-
checkpoint-status |  |  | checkpoint | Item has sufficient fixings
checkpoint-status |  |  | checkpoint | Item is installed plumb and level
checkpoint-status |  |  | checkpoint | Item is installed damage free and defect free
checkpoint-status |  |  | checkpoint | Report sent to Contractor
checklist-flat |  |  | checklist | Speedwall |  |  |  |  | Yes | QA - Speedwall | 80820e6b-457f-4cbe-be93-ae0c8afd910b
checkpoint-status |  |  | checkpoint | Installer details entered
text | 2b197128-dfb4-5101-855e-259a5ffb7b59 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 2b197128-dfb4-5101-855e-259a5ffb7b59 |  | button | Is this task Green Star related? | Yes, No, N/A
button | e0192416-ef66-52ad-b10e-1b7b41e52c48 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for Speedwall install
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Bottom track correctly installed (size, location and fixings)
checkpoint-status |  |  | checkpoint | Top track correctly installed (size, location and fixings)
checkpoint-status |  |  | checkpoint | 20mm minimum gap at head
checkpoint-status |  |  | checkpoint | Install C track Fixings @ 400crs with M6.5 x 32 Mushroom head spikes into concrete
checkpoint-status |  |  | checkpoint | Fixings Hilti X-ENP-19 L15MX fixings 400crs in into steel
checkpoint-status |  |  | checkpoint | 10 x 16 fixings on C-Track to (horizontal panel - vertical C-Track 250crs, horizontal C-Track 400crs) (vertical panel - vertical C-Track 400crs, horizontal C-Track 250crs)
checkpoint-status |  |  | checkpoint | Fire sealant installed correctly and photographed
checkpoint-status |  |  | checkpoint | All joints sealed correctly as per specification
checkpoint-status |  |  | checkpoint | Speedwall installed straight and level
checkpoint-status |  |  | checkpoint | Openings installed for services as per drawings
checklist-flat |  |  | checklist | QA - External Timber Framing |  |  |  |  | Yes | QA - External Timber Framing | 87f62e00-c26f-4050-89a3-4dcf2cd392d6
checkpoint-status |  |  | checkpoint | Installer details entered
text | 9b6afea3-b763-5f0c-b15b-aae2d754ea20 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 9b6afea3-b763-5f0c-b15b-aae2d754ea20 |  | button | Is this task Green Star related? | Yes, No, N/A
button | a3817c6f-4d19-5da4-aedb-9fa0e9d0a6f2 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | External wall timber framing is treated to min H1.2 treatment levels. Specify if any other treatment to be used.
checkpoint-status |  |  | checkpoint | Dimensions / locations of walls checked and correct
checkpoint-status |  |  | checkpoint | DPM installed where required
checkpoint-status |  |  | checkpoint | Timber framing set out. i.e. Stud spacing and nog spacing.
checkpoint-status |  |  | checkpoint | Framing straightness. Nogs flush with studs, and studs flush with top and bottom plates.
checkpoint-status |  |  | checkpoint | Fixings and hold down bolts checked and correct
checkpoint-status |  |  | checkpoint | Moisture reading checked, recorded and acceptable
checkpoint-status |  |  | checkpoint | All relevant nog (service and Special/fixture) installed, checked and correct
checkpoint-status |  |  | checkpoint | DHT installed checked and correct seismic gap
checkpoint-status |  |  | checkpoint | All openings are in correct location and correct size
checkpoint-status |  |  | checkpoint | All frames are square & plumb
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | CLT Checklist |  |  |  |  | Yes | CLT Checklist | 89d8cf03-a889-4d62-9bf1-5a4b51709a4b
checkpoint-status |  |  | checkpoint | Installer details entered
text | 1671ba10-a6b7-5ac9-888f-3f075a4f5d76 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Inspect the panels on receipt at the delivery site &amp; approved (photograph any damage)
checkpoint-status |  |  | checkpoint | Timber stud walls installed correctly with correct fixings/hardware and plywood installed at correct centres.
checkpoint-status |  |  | checkpoint | Blocking connections installed correctly with correct fixings/hardware
checkpoint-status |  |  | checkpoint | Panels installed level and with correct overhang.
checkpoint-status |  |  | checkpoint | Panels installed at correct centres with correct fixing.
checkpoint-status |  |  | checkpoint | Fyreline installed correctly to underside of panels with correct fixing centres.
checkpoint-status |  |  | checkpoint | Fireseal installed to all sheet exposed edges.
checkpoint-status |  |  | checkpoint | Area complete and all housekeeping undertaken.
checkpoint-status |  |  | checkpoint | General photos of area.
checkpoint-status |  |  | checkpoint | Report sent to client.
checklist-flat |  |  | checklist | QA - Ecoply |  |  |  |  | Yes | QA - Ecoply | 8d7376c6-e158-4fe4-abfd-6fd810875c76
checkpoint-status |  |  | checkpoint | Installer details entered
text | 58ae5d90-d2d4-50da-a51c-9dddb97136c3 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 58ae5d90-d2d4-50da-a51c-9dddb97136c3 |  | button | Is this task Green Star related? | Yes, No, N/A
button | 36504390-e45f-5ee0-b85f-701e53658b69 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Ecoply pre cladding/RAB board to be kept dry and under cover
checkpoint-status |  |  | checkpoint | Ecoply Pre-cladding/RAB board installed in accordance with Ecoply barrier installation manual
checkpoint-status |  |  | checkpoint | Tape installed over Ecoply pre-cladding/RaB board vertical joints, corners and openings in accordance with Ecoply Barrier installation manual
checkpoint-status |  |  | checkpoint | uPVC horizontal flashing used at all horizontal joints
checkpoint-status |  |  | checkpoint | Fixings: Type - Stainless Steel/Galv correct spacing
checkpoint-status |  |  | checkpoint | The panels overhang the bottom plate on a concrete slab by a maximum of 40mm as per installation manual
checkpoint-status |  |  | checkpoint | Penetrations through Ecoply pre-cladding/Rab board sealed properly using flexible flashing tape as per E2/AS1
checkpoint-status |  |  | checkpoint | Ecoply report sent to client
checklist-flat |  |  | checklist | Wrapshield Checklist |  |  |  |  | Yes | Wrapshield Checklist | a1cd5d57-a5e7-4daf-9396-8125e6361944
checkpoint-status |  |  | checkpoint | Installer details entered
text | 8fd3f7c1-c4f2-5699-afe8-5ebb51380553 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Structure looks complete
checkpoint-status |  |  | checkpoint | Structure as detailed
checkpoint-status |  |  | checkpoint | Information / details clearly shows waterproofing application requirements
checkpoint-status |  |  | checkpoint | Structure dry and clean for application of Reveal shield
checkpoint-status |  |  | checkpoint | Vaproshield applied as per manufacturers installation methodology
checkpoint-status |  |  | checkpoint | Wrapshield installation allowed for seismic movement
checkpoint-status |  |  | checkpoint | Lapping of sheets as specified by the manufacture.
checkpoint-status |  |  | checkpoint | Additional Liqui-flash applied
checkpoint-status |  |  | checkpoint | Wrapshield completed
checklist-flat |  |  | checklist | Doors |  |  |  |  | Yes | QA - Doors | ab90b404-69a7-48ba-8d81-76f390e1e8f2
checkpoint-status |  |  | checkpoint | Installer details entered
text | af32b81e-5da7-5c89-a69a-7291b894584c |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Installer details input
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
checkpoint-status |  |  | checkpoint | Door opening checked and correct
checkpoint-status |  |  | checkpoint | Direction of door correct
checkpoint-status |  |  | checkpoint | Number of screws and hardware location correct
checkpoint-status |  |  | checkpoint | Door hinges installed in place with correct screws
checkpoint-status |  |  | checkpoint | Floor clearance correct
checkpoint-status |  |  | checkpoint | Undercoat on door surface
checkpoint-status |  |  | checkpoint | Fireseal around door installed as per spec
checkpoint-status |  |  | checkpoint | Door is fully operational after installation
checkpoint-status |  |  | checkpoint | Door jambs are plumb and level
checkpoint-status |  |  | checkpoint | Door gap around door leaf within tolerance
checkpoint-status |  |  | checkpoint | Door report sent through to client
checklist-flat |  |  | checklist | Precast item #: |  |  |  |  | Yes | QA - Precast Panel / Column Placement Checklist | b7dbc380-0220-4c10-9165-69fa10a413eb
checkpoint-status |  |  | checkpoint | Installer details entered
text | ab364257-b487-553b-8ac9-0e667c612c13 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | ab364257-b487-553b-8ac9-0e667c612c13 |  | button | Is this task Green Star related? | Yes, No, N/A
button | 01157a9d-7fe8-5b0e-99f9-e853ab4b65b7 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Precast panel / column received and damage free
checkpoint-status |  |  | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
checkpoint-status |  |  | checkpoint | Installed in correct location with adequate seating
checkpoint-status |  |  | checkpoint | Adequately braced
checkpoint-status |  |  | checkpoint | Panel / column install complete (checked location, height and level)
checkpoint-status |  |  | checkpoint | All props removed for respective panels and stacked neatly
boolean | cfd5d52e-6bbd-5aa8-a14c-448e63074a36 |  | tickbox | Panel surface checked and all Livefirm responsibilities completed
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | Precast item #: |  |  |  |  | Yes | QA - Precast Flooring Placement Checklist | d19d9b9e-425a-4306-a6a3-4eba944ece20
checkpoint-status |  |  | checkpoint | Installer details entered
text | a5841d61-f141-5663-bbbe-da123dcba6bf |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | a5841d61-f141-5663-bbbe-da123dcba6bf |  | button | Is this task Green Star related? | Yes, No, N/A
button | 74c027c4-6394-5860-9157-df6d5854f794 |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Precast Flooring received and damage free
checkpoint-status |  |  | checkpoint | Setout completed and clearly marked (heights and locations) ready for installation
checkpoint-status |  |  | checkpoint | Installed in correct location with adequate seating
boolean | 3ca9c477-6c8b-582c-a1ad-2dce516edf79 |  | tickbox | Bearing strip installed correctly as required
checkpoint-status |  |  | checkpoint | Precast flooring install complete (checked location, height and level)
checkpoint-status |  |  | checkpoint | Report sent through to client
checklist-flat |  |  | checklist | QA - Densglass |  |  |  |  | Yes | QA - Densglass | d6d58de6-895f-40ce-be14-ff9d2fb3a8d6
checkpoint-status |  |  | checkpoint | Installer details entered
text | f720ad82-0bb8-59b8-b90b-116028d7e803 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | All relevant drawings checked and attached
checkpoint-status |  |  | checkpoint | External framing QA checked and passed
checkpoint-status |  |  | checkpoint | Fastners installed at correct centers and 9mm from sheet edge
checkpoint-status |  |  | checkpoint | Densglass sheets staggered
checkpoint-status |  |  | checkpoint | Densglass installed as per spec.
checkpoint-status |  |  | checkpoint | General photos of installation
checkpoint-status |  |  | checkpoint | Report sent to client
holdpoint |  |  | signoff | Sign off
checklist-flat |  |  | checklist | QA - Wall Underlay |  |  |  |  | Yes | QA - Wall Underlay | d77ae5f7-e4b6-4798-87b6-1c7fea924960
checkpoint-status |  |  | checkpoint | Installer details entered
text | df80292e-5eac-51a1-b094-11b396870779 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Ensure substrate is even and free from any protrusions, nails, screws, loose pieces, dust, dirt, etc
checkpoint-status |  |  | checkpoint | Line the internal or external corners of the wall underlay with a vertical 400mm wide strip of ADHERO in place with equal length on each of the walls. with min 150mm overlap on either side
checkpoint-status |  |  | checkpoint | Apply all the remaining membranes - one by one - horizontally in an overlapping, waterproof manner. The minimum horizontal and vertical overlap for membranes is 150 mm
checkpoint-status |  |  | checkpoint | Work all air bubbles in ADHERO to sheet edge, and flatten all creases
checkpoint-status |  |  | checkpoint | Cut ADHERO at 45° from the corners and Fold ADHERO into all sides of the rough door and window opening to the back edge of framing and adhere to all sides.
checkpoint-status |  |  | checkpoint | Apply TESCON EXTOSEAL sill tape to the opening as per application guide
checkpoint-status |  |  | checkpoint | Use ROFLEX grommets and TESCON EXTORA 60 tape to seal all pipe penetrations made through the ADHERO. Refer to the ROFLEX installation guide
checkpoint-status |  |  | checkpoint | Use KAFLEX grommets and TESCON EXTORA 60 tape to seal all round cable penetrations made through the ADHERO. Refer to the KAFLEX installation guide
checkpoint-status |  |  | checkpoint | Wall underlay report sent through to client
checklist-flat |  |  | checklist | QA - Pro Clima - Wall Underlay |  |  |  |  | Yes | QA - Pro Clima - Wall Underlay | d928c992-14e2-4310-b88f-2fa6d6826f39
checkpoint-status |  |  | checkpoint | Installer details entered
text | 7a53446c-7eae-54a7-9a6c-c2fe63374fdf |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Check substrate to ensure it is even and free from any protrusions, nails, screws etc.
checkpoint-status |  |  | checkpoint | Check substrate is dry and free of contaminants before applying ADHERO
checkpoint-status |  |  | checkpoint | Line the internal and external corners of the substrate with at least 400 mm in width and adhere it vertically in place with equal length on each of the walls.
checkpoint-status |  |  | checkpoint | Minimum of 150mm overlap is required at joints
checkpoint-status |  |  | checkpoint | Work all air bubbles in ADHERO to sheet edge and flatten all creases.
checkpoint-status |  |  | checkpoint | Apply sealing tape, sill tape, sealing grommet for joints, door and window opening, services penetrations as per manufacturer’s specifications (or as per designer’s project specific details)
checkpoint-status |  |  | checkpoint | Repair all cuts and tears in ADHERO with TESCON EXTORA 100 sealing tape, to a minimum 50mm past the edges of the damaged area.
checkpoint-status |  |  | checkpoint | Send report to client
checklist-flat |  |  | checklist | QA - Additional Stopping Checklist |  |  |  |  | Yes | QA - GIB Stopping Checklist | ef74de66-95f1-4dfc-af84-e984d4fd2d43
checkpoint-status |  |  | checkpoint | Installer details entered
text | 14ad20d7-addf-5324-a010-04517ca6d393 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached
text | 14ad20d7-addf-5324-a010-04517ca6d393 |  | textbox | Drawing no. and revision
checkpoint-status |  |  | checkpoint | Substrate accepted and approval given to start gib stopping
checkpoint-status |  |  | checkpoint | Correct stopping product and applied correctly
checkpoint-status |  |  | checkpoint | Square stopping, slimlines and joints checked and acceptable
checkpoint-status |  |  | checkpoint | Adequate drying time between applications & No visible bubbling
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | All Stopping completed and specified level of finish achieved
checkpoint-status |  |  | checkpoint | Send report to client
checklist-flat |  |  | checklist | QA - GIB Lining |  |  |  |  | Yes | QA - GIB Lining | f5b683b6-bef3-4f05-b897-6de9817a9bd3
checkpoint-status |  |  | checkpoint | Installer details entered
text | 89470d39-6afd-5457-bfe1-9b590a543f38 |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Green Star details entered
button | 89470d39-6afd-5457-bfe1-9b590a543f38 |  | button | Is this task Green Star related? | Yes, No, N/A
button | fce9fc57-d6a7-517c-b195-bc60eccf214d |  | button | Have you contacted/informed Built Environs Green Star representative? | Yes, No, N/A
checkpoint-status |  |  | checkpoint | All relevant drawings and revision numbers checked and attached/commented
checkpoint-status |  |  | checkpoint | Area ready for GIB install
checkpoint-status |  |  | checkpoint | Insulation installed
checkpoint-status |  |  | checkpoint | General photos, comments and observations during install
checkpoint-status |  |  | checkpoint | Correct lining checked and approved and area specifics checked
checkpoint-status |  |  | checkpoint | Correct fixings used and installed at correct centres
checkpoint-status |  |  | checkpoint | Any bracing elements completed to design specification
checkpoint-status |  |  | checkpoint | GIB Lining completed correctly within specified tolerance, checked and approved
checkpoint-status |  |  | checkpoint | GIB Lining report sent through to client
checklist-flat |  |  | checklist | Weatherboard Cladding |  |  |  |  | Yes | QA - Weatherboard Cladding Checklist | ff7013a2-146c-434a-93bc-7b7e961cbbb1
checkpoint-status |  |  | checkpoint | Installer details entered
text | c4431253-8314-57fe-aa2b-1f50a14e102f |  | textbox | Installer:
checkpoint-status |  |  | checkpoint | Weatherboards & all cut edges sealed prior to installation
checkpoint-status |  |  | checkpoint | Framing Straight and plumb within tolerance
checkpoint-status |  |  | checkpoint | All nogs/ special nogs in place.
checkpoint-status |  |  | checkpoint | Wall underlay and strapping inspected and installed correct.
checkpoint-status |  |  | checkpoint | All aluminium joinery Doors/Windows installed
checkpoint-status |  |  | checkpoint | Cavity batten installed at 400 centres
checkpoint-status |  |  | checkpoint | Cavity closer installed correctly
checkpoint-status |  |  | checkpoint | Aluminium Flashings to internal/external installed as per manufacturer's drawing.
boolean | e26bcd71-1547-5da8-9e79-10b2e5e47b20 |  | tickbox | Head Flashings to Doors & windows installed by others
checkpoint-status |  |  | checkpoint | Fixing Method Checked and correct as per installation manual.
checkpoint-status |  |  | checkpoint | All cladding installation checks completed & inspections carried out
checkpoint-status |  |  | checkpoint | Report sent through to client