## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | CS-4050 - Subgrade Approval Checksheet |  |  |  |  | Yes | CS-4050 - Subgrade Approval Checksheet | 1e2bd14a-d83f-4a0a-9f12-74a83c59bdb1
checkpoint-status |  |  | checkpoint | 1 - Area completely stripped of topsoil & organics
text | 0d63ac76-b157-5747-bf9e-fe1cadc8be22 |  | textbox | Chainage Start:
text | f8d98080-761a-5868-b220-6cd75349a783 |  | textbox | Finish:
label | 1ddfe4f9-410e-5f5b-b65e-5f70528d0f8b |  | note | Photos of area are taken & kept with QA records
checkpoint-status |  |  | checkpoint | 2 - Topsoil strip topo survey carried out
text | eec1a7d3-58ea-541b-bac2-c12db11e868e |  | textbox | Survey receipt #
checkpoint-status |  |  | checkpoint | 3 - Scala Penetrometer Test carried out
label | c9683728-c4ff-552a-bb87-3233f7ed3886 |  | note | To the correct frequency & results captured on the earthwork lab testing register
checkpoint-status |  |  | checkpoint | 4 - Proof Roll carried out & witnessed
text | 07c9152f-0c24-5d9d-bcc2-b0a0fe2478c5 |  | textbox | Equipment used:
checkpoint-status |  |  | checkpoint | 5 - Did Proof Roll pass
label | ba51f856-779a-5b65-a210-f31a9a8b4bbc |  | note | If yes moved to #10. If not undercut required continue below
checkpoint-status |  |  | checkpoint | 6 - Undercut area is to be marked out onsite by Design Engineer
checkpoint-status |  |  | checkpoint | 7 - Undercut to be inspected before backfilling commences by Design Engineer
label | 3be6825d-4b7c-5dd5-8356-a63d79fa41e3 |  | note | To determine that all undercut areas are prepared to the specifications
checkpoint-status |  |  | checkpoint | 8 - Undercut area to be surveyed
text | 052338df-dc73-534a-bafe-cd3b7c486023 |  | textbox | Survey receipt #
checkpoint-status |  |  | checkpoint | 9 - Backfill material is approved to be used and is tested in accordance with specifications
label | e57996cb-5564-59e6-a88f-1e130b84f33f |  | note | Lab Test Result register
checkpoint-status |  |  | checkpoint | 10 - Site is prepared for bulk filling to commence
label | 71f2ad20-df3f-5d2d-8214-1a60f2343742 |  | note | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
checkpoint-status |  |  | checkpoint | Site Engineer
text | 3e6a40d7-1fb0-5c40-90c3-7e0382d69a51 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | b3912017-69a1-559c-bf6a-a48c14ae8459 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | CS-4040 - Concrete Inspection Record |  |  |  |  | Yes | CS-4040 - Concrete Inspection Record | 36c0bd47-ba64-4613-986a-2a9270f0c791
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Concrete Inspection Record
text | bc1da694-f7f8-5678-995f-c43753a3ee6e |  | textbox | Location / Description of Pour:
text | 7f983af5-7ddd-57f8-8da7-3746a30f2c7a |  | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
text | 5964b267-1bd0-538c-be9e-acdfaad5b5cf |  | textbox | Concrete Grade |  |  | MPa
text | eeeaa3d6-b88b-50fc-b746-af1e48e825e2 |  | textbox | Concrete Quantity |  |  | M3
text | 9a269e43-6628-552b-b895-fa9092100e22 |  | textbox | Pour No.:
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Adequately braced and supported
checkpoint-status |  |  | checkpoint | Grout tight
checkpoint-status |  |  | checkpoint | Correct dimensions
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Formed surfaces straight
checkpoint-status |  |  | checkpoint | Major penetrations located
checkpoint-status |  |  | checkpoint | Embedded items located
checkpoint-status |  |  | checkpoint | Specified surface finish:
checkpoint-status |  |  | checkpoint | Adequate seating Pre Cast units
checkpoint-status |  |  | checkpoint | Permit to Load Obtained
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content and size
checkpoint-status |  |  | checkpoint | Grade markings:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
checkpoint-status |  |  | checkpoint | Rigidity and cover
checkpoint-status |  |  | checkpoint | Clean steel
checkpoint-status |  |  | checkpoint | Lap location and lengths
checkpoint-status |  |  | checkpoint | Starters/dowels correctly located
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Location
checkpoint-status |  |  | checkpoint | Roughened
checkpoint-status |  |  | checkpoint | Clean
checkpoint-status |  |  | checkpoint | Water bar placed if specified
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Mix ordered:
text | 8275539f-dc3c-567a-8eca-40f1845d1ac4 |  | textbox | Mix ordered:
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
checkpoint-status |  |  | checkpoint | CPS Engineer notified (48)
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Mix delivered:
text | 0ce041de-f5da-5bb0-83ca-8b17bac80848 |  | textbox | Mix delivered:
checkpoint-status |  |  | checkpoint | Slump/flow Target:
text | 4b3cc63b-ccb3-5c16-bf0e-f9d22c546db1 |  | textbox | Slump/flow Target:
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
checkpoint-status |  |  | checkpoint | Concrete Vibrated
checkpoint-status |  |  | checkpoint | Mandrels drawn through all ducts to verify no leakage / disconnection
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
checkpoint-status |  |  | checkpoint | Surface to required finish eg U2, U4
text | a983868d-71d9-5730-a58f-aee294a0c650 |  | textbox | Surface finish achieved:
checkpoint-status |  |  | checkpoint | Retarder applied at end of the pour
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
text | 780377b4-05e9-5a19-992c-b4b17977d027 |  | textbox | Pour Start Time:
text | 1697fcc9-463c-5553-92fd-fce6bd4f11fb |  | textbox | Pour Complete Time:
text | 96aa9b82-b7ea-5278-8498-400a751c22f5 |  | textbox | Volume Placed:
checkpoint-no-status |  |  | checkpoint | POUR ISSUES – Add as comments (e.g. formwork failure)
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Curing correctly carried out
text | 8b0d7e9c-e741-55d7-ad64-51c762ac24b8 |  | textbox | Concrete Strength for Striking:
text | 3f309b2d-9791-5e43-8994-ff111a539eb3 |  | textbox | Concrete Strength for backfilling:
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
label | b7196bc1-f1b1-50c8-9ee2-cf9523647a2f |  | note | CPS Engineer Inspected.
checkpoint-status |  |  | checkpoint | As-Built complete
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 15b6b989-b3be-54e0-8173-78b52628fae5 |  | textbox | Site Engineer:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | CS-4090 - Utilities Check Sheet |  |  |  |  | Yes | CS-4090 - Utilities Check Sheet | 868e2e7e-173c-44a0-ab26-908575e563f0
checkpoint-group |  |  | section | Pre Construction
checkpoint-status |  |  | checkpoint | Underground services checked
checkpoint-status |  |  | checkpoint | Survey Set Out
checkpoint-status |  |  | checkpoint | Correct materials and sufficient lengths on site
checkpoint-group |  |  | section | Material Approval
checkpoint-status |  |  | checkpoint | Bedding Material approval
checkpoint-status |  |  | checkpoint | Hard fill approval
checkpoint-status |  |  | checkpoint | Draw wired is 10 gauge galvanised mild steel complying with NZS 3471
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | Trench correct depth and width
checkpoint-status |  |  | checkpoint | Subgrade check (scalas), min. 3 % CBR
checkpoint-status |  |  | checkpoint | Bedding laid in trench to correct depth (100mm)
checkpoint-status |  |  | checkpoint | Correct cable and duct sizes laid as per service drawings
checkpoint-status |  |  | checkpoint | Gas provider trench approval
checkpoint-status |  |  | checkpoint | Chorus provider trench approval
checkpoint-status |  |  | checkpoint | Power provider trench approval
checkpoint-status |  |  | checkpoint | Services laid with correct spacing
checkpoint-status |  |  | checkpoint | Irrigation provided to all Rain Gardens and Garden Beds
checkpoint-status |  |  | checkpoint | Lot connections laid 500mm into lot boundary
checkpoint-status |  |  | checkpoint | Street light cables laid to pole locations
checkpoint-status |  |  | checkpoint | As built service locations
checkpoint-status |  |  | checkpoint | Draw wire in all ducts
checkpoint-status |  |  | checkpoint | All ducts end capped
checkpoint-status |  |  | checkpoint | Mag Slab laid
checkpoint-status |  |  | checkpoint | Bedding covering services to correct depth (100mm over Gas, 50mm over all other services)
checkpoint-status |  |  | checkpoint | Approved backfill material placed in 200mm layers
checkpoint-status |  |  | checkpoint | NDM tests every 30m³ of backfill material, 95% of MDD
checkpoint-status |  |  | checkpoint | Warning Tape 400mm below finished surface
checkpoint-status |  |  | checkpoint | Irrigation Pressure Test complete
checkpoint-status |  |  | checkpoint | Gas Pressure Test complete
checkpoint-no-status |  |  | checkpoint | Weather
button | 4dba06c9-0bec-5c8a-a088-2a9c43888b9d |  | button | Weather | Sunny (check plants not left bare root in sun), Raining (ensure soil is not saturated which prevents proper planting), Frost (No planting to be carried out until frost thaws out), Overcast (Good Planting condition)
checkpoint-status |  |  | checkpoint | Sign Off - Site Engineer
label | 0c41cae0-3013-55e0-a2e6-95f1bfc2e796 |  | note | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | CS-4045 - Kerb Construction Record |  |  |  |  | Yes | CS-4045 - Kerb Construction Record | 9237bdb9-9590-4aa5-91df-8147ff0534f8
checkpoint-group |  |  | section | Kerb Construction Record
checkpoint-no-status |  |  | checkpoint | Kerb Construction Record
text | 3fa10605-0eef-57c0-bf66-49eebc1bcab5 |  | textbox | Description of Pour:
text | a72b4ff8-4556-5efe-8673-f13ce114819b |  | textbox | Kerb Type & Dimensions:
text | 4c842844-b45e-5b2d-9351-ea64caf1d16a |  | textbox | Weather conditions:
text | 1e7d7390-424c-5019-ae10-572051dda11f |  | textbox | Concrete Qty:
text | 767f6952-198d-5869-a64d-1cee7abca285 |  | textbox | Concrete Grade: |  |  | MPa
text | 7b288eb2-eb90-57f5-a5f4-fe3149309c0d |  | textbox | Dwg No/Rev:
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Correct profile/dimensions for Kerb Type
checkpoint-group |  |  | section | Subgrade
checkpoint-status |  |  | checkpoint | Ensure subgrade construction is complete and suitable for kerb
checkpoint-status |  |  | checkpoint | Cesspit protection in place
checkpoint-group |  |  | section | Survey Set Out
checkpoint-status |  |  | checkpoint | Check survey set out
checkpoint-status |  |  | checkpoint | Check subcontractors string lines for machine
checkpoint-status |  |  | checkpoint | Vertical levels correct to design +/-5mm vertical tolerance
checkpoint-status |  |  | checkpoint | Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
checkpoint-status |  |  | checkpoint | Crossings / kerb transitions set out
checkpoint-status |  |  | checkpoint | Engineer to mark kerb types at crossings and kerb transitions
checkpoint-status |  |  | checkpoint | Ensure channels fall towards catchpit locations
checkpoint-group |  |  | section | Miscellaneous
checkpoint-status |  |  | checkpoint | Construction joint roughened & clean
checkpoint-status |  |  | checkpoint | Correct mix ordered
checkpoint-group |  |  | section | Pre-pour check – HOLD POINT
checkpoint-status |  |  | checkpoint | Site Engineer
text | 161eb21f-504a-52a9-82ac-9d2b622d6f5c |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | b5ba5db0-51d4-5368-86a2-d7152a5294fd |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered?
checkpoint-status |  |  | checkpoint | Correct slump (within tolerances)?
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected?
checkpoint-status |  |  | checkpoint | Batching Plant Records received?
checkpoint-status |  |  | checkpoint | Kerb meters completed in m
text | ed023c8b-74ce-524d-8694-a465af6c63ac |  | textbox | Kerb meters: |  |  | m
checkpoint-group |  |  | section | During Concrete Pour Inspection
checkpoint-status |  |  | checkpoint | Ensure correct kerb type is being installed in the correct location(s)
checkpoint-status |  |  | checkpoint | Constantly check levels and line to ensure kerb is within design tolerances
checkpoint-status |  |  | checkpoint | Ensure protruded kerb has U4 finish
checkpoint-status |  |  | checkpoint | Ensure Expansion joints are installed
checkpoint-group |  |  | section | Concrete Infill Islands
checkpoint-status |  |  | checkpoint | Ensure F3 finish and the concrete level is no higher than the top of the kerb that forms the median/island
checkpoint-group |  |  | section | Tie ins to pre-cast elements
checkpoint-status |  |  | checkpoint | Aprons to be formed around pre-cast elements
checkpoint-group |  |  | section | Pour Time
checkpoint-no-status |  |  | checkpoint | Pour Time
text | 4b52ed8b-2b87-55ff-8742-c8fe4cb7ade1 |  | textbox | Pour Start Time:
text | df78bc60-f4f4-5ea5-8770-8caa85dd8865 |  | textbox | Pour Complete Time:
text | fe342ca9-098f-50cb-bdbf-7d90736bd476 |  | textbox | Volume Placed:
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Warning tape to be placed over kerb to prevent any damage
checkpoint-status |  |  | checkpoint | Backfilling to commence after 72 hours curing time
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Surface Finish and levels acceptable
checkpoint-status |  |  | checkpoint | Expansion joints satisfactorily completed
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
checkpoint-status |  |  | checkpoint | Site Engineer
text | 8d890a9e-6935-508d-9149-b502c254654d |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | 7cadd054-6083-5618-abd3-b0267fcf9180 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Ensure surface varies no more than 5mm when checked with a 3m straight edge
checklist-flat |  |  | checklist | CS-4000 - 1M Scala Worksheet |  |  |  |  | Yes | CS-4000 - 1M Scala Worksheet | c5bbc2f6-a755-45d5-96b0-112b0943fd17
checkpoint-no-status |  |  | checkpoint | 1M Scala Worksheet
text | 060cc38b-8be2-57a0-952d-cd1090009e10 |  | textbox | CH & Offset:
text | 0deb8c70-bdd3-51df-85f6-d390a5365cf6 |  | textbox | Date:
text | 472a3ed7-2eab-58df-b2d3-ca8f18c51819 |  | textbox | Start Depth (mm):
checkpoint-status |  |  | checkpoint | Depth [mm] - 0-100
text | b0f1bc76-753b-5d2b-a341-aa44751c820c |  | textbox | No. of Blows
text | 8136a97d-9c2b-56be-8621-4d55c3286258 |  | textbox | mm / blow
text | 6d62638a-d22c-5522-907b-b33d9857b90f |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 100-200
text | 6c37d786-5336-5ba5-b985-4b1168eb05d0 |  | textbox | No. of Blows
text | 0a7f99b2-c0a8-5529-8d4b-cbb7b8a8d353 |  | textbox | mm / blow
text | c696a4c9-7e01-5adc-aa7d-c516bada6fc1 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 200-300
text | d8cb54b0-31b4-512b-8219-fc321ffc0e41 |  | textbox | No. of Blows
text | 667c3271-7d86-558a-ac82-1d0f338a4882 |  | textbox | mm / blow
text | 16618054-1e15-5a76-8282-bcea4d5f97b2 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 300-400
text | ce157742-36df-5f59-8f56-7192f0229a44 |  | textbox | No. of Blows
text | c06e4982-f5e6-50f2-8d4b-1b8c324364b8 |  | textbox | mm / blow
text | b0265bc4-e67f-5c4e-9291-d7146078ad38 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 400-500
text | 4684c69b-fe09-5a28-a352-ddf9a2675d6c |  | textbox | No. of Blows
text | 52acd104-1bfc-5090-8cd3-a01670dc1b99 |  | textbox | mm / blow
text | e6c43a19-d14f-5e53-9791-ce0eea637dbc |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 500-600
text | 5cfdfded-b047-50c2-919b-6d8d0cf5c0f9 |  | textbox | No. of Blows
text | ec05f47e-5264-5bdf-aa70-18c3cd48c6c8 |  | textbox | mm / blow
text | 3e9b5e11-da70-5d2c-816c-93138cb175a0 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 600-700
text | 9dd8eab9-135b-5622-bb62-34661bdac2e5 |  | textbox | No. of Blows
text | 546812d1-a647-597c-ad90-11437b3f1bdc |  | textbox | mm / blow
text | d0eceb50-301f-53db-a3c5-471c39ffc257 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 700-800
text | 263cafec-9bf5-5a6d-8794-92d00ca8ed38 |  | textbox | No. of Blows
text | d7341a56-7bd3-58fe-96b5-84e26711281a |  | textbox | mm / blow
text | 2252544d-305a-569c-bbc7-fe6aff95e065 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 800-900
text | 5fbcc6f6-33bb-5698-873f-676014dec111 |  | textbox | No. of Blows
text | 1c9b0fff-ac3d-5fba-919c-ff23d8df95cc |  | textbox | mm / blow
text | 0c21929f-6e96-5c07-ae2b-605af9c7eb4d |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 900-1000
text | 07eceb53-72a6-575f-a2dd-1e9d9bf4cd58 |  | textbox | No. of Blows
text | fdfc800b-4455-5f35-8af0-14e2b5c23957 |  | textbox | mm / blow
text | 1b32b7d9-875b-5d13-9e20-f9c6a929b679 |  | textbox | CBR
checkpoint-no-status |  |  | checkpoint | Tested by:
text | 09653eb8-25f8-5c13-9341-58c6fb34c00a |  | textbox | Tested by:
checkpoint-no-status |  |  | checkpoint | Checked by:
text | 06a3f1d2-e7c7-5f8e-91a4-be60f8921a5b |  | textbox | Checked by:
checklist-flat |  |  | checklist | CS-4055 - Pavement Layers Checksheet |  |  |  |  | Yes | CS-4055 - Pavement Layers Checksheet | f338b86e-0039-4355-bba1-b8d93a8c80b3
checkpoint-no-status |  |  | checkpoint | Details
text | 33705ad9-eed2-5456-b3dc-d8f9c2d1b0a2 |  | textbox | Paved Date:
text | b1a0cc3f-8580-5b5b-a9ba-ed2f3589803e |  | textbox | Location/ Direction:
text | 0c032a8e-3075-53a0-b2fd-55e63c4065ca |  | textbox | Day:
text | 0bd5dd2c-ee56-532f-972a-b47c004c7023 |  | textbox | Shift:
text | cf94f2e5-92b7-54aa-a393-048e1003364e |  | textbox | Chainage(s) From:
text | 330da9c9-65bc-5c44-b6e2-6f1a5144622a |  | textbox | Chainage(s) To:
text | 7a28fe71-74cd-5c4a-b65e-43de4a207328 |  | textbox | Previous Lot(s):
button | 9784abc7-e8ab-567f-9248-30ac789a295f |  | button | Previous Lot(s) Comply? | Yes, No
text | bf991f05-76e8-57b2-b663-60be9db6609f |  | textbox | Corrective action?
checkpoint-status |  |  | checkpoint | HOLD POINT: Previous Layers Quality Manager signed off
button | d30e84ce-a40d-5b15-985a-166fd09bf355 |  | button | Pave this layer | Yes, No
checkpoint-status |  |  | checkpoint | Layer Type:
boolean | d7e5253e-26d5-5230-bd11-87c7deb1e693 |  | tickbox | AC___ Layer # 1
boolean | c2836b80-7974-5f20-83bf-8556f2cf19f5 |  | tickbox | AC___ Layer # 2
boolean | 7d343427-b5c3-56f7-ba6a-72479000c83b |  | tickbox | OGPA / SMA
text | dec79fcf-8f06-525a-b264-ae5c14f65bd5 |  | textbox | Other:
text | 40348727-588c-58d9-9344-c0e509050cbc |  | textbox | Nominal Depth To Pave:
text | e3764799-5345-51fe-a5d5-5a0358e29d31 |  | textbox | m² Paved:
text | 94a2b788-3f2a-5ef1-9815-8713c40209e3 |  | textbox | Linear(m):
text | 20a94d2a-78c2-596b-bdf8-a9b81f3d831e |  | textbox | Tack coat/Membrane l/m²:
text | 75a0eb52-52a5-599c-9a63-83e8d45ffd12 |  | textbox | Nº of Cores required:
text | 5af2451b-ac83-51d7-96a4-01fd98c9190c |  | textbox | Mat:
text | d62d2c8c-4c59-5839-ad4c-20470e8c3ff0 |  | textbox | Joint:
text | e1643be8-7f73-57bd-b466-6599f8230299 |  | textbox | Nº of Cores taken:
text | 03c3bcde-297f-567f-b6cd-b07a48ccfde9 |  | textbox | Mat:
text | 86262852-689b-530d-a413-d643bc80ac9a |  | textbox | Joint:
button | 221ad8ab-b6b6-5ceb-93aa-ef31cb0a6d80 |  | button | Cores Taken: | Yes, No
button | bbaf484c-5a5f-5794-b685-f740b2b2fc41 |  | button | Cores Filled: | Yes, No
text | aff14f03-038f-52d7-ae29-f6464cdc8d04 |  | textbox | Laid (Ton):
text | 558d7b91-ce6b-542e-919e-997b7177872b |  | textbox | Nº of Binder & Gradings required:
text | 3b7da1fa-6102-5097-8e16-6ea0ca1ac2cf |  | textbox | Nº of Binder & Gradings supplied:
text | 29473192-51ae-5c14-b262-1fd46cfd0d9f |  | textbox | Lab Air Voids (%)
button | 6d38c642-af0a-5e93-a4a2-150319d2a67e |  | button | Binder & Gradings Comply? | Yes, No
button | 4976abad-5f7d-5a87-aec3-ca7bd02d757e |  | button | As built Survey Completed? | Yes, No
checkpoint-status |  |  | checkpoint | Air Voids - Run 1
text | 74e88de7-748a-505d-977c-11fc24919809 |  | textbox | Characteristic High:
text | e5d684da-0ae5-5d8f-b1ce-0a629938e0ba |  | textbox | Characteristic Low:
text | c5105d0c-02b1-5c23-bdee-46895aea8976 |  | textbox | Average:
text | d8206dee-9cc6-5bcb-a913-2eb42805c548 |  | textbox | Joint:
checkpoint-status |  |  | checkpoint | Air Voids - Run 2
text | 6895b174-ae33-5fcf-a99e-20dd00ccaee6 |  | textbox | Characteristic High:
text | ea0c5ad0-30b2-5767-b80f-a419c8211531 |  | textbox | Characteristic Low:
text | 15fe76fb-c879-5730-95aa-aed3f61aa9d1 |  | textbox | Average:
text | d149161f-f590-59d6-a1ed-6f306117e9cb |  | textbox | Joint:
checkpoint-status |  |  | checkpoint | Air Voids - Run 3
text | 162a105e-8ae6-5bce-9b42-d2ad9c37aa5d |  | textbox | Characteristic High:
text | 61095523-7187-5ff6-bc25-1582574c2621 |  | textbox | Characteristic Low:
text | 78d44d52-ad93-5078-b5a9-d66bdc693bd3 |  | textbox | Average:
text | a82bcdcc-4be0-58a1-8a1d-68860909d2b9 |  | textbox | Joint:
button | e36bc4b8-b351-5850-ae4b-d1c69336cc6d |  | button | Air Voids Comply? | Yes, No
button | 0a188380-44a1-5568-bdb4-0c097b1c353e |  | button | Core Thickness Comply? | Yes, No
button | f654dfcb-bb09-59e8-8f55-2b228fec6b10 |  | button | OFI attached for non-conformance | Yes, No
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
button | cc991dd6-18df-5214-8075-0603d65507f9 |  | button | HOLD POINT: Does everything above comply? | Yes, No
button | 0882c65c-c731-5dc9-abca-f4c784d3cac7 |  | button | Pave next layer | Yes, No
checkpoint-status |  |  | checkpoint | Site Engineer
text | 0dd81350-5d98-53cc-8ea5-cc724e64283a |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Quality Engineer
text | e33f716a-ed09-58e4-8c4f-ca5eac3c9398 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature