## Mangaheia No.1
Inspection and Test Plan (ITP)
Mangaheia No.1 Bridge - Tauwhareparae Road RP16.17
Dispatch:
WO:
Item | Activity Description | Specification | Verification Activity | Methods or reference | Frequency | Acceptance criteria | Inspection Type | Assessor | Reports to be delivered | Responsible Person | Records/ Remarks Sign and date if appropriate
1 | DELIVERABLES
1.1 | Prestart handover meeting | - | - | Meeting agender items | Once | Prior to commencement of physical works | Internal meeting | Project Manager | Attendance record | Currie
1.2 | Construction Methodology | Letter of Award | - | - | Once | Approved by ER prior to commencement of physical works | Hold Point | WSP | Detailed record | Currie
1.3 | Construction Programme | Special Conditions of Contract cl. 5.10.4 and Letter of Award |  | MS Project format | Updated weekly | Conform to contract requirement | Hold Point | WSP | Detailed record | Currie
1.4 | Site Specific Risk Assessment | Special Conditions of Contract cl. 5.17.1 | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.5 | Health & Safety Management Plan | Special Conditions of Contract cl. 5.17.1 and Letter of Award | - | - | Once | Conform to contract requirement | Hold Point | WSP | Detailed record | Currie
1.6 | Monthly Health & Safety Report | Special Conditions of Contract cl. 5.7.15 |  |  | Monthly | Conform to contract requirement | Verification | WSP | Detailed record | Currie
1.7 | Quality Management Plan | Special Conditions of Contract cl. 5.18.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie
1.8 | Enviromental Management Plan | Special Conditions of Contract cl. 5.22.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie
1.9 | Erosion & Sediment Control Plan | Letter of Award | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.1 | River Based Access | Technical Specification cl. 1.12 | - | Contractor to provide proposed access method | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.11 | Building Consent Expemption | Special Conditions of Contract cl. 1.5.1 | - | - | Once | To be provided to the Contractor prior to construction | Hold Point | WSP | Detailed record | GDC
1.12 | Traffic Management Plan | Special Conditions of Contract cl. 5.19.1 | - | GDC Tranche 4 Generic TMP to be used with possibly some site specific diagrams added | Once | Conform to Contract requirements | Verification | GDC | Detailed record | Currie
1.13 | Bridge Closures | Technical Specification cl. 1.8 | - | The date and duration of any closures to be agreed with the Engineer | On-going | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.14 | Proof of Insurance | Special Conditions of Contract cl. 8.1.1 | Insurer confirmation certificates for construction, plant, public liability & motor vehicle liability | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.15 | Service Locates | Technical Specification cl. 11 | Service providers including Before You Dig & close approach agreement | - | Once | Prior to commencement of physical works | Verification | Foreman | Service details | Currie
1.16 | Dimensions and set-out | Technical Specification cl. 1.11 | - | Contractor to confirm set-out and dimensions with the Engineer on-site | Once | Prior to commencement of physical works | Hold Point | WSP | Verification | Currie
1.17 | Clearing of Site | Technical Specification cl. 1.13 | - | Contractor to agree with Engineer the extent of the clearing | Once | Prior to commencement of physical works | Verification | WSP | Verification | Currie
1.18 | Earthworks | Technical Specification cl. 1.10 | Contractor to submit excavation & compaction methodology to the Engineer | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2 | Materials
2.1 | Nuts, bolts and washers | Technical Specification cl. 2.2 | - | To be Class 8 & HDG | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.2 | All Steelwork to be Grade 300 | Technical Specification cl. 2.3 | Mill certificate | - | Once | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
2.3 | Concrete for steel post footings | Technical Specification cl. 2.4.1 | Contractor to provide concrete mix design | Concrete to be 30MPa | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2.4 | No-fines concrete | Technical Specification cl. 2.4.2 | Contractor to provide concrete mix design | Concrete to be 7.5MPa | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2.5 | Timber lagging | Technical Specification cl. 2.5.1 | Visual | To be SG8 H4 with cut surfaces treated with Metalex | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.6 | Timber lagging fixings | Technical Specification cl. 2.5.1 | - | All fixings to be stainless steel | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.7 | Lagging thickness | Drawings C03 & C04 | Visual | Height from top of wall: 0.0 - 1.6m = 100mm thick ; greater than 1.6m = 200mm thick | On-going | Conform to Contract requirements | Verification | WSP | Verification | Currie
2.8 | Geo-textile | Technical Specification cl. 2.6 | - | A29 required behind timber lagging & around sub-soil drain | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.9 | Drainage composite | Technical Specification cl. 2.7 | - | Filtration Class 1 & Strength Class C - laid over batter slopes | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.1 | Drainage aggregate | Technical Specification cl. 2.8 | - | Free draining clean aggregate with 100% passing 19mm sieve | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.11 | Retaining wall backfill | Technical Specification cl. 2.9 | Contractor to provide concrete mix design | Sand & cement mix with strength of 1MPa & slump of 350 - 500mm | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2.12 | Sub-soil drain | Technical Specification cl. 2.10 | - | 150mm Punched HDPe sub-soil pipe | Once | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.13 | Inspection of sub-soil drain | Technical Specification cl. 14 | Contractor must request an inpection by the Engineer of the sub-soil drain before backfilling | - | Once | Conform to Contract requirements | Hold Point | WSP | Site check | Currie
2.14 | Topsoil | Technical Specification cl. 2.11 | Visual | Re-use existing topsoil | Once | Conform to Contract requirements | Verification | WSP | Verification | Currie
2.15 | Testing of materials | Technical Specification cl. 2.13 | Supplied by the Contractor to the Engineer with 3 days of the activity occurring | - | On-going | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
3 | Steelwork Fabrication
3.1 | Shop drawings | Technical Specification cl. 3.2 | To be supplied to the Engineer | - | Once | Conform to Contract requirements | Verification | WSP | Detailed drawing | Currie
3.2 | All piles, walers & accessories | Technical Specification cl. 3.2 | To be inspected by the Engineer before installation | - | Once | Conform to Contract requirements | Hold Point | WSP | Verification | Currie
4 | Piling
4.1 | Pile holes | Technical Specification cl. 4.1 drg C03 & C04 | 150UC30 piles in 400mm dia hole, min. 1.5m deep rock socket | Engineer to inspect pile holes before pouring | On-going | Conform to Contract requirements | Hold Point | WSP | Site check | Currie
4.2 | Pile spacing | Technical Specification cl. 4.1 drg C03 & C04 | Abutment A: Spacing varies between 1.2m & 1.5m ; Abutment C: Spacing at 1.2m centres | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.3 | Maximum retained height | Technical Specification cl. 4.1 drg C03 & C04 | Abutment A: 3.5m ; Abutment C: 1.9m | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.4 | Pile hole augering methodology | Technical Specification cl. 4.1 | Visual check | Hit one, miss one. "Miss" holes only to be augered 24hrs after concreting "hit" holes. | Once | Conform to Contract requirements | Verification | Foreman | Site check | Currie
4.5 | Augered pile holes | Technical Specification cl. 4.2 | Pile logs submitted to engineer by the next day after augering | - | On-going | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
4.6 | Pile hole tolerances | Technical Specification cl. 4.3 | Pole dia. +50mm/0mm, hole plan position +/-20mm. | Tape measure | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.7 | UC post tolerances | Technical Specification cl. 4.3 | Pole vertical alignment not to exceed 2 deg from design alignment, deviation of pole plan line +/-10mm, pole tops +/-10mm, pole base level +/-50mm | String lines and tape measures | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.8 | UC post size & treatment | Drg C03 & C04 | 150UC30 ungalvanized | - | Once | Conform to Contract requirements | Verification | WSP | Delivery docket | Currie
4.9 | Concreting UC posts | Technical Specification cl. 2.4.1 & 4.3 | 30MPa concrete | Supplier delivery dockets and laboratory concrete compression test results to be delivered to the engineer | On-going | Conform to Contract requirements | Verification | WSP | Detailed records | Currie
5 | Welding
5.1 | Welds | Technical Specification cl. 6.1 | All welds to be category SP | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
5.2 | Welder qualifications | Technical Specification cl. 6.1 | Welder qualifications to be submitted to the Engineer for approval | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed records | Currie
6 | Concreting
6.1 | Formwork | Technical Specification cl. 7.1 | Formwork to remain in place for 48hrs after pouring | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
6.2 | Concrete workmanship | Technical Specification cl. 7.2 | Concrete to be placed in dry conditions | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
6.3 | Concrete testing | Technical Specification cl. 7.4 | Cylinder test results to be supplied to the Engineer. 1 x 7d + 2 x 28d | - | On-going | Conform to Contract requirements | Verification | WSP | Detailed records | Currie
7 | Crib Wall
7.1 | Pouring no-fines concrete | Technical Specification cl. 8.2 | No-fines to be poured up to the front face of the crib wall | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
8 | Ground Anchors
8.1 | Anchor installation | Technical Specification cl. 9.1 | Contractor to notify Engineer at least 2 days prior to installation & testing | - | On-going | Conform to Contract requirements | Verification | Project manager | Verification | Currie
8.2 | Anchor grout volume | Technical Specification cl. 9.1 | Supply grout volume records for each anchor & submit to engineer | - | On-going | Conform to Contract requirements | Verification | WSP | Grout Log Record | Currie
8.3 | Anchor installation | Technical Specification cl. 9.1 | Hollow bars not to be installed at a rate exceeding 1m per minute | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
8.4 | Loading of anchors | Technical Specification cl. 9.1 | Anchors shall not be loaded for at least 7 days following grouting | - | On-going | Conform to Contract requirements | Verification | WSP | Verification | Currie
8.5 | Anchor testing equipment | Technical Specification cl. 9.2 | Contractor to submit all testing equipment calibration certificates to the Engineer prior to testing | - | Once | Conform to Contract requirements | Verification | Project manager | Detailed records | Currie
8.6 | Anchor test results | Technical Specification cl. 9.2 | Contractor to provide the Engineer with test results within 2 days of testing | - | On-going | Conform to Contract requirements | Verification | Project manager | Detailed records | Currie
8.7 | Sacrificial tests | Technical Specification cl. 9.3 | Abutment A: 1 x sacrificial test : Abutment C: 1 x sacrificial test | Positions to be agreed with the Engineer & outside of the work area | Once | Conform to Contract requirements | Verification | WSP/Currie | Verification | Currie
8.8 | Production anchors | Technical Specification cl. 9.2 & 9.4 | All production anchors are to be tested & Contractor to provide the Engineer with test records within 2 days of a test | - | On-going | Conform to Contract requirements | Verification | WSP | Anchor Load Test Record | Currie
8.9 | Sacrificial & production anchors | Technical Specification cl. 9.3 | Engineer to witness testing and shall be given at least 2 days notice of testing | - | On-going | Conform to Contract requirements | Hold Point | WSP | Verification | Currie
8.1 | Grout mix design | Technical Specification cl. 9.7 | Contractor to submit a grout mix design to the Engineer for approval at least 1 x week before grouting | - | Once | Conform to Contract requirements | Verification | Project manager | Detailed records | Currie
8.11 | Anchor grout | Technical Specification cl. 9.3, 9.4 & 9.7 | 30MPa required at 28 days and 30MPa before testing | 1no. X 50mm cubes at 7d and 2no. X 50mm cubes at 28d | Once | 30MPa before testing & proven with cube test results prior to testing | Hold Point | WSP/Project manager | Detailed report | Currie
8.12 | Anchor tolerences | Technical Specification cl. 9.6 | Depth of anchor +0.5m/ -0.0m, anchor position +-20mm, plan location +-50mm, orientation 2 degrees | Tape measure & digital spirit level | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
8.13 | Anchor testing | Drg C11 Table 2 | Anchor bar design yield strength: Abutment A: 30/14 bar = 220kN & 40/20 bar = 430kN ; Abutment C: 30/14 bar = 220 kN | Hydraulic test jack | Every anchor | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
8.14 | Anchor bar lengths | Drg C11 Table 2 | Abutment A: GA1 - GA5 = 3.0m unbonded & min. 3.0m rock socket ; GA6 - GA7 = 3.0m unbonded & min. 5.0m rock socket ; Abutment C: GA8 - GA13 = 3.0m unbonded & min. 3.0m rock socket | Abutment A: GA1 - GA5 = 30/14 anchor at 1.2 - 1.5m centres ; GA6 - GA7 = 40/20 anchor at 1.35m centres ; Abutment C: GA8 - GA13 = 30/14 anchor at 1.2m centres | On-going | Conform to Contract requirements | Verification | WSP | Anchor Log Record | Currie
8.15 | Anchor bar couplers, nuts & washers | All hot dip galvanized | - | - | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
9 | Earthworks
9.1 | Site sourced material | Technical Specification cl. 10.3 | Site sourced to be used for all backfilling EXCEPT for behind the retaining walls | - | On-going | Conform to Contract requirements | Verification | WSP | Visual | Currie
9.2 | Compaction layer thickness | Technical Specification cl. 10.3 | Compaction to be in loose layers not exceeding 300mm | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
9.3 | Centre pier rip rap protection | Drg C01 | Rip rap to be site won | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
10 | COMPLETION
10.1 | Remove erosion and sediment control measures | Remove once planting has taken | - | - | Once | According to Environmental Management Plan | Verification | Foreman | Photo | Currie
10.2 | Remove Traffic Control | Safety | - | - | Once | According to TMP | Verification | Supervisor | Photo | Currie | -
10.3 | Site maintained in a tidy state during construction | Best as is reasonably practicable | - | - | Daily | - | Verification | Supervisor | Photo | Currie | -
10.4 | Practical Completion Inspection | Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a) | Engineer to inspect site on completion of physical works | - | Once | Supply as-built drawings & PS3 | Hold Point | WSP | Inspection record | Currie/WSP
10.5 | Inspect site 12 months after completion | Remedy agreed defects | - | - | Once | - | Verification | WSP | Site Inspection | Currie/WSP

## Mangaheia No.3
Inspection and Test Plan (ITP)
Mangaheia No.3 Bridge - Tauwhareparae Road RP17.7
Dispatch:
WO:
Item | Activity Description | Specification | Verification Activity | Methods or reference | Frequency | Acceptance criteria | Inspection Type | Assessor | Reports to be delivered | Responsible Person | Records/ Remarks Sign and date if appropriate
1 | DELIVERABLES
1.1 | Prestart handover meeting | - | - | Meeting agender items | Once | Prior to commencement of physical works | Internal meeting | Project Manager | Attendance record | Currie
1.2 | Construction Methodology | Letter of Award | - | - | Once | Approved by ER prior to commencement of physical works | Hold Point | WSP | Detailed record | Currie
1.3 | Construction Programme | Special Conditions of Contract cl. 5.10.4 and Letter of Award |  | MS Project format | Updated weekly | Conform to contract requirement | Hold Point | WSP | Detailed record | Currie
1.4 | Site Specific Risk Assessment | Special Conditions of Contract cl. 5.17.1 | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.5 | Health & Safety Management Plan | Special Conditions of Contract cl. 5.17.1 and Letter of Award | - | - | Once | Conform to contract requirement | Hold Point | WSP | Detailed record | Currie
1.6 | Monthly Health & Safety Report | Special Conditions of Contract cl. 5.7.15 |  |  | Monthly | Conform to contract requirement | Verification | WSP | Detailed record | Currie
1.7 | Quality Management Plan | Special Conditions of Contract cl. 5.18.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie
1.8 | Enviromental Management Plan | Special Conditions of Contract cl. 5.22.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie
1.9 | Erosion & Sediment Control Plan | Letter of Award | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.1 | River Based Access | Technical Specification cl. 1.12 | - | Contractor to provide proposed access method | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.11 | Building Consent Expemption | Special Conditions of Contract cl. 1.5.1 | - | - | Once | To be provided to the Contractor prior to construction | Hold Point | WSP | Detailed record | GDC
1.12 | Traffic Management Plan | Special Conditions of Contract cl. 5.19.1 | - | GDC Tranche 4 Generic TMP to be used with possibly some site specific diagrams added | Once | Conform to Contract requirements | Verification | GDC | Detailed record | Currie
1.13 | Bridge Closures | Technical Specification cl. 1.8 | - | The date and duration of any closures to be agreed with the Engineer | On-going | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.14 | Proof of Insurance | Special Conditions of Contract cl. 8.1.1 | Insurer confirmation certificates for construction, plant, public liability & motor vehicle liability | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.15 | Service Locates | Technical Specification cl. 11 | Service providers including Before You Dig & close approach agreement | - | Once | Prior to commencement of physical works | Verification | Foreman | Service details | Currie
1.16 | Dimensions and set-out | Technical Specification cl. 1.11 | - | Contractor to confirm set-out and dimensions with the Engineer on-site | Once | Prior to commencement of physical works | Hold Point | WSP | Verification | Currie
1.17 | Clearing of Site | Technical Specification cl. 1.13 | - | Contractor to agree with Engineer the extent of the clearing | Once | Prior to commencement of physical works | Verification | WSP | Verification | Currie
1.18 | Earthworks | Technical Specification cl. 1.10 | Contractor to submit excavation & compaction methodology to the Engineer | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2 | Materials
2.1 | Nuts, bolts and washers | Technical Specification cl. 2.2 | - | To be Class 8 & HDG | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.2 | All Steelwork to be Grade 300 | Technical Specification cl. 2.3 | Mill certificate | - | Once | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
2.3 | Concrete for steel post footings | Technical Specification cl. 2.4.1 | Contractor to provide concrete mix design | Concrete to be 30MPa | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2.4 | No-fines concrete | Technical Specification cl. 2.4.2 | Contractor to provide concrete mix design | Concrete to be 7.5MPa | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2.5 | Timber lagging | Technical Specification cl. 2.5.1 | Visual | To be SG8 H4 with cut surfaces treated with Metalex | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.6 | Timber lagging fixings | Technical Specification cl. 2.5.1 | - | All fixings to be stainless steel | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.7 | Lagging thickness | Drawings C03 & C04 | Visual | Height from top of wall: 0.0 - 1.6m = 100mm thick ; greater than 1.6m = 200mm thick | On-going | Conform to Contract requirements | Verification | WSP | Verification | Currie
2.8 | Geo-textile | Technical Specification cl. 2.6 | - | A29 required behind timber lagging & around sub-soil drain | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.9 | Drainage composite | Technical Specification cl. 2.7 | - | Filtration Class 1 & Strength Class C - laid over batter slopes | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.1 | Drainage aggregate | Technical Specification cl. 2.8 | - | Free draining clean aggregate with 100% passing 19mm sieve | On-going | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.11 | Retaining wall backfill | Technical Specification cl. 2.9 | Contractor to provide concrete mix design | Sand & cement mix with strength of 1MPa & slump of 350 - 500mm | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
2.12 | Sub-soil drain | Technical Specification cl. 2.10 | - | 150mm Punched HDPe sub-soil pipe | Once | Conform to Contract requirements | Verification | WSP | Supplier docket | Currie
2.13 | Inspection of sub-soil drain | Technical Specification cl. 14 | Contractor must request an inpection by the Engineer of the sub-soil drain before backfilling | - | Once | Conform to Contract requirements | Hold Point | WSP | Site check | Currie
2.14 | Topsoil | Technical Specification cl. 2.11 | Visual | Re-use existing topsoil | Once | Conform to Contract requirements | Verification | WSP | Verification | Currie
2.15 | Testing of materials | Technical Specification cl. 2.13 | Supplied by the Contractor to the Engineer with 3 days of the activity occurring | - | On-going | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
3 | Steelwork Fabrication
3.1 | Shop drawings | Technical Specification cl. 3.2 | To be supplied to the Engineer | - | Once | Conform to Contract requirements | Verification | WSP | Detailed drawing | Currie
3.2 | All piles, walers & accessories | Technical Specification cl. 3.2 | To be inspected by the Engineer before installation | - | Once | Conform to Contract requirements | Hold Point | WSP | Verification | Currie
4 | Piling
4.1 | Pile holes | Technical Specification cl. 4.1 drg C04 | 150UC30 piles in 400mm dia hole, min. 1.5m deep rock socket | Engineer to inspect pile holes before pouring | On-going | Conform to Contract requirements | Hold Point | WSP | Site check | Currie
4.2 | Pile spacing | Technical Specification cl. 4.1 drg C03 | Abutment A: Spacing 1.2m centres | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.3 | Maximum retained height | Technical Specification cl. 4.1 drg C03 & C11 | Abutment A: 2.3m | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.4 | Pile hole augering methodology | Technical Specification cl. 4.1 | Visual check | Hit one, miss one. "Miss" holes only to be augered 24hrs after concreting "hit" holes. | Once | Conform to Contract requirements | Verification | Foreman | Site check | Currie
4.5 | Augered pile holes | Technical Specification cl. 4.2 | Pile logs submitted to engineer by the next day after augering | - | On-going | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
4.6 | Pile hole tolerances | Technical Specification cl. 4.3 | Pole dia. +50mm/0mm, hole plan position +/-20mm. | Tape measure | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.7 | UC post tolerances | Technical Specification cl. 4.3 | Pole vertical alignment not to exceed 2 deg from design alignment, deviation of pole plan line +/-10mm, pole tops +/-10mm, pole base level +/-50mm | String lines and tape measures | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
4.8 | UC post size & treatment | Drg C03 & C04 | 150UC30 ungalvanized | - | Once | Conform to Contract requirements | Verification | WSP | Delivery docket | Currie
4.9 | Concreting UC posts | Technical Specification cl. 2.4.1 & 4.3 | 30MPa concrete | Supplier delivery dockets and laboratory concrete compression test results to be delivered to the engineer | On-going | Conform to Contract requirements | Verification | WSP | Detailed records | Currie
5 | Welding
5.1 | Welds | Technical Specification cl. 6.1 | All welds to be category SP | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
5.2 | Welder qualifications | Technical Specification cl. 6.1 | Welder qualifications to be submitted to the Engineer for approval | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed records | Currie
6 | Concreting
6.1 | Formwork | Technical Specification cl. 7.1 | Formwork to remain in place for 48hrs after pouring | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
6.2 | Concrete workmanship | Technical Specification cl. 7.2 | Concrete to be placed in dry conditions | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
6.3 | Concrete testing | Technical Specification cl. 7.4 | Cylinder test results to be supplied to the Engineer. 1 x 7d + 2 x 28d | - | On-going | Conform to Contract requirements | Verification | WSP | Detailed records | Currie
7 | Crib Wall
7.1 | Pouring no-fines concrete | Technical Specification cl. 8.2 | No-fines to be poured up to the front face of the crib wall | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
8 | Ground Anchors
8.1 | Anchor installation | Technical Specification cl. 9.1 | Contractor to notify Engineer at least 2 days prior to installation & testing | - | On-going | Conform to Contract requirements | Verification | Project manager | Verification | Currie
8.2 | Anchor grout volume | Technical Specification cl. 9.1 | Supply grout volume records for each anchor & submit to engineer | - | On-going | Conform to Contract requirements | Verification | WSP | Grout Log Record | Currie
8.3 | Anchor installation | Technical Specification cl. 9.1 | Hollow bars not to be installed at a rate exceeding 1m per minute | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
8.4 | Loading of anchors | Technical Specification cl. 9.1 | Anchors shall not be loaded for at least 7 days following grouting | - | On-going | Conform to Contract requirements | Verification | WSP | Verification | Currie
8.5 | Anchor testing equipment | Technical Specification cl. 9.2 | Contractor to submit all testing equipment calibration certificates to the Engineer prior to testing | - | Once | Conform to Contract requirements | Verification | Project manager | Detailed records | Currie
8.6 | Anchor test results | Technical Specification cl. 9.2 | Contractor to provide the Engineer with test results within 2 days of testing | - | On-going | Conform to Contract requirements | Verification | Project manager | Detailed records | Currie
8.7 | Sacrificial tests | Technical Specification cl. 9.3 | Abutment A: 1 x sacrificial test | Positions to be agreed with the Engineer & outside of the work area | Once | Conform to Contract requirements | Verification | WSP/Currie | Verification | Currie
8.8 | Production anchors | Technical Specification cl. 9.2 & 9.4 | All production anchors are to be tested & Contractor to provide the Engineer with test records within 2 days of a test | - | On-going | Conform to Contract requirements | Verification | WSP | Anchor Load Test Record | Currie
8.9 | Sacrificial & production anchors | Technical Specification cl. 9.3 | Engineer to witness testing and shall be given at least 2 days notice of testing | - | On-going | Conform to Contract requirements | Hold Point | WSP | Verification | Currie
8.1 | Grout mix design | Technical Specification cl. 9.7 | Contractor to submit a grout mix design to the Engineer for approval at least 1 x week before grouting | - | Once | Conform to Contract requirements | Verification | Project manager | Detailed records | Currie
8.11 | Anchor grout | Technical Specification cl. 9.3, 9.4 & 9.7 | 30MPa required at 28 days and 30MPa before testing | 1no. X 50mm cubes at 7d and 2no. X 50mm cubes at 28d | Once | 30MPa before testing & proven with cube test results prior to testing | Hold Point | WSP/Project manager | Detailed report | Currie
8.12 | Anchor tolerences | Technical Specification cl. 9.6 | Depth of anchor +0.5m/ -0.0m, anchor position +-20mm, plan location +-50mm, orientation 2 degrees | Tape measure & digital spirit level | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
8.13 | Anchor testing | Drg C11 Table 2 | Anchor bar design yield strength: Abutment A: 30/14 bar = 220kN | Hydraulic test jack | Every anchor | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
8.14 | Anchor bar lengths | Drg C11 Table 2 | Abutment A: GA1 - GA6 = 3.0m unbonded & min. 3.0m rock socket | Abutment A: GA1 - GA6 = 30/14 anchor at 1.2m centres | On-going | Conform to Contract requirements | Verification | WSP | Anchor Log Record | Currie
8.15 | Anchor bar couplers, nuts & washers | All hot dip galvanized | - | - | Once | Conform to Contract requirements | Verification | WSP | Site check | Currie
9 | Earthworks
9.1 | Site sourced material | Technical Specification cl. 10.3 | Site sourced to be used for all backfilling EXCEPT for behind the retaining walls | - | On-going | Conform to Contract requirements | Verification | WSP | Visual | Currie
9.2 | Compaction layer thickness | Technical Specification cl. 10.3 | Compaction to be in loose layers not exceeding 300mm | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
9.3 | Rip rap top-up in front of existing bridge piles & new retaining wall | Drg C01 | Rip rap to be site won | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
9.4 | Centre pier rip rap protection | Drg C01 | Rip rap to be site won | - | On-going | Conform to Contract requirements | Verification | WSP | Site check | Currie
10 | COMPLETION
10.1 | Remove erosion and sediment control measures | Remove once planting has taken | - | - | Once | According to Environmental Management Plan | Verification | Foreman | Photo | Currie
10.2 | Remove Traffic Control | Safety | - | - | Once | According to TMP | Verification | Supervisor | Photo | Currie | -
10.3 | Site maintained in a tidy state during construction | Best as is reasonably practicable | - | - | Daily | - | Verification | Supervisor | Photo | Currie | -
10.4 | Practical Completion Inspection | Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a) | Engineer to inspect site on completion of physical works | - | Once | Supply as-built drawings & PS3 | Hold Point | WSP | Inspection record | Currie/WSP
10.5 | Inspect site 12 months after completion | Remedy agreed defects | - | - | Once | - | Verification | WSP | Site Inspection | Currie/WSP