## Mangatokerau
Inspection and Test Plan (ITP)
Mangatokerau Bridge Scour Protection, Paroa Road RP1.1
Dispatch:
WO:
Item | Activity Description | Specification | Verification Activity | Methods or reference | Frequency | Acceptance criteria | Inspection Type | Assessor | Reports to be delivered | Responsible Person | Records/ Remarks Sign and date if appropriate
1 | DELIVERABLES
1.1 | Prestart handover meeting | - | - | Meeting agender items | Once | Prior to commencement of physical works | Internal meeting | Project Manager | Attendance record | Currie
1.2 | Construction Methodology | Letter of Award | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.3 | Monthly Health & Safety Reports | Special Conditions of Contract cl. 5.7.15 | - | - | Monthly | Conform to Contract requirements | Verification | WSP | Detailed record | Currie
1.4 | Health & Safety Management Plan | Special Conditions of Contract cl. 5.17.1 | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.5 | Site Specific Risk Assessment | Special Conditions of Contract cl. 5.17.1 | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.6 | Quality Management Plan | Special Conditions of Contract cl. 5.18.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie
1.7 | Enviromental Management Plan | Special Conditions of Contract cl. 5.22.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie
1.8 | Erosion & Sediment Control Plan | Letter of Award | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.9 | Proof of Insurance | Special Conditions of Contract cl. 8.1.1 | Insurer confirmation certificates | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.1 | Construction Programme | Special Conditions of Contract cl. 5.10.5 & 6 | - | - | Once for approval , then updated weekly | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie
1.11 | Building Consent Exemption | Technical Specification cl. 1.6.1 | - | - | Once | Prior to commencement of physical works | Hold Point | WSP | Detailed record | WSP
1.11 | Service Locates | - | Service providers including Before You Dig & close approach agreement | Expose & protect existing services | Once | Prior to commencement of physical works | Hold Point | Project Manager | Service details | Currie
1.12 | AP40/65 Backfill Material & Road Layerworks | Technical Specification cl. 2 | Check suitability for backfilling PSD, crushing resistence, grading & linear shrinkage | Quarry aggregate laboratory test results | Once | Conform to specification | Hold Point | WSP | Geotech engineer record | Currie
1.13 | Construction methodology | Letter of Award | - | - | Once | Conform to specification | Hold Point | WSP | Detail record | Currie
1.13 | Rock rip rap | Technical Specification cl. 2.8 | Check specific gravity | Quarry aggregate laboratory test results | Once | Conform to specification | Hold Point | WSP | Geotech engineer record | Currie
1.13 | Concrete mix designs for piles, deadman wall & precast panels | Technical Specification cl. 2.5.2 | - | - | Once | Conform to specification | Hold Point | WSP | Supplier design record | Currie
1.13 | All steel Mill Certificates | Technical Specification cl. 2.5.1 | Grade 300 for structural steel, grade 500E for reinforcement & ductbility Class E for anchors | Supplier Mill Certificates | 1 x Week prior to incorporation into works | Conform to specification | Hold Point | WSP | Detailed record | Currie
1.13 | Welding structural steel | - | Welder's welding certificate & experience | - | Once | Conform to specification | Verification | WSP | Detailed record | Currie
1.14 | Traffic Management Plan | Special Conditions of Contract cl. 5.19.1 | - | GDC Generic TMP to be used with some site specific diagrams added | Once | Conform to Contract requirements | Verification | GDC | Detailed record | Currie
2 | Hold & Witness Points
2.1 | Set-out inspection | Technical Specification cl. 2 | To be confirmed with Engineer on-site | - | Once | In accordance with specification and drawings | Hold Point | WSP/Supervisor | Visual | Currie/WSP
2.2 | Installation of sheet piles | Technical Specification cl. 2 | Engineer to witness start of installation on-site | - | Once | In accordance with specification and drawings | Witness Point | WSP/Supervisor | Visual | Currie/WSP
2.3 | Backfilling behind wall | Technical Specification cl. 2 | Engineer to witness start of backfilling | - | Once | In accordance with specification and drawings | Witness Point | WSP/Supervisor | Visual | Currie/WSP
2.4 | Installation of walers, tie rods, bolts/nuts | Technical Specification cl. 2 | Engineer to inspect installation of components | - | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie/WSP
3 | Earthworks
3.1 | Site clearance | Techinical Specification cl. 3.2 | - | Engineer to advise on what vegetation should be taken to spoil | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie
3.2 | Cut or undercut | Techinical Specification cl. 3.3 | - | Cut material that is not required shall be carted to waste unless directed by the Engineer | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
3.3 | Batter slopes | Drg C04 and C05 | - | Batter slopes to be finished to 2H : 1V slope | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
3.4 | TTM | Techinical Specification cl. 3.5 | - | Contractor to provide TTM so the site is safe for road users & pedestrians | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
4 | Retaining Wall
4.1 | Sheet piles | Techinical Specification cl. 4.3 | Supply Mill Certificates | Sheet piles to be grade 390 steel | Once | In accordance with specification and drawings | Verification | WSP | Supplier docket | Currie
4.2 | All tie rods, couplers, washers, nuts and walers | Techinical Specification cl. 4.3 | - | All to be hot dip galvanised | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
5 | Granular Backfill
5.1 | Backfilling to rear of wall | Techinical Specification cl. 5 | - | To be AP65 | On-going | In accordance with specification and drawings | Verification | WSP | Supplier docket | Currie
5.2 | Backfilling to rear of wall | Techinical Specification cl. 5 | Compacted in 200mm compacted layers & compact to 95% MDD or Clegg Hammer CIV ≥32 & ave. CIV35 | NDM testing or Clegg Hammer | NDM testing every 400mm thick with 1no. Test per 10m2 or Clegg Hammer every 200mm layer with 1no test per 5m2 | In accordance with specification and drawings | Verification | WSP | Compaction test record sheet | Currie
6 | Rock Rip Rap
6.1 | Rock rip rap | Technical Specification cl. 6 | Crushing resistance ≥150Kn, UCS ≥ 30MPA, Solid density ≥2.6t/m³, Weathering index AA or AB, Point load strength ≥1.5MPa, Water absorption ≤2% | Quarry aggregate laboratory test results | Submit records at least 1 week prior to placing rock | In accordance with specification and drawings | Verification | WSP | Quarry material test record | Currie
6.2 | Rip rap grading | Techinical Specification cl. 6.1 | D50 800mm (50% passing 800mm) | - | On-going | In accordance with specification and drawings | Verification | WSP | Delivery dockets | Currie
6.3 | Slope finish | Drg C04 & C05 | Finished surface slope to be 2H : 1V | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7 | Sheetpile Wall
7.1 | Welding of sheetpiles | Techinical Specification cl. 7.1 | All welding to be Category SP | Welding to be inspected by a welding inspector | Once | In accordance with specification and drawings | Verification | WSP | Welding inspection report | Currie
7.2 | Construction of sheetpile wall | Techinical Specification cl. 7.2 | Deviation of pile centreline: +/- 10mm; Pile top reduced level: +/- 10mm; Pile base reduced level: +/- 50mm | Tape measure | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.3 | Temporary works | Techinical Specification cl. 7.3 | Sheetpile bench not to exceed 4m wide with batter slope not exceeding 60 degrees | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.4 | Removal of roots | Techinical Specification cl. 7.3 | If roots are encountered, they are to be removed by cutting them out & not by ripping them out | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.5 | Geo-textile under rip rap | Techinical Specification cl. 7.7 | Use A19 geo-textile with minimum laps of 500mm | Tape measure | On-going | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie
8 | Steelwork
8.1 | All steelwork | Techinical Specification cl. 8 | Mill Certificate | Steelwork to be grade 300 | Once | In accordance with specification and drawings | Verification | WSP | Supplier docket | Currie
8.2 | Welding | Techinical Specification cl. 8 | Welding inspector | Welds to be Class SP & 6mm continuous fillet welds | On-going | In accordance with specification and drawings | Verification | WSP | Welding inspection report | Currie
8.3 | All bolts, nuts, washers, couplers, tie bars & walers | Techinical Specification cl. 8 | Walers galvanised to HDG600 | Visual | Once | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie
8.4 | Bolt thread | Techinical Specification cl. 8 | At least one full thread to be exposed beyond all nuts & at least one washer to be used under each nut | Visual | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
9 | Pavement
9.1 | Road sub-grade inspection/testing | Techinical Specification cl. 9 | Scala's taken at 5m c/c to 1.0m deep & submitted to Engineer prior to commencement of pavement works | Scala's | Once | In accordance with specification and drawings | Hold Point | WSP | Scala test records | Currie
9.2 | Sub-base | Techinical Specification cl. 9 | 250mm Thick AP65 | Visual | Once | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie
9.3 | Basecourse | Techinical Specification cl. 9 | 100mm Thick AP40 | Visual | Once | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie
9.4 | Seal | Techinical Specification cl. 9 | Grade 3/5 wet lock 2-coat | Visual | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
9.5 | Testing of layerworks | Techinical Specification cl. 9 | 2no. NDM tests per layer | Troxler | Once | In accordance with specification and drawings | Verification | WSP | Lab test record | Currie
6.6 | Concrete curing | - | Curing compound to be applied to concrete surface following removal of formwork | Paint-on | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
6.7 | Concrete repairs | Techinical Specification cl. 6.1 | Any concrete repairs to be patched with Sika Monotop 438-R | - | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
6.8 | Reinforcing lap lengths | Techinical Specification cl. 6.2 | HD16 for 40MPa concrete: 635mm or X 1.3 = 825mm | Staggered whenever possible | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
6.9 | Concrete workmanship | Techinical Specification cl. 6.3 | Cast concrete in dry weather & have protection materials should they be necessary | - | On-going | In accordance with specification and drawings | Verification | Foreman | Weather check | Currie
7 | Precast Concrete Panels
7.1 | Concrete strength | Techinical Specification cl. 2.5.2 | 40MPa required at 28 days | 1no. Cylinder at 7 days & 2 no. cylinders at 28 days & 1no. slump test - each per 10m3 concrete | On-going & provided by certified concrete supplier | In accordance with specification and drawings | Hold Point | WSP | Detailed report | Currie
7.2 | Concrete cover | Techinical Specification cl. 2.5.2 | 75mm Cover for all surfaces in contact with soil otherwise, 45mm elsewhere | Visual | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.3 | Pre-pour inspection | 2 Days notice requesting inspection by engineer required | - | - | Once | In accordance with specification and drawings | Hold Point | WSP | Site check | Currie
7.4 | Concrete strength before backfilling | Techinical Specification cl. 7.2 | Wait at least 3 days after pouring or 30MPa before backfilling against panels | Cylinder test results | On-going | In accordance with specification and drawings | Verification | WSP | Detailed record | Currie
7.5 | Concrete curing | - | Curing compound to be applied to concrete surface following removal of formwork | Paint-on | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.6 | Concrete repairs | Techinical Specification cl. 6.1 | Any concrete repairs to be patched with Sika Monotop 438-R | - | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.7 | Reinforcing lap lengths | Techinical Specification cl. 6.2 | HD16 for 40MPa concrete: 635mm or X 1.3 = 825mm | Staggered whenever possible | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
7.8 | Concrete workmanship | Techinical Specification cl. 6.3 | Cast concrete in dry weather & have protection materials should they be necessary | - | On-going | In accordance with specification and drawings | Verification | Foreman | Weather check | Currie
8 | Abutment Wingwalls
8.1 | Concrete strength | Techinical Specification cl. 2.5.2 | 40MPa required at 28 days | 1no. Cylinder at 7 days & 2 no. cylinders at 28 days & 1no. slump test - each per 10m3 concrete | On-going & taken on-site | In accordance with specification and drawings | Hold Point | WSP | Detailed report | Currie
8.2 | Concrete cover | Techinical Specification cl. 2.5.2 | 75mm Cover for all surfaces in contact with soil otherwise, 45mm elsewhere | Visual | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie
8.3 | Drilled holes for dowels | Techinical Specification cl. 8 | Drilled holes to be cleaned before chemical applied | Visual | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie
9 | General Earthworks
9.1 | Excavation down to design level | Techinical Specification cl. 9.2 | Once excavated down to design level, call Engineer out for inspection | - | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie
10 | Backfilling
10.1 | Site sourced controlled bulk fill | Techinical Specification cl. 2.7 | Site sourced to be selected and approved by the Engineer | - | On-going | All material passing 100mm sieve & less than 10% passing 75 micron | Hold Point | WSP | Visual | Currie
10.2 | Imported controlled bulk fill | Techinical Specification cl. 2.7 | Only used when "Site Sourced" runs out | - | On-going | All material passing 100mm sieve & less than 10% passing 75 micron | Verification | WSP | Visual | Currie
10.3 | Backilling | Techinical Specification cl. 9.4 | Compacted in 300mm loose layers & compact to Clegg Hammer CIV ≥25 & ave. CIV35 | Clegg Hammer testing at 1no per 2m2 & submitted to Engineer with 48hrs of testing | Every 900mm loose layers | In accordance with specification and drawings | Verification | WSP | Test record | Currie
10.4 | Compaction against concrete | Techinical Specification cl. 9.4 | No compaction to be undertaken within 0.5m of the deadman wall & precast concrete panels | - | On-going | - | Verification | WSP | Visual | Currie
10.5 | Geo-textile behind precast panelled wall | Techinical Specification cl. 2.6 & 9.5 | Laid behind panelled wall & 300mm up cut slope | - | Once | Class C geo-textile equivelent to A29 | Verification | WSP | Supplier docket | Currie
11 | Rock Rip Rap
11.1 | Set-out | Techinical Specification cl. 9.7 | Engineer to confirm set-out with Contractor | Inspection | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie
11.2 | Rock placement | Techinical Specification cl. 9.7 | Rocks to be placed with a 3-pint bearing | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
11.3 | Slope finish | Techinical Specification cl. 9.7 | Finished slope profile not to vary from design profile by more than 500mm | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie
11.4 | Geo-textile under rip rap | Techinical Specification cl. 2.6 & 9.5 | - | - | Once | Class E geo-textile equivelent to A49 | Verification | WSP | Supplier docket | Currie
12 | Topsoil
12.1 | Topsoil thickness | Techinical Specification cl. 9.6 | 100m Thick topsoil laid over all fill areas except under bridge | Inspection | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
12.2 | Grass seed used | Techinical Specification cl. 9.6 | Grass seed mix to be approved by Engineer | - | Once | In accordance with specification and drawings | Hold Point | WSP | Detailed record | Currie
12.3 | Hessian mattress laid over topsoil | Techinical Specification cl. 2.12 & 9.7 | Shall be 100% biodegradable of ≥ 600 gsm min laps of 100mm, pinned with ground staples @ 500mm spacing with at least 200mm long staples | - | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie
13 | Pavement Construction
13.1 | Road sub-grade inspection/testing | Techinical Specification cl. 10.1.2 | Engineer to inspect sub-grade before constructing sub-base layer | - | Once | In accordance with specification and drawings | Hold Point | WSP | Site check | Currie
13.2 | Road sub-base | Techinical Specification cl. 2.13 & 10.1.3 | Locally sourced AP65 | - | 1no. Clegg Hammer test every 2m² | Compact in 200mm layer & compact to Clegg Hammer CIV ≥25 & ave. CIV40 | Verification | WSP | Detailed report | Currie
14.2 | Road basecourse | Techinical Specification cl. 2.14 & 10.1.3 | Locally sourced AP40 | - | 1no. Clegg Hammer test every 2m² | Compact in 100mm layers & compact to Clegg Hammer CIV ≥25 & ave. CIV40 | Verification | WSP | Detailed report | Currie
14 | Site Rail
14.1 | Posts | Techinical Specification cl. 2.15 & 10.2 | 100 x 100mm H5 treated square sections 1.20m long. Posts to be 550mm in the ground | - | Once | In accordance with specification and drawings | Verification | WSP | Site check | Currie
14.2 | Post spacing | Techinical Specification cl. 10.2 | 1.0m centres | - | Once | In accordance with specification and drawings | Verification | WSP | Site check | Currie
14.3 | Horizontal rails | Techinical Specification cl. 2.15 & 10.2 | 50 x 200mm H3 treated timber. | - | Once | In accordance with specification and drawings | Verification | WSP | Site check | Currie
14.4 | Entire site rail timber | Techinical Specification cl. 10.2 | 2-Coats of "bright white" gloss exterior paint on all faces | - | Once | In accordance with specification and drawings | Verification | WSP | Site check | Currie
14.5 | Fixings | - | M12 grade 8.8 HD galv. bolts | - | Once | In accordance with specification and drawings | Verification | WSP | Site check | Currie
10 | COMPLETION
10.1 | Remove erosion and sediment control measures | Remove once planting has taken | - | - | Once | According to Environmental Management Plan | Verification | Foreman | Photo | Currie
10.2 | Remove Traffic Control | Safety | - | - | Once | According to TMP | Verification | Supervisor | - | Currie | -
10.3 | Site maintained in a tidy state during construction | Best as is reasonably practicable | - | - | Daily | - | Verification | Supervisor | Photo | Currie | -
10.4 | Practical Completion Inspection | Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a) | Engineer to inspect site on completion of physical works | - | Once | Supply as-built drawings & PS3 | Hold Point | WSP | Inspection record | Currie/WSP
10.5 | Inspect site 12 months after completion | Specific Conditions of Contract cl. 11.1 | - | - | Once | - | Verification | WSP | Site Inspection | Currie/WSP