## Sheet1
1.1 | Prestart handover meeting | - | - | Meeting agender items | Once | Prior to commencement of physical works | Internal meeting | Project Manager | Attendance record | Currie | 1.1 - Prestart handover meeting | Specification - - | Verification Activity - - | Methods or reference - Meeting agender items | Frequency - Once | Acceptance criteria - Prior to commencement of physical works | Inspection Type - Internal meeting | Assessor - Project Manager | Reports to be delivered - Attendance record | Responsible Person - Currie | 1.1 - Prestart handover meeting
1.2 | Construction Methodology | Letter of Award | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie | 1.2 - Construction Methodology | Specification - Letter of Award | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - Conform to Contract requirements | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Specification - -
1.3 | Monthly Health CHAR(AMP) Safety Reports | Special Conditions of Contract cl. 5.7.15 | - | - | Monthly | Conform to Contract requirements | Verification | WSP | Detailed record | Currie | 1.3 - Monthly Health CHAR(AMP) Safety Reports | Specification - Special Conditions of Contract cl. 5.7.15 | Verification Activity - - | Methods or reference - - | Frequency - Monthly | Acceptance criteria - Conform to Contract requirements | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Verification Activity - -
1.4 | Health CHAR(AMP) Safety Management Plan | Special Conditions of Contract cl. 5.17.1 | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie | 1.4 - Health CHAR(AMP) Safety Management Plan | Specification - Special Conditions of Contract cl. 5.17.1 | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - Conform to Contract requirements | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Methods or reference - Meeting agender items
1.5 | Site Specific Risk Assessment | Special Conditions of Contract cl. 5.17.1 | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie | 1.5 - Site Specific Risk Assessment | Specification - Special Conditions of Contract cl. 5.17.1 | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - Conform to Contract requirements | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Frequency - Once
1.6 | Quality Management Plan | Special Conditions of Contract cl. 5.18.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie | 1.6 - Quality Management Plan | Specification - Special Conditions of Contract cl. 5.18.1 | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - Deemed as submitted under Panel Agreement | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Acceptance criteria - Prior to commencement of physical works
1.7 | Enviromental Management Plan | Special Conditions of Contract cl. 5.22.1 | - | - | Once | Deemed as submitted under Panel Agreement | Verification | WSP | Detailed record | Currie | 1.7 - Enviromental Management Plan | Specification - Special Conditions of Contract cl. 5.22.1 | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - Deemed as submitted under Panel Agreement | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Inspection Type - Internal meeting
1.8 | Erosion CHAR(AMP) Sediment Control Plan | Letter of Award | - | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie | 1.8 - Erosion CHAR(AMP) Sediment Control Plan | Specification - Letter of Award | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - Conform to Contract requirements | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Assessor - Project Manager
1.9 | Proof of Insurance | Special Conditions of Contract cl. 8.1.1 | Insurer confirmation certificates | - | Once | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie | 1.9 - Proof of Insurance | Specification - Special Conditions of Contract cl. 8.1.1 | Verification Activity - Insurer confirmation certificates | Methods or reference - - | Frequency - Once | Acceptance criteria - Conform to Contract requirements | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Reports to be delivered - Attendance record
1.1 | Construction Programme | Special Conditions of Contract cl. 5.10.5 CHAR(AMP) 6 | - | - | Once for approval , then updated weekly | Conform to Contract requirements | Hold Point | WSP | Detailed record | Currie | 1.1 - Construction Programme | Specification - Special Conditions of Contract cl. 5.10.5 CHAR(AMP) 6 | Verification Activity - - | Methods or reference - - | Frequency - Once for approval , then updated weekly | Acceptance criteria - Conform to Contract requirements | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Responsible Person - Currie
1.11 | Service Locates | - | Service providers including Before You Dig CHAR(AMP) close approach agreement | Expose CHAR(AMP) protect existing services | Once | Prior to commencement of physical works | Hold Point | Project Manager | Service details | Currie | 1.11 - Service Locates | Specification - - | Verification Activity - Service providers including Before You Dig CHAR(AMP) close approach agreement | Methods or reference - Expose CHAR(AMP) protect existing services | Frequency - Once | Acceptance criteria - Prior to commencement of physical works | Inspection Type - Hold Point | Assessor - Project Manager | Reports to be delivered - Service details | Responsible Person - Currie | 1.2 - Construction Methodology
1.12 | AP40/65 Backfill Material CHAR(AMP) Road Layerworks | Technical Specification cl. 2 | Check suitability for backfilling PSD, crushing resistence, grading CHAR(AMP) linear shrinkage | Quarry aggregate laboratory test results | Once | Conform to specification | Hold Point | WSP | Geotech engineer record | Currie | 1.12 - AP40/65 Backfill Material CHAR(AMP) Road Layerworks | Specification - Technical Specification cl. 2 | Verification Activity - Check suitability for backfilling PSD, crushing resistence, grading CHAR(AMP) linear shrinkage | Methods or reference - Quarry aggregate laboratory test results | Frequency - Once | Acceptance criteria - Conform to specification | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Geotech engineer record | Responsible Person - Currie | Specification - Letter of Award
1.13 | Welding structural steel | - | Welder's welding certificate CHAR(AMP) experience | - | Once | Conform to specification | Verification | WSP | Detailed record | Currie | 1.13 - Welding structural steel | Specification - - | Verification Activity - Welder's welding certificate CHAR(AMP) experience | Methods or reference - - | Frequency - Once | Acceptance criteria - Conform to specification | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Detailed record | Responsible Person - Currie | Verification Activity - -
1.14 | Traffic Management Plan | Special Conditions of Contract cl. 5.19.1 | - | GDC Generic TMP to be used with some site specific diagrams added | Once | Conform to Contract requirements | Verification | GDC | Detailed record | Currie | 1.14 - Traffic Management Plan | Specification - Special Conditions of Contract cl. 5.19.1 | Verification Activity - - | Methods or reference - GDC Generic TMP to be used with some site specific diagrams added | Frequency - Once | Acceptance criteria - Conform to Contract requirements | Inspection Type - Verification | Assessor - GDC | Reports to be delivered - Detailed record | Responsible Person - Currie | Methods or reference - -
2.1 | Set-out inspection | Technical Specification cl. 2 | To be confirmed with Engineer on-site | - | Once | In accordance with specification and drawings | Hold Point | WSP/Supervisor | Visual | Currie/WSP | 2.1 - Set-out inspection | Specification - Technical Specification cl. 2 | Verification Activity - To be confirmed with Engineer on-site | Methods or reference - - | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Hold Point | Assessor - WSP/Supervisor | Reports to be delivered - Visual | Responsible Person - Currie/WSP | Frequency - Once
2.2 | Installation of sheet piles | Technical Specification cl. 2 | Engineer to witness start of installation on-site | - | Once | In accordance with specification and drawings | Witness Point | WSP/Supervisor | Visual | Currie/WSP | 2.2 - Installation of sheet piles | Specification - Technical Specification cl. 2 | Verification Activity - Engineer to witness start of installation on-site | Methods or reference - - | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Witness Point | Assessor - WSP/Supervisor | Reports to be delivered - Visual | Responsible Person - Currie/WSP | Acceptance criteria - Conform to Contract requirements
2.3 | Backfilling behind wall | Technical Specification cl. 2 | Engineer to witness start of backfilling | - | Once | In accordance with specification and drawings | Witness Point | WSP/Supervisor | Visual | Currie/WSP | 2.3 - Backfilling behind wall | Specification - Technical Specification cl. 2 | Verification Activity - Engineer to witness start of backfilling | Methods or reference - - | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Witness Point | Assessor - WSP/Supervisor | Reports to be delivered - Visual | Responsible Person - Currie/WSP | Inspection Type - Hold Point
2.4 | Installation of walers, tie rods, bolts/nuts | Technical Specification cl. 2 | Engineer to inspect installation of components | - | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie/WSP | 2.4 - Installation of walers, tie rods, bolts/nuts | Specification - Technical Specification cl. 2 | Verification Activity - Engineer to inspect installation of components | Methods or reference - - | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie/WSP | Assessor - WSP
3.1 | Site clearance | Techinical Specification cl. 3.2 | - | Engineer to advise on what vegetation should be taken to spoil | Once | In accordance with specification and drawings | Hold Point | WSP | Visual | Currie | 3.1 - Site clearance | Specification - Techinical Specification cl. 3.2 | Verification Activity - - | Methods or reference - Engineer to advise on what vegetation should be taken to spoil | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Reports to be delivered - Detailed record
3.2 | Cut or undercut | Techinical Specification cl. 3.3 | - | Cut material that is not required shall be carted to waste unless directed by the Engineer | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 3.2 - Cut or undercut | Specification - Techinical Specification cl. 3.3 | Verification Activity - - | Methods or reference - Cut material that is not required shall be carted to waste unless directed by the Engineer | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Responsible Person - Currie
3.3 | Batter slopes | Drg C04 and C05 | - | Batter slopes to be finished to 2H : 1V slope | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 3.3 - Batter slopes | Specification - Drg C04 and C05 | Verification Activity - - | Methods or reference - Batter slopes to be finished to 2H : 1V slope | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | 1.3 - Monthly Health CHAR(AMP) Safety Reports
3.4 | TTM | Techinical Specification cl. 3.5 | - | Contractor to provide TTM so the site is safe for road users CHAR(AMP) pedestrians | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 3.4 - TTM | Specification - Techinical Specification cl. 3.5 | Verification Activity - - | Methods or reference - Contractor to provide TTM so the site is safe for road users CHAR(AMP) pedestrians | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Specification - Special Conditions of Contract cl. 5.7.15
4.1 | Sheet piles | Techinical Specification cl. 4.3 | Supply Mill Certificates | Sheet piles to be grade 390 steel | Once | In accordance with specification and drawings | Verification | WSP | Supplier docket | Currie | 4.1 - Sheet piles | Specification - Techinical Specification cl. 4.3 | Verification Activity - Supply Mill Certificates | Methods or reference - Sheet piles to be grade 390 steel | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier docket | Responsible Person - Currie | Verification Activity - -
4.2 | All tie rods, couplers, washers, nuts and walers | Techinical Specification cl. 4.3 | - | All to be hot dip galvanised | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 4.2 - All tie rods, couplers, washers, nuts and walers | Specification - Techinical Specification cl. 4.3 | Verification Activity - - | Methods or reference - All to be hot dip galvanised | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Methods or reference - -
5.1 | Backfilling to rear of wall | Techinical Specification cl. 5 | - | To be AP65 | On-going | In accordance with specification and drawings | Verification | WSP | Supplier docket | Currie | 5.1 - Backfilling to rear of wall | Specification - Techinical Specification cl. 5 | Verification Activity - - | Methods or reference - To be AP65 | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier docket | Responsible Person - Currie | Frequency - Monthly
5.2 | Backfilling to rear of wall | Techinical Specification cl. 5 | Compacted in 200mm compacted layers CHAR(AMP) compact to 95% MDD or Clegg Hammer CIV ≥32 CHAR(AMP) ave. CIV35 | NDM testing or Clegg Hammer | NDM testing every 400mm thick with 1no. Test per 10m2 or Clegg Hammer every 200mm layer with 1no test per 5m2 | In accordance with specification and drawings | Verification | WSP | Compaction test record sheet | Currie | 5.2 - Backfilling to rear of wall | Specification - Techinical Specification cl. 5 | Verification Activity - Compacted in 200mm compacted layers CHAR(AMP) compact to 95% MDD or Clegg Hammer CIV ≥32 CHAR(AMP) ave. CIV35 | Methods or reference - NDM testing or Clegg Hammer | Frequency - NDM testing every 400mm thick with 1no. Test per 10m2 or Clegg Hammer every 200mm layer with 1no test per 5m2 | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Compaction test record sheet | Responsible Person - Currie | Acceptance criteria - Conform to Contract requirements
6.1 | Rock rip rap | Technical Specification cl. 6 | Crushing resistance ≥150Kn, UCS ≥ 30MPA, Solid density ≥2.6t/m³, Weathering index AA or AB, Point load strength ≥1.5MPa, Water absorption ≤2% | Quarry aggregate laboratory test results | Submit records at least 1 week prior to placing rock | In accordance with specification and drawings | Verification | WSP | Quarry material test record | Currie | 6.1 - Rock rip rap | Specification - Technical Specification cl. 6 | Verification Activity - Crushing resistance ≥150Kn, UCS ≥ 30MPA, Solid density ≥2.6t/m³, Weathering index AA or AB, Point load strength ≥1.5MPa, Water absorption ≤2% | Methods or reference - Quarry aggregate laboratory test results | Frequency - Submit records at least 1 week prior to placing rock | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Quarry material test record | Responsible Person - Currie | Inspection Type - Verification
6.2 | Rip rap grading | Techinical Specification cl. 6.1 | D50 800mm (50% passing 800mm) | - | On-going | In accordance with specification and drawings | Verification | WSP | Delivery dockets | Currie | 6.2 - Rip rap grading | Specification - Techinical Specification cl. 6.1 | Verification Activity - D50 800mm (50% passing 800mm) | Methods or reference - - | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Delivery dockets | Responsible Person - Currie | Assessor - WSP
6.3 | Slope finish | Drg C04 CHAR(AMP) C05 | Finished surface slope to be 2H : 1V | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 6.3 - Slope finish | Specification - Drg C04 CHAR(AMP) C05 | Verification Activity - Finished surface slope to be 2H : 1V | Methods or reference - - | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Reports to be delivered - Detailed record
7.1 | Welding of sheetpiles | Techinical Specification cl. 7.1 | All welding to be Category SP | Welding to be inspected by a welding inspector | Once | In accordance with specification and drawings | Verification | WSP | Welding inspection report | Currie | 7.1 - Welding of sheetpiles | Specification - Techinical Specification cl. 7.1 | Verification Activity - All welding to be Category SP | Methods or reference - Welding to be inspected by a welding inspector | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Welding inspection report | Responsible Person - Currie | Responsible Person - Currie
7.2 | Construction of sheetpile wall | Techinical Specification cl. 7.2 | Deviation of pile centreline: +/- 10mm; Pile top reduced level: +/- 10mm; Pile base reduced level: +/- 50mm | Tape measure | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 7.2 - Construction of sheetpile wall | Specification - Techinical Specification cl. 7.2 | Verification Activity - Deviation of pile centreline: +/- 10mm; Pile top reduced level: +/- 10mm; Pile base reduced level: +/- 50mm | Methods or reference - Tape measure | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | 1.4 - Health CHAR(AMP) Safety Management Plan
7.3 | Temporary works | Techinical Specification cl. 7.3 | Sheetpile bench not to exceed 4m wide with batter slope not exceeding 60 degrees | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 7.3 - Temporary works | Specification - Techinical Specification cl. 7.3 | Verification Activity - Sheetpile bench not to exceed 4m wide with batter slope not exceeding 60 degrees | Methods or reference - - | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Specification - Special Conditions of Contract cl. 5.17.1
7.4 | Removal of roots | Techinical Specification cl. 7.3 | If roots are encountered, they are to be removed by cutting them out CHAR(AMP) not by ripping them out | - | On-going | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 7.4 - Removal of roots | Specification - Techinical Specification cl. 7.3 | Verification Activity - If roots are encountered, they are to be removed by cutting them out CHAR(AMP) not by ripping them out | Methods or reference - - | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Verification Activity - -
7.5 | Geo-textile under rip rap | Techinical Specification cl. 7.7 | Use A19 geo-textile with minimum laps of 500mm | Tape measure | On-going | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie | 7.5 - Geo-textile under rip rap | Specification - Techinical Specification cl. 7.7 | Verification Activity - Use A19 geo-textile with minimum laps of 500mm | Methods or reference - Tape measure | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier dockets | Responsible Person - Currie | Methods or reference - -
8.1 | All steelwork | Techinical Specification cl. 8 | Mill Certificate | Steelwork to be grade 300 | Once | In accordance with specification and drawings | Verification | WSP | Supplier docket | Currie | 8.1 - All steelwork | Specification - Techinical Specification cl. 8 | Verification Activity - Mill Certificate | Methods or reference - Steelwork to be grade 300 | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier docket | Responsible Person - Currie | Frequency - Once
8.2 | Welding | Techinical Specification cl. 8 | Welding inspector | Welds to be Class SP CHAR(AMP) 6mm continuous fillet welds | On-going | In accordance with specification and drawings | Verification | WSP | Welding inspection report | Currie | 8.2 - Welding | Specification - Techinical Specification cl. 8 | Verification Activity - Welding inspector | Methods or reference - Welds to be Class SP CHAR(AMP) 6mm continuous fillet welds | Frequency - On-going | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Welding inspection report | Responsible Person - Currie | Acceptance criteria - Conform to Contract requirements
8.3 | All bolts, nuts, washers, couplers, tie bars CHAR(AMP) walers | Techinical Specification cl. 8 | Walers galvanised to HDG600 | Visual | Once | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie | 8.3 - All bolts, nuts, washers, couplers, tie bars CHAR(AMP) walers | Specification - Techinical Specification cl. 8 | Verification Activity - Walers galvanised to HDG600 | Methods or reference - Visual | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier dockets | Responsible Person - Currie | Inspection Type - Hold Point
8.4 | Bolt thread | Techinical Specification cl. 8 | At least one full thread to be exposed beyond all nuts CHAR(AMP) at least one washer to be used under each nut | Visual | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 8.4 - Bolt thread | Specification - Techinical Specification cl. 8 | Verification Activity - At least one full thread to be exposed beyond all nuts CHAR(AMP) at least one washer to be used under each nut | Methods or reference - Visual | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Assessor - WSP
9.1 | Road sub-grade inspection/testing | Techinical Specification cl. 9 | Scala's taken at 5m c/c to 1.0m deep CHAR(AMP) submitted to Engineer prior to commencement of pavement works | Scala's | Once | In accordance with specification and drawings | Hold Point | WSP | Scala test records | Currie | 9.1 - Road sub-grade inspection/testing | Specification - Techinical Specification cl. 9 | Verification Activity - Scala's taken at 5m c/c to 1.0m deep CHAR(AMP) submitted to Engineer prior to commencement of pavement works | Methods or reference - Scala's | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Scala test records | Responsible Person - Currie | Reports to be delivered - Detailed record
9.2 | Sub-base | Techinical Specification cl. 9 | 250mm Thick AP65 | Visual | Once | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie | 9.2 - Sub-base | Specification - Techinical Specification cl. 9 | Verification Activity - 250mm Thick AP65 | Methods or reference - Visual | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier dockets | Responsible Person - Currie | Responsible Person - Currie
9.3 | Basecourse | Techinical Specification cl. 9 | 100mm Thick AP40 | Visual | Once | In accordance with specification and drawings | Verification | WSP | Supplier dockets | Currie | 9.3 - Basecourse | Specification - Techinical Specification cl. 9 | Verification Activity - 100mm Thick AP40 | Methods or reference - Visual | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Supplier dockets | Responsible Person - Currie | 1.5 - Site Specific Risk Assessment
9.4 | Seal | Techinical Specification cl. 9 | Grade 3/5 wet lock 2-coat | Visual | Once | In accordance with specification and drawings | Verification | WSP | Visual | Currie | 9.4 - Seal | Specification - Techinical Specification cl. 9 | Verification Activity - Grade 3/5 wet lock 2-coat | Methods or reference - Visual | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Visual | Responsible Person - Currie | Specification - Special Conditions of Contract cl. 5.17.1
9.5 | Testing of layerworks | Techinical Specification cl. 9 | 2no. NDM tests per layer | Troxler | Once | In accordance with specification and drawings | Verification | WSP | Lab test record | Currie | 9.5 - Testing of layerworks | Specification - Techinical Specification cl. 9 | Verification Activity - 2no. NDM tests per layer | Methods or reference - Troxler | Frequency - Once | Acceptance criteria - In accordance with specification and drawings | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Lab test record | Responsible Person - Currie | Verification Activity - -
10.1 | Remove erosion and sediment control measures | Remove once planting has taken | - | - | Once | According to Environmental Management Plan | Verification | Foreman | Photo | Currie | 10.1 - Remove erosion and sediment control measures | Specification - Remove once planting has taken | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - According to Environmental Management Plan | Inspection Type - Verification | Assessor - Foreman | Reports to be delivered - Photo | Responsible Person - Currie | Methods or reference - -
10.2 | Remove Traffic Control | Safety | - | - | Once | According to TMP | Verification | Supervisor | - | Currie | 10.2 - Remove Traffic Control | Specification - Safety | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - According to TMP | Inspection Type - Verification | Assessor - Supervisor | Reports to be delivered - - | Responsible Person - Currie | Frequency - Once
10.3 | Site maintained in a tidy state during construction | Best as is reasonably practicable | - | - | Daily | - | Verification | Supervisor | Photo | Currie | 10.3 - Site maintained in a tidy state during construction | Specification - Best as is reasonably practicable | Verification Activity - - | Methods or reference - - | Frequency - Daily | Acceptance criteria - - | Inspection Type - Verification | Assessor - Supervisor | Reports to be delivered - Photo | Responsible Person - Currie | Acceptance criteria - Conform to Contract requirements
10.4 | Practical Completion Inspection | Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) CHAR(AMP) 10.4.5 (b)(a) | Engineer to inspect site on completion of physical works | - | Once | Supply as-built drawings CHAR(AMP) PS3 | Hold Point | WSP | Inspection record | Currie/WSP | 10.4 - Practical Completion Inspection | Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) CHAR(AMP) 10.4.5 (b)(a) | Verification Activity - Engineer to inspect site on completion of physical works | Methods or reference - - | Frequency - Once | Acceptance criteria - Supply as-built drawings CHAR(AMP) PS3 | Inspection Type - Hold Point | Assessor - WSP | Reports to be delivered - Inspection record | Responsible Person - Currie/WSP | Inspection Type - Hold Point
10.5 | Inspect site 12 months after completion | Specific Conditions of Contract cl. 11.1 | - | - | Once | - | Verification | WSP | Site Inspection | Currie/WSP | 10.5 - Inspect site 12 months after completion | Specification - Specific Conditions of Contract cl. 11.1 | Verification Activity - - | Methods or reference - - | Frequency - Once | Acceptance criteria - - | Inspection Type - Verification | Assessor - WSP | Reports to be delivered - Site Inspection | Responsible Person - Currie/WSP | Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.6 - Quality Management Plan
Specification - Special Conditions of Contract cl. 5.18.1
Verification Activity - -
Methods or reference - -
Frequency - Once
Acceptance criteria - Deemed as submitted under Panel Agreement
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.7 - Enviromental Management Plan
Specification - Special Conditions of Contract cl. 5.22.1
Verification Activity - -
Methods or reference - -
Frequency - Once
Acceptance criteria - Deemed as submitted under Panel Agreement
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.8 - Erosion CHAR(AMP) Sediment Control Plan
Specification - Letter of Award
Verification Activity - -
Methods or reference - -
Frequency - Once
Acceptance criteria - Conform to Contract requirements
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.9 - Proof of Insurance
Specification - Special Conditions of Contract cl. 8.1.1
Verification Activity - Insurer confirmation certificates
Methods or reference - -
Frequency - Once
Acceptance criteria - Conform to Contract requirements
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.1 - Construction Programme
Specification - Special Conditions of Contract cl. 5.10.5 CHAR(AMP) 6
Verification Activity - -
Methods or reference - -
Frequency - Once for approval , then updated weekly
Acceptance criteria - Conform to Contract requirements
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.11 - Service Locates
Specification - -
Verification Activity - Service providers including Before You Dig CHAR(AMP) close approach agreement
Methods or reference - Expose CHAR(AMP) protect existing services
Frequency - Once
Acceptance criteria - Prior to commencement of physical works
Inspection Type - Hold Point
Assessor - Project Manager
Reports to be delivered - Service details
Responsible Person - Currie
1.12 - AP40/65 Backfill Material CHAR(AMP) Road Layerworks
Specification - Technical Specification cl. 2
Verification Activity - Check suitability for backfilling PSD, crushing resistence, grading CHAR(AMP) linear shrinkage
Methods or reference - Quarry aggregate laboratory test results
Frequency - Once
Acceptance criteria - Conform to specification
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Geotech engineer record
Responsible Person - Currie
1.13 - Welding structural steel
Specification - -
Verification Activity - Welder's welding certificate CHAR(AMP) experience
Methods or reference - -
Frequency - Once
Acceptance criteria - Conform to specification
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Detailed record
Responsible Person - Currie
1.14 - Traffic Management Plan
Specification - Special Conditions of Contract cl. 5.19.1
Verification Activity - -
Methods or reference - GDC Generic TMP to be used with some site specific diagrams added
Frequency - Once
Acceptance criteria - Conform to Contract requirements
Inspection Type - Verification
Assessor - GDC
Reports to be delivered - Detailed record
Responsible Person - Currie
2.1 - Set-out inspection
Specification - Technical Specification cl. 2
Verification Activity - To be confirmed with Engineer on-site
Methods or reference - -
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Hold Point
Assessor - WSP/Supervisor
Reports to be delivered - Visual
Responsible Person - Currie/WSP
2.2 - Installation of sheet piles
Specification - Technical Specification cl. 2
Verification Activity - Engineer to witness start of installation on-site
Methods or reference - -
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Witness Point
Assessor - WSP/Supervisor
Reports to be delivered - Visual
Responsible Person - Currie/WSP
2.3 - Backfilling behind wall
Specification - Technical Specification cl. 2
Verification Activity - Engineer to witness start of backfilling
Methods or reference - -
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Witness Point
Assessor - WSP/Supervisor
Reports to be delivered - Visual
Responsible Person - Currie/WSP
2.4 - Installation of walers, tie rods, bolts/nuts
Specification - Technical Specification cl. 2
Verification Activity - Engineer to inspect installation of components
Methods or reference - -
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie/WSP
3.1 - Site clearance
Specification - Techinical Specification cl. 3.2
Verification Activity - -
Methods or reference - Engineer to advise on what vegetation should be taken to spoil
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
3.2 - Cut or undercut
Specification - Techinical Specification cl. 3.3
Verification Activity - -
Methods or reference - Cut material that is not required shall be carted to waste unless directed by the Engineer
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
3.3 - Batter slopes
Specification - Drg C04 and C05
Verification Activity - -
Methods or reference - Batter slopes to be finished to 2H : 1V slope
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
3.4 - TTM
Specification - Techinical Specification cl. 3.5
Verification Activity - -
Methods or reference - Contractor to provide TTM so the site is safe for road users CHAR(AMP) pedestrians
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
4.1 - Sheet piles
Specification - Techinical Specification cl. 4.3
Verification Activity - Supply Mill Certificates
Methods or reference - Sheet piles to be grade 390 steel
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier docket
Responsible Person - Currie
4.2 - All tie rods, couplers, washers, nuts and walers
Specification - Techinical Specification cl. 4.3
Verification Activity - -
Methods or reference - All to be hot dip galvanised
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
5.1 - Backfilling to rear of wall
Specification - Techinical Specification cl. 5
Verification Activity - -
Methods or reference - To be AP65
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier docket
Responsible Person - Currie
5.2 - Backfilling to rear of wall
Specification - Techinical Specification cl. 5
Verification Activity - Compacted in 200mm compacted layers CHAR(AMP) compact to 95% MDD or Clegg Hammer CIV ≥32 CHAR(AMP) ave. CIV35
Methods or reference - NDM testing or Clegg Hammer
Frequency - NDM testing every 400mm thick with 1no. Test per 10m2 or Clegg Hammer every 200mm layer with 1no test per 5m2
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Compaction test record sheet
Responsible Person - Currie
6.1 - Rock rip rap
Specification - Technical Specification cl. 6
Verification Activity - Crushing resistance ≥150Kn, UCS ≥ 30MPA, Solid density ≥2.6t/m³, Weathering index AA or AB, Point load strength ≥1.5MPa, Water absorption ≤2%
Methods or reference - Quarry aggregate laboratory test results
Frequency - Submit records at least 1 week prior to placing rock
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Quarry material test record
Responsible Person - Currie
6.2 - Rip rap grading
Specification - Techinical Specification cl. 6.1
Verification Activity - D50 800mm (50% passing 800mm)
Methods or reference - -
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Delivery dockets
Responsible Person - Currie
6.3 - Slope finish
Specification - Drg C04 CHAR(AMP) C05
Verification Activity - Finished surface slope to be 2H : 1V
Methods or reference - -
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
7.1 - Welding of sheetpiles
Specification - Techinical Specification cl. 7.1
Verification Activity - All welding to be Category SP
Methods or reference - Welding to be inspected by a welding inspector
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Welding inspection report
Responsible Person - Currie
7.2 - Construction of sheetpile wall
Specification - Techinical Specification cl. 7.2
Verification Activity - Deviation of pile centreline: +/- 10mm; Pile top reduced level: +/- 10mm; Pile base reduced level: +/- 50mm
Methods or reference - Tape measure
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
7.3 - Temporary works
Specification - Techinical Specification cl. 7.3
Verification Activity - Sheetpile bench not to exceed 4m wide with batter slope not exceeding 60 degrees
Methods or reference - -
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
7.4 - Removal of roots
Specification - Techinical Specification cl. 7.3
Verification Activity - If roots are encountered, they are to be removed by cutting them out CHAR(AMP) not by ripping them out
Methods or reference - -
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
7.5 - Geo-textile under rip rap
Specification - Techinical Specification cl. 7.7
Verification Activity - Use A19 geo-textile with minimum laps of 500mm
Methods or reference - Tape measure
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier dockets
Responsible Person - Currie
8.1 - All steelwork
Specification - Techinical Specification cl. 8
Verification Activity - Mill Certificate
Methods or reference - Steelwork to be grade 300
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier docket
Responsible Person - Currie
8.2 - Welding
Specification - Techinical Specification cl. 8
Verification Activity - Welding inspector
Methods or reference - Welds to be Class SP CHAR(AMP) 6mm continuous fillet welds
Frequency - On-going
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Welding inspection report
Responsible Person - Currie
8.3 - All bolts, nuts, washers, couplers, tie bars CHAR(AMP) walers
Specification - Techinical Specification cl. 8
Verification Activity - Walers galvanised to HDG600
Methods or reference - Visual
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier dockets
Responsible Person - Currie
8.4 - Bolt thread
Specification - Techinical Specification cl. 8
Verification Activity - At least one full thread to be exposed beyond all nuts CHAR(AMP) at least one washer to be used under each nut
Methods or reference - Visual
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
9.1 - Road sub-grade inspection/testing
Specification - Techinical Specification cl. 9
Verification Activity - Scala's taken at 5m c/c to 1.0m deep CHAR(AMP) submitted to Engineer prior to commencement of pavement works
Methods or reference - Scala's
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Scala test records
Responsible Person - Currie
9.2 - Sub-base
Specification - Techinical Specification cl. 9
Verification Activity - 250mm Thick AP65
Methods or reference - Visual
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier dockets
Responsible Person - Currie
9.3 - Basecourse
Specification - Techinical Specification cl. 9
Verification Activity - 100mm Thick AP40
Methods or reference - Visual
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Supplier dockets
Responsible Person - Currie
9.4 - Seal
Specification - Techinical Specification cl. 9
Verification Activity - Grade 3/5 wet lock 2-coat
Methods or reference - Visual
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Visual
Responsible Person - Currie
9.5 - Testing of layerworks
Specification - Techinical Specification cl. 9
Verification Activity - 2no. NDM tests per layer
Methods or reference - Troxler
Frequency - Once
Acceptance criteria - In accordance with specification and drawings
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Lab test record
Responsible Person - Currie
10.1 - Remove erosion and sediment control measures
Specification - Remove once planting has taken
Verification Activity - -
Methods or reference - -
Frequency - Once
Acceptance criteria - According to Environmental Management Plan
Inspection Type - Verification
Assessor - Foreman
Reports to be delivered - Photo
Responsible Person - Currie
10.2 - Remove Traffic Control
Specification - Safety
Verification Activity - -
Methods or reference - -
Frequency - Once
Acceptance criteria - According to TMP
Inspection Type - Verification
Assessor - Supervisor
Reports to be delivered - -
Responsible Person - Currie
10.3 - Site maintained in a tidy state during construction
Specification - Best as is reasonably practicable
Verification Activity - -
Methods or reference - -
Frequency - Daily
Acceptance criteria - -
Inspection Type - Verification
Assessor - Supervisor
Reports to be delivered - Photo
Responsible Person - Currie
10.4 - Practical Completion Inspection
Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) CHAR(AMP) 10.4.5 (b)(a)
Verification Activity - Engineer to inspect site on completion of physical works
Methods or reference - -
Frequency - Once
Acceptance criteria - Supply as-built drawings CHAR(AMP) PS3
Inspection Type - Hold Point
Assessor - WSP
Reports to be delivered - Inspection record
Responsible Person - Currie/WSP
10.5 - Inspect site 12 months after completion
Specification - Specific Conditions of Contract cl. 11.1
Verification Activity - -
Methods or reference - -
Frequency - Once
Acceptance criteria - -
Inspection Type - Verification
Assessor - WSP
Reports to be delivered - Site Inspection
Responsible Person - Currie/WSP