## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Mangaheia No.3 Bridge - Tauwhareparae Road RP17.7 | itp
section | 1.0 - DELIVERABLES
checkpoint | 1.1 - Prestart handover meeting
label | Methods or reference - Meeting agender items
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Internal meeting
label | Assessor - Project Manager
label | Reports to be delivered - Attendance record
label | Responsible Person - Currie
checkpoint | 1.2 - Construction Methodology
label | Specification - Letter of Award
label | Frequency - Once
label | Acceptance criteria - Approved by ER prior to commencement of physical works
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.3 - Construction Programme
label | Specification - Special Conditions of Contract cl. 5.10.4 and Letter of Award
label | Methods or reference - MS Project format
label | Frequency - Updated weekly
label | Acceptance criteria - Conform to contract requirement
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.4 - Site Specific Risk Assessment
label | Specification - Special Conditions of Contract cl. 5.17.1
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.5 - Health & Safety Management Plan
label | Specification - Special Conditions of Contract cl. 5.17.1 and Letter of Award
label | Frequency - Once
label | Acceptance criteria - Conform to contract requirement
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.6 - Monthly Health & Safety Report
label | Specification - Special Conditions of Contract cl. 5.7.15
label | Frequency - Monthly
label | Acceptance criteria - Conform to contract requirement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.7 - Quality Management Plan
label | Specification - Special Conditions of Contract cl. 5.18.1
label | Frequency - Once
label | Acceptance criteria - Deemed as submitted under Panel Agreement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.8 - Enviromental Management Plan
label | Specification - Special Conditions of Contract cl. 5.22.1
label | Frequency - Once
label | Acceptance criteria - Deemed as submitted under Panel Agreement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.9 - Erosion & Sediment Control Plan
label | Specification - Letter of Award
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.10 - River Based Access
label | Specification - Technical Specification cl. 1.12
label | Methods or reference - Contractor to provide proposed access method
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.11 - Building Consent Expemption
label | Specification - Special Conditions of Contract cl. 1.5.1
label | Frequency - Once
label | Acceptance criteria - To be provided to the Contractor prior to construction
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - GDC
holdpoint | HOLD POINT
checkpoint | 1.12 - Traffic Management Plan
label | Specification - Special Conditions of Contract cl. 5.19.1
label | Methods or reference - GDC Tranche 4 Generic TMP to be used with possibly some site specific diagrams added
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - GDC
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.13 - Bridge Closures
label | Specification - Technical Specification cl. 1.8
label | Methods or reference - The date and duration of any closures to be agreed with the Engineer
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.14 - Proof of Insurance
label | Specification - Special Conditions of Contract cl. 8.1.1
label | Verification Activity - Insurer confirmation certificates for construction, plant, public liability & motor vehicle liability
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.15 - Service Locates
label | Specification - Technical Specification cl. 11
label | Verification Activity - Service providers including Before You Dig & close approach agreement
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Service details
label | Responsible Person - Currie
checkpoint | 1.16 - Dimensions and set-out
label | Specification - Technical Specification cl. 1.11
label | Methods or reference - Contractor to confirm set-out and dimensions with the Engineer on-site
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.17 - Clearing of Site
label | Specification - Technical Specification cl. 1.13
label | Methods or reference - Contractor to agree with Engineer the extent of the clearing
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 1.18 - Earthworks
label | Specification - Technical Specification cl. 1.10
label | Verification Activity - Contractor to submit excavation & compaction methodology to the Engineer
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
section | 2.0 - Materials
checkpoint | 2.1 - Nuts, bolts and washers
label | Specification - Technical Specification cl. 2.2
label | Methods or reference - To be Class 8 & HDG
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.2 - All Steelwork to be Grade 300
label | Specification - Technical Specification cl. 2.3
label | Verification Activity - Mill certificate
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 2.3 - Concrete for steel post footings
label | Specification - Technical Specification cl. 2.4.1
label | Verification Activity - Contractor to provide concrete mix design
label | Methods or reference - Concrete to be 30MPa
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.4 - No-fines concrete
label | Specification - Technical Specification cl. 2.4.2
label | Verification Activity - Contractor to provide concrete mix design
label | Methods or reference - Concrete to be 7.5MPa
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.5 - Timber lagging
label | Specification - Technical Specification cl. 2.5.1
label | Verification Activity - Visual
label | Methods or reference - To be SG8 H4 with cut surfaces treated with Metalex
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.6 - Timber lagging fixings
label | Specification - Technical Specification cl. 2.5.1
label | Methods or reference - All fixings to be stainless steel
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.7 - Lagging thickness
label | Specification - Drawings C03 & C04
label | Verification Activity - Visual
label | Methods or reference - Height from top of wall: 0.0 - 1.6m = 100mm thick ; greater than 1.6m = 200mm thick
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 2.8 - Geo-textile
label | Specification - Technical Specification cl. 2.6
label | Methods or reference - A29 required behind timber lagging & around sub-soil drain
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.9 - Drainage composite
label | Specification - Technical Specification cl. 2.7
label | Methods or reference - Filtration Class 1 & Strength Class C - laid over batter slopes
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.10 - Drainage aggregate
label | Specification - Technical Specification cl. 2.8
label | Methods or reference - Free draining clean aggregate with 100% passing 19mm sieve
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.11 - Retaining wall backfill
label | Specification - Technical Specification cl. 2.9
label | Verification Activity - Contractor to provide concrete mix design
label | Methods or reference - Sand & cement mix with strength of 1MPa & slump of 350 - 500mm
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.12 - Sub-soil drain
label | Specification - Technical Specification cl. 2.10
label | Methods or reference - 150mm Punched HDPe sub-soil pipe
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.13 - Inspection of sub-soil drain
label | Specification - Technical Specification cl. 14
label | Verification Activity - Contractor must request an inpection by the Engineer of the sub-soil drain before backfilling
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.14 - Topsoil
label | Specification - Technical Specification cl. 2.11
label | Verification Activity - Visual
label | Methods or reference - Re-use existing topsoil
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 2.15 - Testing of materials
label | Specification - Technical Specification cl. 2.13
label | Verification Activity - Supplied by the Contractor to the Engineer with 3 days of the activity occurring
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
section | 3.0 - Steelwork Fabrication
checkpoint | 3.1 - Shop drawings
label | Specification - Technical Specification cl. 3.2
label | Verification Activity - To be supplied to the Engineer
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed drawing
label | Responsible Person - Currie
checkpoint | 3.2 - All piles, walers & accessories
label | Specification - Technical Specification cl. 3.2
label | Verification Activity - To be inspected by the Engineer before installation
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
holdpoint | HOLD POINT
section | 4.0 - Piling
checkpoint | 4.1 - Pile holes
label | Specification - Technical Specification cl. 4.1 drg C04
label | Verification Activity - 150UC30 piles in 400mm dia hole, min. 1.5m deep rock socket
label | Methods or reference - Engineer to inspect pile holes before pouring
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 4.2 - Pile spacing
label | Specification - Technical Specification cl. 4.1 drg C03
label | Verification Activity - Abutment A: Spacing 1.2m centres
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.3 - Maximum retained height
label | Specification - Technical Specification cl. 4.1 drg C03 & C11
label | Verification Activity - Abutment A: 2.3m
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.4 - Pile hole augering methodology
label | Specification - Technical Specification cl. 4.1
label | Verification Activity - Visual check
label | Methods or reference - Hit one, miss one. "Miss" holes only to be augered 24hrs after concreting "hit" holes.
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.5 - Augered pile holes
label | Specification - Technical Specification cl. 4.2
label | Verification Activity - Pile logs submitted to engineer by the next day after augering
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 4.6 - Pile hole tolerances
label | Specification - Technical Specification cl. 4.3
label | Verification Activity - Pole dia. +50mm/0mm, hole plan position +/-20mm.
label | Methods or reference - Tape measure
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.7 - UC post tolerances
label | Specification - Technical Specification cl. 4.3
label | Verification Activity - Pole vertical alignment not to exceed 2 deg from design alignment, deviation of pole plan line +/-10mm, pole tops +/-10mm, pole base level +/-50mm
label | Methods or reference - String lines and tape measures
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.8 - UC post size & treatment
label | Specification - Drg C03 & C04
label | Verification Activity - 150UC30 ungalvanized
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Delivery docket
label | Responsible Person - Currie
checkpoint | 4.9 - Concreting UC posts
label | Specification - Technical Specification cl. 2.4.1 & 4.3
label | Verification Activity - 30MPa concrete
label | Methods or reference - Supplier delivery dockets and laboratory concrete compression test results to be delivered to the engineer
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
section | 5.0 - Welding
checkpoint | 5.1 - Welds
label | Specification - Technical Specification cl. 6.1
label | Verification Activity - All welds to be category SP
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 5.2 - Welder qualifications
label | Specification - Technical Specification cl. 6.1
label | Verification Activity - Welder qualifications to be submitted to the Engineer for approval
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
holdpoint | HOLD POINT
section | 6.0 - Concreting
checkpoint | 6.1 - Formwork
label | Specification - Technical Specification cl. 7.1
label | Verification Activity - Formwork to remain in place for 48hrs after pouring
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 6.2 - Concrete workmanship
label | Specification - Technical Specification cl. 7.2
label | Verification Activity - Concrete to be placed in dry conditions
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 6.3 - Concrete testing
label | Specification - Technical Specification cl. 7.4
label | Verification Activity - Cylinder test results to be supplied to the Engineer. 1 x 7d + 2 x 28d
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
section | 7.0 - Crib Wall
checkpoint | 7.1 - Pouring no-fines concrete
label | Specification - Technical Specification cl. 8.2
label | Verification Activity - No-fines to be poured up to the front face of the crib wall
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
section | 8.0 - Ground Anchors
checkpoint | 8.1 - Anchor installation
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Contractor to notify Engineer at least 2 days prior to installation & testing
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 8.2 - Anchor grout volume
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Supply grout volume records for each anchor & submit to engineer
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Grout Log Record
label | Responsible Person - Currie
checkpoint | 8.3 - Anchor installation
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Hollow bars not to be installed at a rate exceeding 1m per minute
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 8.4 - Loading of anchors
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Anchors shall not be loaded for at least 7 days following grouting
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 8.5 - Anchor testing equipment
label | Specification - Technical Specification cl. 9.2
label | Verification Activity - Contractor to submit all testing equipment calibration certificates to the Engineer prior to testing
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
checkpoint | 8.6 - Anchor test results
label | Specification - Technical Specification cl. 9.2
label | Verification Activity - Contractor to provide the Engineer with test results within 2 days of testing
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
checkpoint | 8.7 - Sacrificial tests
label | Specification - Technical Specification cl. 9.3
label | Verification Activity - Abutment A: 1 x sacrificial test
label | Methods or reference - Positions to be agreed with the Engineer & outside of the work area
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP/Currie
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 8.8 - Production anchors
label | Specification - Technical Specification cl. 9.2 & 9.4
label | Verification Activity - All production anchors are to be tested & Contractor to provide the Engineer with test records within 2 days of a test
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Anchor Load Test Record
label | Responsible Person - Currie
checkpoint | 8.9 - Sacrificial & production anchors
label | Specification - Technical Specification cl. 9.3
label | Verification Activity - Engineer to witness testing and shall be given at least 2 days notice of testing
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 8.10 - Grout mix design
label | Specification - Technical Specification cl. 9.7
label | Verification Activity - Contractor to submit a grout mix design to the Engineer for approval at least 1 x week before grouting
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
checkpoint | 8.11 - Anchor grout
label | Specification - Technical Specification cl. 9.3, 9.4 & 9.7
label | Verification Activity - 30MPa required at 28 days and 30MPa before testing
label | Methods or reference - 1no. X 50mm cubes at 7d and 2no. X 50mm cubes at 28d
label | Frequency - Once
label | Acceptance criteria - 30MPa before testing & proven with cube test results prior to testing
label | Inspection Type - Hold Point
label | Assessor - WSP/Project manager
label | Reports to be delivered - Detailed report
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 8.12 - Anchor tolerences
label | Specification - Technical Specification cl. 9.6
label | Verification Activity - Depth of anchor +0.5m/ -0.0m, anchor position +-20mm, plan location +-50mm, orientation 2 degrees
label | Methods or reference - Tape measure & digital spirit level
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 8.13 - Anchor testing
label | Specification - Drg C11 Table 2
label | Verification Activity - Anchor bar design yield strength: Abutment A: 30/14 bar = 220kN
label | Methods or reference - Hydraulic test jack
label | Frequency - Every anchor
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 8.14 - Anchor bar lengths
label | Specification - Drg C11 Table 2
label | Verification Activity - Abutment A: GA1 - GA6 = 3.0m unbonded & min. 3.0m rock socket
label | Methods or reference - Abutment A: GA1 - GA6 = 30/14 anchor at 1.2m centres
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Anchor Log Record
label | Responsible Person - Currie
checkpoint | 8.15 - Anchor bar couplers, nuts & washers
label | Specification - All hot dip galvanized
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
section | 9.0 - Earthworks
checkpoint | 9.1 - Site sourced material
label | Specification - Technical Specification cl. 10.3
label | Verification Activity - Site sourced to be used for all backfilling EXCEPT for behind the retaining walls
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 9.2 - Compaction layer thickness
label | Specification - Technical Specification cl. 10.3
label | Verification Activity - Compaction to be in loose layers not exceeding 300mm
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 9.3 - Rip rap top-up in front of existing bridge piles & new retaining wall
label | Specification - Drg C01
label | Verification Activity - Rip rap to be site won
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 9.4 - Centre pier rip rap protection
label | Specification - Drg C01
label | Verification Activity - Rip rap to be site won
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
section | 10.0 - COMPLETION
checkpoint | 10.1 - Remove erosion and sediment control measures
label | Specification - Remove once planting has taken
label | Frequency - Once
label | Acceptance criteria - According to Environmental Management Plan
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.2 - Remove Traffic Control
label | Specification - Safety
label | Frequency - Once
label | Acceptance criteria - According to TMP
label | Inspection Type - Verification
label | Assessor - Supervisor
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.3 - Site maintained in a tidy state during construction
label | Specification - Best as is reasonably practicable
label | Frequency - Daily
label | Inspection Type - Verification
label | Assessor - Supervisor
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.4 - Practical Completion Inspection
label | Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a)
label | Verification Activity - Engineer to inspect site on completion of physical works
label | Frequency - Once
label | Acceptance criteria - Supply as-built drawings & PS3
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Inspection record
label | Responsible Person - Currie/WSP
holdpoint | HOLD POINT
checkpoint | 10.5 - Inspect site 12 months after completion
label | Specification - Remedy agreed defects
label | Frequency - Once
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site Inspection
label | Responsible Person - Currie/WSP
checklist | ITP - Mangaheia No.1 Bridge - Tauwhareparae Road RP16.17 | itp
section | 1.0 - DELIVERABLES
checkpoint | 1.1 - Prestart handover meeting
label | Methods or reference - Meeting agender items
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Internal meeting
label | Assessor - Project Manager
label | Reports to be delivered - Attendance record
label | Responsible Person - Currie
checkpoint | 1.2 - Construction Methodology
label | Specification - Letter of Award
label | Frequency - Once
label | Acceptance criteria - Approved by ER prior to commencement of physical works
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.3 - Construction Programme
label | Specification - Special Conditions of Contract cl. 5.10.4 and Letter of Award
label | Methods or reference - MS Project format
label | Frequency - Updated weekly
label | Acceptance criteria - Conform to contract requirement
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.4 - Site Specific Risk Assessment
label | Specification - Special Conditions of Contract cl. 5.17.1
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.5 - Health & Safety Management Plan
label | Specification - Special Conditions of Contract cl. 5.17.1 and Letter of Award
label | Frequency - Once
label | Acceptance criteria - Conform to contract requirement
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.6 - Monthly Health & Safety Report
label | Specification - Special Conditions of Contract cl. 5.7.15
label | Frequency - Monthly
label | Acceptance criteria - Conform to contract requirement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.7 - Quality Management Plan
label | Specification - Special Conditions of Contract cl. 5.18.1
label | Frequency - Once
label | Acceptance criteria - Deemed as submitted under Panel Agreement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.8 - Enviromental Management Plan
label | Specification - Special Conditions of Contract cl. 5.22.1
label | Frequency - Once
label | Acceptance criteria - Deemed as submitted under Panel Agreement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.9 - Erosion & Sediment Control Plan
label | Specification - Letter of Award
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.10 - River Based Access
label | Specification - Technical Specification cl. 1.12
label | Methods or reference - Contractor to provide proposed access method
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.11 - Building Consent Expemption
label | Specification - Special Conditions of Contract cl. 1.5.1
label | Frequency - Once
label | Acceptance criteria - To be provided to the Contractor prior to construction
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - GDC
holdpoint | HOLD POINT
checkpoint | 1.12 - Traffic Management Plan
label | Specification - Special Conditions of Contract cl. 5.19.1
label | Methods or reference - GDC Tranche 4 Generic TMP to be used with possibly some site specific diagrams added
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - GDC
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.13 - Bridge Closures
label | Specification - Technical Specification cl. 1.8
label | Methods or reference - The date and duration of any closures to be agreed with the Engineer
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.14 - Proof of Insurance
label | Specification - Special Conditions of Contract cl. 8.1.1
label | Verification Activity - Insurer confirmation certificates for construction, plant, public liability & motor vehicle liability
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.15 - Service Locates
label | Specification - Technical Specification cl. 11
label | Verification Activity - Service providers including Before You Dig & close approach agreement
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Service details
label | Responsible Person - Currie
checkpoint | 1.16 - Dimensions and set-out
label | Specification - Technical Specification cl. 1.11
label | Methods or reference - Contractor to confirm set-out and dimensions with the Engineer on-site
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.17 - Clearing of Site
label | Specification - Technical Specification cl. 1.13
label | Methods or reference - Contractor to agree with Engineer the extent of the clearing
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 1.18 - Earthworks
label | Specification - Technical Specification cl. 1.10
label | Verification Activity - Contractor to submit excavation & compaction methodology to the Engineer
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
section | 2.0 - Materials
checkpoint | 2.1 - Nuts, bolts and washers
label | Specification - Technical Specification cl. 2.2
label | Methods or reference - To be Class 8 & HDG
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.2 - All Steelwork to be Grade 300
label | Specification - Technical Specification cl. 2.3
label | Verification Activity - Mill certificate
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 2.3 - Concrete for steel post footings
label | Specification - Technical Specification cl. 2.4.1
label | Verification Activity - Contractor to provide concrete mix design
label | Methods or reference - Concrete to be 30MPa
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.4 - No-fines concrete
label | Specification - Technical Specification cl. 2.4.2
label | Verification Activity - Contractor to provide concrete mix design
label | Methods or reference - Concrete to be 7.5MPa
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.5 - Timber lagging
label | Specification - Technical Specification cl. 2.5.1
label | Verification Activity - Visual
label | Methods or reference - To be SG8 H4 with cut surfaces treated with Metalex
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.6 - Timber lagging fixings
label | Specification - Technical Specification cl. 2.5.1
label | Methods or reference - All fixings to be stainless steel
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.7 - Lagging thickness
label | Specification - Drawings C03 & C04
label | Verification Activity - Visual
label | Methods or reference - Height from top of wall: 0.0 - 1.6m = 100mm thick ; greater than 1.6m = 200mm thick
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 2.8 - Geo-textile
label | Specification - Technical Specification cl. 2.6
label | Methods or reference - A29 required behind timber lagging & around sub-soil drain
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.9 - Drainage composite
label | Specification - Technical Specification cl. 2.7
label | Methods or reference - Filtration Class 1 & Strength Class C - laid over batter slopes
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.10 - Drainage aggregate
label | Specification - Technical Specification cl. 2.8
label | Methods or reference - Free draining clean aggregate with 100% passing 19mm sieve
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.11 - Retaining wall backfill
label | Specification - Technical Specification cl. 2.9
label | Verification Activity - Contractor to provide concrete mix design
label | Methods or reference - Sand & cement mix with strength of 1MPa & slump of 350 - 500mm
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.12 - Sub-soil drain
label | Specification - Technical Specification cl. 2.10
label | Methods or reference - 150mm Punched HDPe sub-soil pipe
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 2.13 - Inspection of sub-soil drain
label | Specification - Technical Specification cl. 14
label | Verification Activity - Contractor must request an inpection by the Engineer of the sub-soil drain before backfilling
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 2.14 - Topsoil
label | Specification - Technical Specification cl. 2.11
label | Verification Activity - Visual
label | Methods or reference - Re-use existing topsoil
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 2.15 - Testing of materials
label | Specification - Technical Specification cl. 2.13
label | Verification Activity - Supplied by the Contractor to the Engineer with 3 days of the activity occurring
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
section | 3.0 - Steelwork Fabrication
checkpoint | 3.1 - Shop drawings
label | Specification - Technical Specification cl. 3.2
label | Verification Activity - To be supplied to the Engineer
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed drawing
label | Responsible Person - Currie
checkpoint | 3.2 - All piles, walers & accessories
label | Specification - Technical Specification cl. 3.2
label | Verification Activity - To be inspected by the Engineer before installation
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 4.1 - Pile holes
label | Specification - Technical Specification cl. 4.1 drg C03 & C04
label | Verification Activity - 150UC30 piles in 400mm dia hole, min. 1.5m deep rock socket
label | Methods or reference - Engineer to inspect pile holes before pouring
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 4.2 - Pile spacing
label | Specification - Technical Specification cl. 4.1 drg C03 & C04
label | Verification Activity - Abutment A: Spacing varies between 1.2m & 1.5m ; Abutment C: Spacing at 1.2m centres
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.3 - Maximum retained height
label | Specification - Technical Specification cl. 4.1 drg C03 & C04
label | Verification Activity - Abutment A: 3.5m ; Abutment C: 1.9m
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.4 - Pile hole augering methodology
label | Specification - Technical Specification cl. 4.1
label | Verification Activity - Visual check
label | Methods or reference - Hit one, miss one. "Miss" holes only to be augered 24hrs after concreting "hit" holes.
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.5 - Augered pile holes
label | Specification - Technical Specification cl. 4.2
label | Verification Activity - Pile logs submitted to engineer by the next day after augering
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 4.6 - Pile hole tolerances
label | Specification - Technical Specification cl. 4.3
label | Verification Activity - Pole dia. +50mm/0mm, hole plan position +/-20mm.
label | Methods or reference - Tape measure
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.7 - UC post tolerances
label | Specification - Technical Specification cl. 4.3
label | Verification Activity - Pole vertical alignment not to exceed 2 deg from design alignment, deviation of pole plan line +/-10mm, pole tops +/-10mm, pole base level +/-50mm
label | Methods or reference - String lines and tape measures
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 4.8 - UC post size & treatment
label | Specification - Drg C03 & C04
label | Verification Activity - 150UC30 ungalvanized
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Delivery docket
label | Responsible Person - Currie
checkpoint | 4.9 - Concreting UC posts
label | Specification - Technical Specification cl. 2.4.1 & 4.3
label | Verification Activity - 30MPa concrete
label | Methods or reference - Supplier delivery dockets and laboratory concrete compression test results to be delivered to the engineer
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
section | 5.0 - Welding
checkpoint | 5.1 - Welds
label | Specification - Technical Specification cl. 6.1
label | Verification Activity - All welds to be category SP
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 5.2 - Welder qualifications
label | Specification - Technical Specification cl. 6.1
label | Verification Activity - Welder qualifications to be submitted to the Engineer for approval
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
holdpoint | HOLD POINT
section | 6.0 - Concreting
checkpoint | 6.1 - Formwork
label | Specification - Technical Specification cl. 7.1
label | Verification Activity - Formwork to remain in place for 48hrs after pouring
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 6.2 - Concrete workmanship
label | Specification - Technical Specification cl. 7.2
label | Verification Activity - Concrete to be placed in dry conditions
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 6.3 - Concrete testing
label | Specification - Technical Specification cl. 7.4
label | Verification Activity - Cylinder test results to be supplied to the Engineer. 1 x 7d + 2 x 28d
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
section | 7.0 - Crib Wall
checkpoint | 7.1 - Pouring no-fines concrete
label | Specification - Technical Specification cl. 8.2
label | Verification Activity - No-fines to be poured up to the front face of the crib wall
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
section | 8.0 - Ground Anchors
checkpoint | 8.1 - Anchor installation
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Contractor to notify Engineer at least 2 days prior to installation & testing
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 8.2 - Anchor grout volume
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Supply grout volume records for each anchor & submit to engineer
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Grout Log Record
label | Responsible Person - Currie
checkpoint | 8.3 - Anchor installation
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Hollow bars not to be installed at a rate exceeding 1m per minute
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 8.4 - Loading of anchors
label | Specification - Technical Specification cl. 9.1
label | Verification Activity - Anchors shall not be loaded for at least 7 days following grouting
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 8.5 - Anchor testing equipment
label | Specification - Technical Specification cl. 9.2
label | Verification Activity - Contractor to submit all testing equipment calibration certificates to the Engineer prior to testing
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
checkpoint | 8.6 - Anchor test results
label | Specification - Technical Specification cl. 9.2
label | Verification Activity - Contractor to provide the Engineer with test results within 2 days of testing
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
checkpoint | 8.7 - Sacrificial tests
label | Specification - Technical Specification cl. 9.3
label | Verification Activity - Abutment A: 1 x sacrificial test : Abutment C: 1 x sacrificial test
label | Methods or reference - Positions to be agreed with the Engineer & outside of the work area
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP/Currie
label | Reports to be delivered - Verification
label | Responsible Person - Currie
checkpoint | 8.8 - Production anchors
label | Specification - Technical Specification cl. 9.2 & 9.4
label | Verification Activity - All production anchors are to be tested & Contractor to provide the Engineer with test records within 2 days of a test
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Anchor Load Test Record
label | Responsible Person - Currie
checkpoint | 8.9 - Sacrificial & production anchors
label | Specification - Technical Specification cl. 9.3
label | Verification Activity - Engineer to witness testing and shall be given at least 2 days notice of testing
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Verification
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 8.10 - Grout mix design
label | Specification - Technical Specification cl. 9.7
label | Verification Activity - Contractor to submit a grout mix design to the Engineer for approval at least 1 x week before grouting
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - Project manager
label | Reports to be delivered - Detailed records
label | Responsible Person - Currie
checkpoint | 8.11 - Anchor grout
label | Specification - Technical Specification cl. 9.3, 9.4 & 9.7
label | Verification Activity - 30MPa required at 28 days and 30MPa before testing
label | Methods or reference - 1no. X 50mm cubes at 7d and 2no. X 50mm cubes at 28d
label | Frequency - Once
label | Acceptance criteria - 30MPa before testing & proven with cube test results prior to testing
label | Inspection Type - Hold Point
label | Assessor - WSP/Project manager
label | Reports to be delivered - Detailed report
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 8.12 - Anchor tolerences
label | Specification - Technical Specification cl. 9.6
label | Verification Activity - Depth of anchor +0.5m/ -0.0m, anchor position +-20mm, plan location +-50mm, orientation 2 degrees
label | Methods or reference - Tape measure & digital spirit level
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 8.13 - Anchor testing
label | Specification - Drg C11 Table 2
label | Verification Activity - Anchor bar design yield strength: Abutment A: 30/14 bar = 220kN & 40/20 bar = 430kN ; Abutment C: 30/14 bar = 220 kN
label | Methods or reference - Hydraulic test jack
label | Frequency - Every anchor
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 8.14 - Anchor bar lengths
label | Specification - Drg C11 Table 2
label | Verification Activity - Abutment A: GA1 - GA5 = 3.0m unbonded & min. 3.0m rock socket ; GA6 - GA7 = 3.0m unbonded & min. 5.0m rock socket ; Abutment C: GA8 - GA13 = 3.0m unbonded & min. 3.0m rock socket
label | Methods or reference - Abutment A: GA1 - GA5 = 30/14 anchor at 1.2 - 1.5m centres ; GA6 - GA7 = 40/20 anchor at 1.35m centres ; Abutment C: GA8 - GA13 = 30/14 anchor at 1.2m centres
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Anchor Log Record
label | Responsible Person - Currie
checkpoint | 8.15 - Anchor bar couplers, nuts & washers
label | Specification - All hot dip galvanized
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
section | 9.0 - Earthworks
checkpoint | 9.1 - Site sourced material
label | Specification - Technical Specification cl. 10.3
label | Verification Activity - Site sourced to be used for all backfilling EXCEPT for behind the retaining walls
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 9.2 - Compaction layer thickness
label | Specification - Technical Specification cl. 10.3
label | Verification Activity - Compaction to be in loose layers not exceeding 300mm
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
checkpoint | 9.3 - Centre pier rip rap protection
label | Specification - Drg C01
label | Verification Activity - Rip rap to be site won
label | Frequency - On-going
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site check
label | Responsible Person - Currie
section | 10.0 - COMPLETION
checkpoint | 10.1 - Remove erosion and sediment control measures
label | Specification - Remove once planting has taken
label | Frequency - Once
label | Acceptance criteria - According to Environmental Management Plan
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.2 - Remove Traffic Control
label | Specification - Safety
label | Frequency - Once
label | Acceptance criteria - According to TMP
label | Inspection Type - Verification
label | Assessor - Supervisor
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.3 - Site maintained in a tidy state during construction
label | Specification - Best as is reasonably practicable
label | Frequency - Daily
label | Inspection Type - Verification
label | Assessor - Supervisor
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.4 - Practical Completion Inspection
label | Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a)
label | Verification Activity - Engineer to inspect site on completion of physical works
label | Frequency - Once
label | Acceptance criteria - Supply as-built drawings & PS3
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Inspection record
label | Responsible Person - Currie/WSP
holdpoint | HOLD POINT
checkpoint | 10.5 - Inspect site 12 months after completion
label | Specification - Remedy agreed defects
label | Frequency - Once
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site Inspection
label | Responsible Person - Currie/WSP