## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Mangatokerau Bridge Scour Protection, Paroa Road RP1.1 | itp
section | 1.0 - DELIVERABLES
checkpoint | 1.1 - Prestart handover meeting
label | Methods or reference - Meeting agender items
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Internal meeting
label | Assessor - Project Manager
label | Reports to be delivered - Attendance record
label | Responsible Person - Currie
checkpoint | 1.2 - Construction Methodology
label | Specification - Letter of Award
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.3 - Monthly Health & Safety Reports
label | Specification - Special Conditions of Contract cl. 5.7.15
label | Frequency - Monthly
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.4 - Health & Safety Management Plan
label | Specification - Special Conditions of Contract cl. 5.17.1
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.5 - Site Specific Risk Assessment
label | Specification - Special Conditions of Contract cl. 5.17.1
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.6 - Quality Management Plan
label | Specification - Special Conditions of Contract cl. 5.18.1
label | Frequency - Once
label | Acceptance criteria - Deemed as submitted under Panel Agreement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.7 - Enviromental Management Plan
label | Specification - Special Conditions of Contract cl. 5.22.1
label | Frequency - Once
label | Acceptance criteria - Deemed as submitted under Panel Agreement
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.8 - Erosion & Sediment Control Plan
label | Specification - Letter of Award
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.9 - Proof of Insurance
label | Specification - Special Conditions of Contract cl. 8.1.1
label | Verification Activity - Insurer confirmation certificates
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.10 - Construction Programme
label | Specification - Special Conditions of Contract cl. 5.10.5 & 6
label | Frequency - Once for approval , then updated weekly
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.11 - Service Locates
label | Verification Activity - Service providers including Before You Dig & close approach agreement
label | Methods or reference - Expose & protect existing services
label | Frequency - Once
label | Acceptance criteria - Prior to commencement of physical works
label | Inspection Type - Hold Point
label | Assessor - Project Manager
label | Reports to be delivered - Service details
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.12 - AP40/65 Backfill Material & Road Layerworks
label | Specification - Technical Specification cl. 2
label | Verification Activity - Check suitability for backfilling PSD, crushing resistence, grading & linear shrinkage
label | Methods or reference - Quarry aggregate laboratory test results
label | Frequency - Once
label | Acceptance criteria - Conform to specification
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Geotech engineer record
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 1.13 - Welding structural steel
label | Verification Activity - Welder's welding certificate & experience
label | Frequency - Once
label | Acceptance criteria - Conform to specification
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
checkpoint | 1.14 - Traffic Management Plan
label | Specification - Special Conditions of Contract cl. 5.19.1
label | Methods or reference - GDC Generic TMP to be used with some site specific diagrams added
label | Frequency - Once
label | Acceptance criteria - Conform to Contract requirements
label | Inspection Type - Verification
label | Assessor - GDC
label | Reports to be delivered - Detailed record
label | Responsible Person - Currie
section | 2.0 - Hold & Witness Points
checkpoint | 2.1 - Set-out inspection
label | Specification - Technical Specification cl. 2
label | Verification Activity - To be confirmed with Engineer on-site
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Hold Point
label | Assessor - WSP/Supervisor
label | Reports to be delivered - Visual
label | Responsible Person - Currie/WSP
holdpoint | HOLD POINT
checkpoint | 2.2 - Installation of sheet piles
label | Specification - Technical Specification cl. 2
label | Verification Activity - Engineer to witness start of installation on-site
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Witness Point
label | Assessor - WSP/Supervisor
label | Reports to be delivered - Visual
label | Responsible Person - Currie/WSP
checkpoint | 2.3 - Backfilling behind wall
label | Specification - Technical Specification cl. 2
label | Verification Activity - Engineer to witness start of backfilling
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Witness Point
label | Assessor - WSP/Supervisor
label | Reports to be delivered - Visual
label | Responsible Person - Currie/WSP
checkpoint | 2.4 - Installation of walers, tie rods, bolts/nuts
label | Specification - Technical Specification cl. 2
label | Verification Activity - Engineer to inspect installation of components
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie/WSP
holdpoint | HOLD POINT
section | 3.0 - Earthworks
checkpoint | 3.1 - Site clearance
label | Specification - Techinical Specification cl. 3.2
label | Methods or reference - Engineer to advise on what vegetation should be taken to spoil
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 3.2 - Cut or undercut
label | Specification - Techinical Specification cl. 3.3
label | Methods or reference - Cut material that is not required shall be carted to waste unless directed by the Engineer
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 3.3 - Batter slopes
label | Specification - Drg C04 and C05
label | Methods or reference - Batter slopes to be finished to 2H : 1V slope
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 3.4 - TTM
label | Specification - Techinical Specification cl. 3.5
label | Methods or reference - Contractor to provide TTM so the site is safe for road users & pedestrians
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
section | 4.0 - Retaining Wall
checkpoint | 4.1 - Sheet piles
label | Specification - Techinical Specification cl. 4.3
label | Verification Activity - Supply Mill Certificates
label | Methods or reference - Sheet piles to be grade 390 steel
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 4.2 - All tie rods, couplers, washers, nuts and walers
label | Specification - Techinical Specification cl. 4.3
label | Methods or reference - All to be hot dip galvanised
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
section | 5.0 - Granular Backfill
checkpoint | 5.1 - Backfilling to rear of wall
label | Specification - Techinical Specification cl. 5
label | Methods or reference - To be AP65
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 5.2 - Backfilling to rear of wall
label | Specification - Techinical Specification cl. 5
label | Verification Activity - Compacted in 200mm compacted layers & compact to 95% MDD or Clegg Hammer CIV ≥32 & ave. CIV35
label | Methods or reference - NDM testing or Clegg Hammer
label | Frequency - NDM testing every 400mm thick with 1no. Test per 10m2 or Clegg Hammer every 200mm layer with 1no test per 5m2
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Compaction test record sheet
label | Responsible Person - Currie
section | 6.0 - Rock Rip Rap
checkpoint | 6.1 - Rock rip rap
label | Specification - Technical Specification cl. 6
label | Verification Activity - Crushing resistance ≥150Kn, UCS ≥ 30MPA, Solid density ≥2.6t/m³, Weathering index AA or AB, Point load strength ≥1.5MPa, Water absorption ≤2%
label | Methods or reference - Quarry aggregate laboratory test results
label | Frequency - Submit records at least 1 week prior to placing rock
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Quarry material test record
label | Responsible Person - Currie
checkpoint | 6.2 - Rip rap grading
label | Specification - Techinical Specification cl. 6.1
label | Verification Activity - D50 800mm (50% passing 800mm)
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Delivery dockets
label | Responsible Person - Currie
checkpoint | 6.3 - Slope finish
label | Specification - Drg C04 & C05
label | Verification Activity - Finished surface slope to be 2H : 1V
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
section | 7.0 - Sheetpile Wall
checkpoint | 7.1 - Welding of sheetpiles
label | Specification - Techinical Specification cl. 7.1
label | Verification Activity - All welding to be Category SP
label | Methods or reference - Welding to be inspected by a welding inspector
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Welding inspection report
label | Responsible Person - Currie
checkpoint | 7.2 - Construction of sheetpile wall
label | Specification - Techinical Specification cl. 7.2
label | Verification Activity - Deviation of pile centreline: +/- 10mm; Pile top reduced level: +/- 10mm; Pile base reduced level: +/- 50mm
label | Methods or reference - Tape measure
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 7.3 - Temporary works
label | Specification - Techinical Specification cl. 7.3
label | Verification Activity - Sheetpile bench not to exceed 4m wide with batter slope not exceeding 60 degrees
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 7.4 - Removal of roots
label | Specification - Techinical Specification cl. 7.3
label | Verification Activity - If roots are encountered, they are to be removed by cutting them out & not by ripping them out
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 7.5 - Geo-textile under rip rap
label | Specification - Techinical Specification cl. 7.7
label | Verification Activity - Use A19 geo-textile with minimum laps of 500mm
label | Methods or reference - Tape measure
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier dockets
label | Responsible Person - Currie
section | 8.0 - Steelwork
checkpoint | 8.1 - All steelwork
label | Specification - Techinical Specification cl. 8
label | Verification Activity - Mill Certificate
label | Methods or reference - Steelwork to be grade 300
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier docket
label | Responsible Person - Currie
checkpoint | 8.2 - Welding
label | Specification - Techinical Specification cl. 8
label | Verification Activity - Welding inspector
label | Methods or reference - Welds to be Class SP & 6mm continuous fillet welds
label | Frequency - On-going
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Welding inspection report
label | Responsible Person - Currie
checkpoint | 8.3 - All bolts, nuts, washers, couplers, tie bars & walers
label | Specification - Techinical Specification cl. 8
label | Verification Activity - Walers galvanised to HDG600
label | Methods or reference - Visual
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier dockets
label | Responsible Person - Currie
checkpoint | 8.4 - Bolt thread
label | Specification - Techinical Specification cl. 8
label | Verification Activity - At least one full thread to be exposed beyond all nuts & at least one washer to be used under each nut
label | Methods or reference - Visual
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
section | 9.0 - Pavement
checkpoint | 9.1 - Road sub-grade inspection/testing
label | Specification - Techinical Specification cl. 9
label | Verification Activity - Scala's taken at 5m c/c to 1.0m deep & submitted to Engineer prior to commencement of pavement works
label | Methods or reference - Scala's
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Scala test records
label | Responsible Person - Currie
holdpoint | HOLD POINT
checkpoint | 9.2 - Sub-base
label | Specification - Techinical Specification cl. 9
label | Verification Activity - 250mm Thick AP65
label | Methods or reference - Visual
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier dockets
label | Responsible Person - Currie
checkpoint | 9.3 - Basecourse
label | Specification - Techinical Specification cl. 9
label | Verification Activity - 100mm Thick AP40
label | Methods or reference - Visual
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Supplier dockets
label | Responsible Person - Currie
checkpoint | 9.4 - Seal
label | Specification - Techinical Specification cl. 9
label | Verification Activity - Grade 3/5 wet lock 2-coat
label | Methods or reference - Visual
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Visual
label | Responsible Person - Currie
checkpoint | 9.5 - Testing of layerworks
label | Specification - Techinical Specification cl. 9
label | Verification Activity - 2no. NDM tests per layer
label | Methods or reference - Troxler
label | Frequency - Once
label | Acceptance criteria - In accordance with specification and drawings
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Lab test record
label | Responsible Person - Currie
section | 10.0 - COMPLETION
checkpoint | 10.1 - Remove erosion and sediment control measures
label | Specification - Remove once planting has taken
label | Frequency - Once
label | Acceptance criteria - According to Environmental Management Plan
label | Inspection Type - Verification
label | Assessor - Foreman
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.2 - Remove Traffic Control
label | Specification - Safety
label | Frequency - Once
label | Acceptance criteria - According to TMP
label | Inspection Type - Verification
label | Assessor - Supervisor
label | Responsible Person - Currie
checkpoint | 10.3 - Site maintained in a tidy state during construction
label | Specification - Best as is reasonably practicable
label | Frequency - Daily
label | Inspection Type - Verification
label | Assessor - Supervisor
label | Reports to be delivered - Photo
label | Responsible Person - Currie
checkpoint | 10.4 - Practical Completion Inspection
label | Specification - Special Conditions of Contract cl. 5.20.1(a), 10.4.5 (a) & 10.4.5 (b)(a)
label | Verification Activity - Engineer to inspect site on completion of physical works
label | Frequency - Once
label | Acceptance criteria - Supply as-built drawings & PS3
label | Inspection Type - Hold Point
label | Assessor - WSP
label | Reports to be delivered - Inspection record
label | Responsible Person - Currie/WSP
holdpoint | HOLD POINT
checkpoint | 10.5 - Inspect site 12 months after completion
label | Specification - Specific Conditions of Contract cl. 11.1
label | Frequency - Once
label | Inspection Type - Verification
label | Assessor - WSP
label | Reports to be delivered - Site Inspection
label | Responsible Person - Currie/WSP