## General
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check point | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | M2F |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | DS2681-SH58-ITP-C-006 - Drainage (MH, HW, Sump) |  |  | Version: | Rev 1 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Drainage Manholes, Headwalls and Sumps | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Nick Talbot | NT
[7 empty] | R | Review | PE | Project Engineer | Dehan Erasmus | DE
Drawings: | 80510096-02B-100-C111-Rev 1 80510096-02B-100-C112- Rev 1 , 80510096-02B-100-C113-Rev 1 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyrese Dickson | TD
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyrese Dickson |  |  | Date: | 2025-07-16 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
Construction Manager |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-07-31
Project Manager |  | Name: | Gordon Lemon |  |  | Signature: |  |  |  |  | Date:
QA Advisor |  | Name: | Lissa Gatehouse |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: please use the correct ITP No. check the ITP register in the WBS, ie DS2681-SH58-ITP-C-005 Drainage (Pipes) DS2681-SH58-ITP-C-006 Drainage (HW/MH/Sumps) DS2681-SH58-ITP-C-007 Drainage (Rock Flumes)

## Construction (MH, HW, Sump)
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[7 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4.1 | Trench subgrade | Project Specification Cl 16.3.12 | Contractor to confirm suitability of foundation material and where the Engineer considers that the foundation material below the pipes or structures is unsuitable as defined in the earthworks specification, this material shall be removed and replaced as outlined in the earthworks specification 3 blows per 100mm | Scala Testing Record Sheet DN-QUA-QC-04 | 10m intervals | Witness Point | W | SE
4.2 | Visual Inspection of Subgrade | Project Specification Cl 16.3.12 TNZ F/1 | Visual inspection of subgrade. Engineer to confirm any undercut treatment, if required. | ConQA Hold Point | Before placing bedding | Holdpoint | H | ER
4.3 | Manhole Installation | Project Specification Cl 16.3.25, Cl 16.2.8 | Manholes are to be installed in accordance with the Regional Standards for Water Services, 2012 and NZS 4404:2010 Land Development and Subdivision Infrastructure, incorporating Hutt City Council amendments as detailed in Porirua City Council’s Code of Land Development and Subdivision Engineering, 2010. Precast concrete structures shall comply with NZS 3106. Joints between precast units shall be of the interlocking, self-centring type and shall be sealed with butyl mastic or similar approved to form a watertight joint | Photos DN-QUA-QC-07 Manhole Installation Checksheet | Per Manhole | Witness Point | W | SE
4.4 | Headwall / Sump Installation | Project Specification Cl 16.3.35 | All wingwalls/headwalls/outfalls shall be pre-cast proprietary and constructed in accordance with the drawings and NZTA F/3, which shall be deemed to form part of this specification Ancillary concrete structures required to complete the pipe installation including: headwalls; wingwalls;baffles, sumps; sump tops; aprons; drops; and intakes shall be reinforced and constructed as shown on thedrawings | Photos DN-QUA-QC-03- Sump/ Catchpit Istallation Check Sheet | During Construction | Witness Point | W | SE
4.5 | Tolerances | Project Specification Cl 16.3.42 | The permissible deviation of the location of manholes from the designated position shall be half a pipe length longitudinally and ±150mm laterally, except where locations are dimensioned from fixtures such as fences, kerbs and boundaries, in which event the permissible deviation in either direction shall be ±50mm The permissible deviation from the designated level of the invert at each manhole shall be ± 25mm. | As-built | During Construction | As-built survey | W | SV
4.6 | Backfilling & compaction | Project Specification Cl 16.3.20 | Hardfill shall be compacted in layers not exceeding 150mm loose depth using approved mechanical compaction equipment. Selected fill and Ordinary fill unless specified otherwise, shall be compacted to at least 90% MDD at optimum moisture content. Pavement layers shall be compacted to average 98% MDD with no result less than 95% | Photos NDM Test Results DN-QUA-QC-09 | Continous | Witness Point | W | SE
4.7 | As-built Survey | Upon completion of works | As built survey record completed | As-Built | After Works | Witness Point | W | SE