## General
SECTION 1 – GENERAL DETAILS
Project Name: | SH58-M2TG | [5 empty] | Inspection Key Use in sections 3, 4 and 5. |  | Responsibilities Use in sections 3, 4 and 5.
Project Number: | DS2681 | [5 empty] | A | Action | Role Key |  | Name | Signature/ Initial
Customer: | Waka Kotahi NZ Transport Agency | [5 empty] | B | Report by Breach | PM | Project Manager | Gordon Lemon | GL
Contract Number: | 106877 | [5 empty] | C | Check point | CM | Construction Manager | Jamie Nisbet | JN
Area/ Sub-System: | M2F |  |  | Lot ID Number: |  |  | D | Dimension Inspection | ER | Stantec Representative | Sam Parkinson | SP
[7 empty] | E | Examine | QE | Quality Engineer | Lyssa Gatehouse | LG
ITP Number: | DS2681-SH58-ITP-C-007 - Drainage (Rock Flume) |  |  | Version: | Rev 1 |  | H | Hold Point | QM | QA Manager | Diliban Sengottian | DS
ITP Description: | Drainage Rock Flumes | [5 empty] | I | Inspection | SV | Surveyor | Jim Robbins | JR
Discipline: | Civil | [5 empty] | M | Monitor on Random Basis | PS | Project Supervisor | John Masters | JM
Specification: | MCIP SH58 East of Moonshine Road to Transmission Gully- Project Specification | [5 empty] | O | Operation | ST | Superintendent | Nick Talbot | NT
[7 empty] | R | Review | PE | Project Engineer | Dehan Erasmus | DE
Drawings: | 80510096-02B-100-C111-Rev 1 80510096-02B-100-C112- Rev 1 , 80510096-02B-100-C113-Rev 1 | [5 empty] | S | Subcontractor | SE | Site Engineer | Tyrese Dickson | TD
[7 empty] | V | Visual Verification | EM | Environmental Manager | Ross Glubb | RG
Prepared By: (Name) | Tyrese Dickson |  |  | Date: | 2025-07-16 |  | W | Witness Point
Quality Specified:
SECTION 2 – SIGNATURES – CLOSE-OUT & APPROVAL
Construction Manager |  | Name: | Jamie Nisbet |  |  | Signature: |  | #VALUE! |  |  | Date: | 2025-07-31
Project Manager |  | Name: | Gordon Lemon |  |  | Signature: |  |  |  |  | Date:
QA Advisor |  | Name: | Lissa Gatehouse |  |  | Signature: |  |  |  |  | Date:
Customer Approval |  | Name: |  |  |  | Signature: |  |  |  |  | Date:
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: please use the correct ITP No. check the ITP register in the WBS, ie DS2681-SH58-ITP-C-005 Drainage (Pipes) DS2681-SH58-ITP-C-006 Drainage (HW/MH/Sumps) DS2681-SH58-ITP-C-007 Drainage (Rock Flumes)

## Construction (Rock flume)
SECTION 4 – IN-PROCESS INSPECTIONS Insert additional or delete unused rows as required. Include reference to specification.
Item No. | Activity/ Task Description | Specification/Drawing Reference | Acceptance Criteria | Verifying Document | Frequency | Inspection Type (Visual, other) | Inspection |  | Inspection Point/ Signature & Date
[7 empty] | Key | By (Role Key) | Downer Signature | Date | Customer Requirements Verification Record / Location
4.1 | Excavation | 80510096-02B-900-C241 | Slope to match bank, report back to engineer If steeper than 1:2 slope | Photos As-builts | during construction | Witness Point | W | SV /SE
4.2 | Geotextile | 80510096-02B-900-C241 | Layer of Geotextile(TNZ F/4 CLASS E GEOTEXTILE) to be placed at the base of the flume excavation | Photos | Continous | Witness Point | W | SE
4.3 | Rip-Rap | Project Specification Cl 16.3.35 | Rip Rap Lined Drain shall consist of sound durable rock not less than 150mm mean rock diameter (d50) and 300mm thick liner properly bedded on geotextile protected prepared drain. | Photos As Builts | during construction | Witness Point | W | SE