## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1d7c48f8-a084-4c68-a0b7-6b33cd20cf0c | checklist | DS2681-SH58-ITP-C-001 Concrete In-Situ | itp | DS2681-SH58-ITP-C-001 Concrete In-Situ
9a5137c8-bbad-47b0-801e-e36c101a42fc | section | SECTION 2 – IN-PROCESS INSPECTIONS
1f168b69-f14f-403c-94ea-23490ef9de9f | checkpoint | 2.01 - Method Statement
e726530a-3dc4-59c3-8c49-573c97861c3f | note | Inspection Point: Quality Control Activity - Prior to works
de5617fc-f84f-5e66-842f-5a5571f200ba | note | Specification Reference - PS Cl. 24.1.18
75943a19-4e35-5277-9a77-0768908a59e8 | note | Acceptance Criteria - The Contractor shall supply a method statement to the Engineer at least 10 working days before the supply of concrete to the project site. The method statement(s) shall clearly demonstrate that the Concrete Supplier and Contractor have carefully considered the Quality Assurance requirements, requirements of this Specification.
b4705e26-d6a3-56b3-b9a0-e1ef5a4312a0 | note | Verifying Document - Method Statement
f101e33d-6572-5eaf-a7c1-c620352ee377 | note | Frequency - 10 Days prior to use
8bd84ff3-301b-53fd-ac6c-5db4d8cc4793 | note | Inspection Type (Visual, other) - Hold Point
06f57650-612a-524d-9717-bfa0bec73d83 | note | Inspection: Key - H
dfb95e9d-0d09-5d93-953f-bf74d09766db | note | Inspection: By (Role Key) - ER
8f1b6a65-4131-4edf-8c9e-a79166bc8d1c | signoff | AUTHORITY HOLDPOINT
f052922d-835e-46a9-b974-670495f07f48 | checkpoint | 2.02 - Reinforcing & Formwork - Cover
f831e5ff-31dc-5294-be64-cc87dce85eb3 | note | Inspection Point: Quality Control Activity - Reinforcing cover to formwork
a8e8c281-1b71-5234-a9f4-a8883055930b | note | Specification Reference - PS Cl. 24.1.13 Table 20.2.2
35196041-e32b-53ba-81c6-56f23da889a3 | note | Acceptance Criteria - TABLE 20.2.2: CONCRETE EXPOSURE CLASSIFICATION — MINIMUM COVER FOR 100 YEAR DESIGN LIFE
a190a936-06ba-5313-b937-1cd85ec6c55c | note | — — — — — — — — — — —
52d7205f-f3cc-5a58-912d-0f6aff2fd37b | note | Exposure Classification ¦¦ Specified Compressive Strength (f'c) — 30 MPa, 40 MPa, 50 MPa
c32f8e7c-3ffb-5f59-8ffe-20da29744627 | note | — — — — — — — — — — —
dfb31e03-17a5-567d-bc94-468cda314714 | note | A2 ¦¦ 40mm, 35mm, 35mm
058f6209-a88d-5cb3-9acb-93b088f90983 | note | B1 ¦¦ 50mm, 40mm, 35mm
6b0ed5c3-cadc-58b6-b764-2f52ddc5194b | note | B2 ¦¦ 65mm, 50mm, 40mm
609d8c10-5c7e-5f16-8e4e-847fbdee0f7f | note | — — — — — — — — — — —
aac68a80-f9d7-5eee-ad79-64b0521fc0b9 | note | Verifying Document - Pre-Pour Inspection
0923bb71-288d-5179-83a2-399c7fb7e68c | note | Frequency - Per Pour
cd6d4f02-dc86-553d-a2a4-84ec784a15b7 | note | Inspection Type (Visual, other) - Documentation
0acfc478-fa65-53a8-981b-afd7fd145bde | note | Inspection: Key - W
84407da7-d02a-57c1-8778-2e49b4ec56ff | note | Inspection: By (Role Key) - SE
f834b1bf-38aa-467e-8f4e-71f18cb33d5c | checkpoint | 2.03 - Reinforcing & Formwork - Reo placement and bar bending
288e0887-38d2-5c00-a11b-8cd881501e40 | note | Inspection Point: Quality Control Activity - Reo placement and bar bending
85d48625-21bf-5556-9a1c-1e89f4aabb03 | note | Specification Reference - Ensure reinforcing bends comform to NZ standards and project specifications
eec091b5-c646-54fb-a813-97f417ff9ef5 | note | Acceptance Criteria - Bars shall be cut and bent in accordance with NZS 3109 to the shapes indictated in the drawings and placed correctly in the arrangement shown;
6fe1a1db-a5e3-5e28-ab11-e030be082539 | note | ○ Unless noted on drawings reinforcing bars to be bent to min bend diameters outlined in NZS3101;
9ce88da7-5ec1-5101-985b-db4f674b7050 | note | ○ Heat bending of bars is prohibited
ff27e326-1dec-5c7e-a3c1-b34e71e9b348 | note | Verifying Document - Pre-Pour Inspection, Bar bending schedule
4e3c32e5-e04d-55e8-a73c-dc425d61cf34 | note | Frequency - Per Pour
581b8cef-e9b3-518d-9a13-65d540afeba9 | note | Inspection Type (Visual, other) - Documentation
e802cce5-d6f8-5e14-b8fe-97ac6f9a777f | note | Inspection: Key - W
2b0f94d8-7442-5b49-8356-9899c55176f6 | note | Inspection: By (Role Key) - SE
41b0961f-2c23-4f5b-86a0-d0d37fefe5ce | checkpoint | 2.04 - Reinforcing & Formwork - Formwork
6cf75c48-a053-53fa-82a4-ea87a83f82ad | note | Inspection Point: Quality Control Activity - Formwork
a506504c-cfe3-50d6-846d-ce7fc7a2367b | note | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109, PS Cl. 24.1.16
5234e75a-35be-5b8b-8fa7-3fa17223c9fe | note | Acceptance Criteria - Formwork to be constructed so that finished concrete will be to the shape, lines and levels shown on the drawings;
28e85dbf-a585-5b57-ab12-76735f5938a5 | note | ○ All forms shall be designed such that exposed concrete edges have a min 20mm chamfer unless otherwise indicated on the drawing;
0f4db29c-ba64-5869-a53b-c6119a808a61 | note | ○ Interior surfaces of the forms shall be treated with a release agent. Any reinforcement in contact with the release agent shall be cleaned thoroughly;
2be3c2b5-ae61-56e0-b412-6cb4c5e478f3 | note | ○ Forms to be sufficiently watertight to prevent grout loss
ea76fdab-d189-5c43-8e46-3e661264f5b7 | note | Verifying Document - Pre-Pour Inspection
c5c85d18-ed4e-5e34-9373-cb0eab0bb5e7 | note | Frequency - Per Pour
7f70c6c6-1547-5021-ba97-c176b4680c6c | note | Inspection Type (Visual, other) - Documentation
ff0a3100-d6ee-53df-ab54-33799e01f602 | note | Inspection: Key - W
d4ce15e3-fe9d-524e-937a-388d00fbca8f | note | Inspection: By (Role Key) - SE
199ba5f5-67f8-4913-8006-49550ba61571 | checkpoint | 2.05 - Pre-pour inspection
246b3ed1-2bd5-527d-b621-32846878332c | note | Inspection Point: Quality Control Activity - Pre-pour Inspection
afbc4b6b-c29d-5360-98db-d2f8e7abdaf2 | note | Specification Reference - PS Cl 24.1.17
0aa33959-ec28-5dd1-9607-4df67805a401 | note | Acceptance Criteria - Pre-pour inspection - Engineer acceptance
eff2e520-d4d3-5a93-a927-f6f888360273 | note | Verifying Document - Pre-Pour Inspection
2347e3d6-dfeb-51e8-8f27-72da4f9e13a9 | note | Frequency - Per Pour
c929c080-913f-58e3-800d-537635a568cc | note | Inspection Type (Visual, other) - Hold Point
58423bf2-1b74-5053-b571-ccd414b52d0e | note | Inspection: Key - H
b525dfb3-219e-50a5-8b34-c0d84973bd81 | note | Inspection: By (Role Key) - ER
7ea88663-e630-4589-bb04-22b5270bc63a | signoff | AUTHORITY HOLDPOINT
59ba7d3e-4d0a-4528-8a38-301f2c584ed1 | checkpoint | 2.06 - Formwork and Pour - Finishes
87f019ac-dd38-5b6f-90f7-5451048f1012 | note | Inspection Point: Quality Control Activity - Formwork and Pour
8a90af33-ab71-5d15-8a88-644d168488e6 | note | Specification Reference - PS Cl. 24.1.16
8c59ef89-c969-5f9d-b31b-5048c4e4a637 | note | Acceptance Criteria -
f5957b3e-6fc0-5cda-99b0-6a5320d15803 | note | Verifying Document - Photo & Pre-pour Inspection
ed11c89e-acb3-55d8-8336-fe094ecf47bb | note | Frequency - Per Visible Surface
a6aa407b-6b48-5f71-8e61-a700288d479d | note | Inspection Type (Visual, other) - Documentation
6cbb0b93-ad32-530c-a153-f5702a3603e2 | note | Inspection: Key - W
aaa2b9d2-29ef-549d-8acc-186441d98a9e | note | Inspection: By (Role Key) - SE
820a48e1-eea0-4ee9-8d09-2d577fcc9510 | checkpoint | 2.07 - Concrete Pour
fcb9a19c-6ff0-5e4d-9ff3-0cf0bf79a58a | note | Inspection Point: Quality Control Activity - Concrete Placement
672d9de1-1f28-5bce-8638-b5edb564e557 | note | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing
4044aa86-b691-549b-b215-487bccec8c94 | note | Acceptance Criteria - Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer.
4cf64a08-84a4-554c-92e0-fa2306aaf6a1 | note | ○ Concreting to be a continous operation between ends of members and/or properly formed construction joints.
e79ee082-239f-589f-a4be-f9923ec26c38 | note | ○ Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m.
c794e989-37dd-50c9-8b7e-544a065c4c85 | note | Verifying Document - Pre-Pour Inspection
6c06b881-a9a2-5d13-aa58-6ac61eec75b0 | note | Frequency - Per Pour
4caea056-09ad-5291-8a82-1c0566db7c90 | note | Inspection Type (Visual, other) - Documentation
40a28413-2758-5395-b0ce-4ac8813cb1cc | note | Inspection: Key - W
81588555-43ab-5dc3-a0b2-a11a54bc249a | note | Inspection: By (Role Key) - SE
8d6b717f-5893-41b0-a1ce-ead160f21c88 | checkpoint | 2.08 - Concrete Pour
b7a0c85b-7907-5b6b-b4ac-25579f1912fa | note | Inspection Point: Quality Control Activity - Concrete Test Cylinders
99b5627e-c6d0-5235-8310-fd95e412f394 | note | Specification Reference - PS Cl.24.1.14
267d7096-3164-54a4-8455-30362e8978cb | note | Acceptance Criteria - A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days.
7d9c4a15-37b6-5833-9249-718733c96fcc | note | ○ Strength of concrete = Dependent on Mix Design.
3074f9ae-642e-5cfe-958c-e8a88cf5fa20 | note | Verifying Document - Lab Report
87fdafc6-3e77-5fde-a2fe-48a74672d3bb | note | Frequency - Per batch
8dd8e531-dd1a-59b4-ba96-f02d5878871b | note | Inspection Type (Visual, other) - Report
72467d16-5639-55a4-a6f9-36583ea2a7fd | note | Inspection: Key - W
df3653b6-2985-5885-a99d-66d83e75dbfd | note | Inspection: By (Role Key) - SE
50f153ad-c03b-4659-abd1-f45626cbbd21 | checkpoint | 2.09 - Concrete Pour
6dcd202d-4cce-5688-8398-d5759357353c | note | Inspection Point: Quality Control Activity - Approved Concrete Mix Design
64e0cf71-3486-5106-95d6-20a4ccbfb3dd | note | Specification Reference - PS Cl 24.1.3
56997b59-1d32-5b56-998a-ebb6ee49b357 | note | Acceptance Criteria - Confirm correct mix design brought to site
7b3d2d8b-b19b-5bd2-8dec-5747148afd02 | note | Concrete Docket Showing:
9163bb08-6eba-5b29-b8ff-e211e3e6849f | note | ○ Mix Design Item Code
2b2c60cc-462b-5d9c-99a1-0fb900884bb2 | note | ○ 28 day specified strength = 45MPa
9fb569f2-5e8e-5afb-bdd5-19aa44019328 | note | ○ Concrete placement method that the mix was designed for - Pump Mix
f27b8797-fd30-5905-95b5-f1e558e64739 | note | ○ Type of supplementary cementitious materials (if used);
ffdb9a9b-2ee1-5fcc-9d4c-d72037071e9e | note | ○ Slump (target and actual slump when measured);
0217ddf2-3868-5f70-9cc6-93113eec0225 | note | ○ Order and Delivery Quantity
83aeec74-c594-5873-a4df-f917ed1aa733 | note | ○ Load Time out of plant
4e2f4bde-e0dd-5558-a987-b815a3f8a260 | note | ○ To site time
1099e568-6e7c-5506-8edb-05fa9ef53a37 | note | ○ Unload Time
08ce4c8e-461e-5f0d-aa77-82fd0d713861 | note | ○ Associated Products e.g. cement and additives
5df2e309-6381-5b59-9c9a-e714d95f51e5 | note | Verifying Document - Concrete Docket
de0b3cf9-c0bf-5360-8172-1919bf9bdb9f | note | Frequency - Each truckload
c5713675-7233-5ba1-8ee9-7a71ccb932f2 | note | Inspection Type (Visual, other) - Documentation
d8d4ebd0-ee8c-5745-9e34-9000e710a5b8 | note | Inspection: Key - W
852729b8-49ca-5707-a0ea-1d0a551c1224 | note | Inspection: By (Role Key) - SE
2a5c2fef-d00f-498f-85a6-2f32f3d1251e | checkpoint | 2.10 - Concrete Pour
dba1c30f-4306-5365-8cc4-09ca8b1b1147 | note | Inspection Point: Quality Control Activity - Slump Test
a52350be-1ac1-5ea9-b657-d59e38f15601 | note | Specification Reference - PS Table 9.1
f9686b1a-dcc8-593c-a390-3f5230dec325 | note | Acceptance Criteria - Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm.
82b64d94-ba23-53a9-97e5-830892016019 | note | Slump test tolerances:
6c7f7c5a-d110-53dd-89f0-b724ad37874f | note | — — — — — — — — — — —
918464ea-6afc-5999-adc3-325aabd71d59 | note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
9098a3ae-4ad8-5570-84d4-a29b6fd3b329 | note | — — — — — — — — — — —
8ee8577f-053f-58bd-81f5-3b7eb851c442 | note | 60 or less ¦¦ ±20
e93d9376-61f0-580e-a85c-a6bca1ba5bab | note | 70 - 110 ¦¦ ±30
772767f1-3d3d-5dce-8f54-1ff49e20dc56 | note | Greater than 110 ¦¦ ±40
18e2b044-3901-5de4-aac2-46cb4bf55754 | note | — — — — — — — — — — —
59a994c0-e540-5279-bd80-6fbbbf3b792d | note | Verifying Document - Visual/Photos
d4e8ca20-6dc9-58bd-beb2-0772727b0c20 | note | Frequency - Each truckload
7ed7ef57-63b3-508c-a18d-beb550c21583 | note | Inspection Type (Visual, other) - Test
ad878cf2-9ba9-51c1-8b3c-0b05d6885d6e | note | Inspection: Key - W
2afa7e65-950d-581e-8f83-a3161f4dac65 | note | Inspection: By (Role Key) - SE
2f8b3ac2-d02a-4951-80d4-1ca12497af27 | checkpoint | 2.11 - Concrete Pour
69631847-9c9e-5d6c-8ef5-a0aa6dea4ad5 | note | Inspection Point: Quality Control Activity - Time Limits
fca06a29-903e-530c-924d-3b158a7ca842 | note | Specification Reference - PS Cl 24.1.17
9b332ec9-7e20-5742-a0a5-64354a4015d9 | note | Acceptance Criteria - Incorporated in the works within 90minutes of batching.
9cc994d2-d619-5fae-8a7e-71cffff00958 | note | ○ Incorporated in the works within 30minutes of discharge from concrete truck/agitator
ad254525-6ef0-5d18-a0df-d672e2abd676 | note | Verifying Document - Dockets & pour sheet
6c299560-b4f0-5e91-bb63-ded2ef7eb88c | note | Frequency - Each truckload
102c195b-857c-53ed-a72d-479eb7daf0ed | note | Inspection Type (Visual, other) - Dockets
a5b3aade-2499-5cbe-8b57-cd0fac3583c3 | note | Inspection: Key - W
b961ef7a-792f-5a1c-8ca0-bf40d0742ab6 | note | Inspection: By (Role Key) - SE
630bd1f5-c3ad-4677-8b96-4c23bc2b9351 | checkpoint | 2.12 - Concrete Pour
2a2d3fa1-9081-53ec-b707-46f4b1af0d7b | note | Inspection Point: Quality Control Activity - Concrete Vibration
68095e1e-3e69-5d1f-bb18-af1bfe16e1dd | note | Specification Reference - Clause 7.6 of NZS 3109
a5b0e28d-9523-5e93-9e3f-031ede5828e1 | note | Acceptance Criteria - All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: -
db3433db-172e-5247-83d5-f5fba579d980 | note | ○ All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured.
26a959f0-7095-5d3a-aed7-8f83b8f2ce8b | note | Verifying Document - Visual/Photos
b5195e1d-2285-548c-9cf7-421c298e1788 | note | Frequency - Per Pour
48fa90bf-941b-5d0d-8ad1-4d1253a3f810 | note | Inspection Type (Visual, other) - Visual
10f8ab5a-074f-52c4-9f36-82a3a0468ddc | note | Inspection: Key - W
38b5f3e6-52c7-55f8-a4ee-a91922208de7 | note | Inspection: By (Role Key) - SE
21d324b9-f40e-4be9-876b-13f5724bc88a | checkpoint | 2.13 - Post Concrete Works
810ca072-3d5c-5fc5-9908-41708e859328 | note | Inspection Point: Quality Control Activity - Curing
5cff1ff6-5d68-5865-ab9b-8cc6e8acc3d9 | note | Specification Reference - AS/NZS 4671: 2001, 'NZS 3109
ca3ed8a9-a831-5329-b83d-3cab2bb6d651 | note | Acceptance Criteria - Concrete to be cured for min 3 days;
97f4509e-9985-53c6-8c30-0a975ed6c684 | note | Verifying Document - Pre-Pour Inspection
69a5d4b7-4494-59ad-9039-5b8ae328343a | note | Frequency - Per Pour
12b89d33-a80e-5559-b53f-b0745da55839 | note | Inspection Type (Visual, other) - Documentation
08a06ac7-d099-5ac8-bf10-6a0a68bbec7f | note | Inspection: Key - W
b8d5e833-b8a7-5216-b4d0-f467b7e67157 | note | Inspection: By (Role Key) - SE
71c9dfa8-1139-491a-ab2d-c153a1b42cfd | section | SECTION 3 – FINAL INSPECTION AND HANDOVER
47e58792-ef08-4ecd-8c83-2034474b2634 | checkpoint | 3.1 - Survey As-built
8f61b2bc-c062-583d-8869-2ce746151367 | note | Inspection Point: Quality Control Activity - Survey as-built
0b7ee739-3ccf-52f7-a5af-c078cc54b183 | note | Specification Reference - Specification Cl 26.4 & AS2159 (Page 167)
fbc100a3-b630-596e-b085-c2602277d33f | note | Acceptance Criteria - As-built survey CAD File
18c3541d-44c9-5cfb-aa39-38216065d0ee | note | Verifying Document - As-built survey CAD File
ebc0df53-b3e9-5904-8787-76a9fcec5aa1 | note | Inspection Type (Visual, other) - Documentation
c1184332-1c24-5a1b-87aa-48b2fbae9695 | note | Inspection: Key - C
10e9b802-6d65-579b-a385-8fcf4a3ddf00 | note | Inspection: By (Role Key) - SE/ER/SV
608836c6-d580-4f07-bb61-5452dcef50e4 | checkpoint | Inspection Point/ Signature & Date
052dfe16-b9a5-5211-a7e5-3c3d2601c7ec | date | Date:
e7a27068-7764-5ad4-8f35-403b7aae59dd | textbox | Customer Requirements Verification Record / Location/ Hold Points
2c0a8af2-57ab-4160-b432-d3bb383f6a4b | signoff | Downer Signature
df729b3c-3315-48f2-a9d5-35188d27738b | checklist | DS2681-SH58-ITP-C-002 Earthworks Cut | itp | DS2681-SH58-ITP-C-002 Earthworks Cut
67451a6a-8cea-4ef4-a602-3d151731a5f4 | section | SECTION 4 – IN-PROCESS INSPECTIONS
eb5fd506-7948-4670-96c6-7831c5fafefd | checkpoint | 4.1 - Topsoil Depth Checks
de3d5445-3307-5b23-8aba-28f82720e2d1 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
44f07abe-85b7-54db-b372-d03d9a585c2c | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
a4de364f-08bf-5b9c-b022-6dc85551c8d9 | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
5510836b-ae61-540a-b704-85c3a5a6bfe6 | note | Verifying Document - Site Photos, Record Sheet
4103d90f-e4e8-5da3-82b6-0ff867bb7135 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2eb5b3dc-7fbe-5392-8414-62b6bcdc5cf3 | note | Inspection Type (Visual, other) - Witness
9e0530ad-9dea-5be2-8d73-2a9795b48e4e | note | Inspection: Key - W
d4639d9a-6767-5269-beb3-1215691074e9 | note | Inspection: By (Role Key) - SE
7f30c528-f201-40dc-a527-ab421a6f883e | checkpoint | 4.2 - Hazardous & Classified Soils
a664ce29-a8e5-5d63-bf17-014a35d000d3 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
f27256d6-4592-5d4e-b73e-a3f74a51ddcb | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
3936fc1e-e1d7-59bf-809a-00f5e6081b10 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
ca6b4c12-6d5d-5ba8-9c78-a9d7afb7bd23 | note | Verifying Document - Visual, Site Photos
4c1efc39-f017-5255-86c2-be965b493de3 | note | Frequency - Continuous
5133fb55-1305-57a9-92d0-3b06cc30e7bb | note | Inspection Type (Visual, other) - Witness
1cb75dd6-d38d-54c4-8a6a-1d495d5c3c41 | note | Inspection: Key - W
8e4f7cfc-35d6-5afe-b23d-7b61efbc098f | note | Inspection: By (Role Key) - SE
7486c58c-9fb9-4a38-88b8-d8792c7aa396 | checkpoint | 4.3 - Final Cut Observation Monitoring
347fdff0-3102-5435-ab25-bee766125209 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.6
4c207fc2-d9dd-50df-b46f-e08c487449e2 | note | Specification Reference - Continuous visual assessments conducted with Stantec Representative. Contractor to address design change if instructed
3ba2bd1d-904b-51b3-b6d0-9bb09aa69e01 | note | Acceptance Criteria - Agreement with Engineer's Rep
66603339-865d-527b-956f-0eb5c2b210cb | note | Verifying Document - As Required by Stantec Representative, QC-01 Earthworks Checksheet
4f7df1dd-eee8-52c9-81fc-4ba03ad868e4 | note | Frequency - As requested by engineer
d2081a75-cfd1-5c2e-b034-a5ec45a3a4b5 | note | Inspection Type (Visual, other) - Hold
56b79a36-efd0-5403-a2ad-bb8a1356d7da | note | Inspection: Key - H
dbb2871b-47f9-592a-8990-7dd356b5fdf4 | note | Inspection: By (Role Key) - ER
f191c6b6-2aab-4164-96e9-e47a0b3675af | signoff | AUTHORITY HOLDPOINT
2cdfb66a-9389-4627-8667-eef40cd2af5f | checkpoint | 4.4 - Cut Batter Tolerances
132eeb5a-fe9d-5df7-9be4-782120e3ef4c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.7
56c83086-c7e9-591b-b20c-40fe8793f938 | note | Specification Reference - Post-construction - Excavation of batters complying with design issued and within tolerance
ee66d3c0-49a5-5d67-a4b8-18faff38f4bf | note | Acceptance Criteria - Slope Tolerance 1H:1V or Flatter: +300 / -300 mm
79a3c917-608e-50cd-ab7f-e9fde7c7f119 | note | ○ Steeper than 1H:1V: +300 / -600mm
bc450905-2158-5089-979e-c8eff2fda31f | note | Verifying Document - As-Built and DN-QUA-QC-01 Earthworks Checksheet
207498a5-e043-56c3-835c-476f874fa023 | note | Frequency - Continuous
efa9913e-4bbe-5fbd-93b7-b9e6a3302e68 | note | Inspection Type (Visual, other) - Witness
d3cab161-6063-560d-945e-a4cc933e71a5 | note | Inspection: Key - W
ab994e35-4b7d-51e2-9377-c0539f957500 | note | Inspection: By (Role Key) - SE/SV
9ac63d2d-3fdf-41a8-8a9e-87424a2ecd20 | checkpoint | 4.5 - Site Fill Material - Segregation of Material Type
6f0f9b0b-029a-522d-a566-d1cf24cf370c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.8
aceeaf6b-a147-5532-9113-38bc69c47f73 | note | Specification Reference - Moisture sensitive material stockpiled
bb49d682-186e-5a46-813b-e57556aa8fa2 | note | Acceptance Criteria - Drainage blanket (polythene cover) if any material is stored on site to avoid saturation
c7f353d1-7f18-5f61-872b-b7f030221da3 | note | Verifying Document - Visual, Site Photos
801989f2-a1a7-5cb5-a394-0c7653136733 | note | Frequency - Continuous
e72a8aec-2da8-56be-bced-9018554b9697 | note | Inspection Type (Visual, other) - Witness
0d762aba-083d-5501-b776-f4c5925a4422 | note | Inspection: Key - W
08311d38-a7ef-5a95-b4bd-5c3fa8e79616 | note | Inspection: By (Role Key) - SE
192b71df-9dfe-44fb-ad89-61f682f2a57c | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
e676d3ad-166c-4de3-98c3-ae9896beecb7 | checkpoint | Inspection Point/ Signature & Date
b072bae1-74c0-5098-bd68-d5405a971db5 | date | Date:
18d8e4a4-5b1d-58d0-8bf9-f29766a313f4 | textbox | Customer Requirements Verification Record / Location/ Hold Points
2a4a07e0-640c-4290-bbe6-638dd12e0a67 | signoff | Downer Signature
90218fb0-56ec-4157-b8eb-076f3f2fd692 | checklist | DS2681-SH58-ITP-C-003 Earthworks Fill | itp | DS2681-SH58-ITP-C-003 Earthworks Fill
d8549d1c-6084-4eb6-aa34-e1037e972367 | section | SECTION 4 – IN-PROCESS INSPECTIONS
9c62c46d-be03-4325-a269-2e1cce813bfd | checkpoint | 4.01 - Topsoil Depth Checks
5b8fa5b8-196b-5600-971a-f3b6d4d676fc | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
a452a378-61e0-5c00-b74c-c726008ddc11 | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
03b3720f-8844-514c-9229-a15264506e4d | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
08613c48-b482-5be7-a20d-be6627cb7408 | note | Verifying Document - Site Photos, Record Sheet
5e42a0de-49e9-5c4a-9848-bd849cebdb25 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2795d9b2-d7e0-5caf-8f7a-d709a310f2ca | note | Inspection Type (Visual, other) - Witness
3c37b622-502a-5fdc-8c4e-c6d62706b017 | note | Inspection: Key - W
a7deaea1-b306-5546-aefc-792f32b9a252 | note | Inspection: By (Role Key) - SE
4f861c4d-56fa-4f86-853b-b326a5bf7d87 | checkpoint | 4.02 - Hazardous & Classified Soils
31f36bba-8168-5228-8e14-d54e6ebb023d | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
602225a7-35c1-539c-84a2-97e895accb97 | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
9e4f6c65-b625-582f-9951-e8ae49d7aa98 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
4aa4b873-ce3c-5c30-9ddc-6654f6e713b5 | note | Verifying Document - Visual, Site Photos
9a2e7738-8add-5898-b720-a8718215117e | note | Frequency - Continuous
54149323-7e72-5849-b492-bf0b4e9e66bb | note | Inspection Type (Visual, other) - Witness
25ac1de1-7c21-582e-addc-72843b5c923a | note | Inspection: Key - W
3618481a-1a64-57a8-9586-d337c91a4efe | note | Inspection: By (Role Key) - SE
c77466cb-88d4-4d6d-a030-db3f490b0008 | checkpoint | 4.03 - Subgrade testing - Trim and Compact
5a6340d0-a1e7-59c4-9ff0-588daa5c7eeb | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.10
b3e2023e-c87d-5688-9fe8-5c28b6e001fb | note | Specification Reference - Trimming & Compaction of in-situ subgrade. Conduct plateau test.
73cd4ba2-b734-5a25-bb8e-51f26523c1bc | note | Acceptance Criteria - N/A
a3135f5c-ffa6-566b-a008-acdf06b7a12a | note | Verifying Document - Plateau worksheet
cd56e528-0d47-5c9b-abb4-a6f1f7588792 | note | Frequency - Full surface
76f971c6-ab70-5525-bc64-d7cd53497773 | note | Inspection Type (Visual, other) - Witness
f9e71c06-ff1d-5a81-b94c-c384b2eb2de0 | note | Inspection: Key - W
9af2e9cd-1409-5027-b8b4-57fd373d5b98 | note | Inspection: By (Role Key) - SE
6e0b306e-8217-45b6-aa98-3f2da0ad944c | checkpoint | 4.04 - Subgrade testing - Scala
f0fc626b-ce1b-5fc1-a9e2-beb9b21d8252 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.11
36376860-ec21-5a49-8311-bb3c84021acb | note | Specification Reference - Scala Testing
f2c390cd-8a69-5e01-80fd-4edcc1f34413 | note | Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement
e92b1fd8-2193-5e1c-828b-0e6a473a274b | note | Verifying Document - DN-QUA-QC-04 1m Scala Worksheet
deec5fd9-20d3-5143-a3bc-06d8138e21c3 | note | Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
35e62849-6a45-54a6-a33a-948f4a254b61 | note | Inspection Type (Visual, other) - Witness
e6ad1732-5fb2-569e-ab78-d897cd7be49c | note | Inspection: Key - W
2e49b9f7-548e-5556-99db-562e0914b2eb | note | Inspection: By (Role Key) - SE
d08f3a23-a67f-46a3-b73b-2d43b3bf99fb | checkpoint | 4.05 - Subgrade testing - Benkelman Beam
28f510e5-01d5-515a-973a-2b22920e6ab5 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.12
bf32ece9-b533-5d25-826a-80b1481b63e4 | note | Specification Reference - Benkelman Beam Testing
4dfdc5b1-2fd1-5773-a841-951f1236e3f9 | note | Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm
3a4a1436-0c04-582c-9fe8-166f28a73d8e | note | Verifying Document - Lab report
8167b6e0-f261-5c03-b8b7-7e2a11cf30eb | note | Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
5d887dfa-3825-5eb6-918c-a27123ab1be0 | note | Inspection Type (Visual, other) - Witness
e06d1c39-0759-5f50-bf41-af433f55d06c | note | Inspection: Key - W
de8ed31f-dca1-543c-ab81-20618767ee4f | note | Inspection: By (Role Key) - SE
69f4e90b-552e-439b-988f-1e72f0b7b957 | checkpoint | 4.06 - Subgrade testing - Proof Roll
1839ae8e-4785-5e89-ae30-6878bdbefa44 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.13
b84289c8-b380-5f42-9801-1dc5845914e1 | note | Specification Reference - Proof Roll
c1f942b1-a560-533c-b67e-43446bab6d03 | note | Acceptance Criteria - As instructed by the Engineer
6d7c2351-765a-59e4-8dd6-c7b85ae08027 | note | Verifying Document - Visual Assessment - Sign off on ConQA by Engineer
cd2ca153-edff-5158-b93a-c3c9bff4a274 | note | Frequency - Proof Roll: Full surface using suitable plant
a473ece9-ef13-57d1-b8b3-63e66c288983 | note | Inspection Type (Visual, other) - Hold
17decdd9-724b-5160-953e-fbe77be61e8c | note | Inspection: Key - H
b1837a51-96fb-5325-b4fc-49fde76f9d1e | note | Inspection: By (Role Key) - ER
4034b935-2e19-43c5-8b87-422e5ce2a877 | signoff | AUTHORITY HOLDPOINT
d234d476-891c-4e8b-ac9e-658ab18f53bd | checkpoint | 4.07 - SIL Layer
904aecf4-f0cc-573f-b855-48af75eaacc6 | note | Inspection Point: Quality Control Activity - TNZ F/1
8a1fda63-0c20-570c-bfb2-2df5f5cc97d3 | note | Specification Reference - SIL Layer detail, if required
994492a1-c6cd-5a5e-b303-6092164af202 | note | Acceptance Criteria - As instructed by the Engineer
91c0ddac-fcd6-5183-8322-3d3771852b34 | note | Verifying Document - ConQA Sign off
9390676f-62e2-5e80-af62-a9feec2f8987 | note | Frequency - Per Lot
68aee8ba-7933-5343-81f9-997a6891b16a | note | Inspection Type (Visual, other) - Hold
8ea3ca79-8f36-5d18-b6a4-b250727a9ef3 | note | Inspection: Key - H
d7b39f34-5a0f-593e-8547-293759cbf1ad | note | Inspection: By (Role Key) - ER
9e8be85e-82e8-4591-8c89-c4c62823b4f9 | signoff | AUTHORITY HOLDPOINT
baff8782-7812-409c-955d-22faaf8a2d45 | checkpoint | 4.08 - Fill Compaction Trial
3b1aa582-7080-50f7-a743-4d1a834e0c3e | note | Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11
b59340bf-1c1e-5b01-9685-d1d249c2da6f | note | Specification Reference - On-site Testing - NDM, Visual, Shear Vane
3072fcc1-2d40-5f8c-a101-d668ffc305b1 | note | Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P
a16bbc46-f692-5511-98cc-f9dba2f08730 | note | Verifying Document - NDM Worksheet, Shear Vane Worksheet, Plateau Density Sheet
245f9472-8924-59b7-af93-07fabe64fbc0 | note | Frequency - When a new type of fill material is used
cb7f9df4-0ad0-511e-9839-256019215ea8 | note | Inspection Type (Visual, other) - Hold
9ad8e962-7572-5e64-9aef-a31d67b4fc4e | note | Inspection: Key - H
c9c7d82b-adec-5235-81cc-c72bb9211895 | note | Inspection: By (Role Key) - ER
f985a566-05fe-4bca-aa0a-63ece48458e9 | signoff | AUTHORITY HOLDPOINT
ac487538-1b27-4fb7-82cb-3d1c832dc83b | checkpoint | 4.09 - Fill Backfill layer thickness
9dc0ddd5-7081-5c5b-aad6-244ddd534627 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8
9100536d-2452-5d74-8636-8012cb1a7aa7 | note | Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction
b573abdd-0e24-5b25-9997-15ae932b717b | note | Acceptance Criteria - Fill placement not exceeding 230mm
c7aae880-1974-5f3b-9be6-50d71e180eb1 | note | Verifying Document - Visual, Site Photos and NDM check sheets, DN-QUA-QC-09 NDM Worksheet
e281d108-66fa-59e2-8851-f46838f6719d | note | Frequency - Every layer
6f256caa-f61b-5b64-b071-a38145b5f2e7 | note | Inspection Type (Visual, other) - Witness
be7beb94-ad2b-54dd-83f0-38c8f5564a6d | note | Inspection: Key - W
35b64125-bc7b-5da4-be26-97b71b7af86c | note | Inspection: By (Role Key) - SE
bcc30a6b-119d-4743-8a79-baaf6dc3ee43 | checkpoint | 4.10 - Fill Compaction Testing Laboratory
613ffacb-21f8-55a0-ac5a-8f2d6e0c9561 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12
abf1c975-f467-550d-8803-5f63bbcc3a2f | note | Specification Reference - Water Content, Standard Proctor and Wet Sieve.
87cb7aef-ee1d-547e-ac81-b90003b86845 | note | Acceptance Criteria - N/A
404f0300-be8d-57c5-9ae3-09ef3f08131c | note | Verifying Document - IANZ report
45d7b2e9-2ab1-5bbb-ba2e-47b28b92899d | note | Frequency - WC - 1 test per 400m3 with 2 tests minimum per day, MDD & WS - 1 test per 2000m3
e4b62afa-6a64-517f-bfcf-bfb487b48f5d | note | Inspection Type (Visual, other) - Witness
78e96303-1f07-5a1a-b96e-b20bc84fe4c0 | note | Inspection: Key - W
66ee5b0c-a583-5bca-87d4-fe169198728e | note | Inspection: By (Role Key) - SE
4d840a77-0d83-418d-8eaa-5d3ace198277 | checkpoint | 4.11 - Fill Compaction Testing Site
170c0ce9-da4c-51cd-a656-534cc2598816 | note | Specification Reference - Compaction test by plateau
4cd4ea6f-fd7d-5182-9cb9-7ecd963f4105 | note | Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions
f435ba24-e53f-5101-81ee-295144d7851c | note | Verifying Document - DNZ Plateau Test work sheet
95c64cd4-0399-5ee6-84c8-fe44e0fe532b | note | Frequency - Daily
05ff474c-f5e3-5368-a1e9-39775e6ad1b0 | note | Inspection Type (Visual, other) - Witness
9df4d291-794f-5154-8fd0-3f6e2da0ae60 | note | Inspection: Key - W
8cd77cf0-88d2-5621-9a62-ae0a6c6560e3 | note | Inspection: By (Role Key) - SE
9bb0e863-25ab-4e2e-a5c8-736f7a3cbf9e | checkpoint | 4.12 - Fill Compaction Testing Site
a0f51fc5-3327-536a-a294-1323489b698c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12
e70d9530-82db-512d-bb7d-6470d91d214f | note | Specification Reference - NDM and OMC testing of fill material, Shear Vane
15556765-8e6f-5346-b003-a5130be21e1e | note | Acceptance Criteria - Moisture Content: between-2% and +4% of OMC
7fcab2ac-a9ab-5872-b45d-bd68049bbef8 | note | ○ Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95%
a801c928-555b-535f-9716-82c12c5aa57f | note | ○ Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only)
e54e9950-49f6-5033-8c0b-245f5090e787 | note | Verifying Document - NDM Record Sheet, DN-QUA-QC-09 NDM Worksheet, Shear Vane Sheet (Cohesive soil only)
6fb339aa-e367-5272-b3ec-08785b7ada50 | note | Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day
017b0e48-efcf-5a5e-bb2b-aa847de2c09d | note | ○ Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only)
d36e4bf3-83f7-5ad9-b4a1-1195d43e9525 | note | Inspection Type (Visual, other) - Witness
479c803f-863e-5ecf-995d-ac9522d1ed37 | note | Inspection: Key - W
91ffb9e9-9267-5718-9b08-82760cad3387 | note | Inspection: By (Role Key) - SE
49dc47d4-4477-45df-98df-0234e7253c87 | checkpoint | 4.13 - Fill Tolerances
40d82a36-02ad-5737-8acb-c456c28f5187 | note | Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11
9e700a68-8e22-58e3-9974-7d3dfdfa1e95 | note | Specification Reference - Survey of finished surface
e79c980c-87de-5e44-b10b-3236c822d8b2 | note | Acceptance Criteria - Tolerance of +-50mm
447e271e-bca4-5ebb-add8-7fc00e2da9c3 | note | Verifying Document - As-built
bb9bf85e-e97c-59a1-ae14-091787bbd065 | note | Frequency - At Completion
460b02c8-ced0-56fb-9524-2652fccfcaa1 | note | Inspection Type (Visual, other) - Witness
7feba2b6-df9e-5aa3-954c-fc41cf3abc3b | note | Inspection: Key - W
d7211d8d-3c2a-58ce-ac35-6a15b5ea8287 | note | Inspection: By (Role Key) - SE/SV
b9a3e932-94cd-4693-a41e-146bbf0d7650 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
91d48c13-d2f8-45c4-af23-fde24dbb16ad | checkpoint | Inspection Point/ Signature & Date
c5b2747d-ce3f-524a-a1e6-6023b29c528c | date | Date:
db896672-4da5-53f6-9550-09d229e89fb7 | textbox | Customer Requirements Verification Record / Location/ Hold Points
f5dea672-25bd-4897-adf3-d2ef22a81c2d | signoff | Downer Signature
1c93c2d6-bdb0-4261-a86d-010847d20f66 | checklist | DS2681-SH58-ITP-C-004 Anchorbloc Retaining Walls | itp | DS2681-SH58-ITP-C-004 Anchorbloc Retaining Walls
0070af52-ca9f-4657-b84e-5430e9606f44 | section | SECTION 4 – CONSTRUCTION
28febff6-18b2-4eed-8c69-60f77e5e65ba | checkpoint | 4.1 - Foundation Test Requirements
844677e1-892b-5754-bf23-f34964ff1bb0 | note | Inspection Point: Quality Control Activity - Following Excavation
1bf8478f-3c59-5fc7-a1e2-f998e8596c2c | note | Specification Reference - Project Specification Cl 18.5.4
36c89919-a314-5702-b387-13ab05b76e41 | note | Acceptance Criteria - Minimum of 3 blows/100 mm penetration
3e953cbf-84b7-5012-8974-21f343c9b5c0 | note | Verifying Document - Scala Testing Record Sheet DN-QUA-QC-04
d1c7957f-9c55-542d-a7d0-953ccac6b82e | note | Frequency - 10m intervals
4ce7b373-4de7-513f-9124-ae6ea04b99ce | note | Inspection Type (Visual, other) - Witness Point
771a23ab-284f-57de-8ed5-a0274693c903 | note | Inspection: Key - W
2315644c-20db-5ed2-ac23-de6c72d40277 | note | Inspection: By (Role Key) - SE
af5cfe66-efb5-48d9-a259-2b2f1deb29f0 | checkpoint | 4.2 - Foundation Subgrade
e9f0d9de-9707-549d-9c2f-bf7d34f0cefb | note | Inspection Point: Quality Control Activity - Following Excavation
31e5f62b-c8c2-5c6f-9f49-90871a71b49d | note | Specification Reference - Project Specification Cl 18.5.2
f2b0981d-4e82-5275-bb42-37db53fcc538 | note | Acceptance Criteria - The foundation for the retaining wall subgrade must be inspected by the Engineer and shall be approved for the placement of the wall facing elements and reinforcement elements
143f9bac-18a2-5a66-b48a-bfc590592a19 | note | Verifying Document - Site Instruction - Hold point release / email
a27824a7-5ade-59f9-84da-f112d52ffb81 | note | Frequency - Following Subgrade digout
aaa0e8ce-5732-5e0a-8248-12df5f431b52 | note | Inspection Type (Visual, other) - Hold Point
ddc2ba18-913f-50b9-97c4-0d55c304b4b6 | note | Inspection: Key - H
007e824e-5690-5524-94c2-e0043195e5e5 | note | Inspection: By (Role Key) - ER
e2d4f669-f265-4e64-b931-fffefa79fbe8 | signoff | AUTHORITY HOLDPOINT
72441abb-2df4-4046-b533-cb988653e1ef | checkpoint | 4.3 - Foundation AP65 - Compaction
df51bac7-08d7-5d9d-9655-45cdd817c2fa | note | Inspection Point: Quality Control Activity - Foundation prep
75f752e5-14be-5ca4-b3ae-fccce2384761 | note | Specification Reference - Project Specification Cl 18.5.5
138eff23-e1d8-5bbd-9616-a1f07b74d3b0 | note | Acceptance Criteria - Foundation Compaction: 95% MDD and+/- 2% of OMC as determined from the plateau test/or lab testing. None less than 92%
dfb967d6-b369-53ca-a0fb-7809e9137234 | note | ○ 1 set of NDM tests (comprising 5 No. NDM tests per set) are required per 200mm fill lift
b5b66591-652a-5625-960e-653187a9090c | note | Verifying Document - NDM Test Results DN-QUA-QC-09
d6b58bf9-e212-5340-b8c7-1b45d7c19547 | note | Frequency - 1 set of NDM tests (comprising 5 No. NDM tests per set)
a6692d15-3ca0-52cc-bbe9-e06126f7924f | note | Inspection Type (Visual, other) - Hold Point
e2b79bb1-0609-5539-b48e-b3a5dd785a34 | note | Inspection: Key - W
9b6299f0-6fa3-51e2-b35e-a03d4a5deee6 | note | Inspection: By (Role Key) - SE
e9fcc3b3-0cfc-4702-9d91-f476f5e8302c | signoff | AUTHORITY HOLDPOINT
2b69c546-bb7c-4e6d-a5da-975196c7d200 | checkpoint | 4.4 - Anchorbloc Placing
13972aca-bc64-55e4-b21d-d1d5d0a1986e | note | Inspection Point: Quality Control Activity - Survey as-built
f00a0b43-dd92-5332-8f68-bc50724fbbd7 | note | Specification Reference - Project Spec Cl 18.5.7
b5bcbdf8-db61-5888-97a3-7cfc7ca26c76 | note | Acceptance Criteria - Anchor blocks shall be placed into correct position, alignment and angle according to drawings
8b74acba-01f2-59de-847d-87940667153a | note | — — — — — — — — — — —
bb0ff02f-ab91-5f4b-948b-e4db9e00d39e | note | a) Position on plan: ± 50 mm
4d334b00-bdf1-554b-b569-a52613b5af12 | note | b) Dimensions on plan: ± 50 mm
fdff608f-f8db-51ef-8466-82eec7abfa56 | note | — — — — — — — — — — —
c307d2cd-92f9-574d-87bf-8178b4eb68c7 | note | Verifying Document - Photo Record, as-built records
4e2b3019-33fb-536d-96ba-7fe91ae765b1 | note | Frequency - Continuous
b7fdeb61-c4b3-5b1d-8fd1-02caad47c9b5 | note | Inspection Type (Visual, other) - Witness Point
9f79024d-ec17-5486-93d2-3b62ad59af81 | note | Inspection: Key - W
f3dc7b91-de36-5e0c-8c18-2fa53424c7c1 | note | Inspection: By (Role Key) - SV
2c128d7d-c2f8-472d-899e-76d5d8b02ec2 | checkpoint | 4.5 - MSE Wall Backfill AP65 - Compaction Testing
27d182f9-1162-5417-ae37-9ea3d7b36757 | note | Inspection Point: Quality Control Activity - MSE Wall Backfill
5bc96bce-e823-57ec-a860-ccd9ca3c2dc1 | note | Specification Reference - Project Specification Cl 18.5.5
dbab5d20-e6d4-5f66-866e-fab7674d0d53 | note | Acceptance Criteria - Foundation Compaction: 98% MDD and+/- 2% of OMC. None less than 95%
662ce5c9-8918-5404-b06c-8a233aab15c8 | note | ○ 1 set of NDM tests (comprising 5 No. NDM tests per set) are required per 200mm fill lift
38df982c-270d-519c-a37c-b80902ddb2f6 | note | Verifying Document - Photos
5ad9ec83-cdab-5b63-bd64-7fba3d8ddb98 | note | Frequency - Placement/ Prior to backfill
9d403c34-0f46-58bf-b04f-615b9d491cc1 | note | Inspection Type (Visual, other) - Witness Point
0a036b31-beaf-5bfb-98fb-690d9fcbbf05 | note | Inspection: Key - W
4e3210d2-719f-5242-bad2-391286c0f3d4 | note | Inspection: By (Role Key) - SE
68cc66de-5327-400d-b3de-47dfc296dd0b | checkpoint | 4.6 - MSE Wall Backfill AP65 - Visual Inspection
be41bc73-eeda-52c6-b265-e426b7512987 | note | Inspection Point: Quality Control Activity - MSE Wall Backfill
1fa61585-170c-51e2-bb03-e8a65f2b03cb | note | Specification Reference - Project Specification Cl 18.5.2
afe5674f-4c94-5f83-9f13-5357f6c7bb3e | note | Acceptance Criteria - The backfill must be witnessed by the engineer with fill layers not exceeding 200mm.
9f0d7946-d100-544f-913a-3595771627d6 | note | Verifying Document - Visual Inspection
b966f61b-28c3-5c19-a8b4-78f33ae5348d | note | Frequency - Placement/ Prior to bakcfill
b71cc487-4c0a-5a42-8c71-d3b8db55229e | note | Inspection Type (Visual, other) - Hold Point
9e500880-ed94-5c6b-8034-d895db9b5af4 | note | Inspection: Key - H
ac626611-2253-5ce1-aa9a-6fb132fee791 | note | Inspection: By (Role Key) - ER
494c671e-6277-44d5-b989-e479eb0fb5cd | signoff | AUTHORITY HOLDPOINT
d211ab61-c81b-43d3-a580-0f76910a6d9c | checkpoint | 4.7 - Placing Geotextiles/geogrid
c833084a-e754-5066-a8d0-6fdb065b00bd | note | Inspection Point: Quality Control Activity - MSE Wall Backfill
28f51c11-abbe-5654-bff7-df543c2c50ea | note | Specification Reference - Project Specification Cl 18.5.2
d1b81d05-6047-594d-98ad-34f38da8b16f | note | Acceptance Criteria - 80510096-02B-900-C470 Wrap top, bottom & front edge with STRATAGRID SGU80
ca164402-cc6a-5d45-aa70-3ea20c9e17f8 | note | Verifying Document - Photos
ed4bc353-9ac4-5c91-882c-f02ca82c56b0 | note | Frequency - Placement/ Prior to backfill of upper layers
5673baf5-c676-5cea-9fc7-bc3972308aee | note | Inspection Type (Visual, other) - Hold Point
ba7852a4-3db8-5a07-834e-4c915b50ecfd | note | Inspection: Key - H
d3f35bb9-e13d-50cc-9f42-c282b0ce81ed | note | Inspection: By (Role Key) - ER
2c613212-a98b-4d18-a3f0-f14636c81f7c | signoff | AUTHORITY HOLDPOINT
6d5c58f1-bdd5-4f9e-be59-d4baeaddaf81 | checkpoint | 4.8 - As-built Survey
54da811f-77f2-5c9c-9226-81a4c7070f59 | note | Inspection Point: Quality Control Activity - Upon completion of works
9a76082a-461c-5ea0-9838-9d2c9db42900 | note | Specification Reference - Project Spec Cl 18.5.7
3deeacd1-df0c-5a67-9d12-25eb704d9cdb | note | Acceptance Criteria - As built survey record completed
4aaf5219-560e-5c9c-bf79-0fec17fed062 | note | — — — — — — — — — — —
c5d1e7cb-2922-5df3-8007-efecd3f285ab | note | a) Position on plan: ± 50 mm
81b06064-6ae2-5f64-8428-d57df0031900 | note | b) Dimensions on plan: ± 50 mm
d5af038c-a333-551a-82e6-d506c881b98a | note | c) Level of surface trimmed to receive wall: ± 50 mm
7943b6d1-80c1-558e-bb18-27aca1af27ff | note | d) Finished levels: ± 50 mm
71371797-19df-5221-91ba-56140e55762b | note | — — — — — — — — — — —
9a70fc93-fe43-5f46-9ade-01bd2d3c068e | note | Verifying Document - As-built records
560064f7-0ed3-5a60-9a94-a3f80837b366 | note | Frequency - At completion
aa536af1-582d-5251-952a-b9e0061f4f7b | note | Inspection Type (Visual, other) - Witness Point
d13c0dcd-764c-548e-be66-002a9d62049e | note | Inspection: Key - W
9b03dfb3-089c-5f65-a95d-de09173e070f | note | Inspection: By (Role Key) - SV
2fbf994c-7779-4e9d-9b20-4f4d7b802dfd | checklist | DS2681-SH58-ITP-C-005 - Drainage (Pipes) | itp | DS2681-SH58-ITP-C-005 - Drainage (Pipes)
d60604d9-d76e-4da8-8a64-4c8ad93b6cb0 | section | SECTION 4 – IN-PROCESS INSPECTIONS
f102ec40-f43e-464a-8b5e-bab1828b8f7a | checkpoint | 4.1 - Trench subgrade
c804225f-c969-5b34-be33-6eebd8222834 | note | Inspection Point: Quality Control Activity - Upon trench excavation
89d6e789-26f0-54fc-b66e-e7afc581688f | note | Specification Reference - Project SpecificationCl 16.3.12
a25e3aa5-39a4-54e3-874c-035c39625602 | note | Acceptance Criteria - Contractor to confirm suitability of foundation material and where the Engineer considers that the foundation material below the pipes or structures is unsuitable as defined in the earthworks specification, this material shall be removed and replaced as outlined in the earthworks specification 3 blows per 100mm
29259c2d-45b9-5b91-a747-1e5518224894 | note | Verifying Document - Scala Testing Record SheetDN-QUA-QC-04
6e1de7d4-135a-55ac-a8e5-0e91ece587e4 | note | Frequency - 10m intervals
d6a5a81c-46f9-58ac-9917-8ad3f0c4520f | note | Inspection Type (Visual, other) - Witness Point
50625f5e-fc05-5940-9d5c-a29b225aab5b | note | Inspection: Key - W
f5e1a6ee-c962-5442-88bd-55634ba5d0bb | note | Inspection: By (Role Key) - SE
c9560171-4259-48f6-aa1a-b6d813c3679b | checkpoint | 4.2 - Foundation Undercut and backfill (WHERE REQUIRED)
989fb158-7243-5566-9990-06c196f7e688 | note | Inspection Point: Quality Control Activity - Prior to backfill
70735cc0-aefb-5f46-9c34-23c80443d92d | note | Specification Reference - Project SpecificationCl 16.3.12 TNZ F/1
c5bd9313-623e-53c8-8496-f508834cba5e | note | Acceptance Criteria - Visual inspection of subgrade. Engineer to confirm any undercut treatment, if required.
38823499-df35-5402-8d77-9b1a1c122e28 | note | Verifying Document - ConQA Hold Point
1512d931-67b4-5976-af07-84fd126b48e8 | note | Frequency - Before placing bedding
4e27720c-cdf5-5b6e-8c7c-ef072909cfb1 | note | Inspection Type (Visual, other) - Holdpoint
f05bc184-c45b-5177-96c2-12721eb99f4b | note | Inspection: Key - H
24c078e1-2be0-5458-a743-afcfb37c992a | note | Inspection: By (Role Key) - ER
80d190c1-026d-48c1-ab7e-2fe7467715ef | signoff | AUTHORITY HOLDPOINT
28a456c0-dbf0-4165-82b6-6dc471a400b9 | checkpoint | 4.3 - Filter Cloth
474b48db-3ab6-5e2c-bb03-1221b42c9de7 | note | Inspection Point: Quality Control Activity - During construction
6e84af12-7781-53f8-8804-82da42727f19 | note | Specification Reference - 80510096-02B-900-C205 Rev1
f920026e-7022-5e2a-a1e3-9a3c83a501f9 | note | Acceptance Criteria - Pipe bedding shall be placed within a layer of geotextile fabric as indicated in the drawings.
c10fb571-bc89-5e30-abab-3dde37b9a9f6 | note | Verifying Document - Photos
f584ccfd-bf12-5e71-b484-4b1baccf584d | note | Frequency - Continous
03552227-7b84-5b8b-a7e2-edaee7283487 | note | Inspection Type (Visual, other) - Witness Point
94c8b5d1-e3d5-5793-8ecb-7f04c231190f | note | Inspection: Key - W
167cddb6-f3d8-5221-9d3d-0ffc281a5943 | note | Inspection: By (Role Key) - SE
b90b567e-7c13-49b9-9b06-2bd30c8add08 | checkpoint | 4.4 - Bedding for rigid pipe
9b8b2670-be89-5884-b202-b5fce142e557 | note | Inspection Point: Quality Control Activity - Prior to laying pipe
ddd382f5-5729-50e9-abbf-2652eaf7eb92 | note | Specification Reference - Project SpecificationCl 16.4.1 80510096-02B-900-C205 Rev1
5d95218b-c9c8-566e-bdd4-4fe9d440a0fe | note | Acceptance Criteria - Bedding material shall be as shown on the drawings
ac05d2ed-283d-5c7c-b345-ced309491ca7 | note | Verifying Document - Photos, As bults
64ba1d54-8d5e-5424-af77-40fec6468efb | note | Frequency - Continous
f85c3b3e-2828-56c1-a0e8-897164967216 | note | Inspection Type (Visual, other) - Witness Point
8f357f06-fa3d-5e89-a69a-1fe672e9fdd4 | note | Inspection: Key - W
a3078c3a-220b-54b4-ba79-e25e74aa3870 | note | Inspection: By (Role Key) - SE
59f80349-f411-46c3-939c-fdb49bcb3e2e | checkpoint | 4.5 - Bedding for flexible pipe
166be78b-c132-5e0d-827e-3b8fa38c2648 | note | Inspection Point: Quality Control Activity - Prior to laying pipe
eddc74f8-2262-5ec1-9b76-79c70efe8d5d | note | Specification Reference - Project SpecificationCl 16.3.17
6fab8f94-dd94-5a46-ba5d-90d3eb7d59cc | note | Acceptance Criteria - Flexible pipe material shall be bedded as per below table
0bf7bff4-4f92-5503-9d91-9c9e1cee246c | note | — — — — — — — — — — —
65c02b9d-60a9-5034-9839-50127ee9a268 | note | Pipe OD mm ¦¦ Bedding below base of pipe mm ¦¦ Bedding above crown of pipe mm ¦¦ Bedding either side of the pipe mm
e7f56ff5-2a3d-595b-8177-32be5c0eb91b | note | — — — — — — — — — — —
9329ad18-7ecd-5cb7-8c88-2a80fc6ae35b | note | ≤ 150 ¦¦ 100 ¦¦ 100 ¦¦ 100
a04707a2-ec8e-5d3e-b3ad-b508a70847f1 | note | >150 and ≤ 300 ¦¦ 100 ¦¦ 150 ¦¦ 150
9084117e-e79b-5b8e-8d28-c9dbf8732312 | note | >300 and ≤ 450 ¦¦ 100 ¦¦ 150 ¦¦ 200
4a795743-4c53-5a6f-9f23-3e36f4386c16 | note | > 450 and ≤ 900 ¦¦ 150 ¦¦ 150 ¦¦ 300
a0bdc23f-e6b5-50b2-97d6-129b02cdd15a | note | > 900 and ≤ 1500 ¦¦ 150 ¦¦ 200 ¦¦ 350
03a8ca6b-7898-5ae4-822f-a50b2f54eb7e | note | > 1500 ¦¦ 150 ¦¦ 300 ¦¦ 0.25 x Pipe OD
b39d07bd-7c9a-5867-8b60-507dba657544 | note | — — — — — — — — — — —
c2fdfc16-9d77-55f5-969e-ff375e026bf3 | note | Verifying Document - Photos, As bults
f8dcad58-3295-5db7-9fa2-135f598805b8 | note | Frequency - Continous
8add4975-cb05-5d16-804f-963fd885458d | note | Inspection Type (Visual, other) - Witness Point
d7fc4b09-7e39-51fc-b5c8-748fe3b26f7b | note | Inspection: Key - W
3e366196-adf8-58f4-8351-8177309c528b | note | Inspection: By (Role Key) - SE
f3ca29a8-f9bc-44ec-b29a-8b616f807235 | checkpoint | 4.6 - Laying pipes
c6250208-6d84-5938-91dd-c3c3efbefbf5 | note | Inspection Point: Quality Control Activity - During construction
530f0920-a955-504b-b031-f505498d8eec | note | Specification Reference - Project SpecificationCl 16.3.18
694db2c3-bbae-575a-84ff-79d90edef3af | note | Acceptance Criteria - All pipes shall be laid in accordance with the relevant standards, the manufacturer’s instructions and good trade practice. Pipe jointing shall be carried out such that the finished joints are watertight and present a smooth invert.
aaab53a1-8281-553d-9c3b-66ea47294b31 | note | ○ For concrete pipes, the spigot and the inside of the socket of pipes shall be clean before jointing. Rubber rings for flexible joints shall be free of dust, grease or dirt. The rubber rings shall be mounted evenly on the extreme end of the spigot
f1f4b95a-9571-53e7-8d4c-aa15cdc65ce5 | note | Verifying Document - Photos, DN-QUA-QC-28 Stormwater Installation Checksheet
54cf23c8-4c41-5f43-8122-376848598ce8 | note | Frequency - Continous
3ffd1303-0ffa-565a-90e2-65e9e9c0c852 | note | Inspection Type (Visual, other) - Witness Point
24ac1702-3e12-54ea-9d86-1ff57a103865 | note | Inspection: Key - W
a51737dd-3d35-5f50-8553-498924e032e3 | note | Inspection: By (Role Key) - SE
9690d0bd-9faa-49ef-b254-18112131636e | checkpoint | 4.7 - Tolerances
b931be74-27d0-524a-8737-e8ff3104bce0 | note | Inspection Point: Quality Control Activity - During construction
33e7ee7b-6289-598a-9697-862f7d0a0874 | note | Specification Reference - Project SpecificationCl 16.3.42
445ce48a-9bd2-5cd5-b2fd-d3eaa89f3d32 | note | Acceptance Criteria - The permissible deviation from the designated level of the invert at each manhole shall be ± 25mm.
3d45cffb-08bc-54fb-8d2c-cc4e9b776a3b | note | ○ The permissible deviation of the alignment and grade of each culvert and pipeline shall be ±20mm from the designated line and level, or from the line between pipe or culvert inverts at successive manholes or catchpits as applicable, when measured over any 6m length, with all such deviations being gradual.
6d2efa7c-ecea-50f5-adad-da59b8b90b9e | note | Verifying Document - As-built
4827b9ae-a1d0-503e-97ea-0b9aae47cc2c | note | Frequency - Continous
970d9b5a-b26a-57db-bac1-89325e9b4de0 | note | Inspection Type (Visual, other) - Witness Point
be72d77b-383d-585a-904b-d03224895245 | note | Inspection: Key - W
8a301c13-ed36-5ac2-98f0-a89c773495d0 | note | Inspection: By (Role Key) - SV
2a3f8154-66e2-438e-a0d1-f081fe7b0c64 | checkpoint | 4.8 - Backfilling & compaction
b4b4c55a-1296-506c-9adb-ea18c98a3e06 | note | Inspection Point: Quality Control Activity - During backfilling
f52db207-109b-5166-a7d3-43022fb0e1d3 | note | Specification Reference - Project SpecificationCl 16.3.20
d058691e-4c02-5f6c-9c98-d6d40b981675 | note | Acceptance Criteria - Hardfill shall be compacted in layers not exceeding 150mm loose depth using approved mechanical compaction equipment.
c55d1be3-870f-551b-8505-cf548318e191 | note | ○ Selected fill and Ordinary fill unless specified otherwise, shall be compacted to at least 90% MDD at optimum moisture content.
03680657-31d4-5bcc-87b3-54e1b827305e | note | ○ Pavement layers shall be compacted as per the pavement specification and corresponding ITP
6531cca6-e412-520d-9c34-0f558b62fcc1 | note | Verifying Document - Photos, NDM Test Results, DN-QUA-QC-09
3f2111f5-048c-5b7f-be47-fcf4564aeba0 | note | Frequency - Continous
18416ab5-88d0-51ba-8b15-4f7f20254727 | note | Inspection Type (Visual, other) - Witness Point
6b2972a6-2596-5478-9d59-b56bc3cae785 | note | Inspection: Key - W
001c3aa8-fc03-57d7-af84-16e6e1fcf6ea | note | Inspection: By (Role Key) - SE
b6d6f681-a1e2-46d2-823c-1da7caca2320 | checkpoint | 4.9 - Inspection Testing
299e53be-c71a-5343-ac5a-7e766ca6bd1b | note | Inspection Point: Quality Control Activity - After laying pipe
fb55af67-c912-5409-ad7f-b747fe9de8aa | note | Specification Reference - Project SpecificationCl 16.3.43
036af830-f687-5210-a43d-c68ca6003428 | note | Acceptance Criteria - Pipes smaller than 600mm diameter shall be hydrostatically tested and inspected by CCTV to identify any leaks or deficiencies in joints.
c3d14b9c-3cf5-5f88-92da-b7c4686d3b44 | note | ○ Pipes larger than 600mm diameter shall be CCTV tested
21a1f236-e08d-58b2-94f5-f86c42cd7aec | note | Verifying Document - Photos
69435c70-3cf0-5e7b-a302-7e28113a0784 | note | Frequency - Prior backfilling
53404932-ba32-5012-a48f-611b1ed6284d | note | Inspection Type (Visual, other) - Witness Point
3d6fe7bb-d866-5a5b-afda-e4fd2e29914a | note | Inspection: Key - W
aaa97981-1a90-5345-a14a-3dfe028e1daf | note | Inspection: By (Role Key) - SE
25661d04-d35f-4c62-85a8-ec1f82043828 | checkpoint | 4.10 - As-built Survey
ee6c9998-2755-51ff-a7c9-139582161ddd | note | Inspection Point: Quality Control Activity - Upon completion of works
2e175fec-9f15-5e3c-881f-dedd8950e4f9 | note | Specification Reference - N/A
45916346-10f8-57ca-addc-de9fb767c187 | note | Acceptance Criteria - As built survey record completed
8fcf14a8-68fb-5b28-9928-02403205a704 | note | Verifying Document - As-Built
53d99784-6150-538d-bf4c-138629dae062 | note | Frequency - After Works
f0ef43ee-b2ef-5138-9850-4c8431e81f67 | note | Inspection Type (Visual, other) - Witness Point
a9e19679-ccb0-57d0-8274-d20b22e4c327 | note | Inspection: Key - W
5dd901ba-4f38-5ce8-a146-44479c4c80a4 | note | Inspection: By (Role Key) - SE
b4397342-998b-4cfc-bc0c-aa011a10cb00 | checklist | DS2681-SH58-ITP-C-015 – Barriers (W-Section) | itp | DS2681-SH58-ITP-C-015 – Barriers (W-Section)
22c96591-dea7-455e-b650-473542926e45 | section | SECTION 4 – IN-PROCESS INSPECTIONS
260258f4-e738-4ad8-aec3-296787ddec7a | checkpoint | 4.1 - Ground beam installation (Pre-Pour)
d6c8f9dc-4ec6-544f-92f5-11f98648c649 | note | Inspection Point: Quality Control Activity - Ground beam installation (Pre-Pour)
278eec01-987a-57a3-8a36-491647e7211f | note | Acceptance Criteria - A concrete pre-pour inspection to be carried out by Engineer to check formwork and reinforced steel (where required), checking dimensions, reo sizes as well as ground preparation.
9604974f-00fe-5726-b753-276007ec6b23 | note | ○ Concrete strength requirement of 30MPa minimum. Specification from NZTA 2014 Technical Memorandum: Road Safety Hardware Series Standard Detail Ground Beam
edde2cab-e0ee-5384-a4e8-e5e94b60c445 | note | Specification Reference - PS Cl24
10aafe94-9e98-5826-8e10-f7a6211212b8 | note | Verifying Document - Pre-pour Inspection Sheet, Concrete Docket, Photos
35dca340-b546-5269-98de-31fb245720e0 | note | Frequency - Prior to every concrete pour
2c0bc421-ed2e-5bfc-8238-bc89c35f905c | note | Inspection Type (Visual, other) - Hold Point
4f1b788e-6d0d-54d8-82e4-909ca77863da | note | Inspection: Key - H
56351287-3c9a-5154-b693-05ecb76af936 | note | Inspection: By - ER
13fd3178-0566-4a56-a8cd-b14d333570ce | signoff | AUTHORITY HOLDPOINT
3fc4f03c-dc94-4f21-b464-c854ab39bb8d | checkpoint | 4.2 - Ground beam installation (Post-Pour)
0c861283-229d-5081-9e78-5473e0ec4790 | note | Inspection Point: Quality Control Activity - Ground beam installation (Post-Pour)
d6bf60ca-d279-52cb-aa92-fd69cd0bcaa8 | note | Acceptance Criteria - Post pour inspeection to check concrete finishes are up to the required specification. No honeycoming. Any defects to be reported to the Engineer with remediation proposal.
04913f40-93c0-5703-b817-06e12c2922dc | note | Specification Reference - PS Cl24
6b0f1d2c-a4c8-5a12-a5f5-454c11207d07 | note | Verifying Document - Post-pour Inspection Sheet, Concrete testing results, Photos
947e5cde-e2a1-5c20-8c69-9cd3eeae1f37 | note | Frequency - After stripping formwork on each concrete pour
5bd310ea-1ec3-526b-839b-a7740a00b7d7 | note | Inspection Type (Visual, other) - Witness Point
2fe3c27d-e902-5574-8ad2-f1ca3b87bf0b | note | Inspection: Key - W
85c271c5-89f6-5dd5-935f-795a9636248e | note | Inspection: By - SE
b67d631c-b921-4d14-89bb-050d327566cd | checkpoint | 4.4 - W-beam positioning behind kerb
021bc717-ea6f-56bd-8775-86062604c039 | note | Inspection Point: Quality Control Activity - W-beam postioning behind kerb
32476581-01ce-5765-8b47-08d9938451ad | note | Acceptance Criteria - Unless detailed in the drawings, where barrier is placed behind a kerb, the face of the barrier is to be no more than 200mm behind the kerb face. Where barrier is placed further than 200mm behind the kerb face this shall be agreed on site with the Engineer prior to installation.
1098442e-5f9b-55d0-8b7d-e484bb68945a | note | Specification Reference - PS Cl22.1.2
6c334316-7edc-5c6e-8c33-d5e9b2f18444 | note | Verifying Document - Engineer Inspection / Measurements Photos
93127c6d-c802-5add-9c4e-73b0812edb0b | note | Frequency - Where Used
bc3cde51-7ebe-5a6b-9040-65eeddeac595 | note | Inspection Type (Visual, other) - Witness Point
6df073e0-cc75-55f5-ac04-56413dcab337 | note | Inspection: Key - W
bec0095e-5f5a-5c0d-8d89-77d64f97f9d9 | note | Inspection: By - SE
8227f627-4a05-4b77-97a8-6e5ee0e844dc | checkpoint | 4.5 - Nesting W-beam barrier
18fabf0f-e868-5f4d-8f58-8aa74ba45e90 | note | Inspection Point: Quality Control Activity - Nesting W-beam barrier
566274ed-eb00-5b48-8a92-830ffc75f062 | note | Acceptance Criteria - Nesting of weak post systems shall be in accordance with manufacturer's instructions.
14c78059-cebd-50f6-bd9a-d90b94f57f78 | note | Specification Reference - PS Cl22.1.7
23213fbe-7fec-56b4-a29f-910ee42408b4 | note | Verifying Document - Photos
b02b1bd2-aff0-5bdc-a14d-45225de33145 | note | Frequency - Where Used
780ce2f2-d606-5aa7-8adb-f46d8d68dd41 | note | Inspection Type (Visual, other) - Witness Point
ba703978-0a42-51d7-8da6-15e74d09fddd | note | Inspection: Key - W
2ab99b72-e14f-5ae5-adb1-ec7412d9a4a9 | note | Inspection: By - SE
df6daf53-b44d-423c-a840-00f9ff50e628 | checkpoint | 4.6 - Barrier Checklists
4783be03-7460-54f0-aa72-25eb2d6d2d71 | note | Inspection Point: Quality Control Activity - Installer Checklist
32501f7b-7677-592d-90fc-c596019d4e9d | note | Acceptance Criteria - An approved barrier installation checklist shall be completed by a person with demonstrable recent experence in barrier installation and signed by the Contractor for each barrier installed and provided to the Engineer within four weeks of installation.
61c9a90c-b447-5859-927b-b16a7234fcdc | note | Specification Reference - PS Cl22.1.6
7932da93-7e89-587d-afa4-8dbbb81abb23 | note | Verifying Document - Installation Checksheet, Photos
b3c4f860-1ceb-5cbe-9c43-3fc3ed023863 | note | Frequency - Per Barrier String
937843ef-f0f2-5a6c-9861-aedcbecd88b8 | note | Inspection Type (Visual, other) - Witness Point
4df711a0-32d6-5f19-907a-6694c26d4149 | note | Inspection: Key - W
29a9ae3f-f7d9-51ca-bc0a-35570c7d851c | note | Inspection: By - SE
1b93c212-3534-4def-80a2-179566ef9481 | checkpoint | 4.7 - Survey
ef1f3160-0e1c-592e-a286-79bd237faf9b | note | Inspection Point: Quality Control Activity - Survey Pick-up
830c0475-8a2d-5234-948e-f84e1ef6c389 | note | Acceptance Criteria - Installed as per the contract drawings
3a628baf-617f-51ec-830e-ed923504c76b | note | Specification Reference - N/A
0d273fda-783e-59e0-87b9-698ed54a5086 | note | Verifying Document - Survey As-Built
6a77bd78-77a4-5cbf-944b-70c6556e6959 | note | Frequency - Per Barrier String
1bdf939f-e386-5b45-95e7-5c7d63d981fc | note | Inspection Type (Visual, other) - Witness Point
ef440001-61b6-5731-853f-5b19deb45caf | note | Inspection: Key - W
2ed920ab-0dcd-552e-867a-f148dc4beb8a | note | Inspection: By - SV
23769390-b34f-4246-8b54-8bc1f86087f9 | checklist | DS2681-SH58-ITP-C-016 – Barriers (Wire Rope) | itp | DS2681-SH58-ITP-C-016 – Barriers (Wire Rope)
8b307aaf-7cfb-439a-985d-b932b268b3ff | section | SECTION 4 – IN-PROCESS INSPECTIONS
895f9fff-59be-425c-97f9-bdfba1d5dc05 | checkpoint | 4.1 - Terminal End (Pre-Pour)
c75cd18a-23c7-5556-b56b-69dac0a336ea | note | Inspection Point: Quality Control Activity - Terminal End (Pre-Pour)
7f17b22b-fa7f-587b-8919-431461f8b314 | note | Acceptance Criteria - A concrete pre-pour inspection to be carried out with the Engineer to check dimensions of trench, formwork and reinforcing, anchor points and ground preparation.
857a3ce8-ae66-5b9f-ab6c-874904e0cbb9 | note | ○ Concrete strength requirement of 30MPa minimum.
21c385be-d707-5e5a-a8fa-13be941b2a2c | note | Specification Reference - PS Cl24
02d22036-d50d-534f-9c0b-367f58dcb969 | note | Verifying Document - Pre-pour Inspection Sheet, Concrete Docket, Photos
35ce600c-8124-5c38-8368-dc15b2f01e40 | note | Frequency - Prior to every concrete pour
a07f2605-ba57-5bb9-afc8-406570c4f06d | note | Inspection Type (Visual, other) - Hold Point
f1e51a4c-dffa-5f3a-a860-9ada1f916cbb | note | Inspection: Key - H
d4dbc312-9140-5d25-aa71-e6f96de5a315 | note | Inspection: By - ER
e4782dd6-e7fa-4e4e-b98b-dde1dc5af7a4 | signoff | AUTHORITY HOLDPOINT
81878c4c-8b02-409b-bcf1-218e90e2a316 | checkpoint | 4.2 - Terminal End (Post-Pour)
25da25fe-d19c-5d24-b1e0-9dfac0b8a408 | note | Inspection Point: Quality Control Activity - Terminal End (Post-Pour)
2c3df04e-3b86-5a8e-8706-6863d12387cd | note | Acceptance Criteria - Post pour inspeection to check top surface finish and ensure anchor points are in place
c353edd7-15eb-5eb0-a14c-5de77bb0d653 | note | Specification Reference - PS Cl24
cf5e1b64-2b00-557e-8f54-e6645f4212dc | note | Verifying Document - Post-pour Inspection Sheet, Concrete testing results, Photos
2c9266d4-d60d-5dc5-b0a2-e39a07aecbf2 | note | Frequency - After stripping formwork on every concrete pour
7a5dd6df-5848-531a-95af-60e9cc0c2a4a | note | Inspection Type (Visual, other) - Witness Point
a543e02e-5f68-528f-8e9f-63010ef1a9af | note | Inspection: Key - W
da797c42-7f46-50e4-b7c4-2cd1ac88a9b2 | note | Inspection: By - SE
b857356f-f49b-4dec-923c-474d76a8c1ae | checkpoint | 4.3 - Barrier Checklists
e0891539-68e2-5608-95df-88d3e0df155a | note | Inspection Point: Quality Control Activity - Installer Checklist
1583aed8-20f9-56ae-be7f-b8680ab1a56e | note | Acceptance Criteria - An approved barrier installation checklist shall be completed and signed by the Contractor for each barrier installed and provided to the Engineer within four weeks of installation.
1e8541a3-869d-5f57-b944-eb5fc04fba10 | note | Specification Reference - PS Cl22.1.6
2cfdd7ae-1d2d-508b-9396-9b6e18d50045 | note | Verifying Document - Installation Checksheet
c8e0d1db-23e7-5b18-b2a3-47074f2b65db | note | Frequency - Per Barrier String
75f71fd8-7d59-5b36-928e-d763496e0948 | note | Inspection Type (Visual, other) - Witness Point
6743524d-6185-5e95-8dee-bec77951c1d6 | note | Inspection: Key - W
66d16be9-4a4b-5f46-b942-e7126c7d282c | note | Inspection: By - SE
1d7b6e18-4483-4b6e-9466-8a58dff233be | checkpoint | 4.4 - Survey
981a7b23-d116-51ec-8b8f-3bf7b46fbe6a | note | Inspection Point: Quality Control Activity - Survey Pick-up
f2ad8a6a-f38b-51b3-955d-16b9d4b892cc | note | Acceptance Criteria - Installed as per the contract drawings
3210996f-9ccc-5e8f-af9b-e3200bcbf716 | note | Specification Reference - N/A
61d59f6b-8687-532a-91e0-39fcecbd5f7a | note | Verifying Document - Survey As-Built
c178f6f6-1a88-5b4c-bf32-d0ede7e17bbe | note | Frequency - Per Barrier String
3f3bfb59-864c-5fc8-aeb9-aed4f06aa3e9 | note | Inspection Type (Visual, other) - Witness Point
eaa014e5-5462-56c7-9856-21d40e0a0f0a | note | Inspection: Key - W
35ec1067-b2a1-5a48-9a73-7b18eac9e8bb | note | Inspection: By - SV
ad5670df-294a-4027-b221-7fd2060b8003 | checklist | DS2681-SH58-ITP-C-019 Ducting | itp | DS2681-SH58-ITP-C-019 Ducting
b0fc4b74-fa3e-40a6-97e7-c2cdcffadb96 | section | SECTION 3 – RECEIVING INSPECTIONS
053f2b87-0701-4657-a6b2-32248e0eb563 | checkpoint | 3.1 - Ducts (PVC)
ae81ca21-76c6-5524-a956-eb76836a502c | note | Inspection Point: Quality Control Activity - Prior to construction
3d6048d7-0987-5fb7-993d-90d58ecc146a | note | Acceptance Criteria - Ducts shall comply with AS/NZS 61386:2015 or AS/NZS 2053.2:2001
fbd9332e-312c-5aa7-8e07-ea2fbdb637e2 | note | Verifying Document - Manufacturer's specification
8b6ebc0a-f982-5d95-b3d0-cbffc866acf1 | note | Frequency - Prior to works
9f55a0be-a132-5024-8ad2-3c4c08e81644 | note | Inspection Type (Visual, other) - Witness Point
70729ba1-c466-521d-8f2b-f692f25c7e6f | note | Inspection: Key - W
84a53475-54d8-55cf-b577-5f4d9b9b95f9 | note | Inspection: By (Role Key) - SE/PE
39dc853e-1147-4099-b4da-178b2c078101 | checkpoint | 3.2 - Bedding sand
b1d110ce-9b9b-5c04-926e-24d669a6542a | note | Inspection Point: Quality Control Activity - Prior to construction
d26b4c62-2b23-5b6e-87e2-632d7e020771 | note | Acceptance Criteria - The bedding material shall contain no organic material that will affect embedment material performance.The bedding material shall be free of materials that would be physically or chemically harmful to any pipeline component, including any protective coating
397f4a16-1cd9-5776-bf82-e086668f3753 | note | Verifying Document - Quarry Testing
22a55e5f-baa5-54b5-9b02-7b92549b85a9 | note | Frequency - Prior to works
af2d8feb-5526-543f-9674-2cc83eb83d06 | note | Inspection Type (Visual, other) - Witness Point
5bedd7c2-6cc3-5ac3-b54f-ec0ce9014672 | note | Inspection: Key - W
b95f5c7a-a7f0-515d-9d10-d9f671e5b225 | note | Inspection: By (Role Key) - SE/PE
2d3be64d-e6d7-4fd7-8ade-dfe96bd0ccb5 | section | SECTION 4 – IN-PROCESS INSPECTIONS
7583c1f6-db51-4525-8e63-0130173e79ed | checkpoint | 4.1 - Bedding
6b5d4844-1a92-5107-bac7-18a39cfb55fb | note | Inspection Point: Quality Control Activity - Minimum bedding
1087617b-3aaf-5a30-a499-1525a2c65396 | note | Acceptance Criteria - A fine layer of fine sand to be laid at the bottom of the trench and top of duct. Minimum bedding layer to be 100mm . Ensure the bottom of trench is free from sharp stones
46805f17-1aed-56ab-b7d1-a2b88522d130 | note | Verifying Document - Photos, DN-QUA-QC-26 Ducting Installation Checksheet
2ea1f737-bf72-5567-86c4-0a03c7b3c4a0 | note | Frequency - During duct installation
6a52dfc0-e156-556c-9df3-b418bc4a6cb1 | note | Inspection Type (Visual, other) - Witness Point
e9e7c3b1-cba5-5e28-b123-cf5cb1c98624 | note | Inspection: Key - W
be0bf783-d5dd-5cf0-8967-ec2439fb905c | note | Inspection: By (Role Key) - SE
4354ae15-f6ad-4273-bd4a-8f76e8222d05 | checkpoint | 4.2 - Duct laying
da7f8e3f-ede1-53c2-b4b0-701ad6a98f55 | note | Inspection Point: Quality Control Activity - Duct spacing
040e47b4-e8ba-5878-85ba-2253dd49f258 | note | Acceptance Criteria - Duct to be installed with with 50mm minimum gap between ducts and 50mm between duct and trench wall.
49ccbf2b-9299-522e-945f-613347d3caa3 | note | ○ Check vs Trench detail. Chorus gapping to be maintained where required.
20f24ed6-d22d-5512-9882-62d65014c2b8 | note | Verifying Document - Photos, DN-QUA-QC-26 Ducting Installation Checksheet
bfe12c39-6228-513f-bcda-80df71d94aee | note | Frequency - During duct installation
229a883c-95a4-5064-aa9a-a5c2e745d99e | note | Inspection Type (Visual, other) - Witness Point
c7042605-6c76-5678-9aac-882f1583f335 | note | Inspection: Key - W
4b5dfa57-6e4d-5a48-9f11-51622d3451a3 | note | Inspection: By (Role Key) - SE
7f11b9f2-5d59-492d-8c53-72710594a44b | checkpoint | 4.3 - Survey of duct alignment
319b5521-75e0-54f5-acc0-c32abb65454a | note | Inspection Point: Quality Control Activity - Duct location
01292317-85d7-54ac-8fbf-b02b8180e679 | note | Acceptance Criteria - Surveyor / Site Engineer to as-built duct location
7307468a-15e4-5c11-8526-e690efcb3e25 | note | Verifying Document - As Builts
6525a0ca-1842-5f8c-ab32-b45dd13a98a3 | note | Frequency - During duct installation
288d8af1-a5aa-5a5e-90aa-03e7e3f952f0 | note | Inspection Type (Visual, other) - Witness Point
f3ccf6ae-3a2e-5b16-a829-ad7f87119fbe | note | Inspection: Key - W
d98bd5cd-cf03-558c-b400-de60e1c8f6e9 | note | Inspection: By (Role Key) - SE
bcf9143c-e1e1-4b6f-9bdd-17b888118fa8 | checkpoint | 4.4 - Warning tape
f501c1db-b624-5544-a5ce-f1617dcb9f84 | note | Inspection Point: Quality Control Activity - Underground service warning
3aa7ccdc-49d4-55c0-8760-efaeae1dee26 | note | Acceptance Criteria - Ensure warning tape is installed 300mm above top of duct
b5ef8a9d-1c06-50d8-9b3e-fa9bcec189a3 | note | Verifying Document - Photos, DN-QUA-QC-26 Ducting Installation Checksheet
9295e029-4686-553c-b539-3e282871b221 | note | Frequency - During duct installation
610c2195-428e-5085-977b-481e13971117 | note | Inspection Type (Visual, other) - Witness Point
5c6cd76a-10bf-5244-8dcd-3717eea09580 | note | Inspection: Key - W
996bb97a-afd4-50c5-b97a-81d0fa7fd179 | note | Inspection: By (Role Key) - SE
6e5f14e0-0e6a-43b8-a875-1003485395ab | checkpoint | 4.5 - Duct cover
4e380a15-4ed7-544f-bf34-f5b586722260 | note | Inspection Point: Quality Control Activity - Minimum cover
e87114c2-74e8-5a0b-b906-13ea4def6f53 | note | Acceptance Criteria - 900mm minimum cover for ducts on road verge
448e7f5c-d6dc-581d-9722-555fcdd6862d | note | Verifying Document - Photos, As Builts, DN-QUA-QC-26 Ducting Installation Checksheet
3f0745bb-43dd-5e0c-aaed-f2d00fc6e910 | note | Frequency - During duct installation
6191c03c-fd03-5c1b-83e7-0111b95598bc | note | Inspection Type (Visual, other) - Witness Point
42bc8ca8-a6ef-516e-9233-cb0769e2844e | note | Inspection: Key - W
9cb25734-afba-552a-bb17-ba6907426ff1 | note | Inspection: By (Role Key) - SE
1afc3674-ca82-42e6-b737-acbea34a9da0 | checkpoint | 4.6 - Compaction of AP65 in Carriageway
638cf626-b1c3-5394-aa66-d15566ad38c7 | note | Inspection Point: Quality Control Activity - Compaction of granular fill
8f4fd501-bd2e-565b-b97e-25e86b1164bf | note | Acceptance Criteria - 200-250mm Lifts
a8648185-3520-5f94-a07d-193f2db2d96e | note | ○ Beneath Pavement Layers: 95% MDD and+/- 2% of OMC as determined from the plateau test/or lab testing. None less than 92%
1a353170-169c-5b0f-9099-9748a1b1ce24 | note | ○ Inside Pavement Layers: 98% MDD and+/- 2% of OMC as determined from the plateau test/or lab testing. None less than 95%
0dcd3b2b-0e3e-57f2-a02d-d8fa9b498b46 | note | Verifying Document - DN-QUA-QC-09 NDM Worksheet
04c51c37-0e71-5eef-8158-901c64e69380 | note | Frequency - 1 set of NDM tests per lift (comprising 5 No. NDM tests per set)
f9c5964f-5774-5038-8de9-a4b25f9c01a0 | note | Inspection Type (Visual, other) - Witness Point
4c196ae5-f93f-5ed4-a200-d7daa3cc55b0 | note | Inspection: Key - W
d15fbe72-e457-588e-a8f9-06f4f8083c1c | note | Inspection: By (Role Key) - SE
886bd232-f809-4ea7-be8d-702ce339e09f | checkpoint | 4.7 - Compaction in verge
08b8f59c-9568-5a38-af91-3483277246ea | note | Inspection Point: Quality Control Activity - Compaction of as won material
5836ad47-bf61-5edd-be9b-065f7c92361e | note | Acceptance Criteria - Ensure compaction in 200-250mm lifts of suitable as-won material.
442d3960-ac30-5fa4-b994-ff63d67f82a5 | note | Verifying Document - Photos, DN-QUA-QC-26 Ducting Installation Checksheet
f3656f18-43d6-5566-8645-3e3111d4c926 | note | Frequency - During backfill operation
ad565dfb-3a10-56c6-a850-6a7613ec5b0f | note | Inspection Type (Visual, other) - Witness Point
a6b8011a-9923-5a1f-b293-2463575bfeff | note | Inspection: Key - W
ab622af2-ad82-5489-bcb4-3c118ce78618 | note | Inspection: By (Role Key) - SE
43c6deb8-e013-4574-8b61-544160cbb6d9 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
b8d264da-5c24-4178-9d0e-6d6a49d35bb8 | checkpoint | 5.1 - As-built Survey
f4d3c757-2f86-5c04-9c46-d995e40cffc4 | note | Inspection Point: Quality Control Activity - Upon completion of works
e0532bd8-7712-5033-8feb-323d0996b462 | note | Acceptance Criteria - Comply with the project specification and drawings
e3745264-92cd-59ce-87f0-3432195c3fdf | note | Verifying Document - As built survey record completed
693b2807-a641-55a8-9c34-bab507d639cc | note | Frequency - Handover
ca02e57d-32e5-5c4a-8d03-e779da27bf2b | note | Inspection Type (Visual, other) - Witness Point
107f322a-f68a-530e-ac21-a8922fbad87e | note | Inspection: Key - W
1e600c3f-2e47-56e3-b79e-6966607ee15f | note | Inspection: By (Role Key) - SE/SV
d9bf022b-80da-4182-b9d7-6f8ae968f607 | checklist | DS2681-SH58-ITP-C-025 Plunged H-Piles (Retaining Wall) | itp | DS2681-SH58-ITP-C-025 Plunged H-Piles (Retaining Wall)
9999bfff-89fa-4ddd-a76f-e63f7b1a6aa1 | section | SECTION 4 – IN-PROCESS INSPECTIONS (MATERIALS)
68cd2ffe-0731-4971-bfd2-e47d92ca091b | checkpoint | 4.01 - Pile casing / sleeves / liners
a297f375-0ab8-507b-89de-c496dd686add | note | Specification/Drg Reference - PS Cl. 24.5.3, 24.5.4
3d6a3162-0b59-5b6a-b325-507834ab9b58 | note | Acceptance Criteria - All steelwork shall comply with the requirements of NZS 3404.
50296f0f-30ea-56d6-bee3-04b1d2096cad | note | ○ The steel casings / sleeves / liners must have an inside diameter not less than the specified diameter of the pile.
1e68a080-f773-5930-9418-f112943422ef | note | Verifying Document - Delivery Dockets
f6492af7-9b6e-5873-95d9-feb83698253e | note | Frequency - Once
c270da2d-c565-5ddb-97f9-6fc9ba616ffc | note | Inspection Type (Visual, other) - Witness Point
5359696d-1fb5-553b-9836-99ba4ebafde5 | note | Inspection: Key - W
e9f98947-27bd-58ea-a180-f57e5d241253 | note | Inspection: By (Role Key) - PE
3cd99b11-de12-4334-a43c-050416e8dbe6 | checkpoint | 4.02 - Concrete Mix Design
d306a342-6853-5b2f-ad0b-54acecce37fd | note | Specification/Drg Reference - Specification Cl 26.1.11
1ab196e4-7343-5c8f-afb4-c0b391033e41 | note | Acceptance Criteria - The concrete mix design must be submitted and approved prior to pouring.
36135c8e-976b-5948-9e15-5941acfc3fb6 | note | Verifying Document - Mix Design
6851c33f-fd75-5c99-b2e3-12944fef91f8 | note | Frequency - Min 10 days prior to works
c3942b0a-1042-53b5-8ddb-d4efe874653e | note | Inspection Type (Visual, other) - Hold Point
d8d4f09a-6262-587f-8563-af914e16bdea | note | Inspection: Key - H
74f293e8-7f1a-55a6-b0c4-8230ca1729ee | note | Inspection: By (Role Key) - SR
71a0796b-2ef2-476b-bb98-f3a6c3b4ca11 | signoff | AUTHORITY HOLDPOINT
0de36156-7cdd-44b4-931d-1d797a0ef4da | checkpoint | 4.03 - Structural Steel
ec410a58-5ff0-5ee0-a304-65b73e2c62c2 | note | Specification/Drg Reference - Specification Cl 26.3
eb377e72-700e-5f7c-af60-eb3dafbd9f23 | note | Acceptance Criteria - All steel shall be in accordance with the appropriate standard as outlined in NZS 3404.
788fdc75-2a26-52e9-8590-9f4d55152e0c | note | Verifying Document - Delivery Dockets, Mill certs, Galvanising certs
3cbb134c-cee9-518a-bdce-72d740556ea8 | note | Frequency - Once
33cfe442-7af3-51fc-9dcc-6ce2941b3cc6 | note | Inspection Type (Visual, other) - Witness Point
cf318baf-22a7-5d86-853d-9c03dd0b5640 | note | Inspection: Key - W
1031673d-8365-5463-aaf8-ba2ac245fd70 | note | Inspection: By (Role Key) - PE
ecff5cbd-1fde-452d-892c-c985af18a2c3 | section | SECTION 4 – IN-PROCESS INSPECTIONS (PILING WORKS)
ae761e30-955f-4f8d-ac27-7bb302071439 | checkpoint | 4.04 - Method Statement
69690319-fc40-5a37-a566-3997d5868cd1 | note | Specification/Drg Reference - PS Cl. 24.5.2
8a06d39f-8b93-5770-bad1-071c5aab4304 | note | Acceptance Criteria - Piling methodology to be approved by Engineer.
01bf2668-1def-5c43-bf1e-4a74a806b93e | note | Verifying Document - Method Statement
9d4668de-83ba-57d2-9122-f70ea15f771f | note | Frequency - Min 10 days prior to works
26c2a417-fb4b-5594-92d2-8691ac933374 | note | Inspection Type (Visual, other) - Hold Point
69e79f54-7cf2-527a-bac3-2db22782f692 | note | Inspection: Key - H
224b4b9d-75a9-53be-ab72-647ec02290b8 | note | Inspection: By (Role Key) - SR
71aba7b7-ad19-4281-bdda-5cfc8eb91d1e | signoff | AUTHORITY HOLDPOINT
eb26f332-9086-4452-b2e0-e87f697a908f | checkpoint | 4.05 - Pile Setout
1b483d95-c1b7-5598-b20c-a7a6e284b2f8 | note | Specification/Drg Reference - Drg 80510096-02B-315-S003
5a1ab77c-35d5-5063-b53d-14833eb44b93 | note | Acceptance Criteria - All pile locations have been set out as required by the drawings, and agreed upon with the engineer. Piles shall be set out in accordance with the SESOC/NZGS construction specification bored and driven piles 2022. Pile Setout coordinates are attached in 80510096-02B-315-S105
0ed68692-9ec7-5659-9f7a-d005b2da250e | note | Verifying Document - ConQA Sign-off
470344d2-556d-557a-b9d5-9acfc9882c71 | note | Frequency - After setout
d5708971-c5c8-5365-b2bd-6976e39ecf83 | note | Inspection Type (Visual, other) - Hold Point
d16eb291-f655-585f-8e28-57c1fceafc4f | note | Inspection: Key - H
7cb02c80-4d03-5ffb-b872-45697df6e7f6 | note | Inspection: By (Role Key) - SR
e72ee855-9e7b-4a58-b8cb-b65198523bc2 | signoff | AUTHORITY HOLDPOINT
dc3915fe-312d-4645-9883-bf8bb24c51f4 | checkpoint | 4.06 - Pile Card
b426afab-0445-58e0-8729-e334fc3953e3 | note | Specification/Drg Reference - Drg 80510096-02B-315-S003
fa310530-0fb1-5542-9302-7dd7584388d2 | note | Acceptance Criteria - A Pile Construction Record Card shall be completed for each pile constructed on site, in accordance with AS 2159:2009.
2e9c8eb4-04ad-5727-bab6-519001605cff | note | Verifying Document - Pile Card
05cbdb40-25c7-5c6d-8868-06dc98716abe | note | Frequency - Continuous
a6f027a0-f7c0-5534-9046-b311f922f979 | note | Inspection Type (Visual, other) - Witness Point
9cbd3339-db49-559f-bd4a-8ad64d537793 | note | Inspection: Key - W
29371109-a8cb-5d6f-a86d-c57ceecd51cf | note | Inspection: By (Role Key) - PE
48d1eaa0-8d6a-4a35-8fc4-828f3d20a233 | checkpoint | 4.07 - Excavation of Pile Foundation
4fe9db95-8f6e-55da-8ab0-a1e8cd77d857 | note | Specification/Drg Reference - Drg 80510096-02B-315-S003
ef434aa4-68d1-5420-a153-11064f5002a0 | note | Acceptance Criteria - Each pile foundation shall be excavated to the depth shown on the drawings. The contractor shall arrange for the engineer to inspect each excavated shaft upon completion.
fe8972e8-d8c6-5930-ad44-a8e1da95c29a | note | Tolerances for Pile:
934a1c1a-b581-510e-93cd-c48d1a91a39f | note | — Diameter - Not less than specified
a6b31ba7-42dc-528f-b471-496f1a0fcda5 | note | — Position - Tops of piles shall not vary by more than 75mm in horizontal and 25mm in vertical
6fe0f5d2-6182-56a0-b4af-01561a34bb2d | note | — Verticality - Max permitted deviation not more than 1:75 (horizontal:vertical)
8c9bbc30-e95d-5274-afc0-3d855f8e9970 | note | ○ Engineer Acceptance
226a2d9b-69b8-54a3-ac17-a99c5480c0e5 | note | Verifying Document - ConQA Sign-off / Photos
b1710ca8-64a1-5d64-a011-7be720c92cda | note | Frequency - Post drilling
d540d2e4-11ed-5b6f-862e-e6f466d03921 | note | Inspection Type (Visual, other) - Hold Point
3d587168-cc28-5d01-868c-71287653f345 | note | Inspection: Key - H
4057fd40-ed75-568d-8684-b597bbbd50ed | note | Inspection: By (Role Key) - SR
fb75acde-3a78-4894-bc21-0720606ac00d | signoff | AUTHORITY HOLDPOINT
fc9a8934-4141-4831-b6c1-0b7a5c351974 | checkpoint | 4.08 - Pre-Pour Inspection
303f9f15-d5bf-5f74-b8e2-17bd02aecf81 | note | Specification/Drg Reference - PS Cl 24.1.17
c23513ee-3c33-522f-b46b-2a92b203c871 | note | Acceptance Criteria - Provide a minimum of 24 hours notice of each initial intention to place concrete to the engineer. A Pre-pour Inspection must verify that the pile hole dimensions (600 mm Ø), steel profile (250UC89) and hole cleanliness comply with design requirements. The concrete mix must meet specifications, and safety measures should be in place before proceeding with the pour.
e3da6e99-fffb-59c0-a6a6-a3f66ec44e62 | note | ○ Engineer Acceptance prior to pour
aea0057f-cee6-5604-a258-14b2e553922b | note | Verifying Document - Pre-Pour Inspection Sheet
1e7b1918-24b5-58dc-996a-a5a29400d721 | note | Frequency - Prior to Concrete Pouring
a452cd82-5acb-5a98-83f1-65c38c2d01b0 | note | Inspection Type (Visual, other) - Hold Point
cd0b2138-cd2f-5bda-a597-e1c728849987 | note | Inspection: Key - H
62393a47-28a7-5faf-bfdf-458fd94394e1 | note | Inspection: By (Role Key) - SR
a11b73f3-4074-485c-b7fb-35937bfa4e29 | signoff | AUTHORITY HOLDPOINT
3bf38176-b517-4999-b581-c11300b66e9f | checkpoint | 4.09 - Concrete Pour - Docket
faa70fe6-f81b-5363-8caa-3e1faa0bc5cf | note | Specification/Drg Reference - PS Cl 24.1.3
191c6565-7efb-52b1-9f0b-46d364ed8bd7 | note | Acceptance Criteria - Confirm correct mix design brought to site
584cde4f-34ce-512d-b201-169ec0aa5f16 | note | Concrete Docket Showing:
f80d91e7-0de3-5977-bc3a-d0e314a0a935 | note | ○ Mix Design Item Code
16df1786-3a12-5c95-a05b-8662eb5972d6 | note | ○ 28 day specified strength
651f6e05-d467-5610-9633-926a91651a7c | note | ○ concrete placement method that the mix was designed for - Pump Mix
862316a1-54b3-52a9-867a-f3f8ed6a6889 | note | ○ type of supplementary cementitious materials (if used);
57583f03-3313-5123-88f2-5df5679b907e | note | ○ slump (target and actual slump when measured);
ecc4ad69-9e43-5eea-ab4d-de29ee1631ed | note | ○ Order and Delivery Quantity
b9db505b-d6b9-5d38-ac2c-8b693135ef4b | note | ○ Load Time out of plant
1e3ac35f-671e-54d0-a245-3292a0986c2d | note | ○ To site time
0893b426-11c5-5320-817a-bda0f47e4165 | note | ○ Unload Time
dc96175b-4396-54f9-b993-f1dbfd38143d | note | ○ Associated Products e.g. cement and additives
ca9200a2-34a7-56b7-a51d-87ff944f2726 | note | Verifying Document - Concrete Docket
d477eac4-1437-5893-bc94-24fba9ffe1f2 | note | Frequency - Each truckload
2b5305d2-28d1-5443-a1c3-5264915c5e92 | note | Inspection Type (Visual, other) - Witness Point
aeeb079d-f982-5be6-94f8-08080e5ca52b | note | Inspection: Key - W
e76b22bf-660f-529f-b3f0-c6f3152ddfef | note | Inspection: By (Role Key) - SE
c3c937a2-f1e7-4310-9230-d878ff6d2174 | checkpoint | 4.10 - Concrete Pour - Placement
1e083d51-279a-5933-b1de-3ef793d32c64 | note | Specification/Drg Reference - AS/NZS 4671: 2001, 'NZS 3109, 26.1.16 Handling and Placing
a2cc17ca-8444-5120-a4b1-7569cad00476 | note | Acceptance Criteria - Concreting to be a continous operation between ends of members and/or properly formed construction joints.
185b22e4-60ba-568f-82ae-010d0a4d37ae | note | ○ Concrete should be placed as close to its final position as practical and drop height shall not exceed 2m.
118b3617-c9d6-5297-bbab-8a4e41295a48 | note | Verifying Document - Pre-Pour Inspection
6f3914df-65b0-5e1e-a145-3a2aa34946a5 | note | Frequency - Per Pour
82f2278a-8296-50ae-87cd-83846b276461 | note | Inspection Type (Visual, other) - Witness Point
502bb0e3-7492-552f-be97-964268d6011f | note | Inspection: Key - W
4e07252a-a990-5ca1-8326-6f26ed20e4b0 | note | Inspection: By (Role Key) - SE
2b468bbd-ce9a-456c-8d1d-876237b0543f | checkpoint | 4.11 - Concrete Pour - Test Cylinders
9363ac5c-06f1-5293-8212-e74242579ccf | note | Specification/Drg Reference - PS Cl.24.1.14
7a7cff87-00b4-5f0d-8191-23567a2a1f8a | note | Acceptance Criteria - A set of specimens for compression tests shall consist of 3 specimens from each sample of concrete. 1no. tested at 7 days and 2no. tested at 28 days.
cfc4e951-2607-5d3b-939b-3bbcb5d22ca5 | note | ○ Strength of concrete = Dependent on Mix Design.
8b0d7807-94ec-5120-9ab1-81128fbf43b8 | note | Verifying Document - Lab Report
5684c5a0-1ff0-5577-a4d1-930cadfc8e99 | note | Frequency - Per batch
5371932a-3353-5847-9d45-a896198e8359 | note | Inspection Type (Visual, other) - Witness Point
892e26ff-8667-55d1-bfa2-0f52d0e8e3fd | note | Inspection: Key - W
bdd871b8-e654-5e4c-a1d4-30ac4af23ee6 | note | Inspection: By (Role Key) - SE
99011c02-836f-498f-8e69-6d3c3541bbad | checkpoint | 4.12 - Concrete Pour - Slump
e67e4627-2a08-5f04-a32d-388a602e1d75 | note | Specification/Drg Reference - PS Table 9.1
32280ef5-3bef-593f-b679-8eff89d34c36 | note | Acceptance Criteria - Slump tests shall be taken for each truckload of concrete and when compressive testing samples are taken. Slump spread test if slump could exceed 210mm. Slump test tolerances:
18fa6e3a-4490-50f0-8c3c-3a25823ac3ce | note | — — — — — — — — — — —
56e0e262-6134-55ef-b033-ed6dd734313a | note | Nominated slump (mm) ¦¦ Tolerance for snatch sample (mm)
1f303848-068b-518d-a7ae-bac658602289 | note | — — — — — — — — — — —
97c00001-cf73-5b95-8035-9196715d8e6c | note | 60 or less ¦¦ ±20
f37b56a8-1d21-5d70-9f63-caa8a5977f15 | note | 70 — 110 ¦¦ ±30
2c3fc18a-420b-526d-b138-64156ea66474 | note | Greater than 110 ¦¦ ±40
6e01cfd2-a301-5c01-895c-6ea69c60a3ab | note | — — — — — — — — — — —
d4f88045-0f3d-50ce-9a87-f5517a89041e | note | Verifying Document - Visual/Photos
73529c01-7386-5c64-9c23-c5f3c9ff9ed7 | note | Frequency - Each truckload
cfa5ad42-9cf6-5321-8e8b-39b2613051ab | note | Inspection Type (Visual, other) - Witness Point
0e3fd2e6-37b6-5bd8-824e-ce4d9ff83793 | note | Inspection: Key - W
9f1eca23-2699-501a-8619-3de769ea325e | note | Inspection: By (Role Key) - SE
efa562a7-cc2a-4124-93e5-8ddfdb55e7b3 | checkpoint | 4.13 - Concrete Pour - Time Limits
3116dc4c-fa38-5bb3-88bd-9e5b697942d1 | note | Specification/Drg Reference - PS Cl 24.1.17
702e2183-41a1-50ed-a1b6-7eba6562cf07 | note | Acceptance Criteria - Incorporated in the works within 90minutes of batching.
dc3955ac-3c1e-50be-a9cb-135f446c86d3 | note | ○ Incorporated in the works within 30minutes of discharge from concrete truck/agitator
6a2fc931-eef9-5586-9309-2f2d25d98087 | note | Verifying Document - Dockets & pour sheet
f3eb38b8-7441-5382-afd4-1ff30e922492 | note | Frequency - Each truckload
310911c2-565c-5fe2-8a6c-e77a4302641f | note | Inspection Type (Visual, other) - Witness Point
10877fe6-7635-56fb-9869-39cdeb8ef906 | note | Inspection: Key - W
b91d6c2b-b40c-5b6d-8aca-7b65f9fa7d5b | note | Inspection: By (Role Key) - SE
a5dadb9d-05fc-4b0b-a024-31fff235c288 | checkpoint | 4.14 - Concrete Pour - Vibration
77abb3fd-eba0-56b1-8c72-9334da7d448c | note | Specification/Drg Reference - Clause 7.6 of NZS 3109
52e55e47-5cae-5494-ac45-e50982d52355 | note | Acceptance Criteria - All compaction of concrete shall be carried out in accordance with Clause 7.6 of NZS 3109 as further modified by the following provisions: -
c612f751-007a-54cc-b38b-0fe1637e7acb | note | ○ All concrete shall be thoroughly compacted during and immediately after depositing, by means of power driven immersion vibrators of a size suitable for the section being poured. At least the top 2m of pile shall be vibrated unless noted otherwise.
1f6abc22-1b83-58d7-bfab-89577be6244b | note | Verifying Document - Visual / Photos
e18fe687-c543-5985-be93-cc3e7d0489b6 | note | Frequency - Per Pour
92d63fe9-b79d-542a-aa8a-1cb080d12202 | note | Inspection Type (Visual, other) - Witness Point
0f0df2dc-459f-58b9-8ff5-266daa90fe06 | note | Inspection: Key - W
ac87749e-9034-505b-850c-32388022a873 | note | Inspection: By (Role Key) - SE
f2c32e47-385c-461d-ba00-9dffa68e5714 | checkpoint | 4.15 - Survey As Built
7875fb14-72f5-51ee-80fb-87fc5c94b9e2 | note | Specification/Drg Reference - PS Cl 24.5.4
59787cf9-6767-5d16-9ec7-f743f7d094bc | note | Acceptance Criteria - Tolerances:
8825fefc-d0fc-551b-b6d2-36aa5cfb933b | note | ○ Diameter - Not less than specified
579bf3c4-4c78-5c84-9ec7-62fd27c5a865 | note | ○ Position - Tops of piles shall not vary by more than 75mm in horizontal and 25mm in vertical
c1c29ee8-e967-5546-be07-c501e7672a30 | note | ○ Verticality - Max permitted deviation not more than 1:75 (horizontal:vertical)
b849d928-3b04-5b3e-8775-f32484bb03b0 | note | ○ Pile Head Level - Overcast by min 0.3m and siphoned/pumped off down to finished level. 25mm tolerance
2944acdb-c977-5ba8-a165-a036e3460fe8 | note | Verifying Document - As-built / Measurements
e0fba8bd-bd86-591c-afd9-b7d315fc58f0 | note | Frequency - Per pile
337159d2-3a35-5f88-9b7b-bc4b7c7f3034 | note | Inspection Type (Visual, other) - Witness Point
0bf849b4-3bd0-5c9d-8d1b-3e654730001e | note | Inspection: Key - W
c8502e57-1435-5029-8b7e-49d7d52b5550 | note | Inspection: By (Role Key) - SE
df1dd48b-f89a-405d-a30c-8f7aae43cf7c | checklist | DS2681-SH58-ITP-M-001 - Drainage Materials | itp | DS2681-SH58-ITP-M-001 - Drainage Materials
0a356081-0f8b-4f8c-bbb2-990551b97294 | section | SECTION 3 – RECEIVING INSPECTIONS
25951c70-f39a-4319-b944-af03d18ee4a5 | checkpoint | 3.1 - Backfill Aggregate (AP65, AP20)
3455bef4-414a-5da2-82d6-882d5b76daaa | note | Inspection Point: Quality Control Activity - Prior to construction
c8d8ceab-19f1-5198-8051-a6762e77d54d | note | Specification Reference - Project Specification CL 16.3.21
6c27fedd-9b2f-5a01-8178-1bea737ef851 | note | Acceptance Criteria - Trench Fill. Site Won Material can be used with agreement of Engineer.
18458cca-f0c8-5af0-a755-3d4692cf9faa | note | ○ free of unsuitable material as defined in the Earthworks Specification.
1f6333eb-23b5-5681-892d-e3c745826c6a | note | ○ Fill to contain no more than 20% passing a 75μm sieve.
a2eba883-6292-588e-80a0-6d4b93a177b6 | note | ○ Fill to have maximum particle size of 100mm
81ea79d2-c46e-5a79-a4be-52c3aa99e090 | note | ○ Fill particles shall be able to be incorporated within a single layer. Further, less than 30% of particles shall be retained on the 37.5 mm sieve.
5c2b29bb-11e9-5e12-9fa5-d5d7052dc70c | note | ○ Unless otherwise approved, the MSE Wall Fill shall have a Liquid Limit less than 70% and a PI less than 6%.
de8e8f04-7785-515f-ab27-7915b600c91b | note | ○ MSE Fill shall be able to be tested in accordance with conventional compaction test methods for soil. Where Nuclear Densometer is used, these methods require less than 20% retained on the 37.5 mm sieve. Where between 20% and 30% of particles are retained on the 37.5 mm sieve the above test methods shall still be adopted and test reports annotated appropriately including reference to any test calibration or correction adopted
7b474dda-3bdb-5ea2-bfb9-993252060fa8 | note | Verifying Document - IANZ Lab Report
4a8f7c85-d509-5238-9bcc-9130666a1e6e | note | Frequency - Prior to works
2462e346-5762-5b6f-af31-12c47b24b2fa | note | Inspection Type (Visual, other) - Visual, Document Review
e99a8c63-dbef-5670-8624-51115a6e5c5d | note | Inspection: Key - H
8bf92274-9c71-575d-ae25-5f6db149e770 | note | Inspection: By (Role Key) - ER
1d413878-1c30-4c7f-b707-8bb5693dde05 | signoff | AUTHORITY HOLDPOINT
8afcecce-cab4-45a0-9559-0d29eca92178 | checkpoint | 3.2 - Bedding Aggregate (AP5, AP10, AP20)
1f1aaa08-3a0e-5a9a-aa20-5755042099e1 | note | Inspection Point: Quality Control Activity - Prior to construction
e36676d7-96db-5ace-9720-0c4f570e5897 | note | Specification Reference - Project Specification CL 16.2.12
de6106e4-3f81-572e-8240-eb98add93abf | note | Acceptance Criteria - The bedding material shall contain no organic material that will affect embedment material performance
8d8a37b3-54cb-59a3-8dc1-1709bf01b5b3 | note | ○ The bedding material shall be free of materials that would be physically or chemically harmful to any pipeline component, including any protective coating
b9e20409-5955-557e-8738-ce4c84711a72 | note | Verifying Document - IANZ Lab Report
cc8b1cba-c9a2-58ad-ae13-db72f18dca44 | note | Frequency - Prior to works
41ae6b0e-135e-5dfb-acea-0d956ba881eb | note | Inspection Type (Visual, other) - Visual, Document Review
5badf741-6602-5f8d-8463-999c8d2567b3 | note | Inspection: Key - H
98769ce8-5940-5c9a-868c-2986e8c9a51f | note | Inspection: By (Role Key) - ER
19495dea-acda-4340-917c-e5c0db4aad7a | signoff | AUTHORITY HOLDPOINT
16100004-c604-4b99-929e-c158d367226d | checkpoint | 3.3 - Filter Cloth
dccb2fa8-5d7d-5d89-ba74-dc3b569f7cfe | note | Inspection Point: Quality Control Activity - Prior to construction
f14111fe-bcf6-5756-bbb0-f07ddd5d2ee7 | note | Specification Reference - 80510096-02B-900-C205 Rev1
41d0ef66-8c5c-5c93-8cc2-123259afa1c9 | note | Acceptance Criteria - Filter fabric Terram 1000 or similar to be used as per drawing
cdbd8d5b-044a-5a28-beaa-a5ec4cc65b4c | note | Verifying Document - Manufacturer technical data sheet, Photos
884b869e-ccfc-5d85-a25b-598c9d5c3958 | note | Frequency - Prior to works
b7650e2d-dd88-57e3-91d2-821dd6d08445 | note | Inspection Type (Visual, other) - Visual, Document Review
1261a563-51ef-5597-aae2-8960817e3753 | note | Inspection: Key - W
1f77f03c-72f8-54f0-bcde-6af72051069f | note | Inspection: By (Role Key) - SE
d0fa6d82-1184-4ec6-8d11-62feec35ea36 | checkpoint | 3.4 - Pipes, Manholes, Sumps and Headwalls
0fd8730b-4130-5ee3-a3e8-538313270421 | note | Inspection Point: Quality Control Activity - Prior to construction
dc24d0db-f515-5228-af59-81d091eb4fe5 | note | Specification Reference - Project Specification Cls. 16.2.3, 16.2.5, 16.2.7, 16.2.8,
b7b80726-069c-5726-a729-f98369c67aa0 | note | Acceptance Criteria - RCRRJ pipes & fittings AS/NZS 4058:2007
677ffb2a-03aa-51ef-b4f8-c17012082d0c | note | ○ UPVC pipes & fittings AS 1254 2010
08115978-b4e9-5896-ad85-e3943eaeea82 | note | ○ Rubber rings used in flexible joints shall comply with AS 1646
6ccf6ddc-05e4-5ae1-bbc0-3600371a0d52 | note | ○ Precast concrete structures shall comply with NZS 3106
5be21035-6652-5758-8111-950a82d06f58 | note | Verifying Document - Manufacturer technical data sheet, DN-QUA-QC-10-Incoming Material Inspection, Photos
03791880-24ef-5f7f-abb6-296e84f04610 | note | Frequency - Prior to works
f24acf2e-798f-52ca-96f6-d25285af769b | note | Inspection Type (Visual, other) - Visual, Document Review
98eae593-91ab-5ad9-9d6c-a212f87dc965 | note | Inspection: Key - W
d825da9f-9456-546f-9791-38a09c203f6e | note | Inspection: By (Role Key) - SE
bd96a05a-88bc-41f4-b97d-da420ccde121 | checkpoint | 3.5 - Rock Flume - Rip Rap
637a12ce-fa95-57e5-acf8-b2e4ed4f0ba8 | note | Inspection Point: Quality Control Activity - Prior to construction
a8c48139-901b-5307-9986-9fc2730ed092 | note | Specification Reference - Project Specification CL 23.2.3
e34428a5-4e8c-51e0-b35c-6eb4b949be2d | note | Acceptance Criteria - Rock sizing as per the contract drawings.
e409fb6f-1c7b-504d-8ced-d377169c7183 | note | ○ Greywacke rock with specific gravity no less than 2.65
6e46d072-8226-5bee-8309-a219cec5d855 | note | ○ See Cl23.2.3 for grading envelopes
6dac6c76-a805-5f02-a609-facb14f23995 | note | Verifying Document - IANZ Lab Report
7b6bdecf-499e-579e-a932-1cebca8fdb90 | note | Frequency - Prior to works
0b88e206-2bcd-51d5-b942-75fe3d5fc005 | note | Inspection Type (Visual, other) - Visual, Document Review
21ac305d-896a-59d6-8ddc-6a9e6db158df | note | Inspection: Key - H
e3199073-27e4-501c-ba44-eaea4d730efa | note | Inspection: By (Role Key) - ER
453e320f-cd7b-4641-97b7-606787dfc68e | signoff | AUTHORITY HOLDPOINT
74365bc3-cd1c-4bf5-ad92-dc3caf907c9f | checklist | DS2681-SH58-ITP-M-002 – Barrier Materials | itp | DS2681-SH58-ITP-M-002 – Barrier Materials
471a096f-65e5-46a0-9d8c-6f5778509964 | section | SECTION 3 – RECEIVING INSPECTIONS
e484edf5-e8f1-4831-afa2-aa0bb258bd6e | checkpoint | 3.1 - Barrier materials (Standard W-Section)
db79f351-9494-5982-84b0-0b96406407f1 | note | Inspection Point: Quality Control Activity - Barrier materials (Standard W-Section)
13b8cade-0bef-5b3f-bcff-7acb0271dcf2 | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
8b163a3c-226c-5985-aa27-787ebb0e7369 | note | ○ W-section to comply with MASH TL-3
232c7304-09dc-5937-92a6-ceeb61b49352 | note | Specification Reference - PS Cl 22.1.1 NZTA M23
fbc1629b-0857-5885-bd0a-2ffcbcdbdea1 | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
8ed1b730-66ad-57a0-a334-fe8a05efeb6c | note | Inspection: Key - W
a3312eff-23cb-5b0e-8c0b-35df136e1363 | note | Inspection: By - SE
0992ddb7-b8f9-476c-8b0d-9e51b9095280 | checkpoint | 3.2 - Barrier materials (End Terminals W-Section)
97dc9cdc-3622-59c1-b262-67e7feebb0d5 | note | Inspection Point: Quality Control Activity - Barrier materials (End Terminals W-Section)
23f3d615-2291-545f-9b61-cfe7b1c2aabd | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
660ba2d5-4bd3-5927-84e5-7738a4489213 | note | ○ Leading End Terminals to comply with MASH TL-3
520643f6-0cc8-5406-9561-049be3cb3e65 | note | ○ Trailing End Terminals to comply with MASH TL-3
4ef63b43-90f0-58cd-9188-8fb6e0edd2af | note | Specification Reference - PS Cl 22.1.4 NZTA M23
849e27ca-c8a8-52f0-b52a-b45b8ba6867b | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
a6948697-3b35-5d71-8e0e-17108a527a18 | note | Inspection: Key - W
e9374a95-696b-532c-b12a-ea52e324152f | note | Inspection: By - SE
7452e330-8449-4b4e-a175-9583779d5d58 | checkpoint | 3.3 - Ground Beam: Concrete Mix Design
32801ec8-21f2-5480-b9af-95ad01ec8f4f | note | Inspection Point: Quality Control Activity - Prior to works
703a732f-3243-5872-adbf-c936b014dc17 | note | Acceptance Criteria - Contractor to provide Concrete Design Mix information to the Engineer. 30MPa Mix
053295dc-d926-54a7-b890-7a75e9f9f4b4 | note | Specification Reference - PS Section 24 Per Manufacturer Specifications
f2db903d-5252-58f7-a44a-27a39eaaf44e | note | Verifying Document - Mix Design
76638934-6c9e-5e35-9a6d-7018f5465526 | note | Inspection: Key - H
2eb135c1-191b-50c9-a3bb-bc5361010e18 | note | Inspection: By - ER
6504a965-f15a-4e72-97a6-b8f7b0cc347c | signoff | AUTHORITY HOLDPOINT
4bd47eb0-06c8-433c-9ab7-63b825aab5ff | checkpoint | 3.4 - Barrier materials (Thrie Beam)
f0521525-f947-50af-8cdb-63b27d7a73a8 | note | Inspection Point: Quality Control Activity - Barrier materials (Thrie Beam)
539e307b-bea8-5eb6-bdb5-8b7b21afd893 | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
5c22bd5d-e0de-5c01-a734-9bb51178e5b7 | note | Specification Reference - PS Cl 22.1.1 NZTA M23
6370f7cf-c2dc-5d00-915e-a0c580fb81e9 | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
45e26742-1ab8-5575-9d5d-cff308f93976 | note | Inspection: Key - W
dcdf5167-58c0-54af-89da-8801a2e6cb11 | note | Inspection: By - SE
2a50eba3-8c21-40e0-88ac-cc1d768a0100 | checkpoint | 3.4 - Barrier materials (Thrie Beam Transitions)
615cd999-83c1-5334-98b4-3c4174f8870c | note | Inspection Point: Quality Control Activity - Barrier materials (Thrie Beam Transitions)
c1cb9cc2-309e-52ae-86fe-8c82f6a5894f | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
950f113e-e503-5e98-9b8c-d7882890691d | note | Specification Reference - PS Cl 22.1.3 NZTA M23
b0e8c93c-67d9-58ab-8eb3-2f46c813dc5e | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
84eb2e97-084b-566e-8c09-04f1893e03b2 | note | Inspection: Key - W
fdeecb55-0319-5daa-8ec3-c1258138f04f | note | Inspection: By - SE
e68dc3f2-6ac7-4c85-8f30-5d2b948f07b5 | checkpoint | 3.5 - Barrier materials (Wire Rope)
94651e0c-127f-58e5-b829-5e7fcf96de64 | note | Inspection Point: Quality Control Activity - Barrier materials (Wire Rope)
730f0aaf-e24c-5696-ac14-1b93bcdd5dc2 | note | Acceptance Criteria - To be supplied, fabricated and protected in accordance with the drawings and specification.
a1b40703-529b-5e87-9243-d87c9ff6f02a | note | ○ Wire Rope to comply with MASH TL-4.
03efe69b-2f77-5e33-a3ab-e537c9002a5c | note | Specification Reference - PS Cl 22.1.1/22.1.8 NZTA M23
2fbc2c9e-82d7-52fb-ab8c-02f343ec424c | note | Verifying Document - Docket, Manufacturer's Drawings/install instructions
9c5f3090-0cdb-5697-9720-3527f0a8c504 | note | Inspection: Key - W
c10d80e7-eb24-5417-b43e-f2d7b03f3d29 | note | Inspection: By - SE
123ac222-293e-4a1c-98c9-5e8dd681f18b | checkpoint | 3.6 - Terminal End: Concrete Mix Design
d04fe5f4-d8de-5d58-84a8-8febc400e946 | note | Inspection Point: Quality Control Activity - Prior to works
8eb8ecd6-d25b-58fa-ac93-8f9d1f1d1842 | note | Acceptance Criteria - Contractor to provide Concrete Design Mix information to the Engineer. 30MPa Mix
35f1dc3d-f242-52de-8657-65a33219c1fd | note | Specification Reference - PS Section 24 Per Manufacturer Specifications
bd0ad8ce-2923-5afa-8991-ea5429c5d267 | note | Verifying Document - Mix Design
0d4b8669-296f-589d-8373-0c7f5a9bca39 | note | Inspection: Key - H
44b70f7d-ef25-5251-a350-95fea634f58b | note | Inspection: By - ER
59afb7f2-432d-4da9-adcf-80a4a2dbf5b9 | signoff | AUTHORITY HOLDPOINT
3e057d11-4fde-4940-ad40-044528697159 | checklist | DS2681-SH58-ITP-M-003 Earthworks Materials | itp | DS2681-SH58-ITP-M-003 Earthworks Materials
58292683-ff6e-4b9c-a15c-e67e34c450e1 | section | SECTION 3 – RECEIVING INSPECTIONS
5e44d725-1630-472f-bd79-01ba92b790a4 | checkpoint | 3.1 - Pre-Construction Survey
b9b7905e-c23e-5cdb-a8f6-635d63445278 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
31ff9d67-1ead-5222-b63c-29ab88a7560f | note | Specification Reference - Drone/GPS
c203eb51-f0a5-5ce8-b6d6-c0b614115687 | note | Acceptance Criteria - Receipt of survey by engineer
98bb493b-d4dd-57e1-a7c7-e83d973342b7 | note | Verifying Document - Topo Survey
0ee5708c-0c7f-5f17-bef2-aae0829e82b5 | note | Frequency - Prior to works - each lot
5647ce7f-29a9-5d0b-b62e-ca4bdc8de760 | note | Inspection Type (Visual, other) - Witness
c35d10d2-94d4-5b0c-9150-77ec04395548 | note | Inspection: Key - W
f9cec978-8728-5a00-96f6-234faab89a65 | note | Inspection: By (Role Key) - SPE & SV
fb6a885f-bc2e-44b8-bf18-5b5936d5de9e | checkpoint | 3.2 - Use of Flighty's Mound material for fill
83e9871d-9b43-5302-9dc6-d7ad045e5cda | note | Inspection Point: Quality Control Activity - N/A
19512bdd-e48b-51dc-89c4-ddfb0de869f2 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
9a4a79a1-2839-5ff4-a126-b0d3452930bf | note | Acceptance Criteria - Confirmation of use
34debe48-a486-546e-904b-6e8014a5a664 | note | Verifying Document - Mail Confirmation from Stantec Representative
6fac3a31-1810-5553-85f6-764a647fa647 | note | Frequency - Start of Earthowrks
5cfd1f51-236d-5777-9593-c8d3aca01c76 | note | Inspection Type (Visual, other) - Hold Point (where required)
9dcd6d82-1c02-5c55-8f6b-61d8d9ced0c4 | note | Inspection: Key - H
443625b6-2d56-5441-8eb8-c89c4b793db6 | note | Inspection: By (Role Key) - ER
83210422-9963-4264-bb3a-721408b0dc84 | signoff | AUTHORITY HOLDPOINT
f57b4c64-1650-4198-bbff-6b3f97bf845d | checkpoint | 3.3 - Use of Moonshine Rd Cut material to be used for fill
23f8223e-8878-53d3-a0b4-46e2e20161d7 | note | Inspection Point: Quality Control Activity - N/A
09355543-d1e1-5825-a9fc-1daeb67f5fa1 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
0c975a8c-c57d-505d-90a6-9cef5f592b6e | note | Acceptance Criteria - Confirmation of use
afb5a1e2-9d9b-593a-af56-f933dbe7038a | note | Verifying Document - Mail Confirmation from Stantec Representative
263b8a98-db66-5c08-91b7-43ddb035d10b | note | Frequency - Start of Earthowrks
ff7f016b-96ef-54bc-b0c7-6e9de2b2743a | note | Inspection Type (Visual, other) - Hold Point (where required)
e959f38a-476c-594c-bad8-8c5109c06a9d | note | Inspection: Key - H
5606d63e-4aa1-5450-9549-55346f1476fd | note | Inspection: By (Role Key) - ER
138b6ec4-b6f6-4d1f-83df-1d656388dcf6 | signoff | AUTHORITY HOLDPOINT
f8ec3898-e7a6-4d2e-9c03-9042496922bf | checkpoint | 3.4 - AP65 Material acceptance
12b60150-0d1a-5092-b38b-a943450949d2 | note | Inspection Point: Quality Control Activity - Specification Cl 17.1.11
8ff19d59-64b5-5ed9-87fc-a16e9060919e | note | Specification Reference - Material Testing and Compliance
f1bd496b-69e9-5504-9056-4bf90fb73070 | note | Acceptance Criteria - IANZ Testing
7b731e0d-5131-5a74-bf8c-b1abebe2a40d | note | Verifying Document - Testing report
3a9226aa-7744-5c32-b720-be008fc9a112 | note | Frequency - Every 1000m3 or change in material source
035aa4a9-d40b-570e-8c9c-72f347b723f5 | note | Inspection Type (Visual, other) - Hold Point
d6f21f79-9c71-50b0-a284-291368871795 | note | Inspection: Key - H
7619a487-0163-5a7f-8316-c16039c2ed5f | note | Inspection: By (Role Key) - ER
e36c2d94-b8f8-442b-b6fc-196ba4557a0c | signoff | AUTHORITY HOLDPOINT
0d369293-c495-45e7-8aba-cda22b54a1e0 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
1588c0dc-9eea-4e9a-8789-a22b28d2b3c1 | checkpoint | Inspection Point/ Signature & Date
f07723a8-9764-5ffd-b451-4922c8f1ca26 | date | Date:
44f8fdc4-4407-5786-b498-e4fe329d162c | textbox | Customer Requirements Verification Record / Location/ Hold Points
72ab6684-5339-492b-a21c-93214725af5a | signoff | Downer Signature
f83a3c3d-19e0-49b0-ad9c-551ff0d9f244 | checklist | DS2681-SH58-ITP-M-004 Anchorbloc Materials | itp | DS2681-SH58-ITP-M-004 Anchorbloc Materials
008e3399-0c4c-480d-985a-d0d9c4a3854e | section | SECTION 3 – MATERIALS
d2cbe193-61d9-48fc-baa3-6459d732b845 | checkpoint | 3.1 - Material Compliance - Precast Anchorbloc
236ea25f-4c47-524b-8b0e-db3422621258 | note | Inspection Point: Quality Control Activity - Prior to construction
b73c317d-2404-5107-a663-cffe95efae0c | note | Specification Reference - Project Specification CL 18.1.5
e120fd47-864b-5ee8-b739-03fb0e5ba0f6 | note | Acceptance Criteria - The Contractor shall provide to the Engineer, full details and specifications of the anchorbloc including ACEGrid and locking bar. Details to be provided by manufacturer
bf74536c-8c0a-5ee0-9cb8-545eba5374c1 | note | Verifying Document - Technical/ product data sheet, Delivery dockets, ITR-Incoming Mateirla Inspection (DN-QUA-QC-10)
fb5cf264-6cd5-558e-a18d-2af877afdc76 | note | Frequency - Prior to works
de5545c8-abec-5c92-9e30-32fc4cba4a1f | note | Inspection Type (Visual, other) - Document Review
4e03527e-8b95-55a9-9493-f2b6132b5d9f | note | Inspection: Key - H
884e1342-d957-545d-aef3-19ab2f2b4ab4 | note | Inspection: By (Role Key) - ER
b23892a2-2706-4e7b-bdb4-b51374b20140 | signoff | AUTHORITY HOLDPOINT
5361584e-066c-4169-b796-06d0a45898e9 | checkpoint | 3.2 - Material Compliance - AP65 (M4 if required) basecourse
3912d841-9a78-5476-a118-fbcf3ea30151 | note | Inspection Point: Quality Control Activity - Prior to construction
27adb929-b263-5858-b8c7-0de22bfc2a46 | note | Specification Reference - Project Specification CL 18.1.5
7e78e64b-8a60-502e-ab8b-a76d767dca24 | note | Acceptance Criteria - free of unsuitable material as defined in the Earthworks Specification.
033c4773-3060-53bf-b10f-384f962d96fd | note | ○ Fill to contain no more than 20% passing a 75μm sieve.
c4069131-935f-5cb4-8049-f7324c1c706c | note | ○ Fill to have maximum particle size of 100mm
37fba15e-deca-5f98-b7d2-a83068cf59a6 | note | ○ Fill particles shall be able to be incorporated within a single layer. Further, less than 30% of particles shall be retained on the 37.5 mm sieve.
d223f501-b8af-5fc5-ab3f-dce154eb86ab | note | ○ Unless otherwise approved, the MSE Wall Fill shall have a Liquid Limit less than 70% and a PI less than 6%.
969f8c1e-14fc-524c-8c57-b5be8de8672d | note | ○ MSE Fill shall be able to be tested in accordance with conventional compaction test methods for soil. Where Nuclear Densometer is used, these methods require less than 20% retained on the 37.5 mm sieve. Where between 20% and 30% of particles are retained on the 37.5 mm sieve the above test methods shall still be adopted and test reports annotated appropriately including reference to any test calibration or correction adopted
87036a87-7c73-55fc-975f-e6c4e7cf490b | note | Verifying Document - IANZ Lab Report
6eff4877-d4fa-59f3-b680-5a730f2d8be1 | note | Frequency - Prior to works
55b77c6c-6e67-55a2-a671-38555ea40c67 | note | Inspection Type (Visual, other) - Lab Test Report
37d8de5c-3fc2-52f6-8254-24c55035f315 | note | Inspection: Key - H
52af1624-9dea-589b-8b13-75408cbd732a | note | Inspection: By (Role Key) - ER
cee8377e-b405-42eb-8f2a-138840960e13 | signoff | AUTHORITY HOLDPOINT
27589e34-bef9-420c-9aef-eb894b1802e5 | checkpoint | 3.3 - Geogrid for Anchorbloc Wall
2b58bf4f-b054-554c-9805-9ea243be3eba | note | Inspection Point: Quality Control Activity - Prior to construction
4d3962ea-e394-55d3-8f73-3840b63196e0 | note | Specification Reference - Project Specification CL 18.1.5
c522d217-5023-5d9a-acc8-b16350beb48d | note | Acceptance Criteria - The Contractor shall provide to the Engineer, full details and specifications of geogrid reinforcements details including manufacture data
fb544482-7b74-5d02-8aa5-59b9841673bb | note | ○ STRATAGRID SGU80 to or equivalent to be used as per 80510096-02B-900-C470 Rev 1 drawing
f6d27564-a890-58bb-8e53-cbfdc50143ef | note | Verifying Document - Technical/ product data sheet, Delivery dockets
bb11fb2e-23de-593f-b8d5-9ecc62d76a1c | note | Frequency - Prior to works
08cef798-9891-5255-89ec-0aac6175b827 | note | Inspection Type (Visual, other) - Document Review
1d7d302c-0604-56fa-86a3-2f7df3b9ee0e | note | Inspection: Key - H
824acc24-ca1d-586f-8759-62b0a8f0ab0c | note | Inspection: By (Role Key) - ER
96b0f1bd-8b75-487a-b951-21670e6269e3 | signoff | AUTHORITY HOLDPOINT
98c0856a-6f56-480f-ac05-7081533624b1 | checklist | DS2681-SH58-ITP-M-005 Concrete Materials | itp | DS2681-SH58-ITP-M-005 Concrete Materials
d5ab3b3c-0f08-4489-b507-966114266098 | section | SECTION 3 – RECEIVING INSPECTIONS
c52c7a87-f426-46df-805c-3e7b8c1cb78c | checkpoint | 1.1 - Concrete Mix - Mix Design
683c9c84-e834-5516-82f9-b2a2f122b7f0 | note | Inspection Point: Quality Control Activity - Mix design submission to Engineer
9ac82ddd-5690-5b40-810b-9c2e4ae23eca | note | Specification Reference - Specification Cl 26.1.11
e8e6e22d-1612-522d-ab85-05f8ce4fc0ac | note | Acceptance Criteria - Mix Design to be forwarded to the Engineer for review and approval.
e586b215-d2da-5d18-8f22-1d0182bad929 | note | Verifying Document - Concrete Mix Design Document
3f2025f5-6889-548d-b1b9-00c7f7f98f9e | note | Frequency - 14 Days Prior to use
8609036c-e724-5049-9dce-fae83954443f | note | Inspection Type (Visual, other) - Hold Point
3d6a9bc8-e1cd-5452-aa63-669a6d5fab88 | note | Inspection: Key - H
aa768536-6844-5b77-898d-0b81e9e2bc9c | note | Inspection: By (Role Key) - ER
03fff456-0140-4c88-916d-6004eb8cddb2 | signoff | AUTHORITY HOLDPOINT
30ecaf87-f7b1-4752-9d73-502fafc45f65 | checkpoint | 1.2 - Reinforcing Steel
c0b4bf55-752c-52d6-893c-08c1d16803c3 | note | Inspection Point: Quality Control Activity - Reinforcing Steel
b5b3a9b4-735d-5260-8a4f-c04e9f2261ee | note | Specification Reference - Specification Cl 26.3
c2a03d3c-4940-5346-925d-d625cea9571a | note | Acceptance Criteria - Reinforcing bars shall be cut and bent according to NZS 3109, Section 3 and NZS 3101, Section 8.4 to the dimensions and shapes as shown or indicated on the Drawings.
f6cbe4a3-af5c-57db-93df-9546b4c687b1 | note | ○ Bend diameters for longitudinal reinforcing shall be in accordance with Table 3.1, NZS 3109 and Table 8.1, NZS 3101. Stirrups shall be bent to standard shapes as shown in NZS 3109.
dc4b71aa-6b62-53a8-ba24-576c2ed1fb2b | note | Verifying Document - Mill Certificates & bar bending schedule
db154963-1182-5cdb-9836-502ecdc64bba | note | Frequency - Prior to & after delivery
11360594-82d0-5280-ad98-4b2662fff509 | note | Inspection Type (Visual, other) - Hold Point
3acae266-bd39-5968-9332-bfdd0f236af9 | note | Inspection: Key - W
d8c29529-4f76-53f2-afe8-2a6cd52b3c3f | note | Inspection: By (Role Key) - SE
a780f40f-b814-44b7-bb81-8c078ba65425 | checklist | DS2681-SH58-ITP-TW-001 Bridge 3 Crane Pad and Cofferdam | itp | DS2681-SH58-ITP-TW-001 Bridge 3 Crane Pad and Cofferdam
8b4a06af-f3fd-4798-b069-a3f54cebe229 | section | SECTION 4 – CONSTRUCTION
a5395934-1809-46a4-b6dc-a722a2f205ec | checkpoint | 3.01 - Sheet piles
337804e3-5d76-59e5-8aec-dce4195acf13 | note | Inspection Point: Quality Control Activity - Prior to works
5517a392-6b81-5998-99a2-5da91322c08f | note | Acceptance Criteria - Prior to installation, a visual inspection of the sheet piles will be conducted to ensure they are in good condition. The inspection will verify that the sheet piles have the required length to reach the necessary depth for proper driving
3cbf7e27-f44d-5a76-b8b1-71e573be162b | note | Specification Reference - Please refer to Bridge 3 – Temporary Works Design.
f7538b9b-dc7a-5e9e-b14b-48e10946998a | note | Verifying Document - Visual
baff159a-488b-54b8-a1a9-cbb1d919649b | note | Inspection/Test: Key - V
5e837a1f-c97f-5a5e-b496-7d3ce39987a8 | note | Inspection/Test: By - SE
8376b579-3291-4bb6-b75b-ea613d6a6667 | checkpoint | 3.02 - Steel Waler Beams
6eafd378-b9a6-52a4-b339-e67d00ad9f74 | note | Inspection Point: Quality Control Activity - Prior to works
10125bf5-c710-5db1-8b7d-e4a10c81dcd6 | note | Acceptance Criteria - Confirm steel section 360UB44
f6b3b1b9-66b2-531c-96a1-b474ba484ab7 | note | Specification Reference - Dwg 2681-TW-003
2d90cdda-9fa2-5bf8-8803-48a08c9185f7 | note | Verifying Document - Visual
85482575-4469-5011-a3de-353ab5e922b5 | note | Inspection/Test: Key - V
3e367dc1-4625-5bfb-9f11-8a43437b3397 | note | Inspection/Test: By - SE
7548f1a5-3352-4102-aeaa-db9ce9c66441 | checkpoint | 3.03 - Welds
6f0eac25-59ba-516b-9906-dbb36268de04 | note | Inspection Point: Quality Control Activity - Prior to works
64155e2c-c540-5846-b625-7eba40d2803a | note | Acceptance Criteria - All welds to be visually inspected and if any defects are found, they need to be reported.
9f255b5b-fe7f-54e4-b631-7e1fa857a8ba | note | Specification Reference - Please refer to Bridge 3 – Temporary Works Design.
63e9be0b-9467-5b25-a09d-028245fb4184 | note | Verifying Document - Visual
61efaa63-47fc-5fb8-82c6-b0fcc86c96ca | note | Inspection/Test: Key - V
1b6332e2-bffa-5e5b-acc5-cc0e68b4f942 | note | Inspection/Test: By - SE
21bb4d73-e0d0-447a-8c2f-e0eb9edd4914 | checkpoint | 3.03 - Concrete
80c2c853-0b26-586c-8c5f-228af463989a | note | Inspection Point: Quality Control Activity - Before removing any walers
ec0be5ec-2a9f-5015-b726-5791d213152a | note | Acceptance Criteria - Report all QA for concrete to the Engineer including delivery dockets and report on placing before removing any Walers.
a7caf8d6-a2c8-580d-ab26-75cb75902352 | note | Specification Reference - Please refer to Bridge 3 – Temporary Works Design.
fc3d5127-7cd8-582b-b316-f0924de07584 | note | Verifying Document - Check
3a0d896a-a4ba-564c-9828-98db646a9051 | note | Inspection/Test: Key - H
83b58ba2-5ac5-5ad7-aa35-f7a4b05aa667 | note | Inspection/Test: By - SE
882324fc-72f4-4814-a79e-a39ae6e53b8e | signoff | AUTHORITY HOLDPOINT
3b6c6df1-a711-4b4e-a385-25bf145be2ff | section | SECTION 4 – IN-PROCESS INSPECTIONS
8fab1a69-89d4-451d-81db-9d2329a26410 | checkpoint | 4.01 - Location and marking of the cofferdam and crane pad.
68c7d3c8-87ea-5372-a1ac-989d8bac9b17 | note | Inspection Point: Quality Control Activity - Prior to works
7e1cd10c-0955-5f8b-9e7d-fc90792fca88 | note | Acceptance Criteria - The final location of the cofferdam and the working platform should be clearly marked on-site, ensuring the dimensions and alignment with respect to the pier extension, and considering the proximity shown on the drawing.
acae8cff-b7c4-5ffe-abbc-9f4be8fb9a03 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
d1aaa651-9a60-522b-a13a-ca353d121b40 | note | Frequency - Prior to sheet piles instalation
ebb5064b-ac29-5395-ba9b-f275d38c1269 | note | Inspection Type (Visual, other) - Dimension inspection
fd8669da-0cb8-5f1f-aed4-bf8e6d1b45b5 | note | Inspection: Key - D
270412f7-1809-5639-a389-cb51b3a9a4d1 | note | Inspection: By - SV
ee09d6fd-8bea-4b74-bfd6-8b2b0d9861c8 | checkpoint | 4.01 - Sheet piles installation
7075e275-b231-5ab9-84e8-ca5cd0c243de | note | Inspection Point: Quality Control Activity - During construction
79cdf414-4da8-5a8d-81cf-bf6d60255d81 | note | Acceptance Criteria - The sheet piles will be driven down with the excavator to just below the platform level, ensuring the design height is achieved and that the piles have reached rock level. Report sheetpile embedment depths to the TW Engineer
5e05615b-780f-5f0a-8423-8e3856198035 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
10586229-eb0b-5dc3-8fb9-f82b39232839 | note | Frequency - Driven down of sheet piles
2145d466-a6d4-59f7-b6ef-dd41e7a1348c | note | Inspection Type (Visual, other) - Hold Point 1
4a79d3a1-6e0a-5543-aa83-7e60acef4bc7 | note | Inspection: Key - C
72611a73-da45-56ee-b855-7840ff8919cf | note | Inspection: By - TWC
dd9bb3b5-6b62-49ce-96cb-13d2d611176c | signoff | AUTHORITY HOLDPOINT
d34ba0f7-dcf7-4855-ba7e-f3e85d08b94f | checkpoint | 4.03 - Top waler installation
23f05287-7479-5f68-a58f-56eb1458fbaf | note | Inspection Point: Quality Control Activity - During construction
c13e7389-5885-5c23-8dcc-d524f8c56c01 | note | Acceptance Criteria - Check the levels of the underside of the waler to ensure it is just above the top of the new pier. Install and support the Top Waler. Drive the sheet piles around the waler. Weld the Top Waler in place.
55ff975b-7b0d-5006-a3ea-597e721d2889 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
fd1dc12e-92d5-5096-99c9-ce5d0c1eeb2c | note | Frequency - First waler installation
a049a546-bdb0-50e2-be8f-9e6c96621348 | note | Inspection Type (Visual, other) - Inspection
22f0954d-1c61-51c4-8c6e-36e4c518217f | note | Inspection: Key - I
0b7fa0a3-1863-58c0-8e73-7486e8560a10 | note | Inspection: By - SE
15272899-c882-44e7-99d9-57f9a0edda84 | checkpoint | 4.04 - Lagging installation
5085e75e-24ce-5a5f-a318-777b307720d7 | note | Inspection Point: Quality Control Activity - During construction
031bd681-1c44-5775-9830-4ce6d90ae797 | note | Acceptance Criteria - During the lagging installation between sheetpiles and bridge Abutment, ensure there is sufficient space for the formwork, with a minimum clearance of 900mm. The lagging must be securely fastened both to the sheet pile and the pier.
e393a6d4-473d-585a-9281-de0b56d5553f | note | ○ As new boards are placed underneath, they may need to be held to the lagging above. Uuse vertical boards nailed to the lagging above if necessary to hold the new lagging in place.
1ba9eef6-e5be-5d14-9ddc-ffda11df9d6e | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
34bc8105-4a47-5c68-bca4-6a21837d5f12 | note | Frequency - During construction
ae9f6082-baf7-52a1-9a42-254860e06d93 | note | Inspection Type (Visual, other) - Check
ef16ee9f-0320-5269-ae48-eb0968cda188 | note | Inspection: Key - C
a58564e0-5a1b-59ad-aa27-aa15a44efb78 | note | Inspection: By - SE
7e7eb349-cf93-4f3b-887b-4913a7e59ded | checkpoint | 4.05 - Second waler
2de26da0-5ae9-5ceb-a06f-121e5831abb5 | note | Inspection Point: Quality Control Activity - During construction
7d5615e4-ea77-5ecf-8002-5448d1d44dc1 | note | Acceptance Criteria - Monitor excavation and ensure that measurements are being taken to not exceed depths.
91397559-b404-5e3a-8d45-2cd8dcd497cb | note | ○ The TWC shall inspect the waler before excavation proceeds. Excavate to a maximum depth of 2.25m, then install the brackets and the second waler. Pack the space between the waler and the sheet piles with grout bags.
300990ae-a1b7-569f-a58e-408ac2f7a53a | note | ○ Support the Waler using chains from the Waler above if necessary until excavation has continued far enough to weld the bracing leg to the bracket.
2ee962bf-6da3-5f8c-8211-6e57937ec023 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
563b749e-a05c-5d1e-9ebe-edaacc6936b4 | note | Frequency - During cofferdam excavation
57f74609-f413-5841-b8ca-2754d5332859 | note | Inspection Type (Visual, other) - Hold Point 2
b798249e-9efe-5fbf-af3f-2cc05e5c6635 | note | Inspection: Key - I
fc71ff53-e045-540d-ac99-6d3fa1837422 | note | Inspection: By - TWC
60eb107e-13c2-47ed-97b8-e8247ab57b7e | signoff | AUTHORITY HOLDPOINT
e790c6a4-080b-48be-869b-7edc89c6f513 | checkpoint | 4.06 - 3rd waler
ff6416f5-6044-5a3d-bbfd-d42bfd3ffc70 | note | Inspection Point: Quality Control Activity - During construction
bd6bfbe1-d8dc-594f-9d67-993c185012d4 | note | Acceptance Criteria - Monitor excavation and ensure that measurements are being taken to not exceed depths.
13da5144-9b38-5250-b1d3-eace21d64ed5 | note | ○ Excavate to 3.58m (max) BGL, install brackets and install 3rd Waler.
54fb1aef-e4c1-5b2d-92fd-7ac64ad48685 | note | ○ Pack between Waler & Sheetpiles with grout bags.
1e11142b-bbaf-5704-aa74-de31164b538e | note | ○ Support the Waler as noted above if necessary as excavation proceeds.
51955ec0-9f13-5bd3-b800-b22abb319b97 | note | ○ TWC to inspect Waler before excavation proceeds.
84a4d86e-045a-571b-84f0-f122dd9ebc41 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
2b24438e-c3f6-5ebe-9b28-59f5cbb52e9f | note | Frequency - During cofferdam excavation
7381e671-b68a-5661-8006-af616f8dab50 | note | Inspection Type (Visual, other) - Hold Point 3
195824c1-6c90-590b-abf3-78964ab292ce | note | Inspection: Key - I
f7e6ae53-2d0c-5d51-a23f-121a339a169d | note | Inspection: By - TWC
3cbd5ce3-a4e8-4eb2-91c2-f525ca6ef055 | signoff | AUTHORITY HOLDPOINT
0f786c51-ffb8-4f73-9f4b-bce7092da028 | checkpoint | 4.07 - Welds
13f5431e-8499-5d4b-b2f8-8c1170f43ccb | note | Inspection Point: Quality Control Activity - Welding review
32ee2221-8d75-5e5e-a466-4947f76ae52f | note | Acceptance Criteria - All welds to be visually inspected by the TWC and any defects reported to the Engineer. Each of the 100mm long stubs are to be identified, marked and photos of each sent to the Engineer for approval.
f113c158-703d-5757-89bd-797cc16bd96b | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
f0a062d4-c8cd-5054-a758-baaf3b87bc4f | note | Frequency - During welding process
687be8bd-3695-5210-ae0e-cfe2feceb1e7 | note | Inspection Type (Visual, other) - Inspection/ Hold point
78a9a900-7f79-5b7a-8167-fc4ed00997d8 | note | Inspection: Key - I
aa876991-959e-599b-9590-1f3445018716 | note | Inspection: By - TWC
bbfd9002-aac9-4858-aeb7-5b8d513b82ef | checkpoint | 4.08 - Welds
fbb27cdb-78a1-5dd3-9dbd-d16edfc1c5db | note | Inspection Point: Quality Control Activity - Welding review
bb9ed266-fe7a-5e72-a019-f00128ee71a5 | note | Acceptance Criteria - All welds to be 6mm Fillet Weld all round UNO.
1f14415d-80a2-5897-bbfd-c011d11a72b0 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
4aa03e57-cf81-5454-8631-69bf7833a748 | note | Frequency - During welding process
274ca933-86ec-55dc-8803-176148bb7bd0 | note | Inspection Type (Visual, other) - Inspection/ Hold point
3b6d152e-9644-5704-81d2-d1967ccbd9f9 | note | Inspection: Key - I
3e8e3f94-7b10-5be2-8782-d8fea60a5846 | note | Inspection: By - SE
1ba4c663-d038-4f64-97c9-c9d1e75d2ef3 | checkpoint | 4.09 - Platform level
b80865ce-8fdd-5bc5-8d72-1af4209c3c33 | note | Inspection Point: Quality Control Activity - Prior to works
5e53ed25-6ca8-592e-bc70-b6f0318347d5 | note | Acceptance Criteria - The platform level must be 325mm below the road level at the center location of the bridge.
bb341712-17d2-5211-89df-9069994e20cc | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
3f47f52b-c406-5d97-b98b-6342c37e9625 | note | Frequency - Before platform works
74fc7cd1-7e00-5ebf-9a4e-b9c14a1bfe0c | note | Inspection Type (Visual, other) - Check
73f4003a-19f0-50aa-baa5-1c4a9c94fd71 | note | Inspection: Key - C
f787b870-02c8-50fe-96eb-deacddeb104b | note | Inspection: By - SE
9a0c8613-e021-4851-a651-0fd6aed860c8 | checkpoint | 4.10 - Reidbar
54caf3de-0629-5ec1-9a36-c1fbbfd36601 | note | Inspection Point: Quality Control Activity - During construction
06620704-e94b-53e5-b922-a28223a8bef9 | note | Acceptance Criteria - Install reidbar ties 500mm below top of platform
246f7222-a6bc-425d-9e0a-6e9058de3076 | checkpoint | 4.11 - Cofferdam excavation
9078b223-b715-5dd0-af82-e8288bf78319 | note | Inspection Point: Quality Control Activity - During construction
db69a183-4b94-5461-b2f8-e73928583f04 | note | Acceptance Criteria - TWC to inspect bracket braces before excavating to full depth. Fully de-water and clean out down to rock level
6725446a-d473-50a5-b250-0ca8db2bc758 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
da6cbf0d-c121-5b77-9116-c36c98d067c9 | note | Frequency - Cofferdam excavation
798dd406-eaf4-5b60-ba45-609836540c23 | note | Inspection Type (Visual, other) - Hold Point 4
8fccafd2-0a6d-5823-b6a8-a3fc6e5ef87a | note | Inspection: Key - A
fdf87a6b-b6ed-54d7-b206-45759560468e | note | Inspection: By - TWC
25da986b-fca7-4c84-af95-c03691608001 | signoff | AUTHORITY HOLDPOINT
a9f9c6b5-8bb7-4b8b-9bb4-cc53f28c4930 | checkpoint | 4.12 - Concrete toe
d5f56073-54ac-585f-a0b4-6c671a71749a | note | Inspection Point: Quality Control Activity - During construction
3a3231be-2795-57c3-9ac1-f559ad009241 | note | Acceptance Criteria - Cast concrete toe support 400mm thick. Report all QA for concrete to the Engineer including delivery dockets and report on placing before removing any Walers. Remove second and third walers after 7 days.
185904ef-7116-56b5-84bc-25282c0d55bc | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
d9a53304-ae18-562e-8031-53b4368eb41f | note | Frequency - After excavating to full depth
ccacef58-ea3b-5794-a208-a82dc2660c1b | note | Inspection Type (Visual, other) - Hold Point 5
dada6981-9412-51b6-a7f3-ef5038112f27 | note | Inspection: Key - A
b037d7e9-0233-5017-a886-be57b81abc9a | note | Inspection: By - TWC
4c2005e5-a3c4-4ee9-b1e2-d10b49ede8e3 | signoff | AUTHORITY HOLDPOINT
1c2b3930-87a3-4180-a9a7-b6fac27e4a1e | checkpoint | 4.13 - Hydro response
0faff7fa-23b2-5a2e-824d-6d12534ed5f6 | note | Inspection Point: Quality Control Activity - After sheet pile installation
88883587-80d2-551a-b5a6-cf303ab4dbd9 | note | Acceptance Criteria - PVC sheeting is to start from the far side of the bridge and continue past the cofferdam, as advised by the waterproofing contractor.
d5137578-76ef-50b3-9492-fdfb1863059e | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
e3fcc12e-3de8-5ba4-8b1b-923982d38aec | note | Frequency - After sheet pile installation
cb9df2e2-ffad-551e-a0cc-30765ea084b0 | note | Inspection Type (Visual, other) - Action
863bbd9e-630e-505b-841c-8a2d5c230b15 | note | Inspection: Key - A
f15a9c01-2082-5818-ae4d-a08605dabc54 | note | Inspection: By - SE
55b44029-4b25-48e4-a853-349a1e708879 | checkpoint | 4.14 - Hydro response
7c2f2089-f6af-5017-932b-6334e9a3ba8e | note | Inspection Point: Quality Control Activity - After sheet pile installation
700d37e2-2711-5819-b701-524ca5b1d5ce | note | Acceptance Criteria - Attach the PVC sheeting to the sheet piles and to the concrete bridge pier beneath the bridge.
5b67b76c-bb12-5a60-a19e-df2292717951 | note | Verifying Document - Please refer to Bridge 3 – Temporary Works Design.
98125785-6358-5d58-80eb-0d0535b977ec | note | Frequency - After sheet pile installation
584d29f0-d061-53a0-b990-f291878a2b25 | note | Inspection Type (Visual, other) - Action
f9b6745d-33d0-5cdd-a8cf-8b3e035433e8 | note | Inspection: Key - A
cbfecad5-3a3a-5803-93d4-c384d4ec8fc3 | note | Inspection: By - SE
4ade9ac3-1d12-4c2b-8279-dde37a0e2f56 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
6a51f8b0-8d64-4aa0-acaa-34fe6047edbb | checkpoint | 5.01 - Final Handover
54babb17-a9b3-5e4e-aba4-de6a7e819239 | note | Inspection Point: Quality Control Activity - Documentation
bc5074e1-6691-5cbd-a5ad-348044d77739 | note | Acceptance Criteria - All hold points must be formally reported to the Engineer for inspection. A photographic record of the inspected works shall be maintained. Proceeding beyond any hold point requires explicit approval from the Engineer.
5b61c1f6-7c03-5863-8a0d-35e6ed7a4a3a | note | Verifying Document - Permit to Load
279ccd49-f799-5389-a103-153e0923ede5 | note | Inspection/Test: Key - A
53f45d76-0e9b-50a3-827a-ac7470cf908d | note | Inspection/Test: By - TWC
22c4a63c-dfe5-4c5b-8872-81e9b4a3c37b | checklist | Ω (DEPRECATED) ITP-0002 Earthworks Cut | itp | ITP-002 Earthworks Cut
58292683-ff6e-4b9c-a15c-e67e34c450e1 | section | SECTION 3 – RECEIVING INSPECTIONS
5e44d725-1630-472f-bd79-01ba92b790a4 | checkpoint | 3.1 - Pre-Construction Survey
b9b7905e-c23e-5cdb-a8f6-635d63445278 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
31ff9d67-1ead-5222-b63c-29ab88a7560f | note | Specification Reference - Drone/GPS
c203eb51-f0a5-5ce8-b6d6-c0b614115687 | note | Acceptance Criteria - Receipt of survey by engineer
98bb493b-d4dd-57e1-a7c7-e83d973342b7 | note | Verifying Document - Topo Survey
0ee5708c-0c7f-5f17-bef2-aae0829e82b5 | note | Frequency - Prior to works - each lot
5647ce7f-29a9-5d0b-b62e-ca4bdc8de760 | note | Inspection Type (Visual, other) - Witness
c35d10d2-94d4-5b0c-9150-77ec04395548 | note | Inspection: Key - W
f9cec978-8728-5a00-96f6-234faab89a65 | note | Inspection: By (Role Key) - SPE & SV
67451a6a-8cea-4ef4-a602-3d151731a5f4 | section | SECTION 4 – IN-PROCESS INSPECTIONS
eb5fd506-7948-4670-96c6-7831c5fafefd | checkpoint | 4.1 - Topsoil Depth Checks
de3d5445-3307-5b23-8aba-28f82720e2d1 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
44f07abe-85b7-54db-b372-d03d9a585c2c | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
a4de364f-08bf-5b9c-b022-6dc85551c8d9 | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
5510836b-ae61-540a-b704-85c3a5a6bfe6 | note | Verifying Document - Site Photos, Record Sheet
4103d90f-e4e8-5da3-82b6-0ff867bb7135 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2eb5b3dc-7fbe-5392-8414-62b6bcdc5cf3 | note | Inspection Type (Visual, other) - Witness
9e0530ad-9dea-5be2-8d73-2a9795b48e4e | note | Inspection: Key - W
d4639d9a-6767-5269-beb3-1215691074e9 | note | Inspection: By (Role Key) - SE
7f30c528-f201-40dc-a527-ab421a6f883e | checkpoint | 4.2 - Hazardous & Classified Soils
a664ce29-a8e5-5d63-bf17-014a35d000d3 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
f27256d6-4592-5d4e-b73e-a3f74a51ddcb | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
3936fc1e-e1d7-59bf-809a-00f5e6081b10 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
ca6b4c12-6d5d-5ba8-9c78-a9d7afb7bd23 | note | Verifying Document - Visual, Site Photos
4c1efc39-f017-5255-86c2-be965b493de3 | note | Frequency - Continuous
5133fb55-1305-57a9-92d0-3b06cc30e7bb | note | Inspection Type (Visual, other) - Witness
1cb75dd6-d38d-54c4-8a6a-1d495d5c3c41 | note | Inspection: Key - W
8e4f7cfc-35d6-5afe-b23d-7b61efbc098f | note | Inspection: By (Role Key) - SE
7486c58c-9fb9-4a38-88b8-d8792c7aa396 | checkpoint | 4.3 - Final Cut Observation Monitoring
347fdff0-3102-5435-ab25-bee766125209 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.6
4c207fc2-d9dd-50df-b46f-e08c487449e2 | note | Specification Reference - Continuous visual assessments conducted with Stantec Representative. Contractor to address design change if instructed
3ba2bd1d-904b-51b3-b6d0-9bb09aa69e01 | note | Acceptance Criteria - Agreement with Engineer's Rep
66603339-865d-527b-956f-0eb5c2b210cb | note | Verifying Document - As Required by Stantec Representative, QC-01 Earthworks Checksheet
4f7df1dd-eee8-52c9-81fc-4ba03ad868e4 | note | Frequency - As requested by engineer
d2081a75-cfd1-5c2e-b034-a5ec45a3a4b5 | note | Inspection Type (Visual, other) - Hold
56b79a36-efd0-5403-a2ad-bb8a1356d7da | note | Inspection: Key - H
dbb2871b-47f9-592a-8990-7dd356b5fdf4 | note | Inspection: By (Role Key) - ER
f191c6b6-2aab-4164-96e9-e47a0b3675af | signoff | AUTHORITY HOLDPOINT
2cdfb66a-9389-4627-8667-eef40cd2af5f | checkpoint | 4.4 - Cut Batter Tolerances
132eeb5a-fe9d-5df7-9be4-782120e3ef4c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.7
56c83086-c7e9-591b-b20c-40fe8793f938 | note | Specification Reference - Post-construction - Excavation of batters complying with design issued and within tolerance
ee66d3c0-49a5-5d67-a4b8-18faff38f4bf | note | Acceptance Criteria - Slope Tolerance 1H:1V or Flatter: +300 / -300 mm
79a3c917-608e-50cd-ab7f-e9fde7c7f119 | note | ○ Steeper than 1H:1V: +300 / -600mm
bc450905-2158-5089-979e-c8eff2fda31f | note | Verifying Document - As-Built and DN-QUA-QC-01 Earthworks Checksheet
207498a5-e043-56c3-835c-476f874fa023 | note | Frequency - Continuous
efa9913e-4bbe-5fbd-93b7-b9e6a3302e68 | note | Inspection Type (Visual, other) - Witness
d3cab161-6063-560d-945e-a4cc933e71a5 | note | Inspection: Key - W
ab994e35-4b7d-51e2-9377-c0539f957500 | note | Inspection: By (Role Key) - SE/SV
9ac63d2d-3fdf-41a8-8a9e-87424a2ecd20 | checkpoint | 4.5 - Site Fill Material - Segregation of Material Type
6f0f9b0b-029a-522d-a566-d1cf24cf370c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.8
aceeaf6b-a147-5532-9113-38bc69c47f73 | note | Specification Reference - Moisture sensitive material stockpiled
bb49d682-186e-5a46-813b-e57556aa8fa2 | note | Acceptance Criteria - Drainage blanket (polythene cover) if any material is stored on site to avoid saturation
c7f353d1-7f18-5f61-872b-b7f030221da3 | note | Verifying Document - Visual, Site Photos
801989f2-a1a7-5cb5-a394-0c7653136733 | note | Frequency - Continuous
e72a8aec-2da8-56be-bced-9018554b9697 | note | Inspection Type (Visual, other) - Witness
0d762aba-083d-5501-b776-f4c5925a4422 | note | Inspection: Key - W
08311d38-a7ef-5a95-b4bd-5c3fa8e79616 | note | Inspection: By (Role Key) - SE
192b71df-9dfe-44fb-ad89-61f682f2a57c | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
e676d3ad-166c-4de3-98c3-ae9896beecb7 | checkpoint | Inspection Point/ Signature & Date
b072bae1-74c0-5098-bd68-d5405a971db5 | date | Date:
18d8e4a4-5b1d-58d0-8bf9-f29766a313f4 | textbox | Customer Requirements Verification Record / Location/ Hold Points
2a4a07e0-640c-4290-bbe6-638dd12e0a67 | signoff | Downer Signature
0fd3b40d-d5bc-4ee1-b7cf-cd706f2c2b77 | checklist | Ω (DEPRECATED) ITP-0003 Earthworks Fill | itp | ITP-003 Earthworks Fill
4db9a2cd-fead-4294-8bda-07b7e01f9ed0 | section | SECTION 3 – RECEIVING INSPECTIONS
33804c9b-8306-4ef4-af37-b1fadcbb644f | checkpoint | 3.1 - Pre-Construction Survey
e2804895-a838-508c-bbb7-43797df277f7 | note | Inspection Point: Quality Control Activity - Specification Cl.2.11.2, Cl.15.6.6
b40edbe2-e1c0-5dcb-8c3e-0b54df45b607 | note | Specification Reference - Drone/GPS
0eaf6ac2-7a41-583a-9fd1-eaa7ba8cb0a8 | note | Acceptance Criteria - Receipt of survey by engineer
849af7f9-f7dc-5970-9ac9-249dc805c4c7 | note | Verifying Document - Topo Survey
75f5bc98-01ce-5c4a-8099-d2120b4139b8 | note | Frequency - Prior to works - each lot
6a3baaa9-45ee-5a22-a888-971cdcfbebdf | note | Inspection Type (Visual, other) - Witness
83370141-d3cb-5408-bcf3-08952a10fd8d | note | Inspection: Key - W
7d34db44-95ae-56cb-bc7f-8eb78d6bda17 | note | Inspection: By (Role Key) - SPE & SV
fb6a885f-bc2e-44b8-bf18-5b5936d5de9e | checkpoint | 3.2 - Use of Flighty's Mound material for fill
83e9871d-9b43-5302-9dc6-d7ad045e5cda | note | Inspection Point: Quality Control Activity - N/A
19512bdd-e48b-51dc-89c4-ddfb0de869f2 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
9a4a79a1-2839-5ff4-a126-b0d3452930bf | note | Acceptance Criteria - Confirmation of use
34debe48-a486-546e-904b-6e8014a5a664 | note | Verifying Document - Mail Confirmation from Stantec Representative
6fac3a31-1810-5553-85f6-764a647fa647 | note | Frequency - Start of Earthowrks
5cfd1f51-236d-5777-9593-c8d3aca01c76 | note | Inspection Type (Visual, other) - Hold Point (where required)
9dcd6d82-1c02-5c55-8f6b-61d8d9ced0c4 | note | Inspection: Key - H
443625b6-2d56-5441-8eb8-c89c4b793db6 | note | Inspection: By (Role Key) - ER
83210422-9963-4264-bb3a-721408b0dc84 | signoff | AUTHORITY HOLDPOINT
f57b4c64-1650-4198-bbff-6b3f97bf845d | checkpoint | 3.3 - Use of Moonshine Rd Cut material to be used for fill
23f8223e-8878-53d3-a0b4-46e2e20161d7 | note | Inspection Point: Quality Control Activity - N/A
09355543-d1e1-5825-a9fc-1daeb67f5fa1 | note | Specification Reference - On site material visual confirmation and IANZ testing requested by the Stantec Representative
0c975a8c-c57d-505d-90a6-9cef5f592b6e | note | Acceptance Criteria - Confirmation of use
afb5a1e2-9d9b-593a-af56-f933dbe7038a | note | Verifying Document - Mail Confirmation from Stantec Representative
263b8a98-db66-5c08-91b7-43ddb035d10b | note | Frequency - Start of Earthowrks
ff7f016b-96ef-54bc-b0c7-6e9de2b2743a | note | Inspection Type (Visual, other) - Hold Point (where required)
e959f38a-476c-594c-bad8-8c5109c06a9d | note | Inspection: Key - H
5606d63e-4aa1-5450-9549-55346f1476fd | note | Inspection: By (Role Key) - ER
138b6ec4-b6f6-4d1f-83df-1d656388dcf6 | signoff | AUTHORITY HOLDPOINT
f8ec3898-e7a6-4d2e-9c03-9042496922bf | checkpoint | 3.4 - AP65 Material acceptance
12b60150-0d1a-5092-b38b-a943450949d2 | note | Inspection Point: Quality Control Activity - Specification Cl 17.1.11
8ff19d59-64b5-5ed9-87fc-a16e9060919e | note | Specification Reference - Material Testing and Compliance
f1bd496b-69e9-5504-9056-4bf90fb73070 | note | Acceptance Criteria - IANZ Testing
7b731e0d-5131-5a74-bf8c-b1abebe2a40d | note | Verifying Document - Testing report
3a9226aa-7744-5c32-b720-be008fc9a112 | note | Frequency - Every 1000m3 or change in material source
035aa4a9-d40b-570e-8c9c-72f347b723f5 | note | Inspection Type (Visual, other) - Hold Point
d6f21f79-9c71-50b0-a284-291368871795 | note | Inspection: Key - H
7619a487-0163-5a7f-8316-c16039c2ed5f | note | Inspection: By (Role Key) - ER
e36c2d94-b8f8-442b-b6fc-196ba4557a0c | signoff | AUTHORITY HOLDPOINT
d8549d1c-6084-4eb6-aa34-e1037e972367 | section | SECTION 4 – IN-PROCESS INSPECTIONS
9c62c46d-be03-4325-a269-2e1cce813bfd | checkpoint | 4.1 - Topsoil Depth Checks
5b8fa5b8-196b-5600-971a-f3b6d4d676fc | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.4
a452a378-61e0-5c00-b74c-c726008ddc11 | note | Specification Reference - Nominal depth checks at 100m intervals longitudinally and 50m interval transverse
03b3720f-8844-514c-9229-a15264506e4d | note | Acceptance Criteria - Photos with tape measure to show depth of topsoil layer. Date and location to be recorded
08613c48-b482-5be7-a20d-be6627cb7408 | note | Verifying Document - Site Photos, Record Sheet
5e42a0de-49e9-5c4a-9848-bd849cebdb25 | note | Frequency - 100m intervals longitudinally and 50m intervals transverse to earthworks
2795d9b2-d7e0-5caf-8f7a-d709a310f2ca | note | Inspection Type (Visual, other) - Witness
3c37b622-502a-5fdc-8c4e-c6d62706b017 | note | Inspection: Key - W
a7deaea1-b306-5546-aefc-792f32b9a252 | note | Inspection: By (Role Key) - SE
4f861c4d-56fa-4f86-853b-b326a5bf7d87 | checkpoint | 4.2 - Hazardous & Classified Soils
31f36bba-8168-5228-8e14-d54e6ebb023d | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.3 & 15.3.5
602225a7-35c1-539c-84a2-97e895accb97 | note | Specification Reference - Hazardous waste and contamined soils encountered during the excavation process
9e4f6c65-b625-582f-9951-e8ae49d7aa98 | note | Acceptance Criteria - Contractor to advise the engineer if type R2, U or H materials are unexpectedly encountered
4aa4b873-ce3c-5c30-9ddc-6654f6e713b5 | note | Verifying Document - Visual, Site Photos
9a2e7738-8add-5898-b720-a8718215117e | note | Frequency - Continuous
54149323-7e72-5849-b492-bf0b4e9e66bb | note | Inspection Type (Visual, other) - Witness
25ac1de1-7c21-582e-addc-72843b5c923a | note | Inspection: Key - W
3618481a-1a64-57a8-9586-d337c91a4efe | note | Inspection: By (Role Key) - SE
c77466cb-88d4-4d6d-a030-db3f490b0008 | checkpoint | 4.3 - Subgrade testing - Trim and Compact
5a6340d0-a1e7-59c4-9ff0-588daa5c7eeb | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.10
b3e2023e-c87d-5688-9fe8-5c28b6e001fb | note | Specification Reference - Trimming & Compaction of in-situ subgrade. Conduct plateau test.
73cd4ba2-b734-5a25-bb8e-51f26523c1bc | note | Acceptance Criteria - N/A
a3135f5c-ffa6-566b-a008-acdf06b7a12a | note | Verifying Document - Plateau worksheet
cd56e528-0d47-5c9b-abb4-a6f1f7588792 | note | Frequency - Full surface
76f971c6-ab70-5525-bc64-d7cd53497773 | note | Inspection Type (Visual, other) - Witness
f9e71c06-ff1d-5a81-b94c-c384b2eb2de0 | note | Inspection: Key - W
9af2e9cd-1409-5027-b8b4-57fd373d5b98 | note | Inspection: By (Role Key) - SE
6e0b306e-8217-45b6-aa98-3f2da0ad944c | checkpoint | 4.4 - Subgrade testing - Scala
f0fc626b-ce1b-5fc1-a9e2-beb9b21d8252 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.11
36376860-ec21-5a49-8311-bb3c84021acb | note | Specification Reference - Scala Testing
f2c390cd-8a69-5e01-80fd-4edcc1f34413 | note | Acceptance Criteria - 1 blow per 100mm is the minimum requirement for general fill placement
e92b1fd8-2193-5e1c-828b-0e6a473a274b | note | Verifying Document - DN-QUA-QC-04 1m Scala Worksheet
deec5fd9-20d3-5143-a3bc-06d8138e21c3 | note | Frequency - Scala Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
35e62849-6a45-54a6-a33a-948f4a254b61 | note | Inspection Type (Visual, other) - Witness
e6ad1732-5fb2-569e-ab78-d897cd7be49c | note | Inspection: Key - W
2e49b9f7-548e-5556-99db-562e0914b2eb | note | Inspection: By (Role Key) - SE
d08f3a23-a67f-46a3-b73b-2d43b3bf99fb | checkpoint | 4.5 - Subgrade testing - Benkelman Beam
28f510e5-01d5-515a-973a-2b22920e6ab5 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.12
bf32ece9-b533-5d25-826a-80b1481b63e4 | note | Specification Reference - Benkelman Beam Testing
4dfdc5b1-2fd1-5773-a841-951f1236e3f9 | note | Acceptance Criteria - Top of subgrade 3.3mm 90th percentile with maximum of 4.0mm
3a4a1436-0c04-582c-9fe8-166f28a73d8e | note | Verifying Document - Lab report
8167b6e0-f261-5c03-b8b7-7e2a11cf30eb | note | Frequency - Beam Tests: Within lane lines staggered wheel path every 10m. Shoulder every 10m.
5d887dfa-3825-5eb6-918c-a27123ab1be0 | note | Inspection Type (Visual, other) - Witness
e06d1c39-0759-5f50-bf41-af433f55d06c | note | Inspection: Key - W
de8ed31f-dca1-543c-ab81-20618767ee4f | note | Inspection: By (Role Key) - SE
69f4e90b-552e-439b-988f-1e72f0b7b957 | checkpoint | 4.6 - Subgrade testing - Proof Roll
1839ae8e-4785-5e89-ae30-6878bdbefa44 | note | Inspection Point: Quality Control Activity - TNZ F/1 Cl.9.2, Project Spec Cl 17.1.5 - 17.1.13
b84289c8-b380-5f42-9801-1dc5845914e1 | note | Specification Reference - Proof Roll
c1f942b1-a560-533c-b67e-43446bab6d03 | note | Acceptance Criteria - As instructed by the Engineer
6d7c2351-765a-59e4-8dd6-c7b85ae08027 | note | Verifying Document - Visual Assessment - Sign off on ConQA by Engineer
cd2ca153-edff-5158-b93a-c3c9bff4a274 | note | Frequency - Proof Roll: Full surface using suitable plant
a473ece9-ef13-57d1-b8b3-63e66c288983 | note | Inspection Type (Visual, other) - Hold
17decdd9-724b-5160-953e-fbe77be61e8c | note | Inspection: Key - H
b1837a51-96fb-5325-b4fc-49fde76f9d1e | note | Inspection: By (Role Key) - ER
4034b935-2e19-43c5-8b87-422e5ce2a877 | signoff | AUTHORITY HOLDPOINT
baff8782-7812-409c-955d-22faaf8a2d45 | checkpoint | 4.7 - Fill Compaction Trial
3b1aa582-7080-50f7-a743-4d1a834e0c3e | note | Inspection Point: Quality Control Activity - Project Spec Cl 15.6.11
b59340bf-1c1e-5b01-9685-d1d249c2da6f | note | Specification Reference - On-site Testing - NDM, Visual, Shear Vane
3072fcc1-2d40-5f8c-a101-d668ffc305b1 | note | Acceptance Criteria - Complete the trial compaction as specified in project specification (15.6.11). Engineer to witness the trial compaction and release H P
a16bbc46-f692-5511-98cc-f9dba2f08730 | note | Verifying Document - NDM Worksheet, Shear Vane Worksheet, Plateau Density Sheet
245f9472-8924-59b7-af93-07fabe64fbc0 | note | Frequency - When a new type of fill material is used
cb7f9df4-0ad0-511e-9839-256019215ea8 | note | Inspection Type (Visual, other) - Hold
9ad8e962-7572-5e64-9aef-a31d67b4fc4e | note | Inspection: Key - H
c9c7d82b-adec-5235-81cc-c72bb9211895 | note | Inspection: By (Role Key) - ER
f985a566-05fe-4bca-aa0a-63ece48458e9 | signoff | AUTHORITY HOLDPOINT
ac487538-1b27-4fb7-82cb-3d1c832dc83b | checkpoint | 4.8 - Fill Backfill layer thickness
9dc0ddd5-7081-5c5b-aad6-244ddd534627 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.3.8
9100536d-2452-5d74-8636-8012cb1a7aa7 | note | Specification Reference - Uncompacted thickness of each fill layer and trial fill section meeting the degree of compaction
b573abdd-0e24-5b25-9997-15ae932b717b | note | Acceptance Criteria - Fill placement not exceeding 230mm
c7aae880-1974-5f3b-9be6-50d71e180eb1 | note | Verifying Document - Visual, Site Photos and NDM check sheets, DN-QUA-QC-09 NDM Worksheet
e281d108-66fa-59e2-8851-f46838f6719d | note | Frequency - Every layer
6f256caa-f61b-5b64-b071-a38145b5f2e7 | note | Inspection Type (Visual, other) - Witness
be7beb94-ad2b-54dd-83f0-38c8f5564a6d | note | Inspection: Key - W
35b64125-bc7b-5da4-be26-97b71b7af86c | note | Inspection: By (Role Key) - SE
bcc30a6b-119d-4743-8a79-baaf6dc3ee43 | checkpoint | 4.9 - Fill Compaction Testing Laboratory
613ffacb-21f8-55a0-ac5a-8f2d6e0c9561 | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.12
abf1c975-f467-550d-8803-5f63bbcc3a2f | note | Specification Reference - Water Content, Standard Proctor and Wet Sieve.
87cb7aef-ee1d-547e-ac81-b90003b86845 | note | Acceptance Criteria - N/A
404f0300-be8d-57c5-9ae3-09ef3f08131c | note | Verifying Document - IANZ report
45d7b2e9-2ab1-5bbb-ba2e-47b28b92899d | note | Frequency - WC - 1 test per 400m3 with 2 tests minimum per day, MDD & WS - 1 test per 2000m3
e4b62afa-6a64-517f-bfcf-bfb487b48f5d | note | Inspection Type (Visual, other) - Witness
78e96303-1f07-5a1a-b96e-b20bc84fe4c0 | note | Inspection: Key - W
66ee5b0c-a583-5bca-87d4-fe169198728e | note | Inspection: By (Role Key) - SE
4d840a77-0d83-418d-8eaa-5d3ace198277 | checkpoint | 4.10 - Fill Compaction Testing Site
170c0ce9-da4c-51cd-a656-534cc2598816 | note | Specification Reference - Compaction test by plateau
4cd4ea6f-fd7d-5182-9cb9-7ecd963f4105 | note | Acceptance Criteria - Plateau Testing to determine true MDD value based on site conditions
f435ba24-e53f-5101-81ee-295144d7851c | note | Verifying Document - DNZ Plateau Test work sheet
95c64cd4-0399-5ee6-84c8-fe44e0fe532b | note | Frequency - Daily
05ff474c-f5e3-5368-a1e9-39775e6ad1b0 | note | Inspection Type (Visual, other) - Witness
9df4d291-794f-5154-8fd0-3f6e2da0ae60 | note | Inspection: Key - W
8cd77cf0-88d2-5621-9a62-ae0a6c6560e3 | note | Inspection: By (Role Key) - SE
9bb0e863-25ab-4e2e-a5c8-736f7a3cbf9e | checkpoint | 4.11 - Fill Compaction Testing Site
a0f51fc5-3327-536a-a294-1323489b698c | note | Inspection Point: Quality Control Activity - Project Spec Cl.15.6.10, Project Spec Cl.15.6.12
e70d9530-82db-512d-bb7d-6470d91d214f | note | Specification Reference - NDM and OMC testing of fill material, Shear Vane
15556765-8e6f-5346-b003-a5130be21e1e | note | Acceptance Criteria - Moisture Content: between-2% and +4% of OMC
7fcab2ac-a9ab-5872-b45d-bd68049bbef8 | note | ○ Insitu Density: average of 98% of materials MDD over 5 consecutive tests. No single result less than 95%
a801c928-555b-535f-9716-82c12c5aa57f | note | ○ Shear Vane 150kPa average for 10 consecutive readings with no result less than 120kPa (Cohesive soil only)
e54e9950-49f6-5033-8c0b-245f5090e787 | note | Verifying Document - NDM Record Sheet, DN-QUA-QC-09 NDM Worksheet, Shear Vane Sheet (Cohesive soil only)
6fb339aa-e367-5272-b3ec-08785b7ada50 | note | Frequency - NDM - 1 test per 200m3 of fill placed, and, a minimum of 5 tests per day
017b0e48-efcf-5a5e-bb2b-aa847de2c09d | note | ○ Shear Vane - 1 test per 100m3 and additional test at NDM location (Cohesive soil only)
d36e4bf3-83f7-5ad9-b4a1-1195d43e9525 | note | Inspection Type (Visual, other) - Witness
479c803f-863e-5ecf-995d-ac9522d1ed37 | note | Inspection: Key - W
91ffb9e9-9267-5718-9b08-82760cad3387 | note | Inspection: By (Role Key) - SE
49dc47d4-4477-45df-98df-0234e7253c87 | checkpoint | 4.12 - Fill Tolerances
40d82a36-02ad-5737-8acb-c456c28f5187 | note | Inspection Point: Quality Control Activity - Project Spec Cl. 15.3.11
9e700a68-8e22-58e3-9974-7d3dfdfa1e95 | note | Specification Reference - Survey of finished surface
e79c980c-87de-5e44-b10b-3236c822d8b2 | note | Acceptance Criteria - Tolerance of +-50mm
447e271e-bca4-5ebb-add8-7fc00e2da9c3 | note | Verifying Document - As-built
bb9bf85e-e97c-59a1-ae14-091787bbd065 | note | Frequency - At Completion
460b02c8-ced0-56fb-9524-2652fccfcaa1 | note | Inspection Type (Visual, other) - Witness
7feba2b6-df9e-5aa3-954c-fc41cf3abc3b | note | Inspection: Key - W
d7211d8d-3c2a-58ce-ac35-6a15b5ea8287 | note | Inspection: By (Role Key) - SE/SV
b9a3e932-94cd-4693-a41e-146bbf0d7650 | section | SECTION 5 – FINAL INSPECTION AND HANDOVER
91d48c13-d2f8-45c4-af23-fde24dbb16ad | checkpoint | Inspection Point/ Signature & Date
c5b2747d-ce3f-524a-a1e6-6023b29c528c | date | Date:
db896672-4da5-53f6-9550-09d229e89fb7 | textbox | Customer Requirements Verification Record / Location/ Hold Points
f5dea672-25bd-4897-adf3-d2ef22a81c2d | signoff | Downer Signature