## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DS2681-SH58-ITP-C-006 Drainage (MH, HW, Sump) | itp |  |  |  |  | DS2681-SH58-ITP-C-006 Drainage (MH, HW, Sump)
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Trench subgrade
label | Specification Reference - Project Specification Cl 16.3.12
label | Acceptance Criteria - Contractor to confirm suitability of foundation material and where the Engineer considers that the foundation material below the pipes or structures is unsuitable as defined in the earthworks specification, this material shall be removed and replaced as outlined in the earthworks specification 3 blows per 100mm
label | Verifying Document - Scala Testing Record Sheet DN-QUA-QC-04
label | Frequency - 10m intervals
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.2 - Visual Inspection of Subgrade
label | Specification Reference - Project Specification Cl 16.3.12 TNZ F/1
label | Acceptance Criteria - Visual inspection of subgrade. Engineer to confirm any undercut treatment, if required.
label | Verifying Document - ConQA Hold Point
label | Frequency - Before placing bedding
label | Inspection Type (Visual, other) - Holdpoint
label | Inspection: Key - H
label | Inspection: By (Role Key) - ER
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Manhole Installation
label | Specification Reference - Project Specification Cl 16.3.25, Cl 16.2.8
label | Acceptance Criteria - Manholes are to be installed in accordance with the Regional Standards for Water Services, 2012 and NZS 4404:2010 Land Development and Subdivision Infrastructure, incorporating Hutt City Council amendments as detailed in Porirua City Council’s Code of Land Development and Subdivision Engineering, 2010.
label | ○ Precast concrete structures shall comply with NZS 3106. Joints between precast units shall be of the interlocking, self-centring type and shall be sealed with butyl mastic or similar approved to form a watertight joint
label | Verifying Document - Photos, DN-QUA-QC-07 Manhole Installation Checksheet
label | Frequency - Per Manhole
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.4 - Headwall / Sump Installation
label | Specification Reference - Project Specification Cl 16.3.35
label | Acceptance Criteria - All wingwalls/headwalls/outfalls shall be pre-cast proprietary and constructed in accordance with the drawings and NZTA F/3, which shall be deemed to form part of this specification
label | ○ Ancillary concrete structures required to complete the pipe installation including: headwalls; wingwalls;baffles, sumps; sump tops; aprons; drops; and intakes shall be reinforced and constructed as shown on thedrawings
label | Verifying Document - Photos, DN-QUA-QC-03- Sump/ Catchpit Istallation Check Sheet
label | Frequency - During Construction
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.5 - Tolerances
label | Specification Reference - Project Specification Cl 16.3.42
label | Acceptance Criteria - The permissible deviation of the location of manholes from the designated position shall be half a pipe length longitudinally and ±150mm laterally, except where locations are dimensioned from fixtures such as fences, kerbs and boundaries, in which event the permissible deviation in either direction shall be ±50mm
label | ○ The permissible deviation from the designated level of the invert at each manhole shall be ± 25mm.
label | Verifying Document - As-built
label | Frequency - During Construction
label | Inspection Type (Visual, other) - As-built survey
label | Inspection: Key - W
label | Inspection: By (Role Key) - SV
checkpoint | 4.6 - Backfilling & compaction
label | Specification Reference - Project Specification Cl 16.3.20
label | Acceptance Criteria - Hardfill shall be compacted in layers not exceeding 150mm loose depth using approved mechanical compaction equipment.
label | ○ Selected fill and Ordinary fill unless specified otherwise, shall be compacted to at least 90% MDD at optimum moisture content.
label | ○ Pavement layers shall be compacted to average 98% MDD with no result less than 95%
label | Verifying Document - Photos, NDM Test Results, DN-QUA-QC-09
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.7 - As-built Survey
label | Specification Reference - Upon completion of works
label | Acceptance Criteria - As built survey record completed
label | Verifying Document - As-Built
label | Frequency - After Works
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checklist | DS2681-SH58-ITP-C-007 Drainage (Rock Flume) | itp |  |  |  |  | DS2681-SH58-ITP-C-007 Drainage (Rock Flume)
section | SECTION 4 – IN-PROCESS INSPECTIONS
checkpoint | 4.1 - Excavation
label | Specification/Drawing Reference - 80510096-02B-900-C241
label | Acceptance Criteria - Slope to match bank, report back to engineer If steeper than 1:2 slope
label | Verifying Document - Photos, As-builts
label | Frequency - during construction
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SV /SE
checkpoint | 4.2 - Geotextile
label | Specification/Drawing Reference - 80510096-02B-900-C241
label | Acceptance Criteria - Layer of Geotextile(TNZ F/4 CLASS E GEOTEXTILE) to be placed at the base of the flume excavation
label | Verifying Document - Photos
label | Frequency - Continous
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE
checkpoint | 4.3 - Rip-Rap
label | Specification/Drawing Reference - Project Specification Cl 16.3.35
label | Acceptance Criteria - Rip Rap Lined Drain shall consist of sound durable rock not less than 150mm mean rock diameter (d50) and 300mm thick liner properly bedded on geotextile protected prepared drain.
label | Verifying Document - Photos, As Builts
label | Frequency - during construction
label | Inspection Type (Visual, other) - Witness Point
label | Inspection: Key - W
label | Inspection: By (Role Key) - SE