## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RSA.BitumenEdgeSeal.ITP | itp |  |  |  |  | RSA.BitumenEdgeSeal.ITP
section | 1 - Preliminary
checkpoint | 1.1 - Access Documentation
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Relevant ATW, LARS / PTA/ Concil Permits/ TMR Permits/ TCP/ TMP
label | Frequency - Prior to Start
label | Test Method - Review
label | Acceptance Criteria - All documents in place and correct.
label | Verifying Documents - LARS / PTA
label | ○ Landholder Notification
label | ○ Traffic Control Permit/Plan
label | ○ TMR Permits
label | ○ Species and Fauna Management
label | ○ Cultural Heritage Induction Attendance Register
label | ○ Cultural Heritage Clearance Report / Form
label | Responsibility: RSA - H
holdpoint | HOLD POINT
checkpoint | 1.2 - Mobilise Machinery & Fit For Purpose (FFP) Inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Permit To Access (PTA), Land Access Rules (LARs),PRA
label | Frequency - Prior to Start
label | Test Method - Review
label | Acceptance Criteria - Valid Weed Hygiene Certification for all vehicles and plant.
label | Verifying Documents - Weed Declaration Certificate. Appenate FFP Form
label | Responsibility: RSA - H
holdpoint | HOLD POINT
checkpoint | 1.3 - Gravel Compliance
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 6
label | Frequency - Each Quarry
label | Test Method - Lab Testing
label | Acceptance Criteria - Type 2.2 Road Base
label | Verifying Documents - NATA Test Report
label | Responsibility: RSA - R
section | 2 - Entry Turnout
checkpoint | 2.1 - Set out Entry Turnout Dimensions and delineate clearance boundaries
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
label | Frequency - Each Entry
label | Test Method - Visual Inspection, Set out by Licensed Surveyor
label | Acceptance Criteria - In accordance with IFC Drawing, Where no traffic lane or edge is marked on the road, the shoulder edge shall be interpreted as the intended traffic lane or edge lane.
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - M
checkpoint | 2.2 - Clear & Grub
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 3.2
label | Frequency - Each Entry
label | Test Method - Visual Inspection
label | Acceptance Criteria - Cleared vegetation stockpiled at regular intervals, As Required on site
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - M
checkpoint | 2.3 - Box Out if required
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
label | Frequency - Each Entry
label | Test Method - Visual Inspection
label | Acceptance Criteria - As Required on site
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - M
checkpoint | 2.4 - Install Invert Table Drain if required
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
label | Frequency - Each Entry
label | Test Method - Visual Inspection
label | Acceptance Criteria - Adequate darinage shall be provided to avoid water polling within the turnout area, Invert level at turnout to be such that flow in table drain is not restricted in any way. The lowest point of the new invert drain shall be the same as the lowest point of the existing table drain
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - M
checkpoint | 2.5 - Gravel Cap Entry Pavement and trim
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
label | Frequency - Each Entry
label | Test Method - Visual Inspection
label | Acceptance Criteria - All new pavement layers shall be adequately compacted and have the minimum required thickness.
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - H
holdpoint | HOLD POINT
checkpoint | 2.6 - Install Bitumen Two Coat Seal - 14/10mm C170
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Site Specific IFC Drawings
label | Frequency - Each Entry
label | Test Method - Visual Inspection
label | Acceptance Criteria - Bitumen edge seal to be applied to ensure surface durability and continuity with existing road pavement.
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - M
checkpoint | 2.7 - As Built Completed
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - IFC Entry Turnouts gravel capping, Seal, Invert Table Drain, SOW
label | Frequency - Each Entry
label | Test Method - As Built Measurement
label | Acceptance Criteria - As built Entry Turnout Layout Drawing
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - D
checkpoint | 2.8 - RSA QA inspection
label | Relevant Documents: Controlling Procedure/ Specification / Standard / Drawings - Senex Specifications OPS-QLDS-CI-SPE-002: Section 7.1.2, Site Specific IFC Drawings
label | Frequency - Each Entry
label | Test Method - Visual Inspection
label | Acceptance Criteria - RSA Supervisor to inspect and accept the works are complete.
label | Verifying Documents - Entry Turnout FIC
label | Responsibility: RSA - H
holdpoint | HOLD POINT
section | Reference Documents
checkpoint-no-value | Reference Documents:
label | SENEX-QLDS-EN-PRC-003 rev 1 (Queensland Erosion and Sediment Control Procedure)
label | OPS-QLDS-CN-GDL-002 (Survey Peg Identification Guide)
label | OPS-QLDS-CS-DWG-011(Senex Standard Property Enrty/Exit Turnout Drawing)
label | R-004 & R-007 WDRC Council Road Turnout Dwgs
section | To be completed upon completion of all work activities
checkpoint | This is to confirm that the above ITP has been completely signed off. All necessary inspections have been completed, the verifying documents have been provided, and the works conform to the contract specification
label | Completed By:
textbox | Contractor Representative - Name:
textbox | Contractor Representative - Position:
textbox | Senex Construction Representative - Name:
textbox | Senex Construction Representative - Position:
label | Approved By:
textbox | Client Representative - Name:
textbox | Client Representative - Position:
date | Date:
holdpoint | Add Signature
checklist | RSA.WP20.FIC Entry Turnout | [5 empty] | RSA.WP20.FIC Entry Turnout
section | FIELD INSPECTION CHECKLIST ENTRY TURNOUT
checkpoint | Set out Entry Turnout dimensions and Delineate Clearance Boundaries
checkpoint | Clear & Grub
checkpoint | Box out if required
checkpoint | Install Invert Table Drain if required
checkpoint | Gravel cap Entry Pavement
holdpoint | HOLD POINT
checkpoint | Install Bitumen Two Coat Seal - 14/10mm C170
checkpoint | As Built Completed
checkpoint | RSA QA Inspection
holdpoint | HOLD POINT