## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP R44 (ed6) - Earthworks QA |  |  |  |  | Yes | ITP R44 (ed6) - Earthworks QA | 0d4889ed-ba25-48e2-b73b-18d36cf36b4a
checkpoint-group |  |  | section | Earthworks QA
checkpoint-status |  |  | checkpoint | 1 - Implement & monitor ERSED controls
label | 7e32794f-d3e6-5792-8d8a-65b981d45ea8 |  | note | Spec / Doc Ref. - R44.1.8, G38.3.1, G38.2.2.2
label | cd4e8c4e-f938-559f-ac00-5374ee468159 |  | note | Inspection Requirement - Submission of an ESCP(s), Submit written advice that the ESCP controls have been implemented or the date they will be implemented.
label | ba5b6107-9ccf-547e-974e-456f32c9ba08 |  | note | Acceptance Criteria - ESCP requirements listed in G38 Cl2.2.2.
label | 9d39707a-a7b6-58fc-b22d-c613905c323b |  | note | Frequency - ≥10 work days prior earthworks, ≥5 work days prior earthworks, each section
label | dd97ba97-2c10-583a-8e19-8a869f8c4cbb |  | note | H / W - H, W
label | 5f15267d-b81f-549e-b738-ee73b316a406 |  | note | Inspection/ Test Type - Submission, Submission & inspection
label | 777989b7-4169-5ffa-aad2-e4eb35b427dc |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, ESCPs, WPR
label | d827efad-4e49-58fd-8efb-ba210e58841c |  | note | Verified by - Project Mgr (PM) / Project Eng’r (PE)
date | 774fcc17-8b3b-5057-a7f7-4c994c0142f7 |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Existing utility locating & NDD potholing
label | d1c76032-6138-5b79-98f7-3cd40c892711 |  | note | Spec / Doc Ref. - R44.1.5.1 (n)
label | 8d249294-1b6f-5da8-a845-d90caf49f816 |  | note | Inspection Requirement - Check service locating & marking, and NDD potholing of existing utilities is completed
label | dac78447-1b4d-53a0-8f86-95b758ff4d78 |  | note | Acceptance Criteria - Controls to protect utilities during earthworks in place
label | 4d63c513-47db-553d-9dce-673a68a9899c |  | note | Frequency - Prior earthworks, each section
label | 9cd60a36-0fef-5a6b-8ffd-b67e873f9da2 |  | note | Inspection/ Test Type - Visual
label | 68ed99bf-ca82-59c0-bdd3-18616dd41112 |  | note | Verified by - PM / PE / Supervisor (S)
date | 1080154f-ffb6-5be3-905c-9a8dc0c8ee54 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 3 - Setout earthworks extents
label | 50e68ac3-dbf4-54a4-9f3e-c6703a98e455 |  | note | Spec / Doc Ref. - R44.1.6.2
label | 1008f8ab-1143-51c0-9c36-d61d50a5a5b1 |  | note | Inspection Requirement - Setout by marking on the ground the earthworks limits
label | cbfe62f2-5655-5832-8b3b-2cf9770feffd |  | note | Frequency - Prior earthworks, each section
label | b5b7750d-d5e9-5805-9ea7-71c22065bd17 |  | note | Inspection/ Test Type - Survey
label | d9392548-dda1-53cb-80f1-a8c1e51faf25 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo of marking in place
label | 15a76ed9-032d-5322-9dca-9260b1410d4c |  | note | Verified by - PM / PE / S / Surveyor
date | b6aebf0b-472f-5f24-83f4-28161ac1475e |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 4 - Removal of topsoil
label | fecb5c4e-607e-583e-94fd-db5104555783 |  | note | Spec / Doc Ref. - R44.2.5.1
label | 411f8b84-5c50-5843-981f-b269bdac22cb |  | note | Inspection Requirement - Check topsoil removed & stockpiled correctly
label | fc44c3cc-00b7-5309-86e0-055d71815a27 |  | note | Acceptance Criteria - Strip full depth of topsoil in earthworks areas. Stockpile for use in revegetation.
label | b34ed4bf-a249-5d7d-92b9-ff1baaacc951 |  | note | Frequency - each section
label | 6008c8fe-1d8f-59db-b021-25223d63046e |  | note | Inspection/ Test Type - Visual
label | baf20a52-6d58-541c-b341-8948b023fedb |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo
label | f953faf8-0e43-5b5f-9363-40f7a28192ff |  | note | Verified by - PM / PE / S
date | 52db033a-118f-5711-b1d9-9385f940dc94 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 5 - Test pits to verify CBR10 day & PI of subgrade & insitu SMZ
label | 040b72e8-0328-5d2c-864f-f1fda001ce73 |  | note | Spec / Doc Ref. - C-0604.00 R1 Table 6 RNB-241, R44/A2.2, R44/L.1
label | d50b5f8a-b8a3-577b-81be-09cf38d1cd31 |  | note | Inspection Requirement - Check CBR & PI samples completed from test pits
label | edc4af9b-ff0c-55e7-95f0-5d5fec5d500d |  | note | Acceptance Criteria - CBR: Subgrade ≥3%, Insitu SMZlower ≥ 15%,
label | 7de5ba4b-9047-5192-8050-ed3ec9c51cd4 |  | note | ○ Insitu SMZupper ≥ 30%
label | 639bd5d7-4cc2-5ed4-ba94-4612c39b1c57 |  | note | ○ PI≤25% (no insitu SMZ)
label | f49e6781-e8bf-54b6-a131-d03094620353 |  | note | ○ PI≤15% (insitu SMZ)
label | 1f826d12-6016-5086-88c1-66c9233ff287 |  | note | ○ SMZ: Max particle dim: 53mm, >50% passing 19mm sieve, >30% passing 2.36mm sieve
label | 44f2e777-df37-59bb-bf69-907d365a4683 |  | note | Frequency - 1 / 1000m2
label | 3274085b-f1f7-5628-b2c7-090ea927f23b |  | note | ○ 1 / 1000m2
label | fca28ef5-5e86-5ead-86b6-1fae5f3c9982 |  | note | ○ 1 / 1000m2
label | 050262ae-bcf3-552c-87d5-75a4d172977f |  | note | ○ 1 / 1000m2
label | 56a68af0-b5b7-5200-a0d3-1d2e12bc808b |  | note | ○ 1 / 1000m2
label | 7701d5e8-8a56-5fd2-8436-6c82d08a9be6 |  | note | ○ Each Lot
label | 1ccb04f7-395f-5de6-a1da-7a92934d6029 |  | note | ○ Each Lot
label | 9f6eaa01-59ba-58c8-82d6-52462740d51d |  | note | ○ Each Lot
label | 26758e8b-45d5-59b3-b1f3-f8ccb1b92547 |  | note | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
label | 55b66211-a001-51b4-91fb-b81e2dd86a06 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - CBR, PI, max particle, T106 test reports
label | 9bc7907e-e7d1-5f46-8e6c-568367a32bac |  | note | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
label | 4cf42276-6e4a-5bbf-88fd-5ec1deea8604 |  | note | Verified by - PM / PE
date | 1b2db79a-645b-5eef-8916-1fb941f1a369 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 6 - Excavate to design levels and profiles
label | c248b095-4188-52c7-89bc-84877aacb651 |  | note | Spec / Doc Ref. - R44.3.2, R44/A2.2 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222 Tbl R44.8
label | a32b30fc-b6a5-52fe-a702-be19216edd05 |  | note | Inspection Requirement - Check excavated to Design Floor Level (DFL). Check CBR & PI tests completed. Present floor for inspection.
label | a2c9aafb-df12-5e68-ac8b-e51eb57d98d5 |  | note | Acceptance Criteria - Where at Top of Formation (DSL-330mm), there is ≥300mm existing Sydney Rd pavement, SMZ comprises existing pavement left in-situ, therefore DFL is DSL-330mm.
label | 42d766b7-c307-504f-9f8f-2094bb035465 |  | note | ○ Where no existing pavement, DFL is DSL-630mm (& a 300mm SMZ to be provided).
label | c83dcd5a-2787-538c-96cf-57c3d271664f |  | note | ○ Level tolerance: +10/-40mm (no insitu SMZ), or +0/-20mm (insitu SMZ)
label | 52561b34-cdfd-5f0b-95fe-4d542d04d039 |  | note | Frequency - each section
label | 19c2d573-e1bd-5ad6-9789-6e96d45ae0f8 |  | note | H / W - H
label | 1bc4226c-25ea-5c46-ad23-24afdd8aa3f9 |  | note | Inspection/ Test Type - Survey, Test & Inspection
label | 4329924e-eac5-5ee4-8fec-cd426bbfa9e9 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, DFL Level conformance report
label | b3b4ba52-c627-5e5a-af00-5ecfe02df83a |  | note | Verified by - PM / PE
date | 7479b377-4a07-5966-8f65-e81b27af968f |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 - Proof roll DFL
label | 44797871-bad2-591a-a700-8e1f2b604c1d |  | note | Spec / Doc Ref. - R44.7.5, R44/L.1
label | c1b78ce6-6cef-59d5-8d63-a65c01ee7a78 |  | note | Inspection Requirement - Notify Council of proof roll (WP)
label | 2bcf2f1c-486c-5e98-b37e-545a84cc6705 |  | note | Acceptance Criteria - Not exhibit visible deformation, rutting, yielding or show signs of distress / instability
label | 011cdb1b-a583-51c1-9997-1d74bf6859bb |  | note | Frequency - ≤1 work day of proof roll
label | 78bec119-cf78-5d4d-b9b8-08931bb602c2 |  | note | H / W - W
label | f44d06f7-e266-5cfc-8081-290c14539877 |  | note | Inspection/ Test Type - T198
label | 016589ad-91b2-5083-bd5b-aef54fc27af1 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, proof roll (T198) report
label | 79acdef4-7007-5d84-bb0c-e1db329ae8ba |  | note | Verified by - PM / PE
date | 1c118335-f815-52f7-903c-f6cc30e43260 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 8 - Unsuitable Material (if any)
label | 7c96e5c1-d30b-5dec-b1ea-021382b31acc |  | note | Spec / Doc Ref. - R44.2.6, R44.5.2.1, R44.7.5, Tbl R44.7 R44/A5, R44/L.1
label | f885b761-5bef-591b-bc7d-64ebc19d14fa |  | note | Inspection Requirement - Where unsuitable material indicated by:
label | cc3b644d-3c3f-5bbf-8be5-6fa35c705faa |  | note | – inspection in item 5,
label | 847febee-7d6f-5e43-ac54-a06323cdc448 |  | note | – CBR / PI testing, or
label | 16b68dfa-d9f8-5f17-9302-9a51855ed654 |  | note | – proof roll, excavate unsuitable to the extent directed by the Principal.
label | f8494e5f-e54c-50dc-bdaf-4fe376426239 |  | note | ○ Notify when unsuitable removed to the extent directed (Hold Point).
label | 330cc4bd-ffc0-5cf7-aa7e-68a54bc12a61 |  | note | ○ Replace w/ compacted Earth Fill or (if directed) Foundation treatments
label | d3c36707-76bb-5b37-b768-7f1964e55906 |  | note | Acceptance Criteria - Min Rel Comp: 98%, Moisture: 60-90% of OMC
label | 0fc465dc-3d7b-59e6-8daf-12f789361071 |  | note | Frequency - each section of unsuitable material
label | a6357b40-86f4-5b3c-a802-bbe59eb59392 |  | note | H / W - H
label | 70ca88a6-96c4-5b3e-94f6-d01c12d821f7 |  | note | Inspection/ Test Type - Inspection, Refer R44/L.1, Refer R44/L.1
label | 30fa86ed-472f-5a26-98ab-941257303b6a |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, compaction & MC (if replaced by compactible material) report, Survey reports (before & after)
label | ab5b9980-2934-5a5c-918b-8abf0ba8169f |  | note | Verified by - PM / PE
date | 8017b09d-646a-5b11-9f71-ee7b13208467 |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9 - Site won SMZ material (for placement where no insitu SMZ)
label | 19ac260f-ba91-57a7-a3eb-f5e1e9bcb579 |  | note | Spec / Doc Ref. - R44.2.8.5.1, R44.6.1.2, R44/A2.2, R44/L.1 C-0604.00 R1 Table6 RNB-241,
label | 5d501bda-e17e-5ec8-a4ab-b6bdb0266133 |  | note | Inspection Requirement - Submit test reports verifying conformity of each site won SMZ material stockpile
label | fc895eda-7350-5c42-b3a2-545e0351686f |  | note | Acceptance Criteria - CBR10 day (per RNB-241)
label | e21fe58b-89e3-5be9-b6c9-a90be494a9e3 |  | note | – Upper layer: ≥30%
label | f55b8b70-704e-5a1b-819e-a5ec56f092a4 |  | note | – Lower layer: ≥15%
label | 6a4f3ddd-afd3-5573-864e-b13963330b1b |  | note | ○ Plasticity Index: ≤15%
label | bfb58ea7-5944-5c83-8536-d8b957d33c99 |  | note | ○ Max particle dim: 53mm
label | 0d314c1b-3ccc-5f36-89a0-64519fbd4209 |  | note | ○ >50% passing 19mm sieve, >30% passing 2.36mm sieve
label | 9442cbf8-a3f5-54f4-ac8d-e726b62b6896 |  | note | Frequency - Prior SMZ placement,
label | 89214678-936e-5ff1-a2bb-cda69281371a |  | note | ○ Each Lot
label | ea20bd1e-662c-58a4-8bc6-15e3a1d5d07b |  | note | ○ Each Lot
label | 617ef8e8-233d-5296-bea3-ad7c54241cc5 |  | note | ○ Each Lot
label | 5ebfe7ef-0405-530e-87cb-e2feba4a743d |  | note | ○ Each Lot
label | 840a481a-53bc-5431-b752-b8e557c99e02 |  | note | ○ Each Lot
label | a5360bf3-d9a7-52e0-b3cf-417664bc8bf2 |  | note | H / W - H
label | c59e0634-ff83-5ccd-b177-eb3b56155015 |  | note | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
label | a454f5ee-94f5-56fc-b8ff-5c3f4f690708 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, CBR, PI, PSD test reports
label | 2f51a9b6-bcb8-5da4-b775-b13f7112bda6 |  | note | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
label | 7c9801e4-7177-524b-9a95-923bc2c4f45c |  | note | Verified by - PM / PE
date | e0a163b3-80c0-540b-a4f4-2ded07531b4d |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10 - Placed site won SMZ Layer (for placement where no insitu SMZ)
label | 74917094-3781-5c5f-86f1-90ea65836b4a |  | note | Spec / Doc Ref. - R44.6.1.2 Tbl R44.7, R44.7.5, R44.7.7.1, R44/A5, R44/L.1 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222
label | 93f3e613-308b-5496-8a82-5980e6e53f70 |  | note | Inspection Requirement - Notify Council of proof roll (WP). Submit verification of conformity of SMZ, with test reports & survey conf reports. Check level, compaction, appearance, proof roll results conform.
label | 075a8ff2-2c2c-593d-8157-06361b52dc0b |  | note | Acceptance Criteria - Level upper: +0/-20mm
label | dfaa2807-8dae-543c-98ef-650ab575fac8 |  | note | ○ Level lower: +10/-40mm
label | 872893b2-0bb5-57bb-9c0b-70cdc21f2135 |  | note | ○ Thickness upper: 150mm
label | 0dfc9653-9759-5b1f-beab-3a3f2a01aeae |  | note | ○ Thickness lower: 150mm
label | 029027ed-0f32-5280-ba6e-267f4163e7c3 |  | note | ○ Compaction: 102%
label | de83741f-60cf-5c97-8383-535d6bda6fef |  | note | ○ MC: 60-90% of OMC
label | 9bec27c2-38ab-5a19-8fb1-c323336b4610 |  | note | ○ Appearance: homogenous & free from segregated stone or excess fines.
label | 86c06c51-08d7-52d0-8b22-f665adc573f6 |  | note | ○ Proof roll: Not exhibit visible deformation, rutting, yielding or show distress/instability
label | 67d92102-29b9-5c94-befb-9caea366865a |  | note | Frequency - ≤1 work day of proof roll, Prior covering SMZ, Survey & geotech testing refer R44/L.1
label | 2d083156-ba57-50dd-a568-abcf4590f9ed |  | note | H / W - W, H
label | c8e1506f-9888-5eac-ac7a-c47c71a4152a |  | note | Inspection/ Test Type - Survey
label | c2ea432d-3983-5b33-ba6f-c256d849ecbb |  | note | ○ Survey
label | a1ef733a-5624-51f2-81d6-6dfeb5c2b91a |  | note | ○ Survey
label | 20231aec-8ceb-5a00-b34f-91a35a5293cc |  | note | ○ Survey
label | e44d5262-946c-5387-ad6b-d68f692578ef |  | note | ○ T166, T173
label | d18789ba-3d38-5eee-bb2e-70bccdae8c12 |  | note | ○ T120/T121
label | c7c8bff9-627a-56f0-b8a7-e837754aa08a |  | note | ○ Visual
label | fdf816ee-a434-5662-ae11-882e3c70a1cb |  | note | ○ T198
label | 6b9d4996-6d13-5875-a7df-2562f0a116aa |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, HPR, Comp & MC test report, proof roll report, survey thickness & level conformance report
label | e2623ccb-542c-508e-adb3-8ce858a1eb1b |  | note | Verified by - PM / PE
date | 619a69ad-0f69-54a9-841f-038fde2add50 |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 11 - Submission – Closed ITP w/ material & test reports, survey records
label | 1fa0e94d-debd-5fd5-a05f-909dd78a58bb |  | note | Inspection Requirement - Submit closed ITP to Council.
label | aa603460-d778-55dc-b0f5-bc321d9458ee |  | note | Acceptance Criteria - Complete submission to Council
label | 6c8eab43-cfe0-5b2b-ad3a-a4bf44bb17f0 |  | note | Frequency - At completion
label | 571f3f8b-bfd8-5dd9-94d4-ea10d685535a |  | note | Inspection/ Test Type - Submission
label | 1fe312ec-7978-5eac-a037-569c26df10f3 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - This closed ITP & associated records
label | d26b3701-2f18-5354-acde-f44cc4003339 |  | note | Verified by - PM / PE
date | 24a93d62-4ad2-5dff-b9cc-b3dc557ca4de |  | date | Verification Signature - Date:
checkpoint-group |  |  | section | The lot verification records are complete and attached with all non-conformances and RFI’s closed out.
checkpoint-status |  |  | checkpoint | Lot Complete / Records available:
text | ab4029dc-8de1-532f-91dd-1c881e2569cd |  | textbox | Name:
text | f554b39d-0144-5402-8f2e-d5fe0cef4824 |  | textbox | Title:
date | 33066db0-cde7-55a4-8d98-2dce73feb3cd |  | date | Date:
holdpoint |  |  | signoff | Signed:
checkpoint-status |  |  | checkpoint | Lot Approved for Closure:
text | af2f79d8-0acb-534a-bd96-305770b5134a |  | textbox | Name:
text | 1422e4f7-2b24-564c-b177-b4b245cb8a68 |  | textbox | Title:
date | d94026d2-c6c6-5d3d-bfa3-a79a0bbeb160 |  | date | Date:
holdpoint |  |  | signoff | Signed: