## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP R44 (ed6) - Earthworks QA |  |  |  |  | Yes | ITP R44 (ed6) - Earthworks QA | 0d4889ed-ba25-48e2-b73b-18d36cf36b4a
checkpoint-group |  |  | section | Earthworks QA
checkpoint-status |  |  | checkpoint | 1 - Implement & monitor ERSED controls
label | 7e32794f-d3e6-5792-8d8a-65b981d45ea8 |  | note | Spec / Doc Ref. - R44.1.8, G38.3.1, G38.2.2.2
label | cd4e8c4e-f938-559f-ac00-5374ee468159 |  | note | Inspection Requirement - Submission of an ESCP(s), Submit written advice that the ESCP controls have been implemented or the date they will be implemented.
label | ba5b6107-9ccf-547e-974e-456f32c9ba08 |  | note | Acceptance Criteria - ESCP requirements listed in G38 Cl2.2.2.
label | 9d39707a-a7b6-58fc-b22d-c613905c323b |  | note | Frequency - ≥10 work days prior earthworks, ≥5 work days prior earthworks, each section
label | dd97ba97-2c10-583a-8e19-8a869f8c4cbb |  | note | H / W - H, W
label | 5f15267d-b81f-549e-b738-ee73b316a406 |  | note | Inspection/ Test Type - Submission, Submission & inspection
label | 777989b7-4169-5ffa-aad2-e4eb35b427dc |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, ESCPs, WPR
label | d827efad-4e49-58fd-8efb-ba210e58841c |  | note | Verified by - Project Mgr (PM) / Project Eng’r (PE)
date | 774fcc17-8b3b-5057-a7f7-4c994c0142f7 |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2 - Existing utility locating & NDD potholing
label | d1c76032-6138-5b79-98f7-3cd40c892711 |  | note | Spec / Doc Ref. - R44.1.5.1 (n)
label | 8d249294-1b6f-5da8-a845-d90caf49f816 |  | note | Inspection Requirement - Check service locating & marking, and NDD potholing of existing utilities is completed
label | dac78447-1b4d-53a0-8f86-95b758ff4d78 |  | note | Acceptance Criteria - Controls to protect utilities during earthworks in place
label | 4d63c513-47db-553d-9dce-673a68a9899c |  | note | Frequency - Prior earthworks, each section
label | 9cd60a36-0fef-5a6b-8ffd-b67e873f9da2 |  | note | Inspection/ Test Type - Visual
label | 68ed99bf-ca82-59c0-bdd3-18616dd41112 |  | note | Verified by - PM / PE / Supervisor (S)
date | 1080154f-ffb6-5be3-905c-9a8dc0c8ee54 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 3 - Setout earthworks extents
label | 50e68ac3-dbf4-54a4-9f3e-c6703a98e455 |  | note | Spec / Doc Ref. - R44.1.6.2
label | 1008f8ab-1143-51c0-9c36-d61d50a5a5b1 |  | note | Inspection Requirement - Setout by marking on the ground the earthworks limits
label | cbfe62f2-5655-5832-8b3b-2cf9770feffd |  | note | Frequency - Prior earthworks, each section
label | b5b7750d-d5e9-5805-9ea7-71c22065bd17 |  | note | Inspection/ Test Type - Survey
label | d9392548-dda1-53cb-80f1-a8c1e51faf25 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo of marking in place
label | 15a76ed9-032d-5322-9dca-9260b1410d4c |  | note | Verified by - PM / PE / S / Surveyor
date | b6aebf0b-472f-5f24-83f4-28161ac1475e |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 4 - Removal of topsoil
label | fecb5c4e-607e-583e-94fd-db5104555783 |  | note | Spec / Doc Ref. - R44.2.5.1
label | 411f8b84-5c50-5843-981f-b269bdac22cb |  | note | Inspection Requirement - Check topsoil removed & stockpiled correctly
label | fc44c3cc-00b7-5309-86e0-055d71815a27 |  | note | Acceptance Criteria - Strip full depth of topsoil in earthworks areas. Stockpile for use in revegetation.
label | b34ed4bf-a249-5d7d-92b9-ff1baaacc951 |  | note | Frequency - each section
label | 6008c8fe-1d8f-59db-b021-25223d63046e |  | note | Inspection/ Test Type - Visual
label | baf20a52-6d58-541c-b341-8948b023fedb |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - Photo
label | f953faf8-0e43-5b5f-9363-40f7a28192ff |  | note | Verified by - PM / PE / S
date | 52db033a-118f-5711-b1d9-9385f940dc94 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 5 - Test pits to verify CBR10 day & PI of subgrade & insitu SMZ
label | 040b72e8-0328-5d2c-864f-f1fda001ce73 |  | note | Spec / Doc Ref. - C-0604.00 R1 Table 6 RNB-241, R44/A2.2, R44/L.1
label | d50b5f8a-b8a3-577b-81be-09cf38d1cd31 |  | note | Inspection Requirement - Check CBR & PI samples completed from test pits
label | edc4af9b-ff0c-55e7-95f0-5d5fec5d500d |  | note | Acceptance Criteria - CBR: Subgrade ≥3%, Insitu SMZlower ≥ 15%,
label | 7de5ba4b-9047-5192-8050-ed3ec9c51cd4 |  | note | ○ Insitu SMZupper ≥ 30%
label | 639bd5d7-4cc2-5ed4-ba94-4612c39b1c57 |  | note | ○ PI≤25% (no insitu SMZ)
label | f49e6781-e8bf-54b6-a131-d03094620353 |  | note | ○ PI≤15% (insitu SMZ)
label | 1f826d12-6016-5086-88c1-66c9233ff287 |  | note | ○ SMZ: Max particle dim: 53mm, >50% passing 19mm sieve, >30% passing 2.36mm sieve
label | 44f2e777-df37-59bb-bf69-907d365a4683 |  | note | Frequency - 1 / 1000m2
label | 3274085b-f1f7-5628-b2c7-090ea927f23b |  | note | ○ 1 / 1000m2
label | fca28ef5-5e86-5ead-86b6-1fae5f3c9982 |  | note | ○ 1 / 1000m2
label | 050262ae-bcf3-552c-87d5-75a4d172977f |  | note | ○ 1 / 1000m2
label | 56a68af0-b5b7-5200-a0d3-1d2e12bc808b |  | note | ○ 1 / 1000m2
label | 7701d5e8-8a56-5fd2-8436-6c82d08a9be6 |  | note | ○ Each Lot
label | 1ccb04f7-395f-5de6-a1da-7a92934d6029 |  | note | ○ Each Lot
label | 9f6eaa01-59ba-58c8-82d6-52462740d51d |  | note | ○ Each Lot
label | 26758e8b-45d5-59b3-b1f3-f8ccb1b92547 |  | note | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
label | 55b66211-a001-51b4-91fb-b81e2dd86a06 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - CBR, PI, max particle, T106 test reports
label | 9bc7907e-e7d1-5f46-8e6c-568367a32bac |  | note | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
label | 4cf42276-6e4a-5bbf-88fd-5ec1deea8604 |  | note | Verified by - PM / PE
date | 1b2db79a-645b-5eef-8916-1fb941f1a369 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 6 - Excavate to design levels and profiles
label | c248b095-4188-52c7-89bc-84877aacb651 |  | note | Spec / Doc Ref. - R44.3.2, R44/A2.2 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222 Tbl R44.8
label | a32b30fc-b6a5-52fe-a702-be19216edd05 |  | note | Inspection Requirement - Check excavated to Design Floor Level (DFL). Check CBR & PI tests completed. Present floor for inspection.
label | a2c9aafb-df12-5e68-ac8b-e51eb57d98d5 |  | note | Acceptance Criteria - Where at Top of Formation (DSL-330mm), there is ≥300mm existing Sydney Rd pavement, SMZ comprises existing pavement left in-situ, therefore DFL is DSL-330mm.
label | 42d766b7-c307-504f-9f8f-2094bb035465 |  | note | ○ Where no existing pavement, DFL is DSL-630mm (& a 300mm SMZ to be provided).
label | c83dcd5a-2787-538c-96cf-57c3d271664f |  | note | ○ Level tolerance: +10/-40mm (no insitu SMZ), or +0/-20mm (insitu SMZ)
label | 52561b34-cdfd-5f0b-95fe-4d542d04d039 |  | note | Frequency - each section
label | 19c2d573-e1bd-5ad6-9789-6e96d45ae0f8 |  | note | H / W - H
label | 1bc4226c-25ea-5c46-ad23-24afdd8aa3f9 |  | note | Inspection/ Test Type - Survey, Test & Inspection
label | 4329924e-eac5-5ee4-8fec-cd426bbfa9e9 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, DFL Level conformance report
label | b3b4ba52-c627-5e5a-af00-5ecfe02df83a |  | note | Verified by - PM / PE
date | 7479b377-4a07-5966-8f65-e81b27af968f |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 7 - Proof roll DFL
label | 44797871-bad2-591a-a700-8e1f2b604c1d |  | note | Spec / Doc Ref. - R44.7.5, R44/L.1
label | c1b78ce6-6cef-59d5-8d63-a65c01ee7a78 |  | note | Inspection Requirement - Notify Council of proof roll (WP)
label | 2bcf2f1c-486c-5e98-b37e-545a84cc6705 |  | note | Acceptance Criteria - Not exhibit visible deformation, rutting, yielding or show signs of distress / instability
label | 011cdb1b-a583-51c1-9997-1d74bf6859bb |  | note | Frequency - ≤1 work day of proof roll
label | 78bec119-cf78-5d4d-b9b8-08931bb602c2 |  | note | H / W - W
label | f44d06f7-e266-5cfc-8081-290c14539877 |  | note | Inspection/ Test Type - T198
label | 016589ad-91b2-5083-bd5b-aef54fc27af1 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, proof roll (T198) report
label | 79acdef4-7007-5d84-bb0c-e1db329ae8ba |  | note | Verified by - PM / PE
date | 1c118335-f815-52f7-903c-f6cc30e43260 |  | date | Verification Signature - Date:
checkpoint-status |  |  | checkpoint | 8 - Unsuitable Material (if any)
label | 7c96e5c1-d30b-5dec-b1ea-021382b31acc |  | note | Spec / Doc Ref. - R44.2.6, R44.5.2.1, R44.7.5, Tbl R44.7 R44/A5, R44/L.1
label | f885b761-5bef-591b-bc7d-64ebc19d14fa |  | note | Inspection Requirement - Where unsuitable material indicated by:
label | cc3b644d-3c3f-5bbf-8be5-6fa35c705faa |  | note | – inspection in item 5,
label | 847febee-7d6f-5e43-ac54-a06323cdc448 |  | note | – CBR / PI testing, or
label | 16b68dfa-d9f8-5f17-9302-9a51855ed654 |  | note | – proof roll, excavate unsuitable to the extent directed by the Principal.
label | f8494e5f-e54c-50dc-bdaf-4fe376426239 |  | note | ○ Notify when unsuitable removed to the extent directed (Hold Point).
label | 330cc4bd-ffc0-5cf7-aa7e-68a54bc12a61 |  | note | ○ Replace w/ compacted Earth Fill or (if directed) Foundation treatments
label | d3c36707-76bb-5b37-b768-7f1964e55906 |  | note | Acceptance Criteria - Min Rel Comp: 98%, Moisture: 60-90% of OMC
label | 0fc465dc-3d7b-59e6-8daf-12f789361071 |  | note | Frequency - each section of unsuitable material
label | a6357b40-86f4-5b3c-a802-bbe59eb59392 |  | note | H / W - H
label | 70ca88a6-96c4-5b3e-94f6-d01c12d821f7 |  | note | Inspection/ Test Type - Inspection, Refer R44/L.1, Refer R44/L.1
label | 30fa86ed-472f-5a26-98ab-941257303b6a |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, compaction & MC (if replaced by compactible material) report, Survey reports (before & after)
label | ab5b9980-2934-5a5c-918b-8abf0ba8169f |  | note | Verified by - PM / PE
date | 8017b09d-646a-5b11-9f71-ee7b13208467 |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9 - Site won SMZ material (for placement where no insitu SMZ)
label | 19ac260f-ba91-57a7-a3eb-f5e1e9bcb579 |  | note | Spec / Doc Ref. - R44.2.8.5.1, R44.6.1.2, R44/A2.2, R44/L.1 C-0604.00 R1 Table6 RNB-241,
label | 5d501bda-e17e-5ec8-a4ab-b6bdb0266133 |  | note | Inspection Requirement - Submit test reports verifying conformity of each site won SMZ material stockpile
label | fc895eda-7350-5c42-b3a2-545e0351686f |  | note | Acceptance Criteria - CBR10 day (per RNB-241)
label | e21fe58b-89e3-5be9-b6c9-a90be494a9e3 |  | note | – Upper layer: ≥30%
label | f55b8b70-704e-5a1b-819e-a5ec56f092a4 |  | note | – Lower layer: ≥15%
label | 6a4f3ddd-afd3-5573-864e-b13963330b1b |  | note | ○ Plasticity Index: ≤15%
label | bfb58ea7-5944-5c83-8536-d8b957d33c99 |  | note | ○ Max particle dim: 53mm
label | 0d314c1b-3ccc-5f36-89a0-64519fbd4209 |  | note | ○ >50% passing 19mm sieve, >30% passing 2.36mm sieve
label | 9442cbf8-a3f5-54f4-ac8d-e726b62b6896 |  | note | Frequency - Prior SMZ placement,
label | 89214678-936e-5ff1-a2bb-cda69281371a |  | note | ○ Each Lot
label | ea20bd1e-662c-58a4-8bc6-15e3a1d5d07b |  | note | ○ Each Lot
label | 617ef8e8-233d-5296-bea3-ad7c54241cc5 |  | note | ○ Each Lot
label | 5ebfe7ef-0405-530e-87cb-e2feba4a743d |  | note | ○ Each Lot
label | 840a481a-53bc-5431-b752-b8e557c99e02 |  | note | ○ Each Lot
label | a5360bf3-d9a7-52e0-b3cf-417664bc8bf2 |  | note | H / W - H
label | c59e0634-ff83-5ccd-b177-eb3b56155015 |  | note | Inspection/ Test Type - T117, T109, Inspection / T280(if req’ed), T106
label | a454f5ee-94f5-56fc-b8ff-5c3f4f690708 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - HPR, CBR, PI, PSD test reports
label | 2f51a9b6-bcb8-5da4-b775-b13f7112bda6 |  | note | ○ Note: Report P20009-1 (in D&N Geotechnical report C-0604.00) indicates the ex pvmnt material at BH01 has CBR10 day of 40% per T117)
label | 7c9801e4-7177-524b-9a95-923bc2c4f45c |  | note | Verified by - PM / PE
date | e0a163b3-80c0-540b-a4f4-2ded07531b4d |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10 - Placed site won SMZ Layer (for placement where no insitu SMZ)
label | 74917094-3781-5c5f-86f1-90ea65836b4a |  | note | Spec / Doc Ref. - R44.6.1.2 Tbl R44.7, R44.7.5, R44.7.7.1, R44/A5, R44/L.1 C-0604.00 R1 Table 6 RNB-241, Pavement Design Approval - STH18 00222
label | 93f3e613-308b-5496-8a82-5980e6e53f70 |  | note | Inspection Requirement - Notify Council of proof roll (WP). Submit verification of conformity of SMZ, with test reports & survey conf reports. Check level, compaction, appearance, proof roll results conform.
label | 075a8ff2-2c2c-593d-8157-06361b52dc0b |  | note | Acceptance Criteria - Level upper: +0/-20mm
label | dfaa2807-8dae-543c-98ef-650ab575fac8 |  | note | ○ Level lower: +10/-40mm
label | 872893b2-0bb5-57bb-9c0b-70cdc21f2135 |  | note | ○ Thickness upper: 150mm
label | 0dfc9653-9759-5b1f-beab-3a3f2a01aeae |  | note | ○ Thickness lower: 150mm
label | 029027ed-0f32-5280-ba6e-267f4163e7c3 |  | note | ○ Compaction: 102%
label | de83741f-60cf-5c97-8383-535d6bda6fef |  | note | ○ MC: 60-90% of OMC
label | 9bec27c2-38ab-5a19-8fb1-c323336b4610 |  | note | ○ Appearance: homogenous & free from segregated stone or excess fines.
label | 86c06c51-08d7-52d0-8b22-f665adc573f6 |  | note | ○ Proof roll: Not exhibit visible deformation, rutting, yielding or show distress/instability
label | 67d92102-29b9-5c94-befb-9caea366865a |  | note | Frequency - ≤1 work day of proof roll, Prior covering SMZ, Survey & geotech testing refer R44/L.1
label | 2d083156-ba57-50dd-a568-abcf4590f9ed |  | note | H / W - W, H
label | c8e1506f-9888-5eac-ac7a-c47c71a4152a |  | note | Inspection/ Test Type - Survey
label | c2ea432d-3983-5b33-ba6f-c256d849ecbb |  | note | ○ Survey
label | a1ef733a-5624-51f2-81d6-6dfeb5c2b91a |  | note | ○ Survey
label | 20231aec-8ceb-5a00-b34f-91a35a5293cc |  | note | ○ Survey
label | e44d5262-946c-5387-ad6b-d68f692578ef |  | note | ○ T166, T173
label | d18789ba-3d38-5eee-bb2e-70bccdae8c12 |  | note | ○ T120/T121
label | c7c8bff9-627a-56f0-b8a7-e837754aa08a |  | note | ○ Visual
label | fdf816ee-a434-5662-ae11-882e3c70a1cb |  | note | ○ T198
label | 6b9d4996-6d13-5875-a7df-2562f0a116aa |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - WPR, HPR, Comp & MC test report, proof roll report, survey thickness & level conformance report
label | e2623ccb-542c-508e-adb3-8ce858a1eb1b |  | note | Verified by - PM / PE
date | 619a69ad-0f69-54a9-841f-038fde2add50 |  | date | Verification Signature - Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 11 - Submission – Closed ITP w/ material & test reports, survey records
label | 1fa0e94d-debd-5fd5-a05f-909dd78a58bb |  | note | Inspection Requirement - Submit closed ITP to Council.
label | aa603460-d778-55dc-b0f5-bc321d9458ee |  | note | Acceptance Criteria - Complete submission to Council
label | 6c8eab43-cfe0-5b2b-ad3a-a4bf44bb17f0 |  | note | Frequency - At completion
label | 571f3f8b-bfd8-5dd9-94d4-ea10d685535a |  | note | Inspection/ Test Type - Submission
label | 1fe312ec-7978-5eac-a037-569c26df10f3 |  | note | Verification Ref. (Record, Test Report, HPR, NCR, etc) - This closed ITP & associated records
label | d26b3701-2f18-5354-acde-f44cc4003339 |  | note | Verified by - PM / PE
date | 24a93d62-4ad2-5dff-b9cc-b3dc557ca4de |  | date | Verification Signature - Date:
checkpoint-group |  |  | section | The lot verification records are complete and attached with all non-conformances and RFI’s closed out.
checkpoint-status |  |  | checkpoint | Lot Complete / Records available:
text | ab4029dc-8de1-532f-91dd-1c881e2569cd |  | textbox | Name:
text | f554b39d-0144-5402-8f2e-d5fe0cef4824 |  | textbox | Title:
date | 33066db0-cde7-55a4-8d98-2dce73feb3cd |  | date | Date:
holdpoint |  |  | signoff | Signed:
checkpoint-status |  |  | checkpoint | Lot Approved for Closure:
text | af2f79d8-0acb-534a-bd96-305770b5134a |  | textbox | Name:
text | 1422e4f7-2b24-564c-b177-b4b245cb8a68 |  | textbox | Title:
date | d94026d2-c6c6-5d3d-bfa3-a79a0bbeb160 |  | date | Date:
holdpoint |  |  | signoff | Signed:
checklist-sectioned |  |  | checklist | ITP - R11 - Stormwater Drainage | itp |  |  |  | Yes | ITP - R11 - Stormwater Drainage | 10922d77-9415-479d-b9e4-319a84f20b42
checkpoint-group |  |  | section | Manufacture Drainage Products
checkpoint-status |  |  | checkpoint | 1. Precast concrete drainage pipes
label | 0f718691-a94f-50c8-ae65-b81264163a78 |  | note | Reference documents - R11.2.1 R11.2.6
label | ff870432-3510-57b6-bbf5-95117e15f79d |  | note | Criteria/Test Method/Spec - The manufacturer must implement and maintain a Quality Management System in accordance with AS/NZS ISO 9001 as a means of ensuring that the manufactured precast concrete pipes conform to the requirements of the Specification.
label | 415ba4f8-d3c2-5e42-bfa2-5ada347a3d25 |  | note | ○ Precast reinforced concrete pipes must comply with AS 4058 and the requirements in R11.2.1 (I to 11)
label | 7fdcc121-1ebf-5877-8823-d0826660500e |  | note | Record for conformity/Inspected by - Submit Certificate of conformity at least 7-day prior works commencement to PV
label | 1c1155c5-c4fc-57b5-b742-023d262b9838 |  | note | Type of Record - HP
label | 699ddc56-b6e9-55d3-ba44-4ca2e30887bd |  | note | Responsible Position - Project Engineer (PE)/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2. Design of “Other Drainage Products
label | 183dd5e9-8512-5a16-a246-f84d0c79d656 |  | note | Reference documents - R11.2.4.1 R11.4.7
label | f3cdc9fa-9417-579e-83d9-d30a7ee0dc0a |  | note | Criteria/Test Method/Spec - The design must be in accordance with the Standards shown in Table R11.1 for the structure or component
label | bc8c54fc-b578-51b8-9600-ec278f9f4485 |  | note | ○ Design and development must also comply with TfNSW Q.
label | 2738f188-8571-5245-9cad-72451465ab70 |  | note | ○ Supply of precast concrete members subject to traffic and/or earth pressure loading, and water retaining structures with capacity greater than 25,000 litres.
label | 9990b108-85da-503a-afa2-2b39b6ad7d31 |  | note | ○ For all pits, such as junction box, gully pit, drop structure, etc, which are deeper than 600 mm, install an individual-rung ladder (step irons) in accordance with AS 1657 on one internal wall for the full depth of the structure.
label | e0673ae2-dd52-5f6b-9c5d-59a1ca75a069 |  | note | Record for conformity/Inspected by - At least 7 days prior to the date of delivery, submit the documents specified in Clause 2.4.1 to the PV.
label | 21286b31-59ea-5684-87b9-14ae6fdc0813 |  | note | Type of Record - HP
label | aef58f1f-81e9-5b5b-b605-3fa468e91875 |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3. Precast Concrete Pits, Access Covers and Grates, Ladders,
label | efc814eb-45c0-54e2-968f-4c13b1b365c5 |  | note | Reference documents - R11.2.4.3, R11.2.4.4, R11.2.4.5
label | a770ab92-cc16-5755-bdf9-53629c7a39ff |  | note | Criteria/Test Method/Spec - If precast units are proposed for use to construct drainage pits, the base units (or any other riser units to which incoming drainage pipes will be joined) must be manufactured specifically to suit the design configuration of the particular pit with pre-formed knockouts only in the walls that require them.
label | a8ac92f8-ec90-5cd8-9658-ddbbb9c7776a |  | note | ○ Metal access covers, grates and frames must comply with AS 3996.
label | 89c6e0cd-c111-5600-99b3-03aa2714a49e |  | note | ○ Ladders, including individual-rung (step-iron) ladders, must comply with AS 1657
label | 91c8fd73-450e-5cac-a71b-6169790234ff |  | note | Record for conformity/Inspected by - Submit Certificate of conformity at least 7-day prior works commencement to PV
label | 3fd89095-ad3b-5ba2-9a7a-cc42e4ef7677 |  | note | Type of Record -
label | 7d6328e0-b91c-539b-851e-4b909f743d7e |  | note | Responsible Position - PV/PE
checkpoint-status |  |  | checkpoint | 4. Marking on precast units
label | 7f215ec7-92ff-58f2-91ce-b5d633628c56 |  | note | Reference documents - R11.2.5
label | 9a1255c5-bfcc-56ab-84e3-2df6d0929570 |  | note | Criteria/Test Method/Spec - Markings on the inside of pipes must, as a minimum, include the following:
label | 1882dfde-2971-52ed-afc1-f0a9fc466657 |  | note | (a) manufacturer’s name or registered mark.
label | 9f15f322-54e0-5bb2-aaf7-54d7c0d7e1c8 |  | note | (b) date of manufacture.
label | 2a15a6d7-9913-56d7-95ac-e401ec052460 |  | note | (c) pipe load class.
label | 8571308c-8800-5701-8c40-35c8e70368c2 |  | note | and may be painted on if located on the obvert of the pipe.
label | 407ea0c6-c1a4-5887-ac59-a6866dc225ec |  | note | Markings for other precast units must include, in addition to items (a) and
label | 9aa5f3cb-2d8a-5769-a3f3-575ffd1064c7 |  | note | (b) above, the following:
label | e2fa8885-31fa-5fe4-addc-62f5694c10cc |  | note | (i) location of manufacture.
label | 242ceb38-e531-5251-946a-cdb6d078515f |  | note | (ii) maximum mass of unit in kilograms
label | 7d1f4ca7-c820-5d9f-a519-5a628a938e8b |  | note | (iii) any other identification necessary to directly relate the unit to tested samples, e.g. batch number;
label | 7abf1dd4-7660-5cbf-8e23-cbec7f2511c2 |  | note | (iv) inspection status
label | 24230de2-54c1-5480-83e9-da068411bfff |  | note | Record for conformity/Inspected by - Visual inspection
label | c686de58-ec1b-5f9c-92e1-fdb94f6ad3b9 |  | note | Type of Record - IP
label | 3a721400-6a62-507c-b5dd-1f02aaeeeac5 |  | note | Responsible Position - PE
checkpoint-group |  |  | section | Bedding and Support Fill Materials
checkpoint-status |  |  | checkpoint | 5. Type BH Select Fill
label | d44e4fd0-6739-5224-b5be-76137982e2a3 |  | note | Reference documents - R11.3.1.1
label | c5bdeec5-aced-5b6c-94c3-118e2aeb8fb2 |  | note | Criteria/Test Method/Spec - a particle size distribution, determined by Test Method TfNSW T201, within the limits set out in Table 6 in AS 3725 (or Table 5.1 in AS 1597.2); and
label | 38a7654d-96f1-5aab-9e05-878ec78dc661 |  | note | ○ a Plasticity Index, determined by Test Method TfNSW T109, of not more than 6.
label | b0ecfa02-3f5d-5132-8ef3-17a346d98b6a |  | note | Record for conformity/Inspected by - Test report (NATA)
label | 8fbce4d7-22e0-5e33-8de7-a6489310f462 |  | note | Type of Record - AP
label | 8c7e947f-4d7f-51eb-acf7-b818a76c3315 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 6. Type SO Select Fill
label | a4df8e2f-98b1-5946-a4cb-84a3cfed76d3 |  | note | Reference documents - R11.3.1.2
label | e4e1f251-1614-527d-81ca-3ce1d2168e76 |  | note | Criteria/Test Method/Spec - a maximum particle dimension of 53 mm; and
label | b75ca151-1414-5c00-b630-d84646fa8e98 |  | note | ○ a Plasticity Index, as determined by Test Method TfNSW T109, of between 2 and 12.
label | ad889d4a-ccb4-5112-92a2-8a2c3bb71fd0 |  | note | Record for conformity/Inspected by - Test report (NATA)
label | 0080e398-cfcb-5b26-acf4-e6134c5c3dc7 |  | note | Type of Record - AP
label | 4d453026-18c4-5624-8aad-17d443e57e9d |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 7. FILL MATERIAL FOR EMBANKMENTS IN OPEN DRAINS
label | bff6b2b4-a392-58ed-8c42-3760a3be1c24 |  | note | Reference documents - R11.3.3
label | 4a55d096-0489-5902-b530-977fd41aa3c5 |  | note | Criteria/Test Method/Spec - a particle size distribution, determined by Test Method TfNSW T107, such that between 20% and 60% inclusive by mass of material passes the 425- micron sieve; and
label | d097a4f2-1af9-5fb5-b4d0-699d60ae7365 |  | note | ○ a Plasticity Index, as determined by Test Method TfNSW T109, of between 15 and 30
label | e671f648-6ca9-52ac-bdaf-09f7e4cb4940 |  | note | Record for conformity/Inspected by - Test report (NATA)
label | 145ab494-2305-56b0-a7f0-94e809c33216 |  | note | Type of Record - AP
label | 4a73d5ff-5aca-5de9-b1c1-c08a703acd67 |  | note | Responsible Position - PE
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 8. Setting Out
label | 232f2499-e8f9-50a9-ad39-b51dba613694 |  | note | Reference documents - R11.4.1.1
label | a690da06-e653-5eae-b3e4-4889d97fd2a8 |  | note | Criteria/Test Method/Spec - Set out of drainage system.
label | 0fbabec0-2191-5de7-b428-a15ac4c62108 |  | note | Record for conformity/Inspected by - PV to Visually inspect set out for drainage system and propose changes if necessary
label | 7012352d-368c-59d2-8911-df7396c63f02 |  | note | Type of Record - HP
label | a8b4cb7e-44c2-51a2-bf84-4b98c462733b |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9. Excavation of Open Drains
label | b6d3eae2-ea97-5be6-a9a4-9a72ded01fbe |  | note | Reference documents - R11.4.2.1
label | c664e83b-afe6-56a8-b1f2-d94257a481bf |  | note | Criteria/Test Method/Spec - Construction of open drains with grade less than 0.5%.
label | 1f60f253-0a63-5944-ba47-0ac7852ce649 |  | note | Record for conformity/Inspected by - PV to consider the matter and direct contractor further before release HP
label | a3323027-5761-510e-b423-9076c42c233e |  | note | Type of Record - HP
label | dd7159c6-d424-5839-a00f-8930b1b83336 |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10. EXCAVATION FOR DRAINAGE STRUCTURES
label | 11e8ae06-1492-5e18-b0f8-e3cef4d4d087 |  | note | Reference documents - R11.4.3
label | 85b4947f-4d04-503d-8e9e-d27db39ff9a5 |  | note | Criteria/Test Method/Spec - Excavation for pipe installation and other drainage structures (Pits)
label | e32b110d-e387-5aa3-9931-5cd46196d03d |  | note | Record for conformity/Inspected by - Notify PV not later than 24 hours but not earlier than 5 working days,
label | 9087756d-f9a2-5256-8f81-38ba2a32b43e |  | note | Type of Record - WP
label | 848c8c61-34c7-5333-86e0-dfbb970355d4 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 11. Inadequate Foundation Material
label | 7d36f9cf-7eb3-541f-9380-b73ec00b523b |  | note | Reference documents - R11.4.3.3
label | f3a1e14d-579b-5aee-8967-acd09b454150 |  | note | Criteria/Test Method/Spec - Replacement of inadequate foundation material
label | 7339593b-8fda-58a4-8042-8a781aa30e6a |  | note | ○ Notification that inadequate foundation material has been excavated to the extent directed.
label | c967b1ba-a70b-5931-92c0-3647777edd5c |  | note | Record for conformity/Inspected by - Notify PV to inspect the excavation and may direct further excavation
label | a5e632d0-70b7-518d-a38d-fa7d84dc20cd |  | note | Type of Record - HP
label | e432d123-aefd-5e75-8df8-de2e85564be6 |  | note | Responsible Position - PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 12. Install Pipe Support Type and concrete pipes
label | 818ccb0b-1f3a-56fd-a7fb-e86ed36a82bc |  | note | Reference documents - R11.4.4.1, R11.4.4.2
label | f4d23ab3-0a1c-5e51-80fc-64d38c4e7012 |  | note | Criteria/Test Method/Spec - Provide pipe support of Type HS3 complying with AS 3725 and Standard Drawing R0240 - 01.
label | bd17d93d-512d-5452-939d-c204427401fe |  | note | ○ Handle, store and install the concrete pipes in accordance with the manufacturer’s recommended practice.
label | 9e09fd74-d1ed-5907-8814-4eca54c38314 |  | note | Record for conformity/Inspected by - Visual inspection
label | db562519-61b6-5f28-ac3e-cf8c51a097a4 |  | note | Type of Record - IP
label | 7faa78a3-38c4-5099-b3bb-68947b5c650b |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 13. Anchor Blocks, Sealing of Lifting Holes, Joints,
label | 32af1955-a419-5d82-a08c-28ccad0f8ed1 |  | note | Reference documents - R11.4.4.3, R11.4.4.4
label | 8ae81a7e-81f0-55ea-88cc-228d746e8369 |  | note | Criteria/Test Method/Spec - Provide anchor blocks at a maximum spacing of 3 m and at bends or junctions for all stormwater pipes laid on a grade exceeding 20% and where shown on the Drawings.
label | 99c21105-3229-5482-9b22-31b81dacff96 |  | note | ○ Seal all lifting holes in the pipes, and all flush or butt joints used to extend existing pipes, to prevent the ingress of materials.
label | 6564719b-5890-558f-841d-c37872277683 |  | note | Record for conformity/Inspected by - Visual inspection
label | b4103940-06f4-5c24-9b1f-703d3210cc8a |  | note | Type of Record - IP
label | 281170b9-ce18-56e6-b66a-80c57e196b08 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 14. Subsurface Drainage Pipe at Discharge End of Pipes
label | cb0c0dbb-8254-52d5-ae76-17ef49194c22 |  | note | Reference documents - R11.4.4.5
label | 83972e2f-0959-5e7c-8a4a-01c2658e84c2 |  | note | Criteria/Test Method/Spec - Install a subsurface drainage pipe, complying with Specification TfNSW 3552, at the discharge end of pipes at gully pits, junction boxes and headwalls unless the Drawings specifically direct the subsurface drainage be omitted.
label | 319dae4d-8494-56e2-a78a-3eadd4beae5b |  | note | ○ Unless shown otherwise on the Drawings, the subsurface drainage pipe must be a 3 m length of 100 mm diameter subsoil pipe laid beside, and 100 mm above the invert level of the drainage pipe discharging through the wall of the pit or headwall.
label | 08372cd2-2351-58aa-92be-21128e956e1e |  | note | Record for conformity/Inspected by - Visual inspection
label | 87fe736d-7704-58d8-912c-f8e9948103c8 |  | note | Type of Record - IP
label | 05cd7066-666b-50b0-b631-8927b11f1f00 |  | note | Responsible Position - PE
checkpoint-group |  |  | section | Construction of "OTHER DRAINAGE STRUCTURES" include gully pits, junction boxes, drop structures, inlet and outlet structures, and energy dissipators
checkpoint-status |  |  | checkpoint | 15. Foundations for “Other Drainage Structures
label | ecfe8000-cf0b-5e3f-94c2-1725cf09372b |  | note | Reference documents - R11.4.7.2
label | a66b0b5c-de99-5ee8-a6a7-cba1612cd957 |  | note | Criteria/Test Method/Spec - For precast pits, install the precast pit on top of a minimum 50 mm thick Class 2 DGB bedding material, complying with Specification TfNSW 3051, or controlled low strength flowable fill material complying with Appendix A in AS 3725, to support the precast pit uniformly
label | 70c38043-ef64-5a93-8f9e-630c4d8adb53 |  | note | Record for conformity/Inspected by - Notify PV for inspection
label | 9431c757-ac13-5952-9ffd-fa9fa8bfc1ae |  | note | Type of Record - WP
label | 725a6d4d-4e6d-512c-b2dc-2f5b4a629d71 |  | note | Responsible Position - PV/PE
checkpoint-status |  |  | checkpoint | 16. Precast Headwalls
label | 081f6b9c-62d0-5b36-828b-1554daf08ed6 |  | note | Reference documents - R11.4.7.3
label | 7de5e218-0e71-557c-8ffc-d1eaf4465b93 |  | note | Criteria/Test Method/Spec - For precast headwalls for pipes of 300 mm to 1200 mm diameter, provide a curtain wall at the outer edge of the apron in accordance with the TfNSW (RMS) Standard Drawings. Do not use precast headwalls for pipes greater than 1200 mm diameter unless approved otherwise by the Principal
label | 15f3c27f-1d23-53ac-99a0-fd7a9c60f841 |  | note | Record for conformity/Inspected by - Visual inspection
label | e57fc199-5ccb-59b9-8f04-f7fdcdad2d51 |  | note | Type of Record - IP
label | a9e456ca-4650-55f0-94da-5385ce162f0a |  | note | Responsible Position - PE
checkpoint-group |  |  | section | Backfilling, Compaction and Disposal of Surplus Excavated Material
checkpoint-status |  |  | checkpoint | 17. Backfilling
label | 69ec9c05-f208-57f6-aebb-2416a38d582d |  | note | Reference documents - R11.4.9.1
label | 58090d7b-8aa6-57d9-9419-a63a73dfdb06 |  | note | Criteria/Test Method/Spec - Backfill the Side and Overlay zones of box culverts with Type SO Select Fill. Refer to Figure 1.1 of AS 1597.2 for schematic details of these zones.
label | 47954c3a-49f3-5257-9e9e-7ca27160af06 |  | note | ○ For pipes and box culverts located within a rock fill embankment, provide a minimum thickness of 1000 mm of Type SO Select Fill within the Side and Overlay zones, separated from the surrounding rock fill by a geotextile complying with Specification TfNSW R63.
label | b938dca2-2d6d-54e4-a3d6-ce3cb5ec2b0b |  | note | ○ Unless otherwise specified or directed by the Principal, place fill material for the foundations, bedding, support and general backfill in layers not exceeding 150 mm compacted thickness. Compact the fill material to the requirements of Clause 4.9.2 of this Specification.
label | 998f8509-32a2-598b-ae66-817d82333eb3 |  | note | ○ Do not carry out backfilling against cast-in-place box culverts until the compressive strength of the concrete has reached at least 75% of the specified 28 day strength, and against other concrete drainage structures until at least 7 days has elapsed after placing the last concrete in the structure, unless authorised otherwise by the Principal.
label | 55be628b-fad4-56d3-bbdc-1c73dbe2b9b1 |  | note | ○ When backfilling against box culverts, the difference in level of the backfill on opposing sides of the culvert must not exceed 500 mm
label | d3bead62-ca26-570f-9085-429c7a7714e9 |  | note | Record for conformity/Inspected by - Visual inspection
label | f4539439-0bea-53dc-b1b1-c10ca776e27e |  | note | Type of Record - IP
label | f1984c59-fe51-5153-bc25-00e5c1b176f9 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 18. Compaction
label | f7260499-0dd7-5ccf-af30-b913688c4772 |  | note | Reference documents - R11.4.9.2
label | d3e2d931-9a6e-598e-9a78-e6a5e47505eb |  | note | Criteria/Test Method/Spec - Compact the foundations and fill material placed to achieve the minimum characteristic value of relative compaction for the particular type of material, as shown in Table R11.2.
label | 7f00c091-52e6-5e69-a2d3-4d2ad10569ea |  | note | ○ Select Fill in the Side and Overlay zones of box culverts (compaction 98%)
label | 149eea7e-db0b-5fef-9a4c-e21f489aa390 |  | note | ○ Backfill material within the Selected Material Zone of the adjoining earthworks (refer Specification TfNSW R44) (102%)
label | 04d601c9-936b-5558-b694-6383f7b75fe1 |  | note | ○ All other embankment (compaction is 95%)
label | 2a79c811-d47c-5389-a3c2-78e04196b00b |  | note | Record for conformity/Inspected by - NATA report
label | d352998e-fa3e-59cb-8cae-598e38bd4165 |  | note | Type of Record - AP
label | 1db7302f-0baa-5de1-a4d1-998f2d508847 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 19. Construction traffic
label | 188a3c8c-defd-51b4-8a2f-1ef66c45ce69 |  | note | Reference documents - R11.4.10
label | 41b77f39-03c8-5b72-9338-dd2e39d8f056 |  | note | Criteria/Test Method/Spec - Moving heavy construction plant or vehicles over pipe or box culvert structures.
label | 44cb89d0-0077-5b4d-81c9-c92478282bcb |  | note | ○ Where you propose to move heavy construction plant and vehicles over pipe or box culvert structures, design and provide protective measures for each crossing in accordance with Specification TfNSW G2.
label | ccdd1956-f92f-53d4-b52b-22a18f231911 |  | note | Record for conformity/Inspected by - Notify PV
label | a409fdfb-a99f-5a73-b85e-d3ef956ee4e1 |  | note | Type of Record - HP
label | ec3109fc-6131-5d9d-9776-0589239f1d2c |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 20. Survey check and tolerances
label | 7b9098c1-1e49-5c5b-bc1b-5a05b1eb1195 |  | note | Reference documents - R11.5.1
label | b6751694-5a3b-56bf-b9f1-a0bf221b0fd7 |  | note | Criteria/Test Method/Spec - Concrete pipes, box culverts, headwalls and wingwalls, energy dissipators, inlet and outlet structures (location within 200 mm of the plan position shown on the Drawings) (invert level within 20 mm of the design level at any point)
label | 5dce7af7-6a6a-5380-9cef-ede80658fac5 |  | note | ○ Gully pits and junction boxes (location Within 200 mm longitudinally and 20 mm laterally of the plan position, with reference to the control line for the road shown on the Drawings) (invert level Within 20 mm of the invert level shown on the Drawings)
label | a392a606-1699-5db4-8e74-c98006b2b99e |  | note | ○ Precast concrete box culvert units (On the internal faces of the walls and roof, no step between adjacent units must exceed 20 mm. Steps between 10 mm and 20 mm must be smoothed to a standard of durability equal to the rest of the culvert)
label | ed335560-f6a9-5c24-8e24-0b634793a917 |  | note | ○ Open drains (location as per R44) (level Within 50 mm of the design level at any point provided that there is a continuous downgrade in the direction of flow not less than 0.5% at any point) (Waterway area Not less than 95% of the design cross sectional area at any point)
label | ba6cf086-72c8-57f5-ba04-b0dde07ce441 |  | note | Record for conformity/Inspected by -
label | f3db9574-509a-5ded-affc-0f1cbd9bcd80 |  | note | Type of Record -
label | ecbeb23b-88a2-567c-993e-e75fb473a116 |  | note | Responsible Position -
checkpoint-status |  |  | checkpoint | 21. Inspection and CCTV test
label | e41741b0-d971-50cb-b868-29374ba11a67 |  | note | Reference documents - R11.5.2
label | 245c46e8-8b4b-5cca-a4c3-cb5c5088ba07 |  | note | Criteria/Test Method/Spec - Carry out closed-circuit television (CCTV) inspections of all pipe and box culverts with dimensions that restrict human access, to verify that the works have been constructed within the specified tolerances
label | b9e8c4cf-9b47-5376-8c69-e3b093e6b77c |  | note | ○ for visible signs of defects, at the following times:(a) on completion of the subject drainage structure and prior to commencement of the overlying pavement, and (b) no more than 14 days prior to Completion
label | 1ba01dd3-9890-5d4c-a70e-fb42bfb4dd6f |  | note | Record for conformity/Inspected by - Submit report results to PV
label | 586ac5c0-0966-5afb-a6fb-25b4c7ea5ef5 |  | note | Type of Record - AP
label | 8bc0f78d-5c10-54df-8978-b7978f963e25 |  | note | Responsible Position - PE
checklist-sectioned |  |  | checklist | ITP - R116 - Asphalt Laying | itp |  |  |  | Yes | ITP - R116 - Asphalt Laying | 170ccea0-d8e1-40aa-916c-88da92f58ecd
checkpoint-group |  |  | section | 1. Nominated mix design
checkpoint-status |  |  | checkpoint | 1. Constituent Materials
label | de51fe9c-8a83-50fa-b0a6-902149e41fb1 |  | note | Reference documents - R116.2.3.3 (a)
label | 293277c6-4065-59da-9e7a-c438d4892b7c |  | note | Criteria/Test Method/Spec - Aggregate of a different type or quality, even if from the same quarry face or from within the same quarry, will be regarded as from a different source
label | 53b5d12a-6414-5d88-aaa6-53aab3cb4562 |  | note | ○ Added filler: type, grade and source
label | ee57bc07-3b58-56a0-a265-f7ae1aad703b |  | note | ○ Binder: source, class or grade
label | 9e3ad91a-16f0-56e9-a139-9da50f983c1b |  | note | ○ RAP material to be comply with R116 Clause 2.2.1 (c)
label | 85faeeea-5ede-5a27-9f68-a84d18c0e9a4 |  | note | ○ granulated glass aggregate: source to be comply with R116 Clause 2.2.1 (d)
label | ba7b4a79-b522-53da-8b8f-7359027d5200 |  | note | ○ Additives: type, source, trade name and manufacturer’s recommendations.
label | 6a034838-655b-57e6-acb5-60e1a8273181 |  | note | ○ Bitumen emulsion tack coat: source, class of bitumen, any bitumen modification
label | febecc8b-b4dc-5243-a335-9966d0845b29 |  | note | Record for conformity/Inspected by - NATA report
label | 76d277e8-3020-591c-bc44-f4e469881567 |  | note | Type of Record - AP
label | fb3e5caa-2c68-5b22-b5ba-ed4f1c1d9f24 |  | note | Responsible Position - Project Engineer (PE)
checkpoint-status |  |  | checkpoint | 2. Mix Design
label | 183f4a1b-ddc7-5c8d-9981-6d6600fb46ea |  | note | Reference documents - R116.2.3.3 (b)
label | 930c4f2c-752f-5630-9faf-1b06749112c6 |  | note | Criteria/Test Method/Spec - For each nominated mix design:
label | af55913e-6e88-5816-96c7-cbd961b0f18b |  | note | ○ Proportion of each constituent by percentage of mass of total mix.
label | 5bf961fc-0cd4-5acd-b7d1-6452faf3966b |  | note | ○ Nominated values and allowable tolerances for each requirement specified in Clause 2.2, where applicable
label | fae6da42-5653-5fbe-b546-8baa796bc96c |  | note | ○ Combined aggregate density, including calculations showing how this is determined
label | 2292ec38-77f1-50e5-b7dd-a9728d2032e8 |  | note | ○ If using RAP material, the RAP Approval Level for which you are approved to use
label | 668b5535-951e-59db-95c6-d04b5339a6ae |  | note | ○ Type and identification number of the asphalt manufacturing plant and mix identification.
label | e617c297-3b3b-5f43-9290-d1d31f9d618a |  | note | ○ Temperature at which the asphalt is manufactured
label | a7404af5-67dc-5be7-8ac7-db7aa2fe971e |  | note | Record for conformity/Inspected by - Mix design submission sheet
label | 6efb14dd-17c0-5cc7-b82a-b947c140bfba |  | note | Type of Record - AP
label | 205675b3-9b55-5e3b-a148-a2d4a9c0bf52 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 3. Production Trial
label | d8316dc9-8165-543a-93ac-116d56f71a70 |  | note | Reference documents - R116.2.3.3 (c)
label | d8a75eb0-9ced-5d94-a9aa-4ca24f8e43f0 |  | note | Criteria/Test Method/Spec - Test results from the production trial in accordance with Clause 2.3.2
label | b7715f7c-5963-5e67-9628-e52502d2f218 |  | note | Record for conformity/Inspected by - Conformity sheet for the nominated mix
label | 857eb0d0-0c7f-56ea-ab9c-c984231b9fad |  | note | Type of Record - IP
label | 8e56ca64-a35f-544f-b601-b8276c63f38a |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 4. Warm Mix Asphalt Additives
label | 4bbbf4c3-e5e8-5c86-b9a5-14dfe834cca9 |  | note | Reference documents - R116.2.3.3 (d)
label | b5d9a46a-f4cd-5afc-b1a8-363d17758da6 |  | note | Criteria/Test Method/Spec - provide details of the additive(s) in your nominated mix design submission
label | b9aea306-40ec-5cfd-95fb-0d10bc679e2f |  | note | ○ any proposed amendments to the mix design procedure, operational processes and/or test methods as a result of the inclusion of a warm mix asphalt additive
label | 6ae42ed0-4c5c-5790-a509-6ff4a27f9760 |  | note | ○ classification of the warm mix asphalt additive
label | cf39d9a2-e697-5027-b0a8-178219c60647 |  | note | Record for conformity/Inspected by - Additive data sheet
label | 484ce030-3606-58b6-b53a-64770677af94 |  | note | Type of Record - AP
label | 22fc6bae-8a09-5ef3-92f9-a7a75a08fe17 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 5. Signed Statement
label | 688541c7-bd76-550f-8eb7-bb3ec9a76aa9 |  | note | Reference documents - R116.2.3.3 (d)
label | fa9aeeeb-9abe-5ae0-a284-d3c52e25bf05 |  | note | Criteria/Test Method/Spec - A signed statement certifying that each nominated mix, the associated production trial mix, and all constituents meet the requirements of Clauses 2.1 and 2.2. The statement must include NATA endorsed test results for all specified tests. Attach a copy of your completed verification checklist.
label | 90774765-2970-59d0-b884-1c48657d4a63 |  | note | Record for conformity/Inspected by - Statement for test results of trial mix
label | b585f047-f58f-59d8-8878-bc56ba1455b2 |  | note | Type of Record - AP
label | aa5c84fb-1f38-5da5-a30c-3b5448d8652d |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 6. Test Report Validity Periods
label | ac526d6a-f2f4-5590-9b3b-03b9f15acd6a |  | note | Reference documents - R116.2.3.4
label | 9520d19a-bdff-57cc-b06a-0a5397c995e8 |  | note | Criteria/Test Method/Spec - ○ All asphalt and binder tests relating to the nominated mix design submission must not be older than one month prior to the date of submission to the principal.
label | 5e02d5a3-f06b-5ce5-a1d7-ee9c3f507ea0 |  | note | ○ For high RAP content asphalt mixes, wheel tracking and beam fatigue tests relating to the submission must not be older than three months prior to the date of submission to the principal.
label | eba26b7e-9065-5bd3-b0a6-f90db723bae7 |  | note | ○ All other tests relating to the submission must not be older than 6 months prior to the date of submission to the principal.
label | 0ba198a6-00b0-513a-9f1e-ad5ff41f7511 |  | note | ○ All phases of any particular test must be performed at the same laboratory
label | b3d901c7-bdd4-577e-91bb-27525b0d5701 |  | note | Record for conformity/Inspected by - Report of conformity
label | 3d7c3dbd-6be9-523b-b0d5-3f8351b4a123 |  | note | Type of Record - AP
label | 36748d94-f35e-5e6f-92d9-244f3dae2596 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 7. Mix design approval
label | 4cc77e4e-3317-5daa-908a-cefb53f607b8 |  | note | Reference documents - R116.2.3.5
label | 6cfe38f9-0c19-568a-bd69-41637ed6fdd1 |  | note | Criteria/Test Method/Spec - Documents as detailed in R116 Clause 2.3.3 at least 7 working days before the nominated mix(es) is (are) proposed to be placed.
label | c483d9ea-60ef-54d3-9720-8afd0fd46a8f |  | note | Record for conformity/Inspected by - The PV will consider the submitted documents prior to authorizing the release of the Hold Point. This Hold Point release is valid for a maximum period of 24 months.
label | 4ce289d8-e275-558a-9ac9-0c25ad6b349b |  | note | Type of Record - HP
label | ab258e1a-2419-540f-845e-a22aab77b69b |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 2. Production of Asphalt
checkpoint-status |  |  | checkpoint | 8. Method of Production and tolerances
label | 9ce9d738-c5ba-569f-915f-84dbfb2f07d4 |  | note | Reference documents - R116.2.4.1 R116.2.4.2
label | 4fde51ba-1f71-5658-bfd4-d5b175f8e453 |  | note | Criteria/Test Method/Spec - (a) control the process and target the nominated mix design;
label | d6be67c7-2c2d-58ce-a8aa-2cc0573af0cc |  | note | (b) supply a homogeneous and consistent product at the nominated manufacturing temperature.
label | 158ab649-40c4-5120-9d4a-b8a2901d1faf |  | note | ○ You may vary the proportion of each constituent for the purpose of process control, provided that:
label | 6b8123c3-5f6a-5575-b764-b09471dfea0d |  | note | (i) the asphalt produced remains uniform and of consistent quality, and subject to the production tolerances specified in Clause 2.4.2;
label | d63992c1-63b6-51ea-aa80-079683673b80 |  | note | (ii) the proportion of RAP does not exceed the RAP Approval Level in Table R116.4 for which you have been approved.
label | 373dd905-3fdc-5906-82f9-2a8caff4298b |  | note | ○ The actual combined particle size distribution and actual binder content may vary from their nominated values within the limits shown in Table R116.8, provided that the actual values also remain within the limits of Tables R116.2 and R116.3 respectively.
label | fe351f7b-b248-5d5b-aaaf-4ed488e97b9a |  | note | Record for conformity/Inspected by - Visual inspection
label | e2e2a50f-2f49-5892-beca-bb6b56c67fb3 |  | note | Type of Record - IP
label | 78adb520-1da8-56db-ab5d-7893ed902d62 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 9. Asphalt Manufacturing Temperatures
label | e583ece3-8781-5969-91ec-9e279e5bc3cd |  | note | Reference documents - R116.2.4.5
label | 2b14a79b-9f8e-5e3a-b1d6-c957b835d6d7 |  | note | Criteria/Test Method/Spec - Control the temperatures of constituent materials in response to suitable thermometer elements placed in the flow of materials from the drier, and in the binder storage system or binder supply line. Thermometer must be readable and accurate to within ± 2°C.
label | 87a8c7bb-329e-5a7c-9614-93b7f9cc5d20 |  | note | Measure and record the temperature of the asphalt when:
label | ec1d8eda-ea4f-5465-a255-f880820b3911 |  | note | (a) asphalt leaves the pugmill or mixing drum; or
label | 1b764e06-26b1-5d7c-ad47-12098a85ddb5 |  | note | (b) asphalt is being discharged from the hot storage bin(s); or
label | 012dc875-4e0c-585c-b2ca-5e992241db53 |  | note | (c) in the delivery vehicles, prior to them leaving the plant.
label | 4e248678-8210-5db4-aec1-e1ccd54b3e09 |  | note | ○ The temperature of asphalt must not at any time in the process exceed 175°C.
label | 4e8870cd-f0db-5f98-86d9-fa081808236c |  | note | Record for conformity/Inspected by - PE to check temperature using suitable thermometer elements
label | 36efe568-b9fc-57e7-9dd2-fb48d5fc1158 |  | note | Type of Record - IP
label | 5d3fa444-060c-537e-87cd-7cbaf4dbef25 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 10. Sampling, Testing During Production and transport of asphalt
label | 59bbfb91-5709-5bb4-b7b9-95fce0986d4d |  | note | Reference documents - R116.2.4.7, R116.2.5
label | 16389858-59d6-5a5b-9283-4aecaad71e0a |  | note | Criteria/Test Method/Spec - Verify conformity with the Specification by sampling and testing, and maintain records of your process control during asphalt production.
label | cc2e45a6-5e36-5f3f-8409-cd5314f958de |  | note | ○ The frequency of sampling and testing must be in accordance with Annexure R116/L.
label | ce1c2abd-5755-5e5d-b928-63498d755fd5 |  | note | ○ Take asphalt samples in accordance with AS/NZS 2891.1.1
label | 09661bee-7f08-5649-9572-8e91a7675666 |  | note | ○ Transport of asphalt must be in accordance with AS 2150.
label | 1175ac3a-2f58-50b9-b747-c0bb72360b7a |  | note | Record for conformity/Inspected by - Visual inspection
label | 7d5fd972-78db-5c7a-b4a3-5a29930b53e7 |  | note | Type of Record - IP
label | 4a4a8ae0-6ec2-5709-8847-a58dc69e8caf |  | note | Responsible Position - PE
checkpoint-group |  |  | section | 3. Placing Asphalt
checkpoint-status |  |  | checkpoint | 11. Provision for Traffic
label | 009b63c1-ca6c-5482-ba8c-4b8ef49b5038 |  | note | Reference documents - R116.3.1.1
label | de0de490-94e2-5538-b9a1-23994d01dc42 |  | note | Criteria/Test Method/Spec - Provide for traffic in accordance with the requirements of Specification TfNSW G10 when carrying out asphalt paving.
label | 0547a7be-2c59-5385-8c01-ce13d2cbc529 |  | note | Record for conformity/Inspected by - Visual inspection
label | 12d52af3-9b25-5264-a913-59d26c503712 |  | note | Type of Record - IP
label | cc27e544-f142-5f98-b87f-ae585f36d230 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 12. Surface Preparation, Protection of Road and Services Fixtures
label | f8f72394-3bd6-543e-97cf-b0d2d667affc |  | note | Reference documents - R116.3.1.2, R116.3.1.3
label | 264ce2fb-e145-53b4-b089-7790bb5a99d6 |  | note | Criteria/Test Method/Spec - Prepare the surface to be paved in accordance with AS 2150, including removal of raised extruded thermoplastic road markings and raised pavement markers.
label | ab5d7c7b-47b3-5f13-9f67-5427fecf35e6 |  | note | ○ Implement measures to prevent asphalt or other material used on the work from entering or adhering to grates, hydrants or valve boxes, service covers, bridge joints and other road fixtures.
label | 9dee27cc-31e0-57ef-b116-c0e8a10c81d3 |  | note | ○ Immediately after the asphalt has been placed, clean and remove all waste asphalt adhering to road and services fixtures
label | 8d1dc2d2-b7bb-5e64-9cc9-867e9deb1ec6 |  | note | Record for conformity/Inspected by - Visual inspection
label | 5baaf07c-1339-5ff3-8a11-1b822261c949 |  | note | Type of Record - IP
label | 33e0f7ce-40e3-57b8-84e0-6498a2271811 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 13. Tackcoat for existing surface, application rate and reduced application
label | f1cc9e97-16fc-5b70-a939-a60b2cdfa52e |  | note | Reference documents - R116.3.2.1, R116.3.2.2, R116.3.2.3
label | 7a4b8144-1b4f-5ecd-aa95-b571b724ac5a |  | note | Criteria/Test Method/Spec - The existing surface must be clean, dry and free from loose material, prior to application of the tackcoat.
label | b0edf2d2-cff4-52a8-8612-2e222721ab2b |  | note | ○ Apply the tackcoat evenly at a rate of between 0.15 and 0.30 litres of residual bitumen per square metre, ensuring that it is effectively bonded to the surface. For joints and chases, double the application rate.
label | 25dbb202-8bf6-5c81-b280-3a2300733cb5 |  | note | ○ Nominate in writing to the principal your proposed tackcoat application rate prior to applying the tackcoat.
label | fc81abbd-bc76-56d6-8bac-6524c34aaec6 |  | note | ○ Determine the required volume by multiplying the nominated application rate of residual bitumen by the specified area of the surface to be tackcoated, including the faces of joints, kerbs and other structures.
label | 3abb8d78-c347-5cee-b539-ca0aa3e6ee3d |  | note | ○ You may propose in writing to the principal a reduced application rate for the tackcoat, for reasons arising from the existing underlying surface material.
label | acdba5b8-7fc0-5a56-b567-d167f72e2191 |  | note | ○ Support your proposal by examples of previous cases where this has been done,
label | fa714691-5133-51c0-8864-7021f4d41491 |  | note | Record for conformity/Inspected by - Visual inspection
label | 47e24bc2-0b6a-5d18-bc7a-10f520b08448 |  | note | Type of Record - IP
label | 0409b60e-8ebe-5547-ba72-2cfb2de08476 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 14. Temperature and Wind Velocity Measurement
label | a54d8929-b1c5-5ce5-9ee2-f72c028fa7f3 |  | note | Reference documents - R116.3.3.1
label | 48960ff6-fc5f-5959-b185-8b7b8226dfe9 |  | note | Criteria/Test Method/Spec - Measure and record the temperature of the surface to be paved, and wind velocity at the point of asphalt placing.
label | 7c18294f-16be-57b9-9ecb-168ed2395f0c |  | note | ○ Do not commence or continue placing asphalt containing binder complying with TfNSW 3253 if the temperature of the surface to be paved over, measured at existing surface level, is less than 8°C where the nominal size of asphalt is less than 20 mm, or less than 5°C where the nominal size of asphalt is 20 mm or greater, for a zero-wind speed.
label | 78dd8d38-ed57-5338-87d2-7fe10e68fc08 |  | note | ○ These minimum temperatures are increased by 5°C for asphalt containing binder complying with TfNSW 3252.
label | 3fb1ffe9-b270-5602-a888-9401542a09b6 |  | note | ○ These minimum temperatures are increased by a further 5°C for each 5 kph of wind speed above zero; however, the minimum temperatures must not exceed 30°C.
label | ca76747e-f181-55ab-8396-98604e53e519 |  | note | ○ Do not place tackcoat and/or asphalt when the surface is wet, and/or when wet weather appears imminent.
label | 1dff566c-3afa-524f-9c9e-1ad71fff9dd1 |  | note | Record for conformity/Inspected by - PE to check temperature with thermometer
label | 83edab11-2f57-5290-b848-2305c53bb321 |  | note | Type of Record - IP
label | 741c0eae-1b0e-5aa2-8530-fa18757d23bb |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 15. Method of placement, equipment, and materials transfer
label | c5b698b7-6b9a-572a-94bf-6dff12e0878e |  | note | Reference documents - R116.3.4.1 R116.3.4.2 R116.3.4.4
label | 9380be4c-5f6e-51e1-8dd7-c4eda2830ecc |  | note | Criteria/Test Method/Spec - Your method of placing and finishing the asphalt must:
label | 7c98eadf-3dfa-50b2-9bbf-2e432b622b11 |  | note | (a) produce a homogeneous product with a tightly bound surface;
label | ad720de3-c78c-5e59-a30d-08862a7eec2d |  | note | (b) achieve a uniform bond to the surface below;
label | 968355ff-6f04-5dbd-931e-41449d873818 |  | note | (c) achieve the finished pavement properties, specified in Clause 5, within the specified tolerances. Compact uniformly each layer of asphalt to achieve insitu air voids requirements before placing the next layer.
label | 953d2b47-5d52-5932-bb09-b3cbbd50f516 |  | note | (a) a receiving hopper compatible with delivery vehicles;
label | 004530a9-0751-5f55-95dd-4f67c56419fe |  | note | (b) conveying mechanisms capable of delivering asphalt to the paver at a minimum rate to suit the paving output;
label | 41c12c85-c356-5190-aa35-377032f45503 |  | note | (c) sufficient power output from the motor to operate with full load on grades up to 6% and travel in tandem with the paver, either directly in front or in an offset position;
label | 14669d93-7e5b-5c71-b685-336f7aed475b |  | note | (d) capacity to store and remix asphalt if the time between loading the delivery vehicles at the asphalt plant and unloading at the Site is equal to or greater than 1.5 hours, or when the temperature of the surface to be paved is below the minimum specified in Clause 3.3.
label | 2594a77f-6300-5107-bba2-e51bb1a22e5b |  | note | ○ If so specified in Annexure R116/A, place the asphalt by echelon paving using a minimum of two pavers operating continuously in tandem.
label | 63259320-0713-5628-a708-9ddde753d25c |  | note | ○ Place the asphalt using a self- propelled paver with the ability to be operated with automatic grade control and automatic joint matching facility.
label | c7ce9562-2787-5f21-b8b0-e4149d50912a |  | note | ○ Hand placement of asphalt is only permitted for minor corrections of the existing surface and in areas where placement with a paver is impractical.
label | e9ad9179-8616-5c45-8a27-95d09374d704 |  | note | The MTV must be a self- propelled machine with independent controls and demonstrated capability to minimise temperature variation and material segregation. It must be equipped with:
label | a48ec638-f379-5edb-82cf-5d766407d33b |  | note | (a) a receiving hopper compatible with delivery vehicles;
label | e079f6ee-9d40-5349-ac49-8b2866d8e714 |  | note | (b) conveying mechanisms capable of delivering asphalt to the paver at a minimum rate to suit the paving output;
label | ca216a8e-ffb9-528a-8a17-1eba7a501fe1 |  | note | (c) sufficient power output from the motor to operate with full load on grades up to 6% and travel in tandem with the paver, either directly in front or in an offset position;
label | afebc01b-9be2-57d0-bed8-905b93d5cd5d |  | note | (d) capacity to store and remix asphalt if the time between loading the delivery vehicles at the asphalt plant and unloading at the Site is equal to or greater than 1.5 hours, or when the temperature of the surface to be paved is below the minimum specified in Clause 3.3.
label | 00048382-c638-5aa5-acdf-2d977b12dffd |  | note | ○ If so specified in Annexure R116/A, place the asphalt by echelon paving using a minimum of two pavers operating continuously in tandem.
checkpoint-status |  |  | checkpoint | 16. Paving and compaction temperature
label | 059300ed-f979-5363-b734-314dd2df06fe |  | note | Reference documents - R116.3.5.1
label | 32bd0a80-7d18-5a65-9765-7a91577d5232 |  | note | Criteria/Test Method/Spec - Commencement of paving using the nominated mix(es), including trial section (refer Clause 3.8).
label | 3786c717-0c56-536c-a8aa-307d8765f881 |  | note | If not previously submitted, details of the following:
label | 7ba1093b-b5a1-56a5-8c27-e9e371bd8ec1 |  | note | (a) minimum temperature at which asphalt will be delivered to the paver;
label | f0aa0775-26c2-5f8a-829d-47ffdc1febd9 |  | note | (b) minimum temperature at which initial compaction of the asphalt can still commence;
label | 29a94ba8-c0d2-589f-b7fc-b924ad262300 |  | note | (c) method of temperature measurement
label | 3ab4b49f-9317-53a4-9317-735d3ef81ef1 |  | note | Record for conformity/Inspected by - The PV will consider the submitted documents prior to authorising the release of the Hold Point
label | 01a9f2bc-802d-5897-850f-ffa335cfd5ee |  | note | Type of Record - HP
label | 595767e1-46df-5bac-b0c4-2d0d378edab9 |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 17. Course and layer thickness
label | 81f88f66-ea45-5571-907a-e1f359de61cf |  | note | Reference documents - R116.3.6.1 R116.3.6.2
label | 53caf8b0-75a2-5e18-8df8-c55453952581 |  | note | Criteria/Test Method/Spec - The nominated thickness of a layer of asphalt must be between 3.0 to 5.0 times the nominal mix size.
label | 61d9c636-fd1c-5e26-9eef-8a86d80b40a1 |  | note | ○ The specified course thickness is detailed in Annexure R116/A, or shown on the Drawings
label | 1ade082a-cae1-5398-b772-dfe00a4ffd6f |  | note | Record for conformity/Inspected by - Survey to submit report to PE
label | 84459834-3fbf-5d1e-8583-4bd53a4f82bb |  | note | Type of Record - AP
label | f8157ddd-6164-521d-8326-8f15b6e93ec4 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 18. Nonconforming Layer Thicknesses
label | 675b1e2e-950f-5dbf-81b1-f4f8b80464e3 |  | note | Reference documents - R116.3.6.3
label | df42c59e-d7d4-545c-9ef5-a2581b9600c8 |  | note | Criteria/Test Method/Spec - Placing of asphalt in layer thicknesses that does not conform to specified layer thicknesses.
label | 970db05e-16b1-57dc-b15c-fd8af8eb55c4 |  | note | Details of the following:
label | 9c0f92a8-1ef7-5dc5-ba39-a5e87ec77ca3 |  | note | (a) nominated layer thicknesses which does not conform to specified thicknesses;
label | 78e9a873-4303-506a-884e-6c4a45fde968 |  | note | (b) work methods capable of producing a dense homogeneous layer at these thicknesses;
label | ce84cc01-cbc4-56bf-80e6-c397e7656597 |  | note | (c) areas affected, and evidence that these areas are the absolute minimum necessary.
label | 2d21c19e-6409-5ad7-b859-1ca3f245bd6f |  | note | Record for conformity/Inspected by - PV will consider the submitted documents prior to authorizing the release of the Hold Point
label | 8fba14c3-0183-5157-ba23-3aaa8efeb6e7 |  | note | Type of Record - HP
label | 6bf721b7-ad73-5fe2-9281-104daefe9883 |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 19. JOINTS, temporary ramp and tie ins to existing pavement
label | 2efa3ca3-ff2d-5582-aec4-a358034b35d0 |  | note | Reference documents - R116.3.7.1 R116.3.7.3 R116.3.7.4
label | 37750291-da75-581e-aca1-1d53e15c5222 |  | note | Criteria/Test Method/Spec - Longitudinal joints must be:
label | 051688bf-8cad-5fef-a6a5-b6a7266cbb6a |  | note | (a) offset by 150 mm from the joint in the underlying layers;
label | bb8168b5-fd02-5ea9-bacd-80c5221177bc |  | note | (b) located within 150 mm of the line of change in crossfall;
label | 91d43715-ee7e-5685-b287-798ca0bcd536 |  | note | (c) coincident with final traffic markings, unless otherwise approved by the Principal. Transverse joints must be:
label | ba14524a-05f8-5985-a0b3-ee870c87c69e |  | note | (i) located at a minimum of 25 m apart;
label | 0785f56f-015a-5c00-a038-9369a839fe89 |  | note | (ii) offset by a minimum of 1 m from the joint in the underlying layer;
label | 1221bc18-173a-51f1-be58-15f85c7ed87f |  | note | (iii) formed at the commencement of each paving run;
label | ab1607e9-7986-5fc1-b9da-82df4d569cdf |  | note | (iv) formed when a delay in paving causes asphalt temperature to fall below the initial compaction temperature nominated in Clause 3.5. Construct temporary ramps at joints for safe trafficking of the work either by placement of asphalt complying with this Specification, or by cold milling the existing or new asphalt layer to form the ramp, as appropriate for the application.
label | 1f9c8bc6-c277-54a5-80cc-1a87502fb365 |  | note | ○ Construct permanent tie-ins to existing pavement by placement of asphalt complying with this Specification
label | 3d96f45d-f48f-5b6b-9cbb-b51f65926f77 |  | note | Record for conformity/Inspected by - Visual inspection
label | 98b63fd8-3693-54cd-af0b-6a641d0b04b7 |  | note | Type of Record - IP
label | 25003c7b-9089-554f-9048-8c29febea72d |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 20. Trial section and commencement of paving at locations other than trials section
label | ae210821-9d2c-5505-9d6f-0a689fccae0e |  | note | Reference documents - R116.3.8.2 R116.3.8.3 R116.3.8.6
label | fe6e946f-881d-5606-8436-f422ab207c05 |  | note | Criteria/Test Method/Spec - Design the trial to implement all the procedures described in your PROJECT QUALITY PLAN and demonstrate conformity with the Specification in respect of:
label | d735465d-5f4b-5cb0-a9ea-b4f1b61aa37e |  | note | (a) homogeneity.
label | 7bdb7e9e-079d-5ae4-8198-aed368dd6ec1 |  | note | (b) insitu air voids.
label | 7a3ac7ee-3f33-560c-9100-2a2c7a995595 |  | note | (c) course thickness.
label | cb1de0bc-bb5b-5df7-860a-19b8a16ce024 |  | note | (d) course position.
label | 2788723a-9b32-5834-bcd8-e39222dbcec1 |  | note | (e) surface shape.
label | 611c9ab6-a889-5b10-baa6-8bb63fe9d331 |  | note | (f) joint quality.
label | 61c121c4-a9b4-54f0-a0ed-285d5767800f |  | note | (g) ride quality, where specified
label | b9fab280-e0b4-56f6-8a56-6b75440a1eda |  | note | ○ Verification checklist and all relevant test results from the trial section demonstrating conformity to the specified requirements, at least 3 working days prior
label | 9f44c092-e7a6-5252-a66e-04c8dd4890d4 |  | note | Record for conformity/Inspected by - Submit report to PV
label | 2bbe1dc5-b616-5fb7-a20c-ea607d81d630 |  | note | Type of Record - HP
label | 1822a9a9-11bc-5189-8f42-8dad68153334 |  | note | Responsible Position - PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | 5. Conformity
checkpoint-status |  |  | checkpoint | 21. HOMOGENEITY
label | 90c661ab-16d5-5700-9e9d-dad15066ebb2 |  | note | Reference documents - R116.5.1 R116.5.2
label | 9cc9933e-fd94-5538-bfd0-a71a59e9551c |  | note | Criteria/Test Method/Spec - During the first 24 months after the Actual Completion Date:
label | df1f6b57-2f36-5363-a6fa-1d8b625ea1b2 |  | note | (a) the placed asphalt must not ravel, rut, shove, strip or bleed; and
label | 1f84df24-d39c-5fb8-9017-eb0a9bb5c6d4 |  | note | (b) the wearing course for the first 12 months must comply with the surface shape requirements specified in Table R116.12.
label | 9f936c2b-5650-5c38-b173-420e29e7d6bc |  | note | ○ Placed asphalt must be homogeneous in appearance, and must not exhibit segregation, cracking, ravelling, bony or fatty material, or have been damaged during construction.
label | 7466893a-a8d6-5d58-a209-7892e31bb059 |  | note | Record for conformity/Inspected by - Visual inspection
label | da437482-57b7-5da7-8ab2-d02781d98d2d |  | note | Type of Record - IP
label | cc25f7b6-9e47-51d3-9bc4-c48c3c1174e9 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 22. Rectification and Replacement
label | 7a7fde29-93d3-5211-be65-5808e4fd7042 |  | note | Reference documents - R116.5.8.5
label | 41692231-3649-5d23-b255-77802d47e071 |  | note | Criteria/Test Method/Spec - Nonconformity Report and details of your proposal to rectify or replace the Lot.
label | c689c4ea-e0c6-58a0-bb26-e5d667f6a8e3 |  | note | Record for conformity/Inspected by - PV will consider the submitted documents prior to authorising the release of the Hold Point.
label | 429d1827-117f-5064-bb1f-534e7672c78f |  | note | Type of Record - HP
label | c4a96476-141f-5409-a53a-f829120d4245 |  | note | Responsible Position - PV/PE
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 23. In situ air voids and Course thickness tolerances
label | 8db0a174-fe5b-5692-8760-2a64f945fba0 |  | note | Reference documents - R116.5.3 R116.5.4
label | 0f2f5da8-ed94-57fd-a606-a902e904e246 |  | note | Criteria/Test Method/Spec - The characteristic values of insitu air voids for a Lot must be within the limits shown in Table R116.9.
label | ef245156-3d11-5f66-b219-89a5bbe45e28 |  | note | ○ For layer thickness between 30- 50mm, air voids must be between 3% to 8%.
label | 88b6c006-48f2-591b-97a7-0b8de5397391 |  | note | ○ For layer thickness more than 50mm, air voids must be between 3% to 7%.
label | 70063524-5382-5d83-9e30-624ceed011dd |  | note | Record for conformity/Inspected by - NATA report
label | cad00d1a-1378-5c76-a31f-e593a5949dd4 |  | note | Type of Record - HP
label | 2511ca46-e6e9-52b5-82b1-fea0e6ce2f66 |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 24. Progression to higher RAP level
label | 1c373d00-c7dd-542b-9407-f1441af2d432 |  | note | Reference documents - Annex. B2.3
label | caa37e77-bac0-5277-afed-bee9b8bbc06b |  | note | Criteria/Test Method/Spec - (a) Proposed corrective action to achieve conformity.
label | a00e5f04-61a0-5b12-93f7-893de96ee9c8 |  | note | (b) Test results for insitu air voids and all properties specified in Clause 2.2 of the nonconforming Lot
label | df27edce-28dc-5605-8d7a-85b3f7de68d4 |  | note | Record for conformity/Inspected by - PV will consider the submitted documents prior to authorising the release of the Hold Point, and will advise whether the nonconforming Lot can be accepted.
label | b68ee2b4-0f79-50b0-8df3-d925ea746c65 |  | note | Type of Record - HP
label | 13d95060-23e5-5315-a0db-439ab47158c2 |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 25. Finished Surface Levels Specified
label | cba95919-3fd3-5c69-96d7-148729316227 |  | note | Reference documents - R116.5.4.2 R116.5.5.1
label | 24bf3a78-0726-5a25-a5fc-818e9c790ade |  | note | Criteria/Test Method/Spec - The actual surface levels of the placed asphalt course as determined by survey must not deviate from the design levels by more than the tolerances shown in Table R116.11.
label | 188c09ed-ea27-5349-8910-bd98030bf274 |  | note | – – – – – – – – – – – – – – –
label | c76f2cb3-a756-5ee0-b3f0-c971597bc6c4 |  | note | Table R116.11 - Course Surface Level Tolerances
label | 308d4825-d07c-5a43-b4b8-74598f414cd1 |  | note | – – – – – – – – – – – – – – –
label | 2b3ceddf-bbe1-5265-bf8a-037d49fc34b0 |  | note | Course ¦¦ Tolerances (mm)
label | a0e1b130-56be-5d4b-9b11-7bf422c83bb3 |  | note | – – – – – – – – – – – – – – –
label | b60d1834-e767-5778-bf47-e06a924f3b64 |  | note | Wearing course ¦¦ -0 / +10
label | 145e2476-ab7f-579e-8b99-df29dccc2933 |  | note | Top Intermediate course ¦¦ -5 / +10
label | 717cdfb6-261a-539d-9451-2852b40ab4e1 |  | note | Other Intermediate Courses ¦¦ -10 / +10
label | 1fc0a8b0-f609-5207-a509-21d96f21281b |  | note | Corrective course ¦¦ -15 / +10
label | d36cdc36-3bc4-5555-a573-7a29e0751cf4 |  | note | – – – – – – – – – – – – – – –
label | b553a2d6-92f9-5be4-87c0-74c442ae7e14 |  | note | Record for conformity/Inspected by - Survey report
label | 5fb65e0e-242a-5634-8096-ac35cb81fe08 |  | note | Type of Record - IP
label | 34836daf-5f5c-547e-a062-0464f037dbbb |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 26. Surface shape
label | 0843208c-05ae-53e3-a20e-e1150a3d8f27 |  | note | Reference documents - R116.5.6
label | f06de17e-8289-56e8-963f-3cfda28a471d |  | note | Criteria/Test Method/Spec - The surface of the course including longitudinal and transverse joints must not pond water.
label | 7d3bae2e-256c-5139-b788-a69364097232 |  | note | ○ The surface shape of the course within and across traffic lanes must not deviate from the bottom of the straightedge (refer Clause 4.5) laid in any direction by more than the tolerances shown in Table R116.12
label | 8d4da2b3-12c4-56d7-9e59-f384695a93ef |  | note | – – – – – – – – – – – – – – –
label | 4af96908-a3f5-56ab-95ea-9fdc3c5b86cd |  | note | Table R116.12 - Maximum Deviation From Straightedge (mm)
label | 94082c2e-eef1-51b0-8c92-70b8431a0bed |  | note | – – – – – – – – – – – – – – –
label | 1120db14-0441-5245-bdd1-1481fd8615f5 |  | note | Course ¦¦ Through Carriageway < 70 kph Traffic Speed, Ramps and Roundabouts ¦¦ Through Carriageway ≥ 70 kph Traffic Speed
label | 74ee4313-8010-57fb-8c3e-b5369631ff23 |  | note | – – – – – – – – – – – – – – –
label | 24f55230-e0a1-519f-af2c-7062095ecf16 |  | note | – Immediately after placing: –
label | 1631e529-b25d-5f39-81e0-0a87fae5c223 |  | note | Corrective course ¦¦ 15 ¦¦ 10
label | 396e967b-5e42-5241-9764-89f0854754cb |  | note | Intermediate course ¦¦ 10 ¦¦ 5
label | 4f54270b-dae5-5c3c-8291-653015e7ce7b |  | note | Wearing course ¦¦ 5 ¦¦ 3
label | 93b17773-ed65-5813-acf3-68c5a956caa8 |  | note | – Prior to placing overlying layer: (1) –
label | 0b168a63-8cb5-5cef-a676-112fdd466563 |  | note | Corrective course ¦¦ 18 ¦¦ 13
label | c718efc2-1bfc-588c-ab38-c59eac324fec |  | note | Intermediate course ¦¦ 13 ¦¦ 8
label | 2c3a7d65-255c-5d66-bf56-a55cae6aff57 |  | note | – 12 months after placing: –
label | 3890a62c-f0bc-55a0-8fd6-4721e9c71dd8 |  | note | Wearing course ¦¦ 8 ¦¦ 6
label | 20157e05-4dd9-57cb-8c9d-a47526ff6d49 |  | note | – – – – – – – – – – – – – – –
label | 0ca7ea44-2279-5374-adf5-14e2ba92f82b |  | note | Notes:
label | 71715888-e6c1-5b0c-9314-7cfc1024e9c1 |  | note | (1) If longer than 1 month after placing.
label | 52890c03-ed31-546c-80c7-43bd564c4962 |  | note | – – – – – – – – – – – – – – –
label | 916158e1-4a02-54ab-b623-a6fa9685ad86 |  | note | Record for conformity/Inspected by - Survey report
label | 073236ed-576f-50b0-a61a-48ae5cfb1004 |  | note | Type of Record - IP
label | e861b778-1f0c-527c-a397-6aa2b7856a73 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 27. Ride quality
label | 0cbbff80-8636-5613-a53e-2337d1ee2b13 |  | note | Reference documents - R116.5.7
label | 8834e81e-3eb0-56f7-82be-45aed360a230 |  | note | Criteria/Test Method/Spec - The surface of the wearing course must have a smooth longitudinal profile.
label | c4d41452-12aa-5b8c-b928-c666ede5c943 |  | note | When:
label | 0116d866-bf40-5e09-8217-ccbbbeb300d2 |  | note | (a) construction of the underlying pavement forms part of the Contract; or
label | 8e129d65-5088-5787-9237-0b08628bed03 |  | note | (b) the course comprises more than one layer of asphalt, including any corrective course, placed over a pavement constructed by others; or
label | 0fae5b2d-12cb-5475-a5f9-1c595b3516d5 |  | note | (c) the aim of the asphalt paving work is to improve the ride quality; the ride quality of each Lot must not exceed an IRIS of 1.56 m/km. Where a single layer of asphalt is placed over pavement constructed by others, the ride quality of each Lot must not exceed the IRISa values determined as follows (refer Clause 4.6):
label | f2f0bd29-8b82-51c8-aa42-fad984489ae3 |  | note | ○ IRISa = 0.2 + (0.6 × IRISb), but not less than 1.56 m/km
label | 933635a1-67b0-5a68-be0a-b4994e09847f |  | note | where: IRISa is the IRIS after placing the asphalt layer (m/km) IRISb is the IRIS before placing the asphalt layer (m/km)
label | a9de579b-024c-5a48-8ad3-6c68ed3f7609 |  | note | Record for conformity/Inspected by - Equation check
label | f2fc29b7-72ea-5ec1-b3dc-d4ed86c1cbd9 |  | note | Type of Record - AP
label | fbe92bd8-ed65-5ebd-b345-cedc6c65b37b |  | note | Responsible Position - PE
checklist-sectioned |  |  | checklist | ITP - R106 - Sprayed Bituminous Surfacing | itp |  |  |  | Yes | ITP - R106 - Sprayed Bituminous Surfacing | 30deca7d-4a0a-470b-b6fd-41807c3d67dd
checkpoint-group |  |  | section | Sprayed Bituminous Surfacing
checkpoint-status |  |  | checkpoint | 1. Prepare Safe Work Method Statement.
label | 4e53d222-a5bc-5a94-a8b6-b4bef4d25fd1 |  | note | Criteria/Test Method/Spec - WHS Act 2011, WHS Regs 2017
label | 4d6dab2a-ac40-5225-817f-68fd02d11e01 |  | note | Inspection/Test Frequency - Prior to commencing
label | 3b2d6860-9fc6-5d64-8c5a-b1244fc0def6 |  | note | Inspection/ Test by - PV
label | dfd4fa1c-8e4f-5027-b51f-ab5d42d2385c |  | note | Responsible Position - Site Supervisor (SS)
label | ea6af761-f587-5fe5-82ad-a21e3f0fbecb |  | note | Type of Record - SWMS, HPR Form
text | 2a86eae6-ebbf-5ec3-8f3a-0e6bbb2d2223 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 2. Submit nominated design including supplier certificates for bituminous surfacing
label | f3b418b3-e8da-5af0-a81f-f92c92c2aa90 |  | note | Criteria/Test Method/Spec - Table R106.1 RMS Form 395A & 395K R106.3.3.3, Release of Hold Point
label | 666b0b45-760d-568c-ba15-0dafa5a270f6 |  | note | Inspection/Test Frequency - Annexure R106/L
label | 7b75d98f-708f-53c0-ab1d-603403a351c5 |  | note | Inspection/ Test by - PV
label | aedcb974-2028-5add-be71-4f7a240647d8 |  | note | Responsible Position - PE/PV
label | 5e184ec3-d8ee-573d-85ca-9004a54e8350 |  | note | Type of Record - Supplier comp certificate Form 395A Form 395K, HPR Form
text | ce840e11-12ec-51db-936e-dbdf3e6c719b |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 3. Submit Aggregate lot details and reviewed target application rates
label | d29f0c0f-02eb-5b1a-a830-fbe42fffb024 |  | note | Criteria/Test Method/Spec - RMS 395K form. R106.3.4, Release of Hold Point
label | 8df24203-c866-5ec9-ac6a-4b5a8d143ecb |  | note | Inspection/Test Frequency - Each lot
label | 1fea1960-b308-513e-a98d-a0575bfd9df5 |  | note | Inspection/ Test by - PV
label | aa17b98c-94cd-53f6-a036-4c622c3e0a35 |  | note | Responsible Position - PE/PV
label | a9801f81-7824-59b2-aba2-02d75a8db69c |  | note | Type of Record - ALD test rep Form 395K HPR Form
text | fc6e110e-f70e-5016-b29b-ebd1dd2ba4e0 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 4. Prepare pavement surface by sweeping and removal of any foreign material. Surface slightly damp for spraying of primer
label | eb88aca6-dbaa-594f-a9d4-b57101e52974 |  | note | Criteria/Test Method/Spec - Visual Inspection
label | 2678c17e-e643-554e-98ee-d93c4b6a7466 |  | note | Inspection/Test Frequency - Each lot
label | bc24fabe-b681-525a-a016-507d6bee74b9 |  | note | Inspection/ Test by - SS
label | 677f9903-e3b0-5654-9a06-08729dff6ba9 |  | note | Responsible Position - SS / PE
text | 9a540eac-7d01-50b8-835f-f1cf60d79c32 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 5. Commencement conditions
label | 6079b302-b1c8-54dc-a7e8-fb2c78b97eed |  | note | ○ Measure pavement temperature
label | 19cad1bd-4e0d-57ab-83ed-df17ae248486 |  | note | ○ Don’t commence if wet pavement or when rain appears imminent/ during strong winds/dust storms.
label | 209f5db4-2873-55fc-852c-948c7142dba3 |  | note | ○ Sprayer has current RMS Form 354
label | 7746db90-fca3-5657-b23f-f3703e4f595b |  | note | Criteria/Test Method/Spec - Pavement temp >10°C
label | b014c484-d6a2-51cb-90f7-8992ce7bdde1 |  | note | Inspection/Test Frequency - Each lot
label | 60d73e74-1263-52a5-b20b-ac13070ec6b3 |  | note | Inspection/ Test by - SS
label | f11c15f8-781a-50d8-abc8-aad85d4edfc9 |  | note | Responsible Position - SS / PE
label | 41d19b71-675d-52ba-9125-b3417078918c |  | note | Type of Record - Form 354
text | ff57f3ea-2404-55e4-990f-14664edeba6e |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 6. Apply Primer: Spray commences & ends on paper Actual application rate determined after each run using dipstick. Binder temp at application recorded Overlap btwn adj long’l runs 50mm.
label | d8a5c126-30da-5a69-9fd9-695660949aef |  | note | Criteria/Test Method/Spec - Note: Target hot application rate = 0.91/m2 Temperature: 10-30°C
label | 26f2c66b-ade9-5f40-83ce-9550298ee190 |  | note | Inspection/Test Frequency - Each lot
label | dd2d2c36-8f53-5e58-b2b7-0ca76c51ff71 |  | note | Inspection/ Test by - SS
label | 3d3564c5-02cf-547e-8a63-3e1294f179fd |  | note | Responsible Position - SS / PE
label | 4f126320-fe22-5e9b-9578-ab126c8152bf |  | note | Type of Record - Form 500A
text | 1a7e515a-e9b3-53b0-8e6b-24c451eb088c |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 7. Primer cured for at least 48hrs prior to application of seal
label | d70725aa-c8ef-5ee9-86ff-a62f2e9bd752 |  | note | Inspection/Test Frequency - Each lot
label | a37acaf6-8624-5280-b1d9-a9ff545bac4f |  | note | Inspection/ Test by - SS
label | a1c0d24d-3943-5cc5-b110-12edc7949efd |  | note | Responsible Position - SS/PE
text | 93e6ecf6-07de-5972-b3ed-28eaabd2e67e |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 8. Apply Seal Binder: Spray commences & ends on paper Cutter oil added per RMS form 382 Actual application rate determined after each run using dipstick. Binder temp at application recorded Overlap btwn adj long’l runs 50mm.
label | 25811cbe-a8b4-5e80-9546-3711251ff075 |  | note | Criteria/Test Method/Spec - Note:
label | 9ce91d8f-ef4a-5924-ab74-0067dcef8e81 |  | note | ○ Target 1st layer hot application rate = 1.55/m2
label | 541ae9a7-9416-5eed-9a3c-d5215eecb44b |  | note | ○ Target 1st layer hot application rate = 1.09/m2
label | acb79702-c675-5c6c-9793-5d97d12fc446 |  | note | ○ Temperature: 160-190°C
label | 83deac12-1a24-5399-9d47-44c6c50027c2 |  | note | Inspection/ Test by - Spray Seal Subcontractor
label | f571f06b-9dad-57ff-bc61-e1dd0dc87a4e |  | note | Responsible Position - SS / PE
label | 5679e044-2f1a-5967-a3e3-62a97ecb1d24 |  | note | Type of Record - Form 500C
text | 6d29d90e-0fca-5d3e-91c7-6b87cc6f13ef |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 9. Application of Aggregate: Aggregate precoated Actual aggregate spread rate measured at Roadworx (per RFI 76) Application complete <15min spray Rolling: 1 (per RFI 76) dual axle pneumatic multi-tyre rollers, >7t, tyre pressure >550KPa, ≥8 passes in <1hr
label | c4980398-c800-5069-8f47-d10ec89231a7 |  | note | Criteria/Test Method/Spec - Note: Target agg appl’n rate 1st layer = 98m2/m3
label | f9671e6b-af3e-5021-8d9a-b4c7907d003d |  | note | ○ Note: Target agg appl’n rate 2nd layer = 171m2/m3
label | 2bc06f92-a3db-57f3-82e3-a73974bc7a9b |  | note | Inspection/ Test by - Spray Seal Subcontractor
label | a2a4d737-2782-55c2-b91b-4e45909c88d8 |  | note | Responsible Position - SS / PE
label | 3a1c1f7a-ac09-577e-a8ba-9bdff9bff1c2 |  | note | Type of Record - Form 500C Aggregate Spread rate record
text | 24468221-dd35-511d-903e-1e4dc84dea69 |  | textbox | Initials:
checklist-sectioned |  |  | checklist | ITP - R15 - Kerb and Gutter | itp |  |  |  | Yes | ITP - R15 - Kerb and Gutter | af253987-5aa6-4227-908e-2f5a36451ec0
checkpoint-group |  |  | section | Kerb and Gutter
checkpoint-status |  |  | checkpoint | 1. REMOVAL OF EXISTING ELEMENTS
label | a458f330-0d82-5885-977e-7e417373cf60 |  | note | Reference documents - R15.3.2
label | 3de49c1c-a65c-51d9-af5c-a4a75a295cdb |  | note | Criteria/Test Method/Spec - Remove existing kerbs, channels, profile transitions, vehicular crossings and kerb ramps where specified or shown on the Drawings. Sawcut where necessary to provide a neat surface at the joint.
label | a243d1ce-5762-555f-b3b6-a4773315a9e5 |  | note | ○ When removing these elements, do not cause damage to adjacent elements which are to be left intact.
label | 244d02cb-ed05-52f5-ac04-a8ddfc415241 |  | note | ○ Re-use the removed elements in the Works, recycle or dispose of them off Site in accordance with Specification TfNSW G36.Backfill the void remaining after removal of existing elements with sound material to prevent the infiltration and ponding of water, unless specified otherwise.
label | 95b06787-7991-5263-985a-916ffc0e5b33 |  | note | ○ Compact the backfill material to at least the relative compaction of the existing material in the adjacent ground.
label | c2efea18-b7a3-5424-a298-5c0788e3c03d |  | note | Record for conformity/Inspected by - Visual check
label | f933f383-ac8b-5950-8250-b9e5b772c3c1 |  | note | Type of Record - IP
label | 141ce698-a82f-56fb-a583-deef046ae417 |  | note | Responsible Position - PE
text | 457e0e55-4882-53ba-aa1a-0b28c47a7efe |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 2. Support layer preparation and no-fine concrete
label | 03bb9e27-9451-57af-bcab-f61e7815422e |  | note | Reference documents - R15.3.3.1, R15.3.3.2
label | 3e7504d8-986b-5d41-941a-4989fa1d260a |  | note | Criteria/Test Method/Spec - Compact subgrade, unbound granular subbase and base layers supporting the K&C to the standard specified for these layers
label | e6e79042-1d4a-5bc0-8de2-78e8962a9810 |  | note | ○ Construct the no fines concrete pad (beneath the K&C), including installing a geotextile around the pad, where shown on the Drawings.
label | e920166e-e53d-5ba2-ac7e-b1ead9fb1bd9 |  | note | ○ Implement measures during placing to prevent segregation and formation of a slurry layer at the surface of the concrete.
label | cd4f13b4-39fd-5f60-bddf-868f013e4cf8 |  | note | Record for conformity/Inspected by - Visual check and survey report
label | 2eb6a7ce-4034-5cc5-bf80-1a385382a9c5 |  | note | Type of Record - IP
label | 734935cc-933a-5b1e-95f2-2c5184677462 |  | note | Responsible Position - PE
text | 59708ee6-b39a-5e10-bbf5-f72c59edf2fe |  | textbox | Initials:
date | ba54553a-32ad-5e0e-9d61-c58c57e7ba45 |  | date | Date:
holdpoint |  |  | signoff | Sign:
checkpoint-status |  |  | checkpoint | 3. Steel reinforcement
label | e1fed1be-1d01-5d8a-ba88-86a4e7a55b65 |  | note | Reference documents - R15.3.5
label | 3a64fd2e-95a8-5ff3-942c-a2f8ba01dfdf |  | note | Criteria/Test Method/Spec - Provide steel reinforcement such as tiebars, to the K&C as shown on the Drawings.
label | 1da53f68-8d5d-5082-96f8-90e347559522 |  | note | ○ Provide a minimum cover for the steel reinforcement in accordance with TfNSW R53, unless shown otherwise on the Drawings.
label | f438f618-f0b5-5b68-b24d-57c9ded30963 |  | note | ○ Provide kerbs which are placed on top of a concrete base with ties as shown on the Drawings
label | 5a2d4310-2426-5a72-9c4a-38fc3a553114 |  | note | Record for conformity/Inspected by - Visual check
label | 503874b2-6b0b-540a-bdb1-79bb1d0f1171 |  | note | Type of Record - IP
label | a8c78fbc-6a0e-5a22-a6c1-2607108d444b |  | note | Responsible Position - PE
text | f482eeff-170b-5848-ad9d-5c538dde5be3 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 4. Concrete placement
label | 0073fabb-7a4c-5b4b-ada4-c3d32f211bd5 |  | note | Reference documents - R15.3.7
label | 536a9eaa-b888-5bc3-b401-38135ebe13ed |  | note | Criteria/Test Method/Spec - Unless otherwise specified, supply, place, compact, finish and cure concrete K&C in conformity with TfNSW R53. The Hold Point in TfNSW R53 for placing of concrete applies.
label | f50b6d06-087d-5517-b3e9-3d15fb648fef |  | note | ○ You may construct K&C either by manual placing using fixed forms, or by machine- placing either by extrusion (dry mix and ramming) or slipforming (wet mix and vibration), unless otherwise specified.
label | 22a0e3db-9ced-5c47-bcd0-08a036e7ce39 |  | note | ○ Do not place by extrusion K&C which are located alongside, and tied to, a concrete base.
label | c83064b9-a21b-5b91-9373-22e94e46062b |  | note | ○ Where the K&C is to be constructed integrally with a concrete base, construct the K&C to the same requirements as that specified for the base.
label | 4d91236b-3805-5c50-ae26-f5ca1379f79e |  | note | Record for conformity/Inspected by - Visual check
label | 0078dabf-4d19-5613-8f6b-cf5385bcb88b |  | note | Type of Record - IP
label | 3240de6f-e35d-5d56-9e43-4b711448ba7d |  | note | Responsible Position - PE
text | 9b882573-dc04-514a-b256-223536fe4b05 |  | textbox | Initials:
checkpoint-group |  |  | section | Joints
checkpoint-status |  |  | checkpoint | 5. Inspection prior to placing concrete, mortar and grout and where washout of vehicles will occur
label | 3f549fcc-0911-581d-98c4-d1d4b1233767 |  | note | Reference documents - Visual inspection R53.3.3
label | c658c2c9-af27-5f4a-99cd-1c3d0c16688c |  | note | Criteria/Test Method/Spec - Each pour
label | 480f19d7-8a4d-521a-a5da-66f5833b64fb |  | note | Record for conformity/Inspected by - PV, Hold Point
label | 75fc9ebf-4de6-5b33-8e9a-8dc94947b4ea |  | note | Type of Record - PE/PV
label | a8db32d7-beaf-5283-b803-5ffaabba155c |  | note | Responsible Position - Customer Notification
text | 14c28e0c-ff53-5746-b748-ff453679cae9 |  | textbox | Initials:
date | ac481721-eec6-5ecc-9161-d72e9f5a2cc4 |  | date | Date:
holdpoint |  |  | signoff | Sign:
checkpoint-status |  |  | checkpoint | 6. Longitudinal Joint with Base
label | 7025112f-3861-5147-a16b-f57d1d8d00db |  | note | Reference documents - R15.3.8.2
label | 74dcb996-e90c-5ea6-8345-2bdcdf465cf8 |  | note | Criteria/Test Method/Spec - (a) With Flexible Pavement Base Where K&C is to be constructed alongside an existing flexible pavement, conform to the requirements shown on the Drawings or specified in Annexure R15/A1.
label | 943c342b-d1d9-5c75-92da-aae8ceae6960 |  | note | (b) With Rigid Pavement Base Where the K&C is not placed integrally with the concrete base, the longitudinal joint between K&C and the concrete base must be continuous over the full length without steps or offsets and must not deviate from a 3 m straightedge by more than 20 mm after due allowance for planned curvature.
label | 39bb601f-f2b1-5823-8eff-3626eb766ff0 |  | note | ○ The longitudinal joint must be tied, and corrugated only where shown as such on the Drawings
label | 094dcdd6-2f08-5eac-a087-f2f062768eba |  | note | Record for conformity/Inspected by - Visual check
label | bb9d520a-99ba-5c70-afff-f6d1f7e2f38e |  | note | Type of Record - IP
label | 42a04972-0b77-5025-a26f-c3f516c738ac |  | note | Responsible Position - PE
text | 0493cf34-268a-501f-8708-c9da97f28ec5 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 7. Sealing of Transverse Joints in Concrete Base
label | 73cbdf4b-98d7-5348-ac49-da263b0bedb6 |  | note | Reference documents - R15.3.8.3
label | 1995f311-35e2-5264-b493-b55d50d9d126 |  | note | Criteria/Test Method/Spec - Where the K&C is constructed after the concrete base (whether constructed on top of or alongside the base), complete the sealing of transverse joints in the base prior to placing the K&C, to prevent the ingress of mortar into joints.
label | a3697a4f-c951-542a-afaf-7b0dd5d9028d |  | note | ○ In the latter case, where the K&C is constructed alongside the base, when sealing the transverse joint in the base, extend the sealant all the way down the joint at the exposed vertical face of longitudinal joint (between the K&C and base), including the crack beneath the sawcut groove if the crack width exceeds 1 mm.
label | 666cd4f6-0eb9-5ca7-a945-fa05f93898f8 |  | note | Record for conformity/Inspected by - Visual check
label | 3eab39f5-fef4-54f2-9288-5836c4d9d195 |  | note | Type of Record - IP
label | a4a875f8-8198-5a73-9d69-58d92b113910 |  | note | Responsible Position - PE
text | 25ef6110-4140-5dc6-a9cb-0288a4a9babf |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 8. Location and Alignment of Transverse Joints in Kerb and Channel
label | 7cf3637a-207d-5688-8d8a-d5db6f8673c3 |  | note | Reference documents - R15.3.8.4
label | c91b442a-178a-5342-bbea-736d0e0be00a |  | note | Criteria/Test Method/Spec - (a) Kerb on Top of Concrete Base Where the kerb is placed on top of a concrete base, align each transverse joint in the K&C exactly (i.e. coincident) with the joint in the underlying base.
label | 26fa03cc-c647-50b1-bada-b5394b5d9213 |  | note | (b) Kerb and Channel Alongside Concrete Base
label | 5c1ae8b4-1961-5b52-bfff-e23643dc3a83 |  | note | ○ Where the K&C is placed alongside a concrete base, locate the transverse joint in the K&C such that it meets the transverse joint in the base at the common longitudinal joint.
label | f44faf5f-79ef-5a7d-997b-5251b57edeee |  | note | ○ Align the transverse joints in the K&C at right angles to the longitudinal alignment of the K&C, as shown on Standard Drawing DS2012/001191 Sheet No 14.
label | 95d52160-cb81-5812-a95f-3616b7abbea5 |  | note | Record for conformity/Inspected by - Visual check
label | bb6ee1a6-052b-5c9d-9733-33be9ec3720c |  | note | Type of Record - IP
label | 5903b3ca-a3a7-5831-8c6a-b01b99312b31 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 9. Expansion Joints
label | 965ab9ba-4cf6-50c5-aad6-4b62b58874d8 |  | note | Reference documents - R15.3.8.5
label | b00d5414-a607-5a98-865b-beeff392fec6 |  | note | Criteria/Test Method/Spec - Provide expansion joints in K&C at all locations where the K&C abuts structures such as drainage pits, retaining walls and bridges, and where shown on the Drawings or specified in Annexure R15/A2.
label | 19e8e4c7-f1fe-575a-80aa-126b15cc7cd3 |  | note | ○ Provide expansion joints at the locations where vehicular crossings and kerb ramps adjoin kerbs, channels and concrete paving to the full depth of vehicular crossings and kerb ramps, unless otherwise approved by the Principal.
label | 30b9b97b-a05a-5319-bb25-d741452c8f3b |  | note | ○ Install a preformed joint filler conforming to Clause 2.6 within the expansion joint.
label | 5eb9758c-d841-57c5-b236-0cf066e11150 |  | note | Record for conformity/Inspected by - Visual check
label | 33e5c305-d880-5181-a272-5938b8dc9c38 |  | note | Type of Record - IP
label | 5da25980-41af-5f45-a959-763280a6199f |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 10. SURFACE FINISH
label | e6a0ecb8-1c3b-5026-8206-16c8c855e56f |  | note | Reference documents - R15.3.9
label | 09b87053-84b3-5550-9395-ddbb55cfd77f |  | note | Criteria/Test Method/Spec - Unless shown otherwise on the Drawings, provide a steel float finish to channel inverts and faces of kerbs and a broomed finish to vehicular crossings and kerb ramps. Where directed by the Principal, provide a broomed finish to the tops of kerbs.
label | 4f82a9e1-7173-5d57-b1e1-3002485ca983 |  | note | ○ Direction of brooming must be transverse to the direction of travel on these elements.
label | 8ddda4e8-556a-576f-8972-4ba7613ebc0c |  | note | ○ Protect the concrete surface from rain during and after surface finishing and until final set.
label | 6e14e91f-03fd-5248-89e4-9361da7561ae |  | note | Record for conformity/Inspected by - Visual check
label | d3365751-3c2b-513c-a466-f68fc2e2068a |  | note | Type of Record - IP
label | 6ccc05e0-bc2a-5323-9d82-3929ded85856 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 11. Modular drainage product type drains
label | 2f5ed2ca-4a8e-570e-aaf9-e565a56c9866 |  | note | Reference documents - R15.3.10
label | f8c3cb08-275d-5cbd-9cd9-9472628276ed |  | note | Criteria/Test Method/Spec - Install MDP type drains at the locations shown on the Drawings.
label | d874e374-e045-5228-9034-e0a31c5893bb |  | note | ○ You may submit for approval by the Principal the use of MDP where they are not shown on the Drawings, but the Principal is not bound to accept your proposal.
label | ddafab8a-620f-5b77-b0fb-4a1b9d464beb |  | note | ○ Include in your proposal evidence that all other options for drainage have been considered, implications on flow if grated drains are not to be installed and verification that the proposed system is fit for purpose.
label | 68513c04-3788-5923-833d-eaf87d645be2 |  | note | Record for conformity/Inspected by - Visual check
label | a3f9e4e8-dbe4-56b9-b385-9b9cd46df1f7 |  | note | Type of Record - IP
label | e1fe0cce-ae19-511f-8694-160546ad9011 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 12. Survey check and tolerances
label | 2b9fa00d-12b1-541b-9797-1808d2d060a8 |  | note | Reference documents - R15.4.1
label | f166708a-35d1-5d9e-abca-cd56a6d66d7a |  | note | Criteria/Test Method/Spec - All finished surfaces must conform to the lines, levels, grades, thicknesses and cross sections shown on the Drawings within the specified tolerances.
label | 8b24512b-4a13-5ebc-b22c-85cef41e5e19 |  | note | ○ The tolerances stated in AS 2876 for irregularities in the bedding layer, level of the bedding layer, horizontal alignment, level, deviation from a 3 m straightedge, deviation on vertical curves, and profile dimensions also apply, except that the level of the constructed channel lip must not vary by more than
label | e7fdb54b-3e69-5ba5-b100-a9920886e726 |  | note | ○ 0 mm above or 10 mm below the adjoining pavement surface at any point.
label | 9b656ed8-5e94-508c-91de-8e60e4262bd9 |  | note | Record for conformity/Inspected by - Survey report
label | 2cf25d3b-e5cb-5d80-8ba6-42f9e16dd866 |  | note | Type of Record - AP
label | dc80c1ae-3ac0-51d1-a490-ff6020f621ba |  | note | Responsible Position - PE
checklist-sectioned |  |  | checklist | ITP - R54 - General Concrete Paving | itp |  |  |  | Yes | ITP - R54 - General Concrete Paving | b0d60f50-9dfa-4c85-9add-15c9d6a0c01a
checkpoint-group |  |  | section | General Concrete Paving
checkpoint-status |  |  | checkpoint | 1. Obtain conformance of granular foundation materials
label | 6dd934fc-1404-5ffa-836e-0b8967067639 |  | note | Reference documents - R54.2.1, Annexure R54/L
label | 848bba48-fd54-58a1-9d05-a0884005208f |  | note | Criteria/Test Method/Spec - Select Fill Type U must consist of a granular material with a particle size grading of 100% passing the 26.5 mm sieve and a Plasticity Index, determined by Test Method RMS T109, of between 2 and 12 (testing frequency 1 per 200m3 prior to placement)
label | 00050514-1a9a-50fc-8ae8-5aa94deefdfe |  | note | ○ Class 2 DGB must comply with Specification RMS 3051.
label | adaa351d-ed2e-5191-bfb6-a70525077109 |  | note | Record for conformity - Test report
label | 35814db5-fe3e-551b-bdb8-4efcd9111383 |  | note | Responsible Position - Project engineer
label | 91b292a0-8c98-5e34-b15c-a483d3bd6200 |  | note | Type of Record - TP
checkpoint-status |  |  | checkpoint | 2. Use approved concrete mix:
text | d24b4689-fe56-5d61-8147-d9295c9efd58 |  | textbox | Hold Point No.:
text | 4f71299b-9edd-546a-a190-9efd603c4772 |  | textbox | Mix ID:
text | ddd18a7a-9f2d-5c0a-9fb0-0f76a81c4ade |  | textbox | Strength:
label | ca228c2a-4d4d-5749-97e7-8d1cbeb92b5a |  | note | Reference documents - R54.2.1.2 & R53.1.4
label | c5884b11-6ba6-5c7b-80a8-adbfb1f2fa48 |  | note | Criteria/Test Method/Spec - Refer to R53-MIX-lots for Concrete mix approvals (Hold Points)
label | 200cb146-b522-560c-9eb6-10c07b47cd4c |  | note | Record for conformity - Mix report
label | 6f589d8e-c876-5817-9b9b-7e1f74e30429 |  | note | Responsible Position - PV/PE
label | 2ed27c9b-02b6-5e7b-937e-3e0bd965ed8a |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3. Obtain Certificate of conformity for reinforcement supply
label | 9dbb2614-b86b-5b63-a563-52123e56b6db |  | note | Reference documents - R54.2.2 & R53.4
label | 74d63dab-887c-55bd-9d9e-6825a5dcc4af |  | note | Criteria/Test Method/Spec - Must comply with either AS/NZS 4671, AS1311 or the supplier is accredited with ACRS
label | d77d3d31-26f1-5fd4-9857-6c6f9f3b884f |  | note | ○ Galvanizing must comply with AS/NZS 4680
label | 6cac8a72-686c-5726-8d28-093a056b1115 |  | note | ○ Welding must comply with AS 1554.3
label | 83831a64-2a8e-53b1-a302-9e2160c14d7d |  | note | Record for conformity - Compliance certificate
label | c26ac846-f70c-5823-bc82-5389825d306c |  | note | Responsible Position - PV/Project engineer
label | e230a02a-bc7a-5f26-829a-200a5b8a95d5 |  | note | Type of Record - AP
checkpoint-status |  |  | checkpoint | 4. Tactile Indicator Tiles
label | 2ab7a743-17a6-5f6b-98d2-d4d3ca8cb1bc |  | note | Reference documents - R54.2.3
label | 14d2f523-28be-512a-9a00-a8a127215505 |  | note | Criteria/Test Method/Spec - Tactile indicators must conform to AS/NZS 1428.4.1 and must be stain, slip, impact and UV resistant.
label | f821d44e-8cc8-599f-a207-70f9d8ac1788 |  | note | ○ Tactile indicators must have a colour contrast to surrounding surfaces and provide a luminance contrast to the surrounding surfaces of ≥ 0.3 (30%) as per Appendix E of AS/NZS 1428.4.1.
label | af770a42-8919-52d9-9adc-9820fdf7eef0 |  | note | ○ Adhesive (proprietary bedding material, as per AS 3958.1) for bedding tactile indicator tiles must be either cement-based adhesive or modified mortar (refer R54 Cl 6.1) which is not susceptible to deterioration from water infiltration and can withstand pedestrian and maintenance vehicle traffic loads.
label | a928bdc3-73ca-5ee1-ae9f-39eb76c7de90 |  | note | Record for conformity - Compliance Certificate
label | a900dc0a-c535-5e97-871e-97b158855ac6 |  | note | Responsible Position - Project engineer
label | 9e480b88-c21a-52db-9c98-d6a7c1cd828e |  | note | Type of Record - AP
checkpoint-status |  |  | checkpoint | 5. Obtain Certificate of Compliance for Preformed Joint Fillers
label | d4dfddc6-b12a-5b1e-b5c2-9fcbb6b3e9ce |  | note | Reference documents - R54.4.4.3
label | 03f5212e-8a3c-5c57-87a0-352a5542d701 |  | note | Criteria/Test Method/Spec - Provide a certificate of compliance verifying that proposed product complies with the requirements of 3204 and NATA endorsed test documents. Certification must relate only to the composition on which the tests were made and valid for ≤ three years. New certification will be required whenever changes in product composition are made.
label | aa2ca34d-7892-52df-a23b-766e4b283326 |  | note | Record for conformity - Compliance Certificate
label | ffe22456-e471-50a9-8244-fde7ec98d03d |  | note | Responsible Position - Project engineer
label | 91655141-7c07-54e7-b7a3-6dd76a7a0fda |  | note | Type of Record - AP
checkpoint-status |  |  | checkpoint | 6. Designate concrete truck washout area (s)
label | f14620fb-5cd8-5640-8cc2-212cd5480b09 |  | note | Reference documents - R53.5
label | 25138741-c4be-58a1-9c41-6aa043270daa |  | note | Criteria/Test Method/Spec - Impermeable plastic lined or approved equivalent bunded area
label | c0330677-bf9d-53ca-bbd4-02fdde0c2984 |  | note | Record for conformity - Verification Checklist
label | c9b8a42a-c33c-5a00-99b2-67f0a84c2f9f |  | note | Responsible Position - Project engineer
label | 4fa4f30e-cfe6-5329-8ba1-cf80b85d7380 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 7. Excavation and Filling
label | b0ba3818-c43f-5014-99a4-2d3927f8f1c1 |  | note | Reference documents - R54.3.1
label | 394baa9c-57ad-5370-9cc9-d7f066dc5cd9 |  | note | Criteria/Test Method/Spec - Verify area is excavated or filled to the levels shown on the design drawings or as directed by the Project Verifier in accordance with R44.
label | 141d48d3-a44a-5ae3-9fda-7fce9542bb33 |  | note | ○ Surplus excavated material to go into general earthworks activities in accordance with R44.
label | 06acad3a-e84f-52c5-92e8-1cfc81a57f49 |  | note | ○ Top up low areas to required levels using Select Fill Type U complying with R54 Cl.2.1.1.
label | adaa4785-ddfc-52cb-9f2f-57e88963e039 |  | note | ○ Where filling at the sides of Paving or behind kerbs unless shown otherwise on the Design drawings or directed by the Project Verifier, fill these areas with Select Fill Type U complying with R54 Cl. 2.1.1.
label | b3a45682-8aca-5092-8656-4c7006c78455 |  | note | Record for conformity - Verification Checklist
label | 7cfe19d1-e0f3-59b1-bf45-22aace560999 |  | note | Responsible Position - Project engineer
label | a4904fcd-0fd5-5f1b-923f-d2a8b6ad4c66 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 8. Unsuitable material
label | 4950f176-6211-5844-ad6f-b6a2e97d5693 |  | note | Reference documents - R54.3.2 & R44
label | 85174046-1b42-52a2-8e6f-4fef6c8b35c3 |  | note | Criteria/Test Method/Spec - If any area of the foundation contains material that is unsuitable to support the proposed pavement, remove and replace this unsuitable material or use some other foundation treatment in accordance with RMS R44.
label | 0b9ca9d9-af66-5dc3-b13d-3a8f7dcab4fd |  | note | ○ The Hold Point in RMS R44 regarding unsuitable material applies.
label | c183226b-a6a7-57ab-af69-60e16d751e11 |  | note | ○ Principal to be notified if found unsuitable materials
label | 2b94f566-3e05-5822-9f79-b2d17381e21c |  | note | Record for conformity - Verification Checklist
label | 2b529b39-0865-51a5-b3a3-9b97ce947ccf |  | note | Responsible Position - PV/Project engineer
label | 134489ce-ee8b-55a3-8546-3fad57b51bae |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9. Notify the GDR that unsuitable materials has been removed as directed
label | 955ddd93-7c80-5e59-b7a3-4392152fe68d |  | note | Reference documents - R54.3.2 & R44.2.4.1
label | 74805046-524a-52ff-81cc-b74bb5503a0d |  | note | Criteria/Test Method/Spec - Notification to the GDR is done after the removal of unsuitable material. The Geotechnical Design Representative will inspect the excavation and may require removal of further material as unsuitable material prior to authorising the release of the Hold Point.
label | 22ce0940-c269-548a-ae59-eca599af3c3a |  | note | Record for conformity - Hold point
label | ff8a1d51-4252-5398-9acd-dd013598f456 |  | note | Responsible Position - PV/ Project engineer
label | 41f026b5-b6c2-521a-8704-4c93686f1d76 |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10. Granular Subbase
label | 3e5ba998-bf03-5fde-929e-a50ec2285878 |  | note | Reference documents - R54.3.3
label | 13379d76-ece8-5b72-aee3-0d6f0fc982f6 |  | note | Criteria/Test Method/Spec - Unless shown otherwise on the Design drawings, construct a subbase layer comprising Class 2 DGB20 beneath the concrete paving as follows:
label | 2206df68-6397-59c4-b344-4d8bce83e0db |  | note | ○ Footpath: 75mm thick;
label | 04b2abd4-9327-51db-9103-ec221b0ec349 |  | note | ○ Bicycle path/shared path: 150 mm thick.
label | 48661e9b-6700-5a46-9ca2-0f35288dd442 |  | note | Record for conformity - Verification Checklist
label | 12a28861-f955-593a-a278-3368d28d8d0c |  | note | Responsible Position - Project engineer
label | 2c148eb8-6b10-59bf-8546-e86a7ee05a1a |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 11. Compaction
label | 9ef893df-e411-5fd1-9c71-2a21dd76c283 |  | note | Reference documents - R54.3.4
label | 52fd0990-5ca0-50f8-b209-f3d7bf26b18d |  | note | Criteria/Test Method/Spec - Compact the subbase, foundation, etc to achieve the minimum characteristic value of relative compaction specified Table R54.1 hence:
label | c306dad0-f0fd-5cff-a251-b95e1c6d91d1 |  | note | ○ Under footpath, bicycle path or shared path & median
label | e4c7f1f3-387f-515d-bb91-aab85dcb207e |  | note | – Subbase layer (where required) ≥100%
label | f9e07fdd-8957-59f1-9daa-92f8f2dda7d9 |  | note | – Top 150 mm of foundation ≥ 98%
label | bf83e928-cd48-5534-a083-24dded00ace7 |  | note | – Filling below a depth of 150 mm from top of foundation ≥ 95%
label | 82d95e69-60e2-586c-9386-3d2d87a2f58c |  | note | ○ Fill outside of footpath, bicycle path/shared path and fill at edge of paving and behind kerbs ≥ 95%
label | 1df621ba-f578-5ac2-a192-c35dba6f291a |  | note | ○ Driveways to comply with the relevant Council’s requirements, unless specified otherwise in the Deed documents.
label | 70a8bc87-7af9-5b06-b8e9-646555053098 |  | note | ○ Testing in accordance with Q6
label | cbd9f089-d46b-50b0-9c6e-e63c83850050 |  | note | Record for conformity - NATA Test Reports
label | e5983f58-8445-50e9-ae1f-cc38a7ebabc0 |  | note | Responsible Position - Project engineer
label | 7f043f27-6fac-5802-b934-632de70b071a |  | note | Type of Record - TP
checkpoint-status |  |  | checkpoint | 12. Check finished surface levels
label | 75eb26dd-863b-5d86-a6d2-f282b809dc51 |  | note | Reference documents - R54.3.5
label | f454f43e-25b5-537d-a2dd-143555a17c6e |  | note | Criteria/Test Method/Spec - Construct top of foundation to the design surface levels, with a tolerance of +5 mm and -10 mm.
label | 2d63c184-202b-5a6c-85cb-7f1e2e901aba |  | note | ○ The finish surface must not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 10 mm, except at grade changes.
label | 747ac126-cebb-5706-99b8-aee309566be9 |  | note | Record for conformity - Survey Report
label | 548386b9-16b5-5204-9c26-f136188814d1 |  | note | Responsible Position - Project engineer
label | 87016361-2300-5cf6-bc0e-424f2c825dc4 |  | note | Type of Record - Surveyor
checkpoint-status |  |  | checkpoint | 13. Install steel reinforcement
label | 8e82c29c-4231-5f81-bf2a-f1ef94e4bfe5 |  | note | Reference documents - R54.4.2, R53.4
label | b1bc98e8-8858-527a-8556-95ee1d32b10b |  | note | Criteria/Test Method/Spec - Provide steel reinforcement for concrete paving
label | 1ea4225d-7f60-5391-84e2-2fb0d2c9c302 |  | note | ○ Where the steel reinforcement is not shown on the Design drawings, provide the reinforcement as specified in Table R54.2. shown on the relevant Council’s STD dwgs, unless specified otherwise deed documents. Reinforcement lap splices as per design drawings or R53 Cl4.
label | 1db8a678-ddea-5f40-8124-3446620f66c6 |  | note | ○ Provide a minimum cover for the steel reinforcement in accordance with R53 Cl.4 hence 50 mm, unless shown otherwise in the Design drawings.
label | 89317374-478c-5fb0-bae0-b46bccda22f5 |  | note | ○ For slab of thickness 120 mm and greater, fix the steel mesh within the top half of the slab.
label | fcd9c08a-331e-5828-a912-2c370fca5660 |  | note | ○ For slabs of thickness less than 120 mm, fix the steel mesh at the mid- depth of the slab. In this case, the minimum cover specified in R53 does not apply.
label | 064fc785-64ce-5235-a027-2005bc14c544 |  | note | Record for conformity - Verification Checklist
label | 40067b7e-baf4-5f8d-b922-9b90940f36e2 |  | note | Responsible Position - PV/Project engineer
label | 3d5ceb72-e0d1-5638-bd38-36d190b8570d |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 14. Commence with pre pour planning activities
label | 38f34142-1ea6-5da2-ae28-3a0562ead74f |  | note | Reference documents - R54.4.3, R53.6.3 & Annexure R53/E
label | f59d3fa8-348f-5d32-adb2-5af31d30b5e8 |  | note | Criteria/Test Method/Spec - Verify formed areas free of water, dirt, construction debris and any other foreign matter removed.
label | 911848f5-0d36-5675-94b2-9f13c074a427 |  | note | ○ Rain not imminent, air temperature between 5- 38oC
label | 3cc95643-afd2-5279-8646-51a3a385aed3 |  | note | ○ Concrete tester arranged as required
label | 47c66bad-33fe-5aa9-aa2b-9a2855f68761 |  | note | ○ Bunded concrete washout area provided
label | 2c0574f1-30df-5c43-a3d3-3db8dcee4798 |  | note | Record for conformity - Verification Checklist
label | 5cbbd80e-670c-5b62-abe1-943bd6fda4d3 |  | note | Responsible Position - Project engineer
label | 7b57c822-4d74-5205-8903-e80423316952 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 15. Notification for Placement of Concrete
label | a8f96b8f-4c58-5e3b-9bdc-bb971c0ea448 |  | note | Reference documents - R54.4.3 & R53.6.1
label | 8bf652c4-4b57-5f96-bd0a-bfac4921a564 |  | note | Criteria/Test Method/Spec - As required for the preceding Witness Point hence:
label | 6db6b3c8-615b-5f81-98c1-472f56ba62fa |  | note | ○ Notify the Project Verifier Representative, not less than 24 hours and not more than 3 clear working days prior to the intended time of commencing to place concrete, mortar or grout, when fixing of the formwork and reinforcement in position (if applicable) will be completed and when concrete, mortar or grout will be placed.
label | 85df3ede-6423-5a4b-9d84-bf061d69641e |  | note | Record for conformity - Hold point
label | 4152fa72-56e9-5734-92bd-5ced0799041a |  | note | Responsible Position - PV/Project engineer
label | d274b769-d776-5c92-8cfa-7e14a0d3e4df |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 16. Carry out the concrete pour
label | df2af9eb-e1ad-5e4a-8518-3393c4bd22ae |  | note | Reference documents - R53.6.2, R53.6.4 & Annexure R53/EL
label | cfde8d1b-5307-52e4-9b12-5891994bdc4b |  | note | Criteria/Test Method/Spec - Concrete docket checked for correct mix
label | aca563bb-dcae-5e97-97a3-4a2acc4b743d |  | note | – Unreinforced paving
label | 3f7d45d7-e643-5ef1-bb91-4b63ccd3cfc4 |  | note | ○ N20, 80mm slump & 20mm aggregate
label | e42c5579-875a-571a-a7f9-9da1ad929e8e |  | note | – Reinforced paving N25, 80mm slump & 20mm aggregate
label | 21657ba4-15e8-5850-ad8f-cd3eb11dd199 |  | note | ○ Ensure concrete is placed & finished to:
label | 76cf47b2-98a5-5c26-9fad-8cdc5ad3c5a0 |  | note | (a) limit segregation or loss of materials;
label | 935896ce-cda0-54b9-a725-cfffd757ca93 |  | note | (b) limit premature stiffening;
label | cb9b382d-2e0d-56d9-a2c8-9f6f64e9d8a9 |  | note | (c) produce a dense homogeneous product which is monolithic between joints and edges;
label | 6ff3c298-6af8-5c3f-a21f-35f67554c7a9 |  | note | (d) expel entrapped air and closely surround all reinforcement and embedments; and
label | af111714-5981-5180-8e1f-9c34f098c9ba |  | note | (e) provide the specified thickness and surface finish.
label | 2dbe1226-da7c-542d-9cfc-557998ad1576 |  | note | ○ Ensure the finishing unformed concrete surface
label | 6a3d6509-f79d-5957-9332-d57d9854a8a3 |  | note | (a) has achieved the specified:
label | 748a027b-b012-519a-ac30-5fe54bf1197e |  | note | (i) dimensions and grade;
label | 9e237920-6fee-5657-83b8-87c9fa84a21c |  | note | (ii) cover from the surface to reinforcement
label | eea22b37-63c2-54a6-aa50-39b3fdf3d602 |  | note | (iii) texture of the surface; and
label | 6a8ca188-0605-5984-9ff5-293a1e0db01a |  | note | (b) has avoided plastic or drying shrinkage cracks.
label | 49de4acc-468a-5709-b96f-489dfb5b6aa3 |  | note | Record for conformity - NATA test report
label | f35898db-8c06-51b3-a871-173d5e0c6fe8 |  | note | Responsible Position - PV/ Project engineer
label | d094144c-8e79-5a70-b171-f860a67ca7dc |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 17. Transverse joints in pavement
label | 5de625ce-9906-5937-9756-06abcb62e7f5 |  | note | Reference documents - R54.4.4.1
label | f0adeb98-5baf-513a-8963-65af4b2b1035 |  | note | Criteria/Test Method/Spec - Transverse joints must be constructed at right angles ±6° to the longitudinal edge of the paving slab, otherwise the slab will be treated as odd shaped slabs.
label | 9a1ed840-4df1-52a7-a4ac-f0f25693114a |  | note | ○ Avoid where possible creating odd shaped and mismatched slabs.
label | 5c6dd6f2-8613-5837-af27-29b4402efb44 |  | note | Record for conformity - Verification Checklist
label | 4068cb20-5349-5d38-8dcf-dc214d0439c9 |  | note | Responsible Position - Project engineer
label | 323450f0-09f7-5acd-979a-acba58101356 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 18. Movement joints in pavement
label | e45376a4-abfc-5091-81fd-ab3bee88290f |  | note | Reference documents - R54.4.4.3
label | 3c2f2364-f396-5a81-8157-48f6a39472aa |  | note | Criteria/Test Method/Spec - a) Footpaths and Medians
label | 50db16d2-5ab6-5932-92ae-b3b818579277 |  | note | ○ Provide contraction joints 3 mm wide and 25 mm deep at every 1.5 m length of footpath or median paving.
label | 4f29f80b-94f2-59c1-9301-7af80cdd5c94 |  | note | ○ Provide expansion joints at intervals not exceeding 6 m and at the location of expansion joints in adjacent kerbs.
label | 2abf0711-2fa7-58f2-9e6a-66022d8991dd |  | note | ○ Provide isolation joints along median paving where the paving abuts against kerbs, gully pits, retaining walls and bridges.
label | 7445e4dc-2f4a-53d2-8efd-94a9cf130e29 |  | note | ○ Expansion and isolation joints must be 10 mm in width for the full depth of the paving and filled with a preformed joint filler in accordance with Specification 3204
label | 22a89d23-7c93-5685-b87c-e5eef7b59f66 |  | note | (b) Bicycle Paths/Shared Path
label | b986eb35-701e-594d-887b-491285d70694 |  | note | – Provide movement joints as shown on the Standard Drawings.
label | 535c302e-eb4f-5d16-a247-12dd4540da89 |  | note | (c) Driveways
label | 0a41db22-4a1c-55fe-9d29-f110e365b959 |  | note | – Provide movement joints in driveways at the locations shown on the relevant Council’s
label | 77062309-fec6-5309-9b66-afe19bfed127 |  | note | Record for conformity - Verification Checklist
label | 2f5ac407-be89-515f-b6ea-bad02787ca64 |  | note | Responsible Position - Project engineer
label | 1bb98af1-bc97-5bb7-a186-1b3684d1ded1 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 19. Finished paving surface
label | 428306ed-22f4-5435-934b-aa7ecfb87c70 |  | note | Reference documents - R54.5.1
label | 42f6cdd8-6ff9-5e95-87e7-12799674f2b2 |  | note | Criteria/Test Method/Spec - ○ Provide on the top surface of concrete paving (except patterned concrete paving) the surface finish specified in Table R54.3
label | e608276a-dce1-5586-bd99-dd595596c1de |  | note | ○ The finished paving surface must be uniform in colour and appearance.
label | 712f048e-f1e3-5f73-be6a-dd17b6486a45 |  | note | ○ All edges, except for those abutting other paving or structures, must be neatly rounded to a radius of 10 mm. Edges abutting other paving or structures must be neatly rounded to 5 mm radius.
label | f5956e1b-fc80-53a8-b7e3-15558d97e07c |  | note | Record for conformity - Verification Checklist
label | 00d35491-dcf5-5bfb-baba-9539667e0b9a |  | note | Responsible Position - Project engineer
label | d735da10-264e-58e0-8117-b97df4499d13 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 20. Curing & protection of concrete paving
label | 7d7aa3ed-0f38-548f-991d-a1186df4035c |  | note | Reference documents - R53.7.1, R53.7.2 & R53.7.3
label | 6c0d0ca1-c382-5751-9918-cb29ada3e98f |  | note | Criteria/Test Method/Spec - Only approved curing compound to be used (refer to R53.7.3 for details)
label | 3917f3f7-76a2-56aa-a0cc-f1260ec6d532 |  | note | ○ After initial set of concrete; surface is firm and free of bleed water, apply curing and cure for at least 7 days
label | 4f50b1f2-3e86-5583-bac1-df3fb75d7080 |  | note | ○ If Moist Curing, immediately after concrete has taken its initial set, spray all exposed surfaces with water and keep the concrete continually wet for at least seven (7) days. The water used must be free from ingredients harmful to concrete.
label | b26d5c32-2961-5852-ac6e-1825838ddc41 |  | note | ○ For Curing Compounds apply in accordance with manufacturer’s recommendations or at a spray rate min. 0.2L/m2 whichever is the greater
label | 9a28c0ac-e2ec-571c-84b6-4b526174609c |  | note | ○ Ensure all exposed surfaces receive a uniform cover of the curing compound.
label | ab141006-4ccc-501e-ae86-8a84786dd659 |  | note | Record for conformity - Verification Checklist
label | 11237612-80e0-5f2b-a07c-b3154a954c32 |  | note | Responsible Position - Project engineer
label | 23e3010a-8018-5dd2-befe-cf8421cbd649 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 21. Submission of patterned concrete paving details
label | 9e9307fb-54a9-5b46-bd54-de15cb08dff5 |  | note | Reference documents - R54.5.2.1
label | 120a2a29-f0c9-57db-a1ef-051989cd4d40 |  | note | Criteria/Test Method/Spec - Provide details of pattern, colour, class of finish and experience of personnel in producing patterns on concrete paving, at least 5 working days prior. The Project Verifier may require a sample panel to be prepared and submitted.
label | 0c2997aa-7e81-5d7d-b8be-64019ac3c927 |  | note | Record for conformity - Hold point
label | 4a52b679-ef64-5976-bf20-1e4af885bd97 |  | note | Responsible Position - PV/Project engineer
label | cc2216ee-4aeb-5618-8104-ac3151a686e8 |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 22. Procedure for constructing concrete paving
label | 1ff3e6a9-69a0-5bbc-8b56-4f178ecb1887 |  | note | Reference documents - R54.5.2.2
label | c8f1ba6d-6f34-5cea-b7b0-9383271628f8 |  | note | Criteria/Test Method/Spec - Apply the stencil only after the bleed water has evaporated from the concrete surface.
label | cf6d2a91-5f64-5a3a-923d-3fe1f4444c92 |  | note | ○ Apply each coat of colour hardener at a consistent rate achieve a total thickness of between 3 mm and 4 mm.
label | e4282ce3-f58a-5844-8fbb-cb9f9cb8ed73 |  | note | ○ On removal of the stencil, the surface must exhibit a well defined pattern with no edge ravelling.
label | 6f8a5349-5aac-5589-9808-215dda4b8144 |  | note | ○ Apply a suitable sealer to the finished surface within 24 hours of forming the pattern, followed by a second coat of sealer 3 days later
label | daad56aa-36b9-5bd0-b357-d629c6d19bb6 |  | note | Record for conformity - Verification Checklist
label | a5e56bbf-3441-5acf-b5cb-3965626e18df |  | note | Responsible Position - Project engineer
label | a82bfbc7-ee52-5a17-b2c6-0f6ad75f6a24 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 23. Finished surface levels
label | 81a3f1fa-dd5e-55ee-91aa-141b68ef9bae |  | note | Reference documents - R54.5.3
label | 85dfeff0-df51-5cd0-84f1-43eba7a635b7 |  | note | Criteria/Test Method/Spec - Verify finished surface of the concrete paving conforms to the design surface levels, with a tolerance of +10 mm, –5 mm.
label | a372999d-3349-5a7d-b063-cb996d23867b |  | note | ○ Verify the finish surface does not deviate from the bottom of a 3 m straight edge laid in any direction, by more than 5 mm, except at grade changes.
label | 603ec8c6-8802-5a96-b06d-c72c5dc5b5a4 |  | note | ○ Where the concrete paving abuts an adjacent structure, any vertical step across the joint must not exceed 5 mm unless shown otherwise on the Design drawings
label | f686b729-bfbb-51ce-8e08-99ee1f2dd086 |  | note | Record for conformity - Survey Report & Straight Edge Test Results Summary
label | 6d8e5d40-ea3a-5286-ac38-19b167d7becc |  | note | Responsible Position - Project engineer
label | e6a4d69c-ce33-5ecf-be1d-3927ad8c22a5 |  | note | Type of Record - Surveyor
checkpoint-status |  |  | checkpoint | 24. Submission of details of proposed tactile indicator tiles
label | 45238034-4801-52ac-8008-1dde04de07be |  | note | Reference documents - R54.6.1
label | 338836b6-bf1c-5a2d-950b-c5eda923ce34 |  | note | Criteria/Test Method/Spec - Provide details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method to the Project Verifier
label | 02870dc3-d9cb-5c73-97d7-20b0764998a7 |  | note | Record for conformity - Hold Point
label | 9facc13d-72c0-502f-a777-51c909cd8401 |  | note | Responsible Position - PV/Project engineer
label | f3d59b0a-6ad9-5a0d-9427-26bcf615952e |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 25. Installation of Tactile Indicators
label | db8b8c24-ad08-5ebd-af94-2037801e91f2 |  | note | Reference documents - R54.6 & AS 3958.1
label | 5691bd0f-46b5-569a-b8f1-2d8af4116d54 |  | note | Criteria/Test Method/Spec - Ensure tactile indicators will be installed at locations as shown on the Design drawings.
label | da51482e-2eed-5986-b51b-f2e87d1967f9 |  | note | ○ Performance level of Tactile indicators is “Commercial” and follow installation guidelines as detailed in AS 3958.1Cl.3.3.1.2 (Exterior floors – General applications, using cement-based adhesive or modified mortar)
label | 2abe8562-3831-5e7b-86ff-c9145980764e |  | note | ○ Prior to installing the tiles, allow the concrete to cure for 7 days (as per R53), or a duration recommended by the tile adhesive manufacturer to suit the adhesive used.
label | 0dd3a6ab-926b-5a94-95eb-6974fa355c2e |  | note | ○ Prior to placing tiles, clean concrete slab of dust using water jets, and any contamination using where necessary high pressure hydro-blasting, sand/grit blasting or mechanical scabbling.
label | 6a0b95fa-d059-58d7-b487-38f363bc7fb2 |  | note | ○ Install tiles so they are fully bedded, without any voids beneath them.
label | 7b674090-9057-5b98-b7d5-b56670feb681 |  | note | ○ Install tiles at the tile manufacturer’s recommended spacing. Pack the spaces between tiles with grout, and free of all voids and
label | a47194ca-a4f2-5fab-ae23-7e37e7fc46e0 |  | note | ○ Do not allow traffic over freshly grouted joints for at least 7 days, unless recommended otherwise by the manufacturer.
label | 86965978-9cb9-5959-978e-c8506881a09e |  | note | ○ Install movement joints at locations where:
label | c084c356-83ff-5fa4-8419-9c60bd4af1ce |  | note | – tiles abut restraining surfaces;
label | 040d468b-2504-5ce0-9aee-4b0cb78c64bb |  | note | – joints exist in the concrete below the tiles;
label | 05edc3c5-c3f6-5d93-af8b-a6eaf44a88f9 |  | note | – a change of plane exists in the tiled surface
label | 89452588-e328-57b5-9225-505ff3d19e29 |  | note | ○ Install the tactile indicator tiles such that the base surface is sitting flush with adjacent concrete surfaces.
label | 009cecea-0163-55db-a60a-23e5ef43667f |  | note | ○ The finished surface level of the tiled surface must comply with the requirements of R54 Cl. 5.3 pits. Remove any excess grout or grout film.
label | 59b691f8-06d2-5863-b303-d56c27a02bf6 |  | note | Record for conformity - Verification Checklist
label | 43e65178-fa22-5671-84dd-290e2837601b |  | note | Responsible Position - Project engineer
label | 6933a4b9-3c17-5d23-b285-7c4a6686cdc8 |  | note | Type of Record - IP
checkpoint-status |  |  | checkpoint | 24. Submission of details of proposed tactile indicator tiles
label | d80e6310-2818-5f4f-8a06-078a5c19e4b9 |  | note | Reference documents - R54.6.1
label | e5b66ece-f947-5d52-ae69-374e8d1e55af |  | note | Criteria/Test Method/Spec - Provide details of proposed tactile indicator tiles, associated materials (such as adhesive), and installation method to the Project Verifier
label | 3c5515a9-5479-5c7d-b61c-f2c69ea8c96f |  | note | Record for conformity - Hold Point
label | 473ba04c-f6d5-5225-a9fd-b030554e55df |  | note | Responsible Position - PV/Project engineer
label | 711bf47f-fb16-5821-b9c1-8e591c82dfbe |  | note | Type of Record - HP
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 25. Installation of Tactile Indicators
label | a64ed327-29bf-5cf2-b6f8-bbefc5d16f1a |  | note | Reference documents - R54.6 & AS 3958.1
label | 6471ab59-ea3f-526e-9bea-fe05f35dd395 |  | note | Criteria/Test Method/Spec - Ensure tactile indicators will be installed at locations as shown on the Design drawings.
label | 5209172b-1291-5426-8384-a9734c532b60 |  | note | ○ Performance level of Tactile indicators is “Commercial” and follow installation guidelines as detailed in AS 3958.1Cl.3.3.1.2 (Exterior floors – General applications, using cement-based adhesive or modified mortar)
label | 2952cf7d-6a3f-51cf-b286-f60046e541f7 |  | note | ○ Prior to installing the tiles, allow the concrete to cure for 7 days (as per R53), or a duration recommended by the tile adhesive manufacturer to suit the adhesive used.
label | 78398011-7017-516e-a862-880a94d6583e |  | note | ○ Prior to placing tiles, clean concrete slab of dust using water jets, and any contamination using where necessary high pressure hydro-blasting, sand/grit blasting or mechanical scabbling.
label | 5a1df0fd-1a7a-5a1c-b3a3-df762a990c7f |  | note | ○ Install tiles so they are fully bedded, without any voids beneath them.
label | 30f4e333-2c3c-53e6-9135-9ab268d9cf94 |  | note | ○ Install tiles at the tile manufacturer’s recommended spacing. Pack the spaces between tiles with grout, and free of all voids and
label | 3044790e-b762-5b42-8434-d9dfe554b885 |  | note | ○ Do not allow traffic over freshly grouted joints for at least 7 days, unless recommended otherwise by the manufacturer.
label | 4f766536-cc27-5464-897a-4ce7eb96da70 |  | note | ○ Install movement joints at locations where:
label | 6a5e014e-0288-5341-b365-0bb917b4f7c4 |  | note | – tiles abut restraining surfaces;
label | 903c5ee5-6974-5a3b-a8da-9a686b5b0a5d |  | note | – joints exist in the concrete below the tiles;
label | ee44e0ed-fbf2-59bf-bc8c-3aa6f28e19a1 |  | note | – a change of plane exists in the tiled surface
label | 6a6228fc-1d5e-5dc0-86b3-67fc1d84de89 |  | note | ○ Install the tactile indicator tiles such that the base surface is sitting flush with adjacent concrete surfaces.
label | 41e966db-c677-5530-8b72-d8aaa6e5ad8a |  | note | ○ The finished surface level of the tiled surface must comply with the requirements of R54 Cl. 5.3 pits. Remove any excess grout or grout film.
label | dc445d20-6e4e-55f1-8791-b088a959321a |  | note | Record for conformity - Verification Checklist
label | 38823edc-5458-5298-a91d-56b0947b1769 |  | note | Responsible Position - Project engineer
label | 66b7cec4-ff4b-526a-9061-43c923af0512 |  | note | Type of Record - IP
checklist-sectioned |  |  | checklist | ITP - R33 - Trench Drains | itp |  |  |  | Yes | ITP - R33 - Trench Drains | bf4f12a3-a51d-4304-9c67-cc8020979c78
checkpoint-group |  |  | section | Trench Drains
checkpoint-status |  |  | checkpoint | 1. Submit material compliance/test certificates for approval.
label | 2a0bc3b2-e68c-5451-ae03-3c6c414761db |  | note | ○ Corrugated plastic slotted pipe
label | 6fe37613-32e7-534f-869e-2b91636eabdd |  | note | ○ Seamless tubular filter fabric
label | e5a16cad-6626-5d91-887d-4cab04ee1765 |  | note | ○ Geotextile
label | e6558c78-f440-5a8c-93d8-11074cfcd040 |  | note | ○ Filter Material – Aggregate
label | 16d3c817-3625-5ca0-9bc2-9f0c3d3ef0fa |  | note | Reference documents - R33.2.1, R33.2.2, R33.2.3, R33.2.4
label | eb82c655-e96c-5bd1-8f3e-0834990d7ad6 |  | note | Criteria/Test Method/Spec - RMS 3552, RMS 3553, RMS R63, RMS 3580 MD.R33.A06
label | e25279b5-270a-515f-a95c-342b6278ca99 |  | note | ○ Release of Hold Point
label | 48a2c0ee-1e57-568b-9d47-f7b9144e95b6 |  | note | Inspection/Test Frequency - In accordance with Annexure R33/L
label | e4900202-8336-51c2-b278-a985478fdaee |  | note | Inspection/Test by - PV
label | 08f83013-ddf7-519e-a606-1fa580bfb48c |  | note | Responsible Position - PV/PE, PV
label | f15dc0dd-a64c-56e3-80f9-c347f2c24d69 |  | note | Type of Record - HPR Form
text | d8787b35-3e6b-5a0f-b83a-38ad4fc02f6a |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 2. Excavate trench to line, grade, width & depth shown on drawings.
label | 7c573a78-7615-549f-91a3-5cee73f2865f |  | note | Reference documents - R33.3.2
label | b0e47bb4-e9b7-5a50-8499-92c272da769c |  | note | Criteria/Test Method/Spec - Minimum grade 0.5%
label | 3bc58681-2286-58b6-82c5-52eb121c7bf3 |  | note | Inspection/Test Frequency - After excavation
label | ad01ba4c-0f6c-527c-9f20-67e4434c9687 |  | note | Inspection/Test by - SS/Surveyor
label | cb6c95df-68b3-5731-8499-92d4104967cc |  | note | Responsible Position - PE/SS
label | 7611ef6f-28e5-5ba3-b3ee-24ccd50402bb |  | note | Type of Record - As-builts
text | 0fd0021f-0d9d-507e-9400-a01225cf3498 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 5. Place geotextile in trench.
label | 5aea2ada-60b1-5a29-ba10-172cea7f3c1a |  | note | Reference documents - R33.3.3
label | 686339da-ec07-5b86-a8d2-fdeee6b7b6a4 |  | note | Criteria/Test Method/Spec - Visual inspection
label | 4ed5c0e6-5dbc-5f9c-8789-25536139f0ab |  | note | Inspection/Test Frequency - After geotextile placement
label | 309ab109-30e6-5aca-8555-87bb08384ade |  | note | Inspection/Test by - SS
label | 574c58f3-0995-5e96-abb7-953ec9984a9c |  | note | Responsible Position - PE/SS
text | 5d3d7e50-1831-5241-929d-a2d2bd37c67a |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 6. Lay pipe on 50mm bed of filter material.
label | 9467a247-3a25-523a-9277-437069abd11b |  | note | Reference documents - R33.3.4
label | ed4ea4e8-67ef-5671-9d82-8de53fd01416 |  | note | Criteria/Test Method/Spec - Visual inspection
label | 6593e4af-1e7f-5b5d-9d89-3848a9985d81 |  | note | Inspection/Test Frequency - After bedding placement
label | 65cc4fc8-9c4d-54ab-b786-4dfca9172618 |  | note | Inspection/Test by - SS/PV
label | c408946e-8399-5938-a2ca-2e284db182ed |  | note | Responsible Position - PE/SS
text | d9c831c9-37f6-5468-8d0b-afb656c79c41 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 7. Verify that pipe laying, jointing & bedding are complete & conforming
label | 7e5d82e2-80f7-5f8e-b2b1-a7acac776a4c |  | note | Reference documents - R33.3.5
label | 0241aca2-2ed0-5c35-80ba-ade268393dfc |  | note | Criteria/Test Method/Spec - R33 Cl 3.5
label | 0bb38d4a-a755-57d4-9266-5d4d92982120 |  | note | ○ Release of Hold Point
label | cbe2d432-662d-58d0-958f-e880e46a87fb |  | note | Inspection/Test Frequency - At completion laying, jointing & bedding
label | 9305eb03-5ab1-5a19-a3ec-e377e84c0f2a |  | note | Inspection/Test by - PV
label | 71ab0359-468e-5116-8fbe-5c39ea467e36 |  | note | Responsible Position - PV/PE
label | e14ece86-dd50-5289-b13b-ed1279c5af2b |  | note | Responsible Position - HPR Form
text | 75dac98c-27c1-5d43-a37d-6c978ebc9fd5 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 8. Backfill pipe with filter material, compact to avoid consolidation & lap geotextile.
label | da376165-44d9-5dcd-80b8-e6de782dbff5 |  | note | Reference documents - R33.3.5
label | d2cf8b9c-d887-5901-a3ca-363c89202eb3 |  | note | Criteria/Test Method/Spec - Visual inspection
label | 748b0467-95c9-5890-a9a6-ba03e05e739e |  | note | Inspection/Test Frequency - After HP release
label | 35289494-1517-502b-8384-e2eb769625b1 |  | note | Inspection/Test by - SS
label | 25585a55-3314-5897-a7a6-29d259cf94a6 |  | note | Responsible Position - PE/SS
text | 256245ee-7817-55e4-88cb-6303b566ff37 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 9. Install flush point covers and outlet in batter, structure including connections to pits.
label | e0c5a942-1ae9-5b0c-aa48-28bbd2c4ab54 |  | note | Reference documents - R33.4.2, R33.4.3, R33.5.2.1, R33.5.2.2
label | 0647252b-38ba-568a-950c-885976ae09ab |  | note | Criteria/Test Method/Spec - Visual inspection
label | 17160939-01b9-5f80-a046-ca5cd7e277fd |  | note | Inspection/Test by - SS
label | 9a087139-bae8-5997-8171-0fda78c26186 |  | note | Responsible Position - PE/SS
text | 937a7d81-e50b-5fb4-bba4-c5c97c4b5fe6 |  | textbox | Initials:
checkpoint-status |  |  | checkpoint | 10. Marking trench drain and submit WAE drawings to Principal <28 days of completion
label | 8ebadb81-869b-5d6f-894c-bfb0bb2c560d |  | note | Reference documents - R33.6
label | 93546324-52b0-5da4-9f50-dc18c975766e |  | note | Criteria/Test Method/Spec - R33 Cl 6
label | 3f14ee72-24a0-5a89-b11d-32fb768875a8 |  | note | Inspection/Test Frequency - <28days of completion
label | 324f8f0a-53ae-5dd8-a760-08a4f962cdc5 |  | note | Inspection/Test by - SS
label | f4c216ca-d0d2-5da0-9f74-d5639cab2c15 |  | note | Responsible Position - PE/SS
label | b3803f47-4ff4-540e-91ac-1563f494e43b |  | note | Type of Record - WAE dwgs
text | 80fa8c37-5c97-53ec-b8df-b454510dca0c |  | textbox | Initials:
checklist-sectioned |  |  | checklist | ITP - R101 - Cold Milling of Road Pavement Materials | itp |  |  |  | Yes | ITP - R101 - Cold Milling of Road Pavement Materials | c454a5bb-04b8-4ba2-b1a0-56c37f49b5b5
checkpoint-group |  |  | section | Cold Milling of Road Pavement Materials
checkpoint-status |  |  | checkpoint | 1. Cold milling of work area.
label | d3472b3a-49a0-5588-8b58-6723c0871538 |  | note | Reference documents - R101.3
label | 8f8ef21d-c339-5031-afe2-b3af23363895 |  | note | Criteria/Test Method/Spec - Submission of verification documentation, the marking of milling depths and locations of all Hidden Objects on site, records and calculations of the areas to be measured under Pay Item R101P6
label | 7c2e10a2-35a5-5f58-baf3-706a74041360 |  | note | Record for conformity/Inspected by - The PV will consider the submitted documents prior to authorizing the release of the Hold Point.
label | 2a40eb2b-ecc3-5be7-a770-b7a5ff695530 |  | note | Type of Record - HP
label | df919fa6-0271-599f-ad21-6b8b708e41fe |  | note | Responsible Position - PE/PV
text | a8acb1cb-4b98-599a-ab66-c68cc8d41ff1 |  | textbox | Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 2. Milling to achieve depth of cut and PV inspection
label | 0b01ef2d-1415-58ce-8216-859a4dae4d52 |  | note | Reference documents - R101.4.2
label | b19c1b36-0991-5278-b72c-d160f294c2cf |  | note | Criteria/Test Method/Spec - Depth of cut and other associated terminology is shown in Figure R101.1
label | 12a27d21-a353-58a0-80ed-8711971c35b7 |  | note | ○ Covering of milled work area and the removal of the cold milling machine and cleaning plant from the site (after milling to specified depth of cut).
label | 8731b1b8-fa5c-5a78-bb59-7d83102c0058 |  | note | ○ Written notice to the Principal at least 24 hours in advance of the time when the floor of the milled area will be available for inspection.
label | b03c9868-4a5a-5c9b-af44-73721d5afd44 |  | note | Record for conformity/Inspected by - The PV will inspect the completed work prior to authorising the release of the Hold Point.
label | 99cf7093-2315-54a6-9f53-91896e2863aa |  | note | Type of Record - HP
label | c074330e-5e16-5acb-9e51-28b2552e2134 |  | note | Responsible Position - PE/PV
text | d97b1e6d-c836-5781-8066-e9d05edd7583 |  | textbox | Initials:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 3. Survey check level of cutting
label | 3049713b-b4d5-5e2b-893c-d8f8be9ec78f |  | note | Reference documents - R101.4.1 R101.4.3
label | b3a95d2b-2601-5ec5-a588-84ef2f2f1d3b |  | note | Criteria/Test Method/Spec - Depth of cut and other dimensions must comply with the tolerances specified in Table R101.1. Report levels to the nearest 5 mm
label | abbdc079-68b6-5e29-9741-c2601b053c54 |  | note | Record for conformity/Inspected by - will inspect the completed work and view the Survey Report (if required by Annexure R101/A) prior to authorising the release of the Hold Point.
label | 4e8fd32f-5b2c-50ff-910f-81bfe0b71e6a |  | note | Type of Record - HP
label | 47543f4a-8f48-5168-bb1c-54472ab7230d |  | note | Responsible Position - PE/PV
text | bf73e146-9117-5506-803d-fb4913b5242c |  | textbox | Initials:
date | 5e032300-ebd5-57da-9317-608742c79d42 |  | date | Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | MILLING OF ASPHALT OVER CONCRETE STRUCTURES
checkpoint-status |  |  | checkpoint | 4. Investigation of thickness of asphalt over concrete structure
label | b1ec70fe-ffd8-5f16-81d7-8457fe29e7d8 |  | note | Reference documents - R101.4.6.1
label | 82f29543-2abc-5022-ac09-8035238b9fad |  | note | Criteria/Test Method/Spec - Carry out the investigation as follows:
label | 3f735684-b3f2-5d28-a9da-595612376441 |  | note | (a) Determine the proposed pattern of milling works and mark on the pavement the lines of movement of the depth sensing foot on each side of the milling machine.
label | ad751639-c0de-5afc-8f4f-87ca5f29430a |  | note | (b) Investigate the thickness of asphalt by taking small diameter cores (e.g. 25 mm), at 3 m intervals (over concrete bridge elements) or 20 m intervals (over other concrete structures) along each line of movement of a depth sensing foot, at least 24 hours prior to the commencement of milling.
label | d5d1d99b-3219-5346-a75d-d974238e4f12 |  | note | Record for conformity/Inspected by - Submit the findings of the investigation to the PV at least 24 hours before commencemen t of milling.
label | 8f1a0dfc-19e3-5453-867e-dcc8bfc10bae |  | note | Type of Record - IP
label | c45e5bdd-d5a4-5203-bcbe-23883cfef7ee |  | note | Responsible Position - PE
text | 8a1cc7cf-214a-5246-88c9-609104a451c6 |  | textbox | Initials:
text | 4512f01b-1528-5403-aa0d-c193f6183327 |  | textbox | Date:
holdpoint |  |  | signoff | Sign:
checkpoint-status |  |  | checkpoint | 5. Revised scope of work based on investigation
label | 35473606-2e91-5e7f-ba53-aadf00a00491 |  | note | Reference documents - R101.4.6.2
label | 56cdac9a-0609-57ca-bbc2-42aa057be105 |  | note | Criteria/Test Method/Spec - Milling of asphalt, including trials, over each Concrete Structure or where the planned base of cut is within 40 mm of the top surface of a Concrete Structure and/or waterproof membrane that is to be retained.
label | 7b6584a6-e895-5ae2-83b1-1dcde2f31c54 |  | note | Record for conformity/Inspected by - Notify the PV not less than 24 hours prior to milling of the time and date of commencemen t of milling and the time and date the proposed depths of cut will be marked on the surface.
label | 21a9487d-18ef-5a4d-b91b-ac7778d61145 |  | note | Type of Record - HP
label | b7c3a01a-4e9b-5415-8086-1c13b8593e74 |  | note | Responsible Position - PE/PV
text | 50d7b625-e40d-51f7-9d4f-409b42860595 |  | textbox | Initials:
date | 23a81f21-2dce-5210-8c14-27c7a5574549 |  | date | Date:
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 6. Milling operators
label | 6b9bbd7a-1e2b-5378-951e-8cf4b085dc16 |  | note | Reference documents - R101.4.6.3
label | 7c96fb38-640f-58f2-a429-4116363fdbfb |  | note | Criteria/Test Method/Spec - Milling operators must have adequate training and experience in the operation of the cold milling machine (including automatic sensing equipment). Provide three suitably trained and skilled milling machine operators at the cold milling machine at all times as follows:
label | f1ff0f13-4117-512e-b96e-a4ff5f3f9d32 |  | note | (i) one on the driving platform;
label | 8b3aa704-6d52-5871-87dc-4713889480e0 |  | note | (ii) one on each side of the machine generally in the vicinity of the sensor/cutting mandrel.
label | 40ed96b9-f4fd-585e-8ebf-e4f78206ceec |  | note | Record for conformity/Inspected by - VOC or tickets
label | ed10b641-0202-567c-b5bf-77af8be035ba |  | note | Type of Record - AP
label | 9e693743-8757-5ec9-925f-f8dcb0e5e7f5 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 7. Equipment requirements
label | 7fd92907-8e40-5979-abe7-50139c65b6a9 |  | note | Reference documents - R101.4.6.4
label | f820dcb5-4449-5c82-a9f7-096070cb2145 |  | note | Criteria/Test Method/Spec - Equipment should Comply with the following:
label | b7ab1259-92d2-5a79-8df7-fae5bb9ac209 |  | note | (a) Maintain the milling machine in “as new” condition and, unless approved otherwise by the Principal, fit the milling machine with a “fine” cutting drum which provides for tooth cut spacing not exceeding 10 mm;
label | 728be481-dba6-5aed-ae8b-df7c5b67c8da |  | note | (b) Conduct a cutting trial using the same machine at the commencement of each working shift and after any repair or adjustment to the machine during the works. The trial must include the operation of depth sensing feet and depth adjustment equipment;
label | e8201a1d-bb74-51df-808c-c64c6f209f72 |  | note | (c) Equip each operator with a gauge to measure the depth of cut in millimetres.
label | 4016bb34-5ef3-509f-b3d9-570d155c7023 |  | note | Record for conformity/Inspected by - Visual check
label | 51642124-829b-5642-8c55-0826aa66ec15 |  | note | Type of Record - IP
label | 1879f4f8-c11a-51af-bc8e-b9ad5825a656 |  | note | Responsible Position - PE/Forman
checkpoint-status |  |  | checkpoint | 8. Milling procedure
label | d6f16c86-e053-584f-a990-0944bdd2d436 |  | note | Reference documents - R101.4.6.5
label | 42cd082c-07fe-5db8-bc75-832cc9474066 |  | note | Criteria/Test Method/Spec - Written notice to the PV together with proposed procedures for the work at least 7 days (except for Clauses 4.6.1 and 4.6.2 where it is 24 hours) prior to the commencement of milling work.
label | f5b2cebe-b0cc-5246-95b1-09ea8656957e |  | note | Record for conformity/Inspected by - The PV will assess the submission, and may require submission of further details on the effects of milling on the bridge structure, prior to authorising the release of the Hold Point.
label | 3106ef0e-fcd4-53d3-b9bf-510294afe47a |  | note | Type of Record - HP
label | 58786de0-89d9-563b-ad68-6d27463fd06e |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 9. Non-conformity due to contact between the cutting teeth of machine and concrete structure
label | 13013cfc-4883-5304-8b26-f544bf73a5c6 |  | note | Reference documents - R101.4.6.6
label | 5287e550-a2aa-59b1-983d-c470fd7ee6c6 |  | note | Criteria/Test Method/Spec - After the cutting teeth have contacted the concrete, notify the PV immediately of the incident and submit details of the cause and the proposed course of action.
label | 0fb8542e-0411-5855-ab0d-2f5cf03dd528 |  | note | Record for conformity/Inspected by - The PV will assess the submission prior to authorising the release of the Hold Point
label | 06ddb558-9941-5856-9d55-a91233c5646f |  | note | Type of Record - HP
label | 630fb124-5c32-596d-89e3-7921bfe5d50a |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 10. Further Milling of Pavement
label | 05ecf091-cf64-5650-95c2-26a3abc356af |  | note | Reference documents - R101.4.6.6.
label | 685b74b8-8cc8-5654-8377-e2f45d16acf8 |  | note | Criteria/Test Method/Spec - After any change to the pattern of the cut surface due to broken or worn cutting teeth, notify the Principal immediately of the incident and submit details of the cause and the proposed course of action.
label | 09c3203f-b055-54b9-a131-35c97bd84ded |  | note | Record for conformity/Inspected by - The PV will assess the submission prior to authorising the release of the Hold Point
label | 3f71e07d-2b1a-5316-a6e7-529e7767042d |  | note | Type of Record - HP
label | 581f5df5-63ae-556f-a622-975fb1783c3c |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 11. Unsuitable materials
label | ec0e82e3-8ec2-5dd1-85c0-549dcb7c4313 |  | note | Reference documents - R101.4.8
label | 29ab6176-4ecf-52c4-a94c-e33e0de1ca40 |  | note | Criteria/Test Method/Spec - Written notice to the PV of the time that the removal of the unsuitable material will be completed and be available for inspection.
label | 560b9c0b-c8ad-503f-bcd1-3750d2fa6be5 |  | note | Record for conformity/Inspected by - PV will inspect and consider the depth of excavation of unsuitable material, to determine whether a sufficient depth of unsuitable material has been removed, prior to authorising the release of the Hold Point.
label | d3ce8426-1421-54f7-9471-d7a57cc31195 |  | note | Type of Record - HP
label | a3c0b27f-1f15-5c95-96d6-a2c2c875929e |  | note | Responsible Position - PE/PV
holdpoint |  |  | signoff | HOLD POINT
checkpoint-group |  |  | section | TEMPORARY TREATMENT AT EDGES OF MILLING
checkpoint-status |  |  | checkpoint | 12. Transverse Joints
label | dc3a7702-1af2-5b0e-9da3-a12359c09ddb |  | note | Reference documents - R101.4.9.i
label | 6469d93e-d024-55ee-871b-ccd9cd844bbf |  | note | Criteria/Test Method/Spec - A minimum taper length of 2.5 m for each 50 mm variation in levels or part thereof for areas where the speed limit exceeds 60 km/h and a minimum taper length of 1.5 m for each 50 mm variation in levels or part thereof for areas where the speed limit is less than or equal to 60 km/h
label | 70d7e4f8-e631-52d9-acdc-d6437195501c |  | note | Record for conformity/Inspected by - Visual inspection
label | 8686cfc6-898d-542b-9695-3523960bf9de |  | note | Type of Record - IP
label | 04d45059-a4f4-5987-ba77-31812a377e0a |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 13. Longitudinal Joints
label | a4e2fddd-5824-5a8c-9581-13ac8f89cdad |  | note | Reference documents - R101.4.9.ii
label | 4cfac0b0-62a7-5a8e-b8f4-77117c085d6c |  | note | Criteria/Test Method/Spec - Where traffic is required to travel on a longitudinal edge, provide a ramp of minimum 1.0 m length for each 50 mm variation in levels (or part thereof)
label | 1f3d9d78-bda4-582f-9af5-c7f8cf7790fa |  | note | Record for conformity/Inspected by - Visual inspection
label | d7f234d4-ca91-56b5-80df-65bdb68b2121 |  | note | Type of Record - IP
label | 435c81ac-0542-5a97-9bb1-e5754e6d5e40 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 14. Interface with Structures
label | e6a9f2fb-86ca-516e-af1a-5b9420d7bbed |  | note | Reference documents - R101.4.9.iii
label | c65203e1-de27-57d4-9e38-2b395221aa50 |  | note | Criteria/Test Method/Spec - Form and compact asphalt ramps around manholes, gully grates, utility covers or other similar structures unless otherwise directed by the PV. The ramps must have a minimum taper length of 1.5 m for each 50 mm depth of cut (or part thereof).
label | 1159f03c-461e-5885-b8e3-0c6a87742425 |  | note | Record for conformity/Inspected by - Visual inspection
label | a61ca4b6-2bdc-5cdd-9386-1bb2e5850fdf |  | note | Type of Record - IP
label | 55d478eb-b730-5098-918f-440ce7b109c1 |  | note | Responsible Position - PE
checkpoint-status |  |  | checkpoint | 15. Clean up and dispose foreign items
label | 2571fff0-a38d-57c9-aa8b-e811c43e8af4 |  | note | Reference documents - R101.4.10
label | 56333bed-36e1-5b1d-8465-de277285fe36 |  | note | Criteria/Test Method/Spec - After the completion of cold milling, remove all loose milled material. The material removed will become your property unless otherwise specified in Annexure R101/A.
label | a54481b0-185b-533a-9117-1f26496542ca |  | note | ○ If the milled material remains the property of the Principal, deliver the milled material to the stockpile site(s) nominated in Annexure R101/A. Shape the milled material in uniform stockpiles with regular sides and, where appropriate, slope the top to promote water runoff. Clearly identify the milled material by signposting.
label | 53340eae-7a96-5fcf-b043-a825623b54b6 |  | note | ○ If the milled material becomes your property, remove it from the site in accordance with the Waste Management Plan
label | 5ecdb8ee-6f47-50a7-8373-797ec73d77d8 |  | note | Record for conformity/Inspected by - Visual inspection
label | d58f9518-a501-5830-bca3-d7add95a0dbe |  | note | Type of Record - IP
label | be443b97-28f2-59c3-8a75-9d55daa3fb8a |  | note | Responsible Position - PE