## Table 1
ITP No: | R106 (Ed 4 / Rev 2) |  | Process: |  |  | Sprayed Bituminous Surfacing |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Process Step |  |  |  | Criteria/Test Method/Spec |  |  | Inspection/Test Frequency |  |  | Inspection/ Test by: | Responsible Position |  | Type of Record |  | Acceptance/Comments Completed Not completed
1. Prepare Safe Work Method Statement. |  |  |  | WHS Act 2011 WHS Regs 2017 |  |  | Prior to commencing |  |  | PV | Site Supervisor (SS) |  | SWMS HPR Form |  | Initials:  Initials: 
2. Submit nominated design including supplier certificates for bituminous surfacing |  |  |  | Table R106.1 RMS Form 395A & 395K R106.3.3.3 Release of Hold Point |  |  | Annexure R106/L |  |  | PV | PE/PV |  | Supplier comp certificate Form 395A Form 395K HPR Form |  | Initials: 
3. Submit Aggregate lot details and reviewed target application rates |  |  |  | RMS 395K form. R106.3.4 Release of Hold Point |  |  | Each lot |  |  | PV | PE/PV |  | ALD test rep Form 395K HPR Form |  | Initials: 
4. Prepare pavement surface by sweeping and removal of any foreign material. Surface slightly damp for spraying of primer |  |  |  | Visual Inspection |  |  | Each lot |  |  | SS | SS / PE |  |  |  | Initials: 
5. Commencement conditions - Measure pavement temperature - Don’t commence if wet pavement or when rain appears imminent/ during strong winds/dust storms. - Sprayer has current RMS Form 354 |  |  |  | Pavement temp >10°C |  |  | Each lot |  |  | SS | SS / PE |  | Form 354 |  | Initials: 
6. Apply Primer: Spray commences & ends on paper Actual application rate determined after each run using dipstick Binder temp at application recorded Overlap btwn adj long’l runs 50mm |  |  |  | Note: Target hot application rate = 0.91/m2 Temperature: 10-30°C |  |  | Each lot |  |  | SS | SS / PE |  | Form 500A |  | Initials: 
ITP No: | R106 (Ed 4 / Rev 2) |  | Process: |  |  | Sprayed Bituminous Surfacing |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
7. Primer cured for at least 48hrs prior to application of seal | [6 empty] | Each lot |  |  | SS | SS/PE |  |  |  | Initials: 
8. Apply Seal Binder: Spray commences & ends on paper Cutter oil added per RMS form 382 Actual application rate determined after each run using dipstick Binder temp at application recorded Overlap btwn adj long’l runs 50mm |  |  |  | Note: Target 1st layer hot application rate = 1.55/m2 Target 1st layer hot application rate = 1.09/m2 Temperature: 160-190°C | [5 empty] | Spray Seal Subcontractor | SS / PE |  | Form 500C |  | Initials: 
9. Application of Aggregate: Aggregate precoated Actual aggregate spread rate measured at Roadworx (per RFI 76) Application complete <15min spray Rolling: 1 (per RFI 76) dual axle pneumatic multi-tyre rollers, >7t, tyre pressure >550KPa, ≥8 passes in <1hr |  |  |  | Note: Target agg appl’n rate 1st layer = 98m2/m3 Note: Target agg appl’n rate 2nd layer = 171m2/m3 | [5 empty] | Spray Seal Subcontractor | SS / PE |  | Form 500C Aggregate Spread rate record |  | Initials: 
REVIEW BY PROJECT MANAGER
Is all testing as per specified frequency? |  |  |  |  | YES/NO
Have all RMS Hold Points been released? |  |  |  |  | YES/NO
Any nonconformances? |  |  |  |  | YES/NO No’s: Closed Out: YES/NO
All work has been satisfactorily completed. |  |  |  |  | YES/NO
ITP No: | R106 (Ed 4 / Rev 2) |  | Process: |  |  | Sprayed Bituminous Surfacing |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Project Manager Date
Prepared By: |  | M Winchester |  |  | Approved By: |  | Date Approved