## Table 1
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
Process Step |  |  |  | Reference documents |  |  | Criteria/Test Method/Spec |  |  |  | Record for conformity/ Inspected by | Type of Record |  | Responsible Position |  | Acceptance/Comments Completed Not completed
Manufacture drainage products
1. Precast concrete drainage pipes |  |  |  | R11.2.1 R11.2.6 |  |  |  The manufacturer must implement and maintain a Quality Management System in accordance with AS/NZS ISO 9001 as a means of ensuring that the manufactured precast concrete pipes conform to the requirements of the Specification.  Precast reinforced concrete pipes must comply with AS 4058 and the requirements in R11.2.1 (I to 11) |  |  |  | Submit Certificate of conformity at least 7-day prior works commencement to PV | HP |  | Project Engineer (PE)/PV
2. Design of “Other Drainage Products |  |  |  | R11.2.4.1 R11.4.7 |  |  |  The design must be in accordance with the Standards shown in Table R11.1 for the structure or component  Design and development must also comply with TfNSW Q.  Supply of precast concrete members subject to traffic and/or earth pressure loading, and water retaining structures with capacity greater than 25,000 litres.  For all pits, such as junction box, gully pit, drop structure, etc, which are deeper than 600 mm, install an individual-rung ladder (step irons) in accordance with AS 1657 on one internal wall for the full depth of the structure. |  |  |  | At least 7 days prior to the date of delivery, submit the documents specified in Clause 2.4.1 to the PV. | HP |  | PV/PE
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
3. Precast Concrete Pits, Access Covers and Grates, Ladders, |  |  |  | R11.2.4.3 R11.2.4.4 R11.2.4.5 |  |  |  If precast units are proposed for use to construct drainage pits, the base units (or any other riser units to which incoming drainage pipes will be joined) must be manufactured specifically to suit the design configuration of the particular pit with pre-formed knockouts only in the walls that require them.  Metal access covers, grates and frames must comply with AS 3996.  Ladders, including individual-rung (step-iron) ladders, must comply with AS 1657 |  |  |  | Submit Certificate of conformity at least 7-day prior works commencement to PV |  |  | PV/PE
4. Marking on precast units |  |  |  | R11.2.5 |  |  | Markings on the inside of pipes must, as a minimum, include the following: (a) manufacturer’s name or registered mark. (b) date of manufacture. (c) pipe load class. and may be painted on if located on the obvert of the pipe. Markings for other precast units must include, in addition to items (a) and (b) above, the following: (i) location of manufacture. (ii) maximum mass of unit in kilograms (iii) any other identification necessary to directly relate the unit to tested samples, e.g. batch number; (iv) inspection status |  |  |  | Visual inspection | IP |  | PE
Bedding and support fill materials
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
5. Type BH Select Fill |  |  |  | R11.3.1.1 |  |  |  a particle size distribution, determined by Test Method TfNSW T201, within the limits set out in Table 6 in AS 3725 (or Table 5.1 in AS 1597.2); and  a Plasticity Index, determined by Test Method TfNSW T109, of not more than 6. |  |  |  | Test report (NATA) | AP |  | PE
6. Type SO Select Fill |  |  |  | R11.3.1.2 |  |  |  a maximum particle dimension of 53 mm; and  a Plasticity Index, as determined by Test Method TfNSW T109, of between 2 and 12. |  |  |  | Test report (NATA) | AP |  | PE
7. FILL MATERIAL FOR EMBANKMENTS IN OPEN DRAINS |  |  |  | R11.3.3 |  |  |  a particle size distribution, determined by Test Method TfNSW T107, such that between 20% and 60% inclusive by mass of material passes the 425- micron sieve; and  a Plasticity Index, as determined by Test Method TfNSW T109, of between 15 and 30 |  |  |  | Test report (NATA) | AP |  | PE
CONSTRUCTION
8. Setting Out |  |  |  | R11.4.1.1 |  |  | Set out of drainage system. |  |  |  | PV to Visually inspect set out for drainage system and propose changes if necessary | HP |  | PV/PE
9. Excavation of Open Drains |  |  |  | R11.4.2.1 |  |  | Construction of open drains with grade less than 0.5%. |  |  |  | PV to consider the matter and direct contractor further before release HP | HP |  | PV/PE
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
10. EXCAVATION FOR DRAINAGE STRUCTURES |  |  |  | R11.4.3 |  |  | Excavation for pipe installation and other drainage structures (Pits) |  |  |  | Notify PV not later than 24 hours but not earlier than 5 working days, | WP |  | PE
11. Inadequate Foundation Material |  |  |  | R11.4.3.3 |  |  |  Replacement of inadequate foundation material  Notification that inadequate foundation material has been excavated to the extent directed. |  |  |  | Notify PV to inspect the excavation and may direct further excavation | HP |  | PE
12. Install Pipe Support Type and concrete pipes |  |  |  | R11.4.4.1 R11.4.4.2 |  |  |  Provide pipe support of Type HS3 complying with AS 3725 and Standard Drawing R0240 - 01.  Handle, store and install the concrete pipes in accordance with the manufacturer’s recommended practice. |  |  |  | Visual inspection | IP |  | PE
13. Anchor Blocks, Sealing of Lifting Holes, Joints, |  |  |  | R11.4.4.3 R11.4.4.4 |  |  |  Provide anchor blocks at a maximum spacing of 3 m and at bends or junctions for all stormwater pipes laid on a grade exceeding 20% and where shown on the Drawings.  Seal all lifting holes in the pipes, and all flush or butt joints used to extend existing pipes, to prevent the ingress of materials. |  |  |  | Visual inspection | IP |  | PE
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
14. Subsurface Drainage Pipe at Discharge End of Pipes |  |  |  | R11.4.4.5 |  |  |  Install a subsurface drainage pipe, complying with Specification TfNSW 3552, at the discharge end of pipes at gully pits, junction boxes and headwalls unless the Drawings specifically direct the subsurface drainage be omitted.  Unless shown otherwise on the Drawings, the subsurface drainage pipe must be a 3 m length of 100 mm diameter subsoil pipe laid beside, and 100 mm above the invert level of the drainage pipe discharging through the wall of the pit or headwall. |  |  |  | Visual inspection | IP |  | PE
CONSTRUCTION OF “OTHER DRAINAGE STRUCTURES” include gully pits, junction boxes, drop structures, inlet and outlet structures, and energy dissipators.
15. Foundations for “Other Drainage Structures |  |  |  | R11.4.7.2 |  |  | For precast pits, install the precast pit on top of a minimum 50 mm thick Class 2 DGB bedding material, complying with Specification TfNSW 3051, or controlled low strength flowable fill material complying with Appendix A in AS 3725, to support the precast pit uniformly |  |  |  | Notify PV for inspection | WP |  | PV/PE
16. Precast Headwalls |  |  |  | R11.4.7.3 |  |  | For precast headwalls for pipes of 300 mm to 1200 mm diameter, provide a curtain wall at the outer edge of the apron in accordance with the TfNSW (RMS) Standard Drawings. Do not use precast headwalls for pipes greater than 1200 mm diameter unless approved otherwise by the Principal |  |  |  | Visual inspection | IP |  | PE
BACKFILLING, COMPACTION AND DISPOSAL OF SURPLUS EXCAVATED MATERIAL
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
17. Backfilling |  |  |  | R11.4.9.1 |  |  |  Backfill the Side and Overlay zones of box culverts with Type SO Select Fill. Refer to Figure 1.1 of AS 1597.2 for schematic details of these zones.  For pipes and box culverts located within a rock fill embankment, provide a minimum thickness of 1000 mm of Type SO Select Fill within the Side and Overlay zones, separated from the surrounding rock fill by a geotextile complying with Specification TfNSW R63.  Unless otherwise specified or directed by the Principal, place fill material for the foundations, bedding, support and general backfill in layers not exceeding 150 mm compacted thickness. Compact the fill material to the requirements of Clause 4.9.2 of this Specification.  Do not carry out backfilling against cast-in-place box culverts until the compressive strength of the concrete has reached at least 75% of the specified 28 day strength, and against other concrete drainage structures until at least 7 days has elapsed after placing the last concrete in the structure, unless authorised otherwise by the Principal.  When backfilling against box culverts, the difference in level of the backfill on opposing sides of the culvert must not exceed 500 mm |  |  |  | Visual inspection | IP |  | PE
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
18. Compaction |  |  |  | R11.4.9.2 |  |  |  Compact the foundations and fill material placed to achieve the minimum characteristic value of relative compaction for the particular type of material, as shown in Table R11.2.  Select Fill in the Side and Overlay zones of box culverts (compaction 98%)  Backfill material within the Selected Material Zone of the adjoining earthworks (refer Specification TfNSW R44) (102%)  All other embankment (compaction is 95%) |  |  |  | NATA report | AP |  | PE
19. Construction traffic |  |  |  | R11.4.10 |  |  |  Moving heavy construction plant or vehicles over pipe or box culvert structures.  Where you propose to move heavy construction plant and vehicles over pipe or box culvert structures, design and provide protective measures for each crossing in accordance with Specification TfNSW G2. |  |  |  | Notify PV | HP |  | PV/PE
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
20. Survey check and tolerances |  |  |  | R11.5.1 |  |  |  Concrete pipes, box culverts, headwalls and wingwalls, energy dissipators, inlet and outlet structures (location within 200 mm of the plan position shown on the Drawings) (invert level within 20 mm of the design level at any point)  Gully pits and junction boxes (location Within 200 mm longitudinally and 20 mm laterally of the plan position, with reference to the control line for the road shown on the Drawings) (invert level Within 20 mm of the invert level shown on the Drawings)  Precast concrete box culvert units (On the internal faces of the walls and roof, no step between adjacent units must exceed 20 mm. Steps between 10 mm and 20 mm must be smoothed to a standard of durability equal to the rest of the culvert)  Open drains (location as per R44) (level Within 50 mm of the design level at any point provided that there is a continuous downgrade in the direction of flow not less than 0.5% at any point) (Waterway area Not less than 95% of the design cross sectional area at any point)
ITP No: | R11 (Ed 5, Rev 8) |  | Process: |  |  | Stormwater drainage |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  |  | Job No: |  | Work Area / Lot No
21. Inspection and CCTV test |  |  |  | R11.5.2 |  |  |  Carry out closed-circuit television (CCTV) inspections of all pipe and box culverts with dimensions that restrict human access, to verify that the works have been constructed within the specified tolerances  for visible signs of defects, at the following times:(a) on completion of the subject drainage structure and prior to commencement of the overlying pavement, and (b) no more than 14 days prior to Completion |  |  | Submit report results to PV |  | AP |  | PE
REVIEW BY PROJECT MANAGER
Have tests passed? | [9 empty] | YES/NO Test Report No:
Is all testing as per specified frequency? | [9 empty] | YES/NO
Are earthworks within location and level tolerances? | [9 empty] | YES/NO
Have all RMS Hold Points been released? | [9 empty] | YES/NO
Any nonconformances? | [9 empty] | YES/NO Sign: For Closed Out: YES/NO
All work has been satisfactorily completed. | [9 empty] | YES/NO
Project Manager Date
Prepared By: |  | Mohammed Almalome |  |  | Approved By: |  |  |  |  | Date Approved
HP: Hold Point AP: Approval Point IP: Inspection point TP: Test Point