## Table 1
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Process Step |  |  |  | Criteria/Test Method/Spec |  | Reference document |  |  | Record of conformity | Type of Record |  | Responsible Position |  | Acceptance/Comments Completed Not completed
1. Confirm safety barrier type & end treatment [ ] W-Beam [ ] Thrie Beam [ ] Thrie Beam Transition [ ] End Terminal Barrier Label:…………… |  |  |  | Check design drawing, correct type of barrier, transitions and/or end connection and any additional material component requirements |  | RF series Design dwgs, R132.2.1 |  |  | Verification Checklist | IP |  | Project engineer
2. Obtain and submit Certificate of |  |  |  |  Obtain Certificate of |  | R132.2.3 & |  |  | Certificate / | IP |  | Project
Compliance for the barrier |  |  |  | Conformance from |  | R132.4.1 |  |  | Verification |  |  | engineer
systems |  |  |  | supplier to R132 |  |  |  |  | Checklist
Specification and submit
to PV Representative at
least 7 days prior to
proposed use of
materials.
 For galvanised steel
components, include a
manufacturer’s
certificate of compliance
certifying the zinc
coating mass is in
accordance with
AS/NZS 4680
requirements, or, for
components of
proprietary safety barrier
systems or devices, the
manufacturer’s
recommendations and
any specified TfNSW
requirements
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
3. Verify conformance of proposed safety barrier materials |  |  |  | Verify safety barrier system components are in accordance with R132, design drawings and manufacturer’s recommendations:  Steel components  Bolts, Nuts & Washers  Protective treatment  Curving steel rails  Plastic members as per manufactures details  Powder coating complies with AS 4506 |  | R132.2.4, R132.2.6, R132.2.7, R132.2.9, TfNSW Requirements & Design dwgs |  |  | Verification Checklist | IP |  | Project engineer
4. Verify conformance of delineators & Retro-reflectors materials |  |  |  |  Delineation unit in accordance with TfNSW STD dwg R0710-18 details  Retroreflective materials must comply with AS 1906.1 or AS 1906.2 as appropriate |  | R132.2.8, R132.4.6 & TfNSW dwg R0710- 18 |  |  | Certificate of Compliance | AP |  | Project engineer
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
5. Inspect guard rail safety barrier items upon delivery |  |  |  | Inspect supplied safety barrier system components are in accordance with R132, design drawings and manufacturer’s recommendations and they are not damaged or defective.  Components shall be marked in text ≤ 20mm high, the following Information: - Manufacture’s name - Batch number, or date of manufacture - Strength grade and base metal thickness of the steel rails  Verify galvanizing is undamaged on curved components. |  | R132.4.1.1 & R132.2.2 |  |  | Receival Inspection Checklist | IP |  | Project engineer
6. Verify underground & overhead services have been identified |  |  |  | Utilise current Ground Penetration Permit or if new permit is required verify:  Dial Before You Dig contacted  As-built for new services available to add to permit  Working near Overhead Services Permit is obtained |  | WHSMP |  |  | Ground Penetration & Overhead Services Permits | IP |  | Project engineer and site foreman
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
7. Set out |  |  |  | Verify pegs are in the ground (or paint marks on hard ground) that mark the start and finish points and line of the safety barrier, transition and end treatments inc the line of flare if applicable, prior to commencing construction. Measure offsets for flares from a line parallel to the adjacent lane line. |  | RF Design dwgs, R132.4.1 & G71 |  |  | Verification Checklist | IP |  | Surveyor
8. Notify PV Representative to inspect set out of safety barrier |  |  |  | Notification that the set out is in accordance with R132 Specification, the Design drawings and manufacturer’s recommendations, ≥ 2 full working days before the proposed commencement of installation of posts. |  | R132.4.1.2 |  |  | Hold Point | HP |  | PV/Project engineer
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Constructing a safety barrier on a road open to traffic |  |  |  | Commence work at the end closest to approaching traffic, except where the barrier connects at its departure end to a fixed object such as the end of a bridge.  Commission end treatments and transitions at the earliest practicable time. Provide temporary end treatments until the permanent treatment is complete. |  | R132.4.1.3 |  |  | Verification Checklist | IP |  | Project engineer
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Installation of guard rail posts by post driving |  |  |  | Installation of the posts must comply with the following requirements:  Posts must be installed to the depth, line and spacing shown on the Design drawings, and to the tolerances in R132.4.5;  Installation process must not cause any structural damage to the post, including any soil plates attached to the post  Installation must not cause any damage to the pavement beyond 100 mm from any part of any post, including any soil plate attached to the post;  When a lateral force of 1 kN is applied in any direction within the top 200 mm of an installed post but before the rail is secured, the movement of the post at ground level must be not more than 3 mm;  Backfill material around the steel tubes and soil plates of gating leading end treatments, |  | R132.4.2 R132.4.5 & Manufactures Docs |  |  | Verification Checklist | IP |  | Foreman
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
must be compacted to a minimum 95% Relative Compaction, measured in accordance with Test Method TfNSW T166;  Disturbed pavement or ground around a post must be trimmed and compacted to a dense, tight, smooth and sealed condition so that resistance to water penetration is similar to that of the adjacent surface.
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Excavating holes for post installation where post driving is unsuited |  |  |  |  Where post is to be installed through a bound pavement layer carry out excavation or pre-boring to achieve a min. hole dia. of 400 mm. Extend hole dia at least within 300 mm of the level of the bottom of the installed post.  Locate each hole so the post will be positioned centrally or towards the nearest traffic lane in the prebored hole.  Backfill around posts must be clean, well graded, non- cementitious granular material or material obtained from excavating the post holes, provided any different material types from within a hole are placed to match surrounding layers. |  | R132.4.2.1 |  |  | Verification Checklist | IP |  | Foreman
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Post construction tolerances |  |  |  |  Posts installed at correct direction, visually smooth and regular and within tolerance. - height: +/-20mm, - line: +/-20mm in plan view, - verticality (to the ground at the front): +/- 15mm at the top, or to manufacturer’s recommendations.  Tolerance on post spacing must be +/-25 mm. The deviation of the top of any post from a straight line joining the tops of the posts on either side must not exceed 10 mm, after allowing for horizontal and vertical curves. |  | R132.4.5.1 R132.4.5.2 & Figure R132.1 |  |  | Verification Checklist | IP |  | Project engineer
Installation of rails |  |  |  | Guard rails are installed to the posts as per manufactures manual installation information, with correct direction, overlapping, and height as detailed on the manufactures associated technical drawings |  | Manufactures Docs |  |  | Verification Checklist | IP |  | Project engineer
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Install end treatments |  |  |  | Install as per manufactures manual installation information and associated technical drawings |  | Manufactures Docs |  |  | Verification Checklist | IP |  | Project engineer
Installation of delineators / retro- reflective units |  |  |  |  Safety barrier delineators are to be spaced to comply with AS 1742.2 or at 20m centres, whichever gives the closer spacing  As per TfNSW STD dwg R0710-18 mounting plates shall be attached to the inside of the posts using M6x25 hex bolt with nut and washer, or other approved fastening system.  Arrange delineation units so that drivers approaching from either direction will see only: (a) red retro-reflectors on their left; (b) white retro-reflectors on their right on two-way carriageways; (c) yellow retro- reflectors on their right on one-way carriageways and medians separating traffic in opposing directions |  | R132.4.6 & TfNSW STD dwg R0710 -18 |  |  | Verification Checklist | IP |  | Project engineer
ITP No: | R132 (Ed3 Rev5) |  | Process: |  | Guard Rail Safety Barriers |  | Project: | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Obtain approval for opening of traffic (if applicable) |  |  |  | Submit, at least three clear working days before the proposed exposure of the safety barrier system without fully operational end treatments, full details of your proposals together with a risk assessment of your proposals. |  | R132.1.4 |  |  | Hold point | HP |  | PV/Project engineer
REVIEW BY PROJECT MANAGER
Have tests passed? | [7 empty] | YES/NO Test Report No:
Is all testing as per specified frequency? | [7 empty] | YES/NO
Are earthworks within location and level tolerances? | [7 empty] | YES/NO
Have all RMS Hold Points been released? | [7 empty] | YES/NO
Any nonconformances? | [7 empty] | YES/NO Sign: For Closed Out: YES/NO
All work has been satisfactorily completed. | [7 empty] | YES/NO
Project Manager Date
Prepared By: |  | Mohammed Almalome |  |  | Approved By: |  |  | Date Approved