## Table 1
ITP No: | R143 (Ed 5 / Rev 3) |  | Process: |  |  | Signposting |  | Project: |  | Sydney Rd / Common St RAB, Goulburn |  |  | Job No: |  | Work Area / Lot No
Process Step |  |  |  | Criteria/Test Method/Spec |  |  | Inspection/Test Frequency |  |  |  | Inspection/ Test by: | Responsible Position |  | Type of Record |  | Acceptance/Comments Completed Not completed
1. Prepare Safe Work Method Statement. |  |  |  | WHS Act 2011 WHS Regs 2017 |  |  | Prior to commencing |  |  |  | PV | Site Supervisor (SS) |  | HPR Form |  | Initials: 
2. Approval of signs for use |  |  |  | RMS 3400 Contract Drawings |  |  | Prior to commencing |  |  |  | PV | SS/PE |  | HPR Form |  | Initials: 
3. Set out for new signs. |  |  |  | RMS R143 Clause 3.2 Contract Drawings Release of Hold Point |  |  | Completion of setout |  |  |  | PV | PE/Surveyor |  | HPR Form |  | Initials: 
4. Install Signs as per Contract Drawings |  |  |  | Visual inspection |  |  | Completion of Installation |  |  |  | SS | PE/Surveyor |  | As-built |  | Initials: 
REVIEW BY PROJECT MANAGER
Is installation within tolerances? | [8 empty] | YES/NO
Have all RMS Hold Points been released? | [8 empty] | YES/NO
Any nonconformances? | [8 empty] | YES/NO Sign: For Closed Out: YES/NO
All work has been satisfactorily completed. | [8 empty] | YES/NO
Project Manager Date
Prepared By: |  | M Winchester |  |  | Approved By: |  |  |  | Date Approved
Title: Inspection and Test Plan (ITP) Version 4 Revision 1 Effective Date: 14 October 2022 ¦ Page 1 of 1
Inspection and Test Plan (ITP)
HSEQ Form